## Inactive Projects
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Latest Payment Date | Actual Letting Date | Target Letting Date | Earliest Auth Date | FMIS Balance | PO Unliquidated | Inactive Days | Last Action Date | Fund Sponsor | Open POs | PCO Des Status
1401279 | R-37908 | Crawfordsville | Tippecanoe | Lafayette - West Lafayette |  | Tippecanoe County | N. River Road and CR 500 N approach in Tippecanoe County | 2022-12-23 07:30 | 2021-01-13 | 2021-01-13 | 2017-03-28 | 181935.94 | 90955.23 | 494 | 2023-01-31 14:21 | Local (MPO) | 0020057754 [CN] | Tracking
1600782 | R-40625 | Fort Wayne | Grant | Not Applicable | Gas City (1183) | Gas City | 1st Street from South H Street to South D Street | 2023-02-24 07:11 | 2021-05-05 | 2021-05-05 | 2021-02-04 | 864.94 | 1081.17 | 431 | 2023-04-04 09:29 | Local (Non-MPO) | 0020064460 [CN] | Tracking
2100085 |  | Fort Wayne | Whitley | Not Applicable |  | Whitley County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2022-2025 | 2023-04-14 06:54 |  |  | 2022-04-14 | 55703.35 | 37267.96 | 382 | 2024-01-17 15:52 | Local (Non-MPO) | 0020095360 [PE] | Tracking
1902072 |  | Greenfield | Hamilton | Not Applicable |  | Hamilton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2021-2024 | 2023-07-21 06:54 |  |  | 2021-08-12 | 262885.29 | 262885.29 | 284 | 2023-07-21 06:54 | Local (Non-MPO) | 0020068666 [PE] | Tracking
1602231 | R-41876 | Greenfield | Hamilton | Indianapolis | Fishers (1162) | Fishers | Small Structure on SR 37, 0.19 miles north of 131st Street | 2022-03-04 07:16 | 2020-12-09 | 2020-12-09 | 2020-11-05 | 811.65 | 811.65 | 788 | 2022-03-04 07:16 | Local (MPO) | 0020056169 [CN] | Tracking
1801713 | R-39747 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Fall Creek Trail Ped Bridge over Fall Creek | 2022-10-14 06:54 | 2021-09-15 | 2021-09-15 | 2021-08-12 | 0 | 1610.28 | 564 | 2023-05-10 08:10 | Local (MPO) | 0020074261 [CN] | Tracking
1601828 | R-41876 | Greenfield | Hamilton | Indianapolis | Fishers (1162) | Fishers | New Bridge; 131st Street over SR 37 | 2023-04-14 06:54 | 2020-12-09 | 2020-12-09 | 2020-11-09 | 55627.55 | 26811.55 | 382 | 2024-03-27 16:33 | Local (MPO) | 0020056169 [CN] | Tracking
1902009 | R-41344 | Greenfield | Hamilton | Indianapolis | Noblesville (1377) | Noblesville | Little Chicago Road - crosses over Morse Reservoir (North of Baywood Dr & South |  | 2023-04-19 | 2023-04-19 | 2023-03-24 | 1737872 | 2979630.57 | 403 | 2023-09-19 14:26 | Local (MPO) | 0020107321 [CN] | Tracking
1802925 | R-42075 | Greenfield | Jay | Not Applicable | Dunkirk (1133) | Dunkirk | Multi-use path in the Dunkirk City Park Along Speedcat Alley | 2021-11-26 07:38 | 2023-09-13 | 2023-09-13 | 2020-07-13 | 9386.8 | 320073.94 | 886 | 2023-11-02 14:51 | Local (Non-MPO) | 0020114925 []; 0020117133 [CE] | Tracking
1801423 | R-41318 | Greenfield | Hancock | Indianapolis | Greenfield (1196) | Greenfield | Multi-use Riley Literary Trail in Downtown Greenfield |  | 2024-02-15 | 2024-02-15 | 2023-02-08 | 0 | 3896000 | 447 | 2024-03-20 16:05 | Local (MPO) | 0020125620 [CN] | Tracking
1401701 | R-38073 | Greenfield | Hamilton | Indianapolis |  | Hamilton County | 146th St, 1000' W Hamilton / Boone Co Line to 1000' W of Shelborne Rd | 2021-04-23 07:37 | 2020-02-05 | 2020-02-05 | 2020-01-15 | 0 | 24639.02 | 1103 | 2023-06-16 13:06 | Local (MPO) | 0020036968 [CN] | Tracking
1702769 | R-41309 | Greenfield | Wayne | Not Applicable | Richmond (1431) | Richmond | E. Main from 7th to 10th,Ft. Wayne Ave from 7th to N. E, N. "E" from 7th to 10th | 2023-05-26 07:17 | 2023-11-15 | 2023-11-15 | 2018-11-08 | 124065.97 | 4818895.87 | 340 | 2024-04-25 16:42 | Local (Non-MPO) | 0020121321 [CE]; 0020123771 []; 0020124008 []; 0020127880 [CN] | Tracking
1801362 |  | LaPorte | Various | South Bend (MI) |  | MPO - South Bend / Elkhart | MACOG MPO Unified Work Program CMAQ, STBG & HSIP for FY 2019-2020 | 2022-10-14 06:54 |  |  | 2018-06-28 | 6773.94 | 6773.92 | 564 | 2022-10-14 06:54 | Local (MPO) | 0020022274 [PL] | Tracking
1601146 | R-39624 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | East Chicago (1139) | East Chicago | Marquette Greenway Trail, Indianapolis Blvd (US20) to Kennedy Ave | 2023-04-25 06:54 |  | 2025-07-09 | 2019-01-07 | 0 | 504150 | 371 | 2024-04-08 10:33 | Local (MPO) | 0020126849 [PE] | Tracking
1600930 | B-40408 | LaPorte | Lake | Not Applicable |  | Lake County | Lake County Bridge #65, 125th Avenue over West Creek | 2023-06-23 07:10 | 2020-10-07 | 2020-10-07 | 2017-10-30 | 8922.37 | 54996.01 | 312 | 2023-06-23 07:10 | Local (Non-MPO) | 0020053375 [CN] | Tracking
1702151 | R-40649 | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | Valparaiso (1520) | Valparaiso | US 30 from 600' W of Hayes Leonard Rd to Industrial Drive, Landscaping |  | 2023-12-13 | 2023-12-13 | 2023-02-06 | 0 | 2897397.78 | 449 | 2024-02-15 07:41 | Local (MPO) | 0020120029 [CE]; 0020122796 [CN] | Tracking
1801238 | R-41187 | LaPorte | Marshall | Not Applicable | Culver (1114) | Culver | SR 10 Sidewalks from School St to N. Lakeshore Dr | 2023-07-21 06:54 | 2021-01-13 | 2021-01-13 | 2018-10-11 | 7280.61 | 6098.42 | 284 | 2023-07-21 06:54 | Local (Non-MPO) | 0020058133 [CN] | Tracking
1600822 | R-40734 | LaPorte | Jasper | Not Applicable | De Motte (1124) | De Motte | 2200' from US 231 on E Division St to Orchid St (700 W) | 2023-05-19 07:04 | 2022-04-06 | 2022-04-06 | 2018-03-19 | 96413.02 | 107984.53 | 347 | 2024-04-25 16:41 | Local (Non-MPO) | 0020127879 [] | Tracking
1702823 | R-41170 | LaPorte | Pulaski | Not Applicable | Winamac (1559) | Winamac | Winamac - Downtown Sidewalks and lighting including locations along US 35 | 2023-04-25 06:54 | 2023-11-15 | 2023-11-15 | 2019-10-11 | 14350.52 | 2766408.24 | 371 | 2024-01-26 08:21 | Local (Non-MPO) | 0020116480 [CE]; 0020120823 [] | Tracking
2200120 |  | Seymour | Clark | Not Applicable |  | Louisville and Indiana Railroad Company | 4 Locations on LIRC at 535382C, 535383J, 535384R, 535366T | 2023-02-24 07:11 |  |  | 2022-04-21 | 202161.75 | 202161.75 | 431 | 2023-02-24 07:11 | Local (Non-MPO) | 0020084286 [RR] | Tracking
2100071 | R-43588 | Seymour | Johnson | Indianapolis | Franklin (1173) | Franklin | Various locations throughout City of Franklin |  | 2023-10-12 | 2023-10-12 | 2023-03-08 | 645241.42 | 1151940.65 | 419 | 2023-11-07 07:48 | Local (MPO) | 0020116615 [CN] | Tracking
1400297 | R-37392 | Seymour | Johnson | Indianapolis |  | Franklin | SR 44 from Crowell Street to Eastview Drive | 2023-05-05 07:07 | 2016-07-13 | 2016-07-13 | 2016-06-03 | 0 | 58.35 | 361 | 2024-03-12 12:09 | Local (MPO) | 0020110392 [CN] | Tracking
1701323 | R-40375 | Seymour | Bartholomew | Columbus | Columbus (1101) | Columbus | Talley Road between 25th Street and Rocky Ford Road | 2022-03-28 07:06 |  | 2025-11-13 | 2018-05-07 | 0 | 214740 | 764 | 2024-02-16 11:13 | Local (MPO) | 0020123163 [PE] | Tracking
1701325 | R-40373 | Seymour | Bartholomew | Columbus | Columbus (1101) | Columbus | Lowell Road between I-65 and Indianapolis Road (Phase 2) | 2022-07-01 07:13 | 2023-12-13 | 2023-12-13 | 2018-05-07 | 0 | 3182209 | 669 | 2024-01-26 13:20 | Local (MPO) | 0020119707 [CE]; 0020121035 [CN] | Tracking
1601197 | R-39642 | Seymour | Johnson | Indianapolis |  | Johnson County | Intersection Roundabout at Fairview and Peterman Road | 2023-03-03 07:11 | 2021-07-14 | 2021-07-14 | 2021-05-24 | 37405.5 | 7282.14 | 424 | 2023-12-13 09:21 | Local (MPO) | 0020118956 [CN] | Tracking
2101273 |  | Seymour | Bartholomew | Not Applicable |  | Louisville and Indiana Railroad Company | Install safety upgrades at 4 crossing; LIRC RR Clark County | 2023-02-24 07:11 |  |  | 2022-04-19 | 72435.97 | 72435.97 | 431 | 2023-02-24 07:11 | Local (Non-MPO) | 0020084285 [RR] | Tracking
1702957 | R-40890 | Seymour | Monroe | Bloomington | Bloomington (1038) | Monroe County | Extension of Sunrise Greeting from Vernal Pike to Gates Drive |  | 2024-02-15 | 2024-02-15 | 2023-01-07 | 6560000 | 10366358.68 | 479 | 2024-04-25 16:29 | Local (MPO) | 0020121879 [CE]; 0020125622 [CN] | Tracking
1702961 | R-40885 | Seymour | Morgan | Not Applicable | Martinsville (1301) | Martinsville | South Street from Ohio Street to Home Avenue | 2023-06-09 07:08 | 2022-01-12 | 2022-01-12 | 2019-03-18 | 92801.29 | 25733 | 326 | 2024-04-23 15:56 | Local (Non-MPO) | 0020127691 [CN] | Tracking
1400617 |  | Seymour | Floyd | Louisville (KY)-IN | New Albany (1356) | Indiana Department of Transportation | Corydon Pike (old SR 62) at NS DOT# 724971N south of New Albany (crossing #2) | 2023-02-24 07:11 |  | 2018-05-31 | 2016-04-19 | 138027.21 | 137728.2 | 431 | 2023-02-24 07:11 | Local (MPO) | 0018818543 [RR] | Tracking
1900406 | R-40890 | Seymour | Monroe | Bloomington |  | Monroe County | New road/bridge connection to Vernal Pike | 2023-05-05 07:07 | 2024-02-15 | 2024-02-15 | 2023-01-07 | 2138127.6 | 2529910.37 | 361 | 2024-04-25 16:29 | Local (MPO) | 0020125622 [] | Tracking

## PED's next 9 Months
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Project End Date | Federal | Expenditure | FMIS Balance | PO Unliquidated | Open POs | Fund Sponsor | PCO Des Status Code | PED Expiration Days | PCO Des Status
2001102 |  | Crawfordsville | Vigo | Terre Haute |  | MPO - Terre Haute | Terre Haute MPO UPWP PL FY 2021-2022 | 2024-06-30 | 539371 | 405167.98 | 134203.02 | 134203.02 | 0020065406 [PL] | Local (MPO) | TR | 61 | Tracking
1500261 | PLC-38271 | Crawfordsville | Warren | Not Applicable |  | Warren County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2024-10-31 | 216182.35 | 202720.87 | 13461.48 | 13461.48 | 0020039233 [PE] | Local (Non-MPO) | TR | 184 | Tracking
1900391 |  | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen (1190) | Goshen | Madison St. at NS RR DOT 510039L in Goshen | 2025-01-31 | 425390.4 | 18355.1 | 407035.3 | 452261.45 | 0020084146 [RR] | Local (MPO) | TR | 276 | Tracking
1801265 |  | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen (1190) | Goshen | Beaver Lane at NS RR DOT # 510019A in Goshen | 2024-12-31 | 703863 | 21939.95 | 681923.05 | 757692.28 | 0020084145 [RR] | Local (MPO) | TR | 245 | Tracking
2100291 |  | Fort Wayne | Elkhart | Not Applicable |  | Elkhart County | Countywide Bridge Inspection and Inventory for Program Years 2022 & 2023 | 2024-10-31 | 183845.82 | 174090.45 | 9755.37 | 9755.37 | 0020088085 [PE] | Local (Non-MPO) | TR | 184 | Tracking
1902757 | R-42770 | Fort Wayne | Huntington | Not Applicable |  | Huntington County | CR 300W at Division Road | 2024-09-30 | 176179.5 | 154982.7 | 21196.8 | 21196.8 | 0020050994 [PE] | Local (Non-MPO) | TR | 153 | Tracking
1901937 |  | Greenfield | Randolph | Not Applicable |  | Randolph County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2024-10-31 | 354687.58 | 303520.5 | 51167.08 | 51167.08 | 0020046582 [PE] | Local (Non-MPO) | TR | 184 | Tracking
2100153 |  | LaPorte | Jasper | Not Applicable |  | Jasper County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2022-2025 | 2024-10-31 | 119377.06 | 111731.56 | 7645.5 | 7013.49 | 0020091902 [PE] | Local (Non-MPO) | TR | 184 | Tracking
1902002 | R-42415 | LaPorte | LaPorte | Michigan City | La Porte (1258) | La Porte | Pavement rehabilitation 3R/4R Park Ave from Furnace St to Erie St | 2024-12-31 | 222264 | 129245.56 | 93018.44 | 93018.44 | 0020042153 [PE] | Local (MPO) | TR | 245 | Tracking
0301165 | R-29682 | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Michigan City | Michigan City - Singing Sands Lighthouse Trail Phase 1, Porter Co to MC | 2024-05-31 | 2828742.73 | 2292007.98 | 536734.75 | 196980.29 | 0020085052 [CN] | Local (MPO) | TR | 31 | Tracking
1902029 |  | LaPorte | LaPorte | Not Applicable |  | LaPorte County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2024-12-31 | 207641.73 | 193946.49 | 13695.24 | 13695.24 | 0020091930 [PE] | Local (Non-MPO) | TR | 245 | Tracking
2001100 |  | LaPorte | LaPorte | Chicago - Northwestern Indiana (IL) |  | MPO - Northwest | NIRPC MPO UPWP PL FY 2021-2022 | 2024-06-30 | 3771914 | 3756155.95 | 15758.05 | 15758.05 | 0020044215 [PL]; 0020065111 [PL] | Local (MPO) | TR | 61 | Tracking
1601146 | R-39624 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | East Chicago (1139) | East Chicago | Marquette Greenway Trail, Indianapolis Blvd (US20) to Kennedy Ave | 2024-10-31 | 145474.61 | 145474.61 | 0 | 504150 | 0020126849 [PE] | Local (MPO) | TR | 184 | Tracking
1801911 | B-41850 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Schererville (1457) | Schererville | Kennedy Avenue over Canadian National and Norfolk Southern railways | 2024-12-02 | 1307097.42 | 1188096.54 | 119000.88 | 149963.71 | 0020095406 [PE]; 0020117496 [] | Local (MPO) | TR | 216 | Tracking
2100973 |  | LaPorte | Pulaski | Not Applicable |  | Pulaski County | Countywide Bridge Inspection and Inventory for Cycle Years 2022-2023 | 2024-11-28 | 97594.22 | 74363.42 | 23230.8 | 3671.77 | 0020093691 [PE] | Local (Non-MPO) | TR | 212 | Tracking
1400633 | R-37503 | LaPorte | St. Joseph | South Bend (MI) | Mishawaka (1325) | Mishawaka | Twelfth Street from Downey to Bykrit | 2024-07-11 | 5650003.02 | 5227814.18 | 422188.84 | 272222.63 | 0020000462 [CE] | Local (MPO) | TR | 72 | Tracking
1702832 | R-41176 | LaPorte | St. Joseph | South Bend (MI) |  | St. Joseph County | Pierce Road from US 31 to Miami Hwy | 2024-12-31 | 1264584.8 | 640265.96 | 624318.84 | 435214.04 | 0020018088 [PE] | Local (MPO) | TR | 245 | Tracking
1593056 |  | LaPorte | St. Joseph | Not Applicable |  | St. Joseph County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2024-12-31 | 261240 | 261239.59 | 0.41 | 133232.41 | 0020045720 [PE] | Local (Non-MPO) | TR | 245 | Tracking
2001101 |  | LaPorte | St. Joseph | South Bend (MI) |  | MPO - South Bend / Elkhart | MACOG MPO UPWP PL FY 2021-2022 | 2024-06-30 | 2539660 | 2518076.8 | 21583.2 | 21580.2 | 0020065641 [PL] | Local (MPO) | TR | 61 | Tracking
2100993 |  | LaPorte | Starke | Not Applicable |  | Starke County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2022-2023 | 2024-11-30 | 75022.4 | 71963.99 | 3058.41 | 0.01 | 0020089201 [PE] | Local (Non-MPO) | TR | 214 | Tracking
1801362 |  | LaPorte | Various | South Bend (MI) |  | MPO - South Bend / Elkhart | MACOG MPO Unified Work Program CMAQ, STBG & HSIP for FY 2019-2020 | 2024-06-30 | 2239178 | 2232404.06 | 6773.94 | 6773.92 | 0020022274 [PL] | Local (MPO) | TR | 61 | Tracking
2001566 |  | Multiple Districts | Various | Not Applicable |  | Indiana Department of Transportation | SRTS Statewide campaign - promote pedestrian & bicycle safety | 2024-12-28 | 2787781.68 | 2628256.82 | 159524.86 | 928850.62 | 0020042980 [CN] | Local (Non-MPO) | TR | 242 | Tracking
2100107 |  | Seymour | Bartholomew | Not Applicable |  | Bartholomew County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2022 & 2023 | 2024-07-31 | 237117.93 | 207601.42 | 29516.51 | 29516.51 | 0020084170 [PE] | Local (Non-MPO) | TR | 92 | Tracking
1400617 |  | Seymour | Floyd | Louisville (KY)-IN | New Albany (1356) | Indiana Department of Transportation | Corydon Pike (old SR 62) at NS DOT# 724971N south of New Albany (crossing #2) | 2024-12-31 | 496383 | 358355.79 | 138027.21 | 137728.2 | 0018818543 [RR] | Local (MPO) | TR | 245 | Tracking
2002982 | B-43647 | Seymour | Harrison | Not Applicable | Corydon (1105) | Harrison County | The project is located approximately 0.2 miles south of SR 62 on Corydon New Mid | 2024-12-30 | 145700 | 81519.07 | 64180.93 | 60213.83 | 0020075280 [PE] | Local (Non-MPO) | TR | 244 | Tracking
2002990 | B-43652 | Seymour | Harrison | Not Applicable |  | Harrison County | Bridge 5752 on Old Hwy 337 approximately 0.8 miles south of Lake Rd. | 2024-12-30 | 109952 | 76496.42 | 33455.58 | 33455.58 | 0020075281 [PE] | Local (Non-MPO) | TR | 244 | Tracking
1400619 |  | Seymour | Harrison | Not Applicable |  | Indiana Department of Transportation | Angel Run Road at NS DOT# 724987K near Crandall | 2024-12-28 | 498212.45 | 425334.05 | 72878.4 | 72878.4 | 0020084743 [RR] | Local (Non-MPO) | TR | 242 | Tracking
1400297 | R-37392 | Seymour | Johnson | Indianapolis |  | Franklin | SR 44 from Crowell Street to Eastview Drive | 2022-07-12 | 7168791.24 | 7168791.24 | 0 | 58.35 | 0020110392 [CN] | Local (MPO) | TR | -658 | Tracking
2002977 | R-43661 | Seymour | Washington | Not Applicable | Salem (1452) | Salem | South Main Street from Beck's Mill Road to bridge over West Fork of Blue River, | 2024-12-30 | 388960 | 285600.37 | 103359.63 | 103359.63 | 0020075347 [PE] | Local (Non-MPO) | TR | 244 | Tracking