## 1 Summary
Riverlink Roadside Toll Collection System Replacement
Form G
Table 1. Summary of Costs
Initial Costs | 0
O&M Costs
Year 1 of Operations | 0
Year 2 of Operations | 0
Year 3 of Operations | 0
Year 4 of Operations | 0
Year 5 of Operations | 0
Year 6 of Operations | 0
Subtotal | 0
TOTAL | 0
Salvage Credit* | 0
*The States’ Parties reserve the right to surplus legacy equipment after the award of the Contract. Should the States’ Parties decide to surplus such equipment, RSP2 shall be responsible to package, label, and deliver such equipment within a 60-mile radius of the bridges.

## 2 Initial Costs
Riverlink Roadside Toll Collection System Replacement
Form G
Table 2. Initial Costs
Item # | Description | Lump Sum Price
1.1 | Mobilization |  | OK | Check: Mobilization max of 10% of Total Initial Costs
1.2 | Planning - Part 1
1.3 | Analysis
1.4 | Design - Part 1
1.5 | Planning - Part 2
1.6 | Design - Part 2
1.7 | Project Hardware and Equipment Purchase and Delivery
1.8 | Factory Acceptance Test (FAT)
1.9 | Planning - Part 3
1.10 | Design - Part 3
1.11 | Planning - Part 4
1.12 | Project Hardware and Equipment Installation
1.13 | Revenue Service Readiness
1.14 | Full Revenue Service Achieved
1.15 | Operational Test and Acceptance |  | ERROR | Check: System Acceptance minimum of 10% of Total Initial Costs
1.16 | Decommission, Removal, and Transport of Existing Equipment
| TOTAL | 0
The following table maps the items listed above to the deliverables described in Form K.
Item # | Description | Req #
1.1 | Mobilization
1.2 | Planning - Part 1
1.2.1 | Detailed Baseline Project Schedule | DEL-016
1.2.2 | Project Management & Quality Assurance Plan (PM&QAP) | DEL-017
1.2.3 | Software Development Plan (SDP) | DEL-018
1.2.4 | Installation and Transition Plan | DEL-019
1.2.5 | Master Test Plan (MTP) | DEL-020
1.3 | Analysis
1.3.1 | RTCS Business Rules | DEL-021
1.3.2 | Initial Requirements Traceability Matrix (RTM) | DEL-022
1.3.3 | Radio Frequency Interference Survey | DEL-023
1.4 | Design - Part 1
1.4.1 | Functional Specifications Document (FSD) | DEL-024
1.5 | Planning - Part 2
1.5.1 | Final RTM | DEL-022
1.5.2 | Transportation Management Plan (TMP) | DEL-041
1.5.3 | Maintenance of Traffic (MOT) Plan and Drawings | DEL-025
1.5.4 | Test Cases & Procedures: Factory Acceptance Test (FAT) | DEL-026, TST-003
1.6 | Design - Part 2
1.6.1 | Detailed Design Document (DDD) | DEL-027
1.6.2 | Reports Design Document (RDD) | DEL-028
1.7 | Project Hardware and Equipment Purchase and Delivery
1.8 | Factory Acceptance Test (FAT)
1.8.1 | Test Report: FAT | DEL-029, TST-003
1.9 | Planning - Part 3
1.9.1 | Test Cases & Procedures: Lane Acceptance Test (LAT) | DEL-026, TST-004
1.9.2 | Test Cases & Procedures: System Integration Test (SIT) | DEL-026, TST-005
1.9.3 | Test Cases & Procedures: System Acceptance Test (SAT) | DEL-026, TST-006
1.9.4 | Test Cases & Procedures: Load Test | DEL-026, TST-007
1.9.5 | Test Cases & Procedures: Penetration Test | DEL-026, TST-008
1.9.6 | Test Cases & Procedures: Disaster Recovery Test | DEL-026, TST-009
1.9.7 | Test Cases & Procedures: Operational Test | DEL-026, TST-010
1.9.8 | Disaster Recovery / Business Continuity Plan (DR/BCP) | DEL-030
1.9.9 | Training Plan | DEL-031
1.9.10 | Operations and Maintenance (O&M) Plan | DEL-032
1.10 | Design - Part 3
1.10.1 | Installation Drawings | DEL-033
1.10.2 | Data Dictionary | DEL-034
1.11 | Planning - Part 4
1.11.1 | Performance Monitoring and Audit Plan | DEL-035
1.11.2 | Safety and Security Plan | DEL-036
1.11.3 | Training Manuals | DEL-037
1.11.4 | User Manuals | DEL-038
1.12 | Roadside Onsite Equipment Installation
1.13 | Revenue Service Readiness
1.13.1 | Test Report: LAT (initial lane(s)) | DEL-029, TST-004
1.13.2 | Test Report: SIT | DEL-029, TST-005
1.13.3 | Test Report: SAT | DEL-029, TST-006
1.13.4 | Test Report: Load Test | DEL-029, TST-007
1.13.5 | Test Report: Penetration Test | DEL-029, TST-008
1.13.6 | Test Report: Disaster Recovery Test | DEL-029, TST-009
1.14 | Full Revenue Service Achieved
1.14.1 | Test Reports: LAT (all lanes) | DEL-029, TST-004
1.15 | Operational Test and Acceptance
1.15.1 | Test Report: Operational Test | DEL-029,TST-010
1.15.2 | As-built Drawings and Documents | DEL-039
1.15.3 | 3rd-Party Licenses and Warranties | DEL-040
1.16 | Decommission, Removal, and Transport of Existing Equipment

## 3 O&M Costs
Riverlink Roadside Toll Collection System Replacement
Form G
Table 3. Operations and Maintenance Costs
Annual Cost
Description | Year 1 of Operations | Year 2 of Operations | Year 3 of Operations | Year 4 of Operations | Year 5 of Operations | Year 6 of Operations
2.1 Roadside Operations and Maintenance
Price Per Month
Number of Months | 12 | 12 | 12 | 12 | 12 | 12
Annual Subtotal | 0 | 0 | 0 | 0 | 0 | 0
2.2 Generator Operations and Maintenance
Price Per Month
Number of Months | 12 | 12 | 12 | 12 | 12 | 12
Annual Subtotal | 0 | 0 | 0 | 0 | 0 | 0
2.3 Changeable Message Sign Operations and Maintenance
Price Per Month
Number of Months | 12 | 12 | 12 | 12 | 12 | 12
Annual Subtotal | 0 | 0 | 0 | 0 | 0 | 0
Annual Total | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0

## 4 Labor Rates
Riverlink Roadside Toll Collection System Replacement
Form G
Table 4 - Labor Rates
Hourly Labor Rates (Fully Loaded) by Calendar Year
Position | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Project Director
Project Manager
Maintenance Technician
Systems Engineer
Systems Analyst
Database Analyst
Network Analyst
Network Architect
Installation Manager
Testing Manager
If additional rows are needed, add above this row.

## 5 Salvage Credit
Riverlink Roadside Toll Collection System Replacement
Form G
Table 5. Salvage Credit
Credit*
*The States’ Parties reserve the right to surplus legacy equipment after the award of the Contract. Should the States’ Parties decide to surplus such equipment, RSP2 shall be responsible to package, label, and deliver such equipment within a 60-mile radius of the bridges.