DETERMINATION AND EXTENSION OF CONTRACT

The Standard Specifications are revised as follows:

SECTION 108, BEGIN LINE 312, INSERT AS FOLLOWS:

The number of days for performance permitted in the contract as awarded will be based on the original quantities as defined in 104.02.

(a)	For a completion date contract, unless otherwise determined, an increase in quantities will increase the time permitted for the performance of the contract by the ratio of the final contract price to the original contract price. The final contract price used in the calculation will not include items that do not reflect additional work performed by the Contractor, such as incentives, disincentives, QA adjustments, failed material adjustments, material substitutions, or other similar items. The contract time shall be the number of calendar days starting with the day after the letting, to and including the original contract completion date.

(b)	If intermediate completion times are specified, unless otherwise determined, an increase in quantities will increase the time permitted. This will be computed by the ratio of the original dollar amounts to the final dollar amounts of only those pay items which are involved in the closure or restrictions work. Items that do not reflect additional work performed by the Contractor, such as incentives, disincentives, QA adjustments, failed material adjustments, material substitutions, or other similar items will not be included in the final dollar amounts of the pay items used in the computation. When computing such time, the number of days specified for the intermediate completion time will be used. If a calendar date is specified, the number of calendar days will be computed by starting with the day after the letting, and continuing to and including the intermediate completion date.