# 108-C-091 FAILURE TO COMPLETE ON TIME FOR RESTRICTION

*(Revised 04-25-21)*

The Standard Specifications are revised as follows:

SECTION 108, AFTER LINE 598, INSERT AS FOLLOWS:

*The work specified shall be arranged and prosecuted such that traffic is restricted on* *for not longer than the number of calendar days shown on the Proposal sheet. Traffic shall not be restricted before* *, 20**.*

*If the necessary work is not completed and* *is not reopened to unrestricted traffic within the number of calendar days for restriction shown on the Proposal sheet, $**will be assessed as liquidated damages, not as a penalty, but as damages sustained for each calendar day for which traffic on* *remains restricted in excess of the number shown on the Proposal sheet.*

*Extension of restriction time, if required, shall be in accordance with 108.08.*