## Slide 1: ESSA Update
Patrick McAlister
Director of Policy
pmcalister@doe.in.gov

## Slide 2: Requirements
Community Meetings
Technical Working Groups
Timeline

## Slide 3: Community Meetings
Evenings
  all meetings are held 6:30-8:00pm local time
Interactive
  Discussion groups, not formal presentations
Parent and Educator-focused questions
  How do elements of ESSA impact communities, schools and districts?
Senior DOE Leadership Participation
  Superintendent or Chief of Staff at each meeting

## Slide 4
City | Location | Date | Time
Evansville | Evansville-Vanderburgh Library - North Park Branch 960 Koehler Dr. Evansville, IN 47710 | March 16 | 6:30-8:00pm CT (7:30-9:00pm EST)
West Lafayette | Tippecanoe County Public Library 627 South Street Lafayette, IN 47901 | March 28 | 6:30-8:00pm EST
Merrillville | To be determined | March 29 | 6:30-8:00pm EST
Kokomo | Indiana University Kokomo 2300 S Washington St Kokomo, IN 46902 | April 3 | 6:30-8:00pm EST
Indianapolis | Indianapolis Urban League 777 Indiana Ave Indianapolis, IN 46202 | April 4 | 6:30-8:00pm EST
New Albany | To be determined | April 6 | 6:30-8:00pm EST
Goshen | To be determined | April 11 | 6:30-8:00pm EST
Richmond | To be determined | April 12 | 6:30-8:00pm EST
Fort Wayne | Fort Wayne Urban League 2135 Hanna St, Fort Wayne, IN 46803 | April 20 | 6:30-8:00pm EST
Virtual | Via WebEx | April 24 | 6:30-8:00pm EST

## Slide 5: Technical Working Groups
DOE
Staff
Assessment and Standards
Accountability
School Improvement
Supporting Excellent Educators
Supporting all Students
DOE Cabinet

## Slide 6: Timeline
Phases | Notes | Dates
Internal Planning |  | January-March 1
Stakeholder Engagement | Community Meetings Technical Working Groups | March 1 – April 30
Writing the Plan | Technical Working Groups Internal and External support | May 1 – June 30
First Draft | Present First Draft for Public Comment Formally Present ESSA Plan to State Board on July 12 | July 1 – August 1
Submit Plan to Governor | Must be 30 days before plan is due | August 15
Submit final ESSA plan to USDOE |  | September 18