Monroe County Community Health Improvement Plan

| CHIP Team Priority Area: PNHSS, Transportation Date: March 6, 2023 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Ensure transportation to support Monroe County residents |  |  |  |  |  |  |  |
| Objective 1: Raise $X (450,000) to support Rural Transit annually, beginning in 2024. |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| Research federal funding opportunities Action Items: Identify group that may want to identify Federal funding opportunities - Rural Transit - Bloomington Public Transit - El Shadday and I, Inc. - Be Loved Transportation - City of Bloomington Transportation & Planning - Area 10 Agency on Aging - IU Transportation Demand Planning - United Way - SafeRide - Car Rentals - Taxi service - Township Trustees - VisitBloomington - DAV Van Service - Early Head Start Program - Natonal Runaway Safeline - Wounded Warriors Family Support Caregiver | - Research Candid database |  | - Tandem intern? | Identify staff to support some of tasks |  |  |  |
| Identify unmet needs/gaps between Bloomington Transit and Rural Transit Action Items: Identify group that may want to lead gap analysis of transportation services | - Identify needs of the community through survey and interviews with nonprofit leaders - Obtain list of nonprofits to survey - Compare data between Rural Transit and Bloomington Transit, such as Rural Transit non-medical emergencies data, to identify gaps and unmet needs |  | - Rural Transit - Public Transit |  |  |  |  |
| Advocate for support for local politicians and ARPA funding |  |  |  |  |  |  |  |
| Securing local match funding |  |  |  |  |  |  |  |

| CHIP Team Priority Area: PNHSS, Transportation Date: March 6, 2023 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Ensure transportation to support Monroe County residents |  |  |  |  |  |  |  |
| Objective 2: Develop voluntary rideshare program in Monroe County by X year |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| Research communities that do a good job at voluntary rideshare programs | - Research United Way program and LyftUp and American Cancer Society Road to Recovery program |  |  |  |  |  |  |
| Survey entities to identify who would house this program | - Research insurance policies - How to manage volunteers (ACS) - Utilize Youth Services Bureau data - Bloomington Volunteer Network |  | - Heading Home (tentative) |  |  |  |  |
| Develop app or streamlined mechanisms | - Research Civic Champs - Talk with Bloomington Volunteer Network |  |  |  |  |  |  |
| Support entity running the program | - Identify funding needs to run program |  |  |  |  |  |  |

| CHIP Team Priority Area: PNHSS, Transportation Date: March 6, 2023 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Ensure transportation to support Monroe County residents |  |  |  |  |  |  |  |
| Objective 3: Creating an educational resource with services and hours provided |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| Survey nonprofits and service providers to identify needs to get people to their area | - Creating survey – research other community transportation surveys - Survey/Interview nonprofits and agencies to see unmet needs – car seats, large items, scheduling needs – to identify questions for survey - Helping Bloomington/Monroe (FindHelp.org), United Way, and other organizations can provide contact lists for action team to merge to develop a large survey group - Creating list of individuals that we want to survey (nonprofits and other agencies) - Identify kinds of transportation (buses, personal vehicles, bicycles, scooters, walking, etc.) - Develop survey - Send survey - Overall pronged approach | 3 months to develop survey 6 months to send out and collect responses (and follow ups) 3 months to analyze results 3 months to publish results | - Helping Bloomington/Monroe – provide contact list - United Way – provide contact list - Bloomington Department of Transportation and Planning – provide any previous data that supports this survey - Transportation Action Team – part of the validation process, approve survey and participant list - IU – may be able to provide support for survey itself | - Contact lists from various organizations - Software – SurveyMonkey / Qualtrics - Funding to conduct survey, analysis, and publish results | - Collected statistically sufficient volume of data to develop analysis for guide - Gaps analysis in transportation options | - Number of participants in the survey - Number of websites/locations that survey information is available - Handing off gaps analysis to agencies and organizations that can address gaps |  |
| Develop guide to transportation in Bloomington | - Process survey results - Identify current transportation services and hours - Any limitations of transportation services (who can be carried, what can be carried, purpose of travel) - Identify who services are available to - Identify vouchers and services areas for transportation - Potential for 2 guides, with one more in depth for agencies: guide for consumer, guide for nonprofit (nonprofit may provide more contact insights) - Development of guide itself - Identify locations final results may be distributed | 3 to 6 months to develop internship and job description with partnering transportation organization 4 months for internship to develop guide | - Transportation Team – review survey results to ensure that survey had adequate responses and is appropriate to move forward with to develop guide. Ensure statistically relevant data sets; work with transportation organize to develop project outline and job description - IU – potential for individual (internship), group, or capstone project to analyze data and develop cohesive document *advertising project/internship on Handshake - Transportation organization (Rural Transit/Bloomington Transit as example) – primary contact to interview student and manage workload | Funding for student internship – work with IU to see if there are programs that work with local organizations (Center for Rural Engagement, Environmental Resilience Institute) | - Readily accessible transportation information readily available for organizations and community members (information for guide) |  |  |
| Put guide resource in public areas and website |  |  |  |  |  |  |  |