Monroe County Community Health Improvement Plan

| CHIP Team Priority Area: PNHSS, Transportation Date: June 16, 2023 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Ensure transportation to support Monroe County residents |  |  |  |  |  |  |  |
| Objective 1: Redefine Bloomington Public Transit service boundaries by January 2024. |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| - Reconsider BT service boundaries in light of Ellettsville classification as UZA | - Stakeholder and public engagement - Route optimization study | - June 2023 – January 2024 | - Bloomington Public Transit - Consultant | - Staff time to address | - Enhanced services to region, particularly the new Ellettsville UZA | - Annual resident satisfaction survey |  |
| Objective 2: Identify transportation gaps and supplemental funding to support local transportation needs. |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| - Identify unmet needs/gaps between Bloomington Transit and Rural Transit | - Contact SICIL to see what information they have - Identify needs of the community through survey and interviews with nonprofit leaders - Obtain list of nonprofits to survey - Compare data between Rural Transit and Bloomington Transit, such as Rural Transit non-medical emergencies data, to identify gaps and unmet needs | - June 2023 - June 2024 | - Public Transit - Rural Transit - City Commission on Community Accessibility | - Community collaboration | - Gap analysis | - Completion of gap analysis | Action Items: Identify group that may want to lead gap analysis of transportation services |
| - Advocate for support for local politicians and ARPA funding | - Research eligibility for ARPA funding - Educate local leaders on transportation gaps | - June 2023 – ongoing | - GTSI will research eligibility for ARPA funding as interim support for transportation gaps | - Time to research topic | - Memo on eligibility of ARPA funding | - Delivery of memo |  |
| - Research federal funding opportunities | - Research Candid database | June 2023 – ongoing | - Public Transit - City Council on Community Accessibility - Gnarly Tree Sustainability Institute - Tandem intern? | - Identify staff to support some of tasks | - Collaborative proposals submitted - Funding received | - Proposals submitted - Amount of funding received | Action Items: Identify group that may want to identify Federal funding opportunities - SICIL - City Commission on Community Accessibility - Rural Transit - Bloomington Public Transit - El Shadday and I, Inc. - Be Loved Transportation - City of Bloomington Transportation & Planning - Area 10 Agency on Aging - IU Transportation Demand Planning - United Way - SafeRide - Car Rentals - Taxi service - Township Trustees - VisitBloomington - DAV Van Service - Early Head Start Program - National Runaway Safeline - Wounded Warriors Family Support Caregiver |
| - Secure local match funding | - Speak with foundations that may be interested in supporting unmet transportation needs (e.g., Community Foundation, Bloomington Health Foundation) | - June 2023 – ongoing | - Bloomington Transit - Rural Transit - City Commission on Community Accessibility - Gnarly Tree Sustainability Institute | Identify staff to support some of tasks | - Collaborative proposals submitted - Funding received | - Proposals submitted Amount of funding received |  |

| CHIP Team Priority Area: PNHSS, Transportation Date: June 16, 2023 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Ensure transportation to support Monroe County residents |  |  |  |  |  |  |  |
| Objective 3: Develop voluntary rideshare program in Monroe County by 2025 |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| - Research communities and organizations that do a good job at voluntary rideshare programs | - Research United Way program and LyftUp and American Cancer Society Road to Recovery program | - June 2023 – June 2024 | - City Commission on Community Accessibility - Heading Home - Gnarly Tree Sustainability Institute | - Staff time to perform case studies | - Case studies of other programs and recommendations for Monroe County | - Completion of report |  |
| - Identify program requirements and survey entities to identify who would house this program | - Research insurance policies - How to manage volunteers (ACS) - Utilize Youth Services Bureau data - Bloomington Volunteer Network | - June 2024 – December 2024 | - Heading Home (tentative) - Gnarly Tree Sustainability Institute - Bloomington Public Transit (consultation) | - Staff time to perform research and analysis | - Report on program requirements | - Completion of report |  |
| Develop app or streamlined mechanisms to request rides, potentially using Go Bloomington! | - Research Civic Champs - Talk with Bloomington Volunteer Network - Talk with Dimension Mill - Talk to Ted Boardman about app development | - June 2024 – December 2024 | - Heading Home (tentative) - Bloomington Public Transit (consultation) | - Staff time to perform research and analysis | - Identification or development of app | - Identification or development of app |  |
| Support entity running the program | - Identify needs to run program, including funding and logistics support | - December 2024 - ongoing | - City Commission on Community Accessibility - Bloomington Transit (driving training) | - Funding and staff time to run program | - Establishment of program | - Annual survey - # Rides given |  |

| CHIP Team Priority Area: PNHSS, Transportation Date: June 16, 2023 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Ensure transportation to support Monroe County residents |  |  |  |  |  |  |  |
| Objective 4: Creating an educational resource with services and hours provided |  |  |  |  |  |  |  |
| Strategies (Method/approach used to accomplish the objective) | Tactics/Activities (Specific actions planned) | Timeline (When will the activity begin & end) | Roles/Responsibilities (Who is responsible for the activities) | Resource Needs (What is needed to do the activities) | Outcomes (What are the desired results) | Evaluation Metrics (How will we measure the outcomes) | Status/Notes (What is the project status, other project notes) |
| - Survey nonprofits and service providers to identify needs to get people to their area | - Creating survey – research other community transportation surveys - Survey/Interview nonprofits and agencies to see unmet needs – car seats, large items, scheduling needs – to identify questions for survey - Helping Bloomington/Monroe (FindHelp.org), United Way, and other organizations can provide contact lists for action team to merge to develop a large survey group - Creating list of individuals that we want to survey (nonprofits and other agencies) - Identify kinds of transportation (buses, personal vehicles, bicycles, scooters, walking, etc.) - Develop survey - Send survey - Overall pronged approach | - June 2023 – June 2024 - 3 months to develop survey - 6 months to send out and collect responses (and follow ups) - 3 months to analyze results - 3 months to publish results | - City Commission on Community Accessibility - Helping Bloomington/Monroe – provide contact list - United Way – provide contact list - Bloomington Department of Transportation and Planning – provide any previous data that supports this survey - Transportation Action Team – part of the validation process, approve survey and participant list - IU – may be able to provide support for survey itself | - Contact lists from various organizations - Software – SurveyMonkey / Qualtrics - Funding to conduct survey, analysis, and publish results | - Collected statistically sufficient volume of data to develop analysis for guide - Gap analysis in transportation options | - Number of participants in the survey - Number of websites/locations that survey information is available - Handing off gap analysis to agencies and organizations that can address gaps |  |
| Develop guide to transportation in Bloomington | - Process survey results - Identify current transportation services and hours - Any limitations of transportation services (who can be carried, what can be carried, purpose of travel) - Identify who services are available to - Identify vouchers and services areas for transportation - Potential for 2 guides, with one more in depth for agencies: guide for consumer, guide for nonprofit (nonprofit may provide more contact insights) - Development of guide itself - Identify locations final results may be distributed | January 2024 – August 2024 3 months to develop internship and job description with partnering transportation organization 4 months for internship to develop guide | - Transportation Team – review survey results to ensure that survey had adequate responses and is appropriate to move forward with to develop guide. Ensure statistically relevant data sets; work with transportation organize to develop project outline and job description - IU – potential for individual (internship), group, or capstone project to analyze data and develop cohesive document *advertising project/internship on Handshake - Transportation organization (Rural Transit/Bloomington Transit as example) – primary contact to interview student and manage workload | Funding for student internship – work with IU to see if there are programs that work with local organizations (Center for Rural Engagement, Environmental Resilience Institute) | - Readily accessible transportation information readily available for organizations and community members (information for guide) | - Completion of transportation guides |  |
| Put guide resource in public areas and website | - Post on Websites - Placed printed copies in public locations | - August 2024 – ongoing | - Transportation Team - Bloomington Transit - Rural Transit - Nonprofits | - Funding for printing - Staff time to promote | - Transportation guide available in print and online | - Number of downloads of guide - Number of print guides distributed |  |