## EXAMPLE of Phase 1
Goal: To provide comprehensive services to people living with HIV in Indiana
Objectives: | Service Category and Unit | Quantity |  |  |  | Funds
List quantifiable time-limited (i.e., SMART) objectives related to the service priorities listed above | Define the service unit to be provided | Number of unduplicated clients to be served (or were served) |  | Number of service units to be provided (or were provided) |  | Amount of funds to be used (or were expended) for this service
|  | Target | Actual | Target | Actual | Allocation | Actual
a: 200 clients will receive 800 HIV outpatient medical visits by the end of the grant year. | Outpatient Ambulatory Health Services (OAHS):
| Service Unit = 1 visit | 200 |  | 800 |  | 120000
c: 100 clients will receive 500 medical case management visits by the end of the grant year. | Medical Case Management:
| Service Unit = 1 visit | 100 |  | 500 |  | 135000

## Phase 1 Workplan Sample Templat
Optional Work Plan Template (Phase 1)
Goal:
Objectives | Service Category and Unit | Quanity |  |  |  | Funds
List quantifiable time-limited (i.e. SMART) objectives related to the service priorities listed above | Define the service unit to be provided | Number of unduplicated clients to be served (or were served) |  | Number of Service Units to be provided (or were provided) |  | Amount of funds to be used (or were expanded) for this service
|  | Target | Actual | Target | Actual | Allocation | Actual
a. | Service Category
Service Unit
b. | Service Category
Service Unit
c. | Service Category
Service Unit

## EXAMPLE Phase 2 Workplan
Goal: To ensure persons with HIV released from incarceration receive optimal care and treatment soon after release.
Objective #1: Establish referral and collaborative relationships with Northern Regional Women’s Jail, Alabaster County Jail and the Hilltop Holding Facility during the first quarter of the grant period to provide services to people with HIV anticipating release from incarceration.
Activities to meet objective | Start Date | Completion Date | Key Personnel
a. Establish MOUs with the three facilities, allowing access to meet with or communicate with women with HIV anticipating release within 90 days. | 2019-10-01 | 2020-01-15 | Agency Executive Director
b. Meet with 90% of women with HIV who are to be released within 90 days at least twice before release | 2020-01-15 | 2020-09-15 | Medical Case Manager
c. Schedule an initial outpatient medical visit for 90% of clients engaged prior to release within 10 days of release. | 2020-01-15 | 2020-09-15 | Medical Case Manager

## Phase 2 Workplan Template
Phase 2 Workplan Sample Templace
Goal:
Objective #1:
Activities to meet objective | Start Date | Completion Date | Key Personnel
a.
b.
c.