## Example
LPA BRIDGE INSPECTION CHANGE FORM
REQUIREMENTS
This form is required when there has been a change to the planned number of bridges inspected, and no additional funds are being requested. An amendment to the contract will be required if the total amount increases or if funds are moved up between phases. Submit the change form to the LPA Bridge Inspection Project Manager.
County |  | Test County
Des Number |  | 1234567
Consultant |  | ABC Consultant
Request Submitted |  | 2020-01-20
INDOT Request Approved |  | 2020-02-01
PHASE | INSPECTION TYPE | PLANNED BRIDGES | ACTUAL BRIDGES | CHANGE IN BRIDGES | BRIDGE NUMBERS | UNIT PRICE | CHANGE AMOUNT
Phase I | Routine | 150 | 144 | -6 | 13, 14, 15, 16, 17, 18 | 500 | -3000
Phase I | Special | 3 | 2 | -1 | 59 | 3000 | -3000
Phase IA | Routine | 10 | 12 | 2 | 20, 21 | 1000 | 2000
TOTAL CHANGE = | [6 empty] | -4000
Notes | Test comments.

## Form
REV.3/5/20
LPA BRIDGE INSPECTION CHANGE FORM
REQUIREMENTS
This form is required when there has been a change to the planned number of bridges inspected, and no additional funds are being requested. An amendment to the contract will be required if the total amount increases or if funds are moved up between phases. Submit the change form to the LPA Bridge Inspection Project Manager.
County
Des Number
Consultant
Request Submitted
INDOT Request Approved
PHASE | INSPECTION TYPE | PLANNED BRIDGES | ACTUAL BRIDGES | CHANGE IN BRIDGES | BRIDGE NUMBERS | UNIT PRICE | CHANGE AMOUNT
TOTAL CHANGE = | [6 empty] | 0
Notes