## Slide 1
River Bridges Rehabilitation
Evansville to Henderson
Evansville MPO Presentation
September 2016

## Slide 2: Project Design and Planning
Purpose and Need
  Realization of the overall scope of the projects and impacts to the community
  Decision to coordinate with Kentucky
How to bring the public onboard?
  Public Involvement
    Traffic Patterns
    Restrictions
    Timeframes
    Future information updates
Notes: COST – 25-30 million
Project Need
  Heavy vehicular use resulting in wearing down of bridge decks and roadway pavement
Purpose
  Address the ongoing deterioration of the bridge decks and cracking pavement
  Extend the lifespan of each bridge before major reconstruction is required.

## Slide 3: Project Area
  3.8 total miles in length
    2.5 miles in KY
  7 bridges OHIO RIVER
  $25 Million
KENTUCKY
INDIANA

## Slide 4: Deciding Factors for Construction and MOT
Type of work to be done.
  Deck replacements
  Pavement replacement
Keep two lanes open in each direction.
Lessen impacts to the traveling public.
Increase the service life of the bridges and pavement by 20 – 25 years
Work zone safety

## Slide 5: Extensive Planning
Safe and efficient project
  Coordination with other projects located in the greater Evansville area.
  Kentucky – Ohio River Bridges
  Numerous meetings with local, federal, and state agencies in Indiana and Kentucky
  Emergency services
  Local commerce
  Utilities
Notes: Extensive over the last year
Shared costs all 8 bridges…but not the pavement
News in Aug 2015
Emergency Mgmt Sept 2015
PODI FHWA Spring 2015

## Slide 6: Locations
Eagle Creek Bridges located south of the US 41 and I-69 interchange
  Project starts at the I-69 interchange
  Bridge decks rehabilitated
  Kentucky Avenue closed only while constructing the southbound lanes
Kentucky Ave
Notes: Picture needs to reflect all of Kentucky Ave

## Slide 7: Locations
Ohio River Overflow
  Bridge decks replaced
Notes: Most drivers don’t even realize that there is a bridge here…

## Slide 8: Locations
Cheatam Slough
  Bridge decks replaced
  Temporary bridge for crossover
Turning Restrictions
  No left turns between Waterworks Road and Shawnee Drive, both north and southbound lanes
Notes: Needs to reflect Waterworks Road

## Slide 9: Locations
Kentucky Ohio River Bridges
  Only southbound bridge
  Deck overlay
  Joint repair
  90 to 120 days construction period
Notes: Absorbing KY bridge into IN project

## Slide 10: Phasing and Maintenance of Traffic
Phase 1
  Primary Goals
    Southbound Main Span over the Ohio River 3,000 foot bridge deck overlay with the expectation to be completed before Phase 2
  Secondary Goals
    Minor utility relocation starting 2016
    Shoulder widening and crossovers
    Temporary bridge at Cheatam Slough
Notes: Utilities
Intention to keep weigh station open during construction

## Slide 11: Phase 1 - Kentucky Ohio River Bridge
  Reconstruct SB structure
    With 1 lane open
    Truck traffic directed onto the open southbound lane
  MOT on NB structure 35 MPH
    1 lane SB
    2 lanes NB

## Slide 12: Phase 1 Multiple Activities
Shoulder widening
  Entire length of the project in order to accommodate 4 lanes during Phase 2 and Phase 3.
  Lane restrictions and night work
Construct crossovers located in roadway median
  Increase worker safety
  Increase speed of construction

## Slide 13: Phase 1 Multiple Activities
Temporary Bridge and crossover located at Cheatam Slough

## Slide 14: Phase 2
  Work complete and re-open the KY Ohio River Bridge southbound structure
  All traffic to be shifted onto southbound lanes
  Construct northbound bridges and roadway
  MOT illustrated by flyover

## Slide 15: Phase 3
  All traffic to be shifted onto northbound lanes
  Construct southbound bridges and roadway
  Kentucky Avenue will be closed
  MOT illustrated by flyover

## Slide 16: MOT – Detour Route
Wide loads and heavy haul
  Detour east to Maceo, Kentucky using US 231 bridge.
  Required during Phase 1
  Encouraged throughout
  Coordination with Motor Truck Assc.

## Slide 17: For Public Safety
Reduced speed limit
Tow trucks on site and on call
  Rush Hours during Phase 1 on site
  24/7 on call
Monitored by law enforcement
  Additional patrols
  INDOT MOU with ISP
Permanent Cameras
  Aid in emergency response

## Slide 18: MOT – Public Awareness
Highway message boards
  Located on I-69, US 41, Lloyd Expressway and Kentucky State Routes
Website
Partner with local news media with updates
Lane Changes
Ahead

## Slide 19: Community
River Run
  No conflict May 6, 2017

## Slide 20: Conclusion: Schedule
Spring and Summer 2017
Fall 2017 through
Fall 2018
Fall 2018 through
Summer 2019

## Slide 21: Contact Information
Kate Francis
Border Bridge Project Manager
100 North Senate Avenue
IGCN 642
Indianapolis, IN 46204
kfrancis@indot.IN.gov
317-234-5289
  INDOT Vincennes Customer Service swincommunications@indot.in.gov 1-800-279-5758