## Sheet1
Tasks |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3 | [11 empty] | YEAR 4
|  |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
PRE AGREEMENT TASKS
Application Preparation
State Review & Revisions
NEPA & Section 106 Coordination
Site Survey, Design, & Engineering
State Plan Review
AFTER FEDERAL APPROVAL - assume by September of the following year
Bid Advertisement and Specifications
State Bid Review
Bidding Timeframe
State Award Review
Construction (weather dependent)
State Final Inspection
Final Inspection Revisions (if required)
Close-Out Paperwork & Final Billing
|  | : Applicant Task | YEAR 2 J: TIMELINE CONSTRAINTS TO CONSIDER
: State Review Period | bar: YEAR 2 J to YEAR 3 N
1. Projects have a maximum of 36 months to reach total completion from the point of Federal Approval
|  | : Local/State Milestone | YEAR 2 F: so designating pre-agreement costs is STRONGLY encouraged to allow for construction buffer time
2. Projects may designate pre-agreement costs up to 3 Years prior to Federal Approval
3. The State begins fiscal year-end shutdown preparations in March every year. Consult with your
grant coordinator to see if this will impact your project