## QI Project Planning+Reporting
QI Project Planning and Reporting Form
This tool is accompanied by the Quality Improvement Project Guide which can be found here https://www.in.gov/isdh/27830.htm
Aim Statement →
Be specific about what you want to change, who is responsible for changing it, who should be affected, how long it will take, and how much change you expect to see.
Drivers → | Aim | Primary Drivers |  | Secondary Drivers |  | Change Ideas
It is essential to understand the drivers that are influencing change and your aim. To the right you will restate your aim in the first column. Then you will identify the "primary drivers," which are the high-level factors that are most influential to your QI project outcomes. Then you will identify "secondary drivers" that are related to each primary driver you listed. The secondary drivers are things that influence your primary drivers. Finally, in the last column, you will identify the change ideas that you can use to address issues related to the drivers identified. You may not identify 4 primary drivers- sometimes there are only a couple drivers. It often takes engagement from many staff and clients to effectively identify all drivers and potential change ideas. | 0
Outcome Measure(s) → | Performance Measure | Operational Definition |  | Disparity Evaluation |  | Measurement Period, Reporting, Target, Baseline
What are the performance measures you created to evaluate the success of what you stated you aim to do above? Create up to two measures. |  | Description: |  |  |  | Measurement Period:
|  | Numerator: |  |  |  | Reporting:
|  | Denominator: |  |  |  | Target:
|  | Exclusions |  |  |  | Baseline:
|  | Description: |  |  |  | Measurement Period:
|  | Numerator: |  |  |  | Reporting:
|  | Denominator: |  |  |  | Target:
|  | Exclusions |  |  |  | Baseline:
Outcome Measure(s) Reporting → | Performance Measure | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result
In your performance measures you decided how frequently you will report on the measures to evaluate your progress. You can track that reporting here. Feel free to edit this template to make it work with your reporting schedule. | 0 | Week 1: | Week 2: | Week 3: | Week 4: | Week 5: | Week 6:
|  | Month 1: | Month 2: | Month 3: | Month 4: | Month 5: | Month 6:
|  | Quarter 1: | Quarter 2: | Quarter 3: | Quarter 4:
| 0 | Week 1: | Week 2: | Week 3: | Week 4: | Week 5: | Week 6:
|  | Month 1: | Month 2: | Month 3: | Month 4: | Month 5: | Month 6:
|  | Quarter 1: | Quarter 2: | Quarter 3: | Quarter 4:
Narrative (optional) | Insert text below:
Is there any additional context you'd like to provide to ISDH about your QI project?

## Example of Completed Form
QI Project Planning and Reporting Form
This tool is accompanied by the Quality Improvement Project Guide which can be found here https://www.in.gov/isdh/27830.htm
Aim Statement → | Care Center Plus will increase the percentage of AAMSM tested for HIV through the outreach program to 30% for the year of 2020.
Be specific about what you want to change, who is responsible for changing it, who should be affected, how long it will take, and how much change you expect to see.
Drivers → | Aim | Primary Drivers |  | Secondary Drivers |  | Change Ideas
It is essential to understand the drivers that are influencing change and your aim. To the right you will restate your aim in the first column. Then you will identify the "primary drivers," which are the high-level factors that are most influential to your QI project outcomes. Then you will identify "secondary drivers" that are related to each primary driver you listed. The secondary drivers are things that influence your primary drivers. Finally, in the last column, you will identify the change ideas that you can use to address issues related to the drivers identified. You may not identify 4 primary drivers- sometimes there are only a couple drivers. It often takes engagement from many staff and clients to effectively identify all drivers and potential change ideas. | Care Center Plus will increase the percentage of AAMSM tested for HIV through the outreach program to 30% for the year of 2020. | Our agency has a lack of presence and lack of trust in the AA community. |  | Few pictures on our website and no pictures with people of color |  | Include staff and board photos on website
|  |  |  | Not enough staff of color |  | Increase diversity in staff by creating a multi-faceted strategic approach to hiring and agency culture
|  |  |  | Agency has no representation at community events, and especially not events attended by many people of color |  | Increase agency representation at community events
|  | AAMSM in our community do not have any communal gathering places |  | Community culture is not accepting of AAMSM |  | Increase outreach and marketing to the AA community in general as a means to reach AAMSM with HIV testing and prevention options
Local "gay bars" do not feel like safe or welcoming spaces for people of color
|  | AAMSM in our commmunity often don't feel comfortable openly identifying as MSM |  | Strong religious roots in the community make it less acceptable to be openly MSM |  | Make marketing efforts broadly focused on all people of color so that AAMSM do not feel as if they're revealing their sexual behavior by utilizing services
Outcome Measure(s) → | Performance Measure | Operational Definition |  | Disparity Evaluation |  | Measurement Period, Reporting, Target, Baseline
What are the performance measures you created to evaluate the success of what you stated you aim to do above? Create up to two measures. | AAMSM HIV Testing | Description: The percentage of outreach HIV testing done amongst AAMSM testing participants |  | MSM (AA, Hispanic, White) |  | Measurement Period: One year (1/1/2020-12/31/2020)
|  | Numerator: The number of people from the denominator who identified their race as AA and MSM as a risk factor |  | MSM Age (13-17, 18-24, 25-34, 35-44, 55+) |  | Reporting: Quarterly
|  | Denominator: The total number of outreach HIV testing participants |  |  |  | Target: 30%
|  | Exclusions: None |  |  |  | Baseline: 17%
|  | Description: |  |  |  | Measurement Period:
|  | Numerator: |  |  |  | Reporting:
|  | Denominator: |  |  |  | Target:
|  | Exclusions |  |  |  | Baseline:
Outcome Measure(s) Reporting → | Performance Measure | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result | Reporting Cycle + Result
In your performance measures you decided how frequently you will report on the measures to evaluate your progress. You can track that reporting here. Feel free to edit this template to make it work with your reporting schedule. | AAMSM HIV Testing | Week 1: | Week 2: | Week 3: | Week 4: | Week 5: | Week 6:
|  | Month 1: | Month 2: | Month 3: | Month 4: | Month 5: | Month 6:
|  | Quarter 1: 18% | Quarter 2: 20% | Quarter 3: 21% | Quarter 4: 25%
| 0 | Week 1: | Week 2: | Week 3: | Week 4: | Week 5: | Week 6:
|  | Month 1: | Month 2: | Month 3: | Month 4: | Month 5: | Month 6:
|  | Quarter 1: | Quarter 2: | Quarter 3: | Quarter 4:
Narrative (optional) | Insert text below:
Is there any additional context you'd like to provide to ISDH about your QI project?