## Budget Example
Itemized Budget for Townville - City Ash Removal and Replacement3
Item | Grant Money1 | Match Money2 | In-kind Match | Total $
Administrative Personnel Costs
Staff Forester/Arborist (21 hours) | 0 | 0 | 845 | 845
Public Works Director (5 hours) | 0 | 0 | 225 | 225
Subtotal | 0 | 0 | 1070 | 1070
Tree Inventory
Contractor or Internal Cost to Inventory trees (estimated $5 per tree) | 10000 | 6000 | 4000 | 20000
Subtotal | 10000 | 6000 | 4000 | 20000
Signage
Design | 0 | 1000 | 0 | 1000
Signage structures | 0 | 6000 | 0 | 6000
Sub Total | 0 | 7000 | 0 | 7000
Tree Planting
Tree Purchase (50 @ $250) | 10000 | 400 | 0 | 10400
Contractor or Internal Cost to Plant (estimated at $45 per hour) | 0 | 6000 | 0 | 6000
Mulch, Soil, Etc. | 0 | 0 | 330 | 330
Subtotal | 10000 | 6400 | 330 | 16730
GRAND TOTAL | 20000 | 19400 | 5400 | 44800
1: Must not exceed 50% of the total project cost. Match Money + In-kind Match will meet or exceed Grant Money.
2: May not include any federal funds.
3: Remove all line items provided not pertinent to your project. Similarly, add additional line items that may not be included but are part of your project. Cells in this spreadsheet will automatically total. You will need to copy formulas into newly added cells to ensure proper totals.

## Budget Template
Itemized Budget³ for (Your Community/Org name + your project description here)
Item | Grant Money1 | Match Money2 | In-kind Match | Total $
Administrative Personnel Costs
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0
Tree Inventory
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0
Tree Removal (ASH TREES ONLY)
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0
Signage
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0
Tree Planting
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0
GRAND TOTAL | 0 | 0 | 0 | 0
1: Must not exceed 50% of the total project cost.
2: May not include any federal funds.
3: Remove all line items provided not pertinent to your project. Similarly, add additional line items that may not be included but are part of your project. Cells in this spreadsheet will automatically total. You will need to copy formulas into newly added cells to ensure proper totals.

## Timeline Example
Project Timeline | Townville - City Ash Removal and Replacement
Date/Month | Task1
February 20212 | Receive Grant Acceptance Letter, mark official project start date
2021-02-01 | Bid landscape services grant for tree removal, purchase, installation, and maintenance (If over $3000, collect minimum 3 bids). If not done already, complete EAB Management Plan.
2021-03-01 | Village Board approves contracts for site prep and planting
2021-04-01 | Stumps removed & trees replanted
April - September 2021 | Watering program to maintain new trees
6/30/20213 | Interim Accomplishment Report to CUF
2021-10-01 | Remaining trees planted
12/15/20213 | Interim Accomplishment Report to CUF
2022-03-01 | Request planting inspection from CUF staff
2022-04-01 | Replace/replant trees to CUF requirements
2021-06-01 | Project documentation to CUF for reimbursement
6/30/20223 | Grant project close - no reimbursable activities after this date
7/1/20223 | Final Accomplishment Report to CUF (or within 30 days of project end)
8/31/20223 | Final date to have all grant documentation submitted to CUF
1 Be specific to your project
2 Your Project Start Date is the date you were informed that your grant application had been accepted.
3 REQUIRED Reports & Grant Milestones

## Timeline Template
Project Timeline | (Your Community/Org name + your project description here)
Date/Month | Task
2021-06-30 | Interim Accomplishment Report to CUF
2021-12-15 | Interim Accomplishment Report to CUF
2022-06-30 | Grant Project Close
2022-07-01 | Final Accomplishment Report to CUF
2022-08-31 | Final date to have all grant documentation submitted

## Work Plan Chart Fields
Information Required in Work Plan Chart
A Work Plan Chart is a required part of your Grant Application. This workbook includes a Work Plan Chart template that you can use. We don't require you to use this template but the following information must appear in your submitted Work Chart. For example, your community's inventory software may be able to export the required data in a different format. Below are explanations of the chart fields and their information that members of the review panel will be looking for in your Work Plan Chart.
REQUIRED INFORMATION
New Tree # | A unique identifier for each tree to be planted in the plan. This can be the ID code used in the community inventory or as simple as labeling the first tree in the Work Plan Chart as 1 and proceeding numerically. The intended purpose is to easily have a way to communicate trees with specific notes during the review & inspection processes. If this tree is a replacement for a removed ash tree, you must also enter the removed tree information on the same line.
Planting Address | This information should enable someone to find the general vicinity of a specific tree without using a map that has precise planting locations. If trees are along roads, a common method is to use the corresponding street address of the nearest building. If trees are within a park, use an identifying feature if available. For example: north side of Red Trail or east of soccer field.
Planting Site Description | How would you describe the location of the tree? Common examples include: park, lawn, right-of-way between street & sidewalk, median, tree pit, etc. This information is intended to help provide a general sense of growing conditions and possible potential conflicts.
Planting Site Size | How much rooting space is available for the tree? Specific site measurements can be provided for each tree or sites can be sorted into broader categories. If using categories be sure to provide a key that lists the measurement range for each. Example categories: small, medium, large, open. See Addendum A of the Grant Application for guidance on site size.
Utilities or Other Potential Conflicts | Be sure to include both above ground and below ground utilities. This information helps justify species choices to reviewers. A common justification is planting a smaller stature species in a site that has the rooting space to support a larger species because there are powerlines present.
Planting Date | This does NOT need to be an exact date. Season and year are sufficient. Example: spring 2021
Genus | The generic name- the first part of the scientific name. Example: Liriodendron tulipifera
Species | Species: The species epithet- the second part of the scientific name. Example: Liriodendron tulipifera
Common Name | The non-Latin name of the tree. Example: tulip poplar
Additional Notes | Any other information that might be pertinent to the reviewers or provide clarification on species selection. Examples: the name of the cultivar if being used, area of park commonly floods, previous homeowner complaints about trees with nuts or large seed pods, etc.
Information Required in Work Plan Chart for Ash Removals
The costs associated with the removal of ash trees as part of site preparation for planting is an acceptable expense that can be applied towards the 1:1 match requirement. If planning to use ash removals as match fill out the additional columns of the Work Plan Chart.
ASH REMOVAL INFORMATION
Replacement Tree Y/N | Is this new tree a replacement for a removed ash tree? Yes/No
Removed Tree # | A unique identifier for each ash tree to be removed in the plan is required. This can be its existing ID code used in the community inventory or as simple as labeling the first tree in the Work Plan Chart as 1 and proceeding numerically. The intended purpose is to easily have a way to communicate trees with specific notes during the review & inspection processes.
Removal Address | This information should enable someone to find the general vicinity of a specific ash tree/removal site without using a map that has precise locations. If trees are along roads, a common method is to use the corresponding street address of the nearest building. If trees are within a park, use an identifying feature if available. For example: north side of Red Trail or east of soccer field.
Species Removed | Which species of ash tree was removed?
Removal Date | This can be an estimated date. Remember work done outside the project period cannot be counted as match. The project period is from the award notification date through June 30, 2022
Formatting Notes: blank cells in your Work Plan Chart are to be expected since not every tree is planted in response to an ash removal and not every removal corresponds to a new tree planting. Just make sure that removals are aligned with their corresponding replacement tree in the Work Plan Chart. When printing an expanded Work Chart, choose landscape orientation on legal or tabloid-sized paper. You may also need to resize your table to fit your paper by changing the Print Area under File in the main menu.

## Work Plan Example
Work Plan for Townville - City Ash Removal and Replacement
Required Information | [9 empty] | Ash Removal Information
New Tree # | Planting Address | Planting Site Description | Planting Site Size (i.e. 8’x8’ or S,M,L) * | Utilities/Other Conflicts | Planting Date | Genus | Species | Common Name | Notes | Replacement Tree Y/N | Removed Tree # | Removal Address | Species Removed | Removal Date
201 | 1445 Tree Lane Rd | Tree lawn/ROW - Arthur BLVD | 8' x 37' |  | 2021-04-01 | Quercus | alba | White Oak | Homeowner requested large canopy tree site is large enough to accommodate one tree | Yes | B34-1998 | 1445 Tree Lane Rd | Green Ash | 2019-10-15
202 | 102 Main St | Public Library Lawn | L |  | fall 2021 | Quercus | imbricaria | Shingle Oak
203 | 102 Main St | Public Library Lawn | L |  | fall 2021 | Taxodium | distichum | Bald Cypress
204 | 104 Main St | City Hall Plaza | 6' x 6' |  | fall 2021 | Tilia | americana | Basswood | Near picnic benches for shade | Y | 224 | 104 Main St | White Ash | 2020-03-15
[9 empty] | Park strip of old strip mall site | N | 1 | 35 Macadamia Lane | Green Ash | 2020-03-15
[9 empty] | " | N | 2 | 37 Macadamia Lane | Green Ash | 2020-03-15
[9 empty] | " | N | 3 | 39 Macadamia Lane | Green Ash | 2020-03-15
205 | 26 Brook Rd | Elementary School | Lawn | 20' from overhead wires | fall 2021 | Tilia | americana | Basswood |  | N
* Please see Addendum A for minimum S, M, L rooting widths

## Work Plan Template
Work Plan for (Your Community/Org name + your project description here)
Required Information | [9 empty] | Ash Removal Information
New Tree # | Planting Address | Planting Site Description | Planting Site Size (i.e. 8’x8’ or S,M,L) * | Utilities/Other Conflicts | Planting Date | Genus | Species | Common Name | Notes | Replacement Tree Y/N | Removed Tree # | Removal Address | Species Removed | Removal Date
* Please see Addendum A for minimum S, M, L rooting widths