## Instructions
The Highway Engineering Division developed the Road Review Checklist and Status Sheet to improve uniformity, transparency, and consistency in the roadway design review process. The Road Review Checklist tab includes the review items applicable at each stage of roadway plan development. The Status Sheet tab includes key project development documents and design components including hydraulics, geotechnical information, pavement design, ADA/TAC coordination, environmental documentation, design exceptions, and other elements necessary for Stage 3 readiness.
Complete the required information on each tab, for each stage, and submit in .xlsx format.
Road Review Checklist Tab
1. | Complete the project data and information associated with the Stage of the submittal. For projects that only require a Stage 3 submittal, items associated with Stage 1 and Stage 2 submittals must be addressed.
2. | Mark items that do not apply to the project as Not Applicable (NA)
3. | Address all reviewer comments in the subsequent submittal
Status Sheet Tab
1. | Complete the project data and information associated with the Stage of the submittal. For projects that only require a Stage 3 submittal, items associated with Stage 1 and Stage 2 submittals must be addressed.
2. | Mark items that do not apply to the project as Not Applicable (NA)
3. | Review and update for each submittal

## Road Review Checklist
[5 empty] | ROAD REVIEW CHECKLIST |  |  |  |  | Review columns are abbreviated as follows: Sufficient (S), Deficient (D), and Not Applicable (NA). Any items marked deficient at any stage may require a resubmittal.
[5 empty] | Highway Engineering Division | [7 empty] | Version Date: 06-4-2026
Note:
For the current road review stage, each designated review item for that stage are required to be filled out.
For any previous stage, all review items are also required to be completed during this review.
| PROJECT DATA To be filled out by Designer. | [6 empty] | Y | N | HIGHWAY SYSTEM To be filled out by Designer. | To be filled out by Designer.
1 | Date | [8 empty] | National Highway System (NHS)
2 | Des No. | [8 empty] | State Highway System | DESIGNER GENERAL PLAN COMMENTS
3 | Submittal Stage |  |  |  | Select a "Stage". |  |  |  |  | National Truck Network
4 | Contract No.
5 | Design Criteria |  |  |  | Select a "Project Design Criteria". |  |  |  |  | REVIEWER INFORMATION To be filled out by Reviewer
6 | Work Type |  |  |  | Select a "Work Type". |  | Date
7 | Route | [5 empty] | Internal ID No.
8 | Location | [5 empty] | Reviewer
9 | INDOT District |  |  |  | Select a "District". |  | Review Firm
10 | Project Manager | [5 empty] | Review Date
11 | County | [5 empty] | REVIEWER GENERAL PLAN COMMENTS To be filled out by Reviewer.
12 | Stg. 3 Constr.Est.
13 | Letting Date
14 | CN Completion Date
15
16 | DESIGNER INFORMATION To be filled out by Designer.
17 | Designer
18 | Phone
19 | E-mail
20 | Design Firm
21 | Submittal Date
22
23 | FUNCTIONAL CLASSIFICATION To be filled out by Designer.
24 | Select a "Functional Classification"
25
26
27 | [10 empty] | Designer's Comments are required by the next stage submittal.
28 | Req'd at | Y | N | NA | TRANSMITTAL LETTER Column Abbreviations: Yes (Y), No (N), & Not Applicable (NA) |  | S | D | NA | REVIEWER REMARKS Column Abbreviations: Sufficient (S), Deficient (D), & Not Applicable (NA) |  | Accept? | Designer's Response
29 | Stage 1 |  |  |  | 1. The Transmittal Letter listing the uploaded files. | 1 |  |  |  |  | 1 | Select
30 | Stage 1 |  |  |  | 2. Stage 1 Status Sheet completed. | 2 |  |  |  |  | 2 | Select
31 | Stage 2 |  |  |  | 3. Stage 2 Status Sheet completed. | 3 |  |  |  |  | 3 | Select
32 | Stage 3 |  |  |  | 4. Stage 3 Status Sheet completed. | 4 |  |  |  |  | 4 | Select
33
34 | Req'd at | Y | N | NA | E-MAIL DESCRIPTIONS |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
35 | Stage 1 |  |  |  | The description must include CN#, Des#, Stage, Route & Work Type at a minimum. | [6 empty] | Select
36
37 | Req'd at | Y | N | NA | ENGINEER'S REPORT |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
38 | Stage 1 |  |  |  | The Engineer's Report shall have all appropriate INDOT approvals (signatures) has submitted - IDM 14-2.01(04)#2(10). For LPA projects, the scoping document was approved by an appropriate LPA official. | [6 empty] | Select
39
40 | Req'd at | Y | N | NA | COST ESTIMATE |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
41 | Stage 1 |  |  |  | 1. Cost Estimate (Contengency 20% max.) | 1 |  |  |  |  | 1 | Select
42 | Stage 2 |  |  |  | 2. Cost Estimate (Contengency 10% max.) | 2 |  |  |  |  | 2 | Select
43 | Stage 3 |  |  |  | 3. Cost Estimate (No Contingency in CES). | 3 |  |  |  |  | 3 | Select
44
45 | Req'd at | Y | N | NA | QUANTITY CALCULATIONS |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
46 | Stage 2 |  |  |  | 1. Quantity Calculations provided. | 1 |  |  |  |  | 1 | Select
47 | Stage 3 |  |  |  | 2. Quantity Calculations - All Pay Items (Initialed/Dated by Designer/Checker). | 2 |  |  |  |  | 2 | Select
48
49 | Req'd at | Y | N | NA | LEVEL 1 CHECKLIST & LEVEL 1 AND LEVEL 2 DESIGN COMPUTATIONS |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
50 | Stage 1 |  |  |  | 1. Level 1 Checklist(s) and computations for the Mainline submitted. | 1 |  |  |  |  | 1 | Select
51 | Stage 1 |  |  |  | 2. Level 1 Checklist(s) and computations for each S-line Submitted. | 2 |  |  |  |  | 2 | Select
52 | Stage 1 |  |  |  | 3. Level 2 Design Criteria Discrepancies were identified. | 3 |  |  |  |  | 3 | Select
53 | Stage 2 |  |  |  | 4. Level 1 Checklist and Calculations were submitted for each Phase of MOT. | 4 |  |  |  |  | 4 | Select
54
55 | Req'd at | Y | N | NA | DESIGN EXCEPTIONS |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
56 | Stage 2 |  |  |  | 1 . Level 1 Design Exception Documentation submitted. | 1 |  |  |  |  | 1 | Select
57 | Stage 2 |  |  |  | 2. Level 2 Design Exception Documentation submitted (Local Authority approves for LPA project). | 2 |  |  |  |  | 2 | Select
58 | Stage 2 |  |  |  | 3. Level 2 Criteria for Non-Standard Application of Guardrail was submitted to the INDOT Standards and Policy Group for approval. | 3 |  |  |  |  | 3 | Select
59 | Stage 3 |  |  |  | 4. Level 1 Design Exception Approved or is Pending Approval. | 4 |  |  |  |  | 4 | Select
60 | Page 1 of 5
61 | Req'd at | Y | N | NA | DESIGN COMPUTATIONS |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
62 | Stage 1 |  |  |  | 1. Guardrail Calculations | 1 |  |  |  |  | 1 | Select
63 | Stage 1 |  |  |  | 2. Horizontal Alignment (i.e. AutoTurn) | 2 |  |  |  |  | 2 | Select
64 | Stage 1 |  |  |  | 3. Horizontal SSD | 3 |  |  |  |  | 3 | Select
65 | Stage 1 |  |  |  | 4. Relocation Plan (stream or utility) | 4 |  |  |  |  | 4 | Select
66 | Stage 1 |  |  |  | 5. Superelevation | 5 |  |  |  |  | 5 | Select
67 | Stage 1 |  |  |  | 6. Vertical Alignment | 6 |  |  |  |  | 6 | Select
68 | Stage 1 |  |  |  | 7. Critical Grade | 7 |  |  |  |  | 7 | Select
69 | Stage 1 |  |  |  | 8. Vertical SSD | 8 |  |  |  |  | 8 | Select
70 | Stage 1 |  |  |  | 9. Intersection Sight Distance calculations. | 9 |  |  |  |  | 9 | Select
71 | Stage 2 |  |  |  | 10. Intersection Sight Distance calculations. | 10 |  |  |  |  | 10 | Select
72
73 | Req'd at | Y | N | NA | MISCELLANEOUS CHECKLIST |  | S | D | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
74 | Stage 1 |  |  |  | 1. Roundabout Checklist | 1 |  |  |  |  | 1 | Select
75 | Stage 3 |  |  |  | 2. Approved MSE Wall Design Review Checklist. | 2 |  |  |  |  | 2 | Select
76
77 | Req'd at | Y | N | NA | CORRESPONDENCE FILE |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
78 | Stage 2 |  |  |  | 1. Preliminary Field Check Meeting Minutes provided. | 1 |  |  |  |  | 1 | Select
79 | Stage 2 |  |  |  | 2. ADA TAC Committee Correspondence provided. | 2 |  |  |  |  | 2 | Select
80 | Stage 3 |  |  |  | 3. Approved Proprietary Materials Request. | 3 |  |  |  |  | 3 | Select
81 | Stage 3 |  |  |  | 4. Underground Storage Tanks Removal Coordination. | 4 |  |  |  |  | 4 | Select
82 | Stage 3 |  |  |  | 5. All Meeting Minutes provided. | 5 |  |  |  |  | 5 | Select
83
84 | Req'd at | Y | N | NA | ENVIRONMENTAL COMPLIANCE FORM |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
85 | Stage 3 |  |  |  | ECF submitted. (Environmental Services will review) | [6 empty] | Select
86
87 | Req'd at | Y | N | NA | COMMITMENTS REPORT |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
88 | Stage 2 |  |  |  | 1. Commitments submitted. (Environmental Services will review) | 1 |  |  |  |  | 1 | Select
89 | Stage 3 |  |  |  | 2. Commitments submitted. (Environmental Services will review w/ resolutions provided.) | 2 |  |  |  |  | 2 | Select
90
91 | Req'd at | Y | N | NA | TMP FOR SIGNIFICANT PROJECTS |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
92 | Stage 1 |  |  |  | 1. DRAFT TMP submitted for Significant Projects. | 1 |  |  |  |  | 1 | Select
93 | Stage 1 |  |  |  | 2. Identification of the TMP Team. | 2 |  |  |  |  | 2 | Select
94 | Stage 1 |  |  |  | 3. TMP Meeting Minutes or Correspondence provided. | 3 |  |  |  |  | 3 | Select
95 | Stage 1 |  |  |  | 4. Determination of Significant Work Zone Impacts. | 4 |  |  |  |  | 4 | Select
96 | Stage 1 |  |  |  | 5. Approved Traffic Control Strategy Memo. | 5 |  |  |  |  | 5 | Select
97 | Stage 1 |  |  |  | 6. Crossover and Runaround Viability Worksheet. | 6 |  |  |  |  | 6 | Select
98 | Stage 1 |  |  |  | 7. Draft Design Exception Request for MOT. | 7 |  |  |  |  | 7 | Select
99 | Stage 1 |  |  |  | 8. List of preferred mitigation measures. | 8 |  |  |  |  | 8 | Select
100 | Stage 2 |  |  |  | 9. Draft IHCP Exception Request submitted. | 9 |  |  |  |  | 9 | Select
101 | Stage 3 |  |  |  | 10. Approved IHCP Exception Request. | 10 |  |  |  |  | 10 | Select
102 | Stage 3 |  |  |  | 11. FINAL TMP Report for Significant Projects Approved. | 11 |  |  |  |  | 11 | Select
103
104 | Req'd at | Y | N | NA | HYDRAULIC COMPUTATIONS & REPORT |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
105 | Stage 1 |  |  |  | 1. Approved Hydraulics Letter, if available. (Small structures due.) | 1 |  |  |  |  | 1 | Select
106 | Stage 2 |  |  |  | 2. Approved Hydraulics Letter, if available. | 2 |  |  |  |  | 2 | Select
107 | Stage 3 |  |  |  | 3. Approved Hydraulics Letter. (Detention and storm sewers due.) | 3 |  |  |  |  | 3 | Select
108
109 | Req'd at | Y | N | NA | GEOTECHNICAL REPORT |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
110 | Stage 1 |  |  |  | 1. Approved Geotechnical Report, if available. (Landslides due.) | 1 |  |  |  |  | 1 | Select
111 | Stage 2 |  |  |  | 2. Approved Geotechnical Report, if available. | 2 |  |  |  |  | 2 | Select
112 | Stage 3 |  |  |  | 3. Approved Geotechnical Report. | 3 |  |  |  |  | 3 | Select
113
114 | Req'd at | Y | N | NA | PAVEMENT DESIGN REPORT |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
115 | Stage 1 |  |  |  | 1. Pavement Design Report, if available. | 1 |  |  |  |  | 1 | Select
116 | Stage 2 |  |  |  | 2. Approved Pavement Design Report, if available. Does it match the Typical X-Section? | 2 |  |  |  |  | 2 | Select
117 | Stage 3 |  |  |  | 3. Approved Pavement Design Report. Does it match the Typical X-Section? | 3 |  |  |  |  | 3 | Select
118
119 | Req'd at | Y | N | NA | PREVIOUS MARKUPS |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
120 | Stage 2 |  |  |  | 1. Stage 1 Comments Letter and Previous Markups provided with Designer responses. | 1 |  |  |  |  | 1 | Select
121 | Stage 3 |  |  |  | 2. Stage 2 Comments Letter and Previous Markups provided with Designer responses. | 2 |  |  |  |  | 2 | Select
122
123 | Req'd at | Y | N | NA | SPECIAL PROVISIONS All files are to be submitted in PDF format |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
124 | Stage 3 |  |  |  | 1. Recurring Special Provisions Menu. | 1 |  |  |  |  | 1 | Select
125 | Stage 3 |  |  |  | 2. Recurring Special Provisions and Plan Details. | 2 |  |  |  |  | 2 | Select
126 | Stage 3 |  |  |  | 3. Unique Special Provisions Menu. | 3 |  |  |  |  | 3 | Select
127 | Stage 3 |  |  |  | 4. Unique Special Provisions. | 4 |  |  |  |  | 4 | Select
128 | Stage 3 |  |  |  | 5. Non-Participating Items? (if Yes, are they listed separately with an asterisk in the estimate?) | 5 |  |  |  |  | 5 | Select
129 | Stage 3 |  |  |  | 6. Proprietary Items? (If Yes, has their use been approved?) | 6 |  |  |  |  | 6 | Select
130 | Page 2 of 5
131 | Req'd at | Y | N | NA | PLANS |  | Y | N | NA | REVIEWER REMARKS |  | Accept? | Designer's Response
132 |  |  |  |  | Plan Notes (Notes to Reviewer are encouraged) | Plan Notes |  |  |  |  | Plan Notes (Notes to Reviewer are encouraged)
133
134
135
136
137 |  |  |  |  | General Plan Information
138 | Stage 1 |  |  |  | 1. Stage 1 Plans - Designer is encouraged to provide Notes to Reviewer. | 1 |  |  |  |  | 1 | Select
139 | Stage 2 |  |  |  | 2. Stage 2 Plans - Should also include the Required Items for Stage 1 and Preliminary Field Check Plans. All Items identified in Chapter 14 to be included in the PFC Plans at Stage 2. | 2 |  |  |  |  | 2 | Select
140 | Stage 3 |  |  |  | 3. Stage 3 Plans - Should also include the Required Items for Stage 1, PFC, and Stage 2 Plans. All Plan Sheets should be at 95% complete. All necessary Sheets and Details for the Final Tracings should be included. | 3 |  |  |  |  | 3 | Select
141
142 |  |  |  |  | Title Sheet
143 | Stage 1 |  |  |  | 1. Designation Number. | 1 |  |  |  |  | 1 | Select
144 | Stage 1 |  |  |  | 2. Culvert Asset ID Number (for a small structure). | 2 |  |  |  |  | 2 | Select
145 | Stage 1 |  |  |  | 3. KIN Information for Bundled Projects, with the LEAD Des identified. | 3 |  |  |  |  | 3 | Select
146 | Stage 1 |  |  |  | 4. Location Map. | 4 |  |  |  |  | 4 | Select
147 | Stage 1 |  |  |  | 5. Project Location Map including North Arrow, Scale, and Paving Exceptions. | 5 |  |  |  |  | 5 | Select
148 | Stage 1 |  |  |  | 6. Description of the Project Work Type and Location. | 6 |  |  |  |  | 6 | Select
149 | Stage 1 |  |  |  | 7. Design Data Table per IDM Fig. 14-3C. | 7 |  |  |  |  | 7 | Select
150 | Stage 1 |  |  |  | 8. Traffic Data. | 8 |  |  |  |  | 8 | Select
151 | Stage 1 |  |  |  | 9. Applicable Reference Point (does not apply to Local Agency Project). | 9 |  |  |  |  | 9 | Select
152 | Stage 1 |  |  |  | 10. Signature Blocks, but not filled in at this stage. | 10 |  |  |  |  | 10 | Select
153 | Stage 1 |  |  |  | 11. Gross and Net Project Lengths, not including incidental construction or lengths along S-lines. | 11 |  |  |  |  | 11 | Select
154 | Stage 1 |  |  |  | 12. Latitude and Longitude. | 12 |  |  |  |  | 12 | Select
155 | Stage 1 |  |  |  | 13. Hydrogeologic Unit Code (HUC), if available. | 13 |  |  |  |  | 13 | Select
156 | Stage 1 |  |  |  | 14. Appropriate version of Standard Specifications. | 14 |  |  |  |  | 14 | Select
157 | Stage 1 |  |  |  | 15. Bridge Structure information. | 15 |  |  |  |  | 15 | Select
158 | Stage 1 |  |  |  | 16. Stage and Submittal Date. | 16 |  |  |  |  | 16 | Select
159 | Stage 1 |  |  |  | 17. Standard Specification Date. | 17 |  |  |  |  | 17 | Select
160 | Stage 1 |  |  |  | 18. Standard Specification Date. | 18 |  |  |  |  | 18 | Select
161 | Stage 1 |  |  |  | 19. LPA owner's signature block. | 19 |  |  |  |  | 19 | Select
162
163 |  |  |  |  | Index Sheet
164 | Stage 1 |  |  |  | 1. An Index of Plan Sheets for Stage 1 Submittal. | 1 |  |  |  |  | 1 | Select
165 | Stage 1 |  |  |  | 2. List of Utility Owners, Addresses, and Contact Person with phone number and email address. | 2 |  |  |  |  | 2 | Select
166
167 |  |  |  |  | Typical Cross Sections
168 | Stage 1 |  |  |  | 1. Lane and Shoulder Widths. | 1 |  |  |  |  | 1 | Select
169 | Stage 1 |  |  |  | 2. Profile Grade, Construction Centerline, Paper-Relocation (PR) Line, and Survey-Line Locations. | 2 |  |  |  |  | 2 | Select
170 | Stage 1 |  |  |  | 3. Typical Cross Sections in normal crown and superelevation. | 3 |  |  |  |  | 3 | Select
171 | Stage 1 |  |  |  | 4. Cross Section Elements: curb-type, auxiliary lanes, sidewalk, cross slopes, side slopes, ditches, bicycle lanes, underdrains, R/W, joints, etc. | 4 |  |  |  |  | 4 | Select
172 | Stage 1 |  |  |  | 5. Clear Zone Width (4R Project) or Obstruction Free Zone (3R Project). | 5 |  |  |  |  | 5 | Select
173 | Stage 1 |  |  |  | 6. Safety Edge Detail | 6 |  |  |  |  | 6 | Select
174 | Stage 2 |  |  |  | 7. Misc. Detail: Guardrail, MSE , etc. | 7 |  |  |  |  | 7 | Select
175 | Stage 2 |  |  |  | 8. Legend - provided on each typical section sheet | 8 |  |  |  |  | 8 | Select
176
177 |  |  |  |  | Plat 1 Sheet
178 | Stage 2 |  |  |  | 1. North Arrow; | 1 |  |  |  |  | 1 | Select
179 | Stage 2 |  |  |  | 2. Scale per IDM; | 2 |  |  |  |  | 2 | Select
180 | Stage 2 |  |  |  | 3. 500 ft. Ticks w/ Sta. 000+00; | 3 |  |  |  |  | 3 | Select
181 | Stage 2 |  |  |  | 4. 100 ft. Ticks; | 4 |  |  |  |  | 4 | Select
182 | Stage 2 |  |  |  | 5. Existing EP & ES; | 5 |  |  |  |  | 5 | Select
183 | Stage 2 |  |  |  | 6. PI Data : Sta., Delta, Radius, Length, E & SE; | 6 |  |  |  |  | 6 | Select
184 | Stage 2 |  |  |  | 7. P.C., P.I. & PT w/ Sta.000+00, "Line Name"; | 7 |  |  |  |  | 7 | Select
185 | Stage 2 |  |  |  | 8. Tangent Lines @ Curves connecting P.C.-P.I. & P.I.-P.T.; | 8 |  |  |  |  | 8 | Select
186 | Stage 2 |  |  |  | 9. Alignment, Equations, and Curve Data; | 9 |  |  |  |  | 9 | Select
187 | Stage 2 |  |  |  | 10. Route, or Street Name; | 10 |  |  |  |  | 10 | Select
188 | Stage 2 |  |  |  | 11. Section Corners Tie-ins identified (i.e. Section, 1/2, or 1/4 lines); | 11 |  |  |  |  | 11 | Select
189 | Stage 2 |  |  |  | 12. Existing R/W Line; | 12 |  |  |  |  | 12 | Select
190 | Stage 2 |  |  |  | 13. Proposed R/W Line & "R/W" noted; | 13 |  |  |  |  | 13 | Select
191 | Stage 2 |  |  |  | 14. Temp. R/W, R/W Line & "Temp. R/W for ….."; | 14 |  |  |  |  | 14 | Select
192 | Stage 2 |  |  |  | 15 Owner Names; | 15 |  |  |  |  | 15 | Select
193 | Stage 2 |  |  |  | 16. Property Boundaries; | 16 |  |  |  |  | 16 | Select
194 | Stage 2 |  |  |  | 17. Legend w/ Designation Symbol and Name; | 17 |  |  |  |  | 17 | Select
195 | Stage 2 |  |  |  | 18. Existing ROW (i.e. Ex. R/W, App. R/W, etc.); | 18 |  |  |  |  | 18 | Select
196 | Stage 2 |  |  |  | 19. Utility Easement; | 19 |  |  |  |  | 19 | Select
197 | Stage 2 |  |  |  | 20. Drainage Easement; | 20 |  |  |  |  | 20 | Select
198 | Page 3 of 5
199 |  |  |  |  | MOT Traffic Maintenance Details
200 |  |  |  |  | MOT Sequence of Operations:
201 | Stage 1 |  |  |  | 1. The Conceptual Traffic-Maintenance Strategy and Phasing should be detailed. | 1 |  |  |  |  | 1 | Select
202 | Stage 2 |  |  |  | 2. Finalize all MOT detai including all pedestrian and bicycle MOT detail where required in accordance 503-3.0. | 2 |  |  |  |  | 2 | Select
203 | [11 empty] | Select
204 |  |  |  |  | Detour: | [6 empty] | Select
205 | Stage 1 |  |  |  | 1. Detour Route Map | 1 |  |  |  |  | 1 | Select
206 | Stage 1 |  |  |  | 2. Sign Legend | 2 |  |  |  |  | 2 | Select
207 | Stage 1 |  |  |  | 3. Summary of Detour Items Table | 3 |  |  |  |  | 3 | Select
208 | Stage 1 |  |  |  | 4. Sign, Route Markers | 4 |  |  |  |  | 4 | Select
209
210 |  |  |  |  | Pedestrian MOT
211 | Stage 2 |  |  |  | 1. Pedestrian Detour Route Details | 1 |  |  |  |  | 1 | Select
212 | Stage 2 |  |  |  | 2. Are TAC inquiries approved? | 2 |  |  |  |  | 2 | Select
213
214 |  |  |  |  | Plan and Profile Sheets
215 | Stage 1 |  |  |  | 1. Existing Topography with Topo Notes for 3R or 4R Projects, not required for Partial 3R Projects. | 1 |  |  |  |  | 1 | Select
216 | Stage 1 |  |  |  | 2. Survey Reference Ties and Benchmark Data. | 2 |  |  |  |  | 2 | Select
217 | Stage 1 |  |  |  | 3. Begin and End of Project, Begin and End Construction (along S-Lines), Begin and End Incidental Construction. | 3 |  |  |  |  | 3 | Select
218 | Stage 1 |  |  |  | 4. Right of Way & Property Lines. | 4 |  |  |  |  | 4 | Select
219 | Stage 1 |  |  |  | 5. Horizontal Alignment (e.g., Horizontal Curve Data, PC, PI, PT, Bearings). | 5 |  |  |  |  | 5 | Select
220 | Stage 1 |  |  |  | 6. Vertical Alignment and its relationship to grade-controlling features. (i.e. bridge clearance) | 6 |  |  |  |  | 6 | Select
221 | Stage 1 |  |  |  | 7. Preliminary Drainage Design including mainline culverts and ditch grades, only if they determine Profile. | 7 |  |  |  |  | 7 | Select
222 | Stage 1 |  |  |  | 8. Preliminary Public Road Approach and Drive Locations. | 8 |  |  |  |  | 8 | Select
223 | Stage 1 |  |  |  | 9. Alignment Controlling Features (e.g., high-water levels, existing crossroads and bridges, regulated drains, drainage structures, railroads, underdrain criteria, traffic-maintenance considerations, cemeteries, historical buildings, parks, ADA requirements, public building access, etc.). | 9 |  |  |  |  | 9 | Select
224 | Stage 1 |  |  |  | 10, Conceptual Locations of ADA Curb Ramps, other ADA Features, noting any potential challenges where coordination with TAC Committee is anticipated. | 10 |  |  |  |  | 10 | Select
225 | Stage 1 |  |  |  | 11. If no Stage 2 Submittal is planned, then the ADA Pedestrian Detour Routes should be detailed at Stage 1. | 11 |  |  |  |  | 11 | Select
226 | Stage 1 |  |  |  | 12. Proposed Guardrail Limits; Type & Limit. | 12 |  |  |  |  | 12 | Select
227 | Stage 2 |  |  |  | 13. Drainage Features (e.g. storm sewers, pipe structures, ditch grades with elevations, preliminary inlet spacing for storm-sewer trunk line design, etc.) and proposed drainage notes. Provide ditch sodding paved side ditch, and riprap limits and quantities. | 13 |  |  |  |  | 13 | Select
228 | Stage 2 |  |  |  | 14. Construction Limits. | 14 |  |  |  |  | 14 | Select
229 | Stage 2 |  |  |  | 15. Proposed Right of Way, including Temporary Right of Way. | 15 |  |  |  |  | 15 | Select
230 | Stage 2 |  |  |  | 16. Public-Road Approach and Drive Locations with callouts. | 16 |  |  |  |  | 16 | Select
231 | Stage 2 |  |  |  | 17. Provide note showing limits of location and types of Roadside Barrier. | 17 |  |  |  |  | 17 | Select
232 | Stage 2 |  |  |  | 18. Permanent Erosion Protection, including Paved Side Ditches, Riprap, and Sodding Limits. | 18 |  |  |  |  | 18 | Select
233 | Stage 3 |  |  |  | 19. Show Earthwork Balance Box. | 19 |  |  |  |  | 19 | Select
234
235 |  |  |  |  | Detail Sheets
236 | Stage 1 |  |  |  | 1. Superelevation Diagrams. | 1 |  |  |  |  | 1 | Select
237 | Stage 1 |  |  |  | 2. For Grade Controlling Structures, provide a Detail Sheet that shows the General Layout and Cover Provided. | 2 |  |  |  |  | 2 | Select
238 | Stage 1 |  |  |  | 3. Preliminary pavement marking detail sheets for projects with any lane delineation for lane shifts, turn lanes, tapers, TWTL, auxiliary lanes, etc. | 3 |  |  |  |  | 3 | Select
239 | Stage 2 |  |  |  | 4. Stormwater Management | 4 | [5 empty] | Select
240 | Stage 2 |  |  |  | 5. Modified Approaches. | 5 |  |  |  |  | 4 | Select
241 | Stage 2 |  |  |  | 6. Intersection Layout Details including Right and Left Turn Lanes with the Turning Movements indicated. | 6 |  |  |  |  | 5 | Select
242 | Stage 2 |  |  |  | 7. Pavement Marking Detail Sheets for Projects, Mainline or S-Line, with any lane delineation complexity showing turn lanes, tapers, auxiliary lanes, begin/end of project, lane and median widths with accompanying transition stations. | 7 |  |  |  |  | 6 | Select
243 | Stage 2 |  |  |  | 8. Special Drainage Structures. | 8 |  |  |  |  | 7 | Select
244 | Stage 2 |  |  |  | 9. Finalize ADA Curb Ramp and Sidewalk Details. | 9 |  |  |  |  | 8 | Select
245 | Stage 2 |  |  |  | 10. Signs, Sign Structures, Lighting, and Signals, where applicable. Traffic Items should be submitted into ERMS to INDOT Traffic for review. | 10 |  |  |  |  | 9 | Select
246 | Stage 3 |  |  |  | 11. Culvert/Structure Detail | 11 |  |  |  |  | 10 | Select
247 | Stage 3 |  |  |  | 12. Wall Detail (Noise, Retaining walls, MSE, & Wingwalls) | 12 |  |  |  |  | 11 | Select
248 | Stage 3 |  |  |  | 13. Spot Elevations | 13 |  |  |  |  | 13 | Select
249 | Stage 3 |  |  |  | 14. Erosion Control | 13 |  |  |  |  | 13 | Select
250 | Page 4 of 5
251 |  |  |  |  | Interchange Geometrics
252 | Stage 1 |  |  |  | 1. Interchange geometric sheet including all horizontal curve data | 1 |  |  |  |  | 1 | Select
253 | Stage 1 |  |  |  | 2. Ramp profile sheets | 2 |  |  |  |  | 2 | Select
254 | Stage 1 |  |  |  | 3. Mainline and crossroad alignments | 3 |  |  |  |  | 3 | Select
255 | Stage 1 |  |  |  | 4. Traffic elements ( Sign structures and signals, etc.) | 4 |  |  |  |  | 4 | Select
256 | Stage 1 |  |  |  | 5. Design Information. | 5 |  |  |  |  | 5 | Select
257
258 |  |  |  |  | Temporary Erosion Control Plans
259 | Stage 3 |  |  |  | - Include completed Temporary Erosion and Sediment Control Details. | [6 empty] | Select
260
261 |  |  |  |  | Tables
262 |  |  |  |  | Stage 2 Tables shown below should be provided and partially completed.
263 | Stage 2 |  |  |  | 1. Pavement Quantities and Approach Table. | 1 |  |  |  |  | 1 | Select
264 | Stage 2 |  |  |  | 2. Structure Data Table. Include stationing, elevation, and structure number. | 2 |  |  |  |  | 2 | Select
265
266 |  |  |  |  | Stage 3 Tables: All table (shown below and any other required) should be submitted and completed.
267 | Stage 3 |  |  |  | 1. Approach Table. | 1 |  |  |  |  | 1 | Select
268 | Stage 3 |  |  |  | 2. Curb Ramp Table. | 2 |  |  |  |  | 2 | Select
269 | Stage 3 |  |  |  | 3. Drainage Structure Data | 3 |  |  |  |  | 3 | Select
270 | Stage 3 |  |  |  | 4. Earthwork Summary. | 4 |  |  |  |  | 4 | Select
271 | Stage 3 |  |  |  | 5. Guardrail Summary | 5 |  |  |  |  | 5 | Select
272 | Stage 3 |  |  |  | 6. Mailbox Table | 6 |  |  |  |  | 6 | Select
273 | Stage 3 |  |  |  | 7. Miscellaneous Table | 7 |  |  |  |  | 7 | Select
274 | Stage 3 |  |  |  | 8. Maintainance-of-Traffic Items | 8 |  |  |  |  | 8 | Select
275 | Stage 3 |  |  |  | 9. Monument Table | 9 |  |  |  |  | 9 | Select
276 | Stage 3 |  |  |  | 10. Pavement Marking Table | 10 |  |  |  |  | 10 | Select
277 | Stage 3 |  |  |  | 11. Pavement Patching Table | 11 |  |  |  |  | 11 | Select
278 | Stage 3 |  |  |  | 12. Paved Side Ditch | 12 |  |  |  |  | 12 | Select
279 | Stage 3 |  |  |  | 13. Pipe Material Tables | 13 |  |  |  |  | 13 | Select
280 | Stage 3 |  |  |  | 14. Right-of-Way Marker Table | 14 |  |  |  |  | 14 | Select
281 | Stage 3 |  |  |  | 15. Riprap Ditch and Sodding Table | 15 |  |  |  |  | 15 | Select
282 | Stage 3 |  |  |  | 16. Sign & Post Summary Table | 16 |  |  |  |  | 16 | Select
283 | Stage 3 |  |  |  | 17. Erosion Control / Water Quality Table | 17 |  |  |  |  | 17 | Select
284 | Stage 3 |  |  |  | 18. Underdrain Table | 18 |  |  |  |  | 18 | Select
285
286 |  |  |  |  | Cross Sections
287 | Stage 1 |  |  |  | 1. Templates of the Typical Sections placed on the Existing Cross Sections. | 1 |  |  |  |  | 1 | Select
288 | Stage 1 |  |  |  | 2. Profile Grade Elevations. | 2 |  |  |  |  | 2 | Select
289 | Stage 1 |  |  |  | 3. Mainline Open Channel Crossing Drainage Structures. | 3 |  |  |  |  | 3 | Select
290 | Stage 2 |  |  |  | 4. Templates of the Typical Sections placed on the Existing Cross Sections showing Side Ditches & R/W. | 4 |  |  |  |  | 4 | Select
291 | Stage 2 |  |  |  | 5. Show Drainage Structures w/ Structure Numbers and Stationing. | 5 |  |  |  |  | 5 | Select
292 | Stage 2 |  |  |  | 6. Show Type of Approaches and Drives including Stationing. | 6 |  |  |  |  | 6 | Select
293 | Stage 3 |  |  |  | 7. Add Proposed Earthwork to the Cross Sections. | 7 |  |  |  |  | 7 | Select
294 | Stage 3 |  |  |  | 8. Show and Quantify any necessary Benching. | 8 |  |  |  |  | 8 | Select
295
Page 5 of 5

## Status Sheet
Status Sheet
1 - 3 | Date: |  |  |  | RFC Date: |  |  | Letting:
1 - 3 | Contract No.: |  |  |  | Des. No.:
1 - 3 | Route: |  |  |  | Stage: | Select a "Stage".
1 - 3 | Company: |  |  |  | Designer:
PLANS
| Items | [5 empty] | Response |  | Comments
Stage 1 | 1 | Engineers/Scope Report |  | Date Approved /Amended: |  |  | Click to Select
Stage 2 | 2 | Hydraulic Review |  | Date Approved: |  |  | Click to Select
Stage 3 | 3 | Geotechnical |  | Date Approved: |  |  | Click to Select
Stage 3 | 4 | Pavement Design |  | Date Approved: |  |  | Click to Select
Stage 2 | 5 | Are pedestrian facilities designed in accordance with the PROWAG? |  |  |  |  | Click to Select
Stage 2 | 6 | If existing pedestrian facilities are impacted during construction, does the MOT address alternate routes for pedestrians? |  |  |  |  | Click to Select
Stage 3 | 7 | - If "Yes", have all issues been approved by TAC? |  | Date Approved: |  |  | Click to Select
Stage 3 | 8 | For any project on or over an Interstate, is an Interstate Highway Congestion Policy (IHCP) exception required? |  |  |  |  | Click to Select
|  | - If “Yes”, date approved: |  | Date Approved:
|  | Are the IHCP exception approved lane closure and mitigation requirements included in the contract documents? |  |  |  |  | Click to Select
Stage 2 | 9 | Does the project involve new or modified Interstate access and require an Interstate Access Document (IAD)? |  |  |  |  | Click to Select
|  | - If “Yes”, date FHWA approved: |  | Date Approved:
Stage 1 | 10 | Is the Level 1 Checklist submitted? |  |  |  |  | Click to Select
Stage 2 |  | Are there Level 1 Design Exceptions for the project? |  |  |  |  | Click to Select
Stage 3 |  | Are the Level 1 Design Exceptions approved? |  |  |  |  | Click to Select
Stage 1 |  | List Level 1 Design Exceptions (DE) |  |  |  | Approval Dates
|  | Design Criteria (select all that apply) |  |  |  | INDOT | MOT | FHWA
Design Speed
Lane Width
Shoulder Width
Design Loading Structural Capacity
Horizontal Curve-Minimum Radius
Stopping Sight Distance-Horizontal Curve
Stopping Sight Distance-Vertical Curve
Maximum Grade
Travel Lane-Cross Slope
Superelevation Rate
Minimum Vertical Clearance
ADA
Stage 3 | 11 | If non-participating items are included in the project, are they listed separately with an asterisk in the construction estimate? |  |  |  |  | Click to Select
Stage 3 | 12 | Are proprietary items included in the contract documents? |  |  |  |  | Click to Select
|  | - If “Yes”, has their use been approved? |  |  |  |  | Click to Select
GENERAL COMMENTS

## PullDownData (hidden)
INDOT "Stage" List: | INDOT District Information Pull Down Menu List: | Work Type Pull Down Menu List: | Project Design Criteria Pull Down Menu List: | Accept Pull Down Menu List: | Functional Classification
Select a "Stage". | Select a "District". | Select a "Work Type". | Select a "Project Design Criteria". | Select | Select a "Functional Classification".
Stage 1 | Crawfordsville | Access Control | New Construction / Reconstruction | Accept | Principal Arterial - Expressway or Freeway
Stage 2 | Greenfield | ADA Sidewalk Ramp | Existing Freeway (3R) / 4(R) Partial Reconstruction | Dismiss | Principal Arterial - Other, Urban
Stage 3 | Fort Wayne | Added Travel Lanes | Existing Non-Freeway (3R) | n/a | Principal Arterial - Other, Rural
Final Tracings | LaPorte | Added Travel Lanes, Construct Turn Lanes | Partial 3R |  | Arterial, Rural
Other | Seymour | Added Travel Lanes, HMA | Other |  | Arterial, Urban
| Vincennes | Arch Reconstruction or Repair |  |  | Collector, Rural
| Central Office | Asphalt Patching |  |  | Collector, Urban
| Other | Auxiliary Lane Construction |  |  | Local Road, Rural
|  | Auxiliary Lane, Passing |  |  | Local Road, Urban
|  | Auxiliary Lane, Two-way Left Turn Lanes |  |  | Other
Auxiliary Lane, Truck Climbing Lanes
Barrier Wall
Bike Pedestrian Facilities
Box Culvert Replacement
Centerline & Edge Line Rumble Stripes Installation
Centerline Rumble Stripes Installation
Chanel Clearing and Proection
Cold-in-Place Recycling
Concrete Pavement Preservation (CPP)
Concrete Pavement Restoration (CPR)
Covered Bridge Rehabilitation
Crack Sealing
Culvert Clean and Repair
Curve Correction
Curve Sign and Marking Visibility Improvements
Debris Removal from Channel
Demolition
Demolition, Remove Building, Foundations
District Wide Bridge Maintenance
Ditch Relocation
Drainage Ditch Correction
Enhancement
Environmental Mitigation
Erosion Control
Fence Replacement
Full Depth Reclamation
Guardrail Attenuators, New or Modernize
Guardrail, Maintenance
Herbicide Treatment
Historical Site Preservation
HMA Overlay Minor Structural
HMA Preventative Maintenance
HMA Overlay, Structural
Install Lighting
Install New Cable Rail Barriers
Install New Guardrail
Institution & Park Road Maintenance
Interchange Modification
Interchange Modification, Multi-Level
Intersect. Improv. w/Added Turn Lanes
Intersect. Improv. w/ Signals
Intersection Improvement
Intersection Improvement, Median U-Turn
Intersection Improvement, Roundabout
Landscaping
Lighting Installation/Maintenance
Median Construction
New Interchange Construction
New Road Construction
New Road Construction, HMA
New Signal Installation
New Traffic Flow Detection Devices/Hardware
Noise Abatement
Other Intersection Improvement
Other Roadside Maintenance
Other Type Project (Miscellaneous)
Overhead Sign Install
Overhead Sign Repair
Parking Area Reconstruction
Partial 3-R
Patch & Rehab. Bituminous Pavement
Patch & Rehab. Pavement
Pavement Markings
Pavement Patching
Pavement Repair or Rehabilitation
Pavement Replacement
Pavement Replacement, HMA
Pavement Replacement, New PCC
Pavement, Other
PCC Thin Overlay
PCCP Cleaning and Sealing Joints
Pedestrian Flashing Beacons, Installed
Protective Buying Pumping/Lift Stations
Radii Improvement
Railing Replace or Repair
Railroad Crossing Removal
Railroad Protection
Rais Bridge/Lower Pavement
Raised Pavement Markings, Refurbished
Repair or Replace Barrier Wall
Repair or Replace Joints
Repair or Replace Lighting
Repairs to Approach Slab
Rest Area Modernization
Road Rehabilitation (3R/4R Standards)
Road Reconstruction (3R/4R Standards)
Retaining Wall Repair or Replacement
Roadside Maintenance
Safety Revisions
Scour Protection (Erosion)
Sewer.Curb.Gutter Construction
Shoulder Rehabilitation
Sight Distance Improvement
Sign Modernization (Series of Units)
Signing
Signing Installation/Repair
Signs, Lighting, Signals & Markings
Single Location Bridge Inspection
Slide Correction
Slotted Drain of Inlet Replacement
Small Structure, New
Small Structure, Maintenance and Repair
Small Structure, Paved Invert
Small Structure, Pipe Lining
Small Structure, Replacement
Small Structure, Replacement with Bridge
Small Structure & Drains Construction
Storm Sewer Repair & Rehabilitation
Straighten Beam
Substructure Repair & Rehabilitation
Surface Treatment, Microsurface
Surface Treatment, Ultra-Thin Bonded Wearing …
Traffic Signal, Maintenance
Traffic Signal, Repair
Traffic Signal, Visibility Improvements
Traffic Signals
Traffic Signal, Modernization
Traffic Signal, New or Modernized
Traffic Signal, Other
Tree Removal/Trimming
Utility Relocation
Vertical Sight Correction
Wedge and Level
Weight Station Constr./Reconstr.
Other