## Sheet1
ITEM | Item Value | Status Report |  | Percent
| Percent | Last Report | This Report | Complete
Review Survey Notes | 0.5 |  |  | 0
Plot, Check & Ink Topo for Plan & Profile | 3 |  |  | 0
Plot & Check Original Cross Sections | 2.5 |  |  | 0
Plot & Check Topo on Layout Sheet | 1.5 |  |  | 0
Prepare Preliminary Typical Cross Sections | 1 |  |  | 0
Prepare Preliminary Title Sheet | 0.5 |  |  | 0
Preliminary Plan Details | 9 | 0 | 0 | 0
Preliminary Guard Rail Design | 1.5 |  |  | 0
Design Preliminary Structure Geometrics on Layout | 2 |  |  | 0
Prepare Preliminary Channel Layout | 1 |  |  | 0
Prepare Preliminary Layout Sheet | 3 |  |  | 0
Economic Cost Analysis (Structure Type) | 3 |  |  | 0
Design Preliminary Grade | 1.5 |  |  | 0
Preliminary Drainage Design | 2 |  |  | 0
Grade Review and Structure Size & Type | 23 | 0 | 0 | 0
Revise Plans per Review | 1 |  |  | 0
Preliminary Approach, Drive & Intersection Details | 1.5 |  |  | 0
Preliminary Plot of Final Cross Sections | 1 |  |  | 0
Prepare Preliminary General Plan | 1.5 |  |  | 0
Preliminary Maintenance of Traffic | 1 |  |  | 0
Preliminary Plat #1 or #3 | 1 |  |  | 0
Preliminary Design Summary | 2 |  |  | 0
Preliminary R/W Design | 2 |  |  | 0
Preliminary Field Check Plans Submission | 34 | 0 | 0 | 0
Field Inspection | 1.5 |  |  | 0
Revised Plans per Field Check Review | 1 |  |  | 0
Final R/W Design & Plans | 2.5 |  |  | 0
Final R/W Plat #1 or #3 | 0.5 |  |  | 0
Finalize Typical Cross Sections | 0.5 |  |  | 0
Final Cross Sections | 2.5 |  |  | 0
Final Plan & Profile Sheets | 2.5 |  |  | 0
Finalize Title Sheet for R/W Plans | 0.5 |  |  | 0
Preliminary Approach Table | 1 |  |  | 0
Preliminary Construction Cost Estimate | 1 |  |  | 0
Final Approach, Drive & Intersection Details | 1 |  |  | 0
Design Hearing Plans & R/W Plans Submission | 48.5 | 0 | 0 | 0
Revise R/W Plans per Review | 0.5 |  |  | 0
R/W Tracings | 49 | 0 | 0 | 0
Hearing | 3 |  |  | 0
Revise Plans per Hearing & Agency Comments | 1.5 |  |  | 0
Foundation Selection | 0.5 |  |  | 0
Soil Boring Sheet | 0.5 |  |  | 0
Final Design Summary | 1 |  |  | 0
Preliminary Plans for Final Approval Submission | 55.5 | 0 | 0 | 0
Final Drainage Design | 1.5 |  |  | 0
Structure Data Sheet | 1.5 |  |  | 0
Superstructure Design & Details | 8 |  |  | 0
Screeds | 1 |  |  | 0
End Bent Design & Details | 5 |  |  | 0
Interior Substructure Design & Details | 8 |  |  | 0
Underdrain Design & Table | 1 |  |  | 0
Paved Side Ditch, Sodding & Sign Table | 1 |  |  | 0
Earthwork Computation & Balance | 2 |  |  | 0
Final Maintenance of Traffic | 2 |  |  | 0
Final Channel Change Layout | 1 |  |  | 0
Final General Plan | 2 |  |  | 0
Quantity Calculations | 2 |  |  | 0
Bridge Summary | 1 |  |  | 0
Preliminary Estimate of Quantities & Cost Estimate | 1.5 |  |  | 0
Finalize Title Sheet | 0.5 |  |  | 0
Preliminary Special Provisions | 0.5 |  |  | 0
Final Plan Submission | 95 | 0 | 0 | 0
Revise Plans per Final Plan Review | 3.5 |  |  | 0
Construction Cost Estimate & Estimate of Quantities | 1 |  |  | 0
Final Special Provisions | 0.5 |  |  | 0
Tracings Submission | 100 | 0 | 0 | 0