## Sheet1
ITEM | Item Value | Status Report |  | Percent
| Percent | Last Report | This Report | Complete
Review Survey Notes | 1 |  |  | 0
Plot, Check & Ink Topo for Plan & Profile | 5 |  |  | 0
Plot & Check Original Cross Sections | 3.5 |  |  | 0
Prepare Preliminary Typical Cross Sections | 2 |  |  | 0
Prepare Preliminary Title Sheet & Index Sheet | 5 |  |  | 0
Preliminary Plotting Complete | 16.5 | 0 | 0 | 0
Establish Grade Controls | 5 |  |  | 0
Design Preliminary Grade & Geometrics | 2 |  |  | 0
Preliminary Plot of Final Cross Sections | 2 |  |  | 0
Grade Review Submission | 25.5 | 0 | 0 | 0
Revise Plans per Grade Review | 2 |  |  | 0
Preliminary Plan & Profile | 1.5 |  |  | 0
Preliminary Drainage Design | 2 |  |  | 0
Preliminary Approach & Drive Details | 2 |  |  | 0
Preliminary Structure Data | 1 |  |  | 0
Preliminary Cross Sections | 2 |  |  | 0
Preliminary Maintenance of Traffic | 2 |  |  | 0
Preliminary Plat #1 or #3 | 1.5 |  |  | 0
Preliminary Detail Sheets | 2 |  |  | 0
Preliminary R/W Design | 1.5 |  |  | 0
Preliminary Field Check Plans Submission | 43 | 0 | 0 | 0
Field Inspection | 2 |  |  | 0
Revise Plans per Preliminary Field Check Review | 3 |  |  | 0
Final R/W Design & Plans | 3 |  |  | 0
Final R/W Plat #1 or #3 | 2 |  |  | 0
Preliminary Construction Cost Estimate | 1 |  |  | 0
Finalize Typical Cross Sections | 1.5 |  |  | 0
Final Cross Sections | 2.5 |  |  | 0
Final Plan & Profile Sheets | 3 |  |  | 0
Final Approach & Drive Details | 2 |  |  | 0
Final Intersection Details | 1.5 |  |  | 0
Preliminary Approach Table | 2 |  |  | 0
Finalize Title Sheet for R/W Plans | 1 |  |  | 0
Design Hearing Plans and R/W Plans Submission | 67.5 | 0 | 0 | 0
Revise R/W Plans per Review | 0.5 |  |  | 0
R/W Tracings | 68 | 0 | 0 | 0
Design Hearing, Preparation & Attendance | 1 |  |  | 0
Design Approval | 69 | 0 | 0 | 0
Revise Plans per Design Hearing | 2 |  |  | 0
Final Drainage Design | 2 |  |  | 0
Structure Data Sheet | 2 |  |  | 0
Underdrain Design & Table | 3 |  |  | 0
Paved Side Ditch & Sodding Table | 2 |  |  | 0
Earthwork Computations / Balance/Mass Diagram | 2 |  |  | 0
Final Maintenance of Traffic | 2.5 |  |  | 0
Prepare Sign Table | 0.5 |  |  | 0
Final Field Check Plans | 85 | 0 | 0 | 0
Final Field Check Held | 2 |  |  | 0
Revise Plans per Field Check | 3 |  |  | 0
Quantity Calculations | 2 |  |  | 0
Preliminary Estimate of Quantities & Cost Estimate | 1.5 |  |  | 0
Preliminary Special Provisions | 1.5 |  |  | 0
Final Check Prints | 95 | 0 | 0 | 0
Revise Plans per Final Check | 3 |  |  | 0
Construction Cost Estimate & Estimate of Quantities | 1 |  |  | 0
Final Special Provisions | 1 |  |  | 0
Tracings Submission | 100 | 0 | 0 | 0