# 108-C-127 EARLIEST DATE TO BEGIN WORK

(Revised 10-20-16)

The Standard Specifications are revised as follows:

SECTION 108, AFTER LINE 611, INSERT AS FOLLOWS:

(e) Earliest Date to Begin Work

For a contract for which the completion time is a specified number of work days, calendar days, or is a calendar completion date, the earliest date to begin work will be as agreed upon by the Contractor and the Engineer. Such date shall not be earlier than the date shown on the Proposal sheet. If the Contractor begins work before the earliest date to begin work as shown on the Proposal sheet, $      will be assessed as liquidated damages, not as a penalty, but as damages sustained, for each workable calendar day on which the Contractor does work. Time will then be charged in accordance with 108.03.

Preliminary field work, such as the placement of construction signs, staking, or verifying cross sections necessary to obtain information to initiate procurement of materials with lengthy delivery schedules, will not constitute work warranting time charges.

Requests for extensions to completion dates or intermediate completion dates due to delay in issuance of the notice to proceed beyond 30 days after the letting will not be considered unless the notice to proceed is issued less than 14 calendar days prior to the earliest date to begin work stated in the contract on the Proposal sheet.