# 108-C-093 FAILURE TO COMPLETE ON TIME FOR ROAD CLOSURE

*(Revised 04-25-21)*

The Standard Specifications are revised as follows:

SECTION 108, AFTER LINE 598, INSERT AS FOLLOWS:

 *The work specified shall be arranged and prosecuted such that* *is closed to traffic for not longer than the number of consecutive calendar days shown on the Proposal sheet. The road shall not be closed before* *, 20**.*

 *If the necessary work is not completed and* *is not reopened to traffic within the number of calendar days for closure shown on the Proposal sheet, $**will be assessed as liquidated damages, not as a penalty, but as damages sustained for each calendar day for which* *remains closed to traffic in excess of the number shown on the Proposal sheet.*

 *Extension of contract time, if required, shall be in accordance with 108.08.*