# 105-C-247 BRIDGE INSPECTION COORDINATION

(Revised 09-18-25)

The following bridge inspections are due to be performed by the Department’s Bridge Inspection Office, or its authorized representative, on each bridge within the construction limits of the contract.

| Bridge Name1 | Bridge Number2 | ## Location | Inspection Type | Last Inspection Date (MM/DD/YY) | Inspection Interval (Mos.) | First Scheduled Inspection (MM/YY) | Second Scheduled Inspection (MM/YY) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 Bridge Name is the Asset Name [example: I70-154-10118 EBL] 2 Bridge Number is the unique Asset Number previously referred to as the NBI number |  |  |  |  |  |  |  |

Each bridge inspection shall be included in the schedule of work in accordance with 108.04. Notice will be given no less than seven days prior to each bridge inspection. Access, coordination, and cooperation for the required bridge inspections shall be in accordance with 105.05.

The Department’s onsite Engineer will notify the Department’s Bridge Inspection Office by email seven days prior to any temporary bridge opening to traffic. The temporary bridge shall be complete in place for two days prior to opening to traffic to allow time for inspection. The notification will be directed to inbridgeshelp@indot.IN.gov, and copied to LoadRating@indot.IN.gov. The email notification will include the Contract Number, Des Number of the permanent bridge under construction if applicable, NBI Number of the existing bridge and “Temporary Bridge Inspection Request” in the subject line.

The Department’s onsite Engineer will notify the Department’s Bridge Inspection Office by email seven days prior to moving traffic to a newly constructed or altered portion of a structure during a maintenance of traffic phase change. The phase shall be complete in place for two days prior to opening to traffic to allow time for inspection. The notification will be directed to inbridgeshelp@indot.IN.gov, and copied to LoadRating@indot.IN.gov. The email notification will include the Contract Number, Des Number of the permanent bridge under construction if applicable, NBI Number of the existing bridge and “Safety Inspection Request” in the subject line.

The Department’s onsite Engineer will notify the Department’s Bridge Inspection Office by email seven days prior to opening the full bridge structure to traffic. The bridge shall be complete in place for two days prior to opening to traffic to allow time for inspection. The notification will be directed to inbridgeshelp@indot.IN.gov, and copied to LoadRating@indot.IN.gov. The email notification will include the Contract Number, Des Number of the permanent bridge under construction if applicable, NBI Number of the existing bridge and “Initial Inspection Request” in the subject line.