## 1. INSTRUCTIONS
INSTRUCTIONS
This is the first of five sheets in this Excel workbook. This first sheet contains instructions for completing the tracker, the second sheet contains the fillable project tracker sheet. The third sheet contains the fillable financial summary sheet, and the fourth and fifth sheets contain examples of the Project Tracker and Financial Summary.
1) Open the "PROJECTS" worksheet (second tab) highlighted in blue and complete the following:
a) This sheet is prepopulated with information from the state’s previously submitted Project Trackers (e.g. 2022), as well as information from CMS Location on recently approved projects. Review the "prepopulated projects" for accuracy and provide updates, as necessary. Please specify any changes in Column M. Additionally, states are required to provide either interim or final project results, as appropriate, in Column J, see below for directions. b) Add any missing projects on a new row and complete all required fields for the "added projects".
State (Column A) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, this field should only be populated with the value that is available in the drop-down selection.
CMS Location (Column B) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, this field should only be populated with the value that is available in the drop-down selection.
Unique Identifier (Column C) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, this field should only be populated with the identifier provided by CMS. Please provide a copy of the CMS approval letter for any projects added to the spreadsheet. c) If adding a continuation or extension project, please enter the project into a separate row with it's assigned UID. DO NOT enter information into the same row as the original project used as the model for the continuation or extension.
Project Start Date (Column D) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) Enter the start date of the project (i.e., the date that funding started). DO NOT enter the date the project was approved for funding. The project may have been approved months before funding began; only enter the date when the funding officially started. Please follow the format (MM/DD/YYYY). Example: 06/10/2022. If the specific date is not known, use the first of the month: 06/01/2022.
Project End Date (Column E) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) Enter the end date of the project. Whenever possible, please include specific dates, not just the month and year. Please follow the format (MM/DD/YYYY). Please indicate in Column M if the project was approved to receive a no-cost extension due to the impacts of the COVID-19 Pandemic on the project activities. Example: 09/25/2022 If the specific date is not known, use the first of the month: 10/01/2022.
Total Amount of CMP Funds Approved for this Project (Column F) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, please add the total amount from the CMS project approval letter.
Project Title (Column G) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, please add the Project Title from the CMS project approval letter.
Project Summary (Column H) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, enter the following project summary information: a) Specific purpose of the project; b) Description of project's measurable goals and/or objectives; c) Explanation of how the project will benefit nursing home (NH) residents; b) Target audience beyond NH residents (i.e., NH staff, caregivers, family councils), if applicable. Please follow the format in the example below. Project ABC's Creative Storytelling will train and certify 50 nursing homes in improvisational storytelling to reduce challenging behaviors and antipsychotic medication use by 10%. c) In addition to improving communication, social connectedness the project will facilitate positive engagement between staff and residents. d) 50 nursing homes in the state. c) Please indicate if the project is an extension or a continuation of a previously approved CMP project.
Funded Entities (Column I) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, list each entity that will directly receive CMP funds for this project (i.e., if funds are being given directly to a nursing home, or non-nursing home entity such as an individual consultant, vendor, or academic institution, please list the name of the entity). DO NOT include the names of subcontracted entities. Example: Project ABC Creative Storytelling, Inc.
Results/Outcomes of the Project (Column J) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. Final project results must be entered for all projects that have been completed. Interim project results must be entered for all ongoing projects. b) For added projects, describe the project's interim or final results and outcomes of the project. Include a brief summary of the specific goals that were met/not met, as well as any other benefits resulting from the project. Reference quantitative measures that reflect goals of the project. If the project is ongoing after the date in which the state submits the Project Tracker, indicate "Results Pending" in Column J. Example: Project ABC recruited 50 nursing homes to engage in training for the ABC program to improve resident communication and social connectiveness. The project outcomes show a 10% reduction in residents exhibiting signs or symptoms of depression, challenging behaviors, and use of antipsychotic medication as well as a 20% in enjoyment of activities and social interaction.
Total Amount of CMP Funds Expended During CY 2021 (Column K) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, enter the total amount expended during CY 2021. If this is a multi-year project or a project that is one year or less but spans multiple years (e.g., 11/05/2019 - 11/04/2022), please enter the funds that were used during calendar year 2021. Example: $50,000.00
Total Amount of CMP Funds Expended During CY 2022 (Column L) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, enter the total amount spent on this project during CY 2022. If this is a multi-year project or a project that is one year or less but spans multiple years (e.g., 11/05/2019 - 11/04/2022), please enter the funds that were used during calendar year 2022. Example: $50,000.00
Notes (Column M) Please use this column to request changes to information in the prepopulated rows for the columns that are locked for editing. Any other data in the notes column will not be included in the final Project Tracker on the CMPRP webpage.
2) Open the "FINANCIAL_SUMMARY” worksheet (third tab) highlighted in orange and complete the following:
a) The state must add information to all four highlighted fields on this tab. Failure to provide this information will result in the file being returned to the state. If the total amount is zero, enter "$0." b) Validate financial information highlighted in blue, which is described below.
CMP Funds Balance as of 01/01/2022 (Obligated and Available) (Column B) Enter the amount that was obligated and available for use as of 01/01/2022 for the state.
CMP Funds Expended for Administrative Uses in CY 2022 (Column C) Enter the actual amount of CMP funds spent for administration in 2022.
CMP Funds Expended for Emergency Uses in CY 2022 (Column D) Enter the actual amount of CMP funds spent for emergencies in 2022.
CMP Funds Added During CY 2022 (Column F) Enter the actual amount of CMP funds that were added to the state's total balance in 2022. Note that the state was required to report the anticipated CMP funds returned to the state in 2022 as part of the CY2023 State Plan submission process.
CMP Funds Spent During CY 2022 on CMP Projects (Column E) This cell will auto-populate with the total amount of CY 2022 funds listed in the projects from tab 3, "PROJECTS," Column L.
CMP Funds Balance as of January 1, 2023 (Column G) This cell will auto-calculate by subtracting expended administrative, emergency and project funds from the CMP Funds Balance as of 01/01/2022, and adding CMP funds added during CY 2022. This balance will not include funds expended from Communicative Technology (CT) or Visitation Aid (VA) applications.
3) Save and send the Project Tracker spreadsheet to the CMPRP mailbox (CMP-Info@cms.hhs.gov) by 02/1/2023
*Please reach out to the CMPRP Team with any questions by contacting the mailbox at: CMP-Info@cms.hhs.gov

## 2. PROJECTS
FILLABLE TRACKER
Tracker Calendar Year (CY)
State | CMS Long-Term Care Location | Unique Identifier | Project Start Date (Please review and edit the values in this field, as applicable) | Project End Date (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Approved for this Project | Project Title | Project Summary (Please review and edit the values in this field, as applicable) a) Specific purpose of the project b) Description of what the project will achieve c) Explanation of how the project will benefit nursing home (NH) residents d) Target audience beyond NH residents, if applicable | Funded Entities (Please review and edit the values in this field, as applicable) | Results/Outcomes of the Project (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Expended on Projects During CY 2021 (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Expended on Projects During CY 2022 (Please review and edit the values in this field, as applicable) | Notes (Please add an applicable information upon your review)
IN | Chicago | IN-0319-ISDH-243 | 2020-10-01 | 2022-09-30 | 497025 | Indiana Healthcare Leadership Conference Project | a) The project will implement two healthcare conferences during the calendar years 2021 and 2022, providing an opportunity for long term care leaders to improve the care to their residents. b) At each conference healthcare leaders will hear current evidence-based practices on quality of life and quality of care concerns and will receive materials that can be used to educate staff, residents and/or families. c) Participants will be able to implement best practices from conference information that will improve both the quality of care and quality of life for residents. Conference materials will be provided that can easily be implemented in a timely manner. d) The target audience is all long-term healthcare workers. The project was revised due to the impacts of the COVID-19 pandemic and the inability to host a large in-person conference during most of the original timeframe. | Travel Leader/ Brookshire Management | The 2021 long-term care Healthcare Leadership Conference, titled "Moving Forward & Recognizing Concerns" was held with 539 long term care healthcare workers attending virtually and Indiana Department of Health (IDOH) survey staff attending in person. Topics covered were: Reflecting on the COVID-19 pandemic, Acute and Chronic Wounds, Wound Care Treatment Options, Wound Rounds and Infection Control, and Long Term Care (LTC) Looking into the Future. The 2022 Healthcare Leadership Conference was titled, "Mental Health Challenges in Long-term Care - Working Together for Solutions." There were 700 attendees split almost evenly between in-person and virtual attendees. A representative from SAMHSA (Substance Abuse and Mental Health Services Agency) spoke at this conference, which aligned with CMS" focus on mental health in long-term care and SAMHSA's involvement in that initiative. For both conferences, over 90% of responses to the evaluations indicated the presentations were useful, the content was good, very good or excellent, and the presenters' knowledge of the topic was good, very good or excellent. | 82013.24 | 16393.6
IN | Chicago | IN-1219-ARS-497 | 2020-07-01 | 2023-06-30 | 1062432 | Accelerated Antimicrobial Stewardship for "At Risk" Skilled Nursing Facilities: Reducing the Impact of Multidrug Resistant Organisms (MDROs) and C. difficile on Resident Quality of Life | a) The project's training will reduce the prevalence of Multi-Drug Resistant Organisms (MDRO) and Clostridium difficile (C-diff) colonization's and infections in skilled nursing facilities through an effective Antimicrobial Stewardship Program (ASP). b) The ASP will be implemented in 10 identified "at risk" facilities yearly for 3 years and will include educational webinars for prescribers, nursing and pharmacy staff on optimal antimicrobial prescribing and the treatment of specific infectious diseases with a focus on improving the residents care and reducing complications. Regular one-on-one interactions between skilled nursing facility appointed contacts will be conducted and include case reviews, therapy optimization and follow up referrals to physicians and specialists. Education related to ASP for residents and families will also be provided. c) The combination of a comprehensive ASP and a targeted focus on education incorporates facility specific data that will enhance the resident care and improve the quality of life by reducing inappropriate use of antimicrobials adn infectious diseases diagnostic and monitoring tests in the specific facilities. Expected outcomes are to reduce the incidence of C. difficile colonization and infection by 15% across the residents in the enrolled facilities and to reduce the incidence of Multi-Drug Resistant Organism (MDRO) colonziation and infection by 15% across the residents in the enrolled facilities. d) The target audience will include healthcare workers, residents, and families. | Antimicrobial Resistance Solutions, Inc. (ARS) | Eight facilities were enrolled the first year of the project. Recruitment challenges encountered included limited or no response from the facilities, contracting delays with facilities, especially those with corporate affiliations and data acquisition from multiple facilities' vendors delayed due ot request process, timeline, uncommon request for information and data mining.Ten facilities were enrolled the second year of hte project. Education, one-on-one interactions, case reviews, therapy optimization and referrals to physicians and specialists were provided as planned. Data has not yet been provided on the expected outcomes to reduce the incidence of C. difficile colonization and infection by 15% and to reduce the incidence of Multi-Drug Resistant Organism (MDRO) colonziation and infection by 15% across the residents in the enrolled facilities. Those results are pending. | 275549.7 | 117545.04
IN | Chicago | IN-1221-UIN-884 |  |  | 393364 | Virtual Education to Improve Quality of Care in Long-Term Care | a) This project will increase the number of long-term care professionals with certificates of training in abuse and neglect prevention, emergency and disaster management and pressure ulcer prevention. b) Participants will improve their knowledge, skills and abilities related to the prevention of abuse and neglect, emergency and disaster preparedness and management and prevention of pressure ulcers. The training seeks to ensure that facilities have the resources and tools necessary to provide a high quality of healthcare. c) The ultimate goals is to benefit residents through the prevention of abuse and neglect, prevention of pressure ulcers and emergency and disaster preparedness and management. d) The training will be offered to administrative and nursing staff and facility education leaders. | University of Indianapolis Center for Aging and Community |  | 0 | 0 | Project will start in 2023. The CMPRP Team will delete this row from the tracker since it is not relevant to CY 2022.
IN | Chicago | IN-1221-VWPM-885 | 2022-08-01 | 2025-07-31 | 198216 | Indiana's Wound Care Excellence Program for Skilled Nursing Facilities | a) The Indiana Wound Care Excellence Program for Skilled Nursing Facilities was created to help increase the wound care knowledge for nurses working at CMS Certified Facilities in Indiana. b) This program will provide wound care certification for 280 nurses. c) Having wound care certified nursing in facilities will improve the quality of care of nursing home residents. d) One nurse from up to 280 nursing homes in Indiana are eligible for this training and certification. | Vohra Wound Physicians Management, LLC ("Vohra Wound Physicians") | Results pending. | 0 | 0
IN | Chicago | IN-0722-MAC-984 |  |  | 189000 | Reduce Isolation and Depression Through MyndVR | MyndVR is a virtual reality (VR) product which will be provided to 18 Majestic Care facilities. This activity will provide immersive experiences for all residents and will improve quality of life through a reduction in isolation, increased socialization and anticipation for the future. Quality of care will also be improved for residents when the VR activity is used as an intervention for anxiety, pain and sundowning behaviors. | Majestic Care |  | 0 | 0 | Project will start in 2023. The CMPRP Team will delete this row from the tracker since it is not relevant to CY 2022.
IN | Chicago | IN-0722-ASC-985 |  |  | 170100 | Improve Cognitive Health Through MyndVR | MyndVR is a virtual reality (VR) product which will be provided to 15 American Senior Communities (ASC) facilities. This activity will provide immersive experiences for all residents and will improve quality of life through a reduction in isolation, increased socialization and anticipation for the future. Quality of care will also be improved for residents when the VR activity is used as an intervention for anxiety, pain and sundowning behaviors. | American Senior Communities |  | 0 | 0 | Project will start in 2023. The CMPRP Team will delete this row from the tracker since it is not relevant to CY 2022.
IN | Chicago | 2018-IN-045 | 2017-10-01 | 2021-06-30 | 332360 | Conversations on Advanced Care Planning in Nursing Homes | a) The project will implement improvements to advance care planning in nursing homes. b) It will focus on person-directed culture, resident quality of life, and resident choice. The most important component of advance care planning is the initial conversation about one's health care wishes. c) This will improve nursing home resident quality of care and quality of life. Staff will be trained in the skill of conducting advanced care planning conversations with residents and families to determine the residents goals and wishes regarding end of life decisions. d) The target audience would include nursing staff, social service staff, residents and families in 15 nursing homes. | University of Southern Indiana (Project Coordinator); Respecting Choices | The COVID-19 pandemic affected the project in ongoing Advanced Care Planning (ACP) education and evaluation efforts. An assessment from all certified ACP facilitators at participating nursing homes was scheduled for April 2020 and postponed until the COVID-19 pandemic subsides. The project team maintainedn contact with each of the 15 participating nursing homes via Facetime using an iPad provided through the grant to engage in ACP education and conversations with families, residents and nursing home staff (usually social service staff).This resulted in residents' wishes regarding end of life decisions being discussed, documented and honored. The project was granted an extension through 6/30/2021 due to the impacts of the COVID-19 Pandemic; however, the project ended earlier than planned on 9/30/2020. | 3626.32 | 0 | The project ended earlier than planned, on 9/30/2020. An invoice was paid on this project in 2022. The CMPRP Team will add the amount in Column L ($3,626.32) to the amount in Column K ($0) as the remaining funds should have been obligated to CY 2021. Funds cannot be obligated to the current year for projects that have ended the previous year.
IN | Chicago | IN-0718-UI-111/2018-IN-047 | 2018-09-01 | 2021-09-30 | 300000 | Infection Prevention in Long Term Care | a) The project proposes a three-part project to give nursing homes the resources and tools needed to enhance their infection prevention programs. b) Project activities include a course for long-term care staff on best practices for infection prevention, a stand-alone training package that buildings can implement on their own, and a stand-alone education package for buildings. c) Teaching infection prevention best practices to nursing facility staff throughout the state ensures the best implementation of infection prevention skills and provide significant benefit to the residents. This training provides staff with innovative best practices for providing a safe and healthy environment and care for the residents. d) The audience would include administrative and nursing staff, in addition to the facility education leaders. The staff can use the information to educate families and residents on their role in infection prevention. | The University of Indianapolis Center for Aging and Community (Project Coordinator) | A total of 285 participants attended a total of six Infection Prevention Savvy Workforce Education Sessions between August 2019 and July 2021. Pre and post knowledge assessments showed the sessions filled in key areas of knowledge gaps among the participants. The participants were given Paraprofessional and Resident/Family Training Packages to educate additional staff, residents and families in their role in infection prevention. Minimum Data Set (MDS) assessment data from second quarter of 2018 through first quarter of 2021 was reviewed and showed an upward trend for the percentage of long-stay residents assessed and appropriately given the pneumococcal vaccine, the seasonal influenza vaccine, and decreased percentage of long-stay residents with urinary tract infections (UTI). The data was limited due to the COVID-19 pandemic. | 70957.65 | 0 | Project was completed in 2021, but invoice paid in 2022. Any funds ($8,527.89) expended after the project ended were obligated to CY 2021. Funds cannot be obligated to the current year for projects that have ended in the previous year. The team will add the funds reported in Column L to the funds reported in Column K ($62,429.76)
IN | Chicago | IN-0518-USI-063 | 2018-09-01 | 2021-08-30 | 835727 | Building a Dementia Competent Nursing Home Workforce | a) The purpose of this three-year project is to improve the quality of life among elders living with dementia in Indiana nursing homes by improving knowledge and skills among caregivers. b) It includes providing Positive Approach to Care (PAC) dementia education to nursing home staff. c) This project will educate healthcare workers in techniques that are successful in providing care and treatment to dementia residents. Teepa Snow's Positive Approach to Care (PAC) techniques and concepts will be provided to different levels of long-term care staff. The staff will include nurse aides, nurses, educators and administrative staff. As long-term care staff become better educated in techniques to care for residents, especially dementia residents, certain behaviors, outburst, physical and emotional reactions can be reduced. d) The target audience will include all levels of long-term healthcare workers. Facility staff will also be able to train families. | University of Southern Indiana | The Positive Approach to Care (PAC) certification course has had a total of 176 learners. Those 176 learners then have trained and coached an additional 1903 participants. 53 CNA programs and 42 nursing homes were reached in 26 counties in Indiana. Participants reported increased knowledge and perceptions of dementia, and learned techniques to care for residents with dementia and behaviors. Five virtual visits were also conducted in 2021 for nursing facilities with Teepa Snow offering individualized advice. The project also developed a dementia-focused nursing home orientation course available for long term care facilities throughout the state. | 285517.96 | 0 | Project was completed in 2021, but invoice paid in 2022. Any funds ($24,579.01) expended after the project ended were obligated to CY 2021. Funds cannot be obligated to projects that have ended in the previous year. The team will add the funds reported in Column L to the funds reported in Column K ($260,938.95)

## 3. FINANCIAL_SUMMARY
FILLABLE FINANCIAL SUMMARY TRACKER
Tracker Calendar Year (CY)
State | CMP Funds Balance as of January 1, 2022 (Obligated & Available) | CMP Funds Expended for Administrative Uses in CY2022 | CMP Funds Expended for Emergency Uses in CY2022 | CMP Funds Spent on Projects in CY2022 | CMP Funds Added in CY2022 | CMP Funds Balance as of January 1, 2023
IN | 11578129.52 | 43338 | 0 | 133938.64 | 2223709 | 13624561.88

## 4. EXAMPLE_PROJECTS
EXAMPLE TRACKER
Tracker Calendar Year (CY) |  | 20XX
State | CMS Long-Term Care Branch | Unique Identifier | Project Start Date | Project End Date | Total Amount of CMP Funds Approved for this Project | Project Title | Project Summary a) Specific purpose of the project b) Description of what the project will achieve c) Explanation of how the project will benefit nursing home (NH) residents d) Target audience beyond NH residents, if applicable | Funded Entities | Results/Outcomes of the Project | Total Amount of CMP Funds Expended During the Calendar Year | Total Amount of CMP Funds Expended During the Calendar Year | Notes
OH | Chicago | XXXX-OH-XXX | 1/1/20XX | 12/31/20XX | 50000 | TimeSlips Creative Storytelling | a) The purpose of this project is to improve communication and social connectedness for nursing home residents. b) TimeSlips Creative Storytelling will train and certify 50 nursing homes in improvisational storytelling. They will recruit and train facility staff, certify lead facilitators, and hold face-to-face and virtual coaching sessions for technical assistance. c) In addition to improving communication and social connectedness, the project aims to reduce challenging behaviors, reduce antipsychotic medications, and encourage positive engagement between staff and residents. d) 50 nursing homes in the state. | TimeSlips Creative Storytelling | TimeSlips recruited 50 nursing homes to engage in training for the Creative Storytelling program. Survey responses collected from all 50 nursing homes showed a 20% reduction in resident depression, irritability, and apathy as well as a 30% increase in enjoyment of activities and social interaction. A total of 49 testimonials detailing resident improvement in imagination/ creativity, community contribution, talking, and laughing serve as strong qualitative indicators of success. | 0 | 30000 | N/A

## 5. EXAMPLE_FINANCIAL_SUMMARY
EXAMPLE FILLABLE FINANCIAL SUMMARY TRACKER
Tracker Calendar Year | 20XX
State | CMP Funds Balance as of January 1, 20XX (Obligated & Available) | CMP Funds Expended for Administrative Uses in CY20XX | CMP Funds Expended for Emergency Uses in CY20XX | CMP Funds Spent on Projects in CY20XX | CMP Funds Added in CY20XX | CMP Funds Balance as of January 1, 20XX
Ohio | 3000000 | 60000 | 100000 | 30000 | 600000 | 3410000

## Drop-down lists (hidden)
State (short) | State (long) | Branch
AK | Alaska | Seattle
AL | Alabama | Atlanta
AR | Arkansas | Dallas
AZ | Arizona | San Francisco
CA | California | San Francisco
CO | Colorado | Denver
CT | Connecticut | Boston
DC | District of Columbia | Philadelphia
DE | Delaware | Philadelphia
FL | Florida | Atlanta
GA | Georgia | Atlanta
HI | Hawaii | San Francisco
IA | Iowa | Kansas City
ID | Idaho | Seattle
IL | Illinois | Chicago
IN | Indiana | Chicago
KS | Kansas | Kansas City
KY | Kentucky | Atlanta
LA | Louisiana | Dallas
MA | Massachusetts | Boston
MD | Maryland | Philadelphia
ME | Maine | Boston
MI | Michigan | Chicago
MN | Minnesota | Chicago
MO | Missouri | Kansas City
MS | Mississippi | Atlanta
MT | Montana | Denver
NC | North Carolina | Atlanta
ND | North Dakota | Denver
NE | Nebraska | Kansas City
NH | New Hampshire | Boston
NJ | New Jersey | New York
NM | New Mexico | Dallas
NV | Nevada | San Francisco
NY | New York | New York
OH | Ohio | Chicago
OK | Oklahoma | Dallas
OR | Oregon | Seattle
PA | Pennsylvania | Philadelphia
RI | Rhode Island | Boston
SC | South Carolina | Atlanta
SD | South Dakota | Denver
TN | Tennessee | Atlanta
TX | Texas | Dallas
UT | Utah | Denver
VA | Virginia | Philadelphia
VT | Vermont | Boston
WA | Washington | Seattle
WI | Wisconsin | Chicago
WV | West Virginia | Philadelphia
WY | Wyoming | Denver