## PMO Deliverables
Deliverable ID | Deliverable Type | Major Deliverables | Deliverable Due
INITIATION
1 | Other Deliverable | Project Kick Off | Within 15 days of contract execution
PERIODIC REPORTING
2 | Governance Deliverable | Weekly Status Reports | Weekly throughout the duration of contract
3 | Governance Deliverable | Monthly Executive Reports | Monthly throughout the duration of contract
4 | Other Deliverable | INvest APDU Documentation | June 30 each project year
PROJECT PLANNING
5 | Plan Deliverable | Master Project Management Plan | Initial submission within 60 days of contract execution, resubmitted biweekly if there is a change
6 | Plan Deliverable | Master Communication Plan | Initial submission within 60 days of contract execution, resubmitted biweekly if there is a change
7 | Plan Deliverable | INvest Stakeholder Management Plan | Initial submission within 60 days of contract execution, resubmitted biweekly if there is a change
8 | Plan Deliverable | PMO Project Management Plan | Initial submission within 60 days of contract execution, resubmitted biweekly if there is a change
PROJECT EXECUTION
9 | Governance Deliverable | Master Project Schedule | Initial submission within 45 days of contract execution, resubmitted biweekly if there is a change
10 | Other Deliverable | INvest Governance Manual Gap Analysis | Within 30 days of contract execution
11 | Other Deliverable | PPM Tool Recommendation and Potential Implementation | Within 90 days of contract execution
12 | Other Deliverable | Organizational Structure & Resource Calendar Documentation | Initial submission within 15 days of contract execution, resubmitted biweekly if there is a change
MONITOR AND CONTROL
13 | Other Deliverable | Meeting Agendas and Minutes | For each meeting throughout duration of contract
14 | Other Deliverable | Risk Notification Documentation | For all risks throughout duration of contract
15 | Other Deliverable | Work & Quality Performance Standards and Project Metrics | Initial submission within 30 days of contract execution, resubmitted biweekly if there is a change
16 | Other Deliverable | Lessons Learned Meetings and Documentation | Througout project and as requested
PROJECT CLOSE OUT
17 | Governance Deliverable | Closeout Activities | Within 30 days after successful implementation of INvest