## Instructions
All Payer Claims Database RFP
Attachment J1 - Resource Usage Template
Team Resourcing Worksheet
I. Complete only the yellow shaded cells for the following categories for both "Supplier / Subcontractor" & "State of Indiana" sections within the table: • "Project Resourcing" Category: o List each role expected for project related activities and stabilization support under the “Role” column o List the estimated number of individuals required for each role under the “# of Resources” column • "Project Hours" Category: o List the estimated number of hours required by role for each stage of project work (columns D-P) o If there are other stages of project work not listed within the table: - List the number of estimated hours required by role under the “Other Project Work” (Column P) - BRIEFLY describe the other project work under the “Comments” column to the right of the table II. Based upon the entries described above, the following fields will AUTOMATICALLY CALCULATE within the table: • “Total Hours” (for both "Supplier / Subcontractor" & "State of Indiana" sections) • “% of Total Project Hours” (for both "Supplier / Subcontractor" & "State of Indiana" sections) • “Total # of Resources” (for both "Supplier / Subcontractor" & "State of Indiana" sections) • "TOTAL Supplier / Subcontractor Hours" • "TOTAL State of Indiana Hours" • "TOTAL PROJECT HOURS" III. Complete only the yellow shaded cells for the Resource Management Plan comments section: • Resource Management Plan: o Describe the Resource Management Plan and how Supplier / Subcontractor and State of Indiana resources will be managed throughout the project o Provide context based on the estimated number of hours indicated in the table
Role Description Worksheet
I. Complete only the yellow shaded cells for the following columns: • "Role" Column: o Provide a consolidated list of each role type under the “Role” column, proposed in the "Team Resourcing" worksheet. • "Role Description" Column: o Provide a description of the responsibilities for each proposed "Role".

## Team Resourcing
Team Resourcing |  | RESPONDENT: | Onpoint Health Data
Supplier / Subcontractor
PROJECT RESOURCING |  |  | PROJECT HOURS
Role | Years of Relevant Experience | # of Resources | Project Management | Requirements & Process Mapping | Design | Application Configuration | Application Development | Testing | Training | Data Conversion | Interfaces | OCM & Comms | Go-Live Preparation & Execution | Production Stabilization | Other Project Services (use "Comments") | Total Hours | % of Total Project Hours | Total # of Resources | Comments (Describe "Other Project Services" if applicable)
Account Management Lead | 11 | 1 | 3128 | [8 empty] | 100 | 100 |  |  | 3328 | 73.31% | 28 | Other Project: Line 10 - stakeholder engagement Line 11 - privacy related tasks
Health IT Project Manager | 14 | 1 | 1488 | [8 empty] | 80 | 200 |  |  | 1768
Technical Project Manager | 3 | 2 | 316 | [12 empty] | 316
Health IT Consultant | 44 | 2 |  | 456 | 80 | [7 empty] | 120 |  | 120 | 776
Privacy Officer | 13 | 1 | [12 empty] | 830 | 830
Data Operations Lead | 3 | 1 |  | 250 |  | 500 |  | 500 | 200 | 500 |  |  | 200 | 200 |  | 2350
Data Operations Analyst | 20 | 2 |  |  |  | 500 |  | 750 | 200 | 2000 |  |  | 200 |  |  | 3650
Health Analytics Lead | 20 | 1 |  | 500 |  | 500 |  | 500 | 300 | 1000 |  |  | 200 | 500 |  | 3500
Health Data Analyst | 8 | 2 |  | 500 |  | 1000 |  | 500 |  | 2500 |  |  | 200 | 500 |  | 5200
Health IT Analyst | 22 | 2 |  | 480 | 480 |  |  | 480 |  |  |  |  | 164 |  |  | 1604
Analytic Engineer | 10 | 1 |  | 250 | 500 |  | 500 | 150 |  |  | 250 |  |  | 500 |  | 2150
QA Engineer | 15 | 2 | [5 empty] | 588 | [7 empty] | 588
Tech. Infrastructure Engineer | 11 | 2 |  |  |  | 750 |  |  |  |  | 750 |  |  |  |  | 1500
Systems Development Engineer | 35 | 3 |  |  |  |  | 1236 |  |  |  | 1236 |  |  |  |  | 2472
Product Manager | 14 | 1 |  | 728 | [11 empty] | 728
Web Developer | 8 | 1 |  |  |  |  | 632 | [8 empty] | 632
UX/UI Designer | 7 | 1 |  |  | 150 | [5 empty] | 150 |  |  |  |  | 300
Data Architect | 23 | 1 |  |  |  | 500 | [9 empty] | 500
Data Report Developer | 10 | 1 |  |  |  |  | 500 | 250 | [7 empty] | 750
TOTAL Supplier / Subcontractor Hours |  |  | 4932 | 3164 | 1210 | 3750 | 2868 | 3718 | 700 | 6000 | 2386 | 180 | 1384 | 1700 | 950 | 32942
State of Indiana
PROJECT RESOURCING |  |  | PROJECT HOURS
Role | Years of Relevant Experience | # of Resources | Project Management | Requirements & Process Mapping | Design | Application Configuration | Application Development | Testing | Training | Data Conversion | Interfaces | OCM & Comms | Go-Live Preparation & Execution | Production Stabilization | Other Project Services (use "Comments") | Total Hours | % of Total Project Hours | Total # of Resources | Comments (Describe "Other Project Services" if applicable)
Program Manager | 5 to 10 | 1 | 1664 | [12 empty] | 1664 | 26.69% | 4 | Interpretation of data and application to IDOI mission
Project Manager | 5 to 10 | 1 | 3328 | [12 empty] | 3328
Senior Analyst | 4 to 6 | 1 |  | 1000 |  |  |  | 500 | 250 | [5 empty] | 1750 | 3500
Junior Analyst | 2 to 5 | 1 |  | 1000 |  |  |  | 500 | 250 | [5 empty] | 1750 | 3500
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
|  | 0 | [13 empty] | 0
TOTAL State of Indiana |  |  | 4992 | 2000 | 0 | 0 | 0 | 1000 | 500 | 0 | 0 | 0 | 0 | 0 | 3500 | 11992
TOTAL PROJECT HOURS |  |  | 9924 | 5164 | 1210 | 3750 | 2868 | 4718 | 1200 | 6000 | 2386 | 180 | 1384 | 1700 | 4450 | 44934
Below, please describe the Resource Management Plan and how Supplier / Subcontractor and State of Indiana resources will be managed throughout the project. Provide context based on the estimated number of hours indicated in the table above.
.Collaboration is a core principle at Onpoint and extends throughout our work across teams and with our clients. Onpoint’s staff have a strong track record of supporting our APCD clients throughout implementation and ongoing operations – from addressing specific deliverables to providing technical assistance and help-desk support. In order to facilitate communication among team members, Onpoint uses a suite of proven tools and resources — regular calls, webinars, Jira, Confluence, a SharePoint-powered Collaboration Zone, and on-site meetings — all backed by our commitment to providing unmatched service. During implementation and on an ongoing basis, Onpoint's team will collaborate with IDOI to translate program vision and goals into concrete action items. Our proposal relies on IDOI resources (e.g., Program Manager, Project Manager, and Analysts) as described in the RFP for meeting the project requirements. For the APCD program to be successful, establishing a project team that includes members of Onpoint staff, subcontractor staff and IDOI will be an important early milestone to confirm roles and responsibilities and begin building the relationships for a successful initiative. Based on our experience working with other state APCD programs, IDOI’s program manager will be a key resource along with some level of administrative and analytical support staff allocated to the program. From the very beginning, Onpoint’s project team will be supported by a seasoned account management lead from our Client Services team with strong APCD experience to manage the project throughout implementation and production. Our account management lead and project manager will coordinate the efforts of all Onpoint team members from our systems development, IT support, information security, quality assurance, and analytics teams. These individuals will be backed by a deep bench of technical experts familiar with all-payer claims data management and analytics experience. These team members offer specialized skills and knowledge across the full range of project domains, including PMBoK; billing and claims processing; Onpoint’s data management processes and systems; analytic enhancements, including third-party tools; health analytics methods and design, including risk adjustment; and reporting systems development and support. To ensure Onpoint is putting forward the best possible team for Indiana, we are excited to be partnering with the Indiana-based organizations Briljent, Haystack, and Vespa Group, all of whom are committed to providing a highly skilled and collaborative team of health data and technology professionals to support the implementation and ongoing operations of Indiana's APCD. Onpoint will base our approach to managing our work with our subcontractors on the following guiding principles: • All subcontractors will have clear and unambiguous subcontracts established that includes clear Statements of Work. Each Statement of Work will be developed jointly by the team, with each subcontractor taking responsibility for the deliverables and services outlined in their areas of responsibility. • Onpoint will work to effectively support the needs of all subcontractors, and effective channels of communications will be clearly defined and established. ─ Each subcontractor will have a single point of contact with Onpoint for contractual matters. The subcontractors will identify their own single point of contact for contractual matters. On a day-to-day basis, all subcontractor personnel will be free to interact with Onpoint’s personnel as needed to fulfil their scope of work. ─ The formal and informal interfaces between Onpoint and our subcontractors, as well as among the subcontractors, will be documented. • The efforts of our subcontractors will be integrated into a cohesive project plan with all subcontractors having a full understanding of where their efforts fit into the overall picture in support of Indiana’s APCD. ─ The work of all subcontractors will be coordinated by Onpoint to ensure that their efforts are integrated into a cohesive process. A Project Schedule will be developed that establishes schedule constraints and identifies contractual and significant internal milestones. • Onpoint will monitor the overall progress of the project, including the progress of all subcontractors. Onpoint will review all subcontractor deliverables for adherence to content requirements and standards, and all products and services provided by the subcontractors will be subject to the acceptance of Onpoint. The acceptance process will be clearly identified and agreed upon by Onpoint and our subcontractors. • Onpoint will support our subcontractors in processing invoices and payments, subject to the invoices being delivered to Onpoint in an acceptable format for consolidation and remittance to IDOI. While we will ensure that the above checks and protocols are in place, we will approach this work as a cohesive team, working together as is Onpoint’s longstanding, proven approach to project success. Onpoint’s goal – shared by our colleagues at Briljent, Haystack, and Vespa Group – is to provide Indiana with an APCD project team that will offer a true partnership to ensure that your needs are met, your deliverables are on time, your data is of the highest quality, and your analysts are supported.

## Role Description
Role Description
Role | Role Description | Specific Training and Knowledge for Role
Account Management Lead | • Serves as primary point of contact for IDOI’s Contract Administrator and other IDOI project sponsors for all project activities • Resolves issues that are escalated by project team • Oversees Onpoint’s Contingency Plan and assignment of resources according to performance agreements | Specific specialty skills required by the Account Management Lead include: • Account management experience • Client relationship management skills • Effective communication processes • Project plan development knowledge • Contract administration knowledge Additional training and knowledge for this role include: • An understanding of all core data integration, validation, enhancement, and dissemination processes involved in APCD development and operations • Experience with the development of quality and cost measurement, reporting solutions, custom analyses, and program evaluation for APCD analytics
Health IT Project Manager | • Serves as primary project manager and chief liaison to IDOI • Ensures delivery and compliance of all information and project documents as outlined by IDOI • Is responsible for successfully initiating, designing, planning, controlling, executing, monitoring, and closing the project • Employs standards set by the Project Management Institute to help the project team and IDOI successfully monitor, track, and achieve project goals related to APCD planning, development, and implementation • Schedules and reports project activities, coordinates personnel resources, documents and resolves issues and risks, and manages IDOI implementation • Leads biweekly status meetings during implementation and schedules ad hoc meetings as needed • Ensures that all operational task and objectives are met on time and on budget while engaging with a wide range of stakeholders and gathering requirements and technical specifications | Specific specialty skills required by the Health IT Project Manager include: • Knowledge of PMBOK terminology and guidelines • Scope, cost, and time-management skills • Strong ability to prioritize multiple tasks and coordinate with the PMO team • High level of data analysis and problem-solving skills in order to plan, organize, and coordinate programs • Skill in researching, analyzing, and compiling data
Technical Project Manager | • Keep the website development project on track and deliverables organized • Manage the majority of communications related to the website design and functionality and ensure that all parties remain on the same page throughout the design project | Specific specialty skills required by the Technical Project Manager include: • A keen understanding of both the technical and client sides • Leading a Project Management team • A deep understanding of the implementation process for software companies • An understanding of systems engineering
Health IT Consultant | • Is responsible for engaging with IDOI and other state agencies and stakeholders to provide subject matter expertise, recommendations • Gathers information related to the planning, solution design, governance, implementation, and delivery of APCD solutions | Specific specialty skills required by the Data Report Developer role include: • Expertise in leading and developing business intelligence solutions, strong experience in data warehouses, OLAP, and dimensional modeling • Leadership experience leading different BI and ETL projects, data warehouse support, and maintenance • Expertise in developing SSIS Packages to ETL data into the data warehouse from various sources • Expertise in developing Power BI, SSRS, Dynamic 365 PowerApps Portals, Power Automate, KPI and Dashboards • Strong experience in designing, developing, and deploying enterprise SSRS reports • High proficiency in using T-SQL for developing complex stored procedures, triggers, tables, views, user functions, and data integrity • Strong experience managing various projects (e.g., impact analyses, data analyses), leading meetings, gathering requirements, development, QA, and deployment. required by the Health IT Consultant include: • An extensive knowledge of Indiana and every aspect of the MES landscape • Experience working firsthand with HIEs, insurers, and other contributors to, and consumers of, APCD data
Privacy Officer | • Is responsible for overseeing Onpoint’s privacy and security program and compliance activities and serving as the regular point of contact for privacy and security matters with IDOI • Manages ongoing reviews to ensure that our solutions continue to meet all relevant federal and state data privacy and security requirements • Reviews the results of regulatory examinations, compliance reviews and audits, and third-party vulnerability assessments and penetration tests • Oversees the development and implementation of new policies and necessary standards and security enhancements | Specific specialty skills required by the Privacy Officer include: • An understanding of information privacy and security program standards and compliance at both the state and federal levels • Experience ensuring that solutions meet federal and state data privacy and security requirements, including HIPAA, HITRUST, and NIST standards Additional training and knowledge for this role include: • Skills and experience in the design, development, and integration of reporting systems and database architecture
Data Operations Lead | • Ensures that IDOI data submission and reporting requirements are met • Manages interactions with data submitters as well as informational resources pertaining to inquiries, Onpoint CDM system configuration, and data files • Creates, documents, reconciles, and maintains logical and physical data models • Captures, integrates, and publishes descriptive metadata across the various applications • Analyzes and measures data quality levels, identifies data quality issues, and works with data stewards, users, and other IT functions to improve data quality • Establishes, manages, and monitors data aggregation and data quality procedures to ensure data integrity | Specific specialty skills required by the Data Operations Lead include: • Knowledge of payer relationship management • Skill in submitter adjudication processes, training, and working closely with submitters to engage them in solutions to data anomalies, providing guidance for data investigations • Management of submission compliance issues Additional training and knowledge for this role include: • Experience with APCD data, submission standards, and investigating end-user questions for APCD development and operations • Expertise in supporting QA review of adjudication algorithms and linkage rates for APCD analytics
Data Operations Analyst | • Analyze data and underlying systems to ensure the quality of Onpoint’s data and analytic deliverables • Design and implement enterprise data governance standards, guidelines, and policies (e.g., master data, metadata, reference data, data collection, data quality, data lineage) • Ensure effective management of the data collection process up to and including preparing the data for QA and extract to IDOI’s data warehouse | Specific specialty skills required by the Data Operations Analyst include: • Expertise around data investigations and submission compliance issues • Knowledge of APCD data submission processes, data validation, quality assurance oversight, and reporting Additional training and knowledge for this role include: • Knowledge of submitter adjudication processes • Training and working closely with submitters to resolve data completion and quality issues, providing guidance for data investigations
Health Analytics Lead | • Leads efforts related to analyzing data for improving healthcare delivery, supporting health policy initiatives and programs, and informing healthcare transformation initiatives • Leads the development of ad hoc reports and special analyses • Serves as the go-to resource for technical questions regarding analytic approach and methodology, training, problem-solving, quality assurance review, and general technical advice • Serves as HEDIS measures subject matter expert, sharing knowledge of claims data and mapping data to HEDIS measures, including advanced analysis, design, development, and implementation of software solutions • Documents the results of queries and analysis, including their interpretations | Specific specialty skills required by the Health Analytics Lead include: • An understanding of claims, clinical, and other healthcare data analysis, including the generation of industry-standard performance measures and primary care reporting • Expertise in SAS and SQL coding • Skill in developing and implementing analytic reporting solutions and conducting quality assurance • Knowledge of claims data and mapping data to HEDIS measures • Skill in validating measures for HEDIS certification Additional training and knowledge for this role include: • Knowledge about the technical application of various third-party tools, including diagnosis, procedure, and episode groupers as well as performance measures (e.g., AHRQ, CMS, NCQA HEDIS) • Knowledge about the execution of provider attribution • The ability to lead complex analytics projects • The ability to work under pressure and manage multiple projects and deadlines
Health Data Analyst | • Work closely with Onpoint’s Health Analytics Lead to review, analyze, and provide graphical and verbal presentations of healthcare data • Prepare graphical reports using PowerPoint, Excel, Tableau, and other statistical programs • Support analytic work by running Onpoint’s data quality processes for extracts and other Onpoint products and reports | Specific specialty skills required by the Health Data Analyst include: • Expertise in analysis of healthcare utilization, cost, and quality based on claims and other health data sources and in the appropriate methods and modeling applications • Expertise in statistical analysis, predictive modeling, and the development of advanced risk-adjustment models • The ability to work under pressure, managing multiple projects and deadlines Additional training and knowledge for this role include: • An understanding of claims, clinical, and other healthcare data analysis, including the generation of industry-standard performance measures and primary care reporting
Health IT Analyst | • Are responsible for gathering project requirements by talking to APCD stakeholders and documenting/capturing them through reports and other methods • Perform extensive research of business practices and stakeholder interviews | Specific specialty skills required by the Health IT Analyst include: • A keen eye for detail, a knowledge of project management techniques, and excellent communication skills
Analytic Engineer | • Designs, develops, tests, and implements reports and dashboards that utilize the underlying data stores, data warehouses, and data marts • Participates in business analysis activities to gather required reporting and dashboard requirements • Translates business requirements into specifications that are used to implement the required reports and dashboards potentially created from multiple data sources • Provides support as required to ensure the availability and performance of developed reports and dashboards for both internal and external users | Specific specialty skills required by the Analytic Engineer include: • Substantial experience in the development and presentation of healthcare performance measures and reporting specifications • Knowledge of APCD analytics, including being skilled in data manipulation, analysis, and reporting of data through SQL-based tools • Expertise with numerous analytical tools, including SAS, SQL, Tableau, and Microsoft Office
QA Engineer | • Assist with building automated testing processes • Review applications at regular intervals throughout projects and report bugs, queuing them for triage | Specific specialty skills required by the QA Engineer include: • The ability to performing such services professionally based on a decade of experience, including experience with the roles of Senior QA Engineer, QA Team Lead, QA Manager, and Associate Director of Application Systems Development
Technical Infrastructure Engineer | • Provides cross-client IT support responsibility for data integration, Analytic Environment, and reporting systems for IDOI • Facilitates the design and implementation of Onpoint’s cloud-based Analytic Environment • Provides end-user support and training for the Analytic Environment and all hosted software tools • Ensures the security of the Analytic Environment and data delivery | Specific specialty skills required by the Technical Infrastructure Engineer include: • Substantial experience in project management • The ability to plan, allocate resources, control the execution, and advance cross-teams projects for data ETL processes Additional training and knowledge for this role include: • HEDIS measure expertise • Knowledge of claims data and mapping data to HEDIS measures, including advanced analysis, design, development, and implementation of software solutions • In-depth knowledge of the software development lifecycle, including analysis, design, development, and implementation of software solutions • Skill in source-to-target data mapping, ETL design, development, and ETL process flow optimization
Systems Development Engineer | • Serves as the team lead for Onpoint’s extract and reporting systems development • Plays a key role in supporting data submitters and end users, providing expertise in extract/transform/load (ETL) and root cause analyses as part of continuous improvement efforts • Responsible for all back-end data integrations and API builds related to the public-facing website • Ensures that data flows smoothly and efficiently between the front end that users see and the back-end software | Specific specialty skills required by the Software Development Engineer include: • Building web applications • Passion for software development • Ability to ask great questions and explain complex solutions to developers and to non-developers alike • A strong background in web and mobile development • A keen eye for how to future-proof applications
Product Manager | • Serves as the primary strategist for the public-facing website solutions • Performs all up-front tasks around documenting the current challenges, diagramming the proposed solution, and providing an outline to the design and engineering resources | Specific specialty skills required by the Product Manager include: • Leading product development teams • An understanding of product engineering processes as they relate to a variety of organization types and needs
Web Developer | • Responsible for the front-end coding of the web interface. This includes all HTML, CSS, and JavaScript that brings the designs to life, as well as compliance with ADA and other accessibility provisions | Specific specialty skills required by the Web Developer include: • Extensive experience in turning designs into desktop and mobile-friendly websites
UX/UI Designer | • Is responsible for understanding the user’s journey and sketches out the most intuitive paths for accomplishing tasks • Is responsible for creating the final designs for engineers to build once low-fidelity wireframes are complete | Specific specialty skills required by the UI/UX Designer include: • The ability to build beautiful and easy-to-use websites and applications by leveraging years of experience working across a variety of clients, including large nonprofits and enterprise corporations
Data Architect | • Translates complex business processes into technical data architecture solutions • Ensures end-user, application, system integration, and compliance requirements are met in the design, testing, deployment, and maintenance of data storage and processing systems | Specific technical skills required by the Data Architect role include: • Expertise in the following systems/tools: C#, SQL Server, LINQ, Business Objects Crystal Reports, Power BI, ASP.NET, JavaScript, SharePoint, .NET Framework, RDBMS, Azure SQL, SSRS, Web Services (SOAP, REST), Azure Data Factory, Power Automate, SQL Server Analysis Services, SQL Server Integration Services (SSIS), Microsoft Dynamics GP, Dynamics GP eConnect, Nintex Workflow, Telerik, Dynamics 365, and Power Apps Additional training and knowledge for this role include: • Skill in server development, data integration, SharePoint development, SQL Server reporting services, SQL Server integration services, Microsoft Dynamics GP, and Business Objects Crystal Reports
Data Report Developer | • Works with end users and stakeholders to understand reporting and dashboarding requirements and translates those requirements into various analytical products and reports • Assists in designing data storage and processing solutions to meet the needs of the organization | Specific specialty skills required by the Data Report Developer role include: • Expertise in leading and developing business intelligence solutions, strong experience in data warehouses, OLAP, and dimensional modeling • Leadership experience leading different BI and ETL projects, data warehouse support, and maintenance • Expertise in developing SSIS Packages to ETL data into the data warehouse from various sources • Expertise in developing Power BI, SSRS, Dynamic 365 PowerApps Portals, Power Automate, KPI and Dashboards • Strong experience in designing, developing, and deploying enterprise SSRS reports • High proficiency in using T-SQL for developing complex stored procedures, triggers, tables, views, user functions, and data integrity • Strong experience managing various projects (e.g., impact analyses, data analyses), leading meetings, gathering requirements, development, QA, and deployment.