## Instructions
Cost Proposal
RFP 0000000748 Attachment D - Cost Proposal Template
Instructions for this Workbook
General Cost Proposal Instructions
This Cost Proposal template is setup to assume a 24 month implementation. If this is not feasible, please provide an explanation as part of the response on the Cost Proposal Narrative tab. Additional columns may also be added for additional phases as applicable so that the total cost and timeline is as accurate as possible.
Prices must be ALL INCLUSIVE, including any and all delivery costs, destination fees and inflation. Project management and other service fees are to be allocated for each module delivered and included in the overall module level cost. For example: the proposed cost for the Trust Fund module should include applicable design, configuration, implementation, project management testing and training as well as any other services needed as part of delivery. Other services as part of delivery may include data conversion, data archival, interfaces, analytics, configuration, customization, reporting, design and cutover.
This Cost Proposal must include all non-infrastructure and non-hardware product and service costs required to fully execute the proposed scope of services.
Each Cost Summary line item should be described fully in the corresponding worksheet for the appropriate cost category (e.g. Solution Product And Services). The descriptions should include a description of all limitations for products and services including licensing. For instance, if the price for a product license is for up to 600 concurrent users, that must be specified in the description for that line item. The lack of described limitations will be interpreted as a product or service without limits.
Additional information can be provided beyond what is included in the Cost Proposal worksheet descriptions. The additional information must be referenced in the specific worksheet line item description. For instance, if a support agreement is included in the Cost Proposal Worksheet "Support Products And Services" and there is a document that provides all the details for the support agreement, the line item in the worksheet should clearly reference the attachment.
All costs in the Cost Proposal should be consistent with the strategy and approach described in Attachment F - Technical Proposal.
The "TOTAL BID AMOUNT" cell (bright red shading) in the Costing Summary worksheet must include all costs for the implementation and will be used to evaluate the total costs for your proposed services.
The State reserves the right to contact proposers on price and scope clarification at any time throughout the selection process and negotiation process.
Do NOT use “To Be Determined” or similar annotations in the Cost Proposal worksheets. Assumptions should be stated in the Cost Proposal Assumptions worksheet or in worksheet for the specific cost sections.
All worksheets in the Cost Proposal should be thoroughly and accurately completed.
Rows and columns can be added or removed to support your level of detail, however, major categories (e.g. Solution Products And Services) cannot be changed and the overall format of the worksheets must be maintained.
Cost Proposal Formatting Information
The light blue shaded cells indicate information Vendors are expected to provide (e.g. Cost Summary Worksheet, Cell D5).
All red text shown in light blue shaded cells represent SAMPLES and/or EXAMPLES (e.g. Cost Summary Worksheet, Cell D5). The provided red text SAMPLES and EXAMPLES should be replaced or removed in the submitted Cost Proposal. Please also add rows as needed.
Major column and row headings in each worksheet have comments, when needed, defining the required information.
The description cells in the Cost Proposal worksheets should be limited to 300 words.
Dollar amounts should always be rounded to the nearest whole dollar.
We have included some formulas, however, it is the Vendor's responsibility to ensure the accuracy of all cells
Rows of appropriate data can and should be added. Columns should not be added without prior approval from IDOA.
Brief Cost Proposal Worksheet Descriptions
Cost Proposal Narrative - a brief narrative (not longer than two pages) in support of each Cost Proposal item. The narrative should be focused on clarifying how the proposed prices correspond directly to the Respondent's Technical Proposal.
Cost Summary - A phase-by-phase summary of all costs required to fully execute the proposed scope of services and fully maintain and support products for 6 months following the final implementation. The implementation phases must be consistent with those described throughout your proposal including the approach, project plan and staffing plan templates. Please pay particular attention to the instructions included as "notes" in certain cells.
Cost Proposal Assumptions - A full description of any assumptions that are not specific to a Cost Proposal section.
Payment Schedule - A module delivery based schedule of payment triggers and payment amounts. NOTE: For each module delivered to be approved for payment, sign-off on the implementation and testing results must occur as part of acceptance by the State. The final implementation related payment trigger must be the final sign-off of complete implementation and must financially represent 10% of the total one-time implementation costs.

## Cost Summary
ONE-TIME IMPLEMENTATION SERVICES AND PRODUCTS | Cost Summary ID | TOTAL | Phase 1 | Phase 2 | Phase 3 | Phase 4
Timeline (Beginning - Ending Months) |  |  | 1 - 6 | 7 - 12 | 13 - 18 | 19-24
1. Implementation of Modules (including applicable services)
Required - Sentencing Module | CS - 1 | 596160 |  |  |  | 596160
Required - Classification Module | CS - 2 | 264960 |  |  |  | 264960
Required - Parole Module | CS - 3 | 264960 |  |  |  | 264960
Required - Trust Fund Module | CS - 4 | 915625 |  | 375000 | 540625
Required - Conduct Module | CS - 5 | 132480 |  |  |  | 132480
Required - Movement Process Module | CS - 6 | 264960 |  |  |  | 264960
Required - Case Management Module | CS - 7 | 132480 |  |  |  | 132480
Project Initiation | CS - 31 | 50104 | 50104
Mi-Case Orientation Session (GAP/FIT) | CS - 32 | 700400 | 412000 | 65920 | 222480
Requirements Documentation | CS - 33 | 725680 | 18480 | 484720 | 222480
Technical Requirements | CS - 34 | 220800 |  |  | 220800
Functional Requirements | CS - 35 | 134964 |  | 134964
Interfaces | CS - 36 | 794880 |  |  |  | 794880
Reports | CS - 37 | 794880 |  |  |  | 794880
Adult Facilities (Male & Female) Processes | CS - 38 | 220800 |  |  | 220800
Juvenile Facilities Processes | CS - 39 | 132480 |  |  | 132480
Data Migration | CS - 40 | 563400 |  | 161400 | 402000
Quality Assurance | CS - 41 | 840000 |  |  |  | 840000
UAT | CS - 42 | 312000 |  |  |  | 312000
Training | CS - 43 | 403200 |  |  |  | 403200
Implementation | CS - 44 | 94356 |  |  |  | 94356
Project Governance | CS - 45 | 1073208 | 268302 | 268302 | 268302 | 268302
Optional - Grievances Module | CS - 8 | 0 | 0 | 0 | 0 | 0
Optional - Job tracking Module | CS - 9 | 0 | 0 | 0 | 0 | 0
Optional - Visitation Module | CS - 10 | 0 | 0 | 0 | 0 | 0
Optional - Re-entry Module | CS - 11 | 25000 | 0 | 0 | 0 | 25000
Optional - Investigations and intelligence (Internal Affairs) Module | CS - 12 | 0 | 0 | 0 | 0 | 0
Optional - Property Module | CS - 13 | 0 | 0 | 0 | 0 | 0
Optional - Other | CS - 14 | 0 | 0 | 0 | 0 | 0
Optional - Other (Please add more rows as needed.) | CS - 15 | 0 | 0 | 0 | 0 | 0
Optional - Intake Module | CS - 46 | 0 | 0 | 0 | 0 | 0
Optional - Document Management Module | CS - 47 | 0 | 0 | 0 | 0 | 0
Optional - Staff Action Queue Dashboard Module | CS - 48 | 0 | 0 | 0 | 0 | 0
Optional - PREA Module | CS - 49 | 0 | 0 | 0 | 0 | 0
Optional - Assessments Module | CS - 50 | 0 | 0 | 0 | 0 | 0
Optional - Count Module | CS - 51 | 0 | 0 | 0 | 0 | 0
Optional - Scheduling Module | CS - 52 | 0 | 0 | 0 | 0 | 0
Optional - Religious Services Module | CS - 53 | 0 | 0 | 0 | 0 | 0
Optional - Warrants Module | CS - 54 | 0 | 0 | 0 | 0 | 0
Optional - Detainers/Holds Module | CS - 55 | 0 | 0 | 0 | 0 | 0
Optional - Victim Services Module | CS - 56 | 0 | 0 | 0 | 0 | 0
SUBTOTAL | CS - 16 | 9657777 | 748886 | 1490306 | 2229967 | 5188618
2. Other Implementation Services and Products
30 Days Post Go -Live Support | CS - 17 | 398160 |  |  |  | 398160
Cloud Hosting Service (including Database Software Initial Purchase) | CS - 18 | 1061075.335 | 621661.33 | 146471.335 | 146471.335 | 146471.335
Estimated (charged at cost) Expenses | CS - 46 | 455400 | 113850 | 113850 | 113850 | 113850
SUBTOTAL | CS - 19 | 1914635.335
3. Implementation Maintenance Services and Products
Mi-Case Software | CS - 20 | 750000 | 750000
(Example) Implementation Maintenance Products | CS - 21 | 0
SUBTOTAL | CS - 22 | 750000 | 750000 | 0 | 0 | 0
ONE-TIME IMPLEMENTATION SERVICES AND PRODUCTS
| CS - 23 | 12322412.335 | 1498886 | 1490306 | 2229967 | 5188618
POST-IMPLEMENTATION SERVICES AND PRODUCTS | Cost Summary ID | TOTAL | Phase 1 | Phase | Phase | Phase 4 | Post-Project Year 1 | Post-Project Year 1 | Post-Project - Years 2+
Timeline (Beginning - Ending Months) |  |  | 1 - 6 | 7 - 12 | 13 - 18 | 19-24 | Months 1 - 6 | Months 7 - 12 | Annual
4. Post-Implementation Maintenance Services
Post-Implementation Maintenance Services | CS - 24 | 2079653 |  |  |  |  | 1039826.5 | 1039826.5 | 2131246
Cloud Hosting Service | CS - 25 | 366000 |  |  |  |  | 183000 | 183000 | 373320
SUBTOTAL | CS - 26 | 2445653 |  |  |  |  | 1222826.5 | 1222826.5 | 2504566
5. Other Post-Implementation Services and Products
(Example) Other Required Recurring Product | CS - 27 | 0
(Example) Other Required Recurring Service | CS - 28 | 0
SUBTOTAL | CS - 29 | 0
RECURRING PRODUCTS AND SERVICES TOTALS
| CS - 30 | 2445653 | 750000 | 0 | 0 | 0 | 1222826.5 | 1222826.5 | 2504566
ONE-TIME AND RECURRING TOTALS
| CS - 31 | 14768065.335 | 2248886 | 1490306 | 2229967 | 5188618 | 1222826.5 | 1222826.5 | 2504566
TOTAL BID AMOUNT |  | 17213718.335
Note on B1: This section should contain all one-time services and products required to fully execute the proposed scope of services for the implementation period. All post-implementation costs should be included in the recurring products and services section.
Note on C1: Must be a unique ID number for the line item beginning with CS for Cost Summary
Note on D1: Must be the total summation of all implementation and post-implementation costs
Note on E1: Costs for this phase
Note on F1: Costs for this phase
Note on G1: Costs for this phase
Note on H1: Costs for this phase
Note on B4: This section should contain all modules planned for implementation. Services required to fully execute the proposed scope of services for each module should also be included in the overall module price for the entire implementation period including, but not limited to, project management, training, testing, data conversion, data archival, interfaces, analytics, configuration, customization, reporting, design and cutover.
Note on B48: This section should contain one-time services and products, not included in Cost Proposal section 1, that are required to fully execute your proposed scope of services for the entire implementation period.
Note on B54: This section should contain services and products that are required to enable the vendor to a) correct system errors, faults or bugs, b) improve performance, and c) assist with enhancementsafter the initial implementation phases and through the final implementation. If the implementation is performed over 3 phases, the vendor should include these services following phase 1 through the final implementation.
Note on B62: Description of each Post-ImplementationService or Product cost item in at least the level of detail in the Cost Summary Example
Note on J62: Costs for months 1 - 6 following final implementation.
Note on K62: Costs for months 7 - 12 following final implementation.
Note on L62: For Informational Purposes Only - Annual post-project costs starting in in year 2 post implementation.
Note on B65: This section should contain services that are required to enable the vendor to a) correct system errors, faults or bugs, b) improve performance, and c) assist enhancements of the OMS solution for 6 months after the final implementation.
Note on B70: This section should contain services and products, not included in Cost Proposal section 4, that are required to operate the OMS solution during the 6 months following final implementation.

## Cost Proposal Assumptions
Assumption Description | ID
All Prices are quoted in US Dollars | CPA - 1
Optional items are included in the base Mi-Case Software cost. Should IDOC wish to enable these modules there will be an additional consulting cost. This cost will be linked to the requisite effort required to implement these modules, with the exception of Re-Entry whereby Mi-Case have provided an implementation cost, as this module is required to facilitate other modules. | CPA - 2
Acceptance criteria for any milestone deliverable shall be agreed with IDOC at the commencement of the project. | CPA - 3
IDOC shall provide an acceptance of any deliverable within 30 days of the delivery to IDOC. In the event IDOC does not accept a deliverable within the 30 days and does not notify Mi-Case of a reason why the deliverable has been rejected, then it will be assumed that the deliverable is accepted. | CPA - 4
The Mi-Case Software License shall be paid on Contract Award. CS-20 | CPA - 5
Payment terms will be in-libe with the contract agreement | CPA - 6
All prices are less any applicable taxes | CPA - 7
Payment Milestone are a negotiable item as parto fo contract negotiations | CPA - 8
CPA - 9
CPA - 10
Note on B1: Unique ID for each line item in this worksheet

## Payment Schedule
ID | Payment Type | Services or Products | Payment Trigger | Cost Summary ID* | Description of Applicable Services and Deliverables | Estimated Completion Phase #** | Estimated # of Months to Deliver | Total Cost of Module and Applicable Services
| Deliverable Based Payments |  | Rows 3 - 9 are required deliverable based payment triggers and milestones.
PS - 1 |  | 1. Implementation of Modules (including applicable services) | Payment Trigger - Sentencing Module Delivery and Acceptance | CS - 1 | The Mi-Case Sentencing Module Configured and Customized for IDOC | 4 | 24 | 596160
PS - 2 |  |  | Payment Trigger - Classification Module Delivery and Acceptance | CS - 2 | The Mi-Case Classification Module Configured and Customized for IDOC | 4 | 24 | 264960
PS - 3 |  |  | Payment Trigger - Parole Module Delivery and Acceptance | CS - 3 | The Mi-Case Parole Module Configured and Customized for IDOC | 4 | 24 | 264960
PS - 4 |  |  | Payment Trigger - Trust Fund Module Delivery and Acceptance | CS - 4 | The Mi-Case (Cashless) Trust Fund Module Configured and Customized for IDOC | 4 | 24 | 915625
PS - 5 |  |  | Payment Trigger - Conduct Module Delivery and Acceptance | CS - 5 | The Mi-Case Conduct Module Configured and Customized for IDOC | 4 | 24 | 132480
|  |  | Payment Trigger - Movement Process Module Delivery and Acceptance | CS - 6 | The Mi-Case Movement Module Configured and Customized for IDOC | 4 | 24 | 264960
PS - 6 |  |  | Payment Trigger - Case Management Module Delivery and Acceptance | CS - 7 | The Mi-Case Case Management Module Configured and Customized for IDOC | 4 | 24 | 132480
Rows 11 - 17 are optional deliverable based payment triggers and milestones.
PS - 7 |  |  | Payment Trigger - Optional - Grievances Module Delivery and Acceptance | CS - 8 | The Mi-Case Grievance Module Out of the Box | 4 |  | 0
PS - 8 |  |  | Payment Trigger - Optional - Job tracking Module Delivery and Acceptance | CS - 9 | The Mi-Case Job Tracking Module Out of the Box | 4 |  | 0
PS - 9 |  |  | Payment Trigger - Optional - Visitation Module Delivery and Acceptance | CS - 10 | The Mi-Case Visitation Module Out of the Box | 4 |  | 0
PS - 10 |  |  | Payment Trigger - Optional - Re-entry Module Delivery and Acceptance | CS - 11 | The Mi-Case Re-Entry Module Configured for IDOC | 4 | 1 | 25000
PS - 11 |  |  | Payment Trigger - Optional - Investigations and intelligence (Internal Affairs) Module Delivery and Acceptance | CS - 12 | The Mi-Case Investigations and intelligence (Internal Affairs) Module Out of the Box | 4 |  | 0
PS - 12 |  |  | Payment Trigger - Optional - Property Module Delivery and Acceptance | CS - 13 | The Mi-Case Propoerty Module Out of the Box | 4 |  | 0
|  |  | Project Initiation | CS - 31 | Initialization of the Project including the creation of all project control documents | 1 | 1 | 50104
|  |  | Mi-Case Orientation Session (GAP/FIT) | CS - 32 | Range of Workshop Sessions used to define scope of each module and identify where the Out of the Box Solution meets IDOC's needs and where configuration and Customization is needed. | 1 through 3 (reports carrying on through phase 3) | 5 | 700400
|  |  | Requirements Documentation | CS - 33 | Joinlty agreed Requirement docuements detailing any customizations and configurations to the Modules. | 1 through 3 (reports carrying on through phase 3) | 12 | 725680
|  |  | Technical Requirements | CS - 34 | Implementation of the IDOC OMS Technical requirements | 2 | 1 | 220800
|  |  | Functional Requirements | CS - 35 | Implementation of the IDOC OMS Fucntional requirements | 2 | 2 | 134964
|  |  | Interfaces | CS - 36 | Development of all IDOC OMS Interfaces | 4 | 6 | 794880
|  |  | Reports | CS - 37 | Development of all IDOC OMS Reports | 4 | 12 | 794880
|  |  | Adult Facilities (Male & Female) Processes | CS - 38 | Impelmentation of requirements for the Adult Facilities | 3 | 5 | 220800
|  |  | Juvenile Facilities Processes | CS - 39 | Impelmentation of requirements for the Juvenile Facilities | 3 | 4 | 132480
|  |  | Data Migration | CS - 40 | Migration of Data from IDOC Legacy systems to Mi-Case | 4 | 11 | 563400
|  |  | Quality Assurance | CS - 41 | Quality Assurance and Testing of the IDOC OMS system | 4 | 17 | 840000
|  |  | UAT | CS - 42 | Support during IDOC UAT | 4 | 12 | 312000
|  |  | Training | CS - 43 | Delivery of a 6 week Train the Trainer trainning program | 4 | 7 | 403200
|  |  | Implementation | CS - 44 | Implementation of the complete solution - Go-Live | 4 | 1 | 94356
|  |  | Project Governance | CS - 45 | Projetc Governance and Management for the duration of the project | 1,2,3,4 | 24 | 1073208
PS - 14 |  |  | Payment Trigger - Optional - Other Module Delivery and Acceptance (add more rows as needed) | CS - 14
| Time and Material Based Payments |  | Rows 19 - ? Are time and materials based payment triggers (add more rows as needed)
|  | 2. Other Implementation Services and Products | 30 Days Post Go -Live Support | CS - 17 | Intensive support to IDOC for a 30 days post Go-Live | 4 | 1 | 398160
|  |  | Cloud Hosting Service (including Database Software Initial Purchase) | CS - 18 | Provison of the software and hardware hosting service | 1 | 1 | 1061075.335
|  | 3. Implementation Maintenance Services and Products | Mi-Case Software | CS - 20 | The Base Mi-Case Software license | 1 |  | 750000
|  |  | (Example) Implementation Maintenance Products | CS - 21
|  | 4. Post-Implementation Maintenance Services | Post-Implementation Maintenance Services | CS - 24
|  |  | Cloud Hosting Service | CS - 25
|  | 5. Other Post-Implementation Services and Products | (Example) Other Required Recurring Product | CS - 27
|  |  | (Example) Other Required Recurring Service | CS - 28
[7 empty] | 289 | 9657777
* Refer to Column C on the Cost Summary tab.
| ** Refer to phases 1 - 4 on the Cost Summary tab. | [6 empty] | 9657777
Note on A1: Baker, Glen: Unique ID for each line item in this worksheet
Note on D1: Payment triggers can be one-time or recurring activity milestones listed in the project plan, date driven milestones in the project plan, date driven triggers (e.g. services and purchase payment plans, post-implementation maintenance and support) or activity driven triggers (e.g. travel & expenses).

## Cost Proposal Narrative
Cost Proposal Narrative
Mi-Case believe that they a providing IDOA with a an extremely cost effective solution. A one that has proven track record of implementation in a number of States and Jurisdictions. All pricing sheets have been completed in accordance with the instructions set forth in the 'Instructions' tab. In the event that the Mi-Case team have misunderstood the instructions or not completeted the sheets to the satisfaction of IDOC, then Mi-Case weclomes the opportunity to adjust and resolve any issues.