## May
2019 21st CCLC Multistate Conference May
Marketing
Status | Task Description | Target Date | Point Person | Notes
Complete | Finalize Website Content/Go Live | 2019-05-01 | Erin
Complete | E-mail Grantees | 2019-05-05 | Erin | Registration Info
In Process | E-mail Presenters | 2019-05-05 | Erin | Registration Info
In Process | E-mail TN, KY, WV Contacts | 2019-05-05 | Erin | Registration Info
Complete | E-mail Planning Team | 2019-05-05 | Erin | Doubletree Hotel Info
Complete | Finalize Hashtag | 2019-05-15 | Social Legends | #GetRooted21stCCLC
Complete | Create Event Promotion Toolkit | 2019-05-15 | Social Legends/Erin
Complete | Create Event Promotion Flyer | 2019-05-15 | Social Legends
Exhibitors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Develop Exhibit Area Map | 2019-05-30 | Erin
In Process | Continue Exhibitor Recruitment | 2019-05-30 | Erin
Sponsors
Status | Task Description | Target Date | Point Person | Notes
In Process | Collect Sponsorship Payments | 2019-05-30 | Social Legends/Erin
In Process | Outreach to Potential Sponsor Candidates | 2019-05-30 | Erin
In Process | Update Spreadsheet of Confirmed Sponsorships | 2019-05-30 | Erin
Presenters
Status | Task Description | Target Date | Point Person | Notes
In Process | Finalize Speaker Session Schedule | 2019-05-15 | Erin/Christen
Not Started | Inform Presenters of Session Schedule | 2019-05-15 | Erin/Christen
In Process | Finalize General Event Schedule | 2019-05-30 | Erin/Christen
Complete | Create Event Schedule Overview Flyer | 2019-05-30 | Social Legends
Logistics
Status | Task Description | Target Date | Point Person | Notes
Complete | Create/Release Volunteer Application | 2019-05-01 | Erin
Complete | Registration Platform Goes Live | 2019-05-01 | Erin
Complete | Create Master Project Plan | 2019-05-10 | Social Legends
Complete | Finalize/Secure Reception Venue | 2019-05-15 | Danielle
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-05-17 | Jeananne
In Process | Complete Tech Plan (Based on Presenter Needs) | 2019-05-30 | Erin
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-05-31 | Jeananne
Not Started | Update Event Budget | 2019-05-31 | Erin/Christen
Complete | Release Art Challenge Information | 2019-05-31 | Christen

## June
2019 21st CCLC Multistate Conference June
Marketing
Status | Task Description | Target Date | Point Person | Notes
Not Started | E-mail TN, KY, WV Promo Toolkit | 2019-06-05 | Christen
Not Started | Send Registration Announcement #1 | 2019-06-15 | Christen | Per Promo Toolkit
Not Started | E-mail TN, KY, WV Schedule Overview Document | 2019-06-20 | Christen | 1-Page Schedule Highlights
Not Started | Send #2 Registration Announcement #2 | 2019-06-29 | Christen | Per Promo Toolkit
Not Started | E-mail to Registered Attendees | 2019-06-30 | Christen | Include: Hotel Booking/Pre-Conference Intensive Sign-Up
Not Started | Update Website | 2019-06-30 | Erin | *As Needed
Not Started | Weekly Social Media Posts | 2019-06-30 | Christen | Per Promo Toolkit
Exhibitors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Continue Exhibitor Recruitment | 2019-06-30 | Erin
Sponsors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Collect Sponsorship Payments | 2019-06-30 | Social Legends/Erin
Not Started | Outreach to Potential Sponsor Candidates | 2019-06-30 | Erin
Not Started | Update Spreadsheet of Confirmed Sponsorships | 2019-06-30 | Erin
Presenters
Status | Task Description | Target Date | Point Person | Notes
In Process | Finalize/Create Schedule Overview Document | 2019-06-15 | Erin | 1-Page Schedule Highlights
Not Started | Finalize Hangers Tour Plan | 2019-06-15 | Erin | *Determine if possible
In Process | Finalize Youth Engagement Plan | 2019-06-30 | Erin
In Process | Confirm Session Schedule with Presenters | 2019-06-30 | Erin
Logistics
Status | Task Description | Target Date | Point Person | Notes
In Process | Determine Welcome Bag Contents | 2019-06-14 | Christen
Not Started | Coordinate Evansville Prep Visit | 2019-06-14 | Christen
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-06-14 | Jeananne
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-06-28 | Jeananne
In Process | Draft Reception Schedule/Timeline | 2019-06-30 | Danielle
In Process | Coordinate Reception Catering | 2019-06-30 | Danielle
Not Started | Send Basket Donation Reminder E-mail | 2019-06-30 | Erin

## July
2019 21st CCLC Multistate Conference July
Marketing
Status | Task Description | Target Date | Point Person | Notes
Not Started | E-mail TN, KY, WV Session Schedule | 2019-07-10 | Christen
Not Started | E-mail to Registered Attendees | 2019-07-17 | Christen | Include: Session Schedule, Pre-Conference Intensive Sign-Up
Not Started | Send Registration Announcement #3 | 2019-07-21 | Christen | Per Promo Toolkit
Not Started | Weekly Social Media Posts | 2019-07-31 | Christen | Per Promo Toolkit
Not Started | Update Website | 2019-07-31 | Erin | *As Needed
Exhibitors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Continue Exhibitor Recruitment | 2019-07-30 | Erin
Not Started | Update Exhibit Map | 2019-07-30 | Erin
Sponsors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Collect Sponsorship Payments | 2019-07-30 | Social Legends/Erin
Not Started | Outreach to Potential Sponsor Candidates | 2019-07-30 | Erin
Not Started | Update Spreadsheet of Confirmed Sponsorships | 2019-07-30 | Erin
Presenters
Status | Task Description | Target Date | Point Person | Notes
Not Started | Send Speaker Presentation Submission Information | 2019-07-10 | Erin | Due Aug 30th
Logistics
Status | Task Description | Target Date | Point Person | Notes
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-07-12 | Jeananne
Not Started | Send Basket Donation Reminder E-mail | 2019-07-15 | Erin
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-07-26 | Jeananne
Not Started | Finalize Reception Schedule/Timeline | 2019-07-31 | Danielle

## August
2019 21st CCLC Multistate Conference August
Marketing
Status | Task Description | Target Date | Point Person | Notes
Not Started | E-mail to Registered Attendees | 2019-08-15 | Christen | Session Schedule/Reception Highlights/Pre-Conference Intensive
Not Started | Send Registration Announcement #4 | 2019-08-31 | Christen | Per Promo Toolkit
Not Started | Update Website | 2019-08-31 | Erin | *As Needed
Not Started | Weekly Social Media Posts | 2019-08-31 | Christen | Per Promo Toolkit
Exhibitors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Continue Exhibitor Recruitment | 2019-08-27 | Erin
Not Started | Finalize Exhibit Map | 2019-08-27 | Erin
Not Started | Send Registered Exhibitor Update/Information | 2019-08-30 | Erin
Sponsors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Collect Sponsorship Payments | 2019-08-30 | Social Legends/Erin
Not Started | Outreach to Potential Sponsor Candidates | 2019-08-30 | Erin
Not Started | Collect Sponsor Logos | 2019-08-30 | Erin | * As needed
Not Started | Update Spreadsheet of Confirmed Sponsorships | 2019-08-30 | Erin
Not Started | Collect Sponsor Ads | 2019-08-30 | Erin
Speakers
Status | Task Description | Target Date | Point Person | Notes
Not Started | Final Speaker Presentations Submitted | 2019-08-31 | Erin
Logistics
Status | Task Description | Target Date | Point Person | Notes
Not Started | Final Submission of Basket Items | 2019-08-01 | Christen
Not Started | Submission of Art Challenge Entries | 2019-08-01 | Christen
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-08-09 | Jeananne
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-08-23 | Jeananne
Not Started | Explore Transportation Needs/Options | 2019-08-30 | Erin
Not Started | Finalize Reception Timeline | 2019-08-30 | Danielle
Not Started | Confirm Conference Photographer | 2019-08-30 | Christen
Not Started | Finalize Venue Layout | 2019-08-30 | Christen
Not Started | Close Registration | 2019-08-30 | Christen
Not Started | Art Challenge Finalists Selected and Notified | 2019-08-30 | Christen

## September
2019 21st CCLC Multistate Conference September
Marketing
Status | Task Description | Target Date | Point Person | Notes
Not Started | Coordinate Statement from Dr. McCormick | 2019-09-01 | Erin
Not Started | Create Event Program | 2019-09-01 | Christen
Not Started | Send Program to Printer | 2019-09-06 | Christen
Not Started | E-mail to Registered Attendees | 2019-09-13 | Christen | Session Schedule/Exhibitor List/Sponsor Highlight/Service Project
Not Started | Update Website | 2019-09-30 | Erin | *As Needed
Not Started | Weekly Social Media Posts | 2019-09-30 | Christen | Per Promo Toolkit
Exhibitors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Finalize Exhibitor Map | 2019-09-13 | Erin
Not Started | Send Registered Exhibitor Update/Information | 2019-09-30 | Erin | Include: Final Map, Session Schedule
Presenters
Status | Task Description | Target Date | Point Person | Notes
Not Started | Review Speaker Presentations | 2019-09-13 | Erin
Not Started | Send Speaker Presentation Revision Requests | 2019-09-20 | Erin | *As Needed
Not Started | Send Speaker Event Information E-mail | 2019-09-30 | Erin | Include: Session Schedule, Presentation Instructions
Sponsors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Collect Sponsorship Payments | 2019-09-30 | Social Legends/Erin
Logistics
Status | Task Description | Target Date | Point Person | Notes
Not Started | Finalize/Order Welcome Bag Supplies | 2019-09-02 | Christen
Not Started | Order Event Supplies | 2019-09-02 | Christen
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-09-06 | Jeananne
Not Started | Finalize Volunteer Schedule/Assignments | 2019-09-06 | Christen
Not Started | Signed Catering BEO Due | 2019-09-06 | Jeananne
Not Started | 50% Catering Deposit Due | 2019-09-06 | Jeananne
Not Started | Create Necessary Venue Signage | 2019-09-13 | Christen
Not Started | Finalize Internal Event Timeline | 2019-09-13 | Christen/Erin
Not Started | Create Set-Up Maps | 2019-09-13 | Christen
Not Started | Finalize Transportation Schedule | 2019-09-13 | Erin
In Process | Create Conference Evaluation Surveys - Online/Hard Copy | 2019-09-13 | Christen
Not Started | Create Event Packing/Set-up List | 2019-09-19 | Christen/Erin
Not Started | Submit all Printing for Processing | 2019-09-20 | Christen
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-09-20 | Jeananne
Not Started | Final Prep Call with Venue | 2019-09-30 | Christen | *As Needed
Not Started | Create Necessary PowerPoint Slides/Presentations | 2019-09-30 | Erin
Not Started | Develop Strategy for Raffle Implementation | 2019-09-30 | Christen
Not Started | Finalize Audio/Visual w/ Venue | 2019-09-30 | Christen
Not Started | Host Volunteer Webinar | 2019-09-30 | Christen
Not Started | Final Catering Balance Due | 2019-09-30 | Jeananne
Not Started | Finalize Guarantee with Venues/Caterers | 2019-09-30 | Jeananne

## October
2019 21st CCLC Multistate Conference October
Marketing
Status | Task Description | Target Date | Point Person | Notes
Not Started | Attendee Final Reminder E-mail | 2019-10-04 | Christen | Include: Session Schedule, Hangers Drive, Transportation Details
Not Started | Update Website | 2019-10-04 | Erin | *As Needed
Not Started | Weekly Social Media Posts | 2019-10-06 | Christen | Per Promo Toolkit
Exhibitors
Status | Task Description | Target Date | Point Person | Notes
Not Started | Final Exhibitor Information E-mail | 2019-10-04 | Erin | Include: Map, Set-Up Times, Final Schedule
Not Started | Create Exhibitor Check-In List | 2019-10-04 | Erin
Presenter
Status | Task Description | Target Date | Point Person | Notes
Not Started | Final Presenter Information E-mail | 2019-10-04 | Erin
Not Started | Create Presenter Check-In List | 2019-10-04 | Erin
Logistics
Status | Task Description | Target Date | Point Person | Notes
Not Started | Pick Up Printing | 2019-10-02 | Christen
Not Started | Print Participant Name Tags/Guest List | 2019-10-02 | Christen
Not Started | Attendee Report Pulled/Distributed to Leadership Team | 2019-10-02 | Jeananne
Not Started | Final Volunteer Information E-mail | 2019-10-04 | Christen
Not Started | Walk Through with Venue | 2019-10-05 | Christen
Not Started | Prepare Participant Packets/Registration | 2019-10-05 | Christen
Not Started | Prepare Exhibitor Packets/Registration | 2019-10-05 | Erin
Not Started | Prepare Presenter Packets/Registration | 2019-10-05 | Erin
Not Started | Prepare Art Challenge Gallery | 2019-10-06 | Christen
Not Started | Prepare Welcome Bags | 2019-10-06 | Christen
Not Started | Recognition of Art Challenge Finalists | 2019-10-08 | Christen
Not Started | Send Conference Evaluation | 2019-10-09 | Christen
Not Started | Pay Outstanding Invoices | 2019-10-31 | Christen/Erin/Jeananne