## Resource Plan Forward
Contract Signing | 2021-10-15
| Initiate and Define | [6 empty] | Build
Org 1 | Project Planning/ System Readiness/Design Sessions & Documentation | [6 empty] | System Configuration
Dept 1 and 2 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12
| 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17
Build
[7 empty] | Org 2 | System Readiness/Design Sessions & Documentation |  |  |  | System Configuration
[7 empty] | Dept 3 and 4 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15
[8 empty] | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07
Build | bar: 2022-01-17 to 2022-02-07
[8 empty] | 2022-01-10: Org 3; 2022-01-17: System Readiness/Design Sessions & Documentation | System Configuration
[11 empty] | Dept 5 and 6 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19
[12 empty] | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07
Build | bar: 2022-02-14 to 2022-03-07
[12 empty] | 2022-02-07: Org 4; 2022-02-14: System Readiness/Design Sessions & Documentation | System Configuration
[15 empty] | Dept 7 and 8 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23
[16 empty] | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04
Build | bar: 2022-03-14 to 2022-04-04
[16 empty] | 2022-03-07: Org 5; 2022-03-14: System Readiness/Design Sessions & Documentation | System Configuration
[19 empty] | Dept 9 and 10 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27
[20 empty] | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02
[28 empty] | Build |  |  |  | Testing and Training |  | All Departments up to this time |  |  |  |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy | bar: 2022-04-11 to 2022-05-02
[20 empty] | 2022-04-04: Org 6; 2022-04-11: System Readiness/Design Sessions & Documentation | System Configuration |  |  |  | QA | QA | QA | Training | UAT | UAT | UAT | Go-Live 1 | Transition | Go-Live 2 | Transition | Go-Live 3 | Transition | Go-Live 4 | Transition | Go-Live 5 | Transition | Go-Live 6 | Transition | Go-Live 7 | Transition | Go-Live 8 | Transition | Go-Live 9 | Transition | Go-Live 10 | Transition | Go-Live 11 | Transition | Go-Live 12 | Transition
[23 empty] | Dept 11 and 12 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 43 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52 | WK 53 | WK 54 | WK 55 | WK 56 | WK 57 | WK 58 | WK 59 | WK 60 | WK 61 | WK 62
[24 empty] | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02
Build
[27 empty] | Org 6 | System Readiness/Design Sessions & Documentation |  |  |  | System Configuration
[27 empty] | Dept 13 and 14 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35
[28 empty] | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27
Build | bar: 2022-06-06 to 2022-06-27
[28 empty] | 2022-05-30: Org 6; 2022-06-06: System Readiness/Design Sessions & Documentation | System Configuration
[31 empty] | Dept 15 and 16 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39
[32 empty] | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25
[40 empty] | Build |  |  |  | Testing and Training | [6 empty] | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy |  | Deploy | bar: 2022-07-04 to 2022-07-25
[32 empty] | 2022-06-27: Org 6; 2022-07-04: System Readiness/Design Sessions & Documentation | System Configuration |  |  |  | QA | QA | QA | Training | UAT | UAT | UAT | Go-Live 13 | Transition | Go-Live 14 | Transition | Go-Live 15 | Transition | Go-Live 16 | Transition | Go-Live 17 | Transition | Go-Live 18 | Transition
[35 empty] | Dept 17 and 18 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 43 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50 | WK 51 | WK 52 | WK 53 | WK 54 | WK 55 | WK 56 | WK 57 | WK 58 | WK 59 | WK 60 | WK 61 | WK 62
[36 empty] | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02