## Slide 1
November 19th 2021
VPMA Control-M
Migration Methodology

## Slide 2
Control-M Implementation Methodology
Step #1
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring
Define the Scope
Overview of Control-M features (i.e. licensed features)
Decide which add-ons and Control Modules are to be implemented
Identify target applications for the onboarding/conversion

## Slide 3
Control-M Implementation Methodology
Step #2
Finalize the Design
Control-M architecture overview
Estimate the number of jobs/users/Agents and forecast the growth rate over x years
Review HA/DR requirements (RPO and RTO)
Produce machine specs/VM/database/network/firewall design
Produce application monitoring, backup and integration design
Event integration design (email, SMS, open tickets etc.)
Security related discussions for LDAP/AD integration and batch account management
Recommend Control-M/Agent, Agentless and Control Module deployment method
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 4
Control-M Implementation Methodology
Step #3
Infrastructure Creation and Configuration
Environment validation
Core components installation and configuration
HA/DR configuration and testing
Control-M/Agent and Control Module deployment
GUI client deployment to end users and/or Citrix farm
Define housekeeping jobs
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 5
Control-M Implementation Methodology
Step #4
Application Integration
Integrate Control-M with third-party event processing platform
Fine tune event triggers and alerting messages
Configure monitoring for Control-M core components
Configure backup for Control-M file system and database
LDAP authentication integration (if required)
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 6
Control-M Implementation Methodology
Step #5
Process Review
Identify existing batch jobs (execution server, script/command location, batch user, permission and schedule)
Develop the best migration approach and execution plan to ensure minimal risk and downtime
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 7
Control-M Implementation Methodology
Step #6
Define Site Standards and Operational Model
Define Control-M job/folder/calendar naming standards
Create Control-M Self-Service rules/definitions (if applicable)
Develop alerting message templates
Identify end users and their roles/responsibilities in Control-M
Define user groups in Control-M and AD, configure security in Control-M
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 8
Control-M Implementation Methodology
Step #7
Product Mentoring
Provide site-specific Control-M product education throughout the project for operators, schedulers and administrators
Provide knowledge transfer before project go-live
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 9
Control-M Implementation Methodology
Step #8
Process Migration and Parallel Testing
Convert and migrate batch jobs into Control-M
Perform parallel execution or dummy execution for selected applications/jobs
Review job schedule and execution behavior in Control-M
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 10
Control-M Implementation Methodology
Step #9
Go-live
Prepare and review the VPMA Control-M go-live check list
Enable jobs for daily execution in Control-M and turn them off in other scheduling tools
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 11
Control-M Implementation Methodology
Step #10
Post Go-live Support
Monitor job execution status
Conduct overall health check and performance review for Control-M
Define the Scope
Finalize the Design
Infrastructure Creation and Configuration
Define Site Standards and Operational Model
Process Review
Application Integration
Process Migration and Parallel Testing
Go-live
Post Go-live Support
Product Mentoring

## Slide 12: Thank You