Table of Contents

1.0 Introduction	2

2.0 Definitions	2

3.0 History and Vision for Indiana’s APS System	4

4.0 Mandatory Requirements	8

5.0 Overview of APS System Functions	8

6.0 APS Staffing & Operations Contractor Functional Requirements	17

7.0 Collaboration with Internal Partners	19

8.0 Collaboration with External Partners	20

9.0 Staffing	21

10.0 Quality Assurance	24

11.0 Reporting	25

12.0 System & Infrastructure Requirements	26

13.0 State Resources for APS Staffing & Operations Contractor	28

14.0 Start-of-Contract Requirements	28

15.0 End-of-Contract Requirements	30

16.0 Corrective Actions and Payment Withholds	30

17.0 Key Performance Indicators	32

18.0 State Audits	34

# 1.0 Introduction

The Indiana Family and Social Services Administration (FSSA), Division of Aging (DA) requests responses from vendors who are able to provide staffing and operations services to support its Adult Protective Services (APS) program. APS and similar programs originated in 1958 from the National Council of Aging with statewide programs first receiving federal funding in 2002 through the Elder Justice Act (EJA) of 2002. The purpose of Indiana Adult Protective Services is to investigate reports of abuse, neglect, or exploitation and provide the least restrictive and person-centered service plan to keep endangered Hoosiers safe and monitor for success. Respondents to this RFP must be committed to providing Adult Protective Services to Hoosiers in accordance with all applicable state rules, regulations, and laws. While it is the Respondent’s responsibility to be aware of all policies that regulate their business, please note that on May 7, 2024, federal regulations for adult protective services were published and can be found at the following link: https://www.govinfo.gov/content/pkg/FR-2024-05-08/pdf/2024-07654.pdf.

The anticipated Go-Live for the Contract and duties contemplated by this RFP is July 1st, 2025. Please read this document and the associated attachments carefully. This Scope of Work (SoW) should be referenced by a Respondent in its preparation of its Technical Proposal - Attachment F.

# 2.0 Definitions

Following are explanations of terms and abbreviations appearing throughout this solicitation. Other special terms may be used in the solicitation, but they are more localized and defined where they appear, rather than in the following list.

APS - Adult Protective Services, a program within Indiana's Division of Aging.

APS-CMS - Case management system provided by the State to the Contractor. Please note the APS-CMS User Manual has been included in Bidder’s Library - Attachment M; as a disclaimer, the contents of this manual reflect the current APS-CMS system and will change to align with the new APS Model.

Battery/Abuse - A person who knowingly or intentionally: (1) Touches another person in a rude, insolent or angry manner; or (2) in a rude, insolent or angry manner places any bodily fluid or waste on another person.

Case - an investigation of the facts and details involved in an allegation of Battery/Abuse, Neglect or Exploitation to an Endangered Adult. Findings are documented and assessed for the safety and well being of an alleged victim or client.

Change Request - A request, submitted by the Contractor, the State, or a Vendor to FSSA, to perform services or provide goods other than those contemplated by the Contract or a Vendor’s respective contract. The definition of Change Request does not apply to any changes Contractor or Vendor are already obligated to provide under the Contract or a Vendor’s respective contract, including without limitation changes to correct deficiencies and changes to any system or software that is considered maintenance or routine upgrades or updates. Change Requests may be used, among other things, for:

  - System changes; and

  - Special projects, training or other services required by FSSA.

Client - An individual resident of Indiana that is the recipient of the goods or services of a Program.

Contract - When capitalized, the contract or contracts, between the State and Contractor resulting from this RFP.

Contractor - The Respondent or Respondents selected as a winning vendor as a result of this RFP and any and all subcontractors to that contractor, collectively.

DA - The Division of Aging, a division of the FSSA.

Emergency - a situation in which a severe threat to the life or health of an endangered adult exists, immediate care or treatment is required to alleviate that threat, and the endangered adult is unable to provide or obtain the necessary care or treatment.

Emergency Services - services deployed in response to a situation in which a severe threat to the life or health of an endangered adult exist, immediate care or treatment is required to alleviate that threat, and the endangered adult is unable to provide or obtain the necessary care or treatment.

Endangered Adult - An individual who meets the criteria outlined in Indiana Code 12-10-3-2.

Exploitation - A person who recklessly, knowingly or intentionally exerts unauthorized use of the personal services or the property of:

  - An endangered adult; or

  - A dependent 18 years of age or older;

  - For the person’s own profit or advantage or for the profit of advantage of another person.

  - Includes, but is not limited to sexual misuse as well as the use of the endangered adult’s labor without pay or exerting unauthorized control over the finances or property of the endangered adult.

FSSA - The Indiana Family and Social Services Administration, including its subdivisions, including but not limited to the Division of Aging.

HIPAA - The Health Insurance Portability and Accountability Act of 1996, the Health Information Technology for Economic Clinical Health Act (“HITECH”), and the associated privacy and security rules located in 45 CFR §§ 160 and 164.

Hoosier - A resident of Indiana.

IN211 - Indiana 211 (IN211) is a division of the State of Indiana Family and Social Services Administration. IN211 provides free, unbiased and confidential referrals to resources to meet the specific needs of Hoosiers.

Intake Reports - a term that encompasses all reports from any reporting method that are sent to the screening center for processing and either screened in as a case or screened out by an APS worker.

Mental Capacity - the ability to make an informed decision by understanding a situation, the options available, and the consequences of the decision. It also includes the ability to use or think about information, remember it, and communicate the decision to others.

NAPSA - National Adult Protective Services Association (NAPSA) is a national non-profit 501 (c)(3) organization with the goal of providing Adult Protective Services (APS) programs a forum for sharing information, solving problems, and improving the quality of services for victims of elder and vulnerable adult mistreatment.

Neglect - The person caring for the individual cannot provide adequate food, clothing, shelter, or medical care.

Preponderance of Evidence - The facts discovered through investigation show that the existence of the allegations is more probable than not. The likelihood that battery, exploitation, or neglect of an endangered adult is present in the situation is greater than 50%.

Quality Assurance (QA) - A systematic process to ensure a product or service being developed is meeting specified requirements.

Respondent - The bidding entity which submits a proposal in response to this RFP.

Self-Neglect - The individual is unable or fails to care for his/herself.

Substantiated or Substantiation - A judicial finding based on a preponderance of the evidence that abuse or neglect occurred. Each allegation made or identified in a given case shall be considered separately in determining whether there should be a finding of substantiated.

State - the State of Indiana and its agencies.

Unsubstantiated - The preponderance (majority) of the evidence gathered and analyzed in an investigation indicates that the allegation is not true.

Vendor - A person or company that has a contract with the State to provide goods or services.

# 3.0 History and Vision for Indiana’s APS System

Adult Protective Services (APS) is a vital Indiana program established to receive and investigate reports of allegations of abuse/battery, neglect or exploitation against an endangered adult, and as appropriate coordinate a proper response to ensure safety and services in the least restrictive and person-centered manner. The Division of Aging (DA) seeks to contract with a respondent(s) to provide Adult Protective Services, through the provision of staff and management of operations for all reports received by the State of Indiana (the State).

The State currently contracts with seventeen (17) county prosecutors to administer the APS program under the supervision of the DA. Each prosecuting attorney is responsible for responding to APS intake reports located in their designated service area. Field staff are required to be county employees of the prosecutors. These county prosecutors, also currently known as APS hub units, operate semi-independently of each other by having decentralized field staff who work out of their respective county prosecutor offices throughout the state. If an APS hub unit has reason to believe that an individual who is 18 years or older is an endangered adult (as described in IC.12-10-3-2), the unit takes the following steps:

- Review the intake report for complete and accurate information. If necessary, call the reporter for more information to determine if the alleged victim meets the definition of an endangered adult.

- Make sure the intake report had an allegation of battery/abuse, neglect or exploitation.

- Create in the APS-CMS contacts of all case associates and screen the intake in or out based on the screening criteria set by the State.

- If the intake report contained information that leads the APS staff to believe there was a criminal element they would refer the intake report to law enforcement.

- Conduct an investigation to determine:

    - Alleged victim meets the definition of endangered adult.

    - Determine by the preponderance of evidence the allegations were substantiated or unsubstantiated.

- Prepare a service plan that addresses the safety and needs of the client, with the client's values, preferences in the least restrictive and person-centered manner.

By law (IC.12-10-3-2), Indiana defines an endangered adult as an adult 18 years or older, incapable of managing or directing their own care because of mental illness, intellectual disability, dementia, habitual drunkenness, excessive drug use, or other physical or mental incapacity, and must be harmed, or threatened with harm, by neglect, battery/abuse, or exploitation (Note: this definition is subject to change; the Contractor should always defer to the most up-to-date definition stated in Indiana Code). Current APS hub units are required to investigate reports of battery/abuse, neglect, and exploitation of endangered adults.

The following paragraphs provide a baseline overview of current APS operations in Indiana which should help guide an approach that best meets the future needs and objectives of the State.

In recent years, all APS county prosecutors have collectively employed approximately seventeen (17) directors; fifty-nine (59) investigators; three (3) case monitors; and eight (8) intake specialists. In 2023, APS hub units received 20,990 intake reports, which resulted in 16,472 cases. Most reports came through the IN211-managed APS Hotline and the APS website; a smaller number of additional reports came from the public directly to the local APS units. The intake reports that did not result in cases were resolved over the phone or referred to other agencies for service. The intake reports that were screened in were assigned a triage level and assigned to an investigator. Annual case volume varies widely between the APS hub units; in 2023, the APS hub unit with the lowest case volume received 227 cases while the APS unit with the largest case volume received 3,803 cases. Case volume is anticipated to minimally match and likely exceed current numbers employed by the State given anticipated growth due to system restructuring and an aging population. Table 1 below shows the number of intake reports and substantiation status for 2023.

Table 1: 2023 Intake Report & Case Figures

| Allegation | Reports Received |
| --- | --- |
| Neglect | 5,666 |
| Self-neglect | 5,969 |
| Battery/Abuse | 1,533 |
| Exploitation | 3,304 |
| 2023 Grand Total | 16,472 |

During the Second Regular Session of the 123rd General Assembly of Indiana (2024), the legislature passed an Adult Protective Services Bill (IN SB0109) that broadens the structural possibilities of Indiana APS. The bill, an adjustment affecting IC.12-10-3-7, removes language mandating that the DA contract only with a prosecuting attorney or governmental entity and instead allows the DA to contract with any entity qualified to provide adult protective services. The DA is taking these regulatory updates from the federal and state level as an opportunity to reimagine its APS program by engaging in a competitive bid process.

In this new vision for APS in Indiana, the DA will assume an administrative role, directing the collaborative efforts of two primary Contractors: an APS Staffing & Operations Contractor and an APS Quality Assurance (QA) Contractor. The APS Staffing & Operations Contractor, being procured by this RFP, shall provide services in response to reports of adult endangerment including but are not limited to, the following:

- Review all intake reports for completeness, create contacts of all associates in the report within APS-CMS.

- Screen intake reports in or out based on the State’s criteria for screening then assign a triage priority level and assign an investigator to conduct an investigation.

- As a measure of last resort, coordinate emergency protective services pursuant to IC.12-10-3-28 and respond to emergency situations in conjunction with law enforcement and emergency responders, as appropriate.

- Conduct an investigation by collecting factual information associated with the case, conduct a face-to-face visit with client/s associated with the allegations.

- Conduct an assessment of the situation to determine if the client is potentially an endangered adult.

- Document all information, to include but not limited to case notes, pictures, videos, written statements, recordings etc. into the APS-CMS within 36hrs from receipt.

- Determine a finding for the allegation(s) based on the information collected. If the elements in the case reach the preponderance of evidence, the allegations will be substantiated, and an assessment of the client’s needs will be conducted. If the elements in the case do not reach the preponderance of evidence, the allegation will be identified as unsubstantiated and referrals for services will be given as appropriate.

- Upon the determination of the finding, substantiated cases will require the completion of the service plan in the APS-CMS with all 5 domains in the system completed. Service plans, with the cooperation of the client, assess client needs, preferences, safety, and connect them with appropriate contacts or services, including but not limited to legal intervention, coordination with service providers, and monitoring of services. Service planning is person-centered and uses the least restrictive means necessary to keep a client safe.

- Shall attend all trainings provided by the State.

- Maintain confidentiality regarding APS investigations in accordance with the IC.12-10-3-15.

- Secure appropriate legal counsel, free from any conflict of interest, to fulfill roles that include, but are not limited to:

  - As appropriate, petitioning a court of law for protective orders, suggest or refer individuals to guardianships, and to testify in court regarding cases as needed.

  - Develop guidelines to determine when court orders are needed; protective orders and guardianships should only be used when other, less restrictive options have been exhausted.

  - Provide guidance surrounding power of attorney Rep-Payee and legal appropriate legal guardianship; APS units cannot serve as guardians.

- Work with the Indiana Department of Health regarding reports of endangered adults in licensed healthcare facilities (IC. 12-10-3-17)

- Ensure that any conflicts of interest are appropriately screened.

  - Ensure that all staff, regardless of whether a conflict exists, are educated on a code of ethics.

  - Ensure that staff are not serving in dual roles, such as also providing services a client needs, and that staff and their families do not have a financial interest in entities to which clients are referred.

- Establish a process to receive and assess any client complaints. The Contractor must share any complaints with the State and QA Contractor its designees, as applicable, and discuss any issues as directed by the State.

- Support on various ad hoc requests and projects from the State.

The APS Quality Assurance Contractor, which will be procured by a separate RFP, will independently monitor the quality and effectiveness of the services provided by the APS Staffing & Operations Contractor. A vendor who is accepted as the APS Staffing and Operations Contractor is ineligible for the role of APS Quality Assurance Contractor.

The State is looking to contract with a Respondent(s) that not only meets all mandatory and functional requirements, but also shares in the State’s objective of providing all qualifying, adult Hoosiers with high quality, effective adult protective services in the least restrictive and person-centered manner possible. In a time when the State is anticipating an increased need for adult protective services, due to shifting demographics and new state and federal requirements, it is crucial that the APS Staffing & Operations Contractor be ready to work collaboratively with the State and other partners to protect and serve one of the State’s most vulnerable populations.

# 4.0 Mandatory Requirements

To be eligible for consideration by the State, a Respondent must meet the following Mandatory Requirements:

- The Contractor must have relevant experience undertaking projects to support endangered adults.

2. The Contractor must be independent from the APS Quality Assurance Contractor.

- The Contractor must be able to provide staffing and operations services statewide and population-wide within Indiana as defined by Section 6.0 below.

- The Contractor must comply with all applicable administrative codes, rules, regulations, laws, policies, procedures, and guidelines.

- The Contractor must comply with all Indiana Office of Technology (IOT) security policies (available at http://www.in.gov/iot/2394.htm) as well as all FSSA specific policies (set forth in greater detail in Attachment B, Sample Contract). These security policies are subject to modification during Contract negotiations pending changes to pending Federal law and FSSA policy.

# 5.0 Overview of APS System Functions

The steps below outline the envisioned structure of the new APS model detailing an APS report from intake to closure. This list is not exhaustive however all the steps below must be fulfilled. The Contractor shall follow all operational and best practices policies and procedures from the State, even beyond what is explicitly named below.

- Step 1: Report Intake and Screening

An APS intake report is a request from anyone for APS intervention in an alleged case of an endangered adult in Indiana. APS receives intake reports primarily through the APS hotline which is managed by IN211 (~54%), an online report form located at https://aps-govcloud.my.site.com/APSOnlineReport/s/ (~38%), and direct reports to local APS offices (~8%). This third option to submit a report directly through a local APS office is being phased out. IN211 will conduct intake for telephone reports received through the APS hotline before sending the report to the Contractor. IN211 is not responsible for screening reports. Online reports will be sent directly to the Contractor.

The Contractor must maintain a centralized screening unit that will receive all reports and then screen, triage, and assign each report out to regional investigative units. Reports will either “screened in” or “screened out” by the Contractor based on the information outlined below:

  - Screened out Criteria: For an APS report to be screened out, it must be determined by the responding worker that the report is not under the jurisdiction of Indiana APS. Reports made to APS may be screened out for reasons including, but not limited to the following:

    - the alleged incident occurred outside of Indiana,

    - the alleged incident is not battery/abuse, exploitation, and neglect,

    - no location is identified to locate the alleged victim,

    - the reporter requests information or guidance rather than service,

    - the alleged incident does not otherwise meet the criteria for screened in report as defined by APS regulations, policies, and procedures.

The Contractor must use a standard screening tool that has been reviewed and approved by the State.

  - Screened Out Next Steps: For reports that are screened out, the reporter shall either be directed, via warm-handoff or referral, to another service or agency or informed that their report does not qualify for further APS action.

  - Screened in Criteria: For an APS intake report to be screened in, it must meet the elements to be screened in as defined by the APS regulations, policies, and procedures. They include but are not limited to the following:

    - The Intake report must have an alleged victim that is 18 or older and has a mental or physical disability in accordance with the state statute's definition of an endangered adult.

    - The intake report must include an allegation of battery/abuse, neglect and or exploitation.

    - The intake report must show the alleged victim is harmed or threatened with battery/abuse, neglect and or exploitation.

    - Determinations on eligibility are part of the investigative process with final eligibility determinations made during Step 4: Case Findings (Section 5.0) based on a preponderance of evidence.

  - Incomplete Reports: If a report contains insufficient information to properly determine whether to screen it in or out, the Contractor must do all that is reasonable to gather the necessary information, including but not limited to calling the reporter.

  - Improperly Screened Reports: If it is believed that a report was improperly screened, the Contractor must have a process for reconsidering the screening of a report.  The function of the unit supervisor will play a key role in this process. The State reserves the right to review this process at any time.

    - In order to appropriately monitor improperly screened reports, a team member from the State or a State designee the QA Contractor will monitor all screened out reports.

    - Additionally, the Staffing & Operations Contractor function of the unit supervisors shall monitor and dispute screened-in cases as necessary.

- Step 2: Assignment of Reports

Once a report is screened in, the Contractor will assign a triage priority level to indicate case urgency and establish a resolution timeline. The Contractor must triage as directed by the State, using the triage priority levels described below and defined in Section 6.0:

  - Priority A: Immediate Risk - Emergency 24-Hour Response Required

    - If the reporter claims that the alleged victim is being seriously harmed or risks dying from abuse or neglect, the Contractor must make face-to-face contact within 24 hours of receipt of allegations.

  - Priority B: High Risk - Urgent 4-Day Response Required

    - If the reporter claims that the alleged victim has a high risk of being harmed by being battered, neglected, exploited, or threatened with the same, the Contractor must make face-to-face contact within four (4) calendar days of receipt of allegations.

  - Priority C: Non-immediate Risk - Standard 20-Day Response Required

    - Current Indiana Code maintains that if the reporter claims that the alleged victim is being battered, neglected, or exploited but the situation is non-emergent and not urgent, the Contractor must make face-to-face contact within twenty (20) calendar days of receipt of allegations. In all cases, a face-to-face visit should be done, however in extenuating circumstances i.e. health epidemic, safety measures can be put in place to facilitate the need and protect both parties.

        - Note: Face-to-face contact should be attempted in all cases, however in extenuating circumstance (e.g. a health epidemic), safety measures can be put in place to facilitate the need and protect both parties.

Once a report is assigned a triage priority level, the report officially becomes a case, and the designated triage clock begins. As such, the Contractor must then swiftly assign the case to an investigator based on the location, availability, and timeliness required by the case.

- Step 3: Investigation of Case

The Contractor shall prepare to investigate a case per the policies and procedures provided by the State and pursuant to all relevant rules and law and following the guidance below:

  - Use a standard assessment tool approved by the State to ensure investigator and client safety and assess for emergency needs.

  - Take all foreseeable and necessary precautions to protect the safety of the client, investigators, and any other involved parties during an investigation.

    - Per state policies and procedures, several safety factors will be tracked in the APS-CMS.

    - If at any point, a possible risk to safety is revealed, the investigator must coordinate with their designated APS unit leader and/or law enforcement, as necessary.

    - The Contractor shall use a pre-existing safety feature within APS-CMS that enables investigators to indicate when they are on a client visit resulting in automatic checks via their phones. If the investigator does not respond to the check, the APS unit supervisor is immediately informed that the investigator is on a client visit and not responding.

    - The Contractor shall develop and use its own safety standard operating procedures and share with the State and QA Contractor its designees for approval.

  - Document preparation actions in the case report using the APS-CMS provided by DA.

  - Review the intake information and gather as much collateral information as possible. If appropriate, speak to other people listed in the intake notes (e.g. family members, friends and neighbors, anyone that would have knowledge of the allegation).

  - Call reporter to gather additional information as needed.

  - Review the APS-CMS database to see if the alleged victim has a previous case report, unless it has already been included in the intake notes.

    - If an APS case report exists, review the case notes and/or contact the personnel familiar with the case.

    - If there is a history of violence, check with law enforcement to see if they are known or if there are any court orders in place.

    - As necessary, review other available resources and/or databases.

  - Coordinate with other agencies as appropriate including but not limited to:

    - Bureau of Developmental Disabilities

    - Division of Family Resources (Medicaid, TANF, SNAP)

    - Indiana Department of Health

    - Department of Child Services

    - Local Law Enforcement Agencies

  - Shall refer reports concerning individuals who are residents of health facilities licensed under IC.16-28 to the Indiana State Department of Health immediately; and cooperate with the Indiana State Department of Health in these cases and carry out the remaining activities of case processing at the request of the department (IC.12-10-3-17).

  - Decide on the type of visit:

    - Announced or unannounced.

    - Alone or with a partner.

    - Visit with other non-Contractor personnel (i.e. caseworker, neighbor(s), family member(s)).

    - At the alleged victim’s home or at a neutral site.

  - Prepare a list of questions based on the information obtained when researching the case. The Contractor must inform clients of their rights to confidentiality, to refuse services, and to speak to APS. The Contractor must ensure this information is presented in a way that is understandable and accessible to the client. The Contractor also must keep a person-centered and trauma-informed perspective with clients.

  - Determine the best time of day to interview the alleged victim.

  - The Contractor shall gather and assess the facts of the of a case as directed by the State and following the guidance below:

  - The Contractor will conduct interviews with the alleged victim, witnesses and all case associates to gather information, documents, pictures, videos, etc. and record them in the APS-CMS within 36hrs of obtaining the information. to gather and archive testimonial evidence from the alleged victim, witnesses or others with knowledge of the allegations.

  - Alleged Victim - The Contractor will conduct or arrange an individual face-to-face interview with the alleged victim of neglect, battery/abuse or exploitation. The Contractor will need to consider client safety, like if the alleged perpetrator is in the home during the time of interview. The State will provide guidance and training for these scenarios.

  - Alleged Perpetrators - The Contractor will conduct or arrange an interview with the alleged perpetrator of battery/abuse, neglect or exploitation unless:

    - The alleged perpetrator cannot be identified or cannot be located.

    - The alleged perpetrator refuses an interview.

    - Attorney representing the alleged perpetrator informs the Contractor that their client will not participate.

    - Law enforcement requests the alleged perpetrator not be interviewed or law enforcement has already conducted an interview, and the Contractor is able to obtain a copy of the report.

    - The interview would place the alleged victim in greater danger.

    - The alleged perpetrator is a minor and the parents/guardian refuse to allow the interview.

  - Other Interviews - Unless an interview could cause undue harm to the client or the client has not given permission to speak with an individual, the Contractor may interview other individuals with knowledge of the allegations in order to:

    - Validate allegations.

    - Assess client’s overall situation, needs and risk.

    - Resolve discrepancies in the information gathered in the case.

  - The Contractor will obtain, and archive documentary information gathered in the case in the APS-CMS.

  - The Contractor will gather all types of documents, photos, video, recordings etc. to assess the alleged victim’s situation and help determine if the allegations will be substantiated. Examples of collected information by type can be found below:

    - Testimonial Information - Written or oral statements from alleged victim, alleged perpetrator, other witnesses

    - Documentary Information

        - Business records

        - Legal documents (e.g. power of attorney, letters of guardianship, wills and trusts)

        - Medical records

        - Financial documents

        - Computer Files

    - Demonstrative Information – Images of physical information

        - Photos

        - Diagrams

        - Objects

        - Injuries

  - The Contractor shall not take physical possession of any documents, if the information is important to the case copies or photos of the necessary information should be taken.

  - The Contractor shall not be responsible for investigating any criminal activity. If criminal conduct is suspected, investigators will contact law enforcement when dealing with evidence.

  - Contracted APS employees shall be required to carry their state-issued photo ID for all on-site investigation activity.

  - The Contractor shall enter all collected documented information into the APS-CMS within 36hr after being obtained.

- Step 4: Case Findings

Case findings is considered to be a two-step process. The Contractor shall first determine if the allegation is substantiated and then assess the situation of the alleged victim. In some cases, the allegation will not be substantiated but the assessment will show that the alleged victim is in need of services. Depending on the severity of the need, the Contractor will determine which is most appropriate between a service plan or a referral made to the appropriate agency. All substantiated cases will require a service plan. Further details about the Case Finding process are outlined below.

Case Finding Determinations:

  - The Contractor shall make a finding on an investigation no later than 30 days from the date of the initial report of neglect, battery/abuse, or exploitation. If a finding cannot be reached within 30 days, an extension may be requested by the Contractor for approval by the APS supervisor in appropriate cases.

  - The Contractor must make a finding of “substantiated” when facts obtained during an investigation provide a preponderance of evidence that is sufficient to lead a reasonable person to believe that neglect, battery/abuse or exploitation of an endangered adult is more likely to have occurred than not.

  - The Contractor must make a finding of “unsubstantiated” when facts obtained during an investigation are unable to provide a preponderance of evidence or that there is insufficient information to lead a reasonable person to believe that neglect, battery/abuse or exploitation of an endangered adult is more likely to have occurred than not.

  - If ever it is unclear whether an investigation is able to provide a preponderance of evidence, review must be requested from the assigned case supervisor who will make the determination of “substantiated”, “unsubstantiated”, or “lacks sufficient information”.

  - The State reserves the right to review case information within the APS-CMS at any time.

  - The Contractor will document all findings, along with all collected information leading to the finding in the case report using the APS-CMS.

- Step 5: Documentation of Findings:

  - The Contractor shall document the findings in the APS-CMS within 36 hours of making the finding. The Contractor must provide a narrative in addition to all case notes for all documents, photos, videos, recording etc. collected. The narrative shall be logical, clear, concise and free from factual errors. Each finding shall have its own separate justification showing that the Contractor personnel:

    - Carefully evaluated all collected information relevant to the case, and the definitions of neglect, self-neglect or exploitations that led to their determination of the finding for each allegation.

    - Assessed credibility of all the information, documents and/or statements collected.

    - Explained the reasoning behind the finding for each allegation.

  - In the APS-CMS, the Contractor must categorize all findings as follows:

    - Substantiated-Criminal: The criminal allegations were substantiated, and the case was referred to law enforcement.

    - Substantiated-Services: The allegations were substantiated; a service plan was completed, and the case was referred to a case manager or social services provider for the provision of services.

    - Substantiated-Criminal & Services: The criminal allegations were substantiated; the case was referred to law enforcement, a service plan completed, and referral made to a case manager or social service provider for the provision of services.

    - Investigation Pending: A finding has not been made regarding the allegations. The investigation is still ongoing.

    - Unsubstantiated: The allegations were unsubstantiated, the client is referred to additional services if warranted, and the case closed.

- Step 6: Service Planning

  - Service planning assesses the client's needs and engages the client by considering their wishes and preferences. The plan uses the least restrictive services needed to protect the client. APS staff will monitor the provision of services and that services are meeting the client's needs. Other individuals, such as caretakers, family, or friends may be involved in the creation of the plan.

  - If a client has a guardian, service planning will be done with the guardian and the client. In the instance where an involuntary protective services order exists, service planning may occur without the consent of the client but as much as practicable, client wishes, values, and preferences should be considered.

  - The Contractor shall be responsible for creating a comprehensive service plan in the APS-CMS for each case following assessment. This plan must address all five domains of APS as defined by the National Adult Protective Services Association (NAPSA) and outlined below:

    - Safety/Risk: complete the Safety/Risk Problem, Safety/Risk Objective, and Safety/Risk Services fields.

    - Living Environment: complete the Living Environment Problem, Living Environment Objective, and Living Environment Services fields.

    - Physical/Medical Impairments: complete the Physical/Medical Impairments Problem, Physical/Medical Impairments Objective, and Physical/Medical Impairments Services fields.

    - Financial/Social: complete the Financial/Social Problem, Financial/Social Objective, and Financial/Social Services fields.

    - Capacity: complete the Capacity Problem, Capacity Objective, and Capacity Services fields.

This service plan should be created with the client maximizing their engagement and respecting their values and preferences. Effective service planning is essential for supporting clients and reducing recidivism. The State retains the right to review these service plans at any time.

- Step 7: Monitoring

  - The Contractor must ensure that case assessment and service planning follow the procedures outlined in the DA's training. A standardized tool, designed to address the client's safety and needs during the triage and service planning process, must also be utilized during case monitoring to ensure proper safety procedure was followed and the needs of the client were met to the best of the APS provider’s ability. Case monitoring should serve as a check to ensure the following:

    - A service plan was created

    - The service plan follows Indiana Code to include the least restrictive protective services necessary to attain the objectives of the plan

    - The APS provider made a thorough attempt at client outreach and communication prior to case closure

  - The State reserves the right to request a review, update, or replace this standardized tool at any time.

- Step 8: Case Closure

The Contractor will close a case when the following is completed:

  - All reasonable measures were taken to ensure the safety of the client, or the client was removed from the threat.

  - All actions observed are documented in case notes and collected materials are entered in the APS-CMS system.

  - Case notes document why the case was closed, and how/when the client was notified.

  - The allegations have a finding (substantiated or unsubstantiated) based on the preponderance of the evidence. All information associated with the findings are documented in the APS-CMS.

  - A needs and risk assessment has been conducted of the circumstances surrounding the client to determine their needs, using person-centered tools, and the least restrictive measures. All notes associated with the needs & risk assessments are documented in the APS-CMS.

  - A service plan has been developed in the APS-CMS.

    - All 5 domains are completed if the findings were substantiated, and a copy given to the client or their guardian/POA or family member responsible for their care.

    - In cases that are unsubstantiated, the assessment may still show a need services beyond a simple referral. If this is the case, a service plan should also be developed for the unsubstantiated case client.

    - Risk factors are identified.

    - Protective services were provided if needed.

    - All necessary referrals for service were made.

    - In the event the client refuses services, the refusal needs to be documented and signed by the client if possible. The case can then proceed to closure without monitoring or follow-up.

  - The Contractor will monitor all services established according to the service plan.

Once the above has been completed or addressed the case can be submitted to the supervisor for closure.

- Step 9: Case Follow Up

  - The Contractor must develop a case follow-up survey program that will be distributed to APS clients. This tool can provide the Contractor with valuable information on the quality of services, and if they are meeting their goals to serve the citizens of Indiana.

    - The Staffing & Operations Contractor shall work alongside the QA Contractor State and its designees, as applicable, to monitor case follow-up outreach and ensure cases are being handled according to APS standards.

    - In addition to the case follow-up outreach, a grievance process shall be made available to clients and others interacting with the APS system. Grievances shall be reviewed by the Staffing & Operations Contractor, as well as the APS QA Contractor the State, and its designees and will be followed up on at the request of the APS QA Contractor State and its designees.

    - The State maintains the right to review case follow-up outreach responses and/or grievances by request.

# 6.0 APS Staffing & Operations Contractor Functional Requirements

The Contractor must fulfill the functional requirements outlined below.

- Statewide Coverage

  - The Contractor must provide Adult Protective Services to Hoosiers in all 92 counties in Indiana. To provide services in all areas, the Contractor and State will work collaboratively to develop APS units, staffed by the Contractor, covering all areas of Indiana.

    - Contractor staffing should reflect population it serves as the anticipated caseload is often driven by the size and demographics of the population served. As such, APS unit design should account for population centers and the drive time for staff, since APS investigators routinely conduct home visits. For instance, the APS unit serving Marion County will have more staff than the APS unit serving a rural county but the staff serving the rural county should be prepared for longer drive times.

- Population Wide Coverage

  - The Contractor shall provide services to all populations eligible for the Indiana's APS program. The current APS eligibility requirements are as follows, but the Contractor must always defer to Indiana Code and guidance from the State when determining eligibility:

    - An individual who is at least 18 years of age

    - Incapable by reason of mental illness, intellectual disability, dementia, habitual drunkenness, excessive drug use, or other physical or mental incapacity, of managing or directing the management of the individual’s property or providing self-care; and

    - Harmed or threatened with harm as a result of:

        - Neglect

        - Self-neglect

        - Battery

        - Exploitation of the individual’s personal services or property

  - As noted above, the Contractor shall defer to Indiana Code when determining an alleged victim’s eligibility to receive adult protective services. If any confusion exists about an alleged victim’s eligibility to receive adult protective services, the State reserves the right to review eligibility determination.

- On-Time Coverage

  - The Contractor shall have the appropriate staff on-call to respond to all emergency APS reports within 24 hours according to the priority areas outlined below.

  - If there is an instance where the alleged endangered adult cannot be contacted in person due to not being home or refusing to answer the door, the Contractor must make three attempts within the required response time. Each attempt must be documented with photos in the APS-CMS.

  - The Contractor shall respond to all incoming APS cases “on time” according to its assigned triage priority as described in Section 5.0 and defined below:

    - Priority A: Immediate Risk - Emergency 24-Hour Response Required

        - If the reporter claims that the alleged victim is at an immediate risk of death, irreparable harm, or significant loss of income, assets, or resources, the Contractor must make face-to-face contact within 24 hours of receipt of the allegations.

        - If there is immediate physical danger, APS must contact law enforcement as soon as possible.

        - When a case receives a Priority A assignment, the Contractor will closely monitor the case preparation to ensure the investigator has all the resources and support needed to meet the 24-hour response time.

        - In cases where immediate risk is suspected, the Contractor shall apply a standardized decision-making tool to assess the immediate safety and risk factors affecting the client or APS worker when responding to the report

        - In some situations, like if the client withdraws consent or cannot consent and is faced with a life-threatening emergency, an emergency protective order may need to be filed pursuant to IC. 12-10-3-28

    - Priority B: High Risk - Urgent 4-Day Response Required

        - If the reporter claims that the alleged victim has a high risk of being harmed by being battered, neglected, exploited, or threatened with the same, the Contractor must make face-to-face contact within four (4) calendar days of receipt of allegations.

    - Priority C: Non-immediate Risk - Standard Response Required

        - Current Indiana Code maintains that if the reporter claims that the alleged victim is being battered, neglected, or exploited but the situation is non-emergent and not urgent, the Contractor must make face-to-face contact within twenty (20) calendar days of receipt of allegations.

- Substantiation Minimum Standards

  - The Contractor shall follow a clear and measurable minimum standard for case substantiation set by the State that includes, at baseline, the preponderance of evidence as a requirement for a case to be deemed substantiated and further action taken to assist the client.

  - The State reserves the right to alter, update, or replace the Contractor’s minimum standards for case substantiation.

- Case Resolution and Closure Process

  - Requirements for documentation in the case record are the same regardless of whether the report is determined to be substantiated or unsubstantiated.

    - The record is subject to review by supervisors, program field representatives, and other staff as appropriate.

    - The case record can be ordered or subpoenaed in subsequent private guardianship or other proceedings if the allegations investigated are pertinent to the proceeding. The Contractor needs access to legal counsel for these types of scenarios.

  - Training Minimum Standards

    - The Contractor will be responsible for training for its staff, this may include but is not limited to internal training, professional development, licensure training, and social work training. The State will provide training related to APS functions including National Adult Protective Services Association’s (NAPSA) core competencies, continuing education, and other APS-specific curriculum. All APS Staffing & Operations Contractor staff, including those in a supervisory, investigative, and/or monitoring function must attend the core competency training within the first year of employment and become NAPSA certified when they are qualified to do so. The State APS training team will assist in accomplishing this goal. All costs associated with certification will be assumed by the Contractor. The Contractor must attend all training sessions with the State.

# 7.0 Collaboration with Internal Partners

The Contractor must collaborate with a wide array of stakeholders in the APS ecosystem including but not limited to other State divisions and agencies. Collaboration is a vital part of providing protective services. Some examples of the notable internal partners are listed below:

- Collaboration with Indiana 211

  - Indiana 211(IN211) is a division of the State of Indiana Family and Social Services Administration. IN211 provides free, unbiased and confidential referrals to resources to meet the specific needs of Hoosiers. The team is composed of experienced and trained Community Navigators, a select group of whom service the APS Hotline for intake of reports. An APS intake report is an inquiry from professionals or the general public for APS to intervene in an alleged allegation of battery/abuse, neglect, or exploitation. APS receives inquiries from the APS hotline number, which is managed by 211; the website online report form; and direct calls or in person to the local APS offices. Currently, approximately 54% of APS reports come through the IN211-managed APS Hotline and 38% are received as online reports through the APS website and 8% come through local APS offices. Direct reports made to local APS offices are being phased out.

  - When an intake report is received, the centralized unit reviews the information and will make attempts to gather more information if needed to aid in the screening process, they will make all known case associates into contacts in the APS-CMS maintained by the Contractor and provided by the State. The Contractor and designated staff will screen the report in or out, determine the triage priority assignment and assign the case to the appropriate unit. The Contractor must keep all reports confidential in conformance with Indiana Code. If the Contractor conducts an investigation, an investigator may contact the individuals reported for additional information; however, the Contractor, Indiana APS or IN211 does not discuss ongoing investigations and will not provide information regarding the details or the status of the investigation to the public.

2. Collaboration with APS Quality Assurance Contractor

2.1. The APS Quality Assurance Contractor (also referred to as the QA Contractor) is an additional third-party contractor that will be hired by the state to oversee the entire APS process and ensure quality is consistently meeting standards across the entire state. The APS Quality Assurance Contractor is responsible for the review and commitment of all functional requirements for the APS Staffing & Operations Contractor including, but not limited to statewide coverage, population-wide coverage, on-time coverage, etc.

- Collaboration with DA

  - DA is the Contractor’s most important relationship, as it is the division responsible for the oversight and management of this contract. Please see Section 13.0 of the Scope of Work for details on resources DA may provide to the APS Staffing & Operations Contractor.

# 8.0 Collaboration with External Partners

The Contractor must collaborate with a diverse range of stakeholders within the APS ecosystem, including but not limited to, service providers, healthcare entities and workers, law enforcement, consumer-rights groups, advocacy groups, and other agencies. The Contractor is responsible for having multidisciplinary teams for general relationship building and collaborative efforts. Collaboration is essential to delivering effective protective services. Notable partners include the following examples:

- Collaboration with Law Enforcement

  - The Contractor shall collaborate with law enforcement. All cases with a criminal element will be referred to law enforcement. Other situations in which law enforcement should be involved include, but are not limited to:

    - Immediate physical danger to the alleged victim

    - Substantiated or suspected criminal allegations involved in a case

    - Any party involved in the case has a history of violence

- Collaboration with Prosecutors

  - The Contractor shall collaborate with the local prosecutors' offices during the first several months of the contract to ensure a smooth transition of information and services.

  - Once services have fully transitioned to the Contractor, collaboration with local prosecutors will occur only once a case has been substantiated and it is determined that legal action is required.

- Collaboration with State Agencies

  - The Contractor shall collaborate with other State agencies to aid in the provision of appropriate services for APS clients. These agencies may include, but are not limited to, Medicaid, Behavioral Health and Human Services, and the Bureau of Disabilities Services.

- Collaboration with Service Providers and Consumer-Rights Groups

  - Any APS service provider for the state of Indiana must collaborate extensively with pre-existing service providers and consumer-rights groups to aid in the timely resolution of APS cases. These providers may include but are not limited to LTC ombudsmen, nursing, assisted living, healthcare providers, Indiana’s Area Agencies on Aging (AAA) and Indiana Legal Services.

# 9.0 Staffing

The Contractor shall ensure that there is sufficient staff to fulfill all of the functions outlined below. Additional guidelines and requirements are listed in Attachment M.

- General Staffing Requirements

  - The Contractor shall ensure that there are sufficient staff and resources available to ensure that staff can open APS cases within one day of receiving the intake report and close APS cases in a timely manner according to policy procedures from the State. The Contractor shall screen intake reports the day they are received or the next business day.

  - The Contractor must work collaboratively with the QA Contractor and the State and its designees, as applicable, to keep record of performance. The Contractor shall share all schedules, case documents, performance data, and communication with the State as requested.

  - The Contractor shall ensure that all staff completes all State mandated training as they are released and assigned by the specified due date.

  - The Contractor shall ensure background checks are conducted prior to hiring and APS staff member.

  - The Contractor shall outline the hiring policy and confirm a clear pathway to hire existing APS staff employed by the County Prosecutor Units and offer full-time employment for all compliant, eligible staff who will be brought on as employees of the Contractor (or applicable subcontractors) or as "contract-to-hire.”

  - The Contractor shall be responsible for ensuring that all vital functions are carried out. It is preferred that each function is performed by a different staff member. However, recognizing that some units may operate in areas with smaller populations and fewer staff, the State permits the same staff member to perform multiple vital functions, as long as each function is adequately fulfilled and previously approved by the State.

  - Contractor is required to establish an employee review process if they don’t have one.

  - Contractor shall ensure that all APS staff carry a photo ID to provide to clients to identify them.

  - The Contractor must develop a case follow-up survey program that will be distributed to APS clients. This tool can provide the contractor with valuable information on the quality of services and whether they are achieving their goals to serve the citizens of Indiana.

  - The Contractor shall keep a staffing directory for each unit and send a copy to the state with employee changes with in 72 hours of hiring an employee and immediately when an employee is removed or leaves.

- Vital functions of staff must include, at a minimum:

  - Leadership/Director Function: Those in a leadership function will be responsible for administrative oversight of an individual APS unit in regard to planning, coordinating, and directing the activities of the unit to carry out its mission to provide protective and supportive services to endangered adults. This function is responsible for maintaining and growing cooperative working relationships with the Division of Aging, the APS Quality Assurance Contractor, service providers, healthcare entities/workers, law enforcement, and a wide array of stakeholders in the APS ecosystem, including other private and government agencies. This function is also responsible for monitoring new developments and best practices which may affect APS services staffing and operations and/or which could be incorporated into APS programs and procedures to improve the quality and range of services offered and the efficiency with which service is provided to APS clients. This function is responsible for the final review of all internal audits and evaluations for accuracy and consistency prior to submission to the DA or the APS Quality Assurance Contractor. This function also oversees the implementation of corrective actions in the APS units and ensures compliance with all State mandates and timeframes. Leadership may be tasked with being an arbitrator when there is a dispute or confusion around appropriate triage level but not as individual who provides triage on a day-to-day basis. This is typically represented as the APS Regional Director.

  - Managerial/Supervisory Function: Those in a managerial and quality assurance function will be responsible for supervising a team of APS staff, providing guidance, support, and conducting performance evaluations. This function oversees the management of cases, ensuring timely and thorough investigations, case documentation, and interventions of investigators. This function also develops regular reports on unit performance, case outcomes, and any compliance issues. This is typically represented as the APS Supervisor or Manager for each unit.

  - Investigative Function: Those in an investigative function will be responsible for conducting investigation to respond to reports of battery/abuse, neglect, or exploitation of endangered adults. This function must gather information through interviews with the alleged victim, family members, caregivers, and other relevant parties. This function will conduct visits to the homes or care facilities of the individuals involved in a report to assess the situation and must maintain detailed records of investigations including findings and actions taken. Additional detail on this function can be found in Section 5.0. This is typically represented as the APS Investigators for each unit.

  - Monitoring Function: Those in a monitoring function will be responsible for assisting in the development of a service plan. They will also monitor the timeliness of establishment of services for clients and evaluate the effectiveness of assigned services. This is typically represented as the APS Investigators or Case Monitors for each unit.

  - Screening and Triage Function: Evaluate, assess, and assign reports received online or via IN211. This function does not belong to any particular region and will forward reports to the appropriate supervisor/manager. This is typically represented by Screening Specialists.

- The functions above are usually handled by various staff members, including but not limited to the roles of APS Regional Directors, APS Unit Supervisors, Investigators, Case Monitors, and Screening Specialists. The Contractor has the discretion to determine the titles used, but all functions must be adequately addressed. Please see Attachment M for additional detail into expected job functions.

- The Contractor shall develop and maintain a Staffing Plan that shall:

  - Contain an administrative organizational structure that meets or exceeds the responsibilities described in this Scope of Work;

  - Describe the overall management and supervisory structure including lines of reporting (including any subcontractors);

  - Provide a plan for monitoring and evaluating staff, including but not limited any corrective action planning;

  - Explain how the staffing plan accommodates potential increases/decreases report volume and staff attrition;

  - Describe how the Contractor will mitigate turnover rates, fill vacancies in a timely manner as determined by the State, and approach project staffing in a way that service delivery and support is not disrupted in any way;

  - Ensure that all Contractor employees are trained on the program policies and procedures of the Indiana APS operation and will utilize the State-provided trainings;

  - Contractor staff may not work in the direct line of supervision of or conduct training for a relative who is employed by the State. “Relative” means any of the following: a spouse, parent or stepparent, child or stepchild, brother, sister, stepbrother or stepsister, niece or nephew, aunt or uncle, and daughter-in-law or son-in-law. An adopted child of an individual is treated the same as a biological child of the individual. “Brother” and “sister” include a brother or sister who share at least one common biological parent. The Contractor shall require Contractor staff to report to the Contractor if they work in the direct line of supervision of or conduct training for a relative who is employed by the State;

  - Throughout the duration of the Contract, the Contractor must maintain staffing at the level identified in their approved staffing plan. The Contractor may not substitute any other technology for staff or in-person investigations unless given explicit State approval.

# 10.0 Quality Assurance

The Contractor must ensure that Quality Assurance is a core component of their delivery, more information on how this will be fulfilled is outlined below.

- The Contractor shall design and submit a quarterly summary report on QA activities to the State and its designees, as applicable APS QA Contractor, starting after the completion of the first quarter of operations. The QA report shall address, but not be limited to, the following QA initiatives and monitoring activities:

  - Problem areas identified;

  - Compliance and non-compliance of contract requirements;

  - Contractual policies and procedures;

  - Corrective actions implemented, with outcomes summarized;

  - Corrective actions to be implemented with time frames;

  - Investigations completed, with worker responsible;

  - Trends in worker performance;

  - Trends in staff turnover and vacancy;

  - Review and assessment of services available for clients;

  - Progress on correcting specific problems; and

  - Resolution of all problems.

- The Contractor shall include all relative aggregate and trended data collected during the QA and monitoring process in the QA quarterly report. The awarded Contractor(s) shall compare and indicate data collected to that of the prior quarter’s report.

- APS Staffing & Operations Contractor staff in the supervisory function shall act as the frontline of quality assurance by ensuring key points in the APS investigation meet standards such as complete documentation, case triage timelines, service plan completeness, and the requirements for case closure.

- The Contractor shall conduct an annual, year-end assessment to review performance trends and analyze any gaps in service across the entire year. This report shall be shared with the State and its designees, as applicable, QA Vendor for review. The DA reserves the right to request and review this annual report at any time.

- The Contractor shall participate in meetings with DA and its designees, as applicable, the APS Quality Assurance Contractor to review findings and jointly assess outcomes as a part of the continuous improvement.

# 11.0 Reporting

The Contractor is required to attend a monthly meeting with the State and submit reports to the State and its designees QA Contractor as directed by the State. At a minimum, the Contractor will submit the following reports. The State reserves the right to request additional recurring or ad-hoc reports.

- Monthly Update Reports

On a monthly basis, the Contractor shall participate in a collaborative touchpoint with the State to provide a verbal update on the status of all operations and any topics of interest to the State. The State reserves the right to request specific leadership positions from the Contractor be in attendance at the Monthly Update Report Meeting. At the State’s discretion, these touchpoints may be conducted in-person at the Indiana Government Center or via a teleconference platform like Microsoft Teams. These updates are an opportunity for the Contractor to communicate its progress and needs to the State. The State, in its sole discretion, may also require a Monthly Update report to be written, in lieu of verbal.

- Annual System Performance Report

Once a year, the Contractor shall provide the State with a report that details the performance of the APS System throughout the immediate year prior to the report. The report shall be a combination of qualitative narrative and quantitative metrics. The exact details of what shall be reported on will be decided by the State based on the priorities and interests of the State for the year.

- Up-to-date Organizational Charts

Within 15 days of a change to the organizational structure of the Contractor, including but not limited to, the number of investigators and case monitors serving a unit, the Contractor shall provide the State with an updated Organizational Chart.

- Ad Hoc Reports

Upon request of the State, the Contractor shall prepare a one-time report or additions to a previous report that provide further information about any area of concern or interest to the State. The State, in its sole discretion, may also request an Ad hoc report to be verbal.

- Up-to-date APS-CMS Documentation

The State and its designees, as applicable, the QA Contractor shall have continuous access to case information within the APS-CMS. The Contractor must maintain up-to-date information within the APS-CMS such that the State and its designees APS QA Contractor are able to pull comprehensive reports and overview system operations. Reports pulled by the State and its designees APS QA Contractor may include but are not limited to the following information:

  - number of reports received by each regional unit;

  - method of reporting used for each report received;

  - type of reports received by each regional unit;

  - number of cases/investigations being handled by each unit;

  - type of case being investigated (i.e. battery/abuse, exploitation, or neglect)

  - number of unsubstantiated vs. substantiated cases in each unit;

  - percentage of cases handled on time according to the assigned triage priority level

  - time from service plan creation to initial contact with services or services waitlist

  - time from service plan creation to receipt of services

# 12.0 System & Infrastructure Requirements

All systems and infrastructure employed by the Contractor must:

- Comply with Clause 12 of Attachment B DA Boilerplate Contract. These security policies are subject to modification during Contract negotiations pending changes to Federal law and FSSA policy.

- Comply with all Indiana Office of Technology (IOT) security policies (available at http://www.in.gov/iot/2394.htm), including the Information Resources Use Agreement (https://www.in.gov/iot/files/2022-IRUA.pdf).

- Protect sensitive data, including recipient data and State-issued credentials (i.e., Incumbent staff are provided State network and system credentials for those individuals who will be directly supporting the State)

- Have applicable and current first- and third-party support

- Not require any installations on State workstations and servers. In the event that installations and/or updates to State workstations and servers are required by the Contractor to access or operate any of these systems, tools, or infrastructure, the Contractor must notify the State. Any State-managed workstation and/or server installations and/or updates are subject to review and approval by the State prior to implementation. The State is not anticipating any third- party software created or owned by the Contractor to interact with State owned data, systems, etc.

- Not require the State to support any State-managed firewall configuration and/or whitelisting to support access and/or operation. In the event that updates to State- managed firewall configuration and/or whitelisting is required by the Contractor to access or operate any of these systems, tools, or infrastructure, the Contractor must notify the State. Any State-managed firewall configuration and/or whitelisting activities are subject to review and approval by the State prior to implementation.

- Risk Management and Mitigation: Within 60 days of the commencement of duties under the Contract, the Contractor shall provide a Risk Management and Mitigation Plan, including its process for documenting and reporting risks and risk status to the State.  This plan should include:

  - The Contractor’s plan to identify potential risks and develop recommended steps to mitigate those risks;

  - The Contractor’s plan to track and manage the implementation of any mitigating steps;

  - Any proposed tool(s) to track, manage, and report risks and to facilitate the Contractor’s Risk Management Plan;

  - The benefits of the recommended risk management and mitigation process to FSSA;

  - That FSSA reserves the right to retain access to all of the Contractor’s risk management tools and reports;

  - The State reserves the right to approve the Contractor’s Risk Management Plan, process, and tools;

  - At no additional charge to the State, the Contractor will be required to have in place a comprehensive, fully tested IT business continuity/disaster recovery plan (ITBCP). The ITBCP will, at a minimum, meet the requirements of NIST SP800-34.

- Ensuring Data Security: Within 60 days of the commencement of duties under the Contract, the Contractor shall provide their plan to secure and protect the State’s data, including but not limited to private Client information. Such plan should include:

  - Steps taken by the Contractor to ensure that Client information is not used, disclosed or maintained in a manner not in accordance with the law and best practices.

  - The Contractor’s policy for the secure destruction of information.

  - The internal security and privacy policies and practices, including managing private Client data, and any staff training to ensure up-to-date compliance.

  - How the Respondent will use the State’s Active Directory repository to authenticate users, where applicable. The proposal must also describe how the Contractor shall inform the State of any potential breaches or compromises of Client information, by any means, immediately for the State to document and track to resolution.

  - The Contractor shall adhere to the IOT Information Resources Use Agreement during use of all state facilities and equipment to execute all activities described in this Scope of Work.

  - The Contractor shall ensure that their proposed solution is compliant with Clause 12 in the Boilerplate Contract.

# 13.0 State Resources for APS Staffing & Operations Contractor

Outlined below are resources provided to the APS Staffing & Operations Contractor by the State.

- State Roles and Resources

  - The State shall provide guidance and approval, collaborate on projects, receive reports, and make ad-hoc requests.

  - Training materials will be available to those who have access to State systems/tools, but it is expected that the Contractor remains the Subject Matter Expert (SME). To the extent that they would like to, the State would make these materials available.

- State System Access

The State shall provide the Contractor with all relevant and necessary access to State systems necessary to perform any of the duties contemplated by the Contract.

# 14.0 Start-of-Contract Requirements

The Contractor must adhere to the below start-of-contract requirements.

- The Contractor, in conjunction with DA, will ensure that the process of transition from the existing model upon contract award, results in predictable, seamless transition where services continue to be delivered in a timely and accurate manner without degradation in service levels. In the time period before the July 1, 2025 handover of services, the Contractor will meet regularly with the DA and other stakeholders to work on preparing for the transition. The Contractor must be prepared to attend intensive onboarding training during the transition period provided by the State and hold additional training sessions as necessary to facilitate a smooth transition. The Contractor may also provide their own intensive training for new employees they are bringing on to their own organization in addition to the State provided training.

- Transition from Current System of County Prosecutor Units

If applicable, Contractor shall prepare a master work plan for the transition from the current provider to Respondent’s solution at least forty-five (45) days before the projected commencement of oversight duties under the Contract.

The Contractor’s work plan must describe all tasks, deliverables, schedules, task dependencies and identification of resource requirements for the Contract, including but not limited to the transition of services from the current provider.

  - The Contractor’s work plan must include the proposed start and completion dates for each deliverable.

  - The Contractor shall, wherever possible, prioritize the consideration of current APS staff for positions within the new APS system.

  - The Contractor’s work plan must detail all tasks requiring FSSA and other State resources (including but not limited to the Indiana Office of Technology), summarize the proposed use of DA and other State resources, and state any assumptions regarding anticipated involvement of these resources. Further, the Respondent must agree that it is the Contractor's obligation to identify its task dependencies on DA resources or tasks, and that the Contractor retains the final responsibility for performance of its obligations including the quality of the deliverables. To the extent that DA review or approval is required of a document, plan or deliverable, DA shall have ten (10) business days to review first drafts and five (5) business days to review any revised drafts.

- Steady State Management

At least thirty (30) days before the projected go-live date of the Contract, the Contractor shall provide a detailed project management plan which explains how the Contractor shall ensure the timely delivery of quality services to the State. This project management plan will be subject to State review and approval. Such a plan shall:

  - Describe the overall project management approach, including but not limited to planning, organizing, and managing Contractor staff and activities throughout the term of the Contract in a manner that ensures the smooth administration and completion of deliverables.

  - Describe what project management tools, if any, will be used by the Contractor.

  - Detail Contractor’s approach to promoting teamwork, facilitating effective communication, and supporting collaborative efforts among the Contractor, any subcontractors, the APS Quality Assurance Contractor, DA, and DA’s designees.

  - Describe the Contractor’s plan to work collaboratively with DA to address stakeholder needs and any issues that require resolution.

  - Describe how the Contractor plans to administer the Change Control process, including Change Requests from the State in response to routine reference/rule changes, capitation rate administration and reconciliation, etc.

- Communication Plan

At least thirty (30) days before the projected go-live date of the Contract, the Contractor shall provide a communication plan describing how the Contractor will work with DA, its designees, the APS Quality Assurance Contractor, and other stakeholders to facilitate communication and coordination. Such plan shall include, but not be limited to:

  - Agreement to meet with the State, including any and all divisions of FSSA (211, DA, etc.), as requested.

  - Proposed monthly meetings with any State designees the APS Quality Assurance Contractor, including meeting attendees and cadence.

  - Periodic written updates.

  - Proposed team members who will serve as key points of contact for certain functions (data lead, quality lead, Project Manager, etc.)

This Communication Plan shall be subject to State review and approval.

- Issue Resolution Plan

At least thirty (30) days before the projected go-live date of the Contract, the Contractor shall provide a plan to identify, track, and resolve issues which may arise between Contractor and the State in the performance of duties under the Contract. Such plan should include:

  - Any trouble-shooting tools and techniques that will diagnose issues with networks, services, equipment, software, and data.

  - The approach and metrics to measure the success of its issue resolution efforts.

  - FSSA’s right to approve all issue resolution plans and procedures prior to implementation.

This Issue Resolution Plan shall be subject to State review and approval.

# 15.0 End-of-Contract Requirements

The Contractor must fulfill the end-of-contract requirements outlined below.

- The Contractor recognizes that the service(s) to be performed under this Contract are vital to the State and must be continued without interruption and that, upon Contract expiration, a successor, either the State or another contractor, may continue them. The Contractor agrees to:

  - Furnish phase-in, phase-out services; and

  - Exercise its best efforts and cooperation to affect an orderly and efficient transition to a successor.

- The Contractor shall, upon the State's written notice:

  - Furnish phase-in, phase-out services of up to (90) days before this Contract expires; and

  - Negotiate in good faith a plan with a successor to determine the nature and extent of phase-in, phase-out services required. The plan shall specify a training program and a date for transferring responsibilities for each division of work described in the plan and shall be subject to the State's approval. The Contractor shall provide sufficient experienced personnel during the phase-in, phase-out period to ensure that the services called for by this Contract are maintained at the required level of proficiency.

- The Contractor shall include a transition plan to a new vendor at the end of the Contract, including a detailed plan for Trainings still in progress that are expected to go beyond the Contract’s end date. The Contractor shall detail a plan to continue APS services uninterrupted through the end of the Contract.

# 16.0 Corrective Actions and Payment Withholds

It is the State’s primary goal to ensure that the Contractor is accountable for delivering services as defined and agreed to in the Contract. This includes, but is not limited to, performing all items described in the Scope of Work, completing all deliverables in a timely manner described in the Scope of Work, and generally performing to the satisfaction of the State. Failure to perform in a satisfactory manner may result in corrective actions and withholdings described below.

It is the intent of the DA to remedy any non-performance at no additional cost to the State.  In the event that the Contractor fails to meet the requirements set forth in the Contract, the State will provide the Contractor with a written notice of non-compliance and may require any of the corrective actions or remedies described in the Contract.

- Each month, the Contractor shall invoice for 85% of the Contractor’s monthly fixed-fee invoice amount (100% of the monthly invoice amount minus the 15% withhold amount) pending verification of the Contractor’s performance against the Performance Metrics described in Section 19.0.

- Following verification that the Contractor successfully met the requirements for all Performance Metrics in a given month, the Contractor may invoice the State for the withheld funds with the subsequent month’s invoice (for example, if the Contractor successfully meets the Performance Metrics requirements for January, and verification is completed in February, the 15% of the January invoice that was withheld can be claimed with the February invoice).

- If the Contractor fails to meet the requirements for one or more Performance Metrics in a given month, the Contractor must submit a Corrective Action Plan (CAP) to the State within fifteen (15) calendar days following the documentation of failure to meet the Metric(s) or the denial of a waiver request. The State shall review and make reasonable efforts to approve the CAP within ten (10) calendar days of the CAP being received. The State will continue to withhold funds for the month in which the Contractor failed to meet the Metric(s) and subsequent months until the Contractor demonstrates that the CAP has been implemented and further successfully meets all Performance Metrics for two consecutive months following the implementation of the CAP. Following verification that Performance Metrics have been met for two consecutive months, the Contractor may invoice the State for release of all withheld funds subject to the exception noted in Section 16.5 below.

- A CAP can also be triggered if the State determines that the Contractor is not performing to the satisfaction of the State, has not completed any deliverable in a satisfactory or timely manner according to the agreed upon Performance Metrics, or upon written request by the State for any reason. All CAPs must be submitted to the State within fifteen (15) calendar days following the documentation of failure to meet expectations. At a minimum, the CAP shall address the causes of the deficiency, the impacts, and the measures being taken and/or recommended to remedy the deficiency and indicate whether the solution is permanent or temporary. It must also include a schedule showing when the deficiency will be remedied, and for when the permanent solution will be implemented, if appropriate. The nature of the corrective action(s) will depend upon the nature, severity and duration of the deficiency, and the repeated nature of the non-compliance. The State shall review and make reasonable efforts to approve the CAP within ten (10) calendar days of the CAP being received.

- If the Contractor fails to meet two (2) or more Performance Metrics in any given month, the State shall permanently retain the 15% withholding for that month’s invoice.

- Verification of Contractor’s success or failure to achieve Performance Metrics may be performed by the State or a designated State contractor. including but not limited to the State’s APS Quality Assurance Contractor.

# 17.0 Key Performance Indicators

To track and maintain the quality of the APS staffing and operations, the State will use the Key Performance Indicators (KPI) listed in Table 2 and Table 3 below. The KPIs listed in Table 2 will be measured monthly starting on contract execution and will be subject to the withhold of payment detailed in Section 16.0 of the Scope of Work.

The KPIs detailed in Table 3 will be tracked and monitored by the State during the first 12 months of this Contract. After that, the State will decide to either continue tracking and monitoring these KPIs, or add them or adjusted version of them, to the KPIs in Table 2, thus making them subject to the same withhold of payment.

Table 2: Key Performance Indicators Subject to Withhold

| Metric Number | Metric Subject | Performance Criteria | Minimum Performance Level |
| --- | --- | --- | --- |
| 1 | Pricing Accuracy | Invoices submitted by Contractor to the State shall accurately reflect the prices in the Contract. | Each invoice must be 100% accurate |
| 2 | Invoice Completeness | Invoices submitted by Contractor must completely reflect 1) the work performed in the subject month, 2) the amount to be withheld in accordance with this exhibit pending review of Contractor performance, and 3) any amount previously withheld pending verification of performance | Each invoice must be 100% accurate |
| 3 | Ad Hoc Reports | Contractor must provide requested Ad Hoc reports, or an explanation for why the request report is not feasible, within five (5) business days of the request by the State or its designee. Reports should be accurate and free of errors. | 90% of requests satisfied within the 5-business day timeframe. Reports shall be accurate and free of errors. |
| 4 | Cases meeting documentation minimum standard | Minimum documentation shall include opening a new case for every screened-in report, filling out all relevant prompts within the APS-CMS, and appropriately documenting case closure along with the determine service plan. | 100% of cases must meet the minimum standard for documentation. |
| 5 | Time to resolution of Priority A cases | Timely response to emergency situations is a critical function of APS. If a case is assigned to Priority Level A and requires an emergency response, the alleged endangered adult is at imminent risk of harm APS must take immediate action to dispatch emergency services within 24 hours of screening the report. | 100% of Priority A cases will be responded to within 24 hours. |
| 6 | Time to resolution of Priority B and Priority C cases | Timely response to high risk and non-immediate risk cases is a critical function of APS. If a case is assigned to Priority B and C and requires a response within either 4 or 20 days, APS must take all necessary action to ensure these timelines are met. | 90% of Priority B and Priority C cases will be responded to within either 4 or 20 days, respectively. |

Table 3: Key Performance Indicators NOT subject to Withhold for the first 12 months

| Metric Number | Metric Subject | Performance Criteria | Performance Level Guidelines |
| --- | --- | --- | --- |
| 1 | Time from case open to close | Cases are closed within 60 days or an adjusted reasonable timeframe due to factors outside of the Contractor’s control such as an outstanding court date. | 90% of cases opened will be closed within the designated timeframe. If a case cannot be closed within this timeframe, reasoning shall be provided in monthly reporting. |
| 2 | Caseload | The Contractor shall be set and maintain an appropriate minimum standard for caseload requirements at the director, supervisor, investigator, and monitor function levels base on their proposed staffing model. | 90% of directors, supervisors, investigators, and monitors must hit their assigned caseload requirements. |
| 3 | Client Satisfaction Follow Up | The Contractor must follow up on any client satisfaction surveys that indicate below 80% satisfaction. The reason for dissatisfaction shall be documented and included in monthly reporting along with what attempts were made to remedy the situation. | 100% of APS satisfaction surveys with an overall score of 80% or below require attempted follow up and appropriate documentation. |
| 5 | Staff attrition rate | Staff retention is an important indicator of agency development, consistency of services, and high-quality management. Barring extenuating circumstances such as extreme budgetary restrictions or a medical epidemic, annual attrition should stay below 15%. | Staff attrition at 20% or below. |
| 6 | Annual Average Case Substantiation Rate | In order to ensure proper and thorough case investigation, the State has set a standard for case substantiation based on the recorded National Average among investigation APS cases. | Aim to achieve an annual average case substantiation rate of 20% - 30%. |

# 18.0 State Audits

The parties acknowledge the importance of preventing fraud, waste and abuse, breaches of confidentiality, and other wrongdoing in the operation of the public assistance programs administered by the FSSA. Contractor, at its own expense, will assist and appropriately act to aid the State in the investigation and detection of any such wrongdoing. This may entail cooperation with the State’s Internal Investigation and Compliance division, law enforcement officials, and authorities of the various State and Federal agencies that are responsible for compliance with the laws and regulations governing the programs. In the cases of any such investigation, the State and Contractor, in conjunction with its legal counsel, agree to fully cooperate in the gathering of evidence in support of law enforcement and investigatory activities. Access to information concerning these matters, which can include time, location, and documents of interest, will be restricted to the state or federal investigatory official until the resolution of the investigation.

- The Contractor acknowledges that its employees may be requested to submit to questioning by State Investigators in support of a State Audit. The Contractor will cooperate with any investigators by making its employees available in a manner that will best facilitate the law enforcement objectives of the interview. Where the Contractor’s employees are suspects in a pending investigation, the Contractor agrees that any employment actions concerning such employees will be reviewed with the State in advance, to avoid taking any action that would jeopardize law enforcement efforts.

- The State will provide the Contractor with reasonable notice of an Audit if it is determined at the State’s discretion, that giving notice is feasible and appropriate and would not be contrary to, defeat the purpose of, or prejudice the conduct of the applicable Audit. The State will use reasonable efforts to ensure that the Audit will be conducted in a manner so as not knowingly to create a material risk of harm to persons or property. Currently, there is a two-year rotation of being audited by FSSA auditors.

- Audit Access. Upon request of the State, and in connection with any Audit, Contractor and its Subcontractors will provide auditors prompt access to the following:

  - Service location, facilities, or installments, in each case, to the extent used to provide Services,

  - The proposed System, and

  - The State Software and the State Recipient data if the data is stored on Contractor’s equipment or proposed Systems.

- Audit Assistance. Contractor will cooperate fully with the State in the conduct of any Audit, including providing all Records in Contractor’s actual or constructive possession that are requested by the State. Contractor must provide any assistance in all reasonable respects with such an Audit.

- Any Audit by FSSA or by any Contract Administrator acting on behalf of FSSA shall be reasonably related to the performance by Contractor or any Subcontractor of the Services, the Delegated Activities, or their performance under this Agreement, any Material Agreement or any Subcontract. Nothing herein shall be deemed to be a waiver of the respective rights of Contractor or any Subcontractor to assert any applicable privilege or any right to protect their confidential and proprietary assets.