ATTACHMENT K1

STATEMENT OF WORK – MOCC SERVICES

INDIANA MEDICAL OPERATIONS COORDINATION CENTER RFP

# EXECUTIVE SUMMARY

## Purpose Statement

On Dec. 29, 2025, Indiana was awarded a grant of nearly $207 million for the first year of a five-year federal Rural Health Transformation Program (RHTP) to address health outcomes in the State’s rural communities. This Rural Health Transformation Program is supported by the Centers for Medicare & Medicaid Services (CMS) of the U.S. Department of Health and Human Services (HHS) as part of a financial assistance award totaling $206,927,896.80 with 100 percent funded by CMS/HHS. The contents are those of the author(s) and do not necessarily represent the official views of, nor an endorsement, by CMS/HHS, or the U.S. Government.

The purpose of this Request for Proposal (RFP) is to procure a qualified vendor to develop, implement, and operate a real-time Medical Operations Coordinator Center (MOCC) for the State of Indiana, which will support the RHTP strategic goal of “Sustainable Access.” The awarded vendor (“Contractor”) shall implement and operate a statewide MOCC as a centralized 24/7 hub for day-to-day hospital and emergency medical services (EMS) operational reporting, patient transfer coordination, and EMS resource alignment with a primary goal of improving the quality and efficiency of statewide care coordination and transport of rural residents dependent on interfacility transfers for trauma, cardiac, stroke, psychiatric, OB/GYN, and urgent care needs. The MOCC and associated system(s) must provide 24/7 network-based delivery in emergency settings and function as a neutral convener capable of aligning hospitals, EMS, and system partners statewide. The MOCC is intended to align operational workforce and functionality to ensure a centralized framework supports regional capacity and coordination of care (across North, Central, South trauma regions of the State) for both day-to-day and extreme situations (see Section 3.4.1 for more information). At the end of the Contract term, the MOCC is expected to be independently sustainable if new funding streams are not available (see Section 8.1 for more information on sustainability expectations).

If the Contractor also submitted a proposal for the MOCC Systems scope (see Attachment K2) but is not awarded that scope, they shall fully cooperate with the State and the MOCC Systems Contractor in the implementation and utilization of the System.

Note: If the Respondent chooses to propose for MOCC Services, complete Attachment D1 (Services Cost Proposal) and Attachment F1 (Services Technical Proposal). Additionally, complete Attachment N (Artificial Intelligence Questions) along with the other forms and attachments required by the RFP.

## MOCC Advisory Committee

The Contractor shall define, develop, and establish a MOCC Advisory Committee, in collaboration with the Indiana Department of Health (IDOH), the Trauma Care Commission and EMS Commission, to ensure regular and transparent communication between MOCC leadership and hospital/EMS leadership. The intent of the Committee is to drive MOCC engagement and operations, and for stakeholders to evaluate current delivery status and progress, discuss new ideas, and remove barriers to progress or positive change while implementing shared authority with MOCC leadership. The Contractor shall regularly collaborate with the MOCC Advisory Committee to discuss activities including but not limited to:

- Establishing policy and procedures that will guide core MOCC operations, including triggers for activation levels. Criteria for triggers should include considerations such as availability of beds and equipment availability.

- Reviewing progress toward the completion of key project milestones and adherence to the project timeline.

- Reviewing quality of MOCC operations, including review of Key Performance Indicators (KPIs) and usage reports.

- Reviewing potential and emerging risks and approach to risk mitigation.

- Strategizing on opportunities for care continuum expansion and support via MOCC operations, including coordination and collaboration with other RHTP initiatives such as telemedicine and interoperability.

- Strategizing long-term sustainability options for MOCC operations that ensure successful outcomes are maintained beyond the RHTP grant period.

## Description of Work

Per federal guidance on the RHTP grant, the Contract resulting from this RFP will have a five-year contract term, but the Contract only has funding for the initial budget period (Budget Period 1). This Contract will be amended to add subsequent funding for each of the budget periods based on federal funding awarded for those budget periods. The federal funding supporting this Contract must be expended within strict deadlines; therefore, failure to complete work by specified deadlines may subject this Contract to termination to ensure funds are spent in accordance with federal requirements.

The Contractor shall:

- Be responsible for all milestones and deliverables as outlined in Table 1. Table 1 is not exclusive and additional milestones and deliverables may be identified during the Contract period. Milestones must be completed and approved by the State in the timeframe noted in Table 1 so funding allotted for specific milestones with each Budget Period’s funding can be utilized (see Section 3.3 for more information).

- Not be responsible for failure to complete milestone and deliverable expectations outlined in Table 1 due to reasons outside of the Contractor’s control.

- Abide by all applicable State and federal laws.

- Invoice IDOH upon milestone completion and approval. The invoice must have sufficient information describing the work performed for reimbursement, including details on deliverables completed to achieve each milestone. Future budget periods will include a combination of milestone payments and monthly staff costs, as described in Attachment D1 – Cost Proposal.

- Submit reports monthly or as requested by IDOH. The reports shall be in a form determined by IDOH and contain information required by IDOH.

- Report quarterly on successes encountered throughout the quarter. These reports should reflect your efforts to meet the strategic goals set forth in the RHTP grant. The report shall be submitted on a form required by IDOH.

IDOH shall:

- Regularly meet and collaborate with MOCC leadership and MOCC Advisory Committee

- Provide staffing support for execution of the Contract and achieving Milestones and Deliverables as outlined in Table 1.

- Review submitted deliverables and reports.

- IDOH shall not be responsible for any work, materials, or costs not expressly identified in this Scope of Work or otherwise agreed to in writing by the State.

# BACKGROUND AND CURRENT STATE

The MOCC will rely upon a broad range of stakeholders (including, but not limited to, hospitals, EMS, and system partners) to monitor health care personnel and utilize the Healthcare Emergency and Hospital Capacity System platform, to understand current capacity and gaps in the health care system, and to facilitate care coordination including referrals and load-balancing through patient transfers. For more information on sample MOCC operations and models, see resources from the American College of Surgeon’s Regional Committees on Trauma: https://www.facs.org/quality-programs/trauma/committee-on-trauma/regional-committees-on-trauma/field-program/rmoccs/.

# SCOPE OF WORK

## Objectives of Engagement

MOCC Priorities. Priorities of the MOCC include the following activities:

- Collecting, analyzing, and disseminating hospital-capacity information: One of the primary roles of the MOCC is to collect and analyze the information provided by each partner (e.g., EMS, State, region, health care facilities). The Contractor shall analyze and disseminate data to support comprehensive situational awareness of available resources across the region. These activities do not replace broader Emergency Operations Center (EOC) based information/intelligence functions.

- Establishing governance, protocols, systems, and activation triggers: The MOCC facilitates the collection and reporting of health care-specific data elements, informs operational planning and stakeholder communications, and initiates regional transfer decision-making. The Contractor shall work with the MOCC Advisory Committee to determine triggers for load-balancing and equitable processes for managing destination decisions when no capacity is available.

- Acting as a single point of contact (POC) for referral requests and life-saving resources while maintaining and incorporating existing system transfer/call centers: The MOCC provides a single POC for health care facilities seeking assistance with patient transfers and for health care system partners in the region that have resources that can help decompress the load in overwhelmed facilities. The Contractor shall obtain necessary equipment to support daily operations and decision-making for patient care coordination.

State of Indiana Strategic Alignment. The objectives of the MOCC align with and will bolster statewide RHTP priorities, including the following:

- Workforce Development: Strengthens EMS and hospital staff through training in transfer protocols, maternal/behavioral health transport, and alternative destination pathways

- Access to Healthcare: Provides bi-directional transfer coordination for rural communities, reducing delays in accessing trauma, stroke, and psychiatric services

- Healthcare Delivery: Acts as a centralized patient flow management system, improving system-wide efficiency and continuity of care between rural hospitals and tertiary specialty centers

- Technology and Innovation: Collaborates with the State and its partners to deploy the Healthcare Emergency and Hospital Capacity system - an advanced IT platform with automated reporting, secure data exchange, and integrated dashboards for hospitals and EMS providers; obtains and utilizes equipment to fully operationalize patient care coordination and ensure statewide access

- Care Continuum Expansion: Aligns with Indiana’s investment in 988 and Certified Community Behavioral Health Clinics (CCBHCs) by creating operational linkages for psychiatric transfer coordination; aligns workforce to ensure regional capacity and coordination is supported

## Deliverables and Deadlines

The Contractor shall provide the deliverables listed in Table 1 below in accordance with the listed Anticipated Completion Dates.

Table 1: Milestones and Deliverables

| Milestone # | Milestone | Deliverable | Anticipated Start Date | Anticipated Completion Date |
| --- | --- | --- | --- | --- |
| Budget Period 1 Funding |  |  |  |  |
| 1 | Hiring and onboarding operational staff and establishing Advisory Committee | - Project Management Plan (PMP), including: - Project Workplan with Schedule and resource allocations - Project Organization Chart and Staffing Plan - Communication Management Plan - Risk and Issue Management Plan - Onboarding Training Plan - Operational staff fully onboarded | 9/1/2026 | 12/31/2026 |
| 2 | Complete planning activities for 1) implementation of Healthcare Emergency and Hospital Capacity System and 2) pilot programs, including identification of pilot areas | - MOCC Implementation Plan, including consideration for implementation of Healthcare Emergency and Hospital Capacity System in MOCC operations - Interfacility Pilot Implementation Plan - Behavioral Health Triage Pilot Implementation Plan | 1/1/2027 | 3/30/27 |
| 3 | Operationalize and begin utilization of Healthcare Emergency and Hospital Capacity System for facility status and patient tracking | - MOCC Operations Plan - Business Continuity Plan (BCP) and Disaster Recovery Plan (DRP) - Complete activities per BCP and DRP - Pilot rollout - Confirmation of Healthcare Emergency and Hospital System implementation/utilization | 3/30/2027 | 6/30/2027 |
| 4 | Implementation of MOCC utilization within pilot areas (TBD) for interfacility transfers | - Post-Interfacility Pilot Implementation Report | 3/30/2027 | 7/31/2027 |
| Budget Period 2 Funding |  |  |  |  |
| 5 | Implementation of MOCC utilization within pilot areas (TBD) for behavioral health triage | - Post-Behavioral Health Triage Pilot Implementation Report | 7/1/2027 | 10/31/2027 |
| 6 | 100% of hospitals submitting data to the Healthcare Emergency and Hospital Capacity System. Note: 172 total hospitals have been identified in the State. All 172 total hospitals, or an identified subset of these hospitals, may be required to submit data to the Healthcare Emergency and Hospital Capacity System pending State leadership and stakeholder discussion* | - MOCC hospital tracking report | 7/1/2027 | 10/30/2027 |
| 7 | 100% of EMS partners submitting data to the Healthcare Emergency and Hospital Capacity System* | - MOCC EMS tracking report - Pilot completion | 7/1/2027 | 10/30/2027 |
| 8 | Implementation of MOCC utilization within 50% of regions for interfacility transfers* | - MOCC interfacility transfer tracking report, validating compliance with milestone requirements | 7/1/2027 | 10/30/2027 |
| 9 | Implementation of MOCC utilization within 50% of regions for behavioral health triage* | - MOCC behavioral health tracking report, validating compliance with milestone requirements | 10/1/2027 | 12/31/2027 |
| 10 | Identification and integration of additional systems, technology, and tools for full integration and utilization of Healthcare Emergency and Hospital Capacity System | - Integration Plan | 7/1/2027 | 12/31/2027 & Ongoing |
| 11 | Training and education on MOCC and Healthcare Emergency and Hospital Capacity System provided to all hospital and EMS partners by region | - Training Plan - Approved provider training materials - Training Results Log, including number of trainings provided, dates, and attendees - Approved communication products - Deliver agreed upon training (as applicable) - Competency Assessments (pre/post training as applicable) | 3/30/2027 | 12/31/2027 |
| 12 | Implementation of MOCC utilization within 100% of regions for interfacility transfers* | - MOCC interfacility transfer tracking report, validating compliance with milestone requirements | 1/1/2028 | 6/30/2028 |
| 13 | Implementation of MOCC utilization within 100% of regions for behavioral health triage* | - MOCC behavioral health tracking report, validating compliance with milestone requirements | 1/1/2028 | 6/30/2028 |
| Budget Period 3 Funding |  |  |  |  |
| 14 | Integration of telemedicine and computer-aided dispatch (CAD) systems into MOCC services for care coordination and triage of patients | - Telemedicine Implementation Plan - CAD Implementation Plan | 7/1/2027 | 10/30/2028 |

*Note: if implementation rate does not meet milestone expectations due to reasons outside of the Contractor’s control (e.g., provider refusal to participate in the MOCC), the State may approve Milestones and/or Deliverables related to implementation rates. The Contractor shall provide evidence of such difficulties for State review and approval in Quarterly Reports.

## Payment and Invoicing

The Contractor shall invoice the State in accordance with the Milestones and payment structure captured in Attachment D1 – Cost Proposal. The invoice must have sufficient information describing the work performed for reimbursement, including details on deliverables completed to achieve each implementation milestone.

CMS has required that all Budget Period 1 costs be drawn down by September 30, 2027. As such, the Contractor shall complete work for all milestones covered by Budget Period 1 funding by July 31, 2027, and shall submit all related invoices no later than August 14, 2027, to allow the State time to process and pay funds in alignment with CMS guidance. For this contract, milestones covered by Budget Period 1 funding shall be milestones 1, 2, 3, and 4, and these milestones must be invoiced by August 14, 2027. Milestones covered by Budget Period 2 funding shall be milestones 5-13, and these milestones must be invoiced by August 14, 2028 unless otherwise directed by the State. The Contractor shall factor in this timing while planning for deliverable submission, review(s), updates (if needed), and approval.

Milestones and activities covered by future budget period amounts will follow the same or similar requirements for invoicing timeliness, to be confirmed by the State pending further guidance from CMS and the State’s RHTP team. Milestones that are anticipated to be completed by 10/30/2028 have been noted in Table 1 and will be confirmed by the State after CMS releases the future budget period funding.

## MOCC Operations

The MOCC shall make data and partner-informed decisions to balance patient load and ensure high-quality care. MOCC decisions may direct the movement of patients (and potentially other resources) from one facility to another or redirect referrals that would usually go to an overwhelmed facility or system to one with capacity. The MOCC must ensure hospitals and emergency response partners engage in shared decision making as hospitals have administrative authority for their operations and have the best understanding of the status and needs of the patients under their care.

### MOCC Day-to-Day and Elevated Operations

Day-to-Day Operations. On a daily basis, the MOCC will monitor and balance the movement of patients throughout the State, including activities such as interfacility transfers, air ambulance management, notification of trauma teams, and navigation of mental health patients to ensure.

Transfer management is a key component of day-to-day MOCC operations. The MOCC shall receive transfer requests and ensure that patients being cared for in a facility that does not provide the necessary services are prioritized and transfer arranged to a facility with the appropriate capacity and capabilities. See Sections 3.4.2 and 3.4.3 for more information on MOCC operations expectations.

Elevated Operations. In addition to daily responsibilities, the MOCC will facilitate support in response to emergent crisis situations that require an elevated response due to a large influx of patients. Examples of crises requiring elevated operational support may include but are not limited to mass casualty incidents (MCIs), severe weather (e.g., tornados or earthquakes), bridge collapse, or motor vehicle collisions (MVCs) (e.g., tour bus or multiple vehicle).

Emergent crisis situations may require load-balancing management. In extreme situations or when normal processes break down, the MOCC may coordinate the movement of patients from an overloaded hospital or other facility type to less burdened facilities to distribute strain more equitably or to free up beds in a specialty center for patients that require specialized care (e.g., coordinating movement of medical patients to a community hospital from a burn center to accommodate a large number of burn patients).

Any facility can request load-balancing based on voluntary cooperation of the other facilities subject to available beds (e.g., if patient movement is needed to free up specialty care capacity). The MOCC should monitor the bed availability within and around their operational area to ensure a common level of saturation including the coordination of out-of-state transfers (if required) to participating health systems. The Contractor, in collaboration with the MOCC Advisory Committee, shall establish policies that guide actions when a facility is considered overwhelmed compared to other facilities to a degree that would prompt load-balancing to occur. Thresholds could include changes to staffing that are more dire than those taken at other facilities (e.g., using non-traditional staff in ICUs) or involve a percentage of occupied beds beyond usual capacity that is more than a determined percentage different from others in the area. Load-balancing assumes that usual surge capacity actions have taken place across the affected hospitals to maximize use of space and staff.

The MOCC should not replace or interfere with usual referral partners or discourage health care systems from distributing patients and prioritizing beds and transfers within their organization. When these usual systems are saturated, the MOCC benefits both patients and providers by providing a “one-call” alternative to multiple phone calls to different hospitals and health care systems looking for a bed and appropriate levels of care.

### Operational Requirements

Once fully operational, the MOCC shall maintain the following operational capabilities:

- Define and establish MOCC Advisory Committee, meeting regularly

- Maintain and utilize the Healthcare Emergency and Hospital Capacity System platform and identify/implement enhancements for statewide visibility and interoperability

- Be optimally and fully staffed, and be able to function as a centralized hub for regional patient transfers on a daily basis

- Be able to be scale up elevated operational capacity rapidly when strain/surge conditions interfere with ability to transfer patients (e.g., MCI/Crisis mode) within time frames determined by the MOCC Advisory Committee

- Monitor and balance regional healthcare capacity, and integrate with emergency management, EMS (including air ambulance), healthcare systems, and long-term care

- Serve as a single point of contact for all hospitals and EMS providers to equalize patient load during strain/surge conditions when usual referral mechanisms are overloaded

- Match patients to the right treatment locations as quickly as possible, within timing guidelines defined in collaboration with the MOCC Advisory Committee

- Maintain timely and efficient access to hospital care and direct EMS units to hospitals that can safely receive patients without delay, based on real-time capacity and clinical need

- Keep the regional standard of care consistent by helping to avoid or reduce crisis conditions that may put patients at risk

- Facilitate “care-in-place” (i.e., immediate treatment) consultation when transfers are not possible

- Ensure patients in community hospitals have access to emergent specialty care, and if emergent specialty care is not accessible, recommend option(s) for appropriate care (e.g., transfer or care-in-place)

- Prioritize transfers during high volume periods when not all requests can be met

- Direct secondary referrals to the most appropriate hospital (e.g., those with capacity and/or the most appropriate level of care given the patient’s condition)

- Serving as a one-call referral line to achieve rapid placement of patients needing critical care, particularly when the referring hospital does not provide the services required (see Section 7.1 for Key Performance Indicators related to patient outcomes).

- Provide consultation with specialty medical providers when required to help prioritize a patient for transfer or receive instructions for care-in-place when this is required for a period of time

- Convene hospitals and EMS providers for situational information sharing, including current contingency measures and potential need for load-balancing/negotiation of load-balancing

### Core Operational Responsibilities

- Workforce. The Contractor shall:

  - Recruit, hire, and train for MOCC staff and expanded EMS workforce capabilities in rural areas, with emphasis on specialty transport (time-sensitive - trauma, stroke, maternal and neonatal) and mental/behavioral health centers.

  - Add leadership and clinical staff (virtually and/or physically) to new or existing operations to support transfer prioritization and care-in-place consultation as required when a referral bed cannot be located.

  - Maintain decision-making authority at the executive leadership level, while also ensuring the MOCC is a clinically informed, operational coordination and escalation function.

- IT/Equipment Advances. The Contractor shall:

  - Develop, implement and utilize statewide emergency reporting systems (including the Healthcare Emergency and Hospital Capacity System platform) and patient transfer tracking tools, maintaining compliance with strong cybersecurity and interoperability standards.

  - Identify and obtain (where necessary) equipment to fully operationalize patient care coordination and communication.

  - Leverage integrated systems that assist with core issues of communication fragmentation, improving patient outcomes, and reducing costs.

  - Identify secure, compliant software and equipment options to fill gaps or address needs associated with communications and statewide patient movement coordination.

  - Ensure robust safe-guarding of proprietary data.

Note, the implementation of the MOCC will take place in conjunction and coordination with the implementation of the Healthcare Emergency and Hospital Capacity System platform. Additionally, ongoing stakeholder engagement efforts will inform the MOCC’s IT and equipment advancement needs. The Contractor shall support the implementation and/or integration of technological needs identified through these ongoing engagements.

Any implementation, acquisition, or upgrade to health IT and the related standards supporting a related activity are subject to 1) the Health Information Technology and Interoperability requirements in 45 CFR part 170, subpart B; and 2) security requirements per Indiana’s RAMP policy. Additionally, the Contractor shall maintain compliance with all standard State policy and procedures for technology. See Section 6 for more information.

- Appropriate Care Availability. The Contractor shall:

  - Support timely transfers and discharge planning to ensure patients receive the right care at the right location (e.g., rural critical access hospital, trauma center, OB/GYN specialty unit, long-term or urgent care).

  - Establish policies and standards for both day-to-day and elevated operations that describe the authorities and operating procedures for the MOCC, including how the MOCC receives information, connects patients to beds (including any “forcing function” that may be needed when all hospitals are at capacity for ICU beds or critical interventions), and load balances hospitals when needed. Other functions may also be included such as staff or supply management or managing information on long-term care center capacity.

- Care Continuum Expansion. The Contractor shall:

  - Enhance psychiatric transfer coordination, supporting substance abuse and addiction treatment centers, mental health services, and integration with crisis stabilization resources.

  - Direct ambulances to urgent care or outpatient providers where appropriate.

  - Align operational workforce to support regional capacity and care coordination (e.g., North, Central, South trauma regions) across the State as operations evolve.

  - Develop and strategically plan for centralized MOCC development with future-state expansion into an integrated regional model.

  - Support planning and implementation of ideas from the MOCC Advisory Committee that support care continuum expansion throughout the State.

- Data, Reporting, and Metrics. The Contractor shall:

  - Ensure appropriate reporting and tracking of operational outputs to inform improvements in care coordination and health outcomes.

  - Establish agreements that allow for collecting data regarding the current capacity of the region’s health system, synthesizing the data to understand the needs of the health system, and determining areas of the health system that may be overwhelmed.

  - Identify and obtain equipment to fully operationalize patient care coordination for reporting and quality improvement.

  - Define and monitor performance measures and health outcomes for both internal and external stakeholders, including quality improvement practices when gaps or needs are experienced. The MOCC reporting structure should align with executive authority and System operations based on guidance from the Indiana Trauma Care Commission and EMS Commission. Metrics aligned with authority should include MOCC utilization, hospital participation, and transfer and coordination performance for accountability purposes. See Section 7.1 for more information.

- Implement an automated reporting process to support transparency and situational awareness related to MOCC-facilitated patient movement. See Section 4.5 for more information.

- Collaboration and Engagement: The Contractor shall:

- Establish and facilitate formal engagement with statewide stakeholders, including but not limited to, IDOH, Family and Social Services Administration (FSSA), Department of Homeland Security, Indiana Hospital Association (IHA), Indiana Rural Health Association (IRHA), Trauma Care Commission, EMS Commission, Statewide 911 Board, 988 Suicide and Crisis Lifeline, Military, Emergency Management, Healthcare Coalitions, local health departments (LHDs), long-term care, dispatch centers, EMS providers, Indiana Council of Community Mental Health Centers, local/regional mental and behavioral health providers, and local hospitals.

- Establish, coordinate, and facilitate monthly MOCC Quality Improvement Review sessions in collaboration with the State and MOCC Advisory Committee. MOCC Quality Improvement Review Sessions shall be held for each of the three trauma regions and should be attended by trauma centers of each region. Sessions shall include review of the past month’s activities, as well as trends over time, such as:

  - Review of key operational metrics (e.g., time to initial contact, time to placement decision, time to transfer initiation and completion) captured in usage reports.

  - Analysis of MOCC-facilitated patient movements to identify trends, gaps, and opportunities for improvement.

  - Collaboration with participants to jointly review findings.

Note: Reports, case studies, and other findings being reviewed in MOCC Quality Improvement Review Sessions should be anonymized and remain confidential unless otherwise approved by participating entities

- Define and implement communications and education/outreach to ensure stakeholder engagement and utilization of the System.

- Explore long-term sustainability opportunities including identification of shared or private funding models once Rural Health Transformation Program concludes.

- Collaborate with the State and its designated partners to identify and advance synergies between the MOCC and other RHTP initiatives, including, but not limited to statewide interoperability and telemedicine integration efforts.

- Consider policy and procedure for activation levels that require activation and reception of hospital representatives (e.g., Level 3-4 activation vs. Level 1-2 activation; natural disasters vs pandemics) in collaboration with the MOCC Advisory Committee.

MOCC has independent operational authority with formal accountability to IDOH and is expected to communicate in the operational language that stakeholders trust. Independence supports faster operational decision making, greater hospital participation, and stronger health system alignment during surge and health system stress.

### Implementation

The Contractor shall be responsible for the following implementation activities:

- Pilot Programs. Planning and rollout of two (2) pilot programs implementing key MOCC capabilities – 1) interfacility transfers and 2) behavioral health triage. In support of these pilot programs, the Contractor shall:

  - Identify pilot areas for both the interfacility transfer and behavioral health triage pilot programs in collaboration with the MOCC Advisory Committee. Pilot areas shall be defined groupings of healthcare facilities and associated EMS networks selected to test and refine MOCC implementation. Each pilot area may include several hospitals or health systems within the same region. Although the exact location of pilot areas is to be determined by the Contractor, the selected pilot areas are expected to align with identified RHTP regions. The State estimates two (2) to three (3) areas to be included for each of the pilots.

  - Develop an Interfacility Pilot Implementation Plan and a Behavioral Health Triage Pilot Implementation Plan describing the Contractor’s approach to successfully implementing MOCC capabilities within the identified pilot areas. The Pilot Implementation Plans are subject to State approval.

  - Develop a Post-Interfacility Pilot Implementation Report and Post-Behavioral Health Triage Pilot Implementation Report describing the outcomes of the pilot programs, including takeaways to be applied to ongoing MOCC rollout.

- Statewide Implementation. In accordance with the Milestones described in Table 1, the Contractor shall:

  - Develop and submit the MOCC Implementation Plan for State approval. The MOCC Implementation Plan shall provide a roadmap of activities and timelines outlining the statewide MOCC implementation process. This deliverable shall also include considerations for implementing and utilizing the Healthcare Emergency and Hospital Capacity System for MOCC operations.

  - Support the implementation and utilization of key MOCC capabilities (interfacility transfers and behavioral health triage) throughout 50% of regions during Budget Period 2 and 100% of regions during Budget Period 3

  - Provide Tracking Reports on interfacility transfers and behavioral health triages. See Section 4.5 for more information.

  - Develop and submit the MOCC Operations Plan for State approval. The MOCC Operations Plan shall outline the Contractor’s approach to operating and maintaining the MOCC, beginning with pilot operations and evolving as the MOCC expands to full operational capacity. At minimum, the MOCC Operations Plan shall address the requirements and expectations outlined for MOCC operations in Sections 3.4.2 and 3.4.3. The MOCC Operations Plan shall be a living document and updated periodically to reflect newly implemented functionality. Updated versions shall be submitted to the State for review and approval throughout the Contract term.

- Additional Technology Integration. The Contractor shall submit an Integration Plan to the State for approval that identifies and describes their approach for integrating additional systems, technology, and/or tools to fully integrate and utilize data from the Healthcare Emergency and Hospital Capacity System for optimal MOCC operations. The Integration Plan shall include the timeline and resources needed for implementation of identified technological additions. Following State approval of the Integration Plan, the Contractor shall implement their proposed technology and tools and provide updates to the State through regular reports.

- Telemedicine Integration. In coordination with other statewide RHTP initiatives focused on the expansion of telehealth and teleconsultation services and technology in the State, the Contractor shall integrate telemedicine into MOCC services for care coordination and triage of patients. The Contractor shall submit a Telemedicine Implementation Plan for State approval that is informed by stakeholder engagement efforts and coordination with relevant RHTP initiatives. The Telemedicine Implementation Plan shall include a timeline, stakeholder engagement efforts, and resources needed for implementation of telemedicine services into the MOCC.

- CAD Integration. The Indiana 911 Board is currently engaged in a pilot project that seeks to improve emergency medical response coordination through enhancements to computer-aided dispatch (CAD) systems in the State. The Contractor and MOCC Advisory Committee shall engage in coordination and collaboration efforts with the Indiana Statewide 911 Board, its designated contractor(s), and other stakeholders to integrate the enhanced CAD system into MOCC operations. The Contractor shall submit a CAD Implementation Plan to the State for review and approval that captures a timeline, stakeholder engagement efforts, and resources needed for integration of CAD systems into MOCC operations.

### Training

MOCC Staff Onboarding and Ongoing Training. The Contractor shall be responsible for the following activities:

- Develop the Onboarding Training Plan, subject to State approval. The Onboarding Training Plan shall include:

  - Onboarding roadmap inclusive of timelines associated with the proposed schedule for training onset and completion.

  - Training curriculums for the Key Persons identified in Section 4.2.

  - Training methods (e.g., virtual sessions, hands-on workshops, train-the-trainer).

  - Training materials.

  - Cross Training. Where appropriate, the Contractor is encouraged to promote and leverage cross-training to develop a skilled and collaborative workforce. Cross-training plans and opportunities should be outlined in the Onboarding Training Plan, incorporated into training materials, and reflected in any relevant deliverables for State approval.

  - Competency assessment methods. The Contractor shall include methodology to evaluate the results of competency assessments and incorporate updates to training curriculums based on these results.

- Provide ongoing training at least annually for all MOCC staff on updated MOCC capabilities and procedures.

- At the request of the State, any Contractor staff displaying poor performance shall receive remedial training. The Contractor must deliver remedial training to the worker and document the details of the training, including type of errors, trainer, date of the training, length of time of the training, and any attachments. Prior to implementation of the remedial training, the Contractor must obtain approval of the materials from the State. These verification documents must be maintained in the employee's personnel file. If poor performance recurs, the State will discuss potential remedial actions with the Contractor and appropriate action, including up to removal from the project, may occur.

External Stakeholder Outreach and Education. The Contractor shall be responsible for the deployment and maintenance of ongoing MOCC education and rural outreach initiatives, as applicable. These efforts could include development of training materials or programs, recommendations for statewide simulation exercises, stakeholder webinars, and awareness campaigns for hospitals, EMS agencies, and public safety based on MOCC implementation. This programming shall support both the initial implementation of the MOCC to ensure understanding of the MOCC’s integration and use cases, as well as ongoing efforts to support the evolution of the MOCC’s capabilities over time.

The Contractor shall develop and submit the following deliverables pertaining to external stakeholder outreach and education for State approval:

- Training Plan, including provider training materials.

- Training curriculum for end users.

- Communication and outreach materials.

- Training Results Log, including the number of trainings provided, dates, and attendees

### Data and Surveillance

Daily data may differ from incident data, and at certain times, capacity conditions may dictate the need for further information. The MOCC should establish and communicate clearly outlined expectations for:

- Performance metrics including health outcomes measures to monitor success and opportunities for internal or external quality improvement efforts. See Section 7 for more information on KPIs.

- Ongoing data collection practices and tracking for evaluation and assessment as to report outcomes.

- Type and frequency of information exchanged and how those expectations may change based on available resources.

- Data protection and use agreements.

- Information sharing about its functions, including the number of placements, type of placement, type of originating facility, type of receiving facility, time to placement, mode of transport, or other data.

- Operational improvements and monitoring trends over time to support potential policy development.

- Patient outcomes to help define the risks of health system strain and transfer delay and optimize MOCC prioritization and placement activities. A standardized patient information form should be utilized that collects at minimum the age, diagnosis, current condition, and current major interventions to facilitate placement.

MOCC leadership must engage with receiving facilities to determine the most appropriate placement. The MOCC should prohibit use of financial or other information that could subject the referral to bias and the receiving facilities should not be able to make insurance status a condition of accepting a transfer. Demographic information may be collected and used in quality improvement and review processes. Legal interpretation should be sought to define if the MOCC as proposed/operated is a Health Insurance Portability and Accountability Act (HIPAA) protected entity and what information technology and other safeguards may need to be in place to ensure privacy and compliance.

### Information Sharing/Situational Awareness

Effective MOCC coordination relies on a common operating picture made up of information from a range of sources. The MOCC must receive and share real-time response and coordination information on the current status of the health care delivery system. The MOCC may also collect information from other partners to help local ESF-8 partners assess their resource requests and assist in their management processes (e.g., from an HCC cache, partner mutual aid, or from deployed state or federal resources).

The MOCC must have certain information to operate, including knowledge of the services provided at each hospital in the region as well as the availability of beds and resources. Web-based information systems are critical to that effort. Currently, no state has integration of all information directly from the HER, and this is a goal that needs to be actively pursued in coordination with other statewide initiatives (e.g., the RHTP interoperability initiative) so that the information system reflects:

Baseline facility information:

- Demographics – name of facility, location, phone number, total operating beds.

- Point of contact for facility – ideally a nurse manager/patient placement as well as a medical director.

- Referral center phone number (if applicable).

- Beds:

  - Counted by type and number (ensure that common definitions are used) – floor, monitored, intermediate/step-down, ICU.

  - Include number of beds that can be utilized for time-critical emergent procedures (e.g., cardiac intervention, thrombectomy).

- Do the ICU services include mechanical ventilation, dialysis, ECMO, or other specialty services?

- Specialty designations such as trauma center level, burn center capability, stroke center designation, etc.

- Surge beds for each bed type that can be made available in addition to usual beds if staffed.

- For community hospitals, determine if there is in-house physician/hospitalist coverage 24/7 and whether this includes adults, pediatrics, or both.

- For community hospitals that do not provide comprehensive critical care, determine comfort level managing certain conditions (e.g., sepsis requiring pressors, respiratory distress requiring non-invasive respiratory support, mild diabetic ketoacidosis, congestive heart failure exacerbation).

Once activated, the MOCC must determine the essential elements of information (EEIs) for the incident, the method for sharing EEIs, and the reporting time intervals. It is intended that all member health care facilities (acute, non-acute, and alternate care sites) within the MOCC boundary will report their EEIs at the request of the MOCC. The information will be updated at an interval defined by the MOCC, which may be adjusted during the incident. The following are sample health care facility EEIs that may be reported to the MOCC:

Health Care Facility EEI. Current situation information (as real-time as possible) on:

- General status of the facility

- Available beds by category

  - Depending on MOCC functions, this EEI may involve only ICU beds or all bed types

  - Pediatric beds should be included in totals but also listed as a subset

  - Beds that can be utilized for time-critical emergent procedures (e.g., cardiac intervention) should be included in totals but also listed as a subset.

- Occupied beds by category, ideally by percentage of usual maximum capacity (e.g., 90% vs.125%), so that direct comparisons between facilities can be made

- Staffing contingencies used (e.g., adjusted staffing ratios, use of non-traditional staff in units)

- Number of admitted patients boarding in the emergency department (ED) awaiting inpatient bed/transfer

- Non-emergency procedure status, such as unrestricted, case-by-case, no procedures that will generate inpatient bed need, or no non-emergency procedures (or other similar stratification that uses common language)

- Markers for inpatient critical care, such as ventilators in use, ideally adding other interventions such as patients on vasopressors or other respiratory interventions (e.g., bilevel positive airway pressure)

- Available resources as required by the incident (e.g., ventilators)

- Critical care contingencies in use (e.g., boarding ICU patients in step-down or other units)

- Surgical capability, including blood supply

- Surge beds in use including in temporary care areas

Definitions are important and need to be established by the MOCC Advisory Committee. Available beds may not mean the same thing (e.g., staffed vs. potential to be staffed) between facilities. EHRs may have difficulty distinguishing surge beds versus usually operated beds or may not be able to register them within the EHR system at all. Data validation is critical, particularly if new systems of data submission are being used. Maintaining baseline capacity data collected over time helps greatly to understand how far above baseline the facility and region is and also helps demonstrate capacity that exists when a no-notice incident begins (e.g., a health system that is two standard deviations above usual capacity when a mass casualty incident occurs is much more likely to require inter-regional assistance than one that is much lower than average).

The Contractor shall collaborate with key stakeholders to establish the method and frequency to report EEIs, ideally in alignment with operational reporting periods. These communications will optimally occur at least twice daily. In addition to data exchange, coordination calls may be necessary in the form of a morning stand-up and an evening closing call, or as otherwise specified by the incident or response. These calls present an opportunity to share clinical challenges and resource issues with key stakeholders and other partners and to identify coordination opportunities and action items.

EMS Agency EEIs. Current situation information (as real-time as possible) on:

- General status of the EMS agency

- Total number of staffed Critical Care Transport ambulances

- Total number of staffed ALS ambulances

- Total number of staffed BLS ambulances

- Total number of paratransit vehicles

- Total number of staffed air medical transport assets

- Additional resources availability, such as ambulance buses and non-medical transport vehicles, as applicable

### Coordination/Patient Movement

The primary purpose of patient movement and tracking within the MOCC is to decompress overwhelmed health care facilities through an equitable distribution of patients, as well as to ensure timely transfers of patients to definitive care. The Contractor shall coordinate the inter-facility transfer of patients (including with alternate care sites, if activated and if the MOCC is unable to find appropriate care resources within a reasonable distance) based on defined standards established by the MOCC Advisory Committee. The MOCC does not replace 911 operations for pre-hospital transport of patients originating outside of the health care system and serves as a resource for EMS providers. Depending on its policies, local patient flow may or may not direct EMS which hospitals to transport 911 patients to. The MOCC is primarily designed to manage inter-hospital referrals. It also does not replace usual referral mechanisms and supplements load-balancing activities that occur within health care systems themselves. Patient Movement shall include:

- Referring Facility/Entity Communicates Request

- MOCC Facilitates Patient Placement

- MOCC Supports Repatriation or Transfer to a Lower Level of Care

### Equipment

The Contractor shall coordinate with State partners and stakeholders to secure appropriate equipment to fully operationalize daily patient care coordination and address resource capacity when/if gaps are identified. Equipment to establish robust and secure channels of communications and consensus between stakeholders, MOCC, and EOC will be necessary. Equipment needs might include but are not limited to:

- Communications equipment (e.g., phones, laptops, headsets).

- Licensing/maintenance fees (e.g., software, applications connecting or sharing information with MOCC and stakeholders).

- Vehicle and equipment upgrades.

- Telehealth-enabled tools.

### Medical Resource Sharing/Capacity

MOCC coordination enables the rapid sharing of lifesaving and life-sustaining medical resources, particularly those required for individuals or a small group of patients (e.g. staff, pharmaceuticals, supplies, and equipment). The scope of resource coordination activities will depend on the resources and governance of the MOCC. As the MOCC evolves into a comprehensive operations center, resource coordination considerations should be included, as the data streams and personnel available to the MOCC help inform logistical support as well as patient transfer support.

Resource coordination within the MOCC does not replace normal supply chain processes or existing Emergency Support Function-8 (ESF-8)/EOC resource request processes but may help to coordinate prioritization and distribution of local, State, and federal resources. The MOCC expedites local sharing of medical resources and can serve both an operational and policy function to allocate scarce resources when demand exceeds supply in collaboration with ESF-8/EOC structure. Providers maintain decision-making and administrative authority over their coverage areas.

### Policy Opportunity

The Contractor shall support policy development and execution related to MOCC activities, including:

- General Policy Support: Defining and making recommendations for governance, authority, and policy/procedure to support best practice decision making.

- Support for Mandatory Reporting: Require all hospitals, in-patient mental and behavioral health facilities, and EMS stakeholders to report daily census, including but not limited to available staffed beds, triage/transport status, and critical staffing shortages, with immediate updates when conditions change.

- Support for Participation Agreements: Mandate statewide participation in reporting and data-sharing while maintaining voluntary transfer participation to preserve hospital autonomy

- EMS Routing: Align EMS agencies with MOCC routing decisions to maximize efficiency and ensure fair distribution of transport resources to and from rural hospitals and specialty centers

- Support for Behavioral Health Navigation: Develop policies linking mental/behavioral health 911 calls with MOCC coordination for triage into the 988 system and Crisis Receiving and Stabilization Services (CRSS)

### Business Continuity and Disaster Recovery

The Contractor shall be responsible for developing and maintaining a Disaster Recovery Plan (DRP) and Business Continuity Plan (BCP).

- The BCP must provide adequate backup and recovery for all operations, both manual and automated, including all functions required to meet the backup and recovery standards.

- The DRP must present actions taken before, during, and after a disruptive event as well as procedures required to respond to an emergency, providing back-up operations during a disaster. The DRP should outline how to respond to an emergency or other occurrence (e.g., fire, vandalism, cyberattack, system failure, and natural disaster) that damages systems that contain protected electronic health information.

- The DRP and BCP shall adhere to all HIPAA requirements.

- The BCP and DRP shall be tested annually. Contractor shall provide notice of scheduled tests and a summary of results, including any issues found and corrective actions taken.

After the Disaster Recovery Plan and Business Continuity Plan’s approval, the Contractor is required to comply with and maintain them. The Contractor shall update these plans, as applicable, based on the evolution of data, infrastructure, and tools. In case of a disaster, the Contractor shall carry out responsibilities assigned to the Contractor in the plan both prior to and during a disaster.

Note, in the event of a natural disaster, the Contractor must be operational as soon as possible but no later than fourteen (14) calendar days after the event.

# PROJECT MANAGEMENT

## Project Management Plan

The Contractor must develop an overall Project Management Plan (PMP) that addresses the approach to and execution of the Contractor’s duties and submit for approval by the State. Once approved, the Contractor shall maintain the PMP by updating it to reflect the evolving Schedule, priorities, and resources (i.e., it is a living document). At a minimum, the PMP shall include:

- A Project Workplan that is attainable based on the requirements and their prior experience, including the project Schedule and resource allocations.

- A Communications Management Plan that addresses communication needs for internal and external stakeholders.

- A Project Organization Chart and Staffing Plan inclusive of the minimum staffing requirements identified in Section 4.2.

- A Risk and Issue Management Plan that addresses how risks and issues are identified, communicated, monitored, mitigated, and resolved.

## Key Persons

The Contractor shall provide adequate personnel to meet the needs and operational requirements of the MOCC identified in this Scope of Work. Successful MOCCs have deployed six key types of staff outlined in Table 2, which are required for this project:

Table 2: Key Persons

| Position* | Responsibilities | Experience |
| --- | --- | --- |
| Executive Director | Responsible for comprehensive MOCC oversight/leadership and cross-sector collaboration with all stakeholders. Ensure program management for statewide MOCC implementation and operations. | Extensive experience and knowledge of health care system operations including system design and policy, Extensive experience and knowledge in regional emergency care and health system administration including preparedness and planning (e.g., incident management). (Required) |
| MOCC Manager(s) | Serves as the unit manager and oversees MOCC operations. MOCC Managers may work rotating call schedules to ensure leadership presence. | Health care operations and patient placement, and health care system emergency response. (Required) |
| Medical Director | Oversees the medical team, support personnel, and clinical resource allocation. Responsibilities include, but are not limited to, the following activities that may be delegated to Medical Officers working rotating call schedules: - Evaluate the clinical acuity of potential transfers. - Evaluate the impact of transfer on clinical operations. - Evaluate the potential need for transfer, risks, and benefits. - Provide emergency medical consultation via phone to referring facilities, particularly smaller community hospitals that may have to manage a critically ill patient awaiting transfer for much longer than usual. - Plan/activate specialty consultation (e.g., burn, pediatrics) when necessary to assist with prioritization and care-in-place recommendations. | Physician with experience in emergency care, critical care, trauma, and/or mass casualty with ability to consult with burn, pediatric, and poison control specialists. (Required) |
| Call Takers | Manages incoming calls to the MOCC and ensures requests are entered in the appropriate platform by the requestor. | Administrative staff, ideally with a background in nursing, EMS, or public safety. (Preferred) |
| Transfer Coordinators | Matches the referral hospital and receiving hospital appropriate for the patient’s acuity. Links the referring physician with the admitting physician at the receiving hospital, including needed clinical documentation for physician review to determine appropriateness of transfer. | Charge nurse, nurse manager, or other hospital clinical staff with background in patient access and flow/throughput. Pediatric experience is helpful. (Preferred) |
| Transport Coordinators | Coordinates the transportation of patients between the facilities as required. | Paramedic supervisor or paramedic or emergency medical technician with strong knowledge of regional systems and incident management. (Preferred) |

*Please note that the positions and responsibilities may be shifted or shared amongst staff. The Contractor must ensure that the responsibilities outlined for each position are accounted for and fulfilled through their Staffing Plan.

In addition to the responsibilities noted in Table 2, the MOCC Manager shall perform the following activities in collaboration with MOCC leadership:

- Determine the location of the MOCC (if not already determined) and if staff will report on-site or virtually.

- Decide the number and type of additional staff needed.

- Distribute the MOCC contact number through local public health, emergency management, and member facility Incident Action Plans and Communication Plans.

- Determine additional logistical/equipment needs of the MOCC and address them through the jurisdiction and the health care system.

- Establish robust and secure communications between stakeholders, the MOCC (and other interfacing MOCCs if activated), and the EOC.

- Establish an operational framework that summarizes expectations and processes and can be used by all stakeholders to build a shared understanding of the MOCC’s work.

Call-takers and MOCC Managers should ideally be drawn from health care system staff who have similar daily responsibilities (however, it is expected that, through just-in-time training and targeted call scripts, resources with less experience will able to participate in the initial call-taking role if demand requires). MOCC Managers must have health care system experience with patient placement, and MOCC leadership is expected to have direct hospital and trauma system program experience. Clinicians with trauma center and system leadership backgrounds understand transfer decision making and escalation thresholds.

During the course of the Contract, the State reserves the right to require replacement of individuals fulfilling the roles identified in Table 2, or any other Contractor employee or Subcontractor employee whose work is unacceptable to the State. Reasons for unacceptable work performance include, but are not limited to, the inability of the person to carry out work assignments or unsatisfactory job performance as determined by the State. The individual shall be removed from the project within two (2) weeks of the request for removal and be replaced within thirty (30) calendar days after the position is vacant or sixty (60) calendar days after Executive Director, MOCC Manager, or Medical Director positions are vacant, unless a longer period is approved by the State.

Minimum Staffing Requirements. During MOCC operations, staffing at a minimum should be a MOCC Manager, Medical Director, Call Taker(s), and Transfer Coordinator. Depending on the call volumes, some of these staff may be virtual, particularly off-hours. Though all of the roles and responsibilities described above are applicable, there may be different titles, staffing, and roles required depending on how, where, and when the MOCC operates and how it supports regional capacity and statewide coordination of care.

During a no-notice incident (i.e., an emergency or elevated situation that occurs without warning), a pre-existing roster of staff and structure must be in place to allow a rapid start-up. Operations during a no-notice incident will be maximal at onset. Subject matter experts (SMEs) may be busy with response operations, depending on the location of the incident, and the roster should include experts in emergency medicine, trauma, critical care, burn, pediatrics, and EMS drawn from across the region to ensure availability of enough individuals.

## Other Project Staff

- IDOH MOCC Coordinator. The contracted IDOH MOCC Coordinator shall work with the Contractor and trauma system partners to coordinate the planning, development, and ongoing implementation of the statewide MOCC. The IDOH MOCC Coordinator will serve as a liaison and provide technical assistance for all MOCC related activities and support regional coordination of care and quality improvement within both trauma and non-trauma hospitals statewide via MOCC operations.

- IDOH Oversight and Support. During the term of the RHTP grant period, IDOH shall serve as the program management and compliance oversight entity for the MOCC. IDOH will monitor vendor performance, review and approve required deliverables and reports, and ensure contractual and programmatic requirements are met. In addition to compliance functions, IDOH will provide technical assistance and collaborative support to help guide implementation and advance the goals of the MOCC throughout the duration of the RHTP grant period.

- External Stakeholder Support. Once operational, it is anticipated that all MOCC stakeholders shall support the following activities:

  - Submit data to support situational awareness and respond in a timely manner to requests for data.

  - Fully cooperate and communicate with each other and the MOCC to effectively respond to a disaster, including agreement on the policies for patient transfers and load-balancing.

  - Provide POCs who can communicate with the MOCC and with their organizations on a continuous basis.

  - Consider and define necessity of in-person vs. virtual based on situation (e.g., activation levels, nature of response).

## Document Management

The Contractor shall:

- Maintain complete, accurate, and up‑to‑date project records (e.g., documentation of communications, deliverables, reports, approvals) in accordance with all applicable federal, State, and local records laws and regulations.

- Use a secure, organized filing structure with logical naming and version control so records are easily identifiable and retrievable,

- Provide the State with timely access to all Contract-related records.

- Protect confidential and personally identifiable information through security protocols consistent with applicable privacy and security standards (e.g., HIPAA).

## Status Updates and Reports

Status Updates. The Contractor shall submit the following reports to the State:

- Status Reports shall be submitted monthly on the 5th day of each month or as requested by the State. The reports shall be in a form determined by the State and contain information required by the State.

- Quarterly Success Reports shall be submitted quarterly on the 5th day of each quarter or as requested by the State, and capture successes encountered throughout the quarter. These reports should reflect the project’s progress to meet the strategic goals set forth in the RHTP Grant. The report shall be submitted on a form required by the State. The Quarterly Success Reports shall include reporting on progress against Outcome KPIs outlined in Section 7.1.

- Tracking Reports shall be submitted in accordance with the Milestones identified in Table 2. Tracking Reports shall validate compliance with data reporting requirements and implementation Milestones.

Usage Reports. The Contractor shall implement an automated reporting process to support transparency and situational awareness related to MOCC-facilitated patient movement. The Contractor shall generate and distribute monthly usage reports to each entity participating in the MOCC summarizing patient movement into and out of their facilities during the reporting period including time efficiency.

For each participating facility, the Contractor shall provide counts of patients received by that facility via MOCC patient movement efforts, and counts of patients transferred from that facility to other facilities. The Contractor shall also provide the State and MOCC Advisory Committee with a monthly statewide report summarizing metrics and flow patterns across the State.

## Change Request Process

The Contractor shall use the following change management process during the Contract.

- The State shall issue a Change Request (CR) to the Contractor

- Within ten (10) calendar days following receipt of a CR, the Contractor shall prepare and deliver to the State a written Change Impact Analysis. It must include the following, at a minimum:

  - Description of the proposed scope

  - Schedule that includes estimated start and end dates and tasks in sufficient detail to allow appropriate tracking and with task owners assigned

  - Justification of the CR

  - Staffing plan and forecasted hours and cost breakdown by position

  - Applicable key performance indicator(s)

  - Security impacts and how they will be addressed

  - A list of work products or deliverables that the Contractor will submit

  - Any other CR-specific requirements requested by the State

- The State will review the CR and either approve or disapprove it and request changes.

- The Change Impact Analysis will be modified until the State provides approval. Upon approval, the Change Impact Analysis shall be deemed an approved CR. The Contractor shall not begin work on any CR prior to receiving the State's approval.

# INDEPENDENT VALIDATIONS AND VERIFICATION

If the State decides to add Independent Verification & Validation (IV&V) services as part of this Contract, the Contractor will copy the Indiana Department of Administration (IDOA) -- IV&V Team member(s) on all project related communications (emails, meeting invites, collaboration tools, etc.) and will grant access to all documents and deliverables throughout the term of the Contract.  If IDOA elects to deploy IV&V services in connection with this engagement, the IV&V Team will review and assess all deliverables to determine compliance with the State's requirements set forth in the Contract including the Statement of Work. For contracts entered into, renewed, or amended after June 30, 2026, the IV&V Team shall serve as an approving authority, and no payment shall be issued to the Contractor unless and until IV&V has provided such approval.

# COMPLIANCE REQUIREMENTS

The Contractor shall:

- Abide by all applicable State and federal laws.

- Maintain compliance with all standard State policies and procedures.

- Maintain compliance with requirements related to the RHTP, including submission of data and reports as requested by the State and/or CMS.

- Abide by security requirements per Indiana’s RAMP policy

- Any materials the Contractor develops in partnership with the State for public distribution and/or to be published on State websites must comply with the State’s Assistive Technology standards and architectural standards, and Section 508 of the US Rehabilitation Act. The Contractor specifically agrees that all hardware, software and services provided to or purchased by the State shall be compatible with the principles and goals contained in the Assistive Technology Standard, within the State’s Information Security Framework (https://www.in.gov/iot/iot-vendor-engagement/), State Assistive Technology (https://www.in.gov/core/accessibility), and the State’s architectural standards. Any deviation from these requirements must be approved in writing by IOT in advance.

# KEY PERFORMANCE INDICATORS

The State will use Key Performance Indicators (KPIs) to measure performance and outcomes of the Contract. The specific KPIs and their targets will be defined and agreed upon by the State and the Contractor during the initial phases of the requirements under the Contract. At a minimum, on time delivery at quality standards of the scope provided within the budget set forth in the Contract will each be measured. Additionally, the State will collect a modified Net Promoter Score from customers to this Contract in its discretion. Low ratings on the modified Net Promoter Score or failure to meet any other KPIs may be deemed, at the discretion of the State, to constitute default under the Contract.

## Outcome KPIs

The Contractor shall report on the following outcome KPIs in Quarterly Success Reports which shall be submitted by the 5th day of each quarter or as defined by the State. The Contractor shall ensure MOCC-specific data relevant to each outcome KPI is recorded and compiled in Quarterly Success Reports. The State shall provide available baseline data for Outcome KPIs and access to other data sources needed to measure KPI targets.

Table 3: Outcome KPIs

| # | KPI | Targets |
| --- | --- | --- |
| 1 | MOCC Utilization (Number of Interfacility Transfers Facilitated by the MOCC) | Increase the number of MOCC-facilitated transfers by 5% in the second year of implementation (compared to year 1) and by 10% over year 1 by FY 2031. |
| 2 | ED Length of Stay Prior to Transfer for MOCC-Facilitated Transfers (High Acuity vs. Low Acuity) | Increase the baseline percentage of transferred patients with ED length of stay <2 hours by 5% annually following implementation (stratified by high acuity vs. low acuity). |
| 3 | Number/proportion of MOCC –Facilitated EMS Encounters for Mental Health Conditions (Without Additional Injury or Illness) Transported to ED | Decrease the number of mental health EMS encounters resulting in transport to an emergency department by 10% over baseline by FY 2031. |

## Operational KPIs

The Contractor shall report on the following operational KPIs in monthly Status Reports, which shall be submitted by the 5th day of each month. The Contractor shall provide full transparency to access all materials and associated work products included in this Contract if requested.

Table 4: Operational KPIs and Threshold for Compliance

| # | KPI | Threshold for Compliance |
| --- | --- | --- |
| 1 | Milestone Timeliness | The Contractor shall successfully complete milestones according to the approved Project Workplan. Milestones shall be considered complete upon receiving written confirmation of milestone acceptance from the State. The Contractor shall notify the State, at minimum, 10 business days prior to the agreed upon milestone completion dates of any risk to milestone delivery. |
| 2 | Staff Quality | The Contractor shall: - Provide ongoing training at minimum annually for all MOCC staff on updated MOCC capabilities and procedures. - Upon the State’s request, ensure that employees are removed within two (2) weeks of the request for removal and be replaced within thirty (30) calendar days after the position is vacant or sixty (60) calendar days after Executive Director, MOCC Manager, or Medical Director positions are vacant, unless a longer period is approved by the State. |
| 3 | Reporting Timeliness | The Contractor shall: - Submit monthly Status Reports on the 5th day of each month or as requested by the State. Status Reports shall include, at minimum: - Progress on overall project milestones, deliverables, and schedule - Validation of meeting KPIs - Planned corrective actions where applicable - Submit Quarterly Success Reports on the 5th day of each quarter or as requested by the State. |
| 4 | Elevated Operations Activation | The Contractor shall comply with prescribed timeframes of activation levels for elevated operations as defined by the MOCC Advisory Committee. |
| 5 | Security Incidents Reporting Timeliness | The Contractor shall: - Communicate any security incident to the State and MOCC Advisory Committee within one hour of discovery. A security incident is defined as an occurrence that actually or potentially jeopardizes the confidentiality, integrity, or availability of an information system or the information the system processes, stores, or transmits or that constitutes a violation or imminent threat of violation of security policies, security procedures, or acceptable use policies. - Submit a written incident report to the State within 48 hours of incident occurrence. |

The Contractor shall accurately track and report on performance against Operational KPIs in monthly Status Reports. It is the intent of the State to remedy any contract infractions through collaboration and discussions with the Contractor prior to the implementation of any payment withholds. If the Contractor fails to meet requirements set forth in the Contract, then the State will provide the Contractor with a written notice of non-compliance and may require any of the corrective actions or remedies discussed below.

Corrective Actions. If the Contractor does not meet the threshold for compliance for the Operational KPIs defined in this section, or if the State determines that the Contractor is not performing to the satisfaction of the State, the Contractor shall submit, within ten (10) business days of the State’s written notice of non-compliance, a written Corrective Action Plan (CAP). The nature of the corrective action(s) will depend upon the nature, severity, and duration of the deficiency and repeated nature. Severity shall be determined by the State, in its sole discretion.

At a minimum, the CAP shall address the causes of the deficiency, the impacts and the measures being taken or recommended to remedy the deficiency, and whether the solution is permanent or temporary. It must also include a schedule showing when the deficiency will be remedied, and when the permanent solution will be implemented, if appropriate. Including specific dates is recommended.

Payment Withholds. Beginning the month in which a CAP is required, the State may withhold up to 10% of the following month’s payment as requested in its submitted invoice and subsequent billing. When the CAP is completed and the proposed remedy to all deficiencies are completed to the satisfaction of the State, the withheld amount shall be returned to the Contractor within 30 days. Should the CAP not be submitted as required or should the remedy not be implemented within the time frame specified by the CAP, the Contractor shall forfeit the withheld amount. In addition, the State reserves the right to pursue appropriate legal recourse for any damage sustained because of this failure to perform.

The Contractor and the State shall schedule regular meetings to discuss the Contractor’s performance on the CAP. The Contractor is required to show satisfactory progress towards milestones and otherwise provide information that can be used to show that performance is satisfactory. Scheduling of review meetings shall be agreed upon mutually between Contractor and the State.

# END OF CONTRACT TRANSITION AND TURNOVER

## Sustainability

The State expects the MOCC to evolve into a sustainable and adaptable model capable of maintaining core functions beyond the initial RHTP grant period. Sustainability planning shall consider potential funding options and future governance and operational models. The Contractor shall be responsible for identifying and assessing feasible pathways for continued MOCC operations, which may include, but are not limited to, transition to an independent entity or integration into an existing healthcare or emergency response infrastructure. The MOCC sustainability and future state planning shall be discussed throughout the Contract term with the State and MOCC Advisory Committee, including potential new funding streams.

## Turnover

In the event that MOCC services are transitioned to a successor entity at or following the end of the Contract term, the Contractor shall cooperate and collaborate fully with the successor entity to ensure a smooth transition of services. The Contractor shall provide all necessary information, documentation, and reasonable assistance to enable continuity of MOCC operations without interruption or degradation of service quality. Transition activities shall be planned and executed in a manner that avoids any adverse impact on stakeholders, including participating healthcare partners.