ATTACHMENT K2

RFP 26-87448

STATEMENT OF WORK – MOCC SYSTEMS

INDIANA MEDICAL OPERATIONS COORDINATION CENTER RFP

# EXECUTIVE SUMMARY

## Purpose Statement

On Dec. 29, 2025, Indiana was awarded a grant of nearly $207 million for the first year of a five-year federal Rural Health Transformation Program (RHTP) to address health outcomes in the State’s rural communities. This Rural Health Transformation Program is supported by the Centers for Medicare & Medicaid Services (CMS) of the U.S. Department of Health and Human Services (HHS) as part of a financial assistance award totaling $206,927,896.80 with 100 percent funded by CMS/HHS. The contents are those of the author(s) and do not necessarily represent the official views of, nor an endorsement, by CMS/HHS, or the U.S. Government.

The purpose of this Request for Proposal (RFP) is to procure a qualified vendor to implement a Healthcare Emergency and Hospital Capacity System for the State of Indiana, which will support the RHTP strategic goal of “Sustainable Access.” The awarded vendor (“Contractor”) will design, develop, implement, maintain, and operate a Healthcare Emergency and Hospital Capacity System (“System”). This system will be a robust, real-time hospital, healthcare, public health and EMS reporting and data delivery system. Respondents may propose either (a) their own configurable solution or (b) a solution brought to the State through a subcontract with a solution vendor. The System must provide 24/7 network-based delivery for the following two components in emergency settings:

(1) Healthcare Infrastructure Status Information and

(2) Pre-Hospital Care and Patient Movement Tracking

If the Contractor also submitted a proposal for the MOCC Services scope (see Attachment K1) but is not awarded that scope, they shall fully cooperate and support the State and the MOCC Services Contractor in the implementation and operations of the MOCC through the System.

Note: If the Respondent chooses to propose for the MOCC System, complete Attachment D2 (System Cost Proposal) and Attachment F2 (System Technical Proposal). Additionally, complete Attachments L (Resource Usage Matrix), M (Infrastructure Overview), and N (Artificial Intelligence Questions) along with the other forms and attachments required by the RFP.

## Description of Work

Per federal guidance on the RHTP grant, the Contract resulting from this RFP will have a five-year contract term, but the Contract only has funding for the initial budget period (Budget Period 1). This Contract will be amended to add subsequent funding for each of the budget periods based on federal funding awarded for those budget periods. The federal funding supporting this Contract must be expended within strict deadlines; therefore, failure to complete work by specified deadlines may subject this Contract to termination to ensure funds are spent in accordance with federal requirements.

# BACKGROUND AND CURRENT STATE

The MOCC will rely upon a broad range of stakeholders (including, but not limited to, hospitals, EMS, and system partners) to monitor health care personnel and utilize the Healthcare Emergency and Hospital Capacity System platform, to understand current capacity and gaps in the health care system, and to facilitate care coordination including referrals and load-balancing through patient transfers. For more information on sample MOCC operations and models, see resources from the American College of Surgeon’s Regional Committees on Trauma: https://www.facs.org/quality-programs/trauma/committee-on-trauma/regional-committees-on-trauma/field-program/rmoccs/.

Table 1 has been included below to provide context to the Contractor of the MOCC Services Contractor’s milestones, deliverables, and associated timeline.

Table 1: MOCC Services Contractor’s Milestones and Deliverables

| Milestone # | Milestone | Deliverable | Anticipated Start Date | Anticipated Completion Date |
| --- | --- | --- | --- | --- |
| Budget Period 1 Funding |  |  |  |  |
| 1 | Hiring and onboarding operational staff and establishing Advisory Committee | - Project Management Plan (PMP), including: - Project Workplan with Schedule and resource allocations - Project Organization Chart and Staffing Plan - Communication Management Plan - Risk and Issue Management Plan - Onboarding Training Plan - Operational staff fully onboarded | 9/1/2026 | 12/31/2026 |
| 2 | Complete planning activities for 1) implementation of Healthcare Emergency and Hospital Capacity System and 2) pilot programs, including identification of pilot areas | - MOCC Implementation Plan, including consideration for implementation of Healthcare Emergency and Hospital Capacity System in MOCC operations - Interfacility Pilot Implementation Plan - Behavioral Health Triage Pilot Implementation Plan | 1/1/2027 | 3/30/27 |
| 3 | Operationalize and begin utilization of Healthcare Emergency and Hospital Capacity System for facility status and patient tracking | - MOCC Operations Plan - Business Continuity Plan (BCP) and Disaster Recovery Plan (DRP) - Complete activities per BCP and DRP - Pilot rollout - Confirmation of Healthcare Emergency and Hospital System implementation/utilization | 3/30/2027 | 6/30/2027 |
| 4 | Implementation of MOCC utilization within pilot areas (TBD) for interfacility transfers | - Post-Interfacility Pilot Implementation Report | 3/30/2027 | 7/31/2027 |
| Budget Period 2 Funding |  |  |  |  |
| 5 | Implementation of MOCC utilization within pilot areas (TBD) for behavioral health triage | - Post-Behavioral Health Triage Pilot Implementation Report | 7/1/2027 | 10/31/2027 |
| 6 | 100% of hospitals submitting data to the Healthcare Emergency and Hospital Capacity System. Note: 172 total hospitals have been identified in the State. All 172 total hospitals, or an identified subset of these hospitals, may be required to submit data to the Healthcare Emergency and Hospital Capacity System pending State leadership and stakeholder discussion* | - MOCC hospital tracking report | 7/1/2027 | 10/30/2027 |
| 7 | 100% of EMS partners submitting data to the Healthcare Emergency and Hospital Capacity System* | - MOCC EMS tracking report - Pilot completion | 7/1/2027 | 10/30/2027 |
| 8 | Implementation of MOCC utilization within 50% of regions for interfacility transfers* | - MOCC interfacility transfer tracking report, validating compliance with milestone requirements | 7/1/2027 | 10/30/2027 |
| 9 | Implementation of MOCC utilization within 50% of regions for behavioral health triage* | - MOCC behavioral health tracking report, validating compliance with milestone requirements | 10/1/2027 | 12/31/2027 |
| 10 | Identification and integration of additional systems, technology, and tools for full integration and utilization of Healthcare Emergency and Hospital Capacity System | - Integration Plan | 7/1/2027 | 12/31/2027 & Ongoing |
| 11 | Training and education on MOCC and Healthcare Emergency and Hospital Capacity System provided to all hospital and EMS partners by region | - Training Plan - Approved provider training materials - Training Results Log, including number of trainings provided, dates, and attendees - Approved communication products - Deliver agreed upon training (as applicable) - Competency Assessments (pre/post training – as applicable) | 3/30/2027 | 12/31/2027 |
| 12 | Implementation of MOCC utilization within 100% of regions for interfacility transfers* | - MOCC interfacility transfer tracking report, validating compliance with milestone requirements | 1/1/2028 | 6/30/2028 |
| 13 | Implementation of MOCC utilization within 100% of regions for behavioral health triage* | - MOCC behavioral health tracking report, validating compliance with milestone requirements | 1/1/2028 | 6/30/2028 |
| Budget Period 3 Funding |  |  |  |  |
| 14 | Integration of telemedicine and computer-aided dispatch (CAD) systems into MOCC services for care coordination and triage of patients | - Telemedicine Implementation Plan - CAD Implementation Plan | 7/1/2027 | 10/30/2028 |

# SCOPE OF WORK

## MOCC Services Deliverables and Deadlines

The MOCC Systems Contractor shall complete System development, design, and implementation activities in alignment with the anticipated start and completion dates in Table 1 to ensure the overall success of MOCC delivery.

## Payment and Invoicing

The Contractor shall invoice the State in accordance with the Milestones and payment structure captured in Attachment D2 – System Cost Proposal. The invoice must have sufficient information describing the work performed for reimbursement, including details on deliverables completed to achieve each implementation milestone.

CMS has required that all Budget Period 1 costs be drawn down by September 30, 2027. As such, the Contractor shall complete work for all milestones and activities covered by Budget Period 1 funding by July 31, 2027, and shall submit all related invoices no later than August 14, 2027, to allow the State time to process and pay funds in alignment with CMS guidance.

For this contract, milestones and activities covered by Budget Period 1 funding shall be (a) implementation of the System for MOCC utilization within pilot areas for interfacility transfers by March 30, 2027, and (b) the months of M&O support post pilot implementation through July 31, 2027. Milestones and M&O monthly fees covered by Budget Period 1 funding must be invoiced by August 14, 2027. The Contractor shall factor in this timing while planning for deliverable submission, review(s), updates (if needed), and approval.

Milestones and activities funded by future budget period amounts will follow the same or similar requirements for invoicing timeliness, to be confirmed by the State pending further guidance from CMS and the State’s RHTP team.

## Overview

System Implementation. The Contractor shall design, develop, implement, maintain, and operate a robust, real-time hospital, healthcare, public health and EMS reporting and data delivery system. The System must provide 24/7 network-based delivery for the following two components in emergency settings:

(1) Healthcare Infrastructure Status Information and

(2) Pre-Hospital Care and Patient Movement Tracking

The Contractor shall provide qualified technical staff with previous experience implementing the proposed solution or a similar solution in another organization.

The Contractor shall be responsible for System Development Lifecycle (SDLC) activities to implement the system in alignment with the milestones in Table 1. The System will meet the requirements noted in Section 3.4 and support the contractual MOCC scope of work. The Contractor shall resolve all defects in a timely manner and at no additional cost to the State. Data conversion and migration needs will be further explored with the Advisory Committee and the State and addressed as a change request.

Maintenance and Operations. The Contractor shall be responsible for the M&O of the System post go-live including: system maintenance, application monitoring, access management, business continuity and disaster recovery, document/artifact management, release management, security management, end user training, help desk, incident management and resolution, and reporting support.

## Requirements

- Capture crucial Essential Elements of Information (EEI)

  - Healthcare Infrastructure Status Information: Capture crucial EEI for effective emergency management, healthcare system coordination, patient transport, and executive leadership decision-making from healthcare facilities, including but not limited to hospitals, EMS, long-term care, dialysis/ESRD, local health department (LHD), urgent care, Federally Qualified Health Care (FQHC), Community Health Centers (CHCs), Rural Health Centers (RHCs), rehabilitation facilities, behavioral mental health providers. The elements include but not limited to:

    - Bed capacity and utilization (e.g., ICU, med/surg, pediatric, behavioral health)

    - Ventilator availability

    - Generator and power status

    - Emergency department functionality

    - Staffing levels and shortages

    - Surge capacity and Mass Causality Triage indicators

    - Diversion Status

    - Telecommunications Status

    - Facility Water Status

    - Electronic Medical Records Status

  - Pre-Hospital Care and Patient Movement Tracking - Capture crucial EEI pertinent to emergency management and patient tracking/care coordination, including but not limited to:

    - Patient destination alerts for emergency transport

    - Real-time tracking of EMS unit status and location including linkage with the local 911 Computer Aided Dispatch (CAD) system.

    - Ambulance availability and response times

    - Hospital diversion status and capacity, including bed availability and types (ICU, med/surg, etc.)

    - Patient triage status and critical care needs

- Role-based Access:

  - Provide configurable, role-based access controls that allow administrators to define multiple permission levels for distinct user groups, including (but not limited to) EMS providers, hospital personnel, emergency management staff, and system administrators. Access should be assignable at both the organizational and functional level to ensure that users only see and perform actions appropriate to their role. There shall be flexibility of page and field level permissions/restrictions, the configurations of which should be flexible to allow for regulation changes in a future-state.

  - Provide the State with Administrator-level access to all systems and associated platforms/applications. Administrator access shall include the ability to generate and export reports, monitor performance, and perform other administrative functions necessary for system oversight, configuration, and utilization. This access shall enable the State to utilize the System for operational purposes beyond the scope of the MOCC (such as DEP Reporting). The MOCC shall maintain autonomy for decision-making around governance, policy and procedures, and process related the MOCC and System operations, but the State shall have direct access and use of the System.

- Application Programming Interface (API)

  - Support interoperability with the following through APIs:

    - Hospital Information Systems (HIS) and Electronic Medical Records (EMR/EHR) platforms for facility status and patient census data

    - 9-1-1 Public Safety Answering Points (PSAPs) Computer Aided Dispatch (CAD) systems

    - EMS systems (EMR, CAD, tracking) for real-time patient transport and hospital destination data

    - Out-of-state health systems, state and locally operated healthcare facilities and EMS tracking systems. These connections will support cross-border transportation and situational awareness.

    - Public Health Systems, including syndromic surveillance, laboratory reporting, and emergency operations databases.

    - State and Federal Data Systems such as Health Care Coalition platforms, or other regional situational awareness tools.

    - Healthcare Infrastructure Status Information Specific

      - IDOH's Analytics Cloud Environment (ACE) - potentially on a near real-time basis

      - Indiana Department of Homeland Security (IDHS) WebEOC platform

      - Hospital and healthcare system EMRs, 911 Public Safety Answering Point Computer Aided Dispatch (CAD) systems

    - Automated Data Upload: Enable continuous (every 15 minutes) and scheduled data transfer from hospital and healthcare systems to maintain accurate, real-time operational data (e.g., bed availability, diversion status, staffing, critical resource levels)

    - Include automated workflows; automated data ingestion must support configurable thresholds and alerts to flag data inconsistencies or operational changes (e.g., capacity thresholds, resource shortages, or diversion status changes)

    - Interoperability: Ensure compliance with national data standards (e.g., HL7, FHIR, NEMSIS, EDXL) and industry best practices for authentication, encryption, and access control.

    - Ensure APIs adhere to industry best practices for authentication, encryption, and access control. Provide technical documentation, testing environments, and support for onboarding partner systems. Provide technical documentation, testing environments, and support for onboarding partner systems

- Dashboards: Provide dashboards (at the healthcare facility, EMS unit, district, and state level) and other methods to take all data elements within the system and turn it into digestible information that can be shared amongst key stakeholders.

- Automation and Data Management: The System shall include automated workflows to collect, validate, and display data without requiring manual entry whenever possible. Automated data ingestion must support configurable thresholds and alerts to flag data inconsistencies or operational changes (e.g., capacity thresholds, resource shortages, or diversion status changes)

- User Experience and Functional Requirements:

  - Collaboration Tools: Users and administrators must be able to send alerts on network, county, district, and statewide levels, enabling coordinated communication during emergencies.

  - Patient Tracking System Integration: The platform must provide the ability to connect with existing patient tracking systems utilized by EMS and healthcare facilities.

  - User-friendly Dashboard: Design a comprehensive dashboard for administrators and users to monitor key metrics

    - Healthcare Infrastructure Status Information examples: bed and ventilator availability, resource statuses, and recent notifications

    - Pre-Hospital Care and Patient Movement Tracking examples: EMS response times, patient tracking, hospital statuses, and alerts in real-time

  - Advanced Reporting Interface: Provide tools for generating reports on-demand or scheduled, with the capability to export in various formats (PDF, Excel, etc.).

  - The system must facilitate patient reunification during mass causality events or other large-scale emergencies.

  - Have web-based and mobile application options to support EMS personnel in the field. The system must be accessible from multiple mobile digital devices, including laptop, tablet, and cell phone.

- Security and Compliance: The System and its integrations and data exchanges must comply with applicable state and federal laws, including HIPAA, HITECH, and state data security standards. The Contractor will implement and maintain appropriate security controls and provide documentation verifying compliance. Examples of standards and laws:

  - State and federal privacy/security regulations (HIPAA Security Rule (45 CFR § 164.300 – 318), HITECH Act, GovRamp. Indiana Code Title 16, Article 39, IOT Security Standards

  - GovRamp standards for secure cloud-based API integrations.

  - De-identification or aggregation of PII/PHI unless safeguards are in place.

  - Secure transport protocols (HTTPS/TLS) and audit logging.

  - State-specific governance for sensitive infrastructure data. All integrations involving sensitive infrastructure data must undergo security review and approval by the Indiana Office of Technology (IOT).

  - IOT standards for: Secure API design, Authentication and authorization, Logging, monitoring, and auditability and Encryption key management aligned with NIST SP 800-57

  - Compliance with IOT Security Framework.

  - TEFCA (Trusted Exchange Framework and Common Agreement), 45 CFR §170.215 – API Standards

- Healthcare Infrastructure Status Information Specific: File Validation - The Contractor will be required to be responsible for the submission of data to the IDOH, along with the National Healthcare Safety Network (NHSN), to include the list of NHSN Organization ID numbers.

- Offline Functionality/Extended Downtime Requirements

  - The System must be designed to operate with partial functionality offline, enabling key features essential for emergency response and patient tracking. This includes:

    - Access to Essential Information: Users should have offline access to critical operational data, such as current bed capacities, staffing levels, and equipment availability to support decision-making during emergencies.

    - Healthcare Infrastructure Status Information Specific:

      - Real-time Patient Tracking: EMS providers should be able to record patient data, transport details, and triage information offline. This data will sync automatically with the central system once connectivity is restored.

      - Critical Alerts and Notification Management: Users must have the ability to send and receive alerts regarding critical incidents, staffing changes, and diversion statuses without relying on an active internet connection.

  - Data Synchronization and Integrity

    - The System must include mechanisms for seamless data synchronization when connectivity is re-established. This ensures that all offline records are captured accurately and integrated into the main database without data loss or duplication.

    - A protocol must be established to validate the integrity of the data transferred during synchronization, ensuring accuracy and consistency across systems.

## Key Testing Requirements

- Develop and obtain approval for an overall System test plan.

- Collaborate with designated hospitals, healthcare coalitions, state agencies, and any other identified stakeholders to:

- Conduct interface testing and data validation.

- Demonstrate real-time data synchronization and accuracy.

- Document successful integration with at least three EMR platforms and one EMS data source prior to full System launch.

- Provide near real time dashboards as agreed upon by the State and Contractor to demonstrate testing status and defect management status.

- User Acceptance Testing (UAT): Conduct thorough testing with EMS teams, hospital staff, healthcare facility staff, any other identified stakeholders, and administrators to validate that all functional requirements are met.

- Performance Testing: Test the System for handling large volumes of data and simultaneous users to ensure it can scale appropriately.

- Security Testing: Software Security Scans and System Penetration Tests should be performed prior to a solution being placed into production with results provided to the State including IOT for signoff.

## User Support and Training Requirements

- Develop a dedicated support structure, including specialists to assist with the design and implementation of System changes.

- Provide initial and ongoing training sessions (using a delivery method agreed to by the State and Contractor) for all users (estimated 150+ users), complemented by 24/7 technical support during incidents and regular business hours.

- Facilitate on-site support during emergency operations to ensure System effectiveness.

- Develop user manuals, an extensive knowledge base, and an online help center to aid users.

## Issue Resolution

If issues arise in the production environment, the Contractor shall work with the State to resolve issues in a timely manner. The Contractor shall have a clear escalation procedure through the appropriate chain of command to help ensure that the production issue is getting the appropriate attention to meet the level of urgency. Table 2 outlines production issue severity levels, and the Contractor’s expected resolution times.

Table 2: Production Issue Severity Levels and Resolution Times

| Severity Level | Description | Example | Resolution Time |
| --- | --- | --- | --- |
| Critical | System failure: no further processing is possible | Critical to solution availability, results, functionality, performance, or usability | Within four (4) hours of identification |
| High | Unable to proceed with selected function or dependents | Critical component unavailable or functionally incorrect (acceptable workaround is not available) | Within one (1) business day of identification |
| Medium | Restricted function capability: however, processing can continue | Non-critical component unavailable or functionally incorrect; incorrect calculation results in functionally critical key fields/dates (acceptable workaround is available) | Within five (5) business days of identification or resolution time approved by State |
| Low | Minor cosmetic change needed | Usability errors: screen or report errors that do not materially affect the quality and correctness of function, intended use, or results | Within two (2) weeks of identification or resolution time approved by State |

Production issues shall be recorded and tracked in an issue tracking tool provided by the Contractor. Critical severity issues must be reported to designated State staff within one (1) hour of discovery.

The Contractor shall provide Incident Reports for all Critical and High severity issues. The Incident Reports must include the affected areas of the system, date of report, date of incident, reference number, start and end times of the incident, issue type, issue impact summary, detailed description of the issue, immediate resolution, permanent solution, and who resolved the issue.

The Contractor must provide initial incident reports for critical and high severity incidents within twenty-four (24) hours from the start of the system incident. If the incident report does not include the permanent solution to the incident, that report must be updated every twenty-four (24) hours to reflect the most current status of the incident until it is resolved. The Contractor must provide a follow-up incident report no later than twenty-four (24) hours after the Contractor has defined the permanent solution for critical and high severity incidents. For medium and low severity levels, initial incident reports must be provided within five (5) business days, or a timeline approved by the State.

If the Contractor cannot resolve an issue within the established resolution time for its severity level, the Contractor must submit a plan and revised timeline for issue resolution to the State in the Incident Reports.

## End of Contract Transition and Turnover

The Contractor shall transfer the following information to the State or its agent on a medium acceptable to the State:

- A copy of the System including its database(s):

- All SDLC artifacts and documentation created, maintained, and updated throughout the Contract term on State-designated repository

- Internal logs and procedures used during the contract to ensure compliance with operational requirements

- Other documentation including, but not limited to, user, provider, and operations manuals; training materials; and documentation of any interfaces developed to support business activities between contractors

- Source/object codes for software components and documentation for transfer systems and any customizations to the Contractor’s COTS software. The State shall receive source code, developer/user documentation, and a perpetual royalty‑free license for any custom code. Note: All new software functionality built on top of any COTS software will be owned by the State.

- All in-progress artifacts and solution components

If the solution is being provided by a third-party solution provider, the Contractor shall cooperate and support the State as the State pursues a separate agreement with the provider to continue maintaining and operating the System.

## Key Performance Indicators

The State will use Key Performance Indicators (KPIs) to measure performance and outcomes of the Contract. The specific KPIs and their targets will be defined and agreed upon by the State and the Contractor during the initial phases of the requirements under the Contract. At a minimum, on time delivery at quality standards of the scope provided within the budget set forth in the Contract will each be measured. Additionally, the State will collect a modified Net Promoter Score from customers to this Contract in its discretion. Low ratings on the modified Net Promoter Score or failure to meet any other KPIs may be deemed, at the discretion of the State, to constitute default under the Contract.

The Contractor shall report on the following operational KPIs in monthly Status Reports, which shall be submitted by the 5th day of each month. The Contractor shall provide full transparency to access all materials and associated work products included in this Contract if requested.

Table 3: KPIs and Threshold for Compliance

| # | KPI | Threshold for Compliance |
| --- | --- | --- |
| 1 | Milestone Timeliness | The Contractor shall successfully complete 100% of milestones according to the approved Project Workplan. Milestones shall be considered complete upon receiving written confirmation of milestone and associated deliverables’ acceptance from the State. The Contractor shall notify the State, at minimum, 5 business days prior to the agreed upon milestone completion dates of any risk to milestone delivery. |
| 2 | Staff Quality | The Contractor shall: - Upon the State’s request, ensure that employees are removed within two (2) weeks of the request for removal and be replaced within thirty (30) calendar days after the position is vacant, unless a longer period is approved by the State. |
| 3 | Reporting Timeliness | The Contractor shall submit monthly Status Reports on the 5th day of each month or as requested by the State. Status Reports shall include, at minimum: - Progress on overall project milestones, deliverables, and schedule - Validation of meeting KPIs - Planned corrective actions where applicable |
| 4 | Security Incidents Reporting Timeliness | The Contractor shall: - Communicate any security incident to the State and MOCC Advisory Committee within one hour of discovery. A security incident is defined as an occurrence that actually or potentially jeopardizes the confidentiality, integrity, or availability of an information system or the information the system processes, stores, or transmits or that constitutes a violation or imminent threat of violation of security policies, security procedures, or acceptable use policies. - Submit a written incident report to the State within 48 hours of incident occurrence, which includes: - Status of open incidents - Risks with risk mitigation strategies - Issues log |
| 5 | Production Environment Availability (M&O) | 99.9% availability, except during scheduled maintenance |
| 6 | Issue Resolution | The Contractor shall resolve issues within the following timeframes: - Critical Severity: 98% of all issues in the production environment are resolved within four (4) hours of identification. - High Severity: 98% of all issues in the production environment are resolved within one (1) business day of identification. - Medium Severity: 98% of all issues in the production environment are resolved within five (5) business days of identification. - Low Severity: 98% of all issues in the production environment are resolved within two (2) weeks of identification. |

The Contractor shall accurately track and report on performance against KPIs in monthly Status Reports. It is the intent of the State to remedy any contract infractions through collaboration and discussions with the Contractor prior to the implementation of any payment withholds. If the Contractor fails to meet requirements set forth in the Contract, then the State will provide the Contractor with a written notice of non-compliance and may require any of the corrective actions or remedies discussed below.

Corrective Actions. If the Contractor does not meet the threshold for compliance for the Operational KPIs defined in this section, or if the State determines that the Contractor is not performing to the satisfaction of the State, the Contractor shall submit, within ten (10) business days of the State’s written notice of non-compliance, a written Corrective Action Plan (CAP). The nature of the corrective action(s) will depend upon the nature, severity, and duration of the deficiency and repeated nature. Severity shall be determined by the State, in its sole discretion.

At a minimum, the CAP shall address the causes of the deficiency, the impacts and the measures being taken or recommended to remedy the deficiency, and whether the solution is permanent or temporary. It must also include a schedule showing when the deficiency will be remedied, and when the permanent solution will be implemented, if appropriate. Including specific dates is recommended.

Payment Withholds. Beginning the month in which a CAP is required, the State may withhold up to 10% of the next payment as requested in its submitted invoice and subsequent billing. When the CAP is completed and the proposed remedy to all deficiencies are completed to the satisfaction of the State, the withheld amount shall be returned to the Contractor within 30 days. Should the CAP not be submitted as required or should the remedy not be implemented within the time frame specified by the CAP, the Contractor shall forfeit the withheld amount. In addition, the State reserves the right to pursue appropriate legal recourse for any damage sustained because of this failure to perform.

The Contractor and the State shall schedule regular meetings to discuss the Contractor’s performance on the CAP. The Contractor is required to show satisfactory progress towards milestones and otherwise provide information that can be used to show that performance is satisfactory. Scheduling of review meetings shall be agreed upon mutually between Contractor and the State.

# BUSINESS CONTINUITY AND DISASTER RECOVERY

The Contractor shall be responsible for developing and maintaining a Disaster Recovery Plan (DRP) and Business Continuity Plan (BCP).

- The BCP must provide adequate backup and recovery for all operations, both manual and automated, including all functions required to meet the backup and recovery standards.

- The DRP must present actions taken before, during, and after a disruptive event as well as procedures required to respond to an emergency, providing back-up operations during a disaster. The DRP should outline how to respond to an emergency or other occurrence (e.g., fire, vandalism, cyberattack, system failure, and natural disaster) that damages systems that contain protected electronic health information.

- The DRP and BCP shall adhere to all HIPAA requirements.

- The BCP and DRP shall be tested annually. Contractor shall provide notice of scheduled tests and a summary of results, including any issues found and corrective actions taken.

After the Disaster Recovery Plan and Business Continuity Plan’s approval, the Contractor is required to comply with and maintain them. The Contractor shall update these plans, as applicable, based on the evolution of data, infrastructure, and tools. In case of a disaster, the Contractor shall carry out responsibilities assigned to the Contractor in the plan both prior to and during a disaster.

Note, in the event of a natural disaster, the Contractor must be operational as soon as possible but no later than fourteen (14) calendar days after the event.

# CHANGE REQUEST PROCESS

The Contractor shall use the following change management process during the Contract.

- The State shall issue a Change Request (CR) to the Contractor

- Within ten (10) calendar days following receipt of a CR, the Contractor shall prepare and deliver to the State a written Change Impact Analysis. It must include the following, at a minimum:

  - Description of the proposed scope

  - Schedule that includes estimated start and end dates and tasks in sufficient detail to allow appropriate tracking and with task owners assigned

  - Justification of the CR

  - Staffing plan and forecasted hours and cost breakdown by position

  - Applicable key performance indicator(s)

  - Security impacts and how they will be addressed

  - A list of work products or deliverables that the Contractor will submit

  - Any other CR-specific requirements requested by the State

- The State will review the CR and either approve or disapprove it and request changes.

- The Change Impact Analysis will be modified until the State provides approval. Upon approval, the Change Impact Analysis shall be deemed an approved CR. The Contractor shall not begin work on any CR prior to receiving the State's approval.

# INDEPENDENT VALIDATION AND VERIFICATION

If the State decides to add Independent Verification & Validation (IV&V) services as part of this Contract, the Contractor will copy the Indiana Department of Administration (IDOA) -- IV&V Team member(s) on all project related communications (emails, meeting invites, collaboration tools, etc.) and will grant access to all documents and deliverables throughout the term of the Contract.  If IDOA elects to deploy IV&V services in connection with this engagement, the IV&V Team will review and assess all deliverables to determine compliance with the State's requirements set forth in the Contract including the Statement of Work. For contracts entered into, renewed, or amended after June 30, 2026, the IV&V Team shall serve as an approving authority, and no payment shall be issued to the Contractor unless and until IV&V has provided such approval.

# COMPLIANCE REQUIREMENTS

The Contractor shall:

- Abide by all applicable State and federal laws.

- Maintain compliance with all standard State policies and procedures.

- Maintain compliance with requirements related to the RHTP, including submission of data and reports as requested by the State and/or CMS.

- Abide by security requirements per Indiana’s RAMP policy

- Any materials the Contractor develops in partnership with the State for public distribution and/or to be published on State websites must comply with the State’s Assistive Technology standards and architectural standards, and Section 508 of the US Rehabilitation Act. The Contractor specifically agrees that all hardware, software and services provided to or purchased by the State shall be compatible with the principles and goals contained in the Assistive Technology Standard, within the State’s Information Security Framework (https://www.in.gov/iot/iot-vendor-engagement/), State Assistive Technology (https://www.in.gov/core/accessibility), and the State’s architectural standards. Any deviation from these requirements must be approved in writing by IOT in advance.