## Inactive Projects
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Latest Payment Date | Actual Letting Date | Target Letting Date | Earliest Auth Date | FMIS Balance | PO Unliquidated | Inactive Days | Last Action Date | Fund Sponsor | Open POs | PCO Des Status | PCO Open Task(s)
1801738 | R-41770 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Gary (1182) | Gary | Complete Streets Enhancements on Lake Street and minor on US 12/20 in Gary |  | 2021-05-05 | 2021-05-05 | 2018-09-04 | 1824016.01 | 2017681.84 | 1427 | 2021-06-01 15:13 | Local (MPO) | 0020056309 [PE]; 0020063648 [CE]; 0020064507 [CN] | Tracking | Blansett, Marcia [PE 94047, 94048, 94049]; Kruger, Jonathon [CE 94031] [CN 91424, 98405]
1400772 | R-38033 | Greenfield | Rush | Not Applicable | Rushville (1448) | Rushville | From Conrad-Harcourt Way north approximately 2,800 feet | 2021-10-15 12:11 |  | 2023-01-19 | 2014-10-30 | 389688.46 | 62507.25 | 290 | 2021-10-15 12:11 | Local (Non-MPO) | 0020070108 [ROW] | Tracking | Mcghghy, Donald [PE 108787, 108788] [RW 108786]
1600971 | R-40327 | Greenfield | Tipton | Not Applicable | Windfall (1561) | Windfall | SW and ADA Upgrades on SR 213 - Sherman Str and Grant St in Windfall | 2021-05-07 08:10 |  | 2025-07-09 | 2017-10-30 | 4682.37 | 4682.37 | 451 | 2021-05-07 08:10 | Local (Non-MPO) | 0018806979 [PE] | Tracking | Teague, Sacha [PE 104591, 109215, 109216]; Unassigned [PE 103836] [102389]
1801218 |  | Greenfield | Madison | Anderson |  | MPO - Anderson | Anderson MPO UPWP for FY 2019-2020 | 2021-07-30 09:10 |  |  | 2018-06-28 | 62388.43 | 0.01 | 367 | 2022-03-02 15:33 | Local (MPO) | 0020022816 [PL] | Tracking | Unassigned [PE 108579]
1900391 |  | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen (1190) | Goshen | Madison St. at NS RR DOT 510039L in Goshen |  |  |  | 2020-01-23 | 425390.4 | 471798.34 | 921 | 2022-04-21 14:09 | Local (MPO) | 0020084146 [RR] | Tracking | Unassigned [104087]
1902723 | R-39660 | Greenfield | Marion | Indianapolis | Beech Grove (1030) | Beech Grove | Beech Grove Greenway - Pedestrian Bridge No. 2 over Lick Creek at Station 28+40 | 2021-10-15 12:11 | 2020-09-02 | 2020-09-02 | 2020-07-28 | 0 | 2755 | 290 | 2022-05-11 07:01 | Local (MPO) | 0020050010 [CN] | Tracking | Douthitt, Aimee [CN 108888]; Wallace, Jonathan [PE 106090]
1005947 | R-33669 | Seymour | Johnson | Not Applicable |  | Johnson County | Between CR325E & CR440 E in Clark Twp, new 2 lane roadway construction | 2021-10-15 12:11 | 2019-12-11 | 2019-12-11 | 2011-04-18 | 1772223.8 | 2363840.64 | 290 | 2021-10-15 12:11 | Local (Non-MPO) | 0016807393 [PE,ROW]; 0020031218 [CE]; 0020034213 [UT]; 0020034334 [CN] | Tracking | Clark, Steve [CN 108819]; Schneider, Chase [CE 108822] [PE 108820] [RW 108821] [UT 108823]
1700735 | R-40293 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | From existing B-Line Trail terminus at Adams Street to 17th at Crescent |  |  | 2023-03-15 | 2021-05-05 | 717640 | 557180 | 453 | 2021-05-05 09:52 | Local (MPO) | 0020063657 [ROW] | Tracking | Unassigned [109343]; Walker, Matthew [PE 108297] [RW 106242]
1801359 |  | LaPorte | Various | Chicago - Northwestern Indiana (IL) |  | MPO - Northwest | NIRPC MPO Unified Work Program UPWP, PL, STBG and CMAQ for FY 2019-2020 | 2021-10-15 12:11 |  |  | 2018-06-28 | 636994.22 | 636992.65 | 290 | 2021-10-15 12:11 | Local (MPO) | 0020022992 [PL] | Tracking | Nsonwu, Emmanuel [108827]; Unassigned [PE 108574]
1801265 |  | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen (1190) | Goshen | Beaver Lane at NS RR DOT # 510019A in Goshen |  |  |  | 2019-05-07 | 703863 | 782070 | 1182 | 2022-04-21 14:09 | Local (MPO) | 0020084145 [RR] | Tracking | Unassigned [104086]
1400944 | B-37591 | Greenfield | Marion | Indianapolis |  | Indianapolis | Monon Bicycle/Pedestrian Bridge over 38th Str.28 miles E of 38th & College | 2020-10-23 07:31 | 2020-01-15 | 2020-01-15 | 2019-11-26 | 17424.62 | 29818.91 | 647 | 2022-07-19 14:00 | Local (MPO) | 0020036255 [CN] | Tracking | Douthitt, Aimee [CN 87933]
1401719 | B-38039 | Greenfield | Marion | Indianapolis |  | Indianapolis | 38th St Bridge (#2001F) over CSX RR; betw Arlington Ave. & Massachusetts Ave | 2021-05-21 07:11 | 2018-11-15 | 2018-11-15 | 2018-09-17 | 0 | 62154.85 | 437 | 2021-05-21 07:11 | Local (MPO) | 0020056808 [RR] | Tracking | Unassigned [100424]
1702868 | R-39110 | Greenfield | Delaware | Muncie | Yorktown (1572) | Yorktown | Bike / Ped facility along bridge 124, Nebo Rd over White River | 2021-09-17 07:29 | 2021-01-13 | 2021-01-13 | 2020-12-04 | 102470.24 | 73377 | 318 | 2021-09-17 07:29 | Local (MPO) | 0020059142 [CE] | Tracking | Darrah, Taylor [CE 107298]; Unassigned [107986]
0901275 | R-36161 | Seymour | Floyd | Louisville (KY)-IN |  | New Albany | Upgrade Market and Spring Streets as 2-way streets from IN 111 to State St | 2021-04-02 07:14 | 2017-03-01 | 2017-03-01 | 2015-04-20 | 66754.79 | 56097.26 | 486 | 2021-04-02 07:14 | Local (MPO) | 0017817671 [RR] | Tracking | Fischvogt, Brandi [RR 100056]; Unassigned [109301]
1401701 | R-38073 | Greenfield | Hamilton | Indianapolis |  | Hamilton County | 146th St, 1000' W Hamilton / Boone Co Line to 1000' W of Shelborne Rd | 2021-04-23 07:37 | 2020-02-05 | 2020-02-05 | 2020-01-15 | 0 | 68787.27 | 465 | 2021-04-23 07:37 | Local (MPO) | 0020036968 [CN] | Tracking | Douthitt, Aimee [CN 98501]
1600986 | R-39744 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Fall Creek Trail Enhancement at 38th and Fall Creek | 2021-10-15 12:11 | 2019-11-14 | 2019-11-14 | 2019-10-09 | 53695 | 67118.75 | 290 | 2021-10-15 12:11 | Local (MPO) | 0020034335 [CN] | Tracking | Douthitt, Aimee [CN 108796]; Mcghghy, Donald [PE 108797]
1593056 |  | LaPorte | St. Joseph | Not Applicable |  | St. Joseph County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2021-03-05 07:20 |  |  | 2020-07-23 | 198877.78 | 198877.78 | 514 | 2022-07-05 10:03 | Local (Non-MPO) | 0020045720 [PE] | Tracking | Langmaid, John [PE 96076, 96077]; Unassigned [102261]
1801422 | R-41316 | Greenfield | Marion | Indianapolis | Beech Grove (1030) | Beech Grove | Thompson Road Multi-Use Trail |  | 2021-10-14 | 2021-10-14 | 2021-08-26 | 431614 | 728359.06 | 340 | 2021-11-03 14:24 | Local (MPO) | 0020073792 [CN] | Tracking | Douthitt, Aimee [CN 105746]; Wallace, Jonathan [PE 106086, 106087]
1500685 | R-38544 | Seymour | Johnson | Indianapolis |  | Franklin | Roundabout at Jefferson St and Westview Dr | 2021-10-15 12:11 | 2019-11-14 | 2019-11-14 | 2015-12-01 | 96272.36 | 104380.14 | 290 | 2021-10-15 12:11 | Local (MPO) | 0020032857 [CN]; 0020062766 [CN] | Tracking | Clark, Steve [CN 108780]
1700976 | R-40337 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | Systematic safety improvements expected to include approximately 25 crosswalks. |  | 2022-04-06 | 2022-04-06 | 2021-02-22 | 541255 | 682293.42 | 525 | 2022-06-01 15:03 | Local (MPO) | 0020076879 [CE]; 0020085465 [CN] | Tracking | Clark, Steve [CN 105614]; Unassigned [CE 95561, 105677]
1802823 |  | Vincennes | Dubois | Not Applicable |  | Dubois County | CR 600W at NS AAR# 724930J in Dubois County |  |  |  | 2019-05-08 | 333893.7 | 370993 | 1181 | 2021-07-08 16:42 | Local (Non-MPO) | 0020035049 [RR] | Tracking | Hudson, Cassandra [42120]
1592891 |  | Fort Wayne | Kosciusko | Not Applicable |  | Kosciusko County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-10-22 06:56 |  |  | 2018-01-10 | 5413.28 | 5413.28 | 283 | 2021-10-22 06:56 | Local (Non-MPO) | 0018812316 [PE] | Tracking | Fox, Brenda [PE 88477]; Langmaid, John [PE 109182, 109183]
1173626 | R-35296 | Crawfordsville | Tippecanoe | Lafayette - West Lafayette |  | Tippecanoe County | Klondike Road (CR 300W) from Lindberg Rd.(CR 200N) to US 52 in Tippecanoe Co. | 2021-07-23 07:16 | 2018-03-14 | 2018-03-14 | 2013-07-21 | 70280.14 | 4043.35 | 374 | 2022-01-07 16:22 | Local (MPO) | 0020050542 [CN] | Tracking | Brockway, Sue [CN 103629]; Unassigned [103988]
1401730 | R-38048 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Intersection of Combs Road and Stop 11 Road | 2021-05-21 07:11 | 2019-09-11 | 2019-09-11 | 2019-07-24 | 15356.88 | 14618.77 | 437 | 2021-05-21 07:11 | Local (MPO) | 0020083492 [CE] | Tracking | Douthitt, Aimee [CN 100274]; Kindred, Shelli [CE 51829]; Unassigned [100276]; Wallace, Jonathan [CE 106197] [PE 106084]
1902724 | R-39660 | Greenfield | Marion | Indianapolis | Beech Grove (1030) | Beech Grove | Beech Grove Greenway - Pedestrian Bridge No. 3 over Lick Creek at Station 105+79 | 2021-10-15 12:11 | 2020-09-02 | 2020-09-02 | 2020-07-28 | 0 | 7105 | 290 | 2021-10-15 12:11 | Local (MPO) | 0020050010 [CN] | Tracking | Douthitt, Aimee [CN 108829]; Wallace, Jonathan [PE 106091]
1902011 | T-42423 | Seymour | Clark | Louisville (KY)-IN | Sellersburg (1461) | Indiana Department of Transportation | AT SR 60/ Bean Rd near Sellersburg - RR preemption signal w install upgraded saf | 2021-10-15 12:11 | 2020-05-07 | 2020-05-07 | 2020-04-06 | 6132.39 | 6000 | 290 | 2021-10-15 12:11 | Local (MPO) | 0020046601 [RR] | Tracking | Schneider, Chase [RR 108825]
1500212 | PLC-38182 | Seymour | Ohio | Not Applicable |  | Ohio County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2021-10-22 06:56 |  |  | 2018-12-19 | 22175.16 | 22175.16 | 283 | 2021-12-28 12:08 | Local (Non-MPO) | 0020033010 [PE] | Tracking | Langmaid, John [PE 106037, 109175]
1500200 | PLC-38170 | Seymour | Brown | Not Applicable |  | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-10-15 12:11 |  |  | 2017-10-16 | 23635.14 | 7256.23 | 290 | 2022-04-15 08:14 | Local (Non-MPO) | 0020024658 [PE] | Tracking | Fox, Brenda [PE 102483, 103953]; Langmaid, John [PE 108889]
1383364 | B-37355 | LaPorte | Porter | Not Applicable |  | Porter County | CR 625W 1.6 miles S of CR 1000 S over Kankakee River Bridge #62 | 2021-09-03 07:15 | 2020-11-10 | 2020-11-10 | 2014-11-24 | 60984.32 | 2920.98 | 332 | 2021-09-03 07:15 | Local (Non-MPO) | 0020054520 [CN] | Tracking | Krueckeberg, John [CE 78750] [RW 78748, 78749]; Kruger, Jonathon [CN 98375, 106283]; Unassigned [107885]
1600655 | R-40224 | Seymour | Johnson | Indianapolis | Franklin (1173) | Franklin | S Main St from S Main Bridge at Young's Creek to US 31 | 2020-12-11 07:29 | 2019-11-14 | 2019-11-14 | 2019-10-08 | 0 | 28855.27 | 598 | 2020-12-11 07:29 | Local (MPO) | 0020033019 [CN] | Tracking | Clark, Steve [CN 91177]
1802805 | R-41802 | Seymour | Clark | Louisville (KY)-IN |  | Clark County | CR 403 and Stacy Road Intersection Improvement | 2021-10-15 12:11 |  | 2024-01-18 | 2019-08-27 | 165568.89 | 165568.89 | 290 | 2022-04-19 07:51 | Local (MPO) | 0020026805 [PE]; 0020084169 [ROW] | Tracking | Fischvogt, Brandi [PE 93893]; Fortson, William [PE 107167, 108805, 108806, 108807, 108808, 108809] [RW 108810]
1802886 | R-41919 | Seymour | Jefferson | Not Applicable | Madison (1295) | Madison | Wilson Avenue, between Industrial Drive/Scott Court and Hutchinson Lane (aka JA |  |  | 2023-07-12 | 2021-08-13 | 352240 | 352240 | 353 | 2021-08-13 12:13 | Local (Non-MPO) | 0020068690 [ROW] | Tracking | Fortson, William [PE 107601, 107602] [RR 107574] [RW 105082]; Unassigned [107905]
1902767 | B-42802 | Seymour | Johnson | Not Applicable |  | Johnson County | Bridge 98 on CR 700E over Fisher Ditch - 0.01 mi N or Urmeyville Road |  |  | 2024-10-09 | 2021-05-04 | 172600 | 78039.44 | 454 | 2021-05-04 12:45 | Local (Non-MPO) | 0020063887 [PE] | Tracking | Unassigned [PE 108647] [102346]
1902078 |  | Seymour | Brown | Not Applicable |  | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2021-2024 |  |  |  | 2021-08-04 | 66162.4 | 66162.4 | 362 | 2021-08-04 08:30 | Local (Non-MPO) | 0020067881 [PE] | Tracking | Langmaid, John [PE 104585, 104586]; Unassigned [107951]
1401813 | R-38151 | LaPorte | Porter | Chicago - Northwestern Indiana (IL) |  | Valparaiso | US 30 Intersection Improvement, Signals & Lighting at Washington | 2019-10-11 07:20 | 2019-03-06 | 2019-03-06 | 2019-01-22 | 0 | 14237.43 | 1025 | 2022-07-29 08:30 | Local (MPO) | 0020020976 [CE] | Tracking | Krueckeberg, John [CE 78753]; Kruger, Jonathon [CN 98206]
1600715 | B-39858 | Crawfordsville | Morgan | Not Applicable |  | Morgan County | Bridge # 75 Bowman Road over Rhodes Creek | 2021-10-15 12:11 | 2021-12-08 | 2021-12-08 | 2018-06-12 | 791577.46 | 946693.18 | 290 | 2022-01-06 17:57 | Local (Non-MPO) | 0020075714 [CE]; 0020077046 [CN] | Tracking | Brockway, Sue [CN 108800]; Kemp, Susan [PE 71696] [RW 71708]; Mcdaniel, Kaitlyn [CE 108802] [PE 108801]
1600974 | R-40321 | Greenfield | Jay | Not Applicable | Dunkirk (1133) | Dunkirk | Highland Ave - W Jay Middle School to Speedcat Alley | 2021-07-30 09:10 |  | 2023-02-15 | 2017-11-16 | 3345.62 | 3345.62 | 367 | 2021-07-30 09:10 | Local (Non-MPO) | 0018808249 [PE] | Tracking | Darrah, Taylor [PE 104201, 104202, 104203, 104589, 105259]; Unassigned [107896]
1702152 | R-37496 | LaPorte | St. Joseph | South Bend (MI) |  | St. Joseph County | Douglas Road over Juday Creek Bridge #191 |  | 2020-12-09 | 2020-12-09 | 2020-11-09 | 846463.24 | 1058079.05 | 630 | 2021-02-04 09:35 | Local (MPO) | 0020056246 [CN] | Tracking | Reed, Paul [CN 90502]
1702153 | R-37496 | LaPorte | St. Joseph | South Bend (MI) |  | St. Joseph County | Ironwood Road over Juday Creek Bridge #192 |  | 2020-12-09 | 2020-12-09 | 2020-11-09 | 842706.93 | 1053383.66 | 630 | 2021-02-04 09:35 | Local (MPO) | 0020056246 [CN] | Tracking | Kruger, Jonathon [CN 98348]; Reed, Paul [CN 94639]
1500286 |  | Greenfield | Madison | Not Applicable |  | Madison County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-04-02 07:14 |  |  | 2018-07-30 | 4484.6 | 4484.6 | 486 | 2021-07-27 11:07 | Local (Non-MPO) | 0020046599 [PE] | Tracking | Fox, Brenda [PE 72651, 98951]; Langmaid, John [PE 97289, 97290]; Unassigned [102301]
1400619 |  | Seymour | Harrison | Not Applicable |  | Indiana Department of Transportation | Angel Run Road at NS DOT# 724987K near Crandall | 2020-07-24 07:29 |  |  | 2016-04-25 | 485595.97 | 479105.24 | 738 | 2022-05-04 13:37 | Local (Non-MPO) | 0020084743 [RR] | Tracking | Hudson, Cassandra [RR 27009]; Unassigned [RR 106481] [104778]

## PED's next 9 Months
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Project End Date | Federal | Expenditure | FMIS Balance | PO Unliquidated | Open POs | Fund Sponsor | PCO Des Status Code | PED Expiration Days | PCO Des Status | PCO Open Task(s)
1500229 | PLC-38260 | Crawfordsville | Clay | Not Applicable |  | Clay County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 316612.16 | 311998.24 | 4613.92 | 4613.92 | 0020002552 [PE] | Local (Non-MPO) | TR | 60 | Tracking | Fox, Brenda [PE 98950]
1500231 | PLC-38261 | Crawfordsville | Clinton | Not Applicable |  | Clinton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 248006.4 | 224352.56 | 23653.84 | 23653.84 | 0020051600 [PE] | Local (Non-MPO) | TR | -62 | Tracking | Fox, Brenda [PE 91943]
1500252 | PLC-38268 | Crawfordsville | Tippecanoe | Not Applicable |  | Tippecanoe County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-12-31 | 775305.68 | 723830.17 | 51475.51 | 51475.51 | 0020004688 [PE] | Local (Non-MPO) | TR | 152 | Tracking | Fox, Brenda [PE 104292]; Langmaid, John [PE 97010]
1592864 |  | Fort Wayne | Adams | Not Applicable |  | Adams County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 269329.6 | 253988.2 | 15341.4 | 15341.4 | 0018815678 [PE] | Local (Non-MPO) | TR | 30 | Tracking | Fox, Brenda [PE 97221]
1173219 | B-35619 | Fort Wayne | Allen | Fort Wayne | Fort Wayne (1165) | Indiana State Agencies | IPFW Pedestrian Bridge over Coliseum Blvd | 2023-02-28 | 4121833.79 | 4072903.01 | 48930.78 | 50366.59 | 0020058242 [CN] | Local (MPO) | TR | 211 | Tracking | Smith, Charles [CN 70008]
1592887 |  | Fort Wayne | Elkhart | Not Applicable |  | Elkhart County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 405110.82 | 404466.34 | 644.48 | 644.48 | 0020001180 [PE] | Local (Non-MPO) | TR | 30 | Tracking | Fox, Brenda [PE 98647]
1592891 |  | Fort Wayne | Kosciusko | Not Applicable |  | Kosciusko County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-03-31 | 220399.65 | 214986.37 | 5413.28 | 5413.28 | 0018812316 [PE] | Local (Non-MPO) | TR | -123 | Tracking | Fox, Brenda [PE 88477]; Langmaid, John [PE 109182, 109183]
1500279 |  | Greenfield | Delaware | Not Applicable |  | Delaware County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 432891.42 | 409120.78 | 23770.64 | 21477.91 | 0020004711 [PE] | Local (Non-MPO) | TR | 183 | Tracking | Fox, Brenda [PE 105885]
1801325 |  | Greenfield | Delaware | Muncie |  | MPO - Muncie | Delaware-Muncie MPO Unified Work Program UPWP, PL & STBG for FY 2019-2020 | 2022-06-30 | 561774 | 531129.06 | 30644.94 | 30644.94 | 0020023023 [PL] | Local (MPO) | TR | -32 | Tracking | Unassigned [PE 108576]
1500281 |  | Greenfield | Hamilton | Not Applicable |  | Hamilton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-03-01 | 473885.78 | 470738.94 | 3146.84 | 3146.84 | 0018800503 [PE] | Local (Non-MPO) | TR | -153 | Tracking | Fox, Brenda [PE 100453]
1500282 |  | Greenfield | Hancock | Not Applicable |  | Hancock County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 232639 | 217388.25 | 15250.75 | 15250.75 | 0018816854 [PE] | Local (Non-MPO) | TR | -32 | Tracking | Fox, Brenda [PE 93891]; Langmaid, John [PE 106025]
1500284 |  | Greenfield | Howard | Not Applicable |  | Howard County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-02-28 | 320104.99 | 319807.17 | 297.82 | 297.82 | 0020004712 [PE] | Local (Non-MPO) | TR | 211 | Tracking | Fox, Brenda [PE 107831]
1801321 |  | Greenfield | Howard | Kokomo |  | MPO - Kokomo | Kokomo MPO Statement of Work(SOW), PL & STBG for 2019-2020 | 2022-07-30 | 437199 | 417728.44 | 19470.56 | 19470.56 | 0020023021 [PL] | Local (MPO) | TR | -2 | Tracking | Unassigned [PE 108577]
1801218 |  | Greenfield | Madison | Anderson |  | MPO - Anderson | Anderson MPO UPWP for FY 2019-2020 | 2022-06-30 | 1289730 | 1227341.57 | 62388.43 | 0.01 | 0020022816 [PL] | Local (MPO) | TR | -32 | Tracking | Unassigned [PE 108579]
1500286 |  | Greenfield | Madison | Not Applicable |  | Madison County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 471974.47 | 467489.87 | 4484.6 | 4484.6 | 0020046599 [PE] | Local (Non-MPO) | TR | 60 | Tracking | Fox, Brenda [PE 72651, 98951]; Langmaid, John [PE 97289, 97290]; Unassigned [102301]
1500287 |  | Greenfield | Marion | Indianapolis |  | Marion County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 1672548.9 | 1609083.82 | 88783.36 | 88783.36 | 0018818297 [PE] | Local (MPO) | TR | -1 | Tracking | Fox, Brenda [PE 95341]; Langmaid, John [PE 106027]
1592159 |  | LaPorte | Jasper | Not Applicable |  | Jasper County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-11-30 | 213407.2 | 177422.55 | 35984.65 | 35984.65 | 0020002482 [PE] | Local (Non-MPO) | TR | 121 | Tracking | Fox, Brenda [PE 102484]
1600448 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Tryon Road at CSX DOT #232070F and Royal Rd DOT# 232071M in Michigan City | 2023-01-01 | 1289231 | 1245112.81 | 44118.19 | 43306.25 | 0020012795 [RR] | Local (MPO) | TR | 153 | Tracking | Hudson, Cassandra [RR 104303]
1600449 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Tilden Street at CSX RR DOT #232080L in Michigan City | 2023-01-01 | 403432 | 369749.06 | 33682.94 | 33682.94 | 0020013249 [RR] | Local (MPO) | TR | 153 | Tracking | Hudson, Cassandra [RR 104285]
1600454 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Carroll Ave at CSX DOT #232077D in Michigan City | 2023-01-01 | 443752 | 404149.87 | 39602.13 | 39602.13 | 0020013248 [RR] | Local (MPO) | TR | 153 | Tracking | Hudson, Cassandra [RR 104242]
1600452 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Greenwood Ave at CSX DOT #232075P in Michigan City | 2023-01-01 | 451828 | 325521.69 | 126306.31 | 126306.31 | 0020013247 [RR] | Local (MPO) | TR | 153 | Tracking | Hudson, Cassandra [RR 104276]
1600451 |  | LaPorte | LaPorte | Michigan City |  | Indiana Department of Transportation | Roeske Ave at CSX DOT #232074H in Michigan City | 2023-01-01 | 496418 | 405510.88 | 90907.12 | 90907.12 | 0020013246 [RR] | Local (MPO) | TR | 153 | Tracking | Hudson, Cassandra [RR 104305]
1601151 |  | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Crown Point (1112) | Crown Point | Purchase E-85 Fuel | 2022-12-30 | 136100.92 | 77133.61 | 58967.31 | 18866.39 | 0020062124 [PE] | Local (MPO) | TR | 151 | Tracking | Blansett, Marcia [PE 93880]
0900064 | R-33678 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | East Chicago (1139) | East Chicago | Indianapolis Blvd Complete St Project: from 152nd St to Columbus Dr. (US 12) | 2022-10-31 | 635979.55 | 559144.35 | 76835.2 | 76835.2 | 0018818554 [PE] | Local (MPO) | TR | 91 | Tracking | Blansett, Marcia [PE 90300, 100449]; Borden, Andrew [PE 100335, 100336]
0810541 | R-35690 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Hobart (1220) | Hobart | Downtown Hobart along Third Street from Main Street to Center Street | 2023-02-08 | 4548999.27 | 4436831.04 | 112168.23 | 124357.83 | 0017819613 [CE]; 0020066600 [CN] | Local (MPO) | TR | 191 | Tracking | Blansett, Marcia [CE 106448]; Kruger, Jonathon [CN 106447]
9981680 |  | LaPorte | Lake | Chicago - Northwestern Indiana (IL) |  | Lake County | Veterans Memorial Trail (Lake County Conrail Rails to Trails) | 2023-01-28 | 1899392 | 701300.51 | 1711994.5 | 823091.49 | 0016817335 [ROW] | Local (MPO) | TR | 180 | Tracking | Blansett, Marcia [RW 105858]
1592160 |  | LaPorte | Lake | Not Applicable |  | Lake County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 697199.13 | 672318 | 24881.13 | 24881.13 | 0020002481 [PE] | Local (Non-MPO) | TR | 30 | Tracking | Fox, Brenda [PE 97224]
1592161 |  | LaPorte | Marshall | Not Applicable |  | Marshall County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 247765.26 | 237695.66 | 10069.6 | 10069.6 | 0020047168 [PE] | Local (Non-MPO) | TR | 183 | Tracking | Fox, Brenda [PE 105886]
1601122 |  | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | Chesterton (1083) | Indiana Department of Transportation | 15th Street at CSX Railroad DOT # 232115K in Chesterton | 2023-01-01 | 363000 | 342577.45 | 20422.55 | 18062.1 | 0020011555 [RR] | Local (MPO) | TR | 153 | Tracking | Hudson, Cassandra [RR 104258]
1592163 |  | LaPorte | Porter | Not Applicable |  | Porter County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 299629.54 | 283168.3 | 16461.24 | 16461.24 | 0018816842 [PE] | Local (Non-MPO) | TR | -62 | Tracking | Fox, Brenda [PE 91946]
1592164 |  | LaPorte | Pulaski | Not Applicable |  | Pulaski County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 171488.2 | 117682.88 | 53805.32 | 53805.32 | 0020002545 [PE] | Local (Non-MPO) | TR | 60 | Tracking | Fox, Brenda [PE 98949]; Langmaid, John [PE 98933, 98934]
1592155 |  | LaPorte | Starke | Not Applicable |  | Starke County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-12-31 | 147281.44 | 142691.69 | 4589.75 | 4588.85 | 0020004708 [PE] | Local (Non-MPO) | TR | 152 | Tracking | Fox, Brenda [PE 104263]; Langmaid, John [PE 98040]
1801359 |  | LaPorte | Various | Chicago - Northwestern Indiana (IL) |  | MPO - Northwest | NIRPC MPO Unified Work Program UPWP, PL, STBG and CMAQ for FY 2019-2020 | 2022-06-30 | 3246451 | 2609456.78 | 636994.22 | 636992.65 | 0020022992 [PL] | Local (MPO) | TR | -32 | Tracking | Nsonwu, Emmanuel [108827]; Unassigned [PE 108574]
1592166 |  | LaPorte | White | Not Applicable |  | White County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 402666.4 | 384444.8 | 18221.6 | 2649.6 | 0020005643 [PE] | Local (Non-MPO) | TR | 183 | Tracking | Fox, Brenda [PE 105887]
1500200 | PLC-38170 | Seymour | Brown | Not Applicable |  | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-09-30 | 179413.02 | 155777.88 | 23635.14 | 7256.23 | 0020024658 [PE] | Local (Non-MPO) | TR | -305 | Tracking | Fox, Brenda [PE 102483, 103953]; Langmaid, John [PE 108889]
1500205 | PLC-38175 | Seymour | Franklin | Not Applicable |  | Franklin County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 225825.43 | 214772.2 | 11053.23 | 11053.23 | 0020004705 [PE] | Local (Non-MPO) | TR | 183 | Tracking | Fox, Brenda [PE 105888]; Langmaid, John [PE 103930]
1703018 | B-40891 | Seymour | Jackson | Not Applicable |  | Jackson County | Bridge #197-CR 100S over McHargue Ditch, .01 mile East of CR 500W | 2022-06-30 | 200501.6 | 56699.01 | 143802.59 | 143802.59 | 0020023689 [PE] | Local (Non-MPO) | TR | -32 | Tracking | Fischvogt, Brandi [PE 93868, 102414]; Walker, Matthew [PE 107166]
1500208 | PLC-38178 | Seymour | Jefferson | Not Applicable |  | Jefferson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-02-28 | 165719.9 | 157625.5 | 8094.4 | 8094.4 | 0020007472 [PE] | Local (Non-MPO) | TR | 211 | Tracking | Fox, Brenda [PE 107839]; Langmaid, John [PE 102633, 102634, 103931]; Unassigned [104022]
1500209 | PLC-38179 | Seymour | Johnson | Not Applicable |  | Johnson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 285488 | 247269.75 | 38218.25 | 38218.25 | 0018817373 [PE] | Local (Non-MPO) | TR | -1 | Tracking | Fox, Brenda [PE 95336]; Langmaid, John [PE 103932]
1802868 | R-41990 | Seymour | Morgan | Not Applicable | Martinsville (1301) | Martinsville | Along Pike St. beginning at Lincoln St. then 7 blocks to the east to the interse | 2022-12-30 | 123840 | 88081.4 | 35758.6 | 31026.62 | 0020036867 [PE] | Local (Non-MPO) | TR | 151 | Tracking | Fischvogt, Brandi [PE 104230]
1802869 | R-41990 | Seymour | Morgan | Not Applicable | Martinsville (1301) | Martinsville | Along Harrison St. beginning at Lincoln St then 6 blocks to the east to the inte | 2022-12-30 | 104480 | 78118.51 | 26361.49 | 25257.15 | 0020035745 [PE] | Local (Non-MPO) | TR | 151 | Tracking | Fischvogt, Brandi [PE 104235]
1500213 | PLC-38183 | Seymour | Ripley | Not Applicable |  | Ripley County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 214627 | 212092.59 | 2534.41 | 2534.41 | 0020047991 [PE] | Local (Non-MPO) | TR | 183 | Tracking | Fox, Brenda [PE 105889]
1592990 |  | Vincennes | Gibson | Not Applicable |  | Gibson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-03-31 | 417524.66 | 415734.01 | 1790.65 | 1790.65 | 0018814317 [PE] | Local (Non-MPO) | TR | 242 | Tracking
1592992 |  | Vincennes | Lawrence | Not Applicable |  | Lawrence County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 261080.8 | 253398.04 | 7682.76 | 7682.76 | 0018816862 [PE] | Local (Non-MPO) | TR | -32 | Tracking | Fox, Brenda [PE 93892]
1592994 |  | Vincennes | Orange | Not Applicable |  | Orange County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 346677.6 | 338613.82 | 8063.78 | 8063.78 | 0018816852 [PE] | Local (Non-MPO) | TR | -62 | Tracking | Fox, Brenda [PE 91947]
1592999 |  | Vincennes | Perry | Not Applicable |  | Perry County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-04-30 | 243406.8 | 235660.01 | 17919.99 | 16206.39 | 0020009818 [PE] | Local (Non-MPO) | TR | 272 | Tracking
1802900 | R-42008 | Vincennes | Pike | Not Applicable |  | Pike County | CR 300N from SR 56/61 to Indiana Southern Railroad | 2022-12-12 | 481440 | 203980.1 | 277459.9 | 277459.9 | 0020028791 [PE] | Local (Non-MPO) | TR | 133 | Tracking | Mischler, Brandi [PE 63378, 103019]
1802899 | R-42008 | Vincennes | Pike | Not Applicable |  | Pike County | Pike County Bridge 30 over Prides Creek along CR 300 N | 2022-12-12 | 60640 | 29904.8 | 30735.2 | 30735.2 | 0020028797 [PE] | Local (Non-MPO) | TR | 133 | Tracking | Mischler, Brandi [PE 70429, 103018]
1593001 |  | Vincennes | Posey | Not Applicable |  | Posey County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-04-30 | 381166.29 | 376019.88 | 5146.41 | 5146.41 | 0018816861 [PE] | Local (Non-MPO) | TR | -93 | Tracking | Fox, Brenda [PE 90227]
1593021 |  | Vincennes | Vanderburgh | Not Applicable |  | Vanderburgh County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 339320.64 | 330983.24 | 8337.4 | 8337.4 | 0020004699 [PE] | Local (Non-MPO) | TR | 183 | Tracking | Fox, Brenda [PE 105884]