## Inactive Projects
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Latest Payment Date | Actual Letting Date | Target Letting Date | Earliest Auth Date | FMIS Balance | PO Unliquidated | Inactive Days | Last Action Date | Fund Sponsor | Open POs | PCO Des Status
1401314 | R-37922 | Crawfordsville | Vigo | Terre Haute |  | Vigo County | Springhill Dr from 7th St to Erie Canal Rd | 2021-12-10 07:55 | 2022-02-09 | 2022-02-09 | 2017-04-28 | 3742700.71 | 4678375.89 | 389 | 2022-12-20 14:25 | Local (MPO) | 0020081276 [CN] | Tracking
1700438 | B-40166 | Crawfordsville | Vigo | Terre Haute |  | Vigo County | Bridge #322 on N 13th st 0.25 miles S of Ft Harrison Road | 2021-12-03 07:51 | 2021-10-14 | 2021-10-14 | 2017-05-04 | 0 | 391572.47 | 396 | 2021-12-03 07:51 | Local (MPO) | 0020074267 [CN]; 0020084457 [CE] | Tracking
1173219 | B-35619 | Fort Wayne | Allen | Fort Wayne | Fort Wayne (1165) | Indiana State Agencies | IPFW Pedestrian Bridge over Coliseum Blvd | 2022-01-07 07:07 | 2017-02-08 | 2017-02-08 | 2013-07-18 | 48930.78 | 50366.59 | 361 | 2022-12-28 14:02 | Local (MPO) | 0020058242 [CN] | Tracking
1592864 |  | Fort Wayne | Adams | Not Applicable |  | Adams County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-02-04 07:05 |  |  | 2018-03-08 | 15341.4 | 15341.4 | 333 | 2022-02-04 07:05 | Local (Non-MPO) | 0018815678 [PE] | Tracking
2001665 | R-43120 | Fort Wayne | Allen | Not Applicable | Woodburn (1568) | Woodburn | Woodburn Var. Locations: Center St, Maple Ln, SR 101, Becker, Carl, Park. |  | 2022-09-14 | 2022-09-14 | 2022-03-23 | 550862.4 | 633359.41 | 286 | 2022-12-28 14:09 | Local (Non-MPO) | 0020090631 [CE]; 0020093646 [CN] | Tracking
1401701 | R-38073 | Greenfield | Hamilton | Indianapolis |  | Hamilton County | 146th St, 1000' W Hamilton / Boone Co Line to 1000' W of Shelborne Rd | 2021-04-23 07:37 | 2020-02-05 | 2020-02-05 | 2020-01-15 | 0 | 275994.61 | 620 | 2022-10-15 10:30 | Local (MPO) | 0020036968 [CN] | Tracking
1401702 | R-38240 | Greenfield | Hamilton | Indianapolis |  | Hamilton County | 146th St. Phase III Towne Road to Shelborne Road | 2022-03-11 06:54 | 2019-01-16 | 2019-01-16 | 2018-12-06 | 147897.76 | 494863.15 | 298 | 2022-03-11 06:54 | Local (MPO) | 0020014154 [CN]; 0020047043 [CN] | Tracking
1592998 | R-39110 | Greenfield | Delaware | Muncie | Yorktown (1572) | Yorktown | Nebo Road from SR 32 to River road | 2021-11-05 06:50 | 2021-01-13 | 2021-01-13 | 2017-04-28 | 133034.68 | 66528 | 424 | 2021-11-05 06:50 | Local (MPO) | 0020059142 [CE] | Tracking
1600961 | R-38033 | Greenfield | Rush | Not Applicable | Rushville (1448) | Rushville | Cherry St - Conrad Harcourt Way N to CR 200 N | 2021-11-26 07:38 |  | 2024-07-10 | 2017-08-28 | 14546.55 | 14546.55 | 403 | 2021-11-26 07:38 | Local (Non-MPO) | 0018803680 [PE] | Tracking
1600971 | R-40327 | Greenfield | Tipton | Not Applicable | Windfall (1561) | Windfall | SW and ADA Upgrades on SR 213 - Sherman Str and Grant St in Windfall | 2021-05-07 08:10 |  | 2025-07-09 | 2017-10-30 | 4682.37 | 4682.37 | 606 | 2021-05-07 08:10 | Local (Non-MPO) | 0018806979 [PE] | Tracking
1600974 | R-40321 | Greenfield | Jay | Not Applicable | Dunkirk (1133) | Dunkirk | Highland Ave - W Jay Middle School to Speedcat Alley | 2021-07-30 09:10 |  | 2023-02-10 | 2017-11-16 | 3345.62 | 3345.62 | 522 | 2021-07-30 09:10 | Local (Non-MPO) | 0018808249 [PE] | Tracking
1600986 | R-39744 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Fall Creek Trail Enhancement at 38th and Fall Creek | 2021-10-15 12:11 | 2019-11-14 | 2019-11-14 | 2019-10-09 | 53695 | 67118.75 | 445 | 2021-10-15 12:11 | Local (MPO) | 0020034335 [CN] | Tracking
1602231 | R-41876 | Greenfield | Hamilton | Indianapolis | Fishers (1162) | Fishers | Small Structure on SR 37, 0.19 miles north of 131st Street | 2022-03-04 07:16 | 2020-12-09 | 2020-12-09 | 2020-11-05 | 811.65 | 811.65 | 305 | 2022-03-04 07:16 | Local (MPO) | 0020056169 [CN] | Tracking
1700933 | B-40370 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Washington Street over Big Eagle Creek | 2021-12-03 07:51 | 2020-10-07 | 2020-10-07 | 2020-09-02 | 0 | 72896.74 | 396 | 2021-12-03 07:51 | Local (MPO) | 0020054246 [CN] | Tracking
1702765 | R-41054 | Greenfield | Hamilton | Indianapolis | Westfield (1547) | Westfield | 151st Street and Towne Road Roundabout | 2022-01-07 07:07 |  | 2024-07-10 | 2019-02-22 | 26593.15 | 26593.15 | 361 | 2022-01-07 07:07 | Local (MPO) | 0020014475 [PE] | Tracking
1702868 | R-39110 | Greenfield | Delaware | Muncie | Yorktown (1572) | Yorktown | Bike / Ped facility along bridge 124, Nebo Rd over White River | 2021-09-17 07:29 | 2021-01-13 | 2021-01-13 | 2020-12-04 | 102470.24 | 73377 | 473 | 2021-09-17 07:29 | Local (MPO) | 0020059142 [CE] | Tracking
1801321 |  | Greenfield | Howard | Kokomo |  | MPO - Kokomo | Kokomo MPO Statement of Work(SOW), PL & STBG for 2019-2020 | 2022-02-18 07:33 |  |  | 2018-06-28 | 19470.56 | 19470.56 | 319 | 2022-02-18 07:33 | Local (MPO) | 0020023021 [PL] | Tracking
1801325 |  | Greenfield | Delaware | Muncie |  | MPO - Muncie | Delaware-Muncie MPO Unified Work Program UPWP, PL & STBG for FY 2019-2020 | 2021-12-10 07:55 |  |  | 2018-06-26 | 30644.94 | 30644.94 | 389 | 2021-12-10 07:55 | Local (MPO) | 0020023023 [PL] | Tracking
1902724 | R-39660 | Greenfield | Marion | Indianapolis | Beech Grove (1030) | Beech Grove | Beech Grove Greenway - Pedestrian Bridge No. 3 over Lick Creek at Station 105+79 | 2021-10-15 12:11 | 2020-09-02 | 2020-09-02 | 2020-07-28 | 0 | 7105 | 445 | 2021-10-15 12:11 | Local (MPO) | 0020050010 [CN] | Tracking
2003046 | R-44163 | Greenfield | Delaware | Muncie | Muncie (1351) | Muncie | McGalliard Road from Tillotson to Wheeling |  |  | 2025-07-09 | 2022-03-02 | 174297.71 | 174297.71 | 307 | 2022-03-02 16:08 | Local (MPO) | 0020081640 [PE] | Tracking
0710056 | B-36229 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Munster (1352) | Munster | Reconstruction of 45th St. from 0.2 miles E of Calumet Avenue | 2022-03-28 07:06 | 2019-02-20 | 2019-02-20 | 2009-04-15 | 884395.91 | 408.29 | 281 | 2022-03-28 07:06 | Local (MPO) | 0020017595 [CN] | Tracking
1172007 | R-34640 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) |  | Lake County | 45th Ave. from Whitcomb to Chase (Ph 2B) | 2022-03-11 06:54 | 2020-04-01 | 2020-04-01 | 2014-07-24 | 288234.32 | 98941.73 | 298 | 2022-03-11 06:54 | Local (MPO) | 0020040291 [CE]; 0020042265 [CN] | Tracking
1383364 | B-37355 | LaPorte | Porter | Not Applicable |  | Porter County | CR 625W 1.6 miles S of CR 1000 S over Kankakee River Bridge #62 | 2021-09-03 07:15 | 2020-11-10 | 2020-11-10 | 2014-11-24 | 60984.32 | 2920.98 | 487 | 2021-09-03 07:15 | Local (Non-MPO) | 0020054520 [CN] | Tracking
1401811 | R-38065 | LaPorte | St. Joseph | South Bend (MI) | South Bend (1475) | South Bend | Coal Line Trail Phase 2 from Riverside Dr to Angela Blvd | 2022-02-18 07:33 | 2022-09-14 | 2022-09-14 | 2016-05-04 | 1960242.23 | 1834340.65 | 319 | 2022-11-17 08:36 | Local (MPO) | 0020091443 [CE]; 0020095205 [CN] | Tracking
1592338 |  | LaPorte | LaPorte | Michigan City |  | LaPorte County | Corridor Study, Kingsbury Industrial park to North side of City of LaPorte | 2022-03-28 07:06 |  |  | 2016-04-29 | 349052.3 | 349052.3 | 281 | 2022-03-28 07:06 | Local (MPO) | 0016818616 [PE] | Tracking
9980080 | R-31949 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) |  | Lake County | 45th Ave from Colfax to Whitcomb (earmark) (PH3) | 2021-11-19 07:19 | 2022-03-09 | 2022-03-09 | 2009-09-22 | 8636869.4 | 10345221.36 | 410 | 2022-04-27 08:24 | Local (MPO) | 0020082138 [CE]; 0020084032 [CN] | Tracking
1500212 | PLC-38182 | Seymour | Ohio | Not Applicable |  | Ohio County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2021-10-22 06:56 |  |  | 2018-12-19 | 22175.16 | 22175.16 | 438 | 2021-12-28 12:08 | Local (Non-MPO) | 0020033010 [PE] | Tracking
1500219 | PLC-38187 | Seymour | Jennings | Not Applicable |  | Jennings County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2022-01-21 06:51 |  |  | 2019-03-12 | 10439.22 | 10439.22 | 347 | 2022-03-28 14:01 | Local (Non-MPO) | 0020016644 [PE] | Tracking
1500685 | R-38544 | Seymour | Johnson | Indianapolis |  | Franklin | Roundabout at Jefferson St and Westview Dr | 2021-10-15 12:11 | 2019-11-14 | 2019-11-14 | 2015-12-01 | 96272.36 | 104380.14 | 445 | 2021-10-15 12:11 | Local (MPO) | 0020032857 [CN]; 0020062766 [CN] | Tracking
1600655 | R-40224 | Seymour | Johnson | Indianapolis | Franklin (1173) | Franklin | S Main St from S Main Bridge at Young's Creek to US 31 | 2020-12-11 07:29 | 2019-11-14 | 2019-11-14 | 2019-10-08 | 0 | 28855.27 | 753 | 2020-12-11 07:29 | Local (MPO) | 0020033019 [CN] | Tracking
1701323 | R-40375 | Seymour | Bartholomew | Columbus | Columbus (1101) | Columbus | Talley Road between 25th Street and Rocky Ford Road | 2022-03-28 07:06 |  | 2024-07-10 | 2018-05-07 | 233035.61 | 233035.61 | 281 | 2022-03-28 07:06 | Local (MPO) | 0018818530 [PE] | Tracking
1702788 | R-40812 | Seymour | Clark | Not Applicable |  | Clark County | Bethany Road Phase 2- 1.63 miles northwest of the SR 62 junction in Clark County | 2022-02-18 07:33 | 2020-02-05 | 2020-02-05 | 2020-01-15 | 15471.5 | 16086.77 | 319 | 2022-09-01 08:15 | Local (Non-MPO) | 0020034218 [CE]; 0020041030 [CN] | Tracking
1702967 | B-40887 | Seymour | Morgan | Not Applicable |  | Morgan County | Bridge #52 on Egbert Road over Stotts Creek | 2021-12-03 07:51 |  | 2023-01-19 | 2019-08-16 | 1643103.44 | 163631.68 | 396 | 2022-12-28 10:38 | Local (Non-MPO) | 0020025681 [PE]; 0020084907 [ROW] | Tracking
1800008 | R-40375 | Seymour | Bartholomew | Columbus |  | Bartholomew County | Bridge #103 on Talley Road between 25th Street and Rocky Ford Road | 2022-03-28 07:06 |  | 2024-07-10 | 2018-05-07 | 84620.19 | 84620.19 | 281 | 2022-03-28 07:06 | Local (MPO) | 0018818528 [PE] | Tracking
1801452 | R-41322 | Seymour | Johnson | Indianapolis |  | Johnson County | Intersection of Saddle Club Road (400W) and Stones Crossing Road (700N) |  | 2022-05-05 | 2022-05-05 | 2022-02-01 | 1169305 | 2142000 | 336 | 2022-06-01 15:13 | Local (MPO) | 0020079815 [CE]; 0020085734 [CN]; 0020085735 [CN] | Tracking
1802805 | R-41802 | Seymour | Clark | Louisville (KY)-IN |  | Clark County | CR 403 and Stacy Road Intersection Improvement | 2021-10-15 12:11 |  | 2024-01-18 | 2019-08-27 | 165568.89 | 165568.89 | 445 | 2022-04-19 07:51 | Local (MPO) | 0020026805 [PE]; 0020084169 [ROW] | Tracking
1802881 | B-41920 | Seymour | Morgan | Not Applicable |  | Morgan County | Robb Hill RD over Sycamore Creek | 2022-01-03 07:13 |  | 2023-07-12 | 2020-07-07 | 146363.31 | 146363.31 | 365 | 2022-01-03 07:13 | Local (Non-MPO) | 0020045453 [PE] | Tracking
1900402 | R-41895 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | 17th Street from Monroe Street to Grant Street |  | 2022-05-05 | 2022-05-05 | 2022-03-24 | 2307822 | 3293676.95 | 285 | 2022-09-01 17:55 | Local (MPO) | 0020083079 [CE]; 0020085727 [CN] | Tracking
1902011 | T-42423 | Seymour | Clark | Louisville (KY)-IN | Sellersburg (1461) | Indiana Department of Transportation | AT SR 60/ Bean Rd near Sellersburg - RR preemption signal w install upgraded saf | 2021-10-15 12:11 | 2020-05-07 | 2020-05-07 | 2020-04-06 | 6132.39 | 6000 | 445 | 2022-08-31 13:59 | Local (MPO) | 0020046601 [RR] | Tracking
1902078 |  | Seymour | Brown | Not Applicable |  | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2021-2024 |  |  |  | 2021-08-04 | 79594.4 | 13432 | 517 | 2022-10-27 11:18 | Local (Non-MPO) | 0020095559 [PE] | Tracking
2002980 | B-43654 | Seymour | Jefferson | Not Applicable |  | Jefferson County | Bridge 107 on Sugan Hollow Road crossing over Brushy Fork Creek |  |  | 2026-03-11 | 2022-03-08 | 234604 | 234604 | 301 | 2022-03-08 15:28 | Local (Non-MPO) | 0020081538 [PE] | Tracking
1400549 | R-37200 | Vincennes | Vanderburgh | Evansville (KY) |  | Vanderburgh County | Green River Rd from Kansas Rd to Boonville-New Harmony Rd | 2022-03-28 07:06 | 2018-08-10 | 2018-08-08 | 2018-06-07 | 106506.67 | 1.67 | 281 | 2022-08-24 13:57 | Local (MPO) | 0020090096 [CN] | Tracking
1592990 |  | Vincennes | Gibson | Not Applicable |  | Gibson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-11-26 07:38 |  |  | 2018-02-20 | 1790.65 | 1790.65 | 403 | 2021-11-26 07:38 | Local (Non-MPO) | 0018814317 [PE] | Tracking
1593001 |  | Vincennes | Posey | Not Applicable |  | Posey County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-11-19 07:19 |  |  | 2018-04-04 | 5146.41 | 5146.41 | 410 | 2021-11-19 07:19 | Local (Non-MPO) | 0018816861 [PE] | Tracking
1593021 |  | Vincennes | Vanderburgh | Not Applicable |  | Vanderburgh County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-03-28 07:06 |  |  | 2018-08-23 | 25163.11 | 25163.11 | 281 | 2022-11-29 09:26 | Local (Non-MPO) | 0020004699 [PE] | Tracking

## PED's next 9 Months
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Project End Date | Federal | Expenditure | FMIS Balance | PO Unliquidated | Open POs | Fund Sponsor | PED Expiration Days | PCO Des Status
1500259 | PLC-38258 | Crawfordsville | Benton | Not Applicable |  | Benton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-08-31 | 213917.64 | 176895.06 | 44732.45 | 44732.45 | 0020019641 [PE] | Local (Non-MPO) | 240 | Tracking
1500251 | PLC-38267 | Crawfordsville | Putnam | Not Applicable |  | Putnam County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-06-30 | 317791.28 | 316383.11 | 1408.17 | 1408.17 | 0020014177 [PE] | Local (Non-MPO) | 178 | Tracking
1592864 |  | Fort Wayne | Adams | Not Applicable |  | Adams County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 269329.6 | 253988.2 | 15341.4 | 15341.4 | 0018815678 [PE] | Local (Non-MPO) | -125 | Tracking
1700310 | R-40098 | Fort Wayne | Elkhart | Elkhart - Goshen |  | Elkhart County | CR 17 Multi-Use Path: From US 33 to CR 45 | 2023-06-30 | 410920 | 252692.76 | 158227.24 | 158227.24 | 0018810716 [PE]; 0020046055 [ROW] | Local (MPO) | 178 | Tracking
1592929 |  | Fort Wayne | Noble | Not Applicable |  | Noble County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-07-31 | 183678.43 | 173323.09 | 10355.34 | 10355.34 | 0020016117 [PE] | Local (Non-MPO) | 209 | Tracking
1801325 |  | Greenfield | Delaware | Muncie |  | MPO - Muncie | Delaware-Muncie MPO Unified Work Program UPWP, PL & STBG for FY 2019-2020 | 2022-06-30 | 561774 | 531129.06 | 30644.94 | 30644.94 | 0020023023 [PL] | Local (MPO) | -187 | Tracking
1801321 |  | Greenfield | Howard | Kokomo |  | MPO - Kokomo | Kokomo MPO Statement of Work(SOW), PL & STBG for 2019-2020 | 2022-07-30 | 437199 | 417728.44 | 19470.56 | 19470.56 | 0020023021 [PL] | Local (MPO) | -157 | Tracking
1500284 |  | Greenfield | Howard | Not Applicable |  | Howard County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-02-28 | 320104.99 | 319807.17 | 297.82 | 297.82 | 0020004712 [PE] | Local (Non-MPO) | 56 | Tracking
1801218 |  | Greenfield | Madison | Anderson |  | MPO - Anderson | Anderson MPO UPWP for FY 2019-2020 | 2022-06-30 | 1289730 | 1289729.99 | 0.01 | 0.01 | 0020022816 [PL] | Local (MPO) | -187 | Tracking
1382070 | B-36439 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Central Avenue Bridge (#1804F) over Fall Creek | 2023-08-28 | 5766749.02 | 5766451.56 | 297.46 | 371.83 | 0020077294 [CN] | Local (MPO) | 237 | Tracking
1500287 |  | Greenfield | Marion | Indianapolis |  | Marion County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 1672548.9 | 1643752.18 | 54115 | 54115 | 0018818297 [PE] | Local (MPO) | -156 | Tracking
1500292 |  | Greenfield | Union | Not Applicable |  | Union County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-05-31 | 141181.2 | 140965.2 | 216 | 216 | 0020019192 [PE] | Local (Non-MPO) | 148 | Tracking
1592159 |  | LaPorte | Jasper | Not Applicable |  | Jasper County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-11-30 | 213407.2 | 177422.55 | 35984.65 | 35984.65 | 0020002482 [PE] | Local (Non-MPO) | -34 | Tracking
1600452 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Greenwood Ave at CSX DOT #232075P in Michigan City | 2023-01-01 | 451828 | 325521.69 | 126306.31 | 126306.31 | 0020013247 [RR] | Local (MPO) | -2 | Tracking
1600454 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Carroll Ave at CSX DOT #232077D in Michigan City | 2023-01-01 | 443752 | 407338.46 | 36413.54 | 36413.54 | 0020013248 [RR] | Local (MPO) | -2 | Tracking
1600448 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Tryon Road at CSX DOT #232070F and Royal Rd DOT# 232071M in Michigan City | 2023-01-01 | 1289231 | 1245112.81 | 44118.19 | 43306.25 | 0020012795 [RR] | Local (MPO) | -2 | Tracking
1600449 |  | LaPorte | LaPorte | Michigan City | Michigan City (1314) | Indiana Department of Transportation | Tilden Street at CSX RR DOT #232080L in Michigan City | 2023-01-01 | 403432 | 369749.06 | 33682.94 | 33682.94 | 0020013249 [RR] | Local (MPO) | -2 | Tracking
1801831 | R-41660 | LaPorte | LaPorte | Michigan City |  | LaPorte County | Lincoln Trail Extension 421/2 to south entrance to Purdue NW | 2023-05-31 | 565312.91 | 315399.25 | 289794.41 | 285281.07 | 0020018418 [PE] | Local (MPO) | 148 | Tracking
1600451 |  | LaPorte | LaPorte | Michigan City |  | Indiana Department of Transportation | Roeske Ave at CSX DOT #232074H in Michigan City | 2023-01-01 | 496418 | 371320.59 | 125097.41 | 90907.12 | 0020013246 [RR] | Local (MPO) | -2 | Tracking
0900064 | R-33678 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | East Chicago (1139) | East Chicago | Indianapolis Blvd Complete St Project: from 152nd St to Columbus Dr. (US 12) | 2022-10-31 | 635979.55 | 559144.35 | 76835.2 | 76835.2 | 0018818554 [PE] | Local (MPO) | -64 | Tracking
0810541 | R-35690 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Hobart (1220) | Hobart | Downtown Hobart along Third Street from Main Street to Center Street | 2023-02-08 | 4584527.3 | 4436831.04 | 147696.26 | 53515.01 | 0020066600 [CN] | Local (MPO) | 36 | Tracking
1500416 | B-39009 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) |  | Hammond | Bike/Ped Bridge over US 41 (Calumet) near Conkey St. | 2023-07-11 | 2450400 | 2316091.75 | 134308.25 | 225954.58 | 0020000463 [CE]; 0020003280 [CN] | Local (MPO) | 189 | Tracking
1592160 |  | LaPorte | Lake | Not Applicable |  | Lake County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 697199.13 | 680907.59 | 16291.54 | 16291.54 | 0020002481 [PE] | Local (Non-MPO) | -125 | Tracking
1592161 |  | LaPorte | Marshall | Not Applicable |  | Marshall County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 247765.26 | 247764.46 | 0.8 | 0.8 | 0020047168 [PE] | Local (Non-MPO) | 28 | Tracking
1401029 | R-37669 | LaPorte | Porter | Chicago - Northwestern Indiana (IL) |  | Porter County | CR 100S - 2000' W of CR 725W to 1000' E of CR 500W Sight Distance Improvement | 2023-08-31 | 2169937.6 | 1606752.54 | 563185.06 | 141024.41 | 0016813708 [PE]; 0020010745 [ROW] | Local (MPO) | 240 | Tracking
1801359 |  | LaPorte | Various | Chicago - Northwestern Indiana (IL) |  | MPO - Northwest | NIRPC MPO Unified Work Program UPWP, PL, STBG and CMAQ for FY 2019-2020 | 2022-06-30 | 3246451 | 3244735.87 | 1715.13 | 1713.56 | 0020022992 [PL] | Local (MPO) | -187 | Tracking
1592166 |  | LaPorte | White | Not Applicable |  | White County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 404117.6 | 386180.8 | 17936.8 | 702.4 | 0020005643 [PE] | Local (Non-MPO) | 28 | Tracking
1700724 | R-40288 | Seymour | Clark | Louisville (KY)-IN | Clarksville (1088) | Clarksville | Blackiston Mill Road from north of the Kroger entrance to Blackiston View | 2023-06-30 | 850000 | 622281.63 | 227718.37 | 227718.37 | 0020058108 [ROW] | Local (MPO) | 178 | Tracking
2001088 |  | Seymour | Clark | Louisville (KY)-IN |  | MPO - Louisville | KIPDA MPO UPWP PL FY 2021 | 2023-06-30 | 657261 | 565576.8 | 91684.2 | 91684.2 | 0020044232 [PL] | Local (MPO) | 178 | Tracking
1500202 | PLC-38172 | Seymour | Dearborn | Not Applicable |  | Dearborn County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-07-31 | 198529.67 | 188365.8 | 10163.87 | 10163.87 | 0020016643 [PE] | Local (Non-MPO) | 209 | Tracking
1700788 | B-40311 | Seymour | Floyd | Louisville (KY)-IN |  | Floyd County | Bridge #51- Blackiston Mill Road over Silver Creek | 2023-06-30 | 404420 | 287875.07 | 116544.93 | 116544.93 | 0020024909 [PE] | Local (MPO) | 178 | Tracking
1500205 | PLC-38175 | Seymour | Franklin | Not Applicable |  | Franklin County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 225825.43 | 214772.2 | 11053.23 | 11053.23 | 0020004705 [PE] | Local (Non-MPO) | 28 | Tracking
1500207 | PLC-38177 | Seymour | Jackson | Not Applicable |  | Jackson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-06-30 | 327812.8 | 294897.57 | 32915.23 | 27267.23 | 0020014176 [PE] | Local (Non-MPO) | 178 | Tracking
1500208 | PLC-38178 | Seymour | Jefferson | Not Applicable |  | Jefferson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-02-28 | 165719.9 | 157625.5 | 8094.4 | 8094.4 | 0020007472 [PE] | Local (Non-MPO) | 56 | Tracking
1500219 | PLC-38187 | Seymour | Jennings | Not Applicable |  | Jennings County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-07-31 | 145292.69 | 144581.49 | 10439.22 | 10439.22 | 0020016644 [PE] | Local (Non-MPO) | 209 | Tracking
1500212 | PLC-38182 | Seymour | Ohio | Not Applicable |  | Ohio County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-05-31 | 67560 | 52676.84 | 22175.16 | 22175.16 | 0020033010 [PE] | Local (Non-MPO) | 148 | Tracking
1500213 | PLC-38183 | Seymour | Ripley | Not Applicable |  | Ripley County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 214627 | 212092.59 | 2534.41 | 2534.41 | 0020047991 [PE] | Local (Non-MPO) | 28 | Tracking
1592990 |  | Vincennes | Gibson | Not Applicable |  | Gibson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-03-31 | 417524.66 | 415734.01 | 1790.65 | 1790.65 | 0018814317 [PE] | Local (Non-MPO) | 87 | Tracking
1592999 |  | Vincennes | Perry | Not Applicable |  | Perry County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-04-30 | 253580 | 237944.81 | 15635.19 | 13358.39 | 0020009818 [PE] | Local (Non-MPO) | 117 | Tracking
1593000 |  | Vincennes | Pike | Not Applicable |  | Pike County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2023-07-31 | 278913.44 | 267593.28 | 32421.68 | 25680.96 | 0020016095 [PE] | Local (Non-MPO) | 209 | Tracking
1593001 |  | Vincennes | Posey | Not Applicable |  | Posey County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-04-30 | 381166.29 | 376019.88 | 5146.41 | 5146.41 | 0018816861 [PE] | Local (Non-MPO) | -248 | Tracking
1593021 |  | Vincennes | Vanderburgh | Not Applicable |  | Vanderburgh County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2023-01-31 | 356146.35 | 330983.24 | 25163.11 | 25163.11 | 0020004699 [PE] | Local (Non-MPO) | 28 | Tracking