## Inactive Projects
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Latest Payment Date | Actual Letting Date | Target Letting Date | Earliest Auth Date | FMIS Balance | PO Unliquidated | Inactive Days | Last Action Date | Fund Sponsor | Open POs | PCO Des Status | PCO Task ID
1401647 | R-38012 | Crawfordsville | Hendricks | Indianapolis | Brownsburg (1053) | Brownsburg | New Alignment on Northfield Drive between CR 300 N to Airport Rd CR 400 N | 2021-04-30 06:58 | 2018-07-11 | 2018-07-11 | 2018-05-17 | 58543.41 | 58543.41 | 304 | 2021-07-07 09:39 | Local (MPO) | 0020022663 [CE] | TR | #N/A
1500253 | PLC-38269 | Crawfordsville | Vermillion | Not Applicable |  | Vermillion County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2021-04-02 07:14 |  |  | 2019-07-08 | 61048.32 | 61048.32 | 332 | 2021-05-07 07:13 | Local (Non-MPO) | 0020024552 [PE] | TR | #N/A
1500254 | PLC-38270 | Crawfordsville | Vigo | Not Applicable |  | Vigo County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-01-15 11:03 |  |  | 2017-06-14 | 3166.38 | 3166.38 | 409 | 2021-01-15 11:03 | Local (Non-MPO) | 0018800501 [PE] | TR | #N/A
1801364 |  | Crawfordsville | Vigo | Terre Haute |  | MPO - Terre Haute | Terre Haute MPO Unified Work Program UPWP, PL & HSIP for FY 2019-2020 | 2021-02-19 07:32 |  |  | 2018-06-28 | 61158.2 | 61158.2 | 374 | 2021-05-13 15:01 | Local (MPO) | 0020044242 [PL] | TR | #N/A
1592940 |  | Fort Wayne | Wells | Not Applicable |  | Wells County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-03-12 07:50 |  |  | 2017-08-07 | 4872 | 4872 | 353 | 2021-03-12 07:50 | Local (Non-MPO) | 0018802896 [PE] | TR | #N/A
1702858 | R-41143 | Fort Wayne | Blackford | Not Applicable | Hartford City (1212) | Hartford City | Sidewalks, Jefferson St:: Kentucky Ave. to Park Ave Park Ave: Jefferson to High | 2021-01-22 08:54 | 2021-08-11 | 2021-08-11 | 2019-12-05 | 137369.02 | 164139.22 | 402 | 2021-09-09 15:54 | Local (Non-MPO) | 0020031829 [PE]; 0020068387 [CE]; 0020069800 [CN] | TR | #N/A
1801666 | R-41416 | Fort Wayne | Allen | Fort Wayne | Fort Wayne (1165) | Fort Wayne | Maplecrest Rd (Phase 1): from State St to Trier Rd | 2021-01-29 11:36 | 2019-08-07 | 2019-08-07 | 2019-06-11 | 191240 | 0.54 | 395 | 2022-02-09 14:00 | Local (MPO) | 0020079397 [CE] | TR | #N/A
1383176 | B-36900 | Greenfield | Marion | Indianapolis |  | Indianapolis | 0.15 miles NW of Kentucky Ave ove White River, Oliver Ave Over White River | 2021-04-30 06:58 | 2017-12-13 | 2017-12-13 | 2017-09-14 | 6135.58 | 178167.64 | 304 | 2021-04-30 06:58 | Local (MPO) | 0018812324 [CN] | TR | #N/A
1400944 | B-37591 | Greenfield | Marion | Indianapolis |  | Indianapolis | Monon Bicycle/Pedestrian Bridge over 38th Str.28 miles E of 38th & College | 2020-10-23 07:31 | 2020-01-15 | 2020-01-15 | 2019-11-26 | 0 | 1995.33 | 493 | 2021-05-03 12:43 | Local (MPO) | 0020036255 [CN] | TR | #N/A
1401701 | R-38073 | Greenfield | Hamilton | Indianapolis |  | Hamilton County | 146th St, 1000' W Hamilton / Boone Co Line to 1000' W of Shelborne Rd | 2021-04-23 07:37 | 2020-02-05 | 2020-02-05 | 2020-01-15 | 0 | 68787.27 | 311 | 2021-04-23 07:37 | Local (MPO) | 0020036968 [CN] | TR | #N/A
1401719 | B-38039 | Greenfield | Marion | Indianapolis |  | Indianapolis | 38th St Bridge (#2001F) over CSX RR; betw Arlington Ave. & Massachusetts Ave | 2021-05-21 07:11 | 2018-11-15 | 2018-11-15 | 2018-09-17 | 0 | 62154.85 | 283 | 2021-05-21 07:11 | Local (MPO) | 0020056808 [RR] | TR | #N/A
1500285 |  | Greenfield | Jay | Not Applicable |  | Jay County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-02-26 06:53 |  |  | 2017-08-07 | 563.2 | 563.2 | 367 | 2021-02-26 06:53 | Local (Non-MPO) | 0020047685 [PE] | TR | #N/A
1500286 |  | Greenfield | Madison | Not Applicable |  | Madison County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-04-02 07:14 |  |  | 2018-07-30 | 4484.6 | 4484.6 | 332 | 2021-07-27 11:07 | Local (Non-MPO) | 0020046599 [PE] | TR | #N/A
1600597 | R-39726 | Greenfield | Hamilton | Indianapolis |  | Hamilton County | 276th St. .6 miles W of Gwinn Rd to 281st at Gwinn Rd & along 281st over to SR 1 | 2020-10-30 08:51 | 2019-05-09 | 2019-05-09 | 2019-04-10 | 0 | 617160.34 | 486 | 2021-05-05 07:36 | Local (MPO) | 0020020968 [CN]; 0020063441 [CN] | TR | #N/A
1600971 | R-40327 | Greenfield | Tipton | Not Applicable | Windfall (1561) | Windfall | SW and ADA Upgrades on SR 213 - Sherman Str and Grant St in Windfall | 2021-05-07 08:10 |  | 2022-05-05 | 2017-10-30 | 4682.37 | 4682.37 | 297 | 2021-05-07 08:10 | Local (Non-MPO) | 0018806979 [PE] | TR | #N/A
1600987 | R-39745 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Fall Creek Trail; Meridian Street to Central Canal - Phase 1 | 2021-02-05 08:40 | 2020-03-04 | 2020-03-04 | 2019-10-30 | 79763.64 | 132449.72 | 388 | 2022-01-26 12:59 | Local (MPO) | 0020075562 [CN]; 0020078514 [CN] | TR | #N/A
1601829 | B-39873 | Greenfield | Hamilton | Indianapolis | Noblesville (1377) | Fishers | Drainage pipe installation along 131st near SR 37 | 2021-04-02 07:14 | 2018-09-12 | 2018-09-12 | 2018-07-10 | 12195.06 | 11476.35 | 332 | 2021-04-02 07:14 | Local (MPO) | 0020034328 [CN] | TR | #N/A
1700902 | T-40357 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Pedestrian Crash Focus Area 5 | 2021-04-16 07:52 | 2020-10-07 | 2020-10-07 | 2020-09-02 | 0 | 55568.88 | 318 | 2021-04-16 07:52 | Local (MPO) | 0020054245 [CN] | TR | #N/A
1700903 | T-40358 | Greenfield | Marion | Indianapolis | Indianapolis (1233) | Indianapolis | Pedestrian Crash Focus Area 3 |  | 2021-11-17 | 2021-11-17 | 2020-10-07 | 1454463 | 1987719.6 | 509 | 2021-12-22 17:56 | Local (MPO) | 0020076278 [CN] | TR | #N/A
1702392 | R-41838 | Greenfield | Hancock | Indianapolis |  | Hancock County | Environmental mitigation site for 300N West of 600W | 2021-04-30 06:58 | 2019-03-06 | 2019-03-06 | 2019-01-14 | 34174.48 | 18607.51 | 304 | 2021-04-30 06:58 | Local (MPO) | 0020015810 [CE] | TR | #N/A
1902776 | R-42797 | Greenfield | Rush | Not Applicable | Rushville (1448) | Rushville | Morgan St Trail along Morgan St from 3rd St to 13th St and 13th St from Morgan S |  |  | 2024-11-14 | 2020-08-18 | 217568 | 167183.8 | 559 | 2020-08-18 16:20 | Local (Non-MPO) | 0020047783 [PE] | TR | #N/A
1902801 | R-42757 | Greenfield | Hamilton | Indianapolis | Westfield (1547) | Westfield | Little Eagle Creek Avenue between 146th Street and Shelborne Road |  |  | 2025-08-06 | 2021-04-08 | 255600 | 255600 | 326 | 2021-04-08 11:00 | Local (MPO) | 0020061673 [PE] | TR | #N/A
1298578 | R-40170 | LaPorte | St. Joseph | South Bend (MI) |  | St. Joseph County | Cleveland Road over St. Joseph River to SR 933 | 2021-01-29 11:36 | 2017-12-13 | 2017-12-13 | 2016-03-01 | 27883.67 | 27883.67 | 395 | 2022-01-05 11:35 | Local (MPO) | 0017811922 [CE] | TR | #N/A
1592164 |  | LaPorte | Pulaski | Not Applicable |  | Pulaski County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2021-04-30 06:58 |  |  | 2018-07-31 | 58475.66 | 58475.66 | 304 | 2021-07-23 15:35 | Local (Non-MPO) | 0020002545 [PE] | TR | #N/A
1593056 |  | LaPorte | St. Joseph | Not Applicable |  | St. Joseph County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2020-2023 | 2021-03-05 07:20 |  |  | 2020-07-23 | 67729.78 | 67729.78 | 360 | 2021-07-23 15:36 | Local (Non-MPO) | 0020045720 [PE] | TR | #N/A
1702152 | R-37496 | LaPorte | St. Joseph | South Bend (MI) |  | St. Joseph County | Douglas Road over Juday Creek Bridge #191 |  | 2020-12-09 | 2020-12-09 | 2020-11-09 | 846463.24 | 1058079.05 | 476 | 2021-02-04 09:35 | Local (MPO) | 0020056246 [CN] | TR | #N/A
1702153 | R-37496 | LaPorte | St. Joseph | South Bend (MI) |  | St. Joseph County | Ironwood Road over Juday Creek Bridge #192 |  | 2020-12-09 | 2020-12-09 | 2020-11-09 | 842706.93 | 1053383.66 | 476 | 2021-02-04 09:35 | Local (MPO) | 0020056246 [CN] | TR | #N/A
1801362 |  | LaPorte | Various | South Bend (MI) |  | MPO - South Bend / Elkhart | MACOG MPO Unified Work Program CMAQ, STBG & HSIP for FY 2019-2020 | 2021-04-02 07:14 |  |  | 2018-06-28 | 30600.21 | 28617.41 | 332 | 2022-01-06 18:00 | Local (MPO) | 0020022274 [PL] | TR | #N/A
1801738 | R-41770 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Gary (1182) | Gary | Complete Streets Enhancements on Lake Street and minor on US 12/20 in Gary |  | 2021-05-05 | 2021-05-05 | 2018-09-04 | 1824016.01 | 2819627.08 | 1273 | 2021-06-01 15:13 | Local (MPO) | 0020056309 [PE]; 0020063648 [CE]; 0020064507 [CN] | TR | #N/A
2000783 |  | LaPorte | St. Joseph | South Bend (MI) | South Bend (1475) | Norfolk Southern Railway Co | NS RR - S Franklin DOT 478509G, W Main DOT 478510B, S Elder DOT 522522P, S Verno |  |  |  | 2021-02-10 | 1676540.7 | 1673707.63 | 383 | 2021-04-30 13:56 | Local (MPO) | 0020057387 [RR] | TR | #N/A
0901275 | R-36161 | Seymour | Floyd | Louisville (KY)-IN |  | New Albany | Upgrade Market and Spring Streets as 2-way streets from IN 111 to State St | 2021-04-02 07:14 | 2017-03-01 | 2017-03-01 | 2015-04-20 | 66754.79 | 56097.26 | 332 | 2021-04-02 07:14 | Local (MPO) | 0017817671 [RR] | TR | #N/A
1382874 | R-37105 | Seymour | Brown | Not Applicable |  | Brown County | Salt Creek Trail - Phases 2 & 3 | 2021-04-23 07:37 |  | 2024-07-10 | 2015-03-23 | 158820 | 40820 | 311 | 2021-04-23 07:37 | Local (Non-MPO) | 0015813623 [PE] | TR | #N/A
1400615 |  | Seymour | Floyd | Louisville (KY)-IN | New Albany (1356) | Indiana Department of Transportation | Corydon Pike (old SR 62) at NS DOT# 724966S south of New Albany | 2021-05-14 07:35 |  | 2018-05-31 | 2016-04-19 | 390763.9 | 121.76 | 290 | 2021-06-22 13:15 | Local (MPO) | 0020045342 [PE] | TR | #N/A
1600655 | R-40224 | Seymour | Johnson | Indianapolis | Franklin (1173) | Franklin | S Main St from S Main Bridge at Young's Creek to US 31 | 2020-12-11 07:29 | 2019-11-14 | 2019-11-14 | 2019-10-08 | 0 | 28855.27 | 444 | 2020-12-11 07:29 | Local (MPO) | 0020033019 [CN] | TR | #N/A
1700735 | R-40293 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | From existing B-Line Trail terminus at Adams Street to 17th at Crescent |  |  | 2022-11-16 | 2021-05-05 | 717640 | 717640 | 299 | 2021-05-05 09:52 | Local (MPO) | 0020063657 [ROW] | TR | #N/A
1700976 | R-40337 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | Systematic safety improvements expected to include approximately 25 crosswalks. |  |  | 2022-04-06 | 2021-02-22 | 453292.71 | 5000 | 371 | 2021-12-23 19:02 | Local (MPO) | 0020076879 [CE] | TR | #N/A
1800008 | R-40375 | Seymour | Bartholomew | Columbus |  | Bartholomew County | Bridge #103 on Talley Road between 25th Street and Rocky Ford Road | 2021-03-26 07:25 |  | 2024-07-01 | 2018-05-07 | 90351.39 | 90351.39 | 339 | 2021-03-26 07:25 | Local (MPO) | 0018818528 [PE] | TR | #N/A
1801245 |  | Seymour | Monroe | Bloomington |  | MPO - Bloomington | Bloomington MPO UPWP for FY 2019-2020 | 2020-12-28 07:22 |  |  | 2018-06-28 | 93864.56 | 61075.13 | 427 | 2020-12-28 07:22 | Local (MPO) | 0020021893 [PL] | TR | #N/A
1900403 | R-41896 | Seymour | Monroe | Bloomington | Bloomington (1038) | Bloomington | Numerous Location in and near downtown Bloomington that require accessible curb |  |  | 2022-10-13 | 2021-04-21 | 81858 | 81858 | 313 | 2021-04-21 13:29 | Local (MPO) | 0020062380 [PE] | TR | #N/A
1902767 | B-42802 | Seymour | Johnson | Not Applicable |  | Johnson County | Bridge 98 on CR 700E over Fisher Ditch - 0.01 mi N or Urmeyville Road |  |  | 2024-10-09 | 2021-05-04 | 172600 | 172600 | 300 | 2021-05-04 12:45 | Local (Non-MPO) | 0020063887 [PE] | TR | #N/A
1593023 |  | Vincennes | Warrick | Not Applicable |  | Warrick County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-02-26 06:53 |  |  | 2017-06-14 | 49157 | 49157 | 367 | 2021-02-26 06:53 | Local (Non-MPO) | 0018800617 [PE] | TR | #N/A
1802823 |  | Vincennes | Dubois | Not Applicable |  | Dubois County | CR 600W at NS AAR# 724930J in Dubois County |  |  |  | 2019-05-08 | 333893.7 | 370993 | 1027 | 2021-07-08 16:42 | Local (Non-MPO) | 0020035049 [RR] | TR | #N/A
1802901 | R-41237 | Vincennes | Perry | Not Applicable | Tell City (1504) | Tell City | Washington Street from SR 66 (12th Street) to Main Street (8th Street) | 2021-04-02 07:14 |  | 2022-04-06 | 2019-10-11 | 863888 | 41351.57 | 332 | 2022-02-24 14:12 | Local (Non-MPO) | 0020028788 [PE] | TR | #N/A

## PED's next 9 Months
Des | CN Contract | District | County | Urban Area | City Boundary / Federal Place | Sponsor | Project Location | Project End Date | Federal | Expenditure | FMIS Balance | PO Unliquidated | Open POs | Fund Sponsor | PCO Des Status | PED Expiration Days | PCO Task ID
1500229 | PLC-38260 | Crawfordsville | Clay | Not Applicable |  | Clay County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 316612.16 | 311238.24 | 5373.92 | 5373.92 | 0020002552 [PE] | Local (Non-MPO) | TR | 214 | #N/A
1500231 | PLC-38261 | Crawfordsville | Clinton | Not Applicable |  | Clinton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 248006.4 | 221541.95 | 26464.45 | 23653.84 | 0020051600 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1500232 | PLC-38262 | Crawfordsville | Fountain | Not Applicable |  | Fountain County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 364788.31 | 336822.1 | 27966.21 | 27966.21 | 0018817374 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1500241 | PLC-38263 | Crawfordsville | Hendricks | Not Applicable |  | Hendricks County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-04-30 | 321040.52 | 317053.33 | 3987.19 | 1139.19 | 0020044157 [PE] | Local (Non-MPO) | TR | 61 | #N/A
1600821 | R-39860 | Crawfordsville | Parke | Not Applicable | Rockville (1441) | Rockville | S Market Street | 2022-06-30 | 444400 | 356420.31 | 87979.69 | 87979.69 | 0018813144 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1801323 |  | Crawfordsville | Tippecanoe | Lafayette - West Lafayette |  | MPO - Lafayette | Lafayette MPO Unified Work Program UPWP, PL for FY 2019-2020 | 2022-06-30 | 676444 | 675629 | 815 | 815 | 0020023022 [PL] | Local (MPO) | TR | 122 | #N/A
1500254 | PLC-38270 | Crawfordsville | Vigo | Not Applicable |  | Vigo County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-06-30 | 299785.17 | 296618.79 | 3166.38 | 3166.38 | 0018800501 [PE] | Local (Non-MPO) | TR | -243 | #N/A
1801364 |  | Crawfordsville | Vigo | Terre Haute |  | MPO - Terre Haute | Terre Haute MPO Unified Work Program UPWP, PL & HSIP for FY 2019-2020 | 2022-06-30 | 557416 | 496257.8 | 61158.2 | 61158.2 | 0020044242 [PL] | Local (MPO) | TR | 122 | #N/A
1592864 |  | Fort Wayne | Adams | Not Applicable |  | Adams County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 269329.6 | 253988.2 | 15341.4 | 15341.4 | 0018815678 [PE] | Local (Non-MPO) | TR | 184 | #N/A
1592872 |  | Fort Wayne | Allen | Not Applicable |  | Allen County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 697827.02 | 695233.89 | 2593.13 | 2593.13 | 0018815672 [PE] | Local (Non-MPO) | TR | 153 | #N/A
1592883 |  | Fort Wayne | Blackford | Not Applicable |  | Blackford County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 115564 | 110057.54 | 5506.46 | 5506.46 | 0020004680 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1592887 |  | Fort Wayne | Elkhart | Not Applicable |  | Elkhart County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 405110.82 | 376210.08 | 28900.74 | 16626.23 | 0020001180 [PE] | Local (Non-MPO) | TR | 184 | #N/A
1592891 |  | Fort Wayne | Kosciusko | Not Applicable |  | Kosciusko County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-03-31 | 220399.65 | 214986.37 | 5413.28 | 5413.28 | 0018812316 [PE] | Local (Non-MPO) | TR | 31 | #N/A
1592940 |  | Fort Wayne | Wells | Not Applicable |  | Wells County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-03-31 | 223002.27 | 218130.27 | 4872 | 4872 | 0018802896 [PE] | Local (Non-MPO) | TR | 31 | #N/A
1801325 |  | Greenfield | Delaware | Muncie |  | MPO - Muncie | Delaware-Muncie MPO Unified Work Program UPWP, PL & STBG for FY 2019-2020 | 2022-06-30 | 561774 | 531129.06 | 30644.94 | 30644.94 | 0020023023 [PL] | Local (MPO) | TR | 122 | #N/A
1500281 |  | Greenfield | Hamilton | Not Applicable |  | Hamilton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-03-01 | 473885.78 | 470738.94 | 3146.84 | 3146.84 | 0018800503 [PE] | Local (Non-MPO) | TR | 1 | #N/A
1500282 |  | Greenfield | Hancock | Not Applicable |  | Hancock County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 232639 | 217388.25 | 15250.75 | 15250.75 | 0018816854 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1801321 |  | Greenfield | Howard | Kokomo |  | MPO - Kokomo | Kokomo MPO Statement of Work(SOW), PL & STBG for 2019-2020 | 2022-07-30 | 437199 | 417728.44 | 19470.56 | 19470.56 | 0020023021 [PL] | Local (MPO) | TR | 152 | #N/A
1500285 |  | Greenfield | Jay | Not Applicable |  | Jay County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-04-29 | 284033.4 | 283470.2 | 563.2 | 563.2 | 0020047685 [PE] | Local (Non-MPO) | TR | 60 | #N/A
1500286 |  | Greenfield | Madison | Not Applicable |  | Madison County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 471974.47 | 467489.87 | 4484.6 | 4484.6 | 0020046599 [PE] | Local (Non-MPO) | TR | 214 | #N/A
1801218 |  | Greenfield | Madison | Anderson |  | MPO - Anderson | Anderson MPO UPWP for FY 2019-2020 | 2022-06-30 | 1244730 | 1227341.57 | 62388.43 | 3299.45 | 0020022816 [PL] | Local (MPO) | TR | 122 | #N/A
1500287 |  | Greenfield | Marion | Indianapolis |  | Marion County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 1672548.9 | 1595974.86 | 101892.32 | 88783.36 | 0018818297 [PE] | Local (MPO) | TR | 153 | #N/A
1383176 | B-36900 | Greenfield | Marion | Indianapolis |  | Indianapolis | 0.15 miles NW of Kentucky Ave ove White River, Oliver Ave Over White River | 2022-11-15 | 3765906.95 | 3759771.37 | 6135.58 | 178167.64 | 0018812324 [CN] | Local (MPO) | TR | 260 | #N/A
1500172 |  | Greenfield | Tipton | Not Applicable |  | Indiana Department of Transportation | Ind. St at NS DOT# 474671H; also 474672P; 474673W; 474669G; 474670B in Tipton | 2021-12-31 | 1740637.63 | 1490653.78 | 249983.85 | 30746.42 | 0017818361 [RR]; 0020078330 [] | Local (Non-MPO) | TR | -59 | #N/A
1500293 |  | Greenfield | Wayne | Not Applicable |  | Wayne County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 496084.41 | 478716 | 17368.41 | 17368.41 | 0018814391 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1592158 |  | LaPorte | Fulton | Not Applicable |  | Fulton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 149046.08 | 142343.68 | 6702.4 | 594.4 | 0020036120 [PE] | Local (Non-MPO) | TR | 153 | #N/A
1592159 |  | LaPorte | Jasper | Not Applicable |  | Jasper County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-11-30 | 213407.2 | 175328.15 | 38079.05 | 38079.05 | 0020002482 [PE] | Local (Non-MPO) | TR | 275 | #N/A
0900064 | R-33678 | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | East Chicago (1139) | East Chicago | Indianapolis Blvd from McShane Dr to Michigan St. | 2022-10-31 | 635979.55 | 264404.43 | 371575.12 | 371575.12 | 0018818554 [PE] | Local (MPO) | TR | 245 | #N/A
1592160 |  | LaPorte | Lake | Not Applicable |  | Lake County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-08-31 | 697199.13 | 669578 | 27621.13 | 27621.13 | 0020002481 [PE] | Local (Non-MPO) | TR | 184 | #N/A
1592162 |  | LaPorte | Newton | Not Applicable |  | Newton County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 260375.55 | 256194.02 | 4181.53 | 4181.53 | 0020002546 [PE] | Local (Non-MPO) | TR | 214 | #N/A
1382657 | R-36384 | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | Chesterton (1083) | Chesterton | Westchester-Liberty Trail, Phase 2 | 2022-04-05 | 684766.05 | 642078.21 | 42687.84 | 3118.01 | 0015806590 [PE] | Local (MPO) | TR | 36 | #N/A
1592163 |  | LaPorte | Porter | Not Applicable |  | Porter County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 299629.54 | 276013.36 | 23616.18 | 23616.18 | 0018816842 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1592164 |  | LaPorte | Pulaski | Not Applicable |  | Pulaski County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-09-30 | 171488.2 | 113012.54 | 58475.66 | 58475.66 | 0020002545 [PE] | Local (Non-MPO) | TR | 214 | #N/A
1801359 |  | LaPorte | Various | Chicago - Northwestern Indiana (IL) |  | MPO - Northwest | NIRPC MPO Unified Work Program UPWP, PL, STBG and CMAQ for FY 2019-2020 | 2022-06-30 | 3246451 | 2609456.78 | 636994.22 | 636992.65 | 0020022992 [PL] | Local (MPO) | TR | 122 | #N/A
1801362 |  | LaPorte | Various | South Bend (MI) |  | MPO - South Bend / Elkhart | MACOG MPO Unified Work Program CMAQ, STBG & HSIP for FY 2019-2020 | 2022-06-30 | 2239178 | 2208577.79 | 30600.21 | 28617.41 | 0020022274 [PL] | Local (MPO) | TR | 122 | #N/A
1500192 | PLC-38169 | Seymour | Bartholomew | Not Applicable |  | Bartholomew County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 428274.52 | 418068.62 | 10205.9 | 10205.9 | 0018816864 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1500200 | PLC-38170 | Seymour | Brown | Not Applicable |  | Brown County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2021-09-30 | 179413.02 | 155777.88 | 23635.14 | 23635.14 | 0020024658 [PE] | Local (Non-MPO) | TR | -151 | #N/A
1382874 | R-37105 | Seymour | Brown | Not Applicable |  | Brown County | Salt Creek Trail - Phases 2 & 3 | 2022-06-30 | 396240 | 237420 | 158820 | 40820 | 0015813623 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1500201 | PLC-38171 | Seymour | Clark | Not Applicable |  | Clark County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-04-30 | 254206.11 | 244740.22 | 9465.89 | 9465.89 | 0018814316 [PE] | Local (Non-MPO) | TR | 61 | #N/A
1802805 | R-41802 | Seymour | Clark | Louisville (KY)-IN |  | Clark County | CR 403 and Stacy Road Intersection Improvement | 2022-06-30 | 283500 | 189651.11 | 93848.89 | 93848.89 | 0020026805 [PE] | Local (MPO) | TR | 122 | #N/A
1500204 | PLC-38174 | Seymour | Floyd | Not Applicable |  | Floyd County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-02-28 | 165514.5 | 160492.97 | 5021.53 | 5021.53 | 0018812308 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1703018 | B-40891 | Seymour | Jackson | Not Applicable |  | Jackson County | Bridge #197-CR 100S over McHargue Ditch, .01 mile East of CR 500W | 2022-06-30 | 200501.6 | 42042.41 | 158459.19 | 158459.19 | 0020023689 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1500209 | PLC-38179 | Seymour | Johnson | Not Applicable |  | Johnson County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-07-31 | 285488 | 247269.75 | 38218.25 | 38218.25 | 0018817373 [PE] | Local (Non-MPO) | TR | 153 | #N/A
1801245 |  | Seymour | Monroe | Bloomington |  | MPO - Bloomington | Bloomington MPO UPWP for FY 2019-2020 | 2022-06-30 | 545584 | 451719.44 | 93864.56 | 61075.13 | 0020021893 [PL] | Local (MPO) | TR | 122 | #N/A
1500211 | PLC-38181 | Seymour | Morgan | Not Applicable |  | Morgan County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-11-30 | 345057.16 | 279162.31 | 65894.85 | 65894.85 | 0020001444 [PE] | Local (Non-MPO) | TR | 275 | #N/A
1500215 | PLC-38185 | Seymour | Switzerland | Not Applicable |  | Switzerland County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 88899.07 | 87737.47 | 1161.6 | 1161.6 | 0020038641 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1592987 |  | Vincennes | Dubois | Not Applicable |  | Dubois County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-02-28 | 203881.83 | 202066.19 | 1815.64 | 1815.64 | 0020054176 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1592992 |  | Vincennes | Lawrence | Not Applicable |  | Lawrence County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-06-30 | 261080.8 | 251233.24 | 9847.56 | 7682.76 | 0018816862 [PE] | Local (Non-MPO) | TR | 122 | #N/A
1592993 |  | Vincennes | Martin | Not Applicable |  | Martin County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-02-28 | 217973.6 | 217344 | 629.6 | 629.6 | 0018806817 [PE] | Local (Non-MPO) | TR | 0 | #N/A
1592994 |  | Vincennes | Orange | Not Applicable |  | Orange County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-05-31 | 346677.6 | 334134.62 | 12542.98 | 12542.98 | 0018816852 [PE] | Local (Non-MPO) | TR | 92 | #N/A
1593001 |  | Vincennes | Posey | Not Applicable |  | Posey County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-04-30 | 381166.29 | 376019.88 | 5146.41 | 5146.41 | 0018816861 [PE] | Local (Non-MPO) | TR | 61 | #N/A
1593016 |  | Vincennes | Spencer | Not Applicable |  | Spencer County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2022-11-30 | 311101.12 | 308322.29 | 2778.83 | 2778.83 | 0020001438 [PE] | Local (Non-MPO) | TR | 275 | #N/A
1593023 |  | Vincennes | Warrick | Not Applicable |  | Warrick County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2022-08-31 | 354093.39 | 304936.39 | 49157 | 49157 | 0018800617 [PE] | Local (Non-MPO) | TR | 184 | #N/A

## Data
Des # | Task Id | Task Owner
0901135 | 99844
1500256 | 99215 | Nieman, Gerald