## Inactive Projects
Des | Contract | INDOT District | County | FMIS Urban Area | City Boundary / Federal Place Code | Sponsoring Organizarion | Location | FMIS Latest Payment Date | Actual Letting Date | Target Letting Date | Earliest Authorization Date | FMIS Balance | PO Unliquidated Amount | Days Inactive | FMIS Header Last Action Date | PO Phase | PCO Task ID
1401280 | R-37909 | Crawfordsville | Tippecanoe | Lafayette - West Lafayette | N/A | Tippecanoe County | Morehouse Rd from Sagamore Parkway to just N of Mason Dixon Rd (phase 2) | 2020-11-27 | N/A | 2024-11-14 | 2017-01-18 | 1431.8 | 204274.2 | 399 | 2021-07-26 | PE ROW | #N/A
1401646 | R-38013 | Crawfordsville | Hendricks | Indianapolis | Brownsburg | Brownsburg | Intersection reconstruction at Hornaday Road and E CR 300 N | 2020-12-28 | 2019-02-06 | 2019-02-06 | 2018-12-13 | 92424.26 | 115530.33 | 368 | 2020-12-28 | CE CN | #N/A
1400995 | R-37648 | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen | Goshen | Ninth St Multi-Use Path: from College Ave to Purl St | 2020-12-28 | 2019-01-16 | 2019-01-16 | 2015-01-26 | 28611.88 | 27675.22 | 368 | 2020-12-28 | PE RR CE CN | 93598
1592889 | N/A | Fort Wayne | Huntington | Not Applicable | N/A | Huntington County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 | 2020-12-28 | N/A | N/A | 2017-08-07 | 1847.49 | 1847.49 | 368 | 2020-12-28 | PE | #N/A
1902757 | R-42770 | Fort Wayne | Huntington | Not Applicable | Huntington | Huntington County | CR 300W at Division Road | N/A | N/A | 2024-12-11 | 2020-10-14 | 176179.5 | 143883.9 | 443 | 2020-10-15 | PE | #N/A
1902847 | R-42778 | Fort Wayne | Grant | Not Applicable | Sweetser | Sweetser | ADA Ramp and Sidewalks at Various locations in Sweetser | N/A | N/A | 2024-12-11 | 2020-11-24 | 44480 | 44480 | 402 | 2020-11-24 | PE | #N/A
1401717 | B-38037 | Greenfield | Marion | Indianapolis | N/A | Indianapolis | Morgantown Road Bridge (#4509F) over Pleasant Run | 2020-10-16 | 2019-02-06 | 2019-02-06 | 2018-12-19 | 37995.6 | 47494.5 | 441 | 2021-06-14 | CE CN | #N/A
1401722 | B-38042 | Greenfield | Marion | Indianapolis | N/A | Indianapolis | Dandy Trail Bridge (#1501F) over Big Eagle Creek | 2020-10-23 | 2019-02-06 | 2019-02-06 | 2018-12-19 | 16924.52 | 20193.26 | 434 | 2020-10-23 | CE CN | #N/A
1401818 | R-39533 | Greenfield | Howard | Kokomo | N/A | Kokomo | Lincoln Road; from Webster to Park | 2020-12-11 | 2019-02-06 | 2019-02-06 | 2016-04-20 | 208069.57 | 27468.34 | 385 | 2020-12-11 | PE ROW CE CN | #N/A
1500432 | R-38414 | Greenfield | Marion | Indianapolis | N/A | Indianapolis | Within 1/2 mile of the E Michigan St & Tecumseh St Intersection | 2020-12-28 | 2018-12-12 | 2018-12-12 | 2016-04-18 | 43082.36 | 46095.14 | 368 | 2020-12-28 | PE CE CN | #N/A
1802925 | R-42075 | Greenfield | Jay | Not Applicable | Dunkirk | Dunkirk | Multi-use path in the Dunkirk City Park Along Speedcat Alley | 2020-12-28 | N/A | 2023-09-13 | 2020-07-13 | 19678.8 | 19678.8 | 368 | 2020-12-28 | PE | #N/A
1802944 | R-42071 | Greenfield | Randolph | Not Applicable | Union City | Union City | The project is located approx. 350' north of the Intersection of W. Chestnut St. | 2020-10-09 | N/A | 2023-07-12 | 2020-04-30 | 74338.24 | 70412.24 | 448 | 2020-12-30 | PE RR | 93446
1298670 | R-35881 | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | Valparaiso | Valparaiso | US 30 Corridor Improvements | 2020-10-16 | N/A | 2019-01-16 | 2013-04-11 | 964123.92 | 1016819.63 | 441 | 2020-10-16 | PE ROW RR | #N/A
1592157 | N/A | LaPorte | Cass | Not Applicable | N/A | Cass County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2019-2022 | 2020-05-08 | N/A | N/A | 2019-04-25 | 0.09 | 4017.6 | 602 | 2021-04-07 | PE | #N/A
1601899 | N/A | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Gary | Gary | Road Safety Audit - Ridge Rd, Grant St and Lake Street | 2020-12-28 | N/A | N/A | 2017-05-01 | 87275 | 87275 | 368 | 2020-12-28 | PE | #N/A
1702834 | R-41179 | LaPorte | Starke | Not Applicable | North Judson | North Judson | ADA ramp and sidewalk upgrades around downtown North Judson Phase 3 | 2020-11-27 | N/A | 2021-12-08 | 2019-12-18 | 10109.19 | 10109.19 | 399 | 2020-11-27 | PE | #N/A
0710003 | R-31759 | Seymour | Clark | Louisville (KY)-IN | N/A | Clark County | Bethany Road Phase 1- SR 62 to 1.31 miles northwest of SR62 | 2020-11-20 | 2018-05-10 | 2018-05-10 | 2008-02-01 | 560992.29 | 584586.58 | 406 | 2021-09-02 | PE ROW UT RR CE CN | #N/A
1400619 | N/A | Seymour | Harrison | Not Applicable | N/A | Indiana Department of Transportation | Angel Run Road at NS DOT# 724987K near Crandall | 2020-07-24 | N/A | 2018-05-31 | 2016-04-25 | 485595.52 | 475597.35 | 525 | 2021-06-22 | RR | #N/A
1400675 | R-37467 | Seymour | Dearborn | Cincinnati | N/A | Dearborn County | State Line Rd, from 1600' S of Georgetown Road to 400' N, Roadway alignment | 2020-12-11 | 2020-03-04 | 2020-03-04 | 2015-03-11 | 5443.37 | 5403.35 | 385 | 2020-12-11 | PE ROW UT CE CN | #N/A
1500211 | PLC-38181 | Seymour | Morgan | Not Applicable | N/A | Morgan County | Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 | 2020-12-28 | N/A | N/A | 2018-07-11 | 124529.89 | 124529.89 | 368 | 2021-06-14 | PE | #N/A
1500382 | R-38348 | Seymour | Monroe | Bloomington | N/A | Bloomington | Sidepath on E Rogers Rd at the Jackson Creek bridge to The Stands Drive | 2020-12-18 | 2020-01-15 | 2020-01-15 | 2017-04-20 | 60000 | 183764.15 | 378 | 2020-12-18 | PE CN | #N/A
1500383 | R-38348 | Seymour | Monroe | Bloomington | N/A | Bloomington | Sidepath construction on Winslow Rd from Henderson St to S Highland Ave | 2020-12-18 | 2020-01-15 | 2020-01-15 | 2017-04-14 | 10954.65 | 82118.63 | 378 | 2020-12-18 | PE CN | #N/A
1500384 | R-38348 | Seymour | Monroe | Bloomington | N/A | Bloomington | Sidepath CN on S Henderson from eastern termini of Black Lumber Trail to Winslow | 2020-12-18 | 2020-01-15 | 2020-01-15 | 2017-04-20 | 30664.22 | 139261.37 | 378 | 2020-12-18 | PE CN | #N/A
1601851 | R-39976 | Seymour | Monroe | Bloomington | Bloomington | Bloomington | W 2nd St/W Bloomfield Rd between S Adams & S Patterson Street | 2020-08-07 | 2019-01-16 | 2019-01-16 | 2017-03-22 | 41876.99 | 75451.35 | 511 | 2020-08-07 | PE CE CN | #N/A
1702967 | B-40887 | Seymour | Morgan | Not Applicable | N/A | Morgan County | Bridge #52 on Egbert Road over Stotts Creek | 2020-10-09 | N/A | 2022-10-13 | 2019-08-16 | 199753.81 | 164300 | 448 | 2020-10-09 | PE | #N/A
1801245 | N/A | Seymour | Monroe | Bloomington | N/A | MPO - Bloomington | Bloomington MPO UPWP for FY 2019-2020 | 2020-12-28 | N/A | N/A | 2018-06-28 | 93864.56 | 61075.13 | 368 | 2020-12-28 | PL | #N/A
1902760 | R-40411 | Seymour | Johnson | Indianapolis | Edinburgh | Edinburgh | State Road 252 | N/A | N/A | 2024-09-11 | 2020-11-17 | 44000 | 44000 | 409 | 2020-11-17 | PE | #N/A
1383066 | R-36943 | Vincennes | Vanderburgh | Evansville (KY) | Evansville | Evansville | Washington Ave at 2nd Street and 2nd Street at Parrott St/Jefferson St | 2020-11-27 | 2019-12-11 | 2019-12-11 | 2014-08-18 | 45264.26 | 73078.11 | 399 | 2021-10-26 | PE ROW CN | 93528
Formulas:
Target Letting Date = VLOOKUP([Des],Data2,5,FALSE)

## PED's next 9 months
Des | Contract | INDOT District | County | FMIS Urban Area | City Boundary | Sponsoring Organization | Project Description | Performance End Date | Federal Amount | Expenditure Amount | Balance Remaining | PO Unliquidated Amount | PO Phase | PCO Task ID
1500241 | PLC-38263 | Crawfordsville | Hendricks | Not Applicable | N/A | Hendricks County | PLC-38263 DES 1500241 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Hendricks County Crawfordsville District | 2022-04-30 | 321040.52 | 317053.33 | 3987.19 | 3987.19 | PE | #N/A
1500231 | PLC-38261 | Crawfordsville | Clinton | Not Applicable | N/A | Clinton County | PLC-38261 DES 1500231 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Clinton County Crawfordsville District | 2022-05-31 | 248006.4 | 219458.75 | 28547.65 | 28547.65 | PE | #N/A
1500232 | PLC-38262 | Crawfordsville | Fountain | Not Applicable | N/A | Fountain County | PLC-38262 DES 1500232 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Fountain County Crawfordsville District | 2022-06-30 | 364788.31 | 336822.1 | 27966.21 | 27966.21 | PE | #N/A
1600821 | R-39860 | Crawfordsville | Parke | Not Applicable | Rockville | Rockville | R-39860 DES 1600821 Road Reconstruction (3R/4R Standards) on ST1010 S Market Street in Parke County Crawfordsville District | 2022-06-30 | 444400 | 335312.8 | 109087.2 | 95784.49 | PE | #N/A
1801323 | N/A | Crawfordsville | Tippecanoe | Lafayette - West Lafayette | N/A | MPO - Lafayette | - DES 1801323 Other Type Project (Miscellaneous) on MSUPWP Lafayette MPO Unified Work Program UPWP PL for FY 2019-2020 in Tippecanoe County Crawfordsville District | 2022-06-30 | 676444 | 482988.98 | 193455.02 | 815 | PL | #N/A
1801364 | N/A | Crawfordsville | Vigo | Terre Haute | N/A | MPO - Terre Haute | - DES 1801364 Other Type Project (Miscellaneous) on MSUPWP Terre Haute MPO Unified Work Program UPWP PL & HSIP for FY 2019-2020 in Vigo County Crawfordsville District | 2022-06-30 | 557416 | 496257.8 | 61158.2 | 61158.2 | PL | #N/A
1592883 | N/A | Fort Wayne | Blackford | Not Applicable | N/A | Blackford County | - DES 1592883 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Blackford County Fort Wayne District | 2022-05-31 | 115564 | 108850.34 | 6713.66 | 6713.66 | PE | #N/A
1005734 | R-34132 | Fort Wayne | Elkhart | Elkhart - Goshen | Goshen | Goshen | R-34132 DES 1005734 New Road Construction on ST1001 South Link Rd (Waterford Mills Pkwy) frm SR 15 to Regent St in Elkhart County Fort Wayne District | 2022-06-30 | 3776506.89 | 3776506.89 | 0 | 28311.9 | CE CN | #N/A
1592939 | N/A | Fort Wayne | Various | Not Applicable | N/A | Wabash County | - DES 1592939 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Wabash County Fort Wayne District | 2022-06-30 | 326563.56 | 287438.76 | 78249.6 | 30650.06 | PE | #N/A
1500285 | N/A | Greenfield | Jay | Not Applicable | N/A | Jay County | - DES 1500285 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2017-2020 in Jay County Greenfield District | 2022-04-29 | 284033.4 | 283470.2 | 563.2 | 563.2 | PE | #N/A
1500282 | N/A | Greenfield | Hancock | Not Applicable | N/A | Hancock County | - DES 1500282 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Hancock County Greenfield District | 2022-06-30 | 232639 | 211020.3 | 21618.7 | 21618.7 | PE | #N/A
1500293 | N/A | Greenfield | Various | Not Applicable | N/A | Wayne County | - DES 1500293 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Wayne County Greenfield District | 2022-06-30 | 496084.41 | 478716 | 17368.41 | 17368.41 | PE | #N/A
1801218 | N/A | Greenfield | Madison | Anderson | N/A | MPO - Anderson | - DES 1801218 Other Type Project (Miscellaneous) on MSUPWP Anderson MPO UPWP for FY 2019-2020 in Madison County Greenfield District | 2022-06-30 | 1244730 | 1227341.57 | 62388.43 | 3299.45 | PL | #N/A
1801325 | N/A | Greenfield | Delaware | Muncie | N/A | MPO - Muncie | - DES 1801325 Other Type Project (Miscellaneous) on MSUPWP Delaware-Muncie MPO Unified Work Program UPWP PL & STBG for FY 2019-2020 in Delaware County Greenfield District | 2022-06-30 | 561774 | 499259.47 | 62514.53 | 62514.53 | PL | #N/A
1382657 | R-36384 | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | Chesterton | Chesterton | R-36384 DES 1382657 Bike/Pedestrian Facilities on SPBIKE Westchester-Liberty Trail Phase 2 in Porter County LaPorte District | 2022-04-05 | 684766.05 | 641655.99 | 43110.06 | 3118.01 | PE ROW CE CN | #N/A
1592163 | N/A | LaPorte | Porter | Not Applicable | N/A | Porter County | - DES 1592163 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Porter County LaPorte District | 2022-05-31 | 299629.54 | 276013.36 | 23616.18 | 23616.18 | PE | #N/A
1601151 | N/A | LaPorte | Lake | Chicago - Northwestern Indiana (IL) | Crown Point | Crown Point | - DES 1601151 Other Type Project (Miscellaneous) on VA1042 Purchase E-85 Fuel in Lake County LaPorte District | 2022-06-30 | 136100.92 | 67112.46 | 68988.46 | 24940.16 | PE | #N/A
1801359 | N/A | LaPorte | Porter | Chicago - Northwestern Indiana (IL) | N/A | MPO - Northwest | - DES 1801359 Other Type Project (Miscellaneous) on MSUPWP NIRPC MPO Unified Work Program UPWP PL STBG and CMAQ for FY 2019-2020 in Various County LaPorte District | 2022-06-30 | 3246451 | 2609456.78 | 636994.22 | 636992.65 | PL | #N/A
1801362 | N/A | LaPorte | Elkhart | South Bend (MI) | N/A | MPO - South Bend / Elkhart | - DES 1801362 Other Type Project (Miscellaneous) on MSUPWP MACOG MPO Unified Work Program CMAQ STBG & HSIP for FY 2019-2020 in Various County LaPorte District | 2022-06-30 | 2208578 | 2208577.79 | 30600.21 | 28617.41 | PL | #N/A
2001566 | N/A | Multiple Districts | Various | Not Applicable | N/A | Indiana Department of Transportation | - DES 2001566 Bike/Pedestrian Facilities on VA1027 SRTS Statewide campaign - promote pedestrian & bicycle safety in Various County Multiple Districts District | 2022-05-28 | 2487781.68 | 664317.66 | 1823464.02 | 1584404.02 | CN | #N/A
1500201 | PLC-38171 | Seymour | Clark | Not Applicable | N/A | Clark County | PLC-38171 DES 1500201 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Clark County Seymour District | 2022-04-30 | 254206.11 | 244740.22 | 9465.89 | 9465.89 | PE | #N/A
1500192 | PLC-38169 | Seymour | Bartholomew | Not Applicable | N/A | Bartholomew County | PLC-38169 DES 1500192 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Bartholomew County Seymour District | 2022-05-31 | 428274.52 | 413280.84 | 14993.68 | 14993.68 | PE | #N/A
1500215 | PLC-38185 | Seymour | Switzerland | Not Applicable | N/A | Switzerland County | PLC-38185 DES 1500215 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Switzerland County Seymour District | 2022-05-31 | 88899.07 | 87737.47 | 1161.6 | 1161.6 | PE | #N/A
1382874 | R-37105 | Seymour | Brown | Not Applicable | N/A | Brown County | R-37105 DES 1382874 Bike/Pedestrian Facilities on VAVARI Salt Creek Trail - Phases 2 & 3 in Brown County Seymour District | 2022-06-30 | 396240 | 237420 | 158820 | 40820 | PE ROW | #N/A
1703018 | B-40891 | Seymour | Jackson | Not Applicable | N/A | Jackson County | B-40891 DES 1703018 Bridge Replacement on IR1009 Bridge #197-CR 100S over McHargue Ditch .01 mile East of CR 500W in Jackson County Seymour District | 2022-06-30 | 200501.6 | 35759.21 | 164742.39 | 162276.55 | PE | #N/A
1801245 | N/A | Seymour | Monroe | Bloomington | N/A | MPO - Bloomington | - DES 1801245 Other Type Project (Miscellaneous) on MSUPWP Bloomington MPO UPWP for FY 2019-2020 in Monroe County Seymour District | 2022-06-30 | 545584 | 451719.44 | 93864.56 | 61075.13 | PL | #N/A
1802805 | R-41802 | Seymour | Clark | Louisville (KY)-IN | N/A | Clark County | R-41802 DES 1802805 Intersection Improvement Roundabout on IR1047 CR 403 and Stacy Road Intersection Improvement in Clark County Seymour District | 2022-06-30 | 283500 | 189651.11 | 93848.89 | 93848.89 | PE | #N/A
1593001 | N/A | Vincennes | Posey | Not Applicable | N/A | Posey County | - DES 1593001 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Posey County Vincennes District | 2022-04-30 | 381166.29 | 356311.22 | 24855.07 | 5146.41 | PE | #N/A
1592994 | N/A | Vincennes | Orange | Not Applicable | N/A | Orange County | - DES 1592994 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Orange County Vincennes District | 2022-05-31 | 346677.6 | 309745.82 | 36931.78 | 36931.78 | PE | #N/A
1592992 | N/A | Vincennes | Lawrence | Not Applicable | N/A | Lawrence County | - DES 1592992 Bridge Inspections on VAVARI Countywide Bridge Inspection and Inventory Program for Cycle Years 2018-2021 in Lawrence County Vincennes District | 2022-06-30 | 261080.8 | 237004.04 | 24076.76 | 24076.76 | PE | #N/A

## Data
Des # | Task Id | Task Owner | Des | County Desc | City Boundary | Sponsoring Organization | Target Letting Date | Phase
1383066 | 93528 |  | 0000010 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2000-03-21
1383066 | 93527 |  | 0000020 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2000-02-08
1400818 | 93594 | Stoops, Shannon | 0000120 |  | AI Engineers, Inc. | Indiana Department of Transportation | 2001-03-20
1400995 | 93598 |  | 0000130 |  |  | Indiana Department of Transportation | 2001-03-20
1401015 | 93374 | Nieman, Gerald | 0000140 |  |  | Indiana Department of Transportation | 2001-03-20
1702152 | 93534 |  | 0000150 |  |  | Indiana Department of Transportation | 2001-07-17
1702153 | 93533 |  | 0000160 |  | Archaeology and Geomorphology Services | Indiana Department of Transportation | 2001-05-22
1801295 | 92977 | Nsonwu, Emmanuel | 0000170 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2001-03-20
1802823 | 93595 | Marsischky, Cheri | 0000180 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2001-03-20
1802944 | 93446 | Greene, Jeremy | 0000190 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2001-05-22
1802944 | 93445 | Greene, Jeremy | 0000200 |  |  | Indiana Department of Transportation | 2001-05-22
2001050 | 93592 |  | 0000210 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0000220 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0000230 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2001-04-24
|  |  | 0000240 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0000250 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0000260 | Elkhart |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
ROW
RR
UT
|  |  | 0000270 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0000280 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0000290 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0000300 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0000310 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0000320 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2004-05-25 | CE
CN
ROW
UT
|  |  | 0000330 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0000340 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0000350 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2001-05-25
|  |  | 000036R | Spencer |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
RR
UT
|  |  | 0000370 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0000380 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 000038R | Spencer |  | Indiana Department of Transportation | -339679.2083 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0000390 |  | DCD Consulting LLC | Indianapolis | 2001-01-17
|  |  | 0000400 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0000420 | Marion |  | Indiana Department of Transportation | 2000-10-17 | CE
CN
|  |  | 0000430 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0000440 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0000450 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0000490 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0000510 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0000520 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0000540 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0000550 |  | Collier Transport Inc. | Indiana Department of Transportation | 2000-08-15
|  |  | 0000560 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0000580 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0000590 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0000600 |  | H.R. Gray | Indiana Department of Transportation | -339679.2083
|  |  | 0000610 | Marion |  | Indiana Department of Transportation | 2002-04-23 | CE
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
PE
|  |  | 0000620 | Marion |  | South Bend | -339679.2083 | CE
|  |  |  | St. Joseph |  | South Bend | -339679.2083 | CE
CN
PE
|  |  | 0000630 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0000650 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0000660 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0000670 |  | ABt SRBI | Angola | 2002-07-16
|  |  | 0000680 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0000700 |  | H.R. Gray | Indiana Department of Transportation | -339679.2083
|  |  | 0000710 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2004-05-25 | CE
CN
ROW
UT
|  |  | 0000720 | Marion | DCD Consulting LLC | Indianapolis | 2004-07-20 | CE
CN
|  |  | 0000730 | Marion | DCD Consulting LLC | Indianapolis | 2004-07-20 | CE
CN
|  |  | 0000740 | Marion | DCD Consulting LLC | Indianapolis | 2004-07-20 | CE
CN
|  |  | 0000750 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0000760 |  | DCD Consulting LLC | Indiana Department of Transportation | 2012-05-31
|  |  | 0000770 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0000810 | St. Joseph |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
ROW
UT
|  |  | 000081A | Adams | Bidinfo | Indiana Department of Transportation | 2008-05-08 | CE
CN
PE
ROW
|  |  | 0000820 |  |  | Indiana Department of Transportation | 2000-09-12
|  |  | 0000830 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2000-03-21
|  |  | 000083A | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
RR
UT
|  |  | 000083B | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 000083C | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 000083X | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 0000840 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2000-09-12
|  |  | 000084A | Cass | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0000850 |  |  | Indiana Department of Transportation | 2000-06-20
|  |  | 0000860 |  |  | Indiana Department of Transportation | 2000-06-20
|  |  | 0000870 |  |  | Indiana Department of Transportation | 2000-06-20
|  |  | 0000880 |  |  | Indiana Department of Transportation | 2000-06-20
|  |  | 0000910 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0000920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0000930 |  |  | Indiana Department of Transportation | 2000-09-12
|  |  | 0000940 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0000950 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0000960 | Tippecanoe |  | Indiana Department of Transportation | 2001-02-13 | CE
CN
PE
ROW
|  |  | 0001010 | Gibson |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
PE
|  |  |  | Knox |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0001020 |  | CGI | Indiana Department of Transportation | 2002-01-15
|  |  | 0001030 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0001040 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0001050 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0001060 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0001070 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0001080 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0001110 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2004-06-15 | CE
CN
RR
UT
|  |  | 0001130 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0001140 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0001150 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0001160 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
|  |  |  | Porter | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
UT
|  |  | 0001170 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0001180 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0001190 |  | Global Land Surveying, LLC | Indiana Department of Transportation | 2000-12-20
|  |  | 0001200 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
UT
|  |  | 0001210 |  | EcoTec, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0001220 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2000-07-18
|  |  | 0001230 | Spencer | Appraisers, Inc. | Indiana Department of Transportation | 2004-03-23 | CE
CN
UT
|  |  | 0001240 | Cass | Eco Logic, LLC | Logansport | 2001-10-16 | CE
CN
UT
|  |  | 0001250 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
UT
[5 empty] | Bayswater Company, LLC | Indiana Department of Transportation | 2003-03-25
|  |  | 0001260 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2000-12-20 | CE
CN
|  |  | 0001270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0001280 |  |  | Indiana Department of Transportation | 2000-11-21
|  |  | 0001290 |  | Global Land Surveying, LLC | Indiana Department of Transportation | 2000-12-20
|  |  | 0001310 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0001320 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 2000-07-18
|  |  | 0001330 | Spencer | Appraisers, Inc. | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0001340 | Cass | Eco Logic, LLC | Logansport | 2001-10-16 | CE
CN
UT
|  |  | 0001350 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
RR
UT
|  |  | 0001360 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2001-01-17
|  |  | 0001370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0001380 |  |  | Indiana Department of Transportation | 2000-11-21
|  |  | 0001390 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0001410 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0001420 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0001430 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
UT
|  |  | 0001440 | Cass | Eco Logic, LLC | Logansport | 2001-10-16 | CE
CN
UT
|  |  | 0001470 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0001480 | Scott |  | Indiana Department of Transportation | 2005-01-19 | ROW
|  |  | 0001490 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0001500 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0001510 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0001520 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2000-08-15
|  |  | 0001530 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
UT
|  |  | 0001540 | Cass | Eco Logic, LLC | Logansport | 2001-10-16 | CE
CN
UT
|  |  | 0001550 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2001-06-19
|  |  | 0001560 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | 2000-11-21
|  |  | 0001570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0001580 |  | Casteel Real Estate | Indiana Department of Transportation | 2001-05-22
|  |  | 0001610 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0001620 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2000-08-15
|  |  | 0001630 | Clark |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
PE
|  |  | 0001640 | Cass | Eco Logic, LLC | Logansport | 2001-10-16 | CE
CN
UT
|  |  | 0001650 |  |  | Indiana Department of Transportation | 2000-10-16
|  |  | 0001660 | Clark |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
PE
ROW
UT
|  |  | 0001670 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0001690 |  | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 2001-05-22
|  |  | 0001710 | Clinton |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
ROW
UT
|  |  | 0001720 | Lake |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
PE
ROW
|  |  | 0001730 |  | Debbie L. Morris | Indiana Department of Transportation | 2001-11-20
|  |  | 0001740 | Cass | Eco Logic, LLC | Logansport | 2001-10-16 | CE
CN
UT
|  |  | 0001750 |  | CGI | Indiana Department of Transportation | 2001-02-13
|  |  | 0001770 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0001780 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0001800 | Boone |  | Indiana Department of Transportation | 2001-06-19 | CE
PE
ROW
UT
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
PE
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
ROW
RR
UT
|  |  | 0001810 | Howard | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
UT
|  |  | 0001820 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0001830 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2001-12-19
|  |  | 0001840 |  | Eco Logic, LLC | Indiana Department of Transportation | 2001-10-16
|  |  | 0001850 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0001880 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0001900 | Boone |  | Indiana Department of Transportation | 2001-06-19 | CE
PE
ROW
UT
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
PE
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
ROW
RR
UT
|  |  | 0001910 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2004-03-23 | CE
CN
PE
ROW
RR
UT
|  |  | 0001920 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0001930 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0001940 |  |  | Indiana Department of Natural Resources | 2001-10-16
|  |  | 0001950 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0001960 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | 2001-10-16
|  |  | 0001980 | Marion |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0001990 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2000-09-12 | CE
CN
|  |  | 0002000 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0002010 | Porter |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
UT
|  |  | 0002020 | Marion |  | Indiana Department of Transportation | 2002-04-23 | CE
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
PE
|  |  | 0002030 | Switzerland |  | Indiana Department of Transportation | -339679.2083 | CE
CN
UT
|  |  | 0002040 | Switzerland |  | Indiana Department of Transportation | -339679.2083 | CE
CN
UT
|  |  | 0002050 |  | DCD Consulting LLC |  | 2000-06-20
|  |  | 0002060 |  | DCD Consulting LLC |  | 2000-06-20
|  |  | 0002070 |  | DCD Consulting LLC |  | 2000-06-20
|  |  | 0002080 |  | Carters Appraisal Service | Indiana Department of Transportation | 2000-05-23
|  |  | 0002090 |  | Carters Appraisal Service | Indiana Department of Transportation | 2000-05-23
|  |  | 0002100 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2001-09-11
|  |  | 0002110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0002120 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0002130 |  |  | Indian Heights | 2001-02-13
|  |  | 0002140 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0002150 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2000-09-12
|  |  | 0002160 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0002170 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0002210 | Henry |  | Indiana Department of Transportation | 2007-07-25 | CE
CN
PE
ROW
|  |  | 0002220 | Spencer |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
PE
ROW
UT
|  |  | 0002230 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-07-17
|  |  | 0002240 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0002250 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0002260 | Lake |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
UT
|  |  | 0002270 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2001-04-24
|  |  | 0002280 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2001-05-22
|  |  | 0002290 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0002300 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2001-05-22
|  |  | 0002310 | Henry |  | Indiana Department of Transportation | 2007-07-25 | CE
CN
PE
ROW
|  |  | 0002320 | Spencer |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0002340 | Ripley | ARCADIS | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0002350 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0002360 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0002380 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2001-05-22 | CE
CN
|  |  | 0002390 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0002400 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0002410 | Daviess |  | Indiana Department of Transportation | 2007-04-04 | CE
CN
PE
ROW
UT
|  |  | 0002440 | Ripley | ARCADIS | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0002450 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2001-07-17
|  |  | 0002460 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2001-11-20
|  |  | 0002480 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2001-05-22 | CE
CN
|  |  | 0002490 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0002500 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0002510 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 000253A | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
ROW
UT
|  |  | 000253X | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
ROW
UT
|  |  | 0002540 | Ripley | ARCADIS | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0002550 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0002560 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0002580 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2001-05-22 | CE
CN
|  |  | 0002590 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 000259A | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
|  |  | 0002600 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0002610 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2010-02-10 | RR
|  |  | 0002620 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2001-05-22
|  |  | 0002640 | Boone |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
UT
|  |  | 0002660 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0002690 | Lawrence |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0002700 | St. Joseph |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
|  |  | 0002710 | Hamilton |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
ROW
UT
|  |  | 0002720 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0002740 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-01-17
|  |  | 0002790 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2007-07-25 | CE
CN
|  |  | 0002800 | Howard |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0002810 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0002820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0002830 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0002840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0002890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0002900 | Howard |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0002910 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0002930 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0002940 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0002980 |  |  | Indiana Department of Transportation | 2001-05-25
|  |  | 0003010 | Elkhart |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0003030 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2001-10-16
|  |  | 0003040 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0003080 | Porter |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0003110 | Elkhart |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0003130 |  | B. L. A., Inc. | Indiana Department of Transportation | 2001-06-19
|  |  | 0003150 | Porter |  | Indiana Department of Transportation | 2002-01-15 | CE
CN
|  |  | 0003190 | Sullivan |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
PE
|  |  | 0003210 | Elkhart |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0003220 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2001-03-20 | CN
|  |  | 0003230 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0003240 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0003250 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0003290 | Cass | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2008-07-16 | CE
CN
PE
ROW
|  |  | 0003310 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0003320 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0003330 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0003340 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0003350 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0003390 | Vigo |  | Indiana Department of Transportation | 2008-05-07 | CE
CN
PE
ROW
RR
UT
|  |  | 0003400 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2008-05-07 | CE
CN
PE
ROW
RR
UT
|  |  | 0003410 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0003420 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0003430 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0003490 | Vigo |  | Indiana Department of Transportation | 2008-05-07 | CE
CN
PE
ROW
RR
UT
|  |  | 0003500 | Bartholomew |  | Indiana Department of Transportation | 2006-09-13 | CE
CN
PE
ROW
|  |  | 0003510 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0003520 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0003540 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0003590 | Grant |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
ROW
UT
|  |  | 0003600 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2007-08-22 | CE
CN
PE
ROW
|  |  | 0003610 | Dubois |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0003620 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0003690 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
ROW
UT
|  |  | 0003700 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2009-06-24 | CN
PE
ROW
|  |  | 0003710 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0003720 | Monroe |  | Indiana Department of Transportation | 2001-10-16 | CE
CN
PE
ROW
UT
|  |  | 0003790 | Vanderburgh |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
PE
UT
|  |  | 0003810 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0003820 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0003850 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0003910 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0003940 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0004010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0004110 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0004120 | Dubois |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
ROW
UT
|  |  |  | Spencer |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
PE
ROW
UT
|  |  | 0004130 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0004140 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0004150 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0004190 | Monroe |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
RR
UT
|  |  | 0005650 | St. Joseph |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0006371 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0006372 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0006610 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
ROW
UT
|  |  |  | Hancock | CPS Acquisitions, LLC | Indiana Department of Transportation | 2008-02-27 | CE
CN
ROW
|  |  | 0006620 | Hamilton |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
ROW
UT
|  |  |  | Hancock |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
ROW
|  |  | 0006630 | Hamilton |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
ROW
UT
|  |  |  | Hancock |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
ROW
|  |  | 0006640 | Hamilton | CGI | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
ROW
UT
|  |  |  | Hancock | CGI | Indiana Department of Transportation | 2008-02-27 | CE
CN
ROW
|  |  | 0006741 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0006742 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0006743 | Hancock |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 000771A |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 000771B |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 000771C |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 000771X |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0008950 | Hendricks | Franklin Property Matters, LLC. | Indiana Department of Transportation | 2009-05-27 | CE
CN
|  |  |  | Morgan | Franklin Property Matters, LLC. | Indiana Department of Transportation | 2009-05-27 | CE
CN
|  |  | 0010000 |  | Holloway Engineering, LLC | Peru | -339679.2083
|  |  | 0010010 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0010020 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0010510 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2000-08-15 | CE
CN
|  |  | 0010520 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2006-10-18 | CE
CN
|  |  | 0010530 | Hamilton | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0010540 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0010550 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0010560 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0010710 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0010720 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2000-11-21
|  |  | 0010730 |  | Gensic Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0010740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0010750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0010760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0010770 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0010780 |  |  | Indiana Department of Transportation | 2002-10-22
|  |  | 0010790 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0010800 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2002-02-19
|  |  | 0010810 |  | Hanson Professional Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0010820 |  | Hanson Professional Services, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0010830 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0010840 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0010850 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0010860 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0010870 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2002-02-19
|  |  | 0010880 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0010890 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2002-02-19
|  |  | 0010900 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2002-02-19
|  |  | 0010910 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2002-02-19
|  |  | 0010920 |  | Hanson Professional Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0010930 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0010950 |  |  | Indiana Department of Transportation | 2000-03-21
|  |  | 0010960 |  |  | Indiana Department of Transportation | 2000-03-21
|  |  | 0010980 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2000-03-21
|  |  | 0010990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011080 | Various | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0011090 |  | AES Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011100 | Various | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0011110 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
ROW
UT
[6 empty] | Indiana Department of Transportation | 2011-02-23
|  |  | 0011111 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
ROW
UT
|  |  | 0011112 | Washington | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2011-02-23 | CE
CN
ROW
UT
|  |  | 0011113 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011140 | Steuben |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
PE
ROW
|  |  | 0011150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011170 | Steuben |  | Indiana Department of Transportation | 2013-05-25 | CN
PE
|  |  | 0011210 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0011230 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011250 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011270 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011280 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011290 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0011300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011310 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011320 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2002-06-18
|  |  | 0011330 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0011340 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0011350 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0011360 |  | Hambleton LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0011370 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011380 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-07-15
|  |  | 0011390 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011400 | Owen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0011410 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0011420 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0011430 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011440 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011450 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011460 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011470 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011480 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0011490 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011500 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011510 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011520 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011530 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011540 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011550 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011560 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011570 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011580 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011590 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011600 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011610 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011620 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011630 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011640 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2005-03-16
|  |  | 0011650 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2005-03-16
|  |  | 0011660 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2005-03-16
|  |  | 0011670 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2005-03-16
|  |  | 0011680 |  | Hambleton LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0011690 |  | Hambleton LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0011700 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0011710 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0011720 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0011730 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0011740 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0011750 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0011760 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0011770 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0011780 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0011790 | Huntington |  | Indiana Department of Transportation | 2002-05-21 | CE
CN
|  |  |  | Wabash |  | Indiana Department of Transportation | 2002-05-21 | CE
CN
|  |  | 0011800 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
ROW
RR
UT
|  |  | 0011810 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0011820 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0011830 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2007-11-28 | CE
CN
PE
ROW
RR
[5 empty] | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0011840 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | 2006-05-24 | CE
CN
PE
ROW
RR
UT
|  |  | 0011850 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011870 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011880 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011890 | Jennings |  | Jennings County | 2007-04-04 | CE
CN
PE
|  |  | 0011900 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0011920 |  | DCD Consulting LLC | Indiana Department of Transportation | 2000-03-13
|  |  | 0011930 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0011940 |  |  | Indiana Department of Transportation | 2010-05-20
|  |  | 0011950 | Grant |  | Indiana Department of Transportation | 2009-06-24 | CN
PE
ROW
|  |  | 0011960 | Allen |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  | 0011970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0011980 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0011990 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0012010 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2000-12-20
|  |  | 0012020 |  | IXOYE, Limited | Indiana Department of Transportation | 2001-05-22
|  |  | 0012030 |  | Indiana Connect - a Joint Venture | Indiana Department of Transportation | 2001-01-17
|  |  | 0012040 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0012050 |  | GS-IN P.C. | Indiana Department of Transportation | 2001-03-20
|  |  | 0012060 | Howard |  | Indiana Department of Transportation | 2001-01-17 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2001-01-17 | CE
CN
|  |  | 0012070 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0012080 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2000-12-20
|  |  | 0012090 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0012100 |  |  | Jefferson County | 2010-01-13
|  |  | 0012110 | Sullivan |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
PE
|  |  | 0012120 | Sullivan |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
PE
|  |  | 0012210 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2007-05-02
|  |  | 0012220 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2000-03-21 | CE
CN
|  |  | 0012230 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2000-03-21 | CE
CN
|  |  | 0012240 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2000-07-18
|  |  | 0012250 |  |  | Indiana Department of Transportation | 2000-06-20
|  |  | 0012260 |  |  | Indiana Department of Transportation | 2000-07-18
|  |  | 0012270 |  | DCD Consulting LLC | Indiana Department of Transportation | 2000-09-12
|  |  | 0012280 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0012290 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0012310 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0012320 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0012330 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2000-10-17
|  |  | 0012340 | Boone |  | Indiana Department of Transportation | 2001-07-17 | CE
CN
|  |  | 0012350 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0012360 |  | Meca Engineering Corporation of America Incorporated | Indiana Department of Transportation | 2001-04-24
|  |  | 0012370 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0012380 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0012390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012400 | Allen |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0012410 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2001-04-24
|  |  | 0012430 | Miami |  | Indiana Department of Transportation | 2001-09-11 | CE
CN
|  |  | 0012440 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2001-06-19 | CE
CN
|  |  | 0012470 | Porter |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0012480 | Porter |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0012490 | Porter |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0012500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012501 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012510 | Grant |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0012520 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 0012530 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0012540 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0012550 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0012560 | Harrison |  | Indiana Department of Transportation | 2017-01-01 | PE
|  |  |  | Washington |  | Indiana Department of Transportation | 2017-01-01 | PE
|  |  | 0012570 | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0012580 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0012590 | Various |  | Indiana Department of Transportation | 2000-09-12 | CE
CN
|  |  | 0012600 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2008-05-08 | CE
CN
PE
ROW
RR
|  |  | 0012610 | Benton |  | Indiana Department of Transportation | 2004-12-14 | CE
CN
PE
|  |  | 0012620 | Benton |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
PE
|  |  | 0012630 | Boone |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0012640 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0012650 | Tippecanoe |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  | 0012660 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0012670 | Benton |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
PE
ROW
|  |  | 0012680 | White |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0012690 | Putnam | Bayswater Company, LLC | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0012700 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012720 | Fountain |  | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0012730 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012740 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0012760 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
ROW
RR
UT
|  |  | 0012770 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
ROW
RR
UT
|  |  | 0012800 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0012810 | Benton | CDM Smith, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
RR
|  |  | 0012820 | Vigo |  | Indiana Department of Transportation | 2008-03-26 | CE
CN
PE
|  |  | 0012830 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2002-06-18
|  |  | 0012840 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0012850 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0012860 | Parke |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0012870 | Hendricks |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
PE
ROW
UT
|  |  | 0012880 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012890 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2008-02-06 | CE
CN
PE
ROW
|  |  | 0012900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012910 | Vigo |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 0012920 | White |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0012930 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0012940 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0012950 | Tippecanoe |  | Indiana Department of Transportation | 2015-10-07 | PE
|  |  | 0013020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013030 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2003-02-18 | CE
CN
|  |  | 0013040 | Grant |  | Indiana Department of Transportation | 2003-02-18 | CE
CN
RR
|  |  | 0013050 | Grant |  | Indiana Department of Transportation | 2003-02-18 | CE
CN
RR
|  |  | 0013080 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | CE
CN
UT
|  |  | 0013090 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0013100 | Adams |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
|  |  | 0013110 | Steuben | ABt SRBI | Indiana Department of Transportation | 2008-07-09 | CE
CN
PE
ROW
|  |  | 0013120 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2008-05-08 | CE
CN
PE
ROW
|  |  | 0013130 | Adams |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
ROW
|  |  | 0013140 | Grant |  | Indiana Department of Transportation | 2007-05-31 | CE
CN
ROW
|  |  | 0013150 | Allen |  | Indiana Department of Transportation | 2006-12-13 | CE
CN
PE
ROW
|  |  | 0013160 | Blackford |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
PE
ROW
|  |  | 0013170 | Wells |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
|  |  | 0013180 | Elkhart |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
PE
ROW
|  |  | 0013190 | Allen |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
|  |  | 0013200 | Elkhart |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
|  |  | 0013210 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2016-11-02 | PE
|  |  | 0013490 | Grant | CGS Real Estate Services, LLC | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
UT
|  |  | 0013500 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2008-05-08 | CE
CN
ROW
|  |  | 0013510 | Delaware |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0013520 | Delaware |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0013530 | Delaware |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0013540 | Delaware |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0013550 | Delaware |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0013560 | Delaware |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0013570 | Delaware |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
RR
|  |  | 0013580 | Franklin |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0013590 | Shelby |  | Indiana Department of Transportation | 2002-06-18 | CE
CN
|  |  | 0013600 | Henry |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  | 0013610 | Wayne |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  | 0013620 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0013630 | Madison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
UT
|  |  | 0013640 | Hamilton | AECOM USA, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
RR
|  |  |  | Tipton | AECOM USA, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0013650 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0013660 | Union |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
PE
ROW
UT
|  |  | 0013670 | Hancock |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0013680 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0013690 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2008-09-04 | CE
CN
PE
ROW
UT
|  |  | 0013700 | Madison |  | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
|  |  | 0013710 | Carroll |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Howard |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0013720 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0013730 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013740 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0013750 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2009-07-15 | CE
CN
PE
ROW
RR
UT
|  |  | 0013760 | Tipton |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
PE
ROW
RR
|  |  | 0013770 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2012-02-08 | PE
ROW
RR
|  |  | 0013780 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013790 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
|  |  | 0013800 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013810 | Randolph |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  | 0013820 | Henry | Debbie Mann Consulting, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 0013830 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013840 | Delaware |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
|  |  | 0013850 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0013860 | Jay | IXOYE, Limited | Indiana Department of Transportation | 2008-07-16 | CE
CN
PE
ROW
RR
UT
|  |  | 0013870 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 0013880 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0013890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013910 | Howard |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0013920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013930 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013940 | Hamilton |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
ROW
UT
|  |  |  | Hancock |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
ROW
|  |  | 0013950 | Wayne |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
PE
|  |  | 0013960 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0013980 | Jay |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0014000 | Delaware |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  |  | Grant |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
ROW
|  |  | 0014010 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 0014020 | Randolph |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0014030 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0014050 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2016-03-11 | PE
ROW
|  |  | 0014060 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2012-05-11 | CE
CN
PE
ROW
RR
|  |  | 0014070 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | CN
PE
ROW
|  |  | 0014080 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CE
CN
ROW
UT
|  |  | 0014090 | Porter |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
PE
|  |  | 0014100 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014110 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014120 | LaPorte |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
PE
ROW
|  |  | 0014130 | Lake | Karen | Indiana Department of Transportation | 2009-04-22 | CE
CN
PE
|  |  | 0014140 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0014150 |  | Hanson Professional Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0014160 |  | Civil Engineering Consultants | Indiana Department of Transportation | -339679.2083
|  |  | 0014170 |  | Independent Appraisers-Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0014180 | Lake | Karen | Indiana Department of Transportation | 2003-01-22 | CE
CN
RR
|  |  | 0014190 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0014200 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0014210 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2012-11-20 | CE
CN
PE
ROW
RR
UT
|  |  | 0014220 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0014230 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014240 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0014250 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0014260 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0014270 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0014280 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014360 | Lake |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0014370 | Lake |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0014380 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
UT
[5 empty] | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2011-12-14
|  |  | 0014390 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0014400 | LaPorte |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
PE
|  |  | 0014410 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2001-10-16 | CE
CN
|  |  | 0014420 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2001-10-16 | CE
CN
|  |  | 0014430 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2001-07-17
|  |  | 0014440 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2000-12-20 | CE
CN
|  |  | 0014450 | LaPorte |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0014460 | Fulton | InfoTech | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
ROW
|  |  | 0014470 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014500 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
ROW
UT
|  |  | 0014510 | Porter |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0014520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014530 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014550 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014560 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014600 | Bartholomew |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
PE
ROW
UT
|  |  | 0014610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014640 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
ROW
UT
|  |  | 0014650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014660 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014670 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014680 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0014690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014700 | Franklin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014710 | Jackson |  | Indiana Department of Transportation | 2016-11-02 | PE
[6 empty] | Indiana Department of Transportation | 2016-11-02
|  |  | 0014720 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014730 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0014740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014750 | Bartholomew |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
ROW
|  |  | 0014760 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014770 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014780 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
|  |  | 0014790 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014800 | Brown |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Monroe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014810 | Jennings |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014820 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  |  | Jackson | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014850 | Bartholomew |  | Indiana Department of Transportation | 2013-12-11 | PE
|  |  | 0014860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014870 | Scott |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
PE
ROW
UT
|  |  | 0014890 | Greene |  | Indiana Department of Transportation | 2016-04-08 | PE
ROW
[6 empty] | Indiana Department of Transportation | 2016-04-08
|  |  | 0014900 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0014920 | Dubois |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0014960 | Daviess |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0014970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0014980 | Knox |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
UT
|  |  | 0014990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0015000 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2025-05-31 | PE
ROW
UT
|  |  | 0015010 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2003-03-25 | CE
CN
RR
|  |  | 0015020 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
ROW
RR
UT
|  |  | 0015030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0015040 | Spencer |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
PE
ROW
UT
|  |  | 0015050 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0015070 | Knox | AV Consulting Engineers, Inc. | Indiana Department of Transportation | 2017-02-11 | PE
|  |  | 0015090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0015100 | Martin | EcoTec, Inc. | Indiana Department of Transportation | 2014-08-06 | PE
|  |  | 0015110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0015120 | Greene | LFR, Inc. | Indiana Department of Transportation | 2002-10-22 | CE
CN
|  |  | 0015140 | Boone |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
PE
|  |  | 0015810 | Newton |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015820 | Jasper |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015830 |  |  | Indiana Department of Transportation | 2010-05-19
|  |  | 0015840 | Jasper |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015850 | Madison | Duneland Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015860 | Lake |  | Indiana Department of Transportation | 2007-03-21 | RR
|  |  | 0015870 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015880 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0015890 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015900 | Orange |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015910 | Spencer |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015920 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0015930 | Ripley |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015940 | Ripley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0015950 | Jennings |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0015960 | Jackson |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0015970 | Daviess |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0015980 | Hancock |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0015990 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016000 | Porter |  | Indiana State Agencies | -339679.2083 | RR
|  |  | 0016010 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016020 | Lake |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0016030 | Porter |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0016040 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0016050 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0016060 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0016070 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0016080 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016090 | White |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016100 | Vermillion |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016110 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016120 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016130 | Greene | Dan Moore Real Estate Services, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016140 | Madison |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016150 | Madison |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016160 | Blackford |  | Indiana State Agencies | -339679.2083 | PE
RR
|  |  | 0016170 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016180 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016190 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016200 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016210 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016220 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016230 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016240 | Huntington | D & D Consulting Services, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016250 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016260 | Whitley |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016270 | Whitley |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016280 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016290 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016300 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016310 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016320 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016330 | Marshall |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016340 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016350 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016360 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016370 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016380 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016390 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016400 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016410 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016420 | Lake |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016430 | Carroll |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016440 | Carroll |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016450 | Carroll |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016460 | Noble |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016470 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016480 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016490 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016500 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016510 | Dekalb | August Mack Environmental, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016520 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016530 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016540 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016550 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016560 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016570 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016580 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016590 | Madison |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016600 | Putnam |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0016610 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016620 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016630 | Lake |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016640 | Lake |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016650 | Gibson |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016660 | Blackford |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016670 | Henry |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016680 | Henry |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016690 | Henry |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0016700 | Hancock | CTLGroup | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0016710 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0016810 | Various |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0016820 | Various |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0016830 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 0016840 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2001-02-13 | CE
CN
|  |  | 0016850 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0016860 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0016870 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0016880 |  | HE-BFS, LLC | Indiana Department of Transportation | 2001-02-13
|  |  | 0016890 |  | ABt SRBI | Indiana Department of Transportation | 2001-06-19
|  |  | 0016900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0017010 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017020 | Vermillion |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  |  | Warren |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  | 0017030 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017040 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0017050 | White |  | Indiana Department of Transportation | 2002-02-19 | CN
|  |  | 0017060 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0017070 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017080 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0017090 | Clinton |  | Indiana Department of Transportation | 2001-02-13 | CE
CN
|  |  | 0017100 | Hendricks | GAI Consultants, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0017110 |  | DLZ Indiana, LLC | Indiana Department of Transportation | 2002-02-19
|  |  | 0017120 | Benton |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0017130 | Vermillion |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0017140 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0017150 | Parke |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0017160 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0017170 | Carroll |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0017180 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0017200 | Benton |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0017210 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0017220 |  |  | Indiana Department of Transportation | 2000-09-12
|  |  | 0017230 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0017240 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0017250 |  |  | Indiana Department of Transportation | 2000-11-21
|  |  | 0017260 |  | CGI | Indiana Department of Transportation | 2000-11-21
|  |  | 0017270 |  | CGI | Indiana Department of Transportation | 2000-11-21
|  |  | 0017310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0017320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0017330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0017340 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0017350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0017370 | Marion |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
|  |  | 0017375 | Marion |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
|  |  | 0017380 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0017410 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0017420 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2001-03-20
|  |  | 0017430 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0017440 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2001-01-17 | CE
CN
|  |  | 0017450 | Marshall |  | Indiana Department of Transportation | 2001-04-24 | CE
CN
|  |  | 0017460 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0017470 | Marshall |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
|  |  | 0017480 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0017485 |  | Eco Logic, LLC | Indiana Department of Transportation | 2001-06-19
|  |  | 0017490 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017500 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017610 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0017620 |  | Duesler Realty House | Indiana Department of Transportation | 2000-12-20
|  |  | 0017630 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0017640 |  | Marine Solutions, Inc. | Indiana Department of Transportation | 2000-12-20
|  |  | 0017650 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0017660 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017670 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017700 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0017710 | Huntington |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0017720 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017730 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0017740 | Adams |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0017750 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-06-19
|  |  | 0017760 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-06-19
|  |  | 0017770 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-06-19
|  |  | 0017810 | Steuben |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0017850 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017860 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0017870 |  | Collier Transport Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0017880 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0017890 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0017900 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0017970 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0017980 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0017990 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0018000 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0018010 | Grant |  | Indiana Department of Transportation | 2002-05-21 | CE
CN
UT
|  |  |  | Madison |  | Indiana Department of Transportation | 2002-05-21 | CE
CN
UT
|  |  | 0018020 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0018030 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0018040 | Hamilton |  | Indiana Department of Transportation | 2001-04-24 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2001-04-24 | CE
CN
|  |  | 0029535 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2000-03-21
|  |  | 0029536 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2000-03-21
|  |  | 0040000 |  | Spire Real Estate Valuation & Advisory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0064410 |  |  | Indiana Department of Transportation | 2000-03-21
|  |  | 0065110 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
PE
PL
UT
|  |  | 0065120 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065130 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065140 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065150 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065160 | Marion |  | Indiana Department of Transportation | 2009-03-11 | CN
PE
PL
ROW
UT
|  |  | 0065170 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065180 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065190 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065200 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065210 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0065300 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28 | PE
ROW
RR
UT
|  |  | 0065400 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0065410 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0065420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0065430 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20 | CE
CN
ROW
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20 | CE
|  |  | 0065440 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0065500 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2000-08-15
|  |  | 0065510 |  | DCD Consulting LLC | Indiana Department of Transportation | 2000-06-20
|  |  | 0065520 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2000-09-12 | CE
CN
|  |  | 0065600 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065610 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065611 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065612 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065613 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065614 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065615 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065616 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065617 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065618 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065619 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065620 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065621 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
UT
|  |  | 0065700 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065710 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065720 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0065730 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065740 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0065750 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0065770 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065780 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065790 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065800 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065810 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065820 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065830 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065840 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065850 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0065860 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065870 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0065880 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065890 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065900 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065910 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065915 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065920 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065925 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065930 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065940 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065950 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0065960 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065970 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
UT
|  |  | 0065971 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065972 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065973 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065974 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065975 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065976 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065977 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065978 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2001-06-19 | CE
CN
|  |  | 0065979 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0065980 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065981 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065982 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065983 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065984 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065985 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0065990 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
UT
|  |  | 0066000 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2001-04-24
|  |  | 0066110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066120 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0066130 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0066131 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0066132 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0066140 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0066145 | Crawford |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
|  |  | 0066160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066510 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0066610 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0066620 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0066630 |  | CGI | Indiana Department of Transportation | 2001-03-20
|  |  | 0066640 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2001-10-16 | CE
CN
|  |  | 0066650 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0066651 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066652 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066653 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066654 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0066710 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0066810 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-01-12 | CE
CN
ROW
|  |  | 0066820 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0066880 | Allen |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
UT
|  |  | 0066890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0067100 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067101 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067102 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067104 |  |  | Indiana Department of Transportation | 2000-07-18
|  |  | 0067109 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0067110 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 0067111 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0067114 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0067117 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0067118 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0067119 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0067120 | Boone |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  |  | Montgomery |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
|  |  | 0067121 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067122 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0067123 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067124 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067125 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067126 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067127 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067200 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067201 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067202 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067203 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067204 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067205 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067206 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2000-05-23
|  |  | 0067207 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067208 |  | Hambleton LLC | Indiana Department of Transportation | 2000-05-23
|  |  | 0067209 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2000-05-23
|  |  | 0067210 |  | ERES International, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0067211 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067212 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067215 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067216 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2000-07-18
|  |  | 0067217 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067218 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067219 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067223 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067300 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067301 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067302 |  | GS-IN P.C. | Indiana Department of Transportation | 2000-07-18
|  |  | 0067303 |  | DCD Consulting LLC | Indiana Department of Transportation | 2000-07-18
|  |  | 0067304 |  | DCD Consulting LLC | Indiana Department of Transportation | 2000-07-18
|  |  | 0067305 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0067306 |  |  | Indiana Department of Transportation | 2000-08-29
|  |  | 0067308 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0067310 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0067311 |  |  | Indiana Department of Transportation | 2001-06-14
|  |  | 0067313 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0067320 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0067322 |  | GS-IN P.C. | Indiana Department of Transportation | 2001-05-22
|  |  | 0067323 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2001-04-24
|  |  | 0067324 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0067330 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0067331 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0067333 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0067400 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067401 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067402 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067403 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067404 |  | Brenner Design Incorporated | Indiana Department of Transportation | 2000-04-18
|  |  | 0067405 |  |  | Indiana Department of Transportation | 2000-07-18
|  |  | 0067408 |  |  | Indiana Department of Transportation | 2000-07-18
|  |  | 0067411 |  | Eco Logic, LLC | Indiana Department of Transportation | 2001-02-13
|  |  | 0067416 |  | Hanson Professional Services, Inc. | Indiana Department of Transportation | 2001-01-17
|  |  | 0067417 |  | Eco Logic, LLC | Indiana Department of Transportation | 2001-04-24
|  |  | 0067418 |  | Consolidated Test Company | Indiana Department of Transportation | 2000-11-21
|  |  | 0067500 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0067501 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0067502 |  | Martin Riley, Inc. | Indiana Department of Transportation | 2000-09-12
|  |  | 0067503 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0067506 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0067507 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0067508 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0067600 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067601 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0067602 |  | HNTB Indiana, Inc. | Indiana Department of Transportation | 2000-05-23
|  |  | 0067603 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2000-05-23
|  |  | 0067604 |  |  | Indiana Department of Transportation | 2000-07-18
|  |  | 0067605 |  | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2000-09-12
|  |  | 0067606 |  |  | Indiana Department of Transportation | 2000-08-15
|  |  | 0067607 |  |  | Indiana Department of Transportation | 2000-11-21
|  |  | 0067608 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 0067609 |  |  | Indiana Department of Transportation | 2000-10-17
|  |  | 006760A |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 006760C |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 006760E |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 006760G |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 006760H |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 006760J |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0067610 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0067611 |  | CGI | Indiana Department of Transportation | 2007-06-06
|  |  | 0081241 | Marion | DCD Consulting LLC | Indianapolis | 2003-12-17 | CE
CN
|  |  | 0081271 | Marion | KERAMIDA Environmental, Inc. | Speedway | 2000-07-18 | CE
CN
|  |  | 0088000 | Owen |  | Owen County | 2000-07-18 | CE
CN
|  |  | 0088020 | Vanderburgh | CGI | Evansville | -339679.2083 | RR
|  |  | 0088030 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0088040 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0088050 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2004-07-20 | CE
CN
|  |  | 0088060 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 0088070 | Vanderburgh |  | Vanderburgh County | 2008-11-19 | CE
CN
PE
UT
|  |  | 0088080 | Vanderburgh | CGI | Evansville | 2008-05-08 | CE
CN
RR
|  |  | 0088090 | Vanderburgh | CGI | Evansville | -339679.2083 | CN
|  |  | 0088100 | Vanderburgh | CGI | Evansville | -339679.2083 | CN
|  |  | 0088110 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0088120 | Marion | DCD Consulting LLC | Indianapolis | 2001-05-22 | CE
CN
|  |  | 0088130 |  | DCD Consulting LLC | Indianapolis | 2001-06-19
|  |  | 0088140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0088150 |  |  | St. Joseph County | -339679.2083
|  |  | 0088160 |  |  | St. Joseph County | -339679.2083
|  |  | 0088170 | St. Joseph |  | St. Joseph County | 2007-05-31 | CE
CN
|  |  | 0088180 | Elkhart |  | Goshen | 2006-10-18 | CE
CN
|  |  | 0088190 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2003-03-25 | CE
CN
|  |  | 0088200 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2001-07-17 | CE
CN
|  |  | 0088210 | Clark |  | Clarksville | 2001-12-19 | CE
CN
|  |  | 0088220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0088230 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2002-08-13 | CE
CN
|  |  | 0088240 |  | ASC Group, Inc. | Beech Grove | -339679.2083
|  |  | 0088250 | Marion | ASC Group, Inc. | Beech Grove | 2002-06-18 | CE
CN
|  |  | 0088270 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 0088280 |  |  | Lake County | -339679.2083
|  |  | 0088290 |  |  | Lake County | -339679.2083
|  |  | 0088300 | Greene |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0088310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0088320 | Vigo |  | Vigo County | -339679.2083 | CN
|  |  | 0088330 | Delaware | GS-IN P.C. | Muncie | 2007-01-24 | CE
CN
PE
RR
|  |  | 0088340 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 0088350 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 0088360 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 0088370 | Delaware | GS-IN P.C. | Muncie | 2006-03-15 | CE
CN
PE
|  |  | 0088380 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0088390 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2007-08-22 | CE
CN
PE
UT
|  |  | 0088400 | Lake | Cornerstone Design | Highland | 2008-08-20 | CE
CN
|  |  | 0088410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0088420 | Benton |  | Benton County | 2005-06-22 | CE
CN
|  |  | 0088430 | Daviess |  | Dubois County | 2006-12-13 | CE
CN
|  |  |  | Dubois |  | Dubois County | 2006-12-13 | CE
CN
UT
|  |  | 0088440 | Franklin |  | Franklin County | 2010-02-24 | CE
CN
|  |  | 0088450 | Franklin | Haas & Associates, L.L.C. | Franklin County | 2006-08-16 | CE
CN
|  |  | 0088460 | Gibson |  | Gibson County | 2009-11-04 | CE
CN
|  |  | 0088470 |  |  | Henry County | -339679.2083
|  |  | 0088480 | Henry |  | Henry County | 2007-08-08 | CE
CN
|  |  | 0088490 | Jennings |  | Jennings County | 2014-08-06 | CE
CN
PE
|  |  | 0088500 | Knox |  | Knox County | 2008-09-04 | CE
CN
RR
|  |  | 0088510 | Madison |  | Madison County | 2005-09-14 | CE
CN
UT
|  |  | 0088520 |  |  | Martin County | -339679.2083
|  |  | 0088530 | Morgan |  | Morgan County | 2008-08-06 | CE
CN
|  |  | 0088540 |  |  | Miami County | -339679.2083
|  |  | 0088550 | Morgan |  | Morgan County | 2003-06-17 | CE
CN
|  |  | 0088560 | Morgan |  | Morgan County | 2005-02-16 | CE
CN
UT
|  |  | 0088570 | Scott |  | Scott County | 2007-09-06 | CE
CN
|  |  | 0088580 | Scott |  | Scott County | 2005-10-19 | CE
CN
|  |  | 0088590 | Tipton |  | Tipton County | 2003-03-25 | CE
CN
|  |  | 0088600 | Vermillion |  | Vermillion County | 2009-10-07 | CE
CN
|  |  | 0088610 | Vermillion |  | Vermillion County | 2009-01-14 | CE
CN
|  |  | 0088620 | Wayne |  | Wayne County | 2004-05-25 | CE
CN
|  |  | 0088630 | Lake | Consolidated Test Company | Lake County | 2002-02-19 | CE
CN
RR
|  |  | 0088640 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0088650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0088660 | Gibson |  | Gibson County | 2008-04-02 | CE
CN
|  |  | 0088670 | Lake |  | Merrillville | 2004-07-20 | CE
CN
ROW
|  |  | 0088680 | Johnson |  | Johnson County | 2006-06-21 | CE
CN
ROW
|  |  | 0088690 |  | CGI | Evansville | 2002-06-18
|  |  | 0088700 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0088710 | Jefferson | Engineering Resources, Inc. | Madison | 2001-04-24 | CE
CN
|  |  | 0088720 | Noble | Debbie L. Morris | Kendallville | 2007-08-22 | CE
CN
PE
RR
UT
|  |  | 0088740 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 0088750 | Kosciusko | McLane Realty, Inc. | Winona Lake | 2007-05-16 | CE
CN
RR
|  |  | 0088760 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 0088770 | Steuben | ABt SRBI | Angola | 2010-04-14 | CE
CN
ROW
|  |  | 0088780 | Wells | Accidental Discoveries, LLC | Bluffton | 2005-05-25 | CE
CN
|  |  | 0088790 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2009-05-06 | CE
CN
PE
ROW
|  |  | 0088800 | Clinton | Carters Appraisal Service | Frankfort | 2011-07-13 | CE
CN
RR
UT
|  |  | 0088810 | Jay | Hydrogeology, Inc. | Portland | 2007-10-17 | CE
CN
RR
|  |  | 0088820 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 0088830 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2004-08-17 | CE
CN
UT
|  |  | 0088840 | Gibson | III FFC | Princeton | 2006-04-19 | CE
CN
|  |  | 0088850 | Dearborn |  | Aurora | 2009-09-10 | CE
CN
[6 empty] | Aurora | 2009-09-10
|  |  | 0088860 | Posey | GRL Engineers, Inc. | Mount Vernon | 2005-05-25 | CE
CN
PE
RR
|  |  | 0088870 | Jennings |  | North Vernon | 2010-01-13 | CE
CN
|  |  | 0088880 |  | JCI Bridge Group, Inc. | Washington County | -339679.2083
|  |  | 0088890 |  | JCI Bridge Group, Inc. | Salem | -339679.2083
|  |  | 0088900 |  |  | Tell City | -339679.2083
|  |  | 0088910 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2000-12-20 | CE
CN
|  |  | 0088920 | Clark |  | Clark County | 2003-05-20 | CE
CN
UT
|  |  | 0088940 | Allen |  | Allen County | 2005-11-16 | CE
CN
PE
|  |  | 0088950 | Rush |  | Rush County | 2004-10-19 | CE
CN
|  |  | 0088970 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0088980 | Warren |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0088990 | Newton |  | Lake County | -339679.2083 | CE
CN
|  |  | 0089000 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0089010 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2001-01-17 | CE
CN
RR
|  |  | 0089020 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0089030 | Allen |  | Fort Wayne | 2007-10-31 | CE
CN
ROW
|  |  | 0089040 | Miami |  | Peru | -339679.2083 | CN
|  |  | 0089050 |  |  | LaPorte County | 2001-06-19
|  |  | 0089060 | LaPorte |  | LaPorte County | 2001-08-14 | CE
CN
|  |  | 0089070 |  |  | LaPorte County | 2002-01-15
|  |  | 0089080 | Delaware | GS-IN P.C. | Muncie | 2003-11-18 | CE
CN
|  |  | 0089090 | Lake | Brenner Design Incorporated | Dyer | 2002-05-21 | CE
CN
|  |  | 0089100 | Marion | DCD Consulting LLC | Indianapolis | 2003-12-17 | CE
CN
|  |  | 0089101 | Marion | DCD Consulting LLC | Indianapolis | 2003-12-17 | CE
CN
|  |  | 0089102 | Marion | DCD Consulting LLC | Indianapolis | 2003-12-17 | CE
CN
|  |  | 0089110 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0089120 | St. Joseph | KZF Design, Inc. | St. Joseph County | 2002-06-18 | CE
CN
|  |  | 0089130 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0089140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0089150 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0089160 | St. Joseph | KZF Design, Inc. | St. Joseph County | 2005-04-20 | CE
CN
|  |  | 0089170 | Elkhart | C Blair Enterprises, Inc. | Elkhart County | 2003-03-25 | CE
CN
|  |  | 0089180 | LaPorte |  | LaPorte County | 2001-08-14 | CE
CN
|  |  | 0089190 |  |  | LaPorte County | 2001-11-20
|  |  | 0089200 | Franklin |  | Franklin County | 2010-05-12 | CE
CN
PE
|  |  | 0089210 |  |  | Miami County | -339679.2083
|  |  | 0089220 |  |  | Aurora | -339679.2083
|  |  | 0089230 | Allen | Global Management Group, Inc. | New Haven | 2004-08-17 | CE
CN
|  |  | 0089240 | Marion | DCD Consulting LLC | Indianapolis | 2002-06-11 | CE
CN
|  |  | 0089250 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2004-03-23 | CE
CN
|  |  | 0089260 | Porter | Huff & Huff, Inc. | Portage | 2007-01-24 | CE
CN
|  |  | 0089270 |  |  | South Bend | -339679.2083
|  |  | 0089280 | Elkhart | C Blair Enterprises, Inc. | Elkhart | -339679.2083 | CE
CN
|  |  | 0089290 | Fulton | 2IM Group, LLC | Akron | 2003-02-18 | CE
CN
|  |  | 0089300 | Hendricks | Horner and Shifrin, Inc. | Plainfield | 2007-02-21 | CN
|  |  | 0089310 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2001-04-24 | CE
CN
|  |  | 0089320 | Hamilton |  | Hamilton County | 2003-07-15 | CE
CN
|  |  | 0089330 | Monroe | Absolute Title Services, LLC | Bloomington | 2003-01-22 | CE
CN
|  |  | 0089340 | Porter |  | Porter County | 2005-07-20 | CE
CN
|  |  | 0089350 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0089360 | Vigo | Bayswater Company, LLC | Terre Haute | -339679.2083 | CE
CN
|  |  | 0089370 |  | Dan Moore Real Estate Services, Inc. | Jasonville | -339679.2083
|  |  | 0089380 | LaGrange | John A. Doyle Associates, Inc. | Shipshewana | 2005-12-14 | CE
CN
|  |  | 0089390 |  | CGI | Evansville | -339679.2083
|  |  | 0089400 | Morgan |  | Morgan County | 2004-02-17 | CE
CN
|  |  | 0089410 |  |  | Crawford County | -339679.2083
|  |  | 0089420 | Owen |  | Owen County | 2004-06-22 | CE
CN
|  |  | 0089430 | Floyd |  | Floyd County | 2005-10-19 | CE
CN
|  |  | 0089440 | Washington | Greenman-Pedersen, Inc. | Washington County | 2006-03-15 | CE
CN
|  |  | 0089450 | Hancock |  | Hancock County | 2005-07-20 | CE
CN
|  |  | 0089460 | Jefferson |  | Jefferson County | 2004-01-21 | CE
CN
|  |  | 0089470 |  |  | Warrick County | -339679.2083
|  |  | 0089480 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CE
CN
|  |  | 0089500 |  |  | St. Joseph County | -339679.2083
|  |  | 0089530 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0089540 | Marion |  | Indianapolis | 2003-10-21 | CE
CN
|  |  | 0089550 | Marion |  | Indianapolis | 2005-01-19 | CE
CN
RR
|  |  | 0089560 |  | DCD Consulting LLC | Indianapolis | 2001-09-11
|  |  | 0089570 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0089580 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0089590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0089600 | Warren | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0089700 |  |  | Indiana Department of Transportation | 2000-11-21
|  |  | 0089710 | Hamilton | Another Test Company | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0089720 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 2000-11-21
|  |  | 0089730 |  |  | Indiana Department of Transportation | 2001-01-17
|  |  | 0089740 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2001-02-13
|  |  | 0089750 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0089760 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-03-20
|  |  | 0089800 | LaPorte |  | LaPorte County | 2001-10-16 | CE
CN
|  |  | 0089810 |  |  | Delaware County | -339679.2083
|  |  | 0089820 | Lake | Compliance Consulting Service, Inc. | Griffith | 2003-11-18 | CE
CN
|  |  | 0089830 |  |  | LaPorte County | -339679.2083
|  |  | 0089840 |  |  | LaPorte County | -339679.2083
|  |  | 0089850 |  |  | LaPorte County | -339679.2083
|  |  | 0089860 |  |  | LaPorte County | -339679.2083
|  |  | 0089870 | Dubois |  | Huntingburg | 2001-03-20 | CE
CN
|  |  | 0089880 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 2001-03-20
|  |  | 0089890 | Dubois |  | Huntingburg | 2001-03-20 | CE
CN
|  |  | 0089900 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2001-05-22 | CE
CN
UT
|  |  | 0089910 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2001-01-17 | CE
CN
RR
|  |  | 0089920 | Randolph |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0090010 | Marion | DCD Consulting LLC | Indianapolis | 2006-02-22 | CE
CN
|  |  | 0090020 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-10-22 | CN
|  |  | 0090030 |  | DCD Consulting LLC | Indianapolis | 2004-03-23
|  |  | 0090040 | Marion | DCD Consulting LLC | Indianapolis | 2001-11-20 | CE
CN
|  |  | 0090050 | Marion | DCD Consulting LLC | Indianapolis | 2004-05-25 | CE
CN
|  |  | 0090060 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0090070 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0090080 | Marion | DCD Consulting LLC | Lawrence | 2003-11-18 | CE
CN
|  |  | 0090100 | Marion | KCI Technologies, Inc. | Southport | 2011-11-16 | CE
CN
PE
|  |  | 0090110 | Marion | DCD Consulting LLC | Southport | 2003-04-22 | CE
CN
|  |  | 0090120 | Johnson | DCD Consulting LLC | Greenwood | 2010-01-13 | CE
CN
|  |  | 0090140 | Hancock |  | Hancock County | 2005-03-16 | CE
CN
PE
ROW
|  |  | 0090150 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0090160 | Lake | Consolidated Test Company | Hammond | 2007-01-24 | CE
CN
RR
|  |  | 0090170 | Lake |  | Lake County | 2007-07-11 | CE
CN
|  |  | 0090180 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0090200 | Lake |  | Hobart | 2002-05-21 | CE
CN
|  |  | 0090210 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2003-04-22 | CE
CN
|  |  | 0090240 | Lake |  | Lake County | 2006-03-15 | CE
CN
|  |  | 0090260 | Lake |  | Lake County | 2012-05-02 | CE
CN
|  |  | 0090270 | Porter |  | Porter County | -339679.2083 | PE
RR
|  |  | 0090280 | Lake |  | Munster | 2009-08-12 | CE
CN
|  |  | 0090290 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2006-03-15 | CE
CN
|  |  | 0090300 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083 | CE
CN
RR
|  |  | 0090310 | Porter |  | Porter County | -339679.2083 | PE
RR
|  |  | 0099000 |  |  | Indiana Department of Transportation | 2000-03-21
|  |  | 0099010 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0099020 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0099030 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0099040 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0099050 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 0099060 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0099070 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 0100001 |  |  | Warrick County | -339679.2083
|  |  | 0100002 | Decatur |  | Decatur County | -339679.2083 | CN
PE
|  |  | 0100003 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0100004 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100005 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100006 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100007 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100008 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100009 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100010 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100011 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100012 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2002-10-08 | CE
CN
PE
ROW
UT
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-10-08 | CE
CN
PE
UT
|  |  | 0100013 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0100014 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0100015 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100016 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0100017 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2002-10-08 | CE
CN
ROW
UT
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-10-08 | CE
CN
|  |  | 0100018 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100019 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100020 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100021 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100022 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100023 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100024 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100025 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100026 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100027 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100028 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100029 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-07-15
|  |  | 0100030 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-07-15
|  |  | 0100031 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-07-15
|  |  | 0100032 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0100033 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0100034 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0100035 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0100036 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0100037 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0100038 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100039 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100040 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0100041 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0100042 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0100043 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0100044 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2006-03-29
|  |  | 0100045 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2006-03-29
|  |  | 0100046 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100047 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100048 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0100049 |  | Duesler Realty House | Indiana Department of Transportation | 2006-02-22
|  |  | 0100050 |  | Duesler Realty House | Indiana Department of Transportation | 2006-02-22
|  |  | 0100051 |  | Hambleton LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0100052 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0100053 |  | Certified Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100054 |  | Certified Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100055 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0100056 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2003-02-18
|  |  | 0100057 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0100058 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2002-09-17
|  |  | 0100059 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100060 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100063 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100064 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100065 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100067 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100068 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100069 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100070 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100071 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100072 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100073 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100074 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100075 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0100076 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0100077 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100078 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100079 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100080 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0100081 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0100082 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100083 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100085 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0100086 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0100087 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0100088 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0100089 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0100090 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0100091 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100092 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100093 | Wayne | Fleis & VandenBrink Engineering, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
ROW
RR
UT
|  |  | 0100094 | Lake |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100095 | Porter | Corn Island Archaeology, LLC | Indiana Department of Transportation | 2007-02-21 | CE
CN
ROW
UT
|  |  | 0100096 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100097 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100098 |  |  | Indiana Department of Transportation | 2002-07-16
|  |  | 0100099 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100101 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100102 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100103 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100104 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2001-04-24
|  |  | 0100105 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100106 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 0100107 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100108 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0100109 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2001-07-17
|  |  | 0100110 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2001-07-17
|  |  | 0100111 | Rush |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 0100112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100113 | Franklin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Rush |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100114 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100115 |  | CGI | Indiana Department of Transportation | 2002-04-23
|  |  | 0100116 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2001-10-16
|  |  | 0100117 | Hendricks |  | Indiana Department of Transportation | 2004-09-14 | ROW
|  |  | 0100118 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2001-04-24
|  |  | 0100120 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100121 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-04-24
|  |  | 0100122 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100123 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100124 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2001-06-19
|  |  | 0100125 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100126 |  | Land Construction Corp | Indiana Department of Transportation | 2001-06-19
|  |  | 0100127 |  | GS-IN P.C. | Indiana Department of Transportation | 2001-08-14
|  |  | 0100128 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-06-19
|  |  | 0100129 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0100130 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0100131 | Randolph |  | Indiana Department of Transportation | 2001-02-13 | CE
CN
|  |  | 0100132 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100133 | White |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100134 | Jackson |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100135 | Lawrence |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100136 | Lawrence |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100137 | Dearborn |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100138 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100139 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100140 | Marshall |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100141 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100142 | Henry |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100143 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100144 | Pike |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100145 | Pike |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100146 | Madison |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100147 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100148 | Wayne |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100149 | Wayne |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0100150 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-01-21 | CE
CN
PE
RR
UT
|  |  | 0100151 | Porter |  | Brown County | 2010-10-06 | CN
[6 empty] | Brown County | 2010-10-06
|  |  | 0100162 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2001-05-22
|  |  | 0100163 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0100164 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100165 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0100166 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100167 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100178 | Boone |  | Indiana Department of Transportation | 2001-06-19 | CE
CN
UT
|  |  | 0100179 | Jay |  | Indiana Department of Transportation | 2001-08-14 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2001-08-14 | CE
CN
|  |  | 0100180 |  |  | Indiana State Agencies | 2001-09-19
|  |  | 0100181 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100185 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100186 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100187 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100188 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100196 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100197 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 0100198 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100199 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100200 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100201 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100202 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2001-10-16
|  |  | 0100203 |  | Richmond | Indiana Department of Transportation | -339679.2083
|  |  | 0100209 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2001-10-16
|  |  | 0100210 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2002-01-15 | CE
CN
|  |  | 0100211 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0100212 | Grant |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Howard |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100213 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0100214 |  | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | 2001-11-20
|  |  | 0100215 | Hamilton |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100216 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100217 | Fayette | EHI Consultants, Inc. | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  |  | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100218 | Henry | EFI Global, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Wayne | EFI Global, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100219 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100220 | Hamilton |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100221 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100222 | Madison |  | Indiana Department of Transportation | 2002-01-15 | CE
CN
UT
|  |  | 0100223 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100226 | Delaware |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100227 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100228 | Randolph |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Wayne |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100229 | Hamilton |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100230 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100233 | Henry |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100234 | Grant |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100235 |  | West Lafayette | Indiana Department of Transportation | -339679.2083
|  |  | 0100239 | Henry | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  |  | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100240 | Henry | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  |  | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100241 | Grant |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100242 | Randolph | Langworthy, Strader, LeBlanc & Associates, Inc. | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  | 0100243 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0100244 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100245 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100246 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100247 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100248 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100249 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100250 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100252 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100253 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2001-04-24
|  |  | 0100254 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
PE
ROW
RR
[5 empty] | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2011-07-13
|  |  | 0100256 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0100269 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0100272 |  |  | Indiana Department of Natural Resources | 2001-07-17
|  |  | 0100273 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100274 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100275 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2001-06-19
|  |  | 0100287 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0100288 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100294 | Tippecanoe |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
RR
UT
|  |  | 0100305 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0100307 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100308 | Tippecanoe | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 2004-02-17 | CE
CN
RR
UT
|  |  | 0100309 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100310 | Vermillion |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
RR
|  |  | 0100312 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100313 |  | Madison Milton Ferry LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100314 | Kosciusko | Fink Roberts & Petrie | Indiana Department of Transportation | 2010-01-27 | CE
CN
PE
ROW
|  |  | 0100315 | Wabash | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
ROW
RR
|  |  | 0100316 | Floyd |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0100317 | Marion |  | Indiana Department of Transportation | 2010-01-27 | CE
CN
PE
ROW
|  |  | 0100318 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0100319 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100320 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100321 |  | Absolute Title Services, LLC | Bloomington | 2001-04-24
|  |  | 0100322 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2001-06-19 | CE
CN
|  |  | 0100323 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100324 | Wayne |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
ROW
|  |  | 0100325 | Shelby |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0100326 | Shelby |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0100327 | Shelby |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0100328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100329 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100330 | Cass |  | Indiana Department of Transportation | 2007-07-25 | CE
CN
ROW
|  |  | 0100331 | LaPorte |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0100332 | Gibson |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0100334 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100335 | Greene | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2006-09-13 | CE
CN
RR
|  |  | 0100336 |  | Farren Real Estate Services | Indiana Department of Transportation | 2001-09-11
|  |  | 0100337 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
|  |  | 0100338 |  | ERES International, Inc. | Indiana Department of Transportation | 2001-05-22
|  |  | 0100339 |  | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100340 |  |  | Rush County | -339679.2083
|  |  | 0100341 | Fulton |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
|  |  | 0100342 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100343 | Dearborn |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
UT
|  |  | 0100344 | Morgan |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
ROW
UT
|  |  | 0100345 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100346 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100348 | Harrison |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
UT
|  |  | 0100349 | Franklin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100350 | Clinton |  | Indiana Department of Transportation | 2007-10-17 | CE
CN
ROW
[6 empty] | Indiana Department of Transportation | 2007-10-17
|  |  | 0100351 | Montgomery |  | Montgomery County | 2007-02-21 | CE
CN
UT
|  |  | 0100352 | Fulton |  | Fulton County | 2004-05-25 | CE
CN
|  |  | 0100353 | Adams |  | Adams County | 2005-03-16 | CE
CN
|  |  | 0100354 |  |  | Ripley County | -339679.2083
|  |  | 0100355 | Wayne |  | Wayne County | 2006-04-19 | CE
CN
|  |  | 0100356 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100357 | Clinton |  | Clinton County | 2004-09-14 | CE
CN
|  |  | 0100358 | Randolph |  | Randolph County | 2015-03-04 | CE
CN
|  |  | 0100359 | Jackson |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
ROW
|  |  | 0100360 | Huntington |  | Huntington County | 2004-04-20 | CE
CN
|  |  | 0100361 | Shelby |  | Shelby County | 2018-04-11 | CE
CN
PE
ROW
|  |  | 0100362 | Fayette |  | Fayette County | 2010-12-08 | CE
CN
|  |  | 0100363 | Fayette |  | Fayette County | 2012-02-08 | CE
CN
UT
|  |  | 0100364 | Fayette |  | Fayette County | 2012-05-02 | CE
CN
|  |  | 0100365 | Tippecanoe |  | Tippecanoe County | 2010-05-12 | CE
CN
UT
[6 empty] | Tippecanoe County | 2010-05-12
|  |  | 0100366 | Sullivan |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
ROW
UT
|  |  | 0100367 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0100368 |  | ASA Land Surveying | Lawrence County | -339679.2083
|  |  | 0100369 |  |  | Fountain County | -339679.2083
|  |  | 0100370 |  |  | Perry County | -339679.2083
|  |  | 0100371 | Hancock | Great Lakes Engineering, Inc. | Hancock County | 2007-01-24 | CE
CN
RR
|  |  | 0100372 | Madison |  | Madison County | 2015-05-07 | CE
CN
|  |  | 0100373 | Madison |  | Madison County | 2005-09-14 | CE
CN
|  |  | 0100374 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0100375 |  | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100376 |  | ABNA of Illinois | Indiana Department of Transportation | -339679.2083
|  |  | 0100377 | Montgomery | Banning Engineering, P.C. | Montgomery County | 2005-05-25 | CE
CN
UT
|  |  | 0100378 | Henry |  | Henry County | 2004-08-17 | CE
CN
|  |  | 0100379 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0100380 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2007-02-21 | CE
CN
PE
|  |  | 0100381 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100382 | Jasper |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  | 0100383 | White |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100384 | Pulaski |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0100385 | Newton |  | Indiana Department of Transportation | 2011-10-13 | PE
|  |  | 0100386 | Hendricks | Bella Villa Realtors, LLC | Hendricks County | 2006-11-15 | CE
CN
RR
|  |  | 0100387 | Pulaski |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
|  |  | 0100388 | Howard |  | Howard County | 2004-07-20 | CE
CN
|  |  | 0100389 | Jasper |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
|  |  | 0100390 | Vigo |  | Vigo County | 2007-10-31 | CE
CN
RR
UT
|  |  | 0100391 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0100392 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2004-06-22 | CE
CN
RR
|  |  | 0100393 |  |  | Indiana State Agencies | -339679.2083
|  |  | 0100394 | Porter |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
RR
|  |  | 0100395 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100396 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100397 |  | Duesler Realty House | Indiana Department of Transportation | 2001-06-19
|  |  | 0100398 | LaPorte |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100399 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100400 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100401 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100402 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100403 | Lake |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100404 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0100405 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100406 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0100407 | Marshall | Knies Constr/Calcar Paving J/V | Indiana Department of Transportation | 2004-04-20 | CE
CN
RR
|  |  | 0100408 | Marshall |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
RR
|  |  | 0100409 | Porter |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
RR
|  |  | 0100410 | Lake |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
|  |  | 0100411 | Scott | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 2001-05-22 | CE
CN
|  |  |  | Vigo | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 2001-05-22 | CE
CN
PE
ROW
|  |  | 0100412 |  | Bidinfo | Indiana Department of Transportation | -339679.2083
|  |  | 0100413 |  | BradsKo Engineering and Surveying Inc. | Indiana Department of Transportation | 2001-07-17
|  |  | 0100414 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0100415 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100416 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0100417 | Clay |  | Indiana Department of Transportation | 2004-07-20 | CE
CN
|  |  | 0100418 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100419 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100421 | Allen |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
ROW
|  |  |  | Whitley |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
ROW
|  |  | 0100422 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
|  |  | 0100423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100424 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100425 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0100426 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
ROW
|  |  | 0100427 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100429 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100430 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2003-02-18
|  |  | 0100431 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100432 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100433 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100434 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100435 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100436 | Orange |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100437 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0100438 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 0100439 |  | Farren Real Estate Services | Indiana Department of Transportation | 2001-05-22
|  |  | 0100440 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100441 | Various |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0100442 | Shelby |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0100443 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100444 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-01-15
|  |  | 0100445 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 0100446 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0100447 | Shelby |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
ROW
|  |  | 0100448 | Huntington |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100449 | Tippecanoe |  | Indiana Department of Transportation | 2002-05-21 | CN
|  |  | 0100450 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100451 | Rush |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
UT
|  |  | 0100452 | Rush |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
|  |  | 0100453 | Rush |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0100454 | Rush |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0100455 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100456 | Rush |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0100457 | Wayne |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  | 0100458 | Wayne |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  | 0100459 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0100460 | Rush |  | Indiana Department of Transportation | 2012-11-20 | CE
CN
PE
ROW
|  |  | 0100461 | Rush |  | Indiana Department of Transportation | 2012-11-20 | CE
CN
PE
ROW
|  |  | 0100462 | Rush |  | Indiana Department of Transportation | 2012-11-20 | CE
CN
PE
ROW
|  |  | 0100463 | Wayne |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
ROW
|  |  | 0100464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100465 | Franklin |  | Indiana Department of Transportation | 2009-05-06 | CE
CN
|  |  | 0100466 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0100467 | Henry |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
ROW
|  |  | 0100468 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0100469 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100470 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100471 | Greene |  | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0100472 |  | AV Consulting Engineers, Inc. | Indiana Department of Transportation | 2004-08-17
|  |  | 0100473 | Various |  | Indiana Department of Transportation | 2002-06-18 | CE
CN
|  |  | 0100474 | Various |  | Indiana Department of Transportation | 2002-06-18 | CE
CN
|  |  | 0100475 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100476 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100477 | Lake |  | Indiana Department of Transportation | 2008-06-18 | CE
CN
PE
ROW
|  |  | 0100478 | Owen |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
ROW
|  |  | 0100479 | Fulton | InfoTech | Indiana Department of Transportation | 2008-11-19 | PE
|  |  | 0100480 | Parke |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
PE
ROW
|  |  | 0100481 |  |  | Switzerland County | -339679.2083
|  |  | 0100482 | Vanderburgh |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0100483 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100484 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100485 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0100486 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100487 | Harrison |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100488 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100489 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100490 | Daviess |  | Indiana Department of Transportation | 2007-09-19 | CE
CN
|  |  | 0100491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100493 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100495 | Clay |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
UT
|  |  | 0100496 | Benton |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
ROW
|  |  | 0100497 |  | Linda F. Russell | Indiana Department of Transportation | -339679.2083
|  |  | 0100498 |  |  | Indiana Department of Transportation | 2007-05-02
|  |  | 0100499 |  | Fink Roberts & Petrie | Indiana Department of Transportation | -339679.2083
|  |  | 0100500 | Noble |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
ROW
|  |  | 0100501 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100502 | Daviess |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0100503 | Kosciusko | FPBH, Inc. | Indiana Department of Transportation | 2008-10-01 | CE
CN
ROW
|  |  | 0100504 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
ROW
|  |  | 0100505 | Greene |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  |  | Knox |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0100506 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100507 | Gibson |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0100508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100511 | Sullivan |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0100512 | LaPorte |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0100513 | Orange |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100514 | Marshall |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0100515 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0100516 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100517 | Ripley | ARCADIS | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
ROW
UT
|  |  | 0100518 | Daviess |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0100519 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0100520 |  |  | South Bend | -339679.2083
|  |  | 0100521 | White |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
RR
[6 empty] | Indiana Department of Transportation | 2011-04-13
|  |  | 0100522 | White | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 2013-07-10 | PE
|  |  | 0100523 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 0100524 |  | D L Savage Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100525 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100526 | Sullivan | Anelena Ackerly | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
RR
UT
|  |  | 0100527 |  | AMEC E&I, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100528 | Various |  | Indiana State Agencies | -339679.2083 | PE
|  |  | 0100529 |  |  | Goshen | -339679.2083
|  |  | 0100530 | Henry |  | Henry County | -339679.2083 | CN
|  |  | 0100531 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100532 | Boone |  | Boone County | -339679.2083 | CN
|  |  | 0100533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100534 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100535 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100536 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100537 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100539 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100541 | Hendricks |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
|  |  | 0100542 | Hancock |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100543 | Tipton |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100544 | Madison |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100545 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100546 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100547 | Randolph |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100548 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0100549 | Jay |  | Indiana Department of Transportation | 2005-06-01 | UT
|  |  | 0100550 | Howard | J.F. New & Associates, Inc. | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0100551 | Rush |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0100552 | Wayne |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
ROW
|  |  | 0100553 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0100554 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0100555 | Blackford |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0100556 | Delaware |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
ROW
|  |  | 0100557 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0100558 | Randolph |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 0100559 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0100560 |  |  | St. Joseph County | -339679.2083
|  |  | 0100561 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2001-09-11 | CE
CN
|  |  | 0100562 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 0100563 |  |  | South Bend | -339679.2083
|  |  | 0100564 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2002-11-19
|  |  | 0100565 | Elkhart | Gandhi and Associates, Inc. | Nappanee | -339679.2083 | CN
|  |  | 0100566 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2006-10-18 | CE
CN
|  |  | 0100567 | Carroll | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  | 0100568 | Jay | Alliance Survey Company | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 0100569 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100570 |  |  | South Bend | 2004-01-21
|  |  | 0100571 | Porter |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100572 | Boone |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 0100573 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0100574 | Vanderburgh | CGI | Evansville | 2014-12-10 | CE
CN
PE
|  |  | 0100575 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100576 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2001-06-19
|  |  | 0100577 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100578 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100579 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100580 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0100581 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100582 |  | Active Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100583 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0100584 | Madison |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100585 | Madison |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100586 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0100587 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100588 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100589 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100590 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100591 |  | CGI | Vanderburgh County | -339679.2083
|  |  | 0100592 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100593 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100594 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100595 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100596 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100597 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100598 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100599 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100600 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 0100601 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100602 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100603 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0100604 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100605 |  | GSG Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100606 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0100607 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100609 | Crawford | Engineering Technologies, Inc. | Indiana Department of Transportation | 2008-07-09 | CE
CN
PE
|  |  | 0100610 | Knox |  | Indiana Department of Transportation | 2002-07-16 | CE
CN
|  |  | 0100611 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100612 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100613 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100614 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100615 | Boone |  | Indiana Department of Transportation | -339679.2083 | ROW
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 0100616 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100617 | Various |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100618 | Marion |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
PE
UT
|  |  |  | Shelby |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
UT
|  |  | 0100619 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0100620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100621 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100622 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100623 | St. Joseph |  | St. Joseph County | 2009-03-11 | CE
CN
|  |  | 0100624 |  |  | St. Joseph County | -339679.2083
|  |  | 0100625 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100626 |  |  | Elkhart County | -339679.2083
|  |  | 0100627 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100628 | Elkhart |  | Elkhart County | 2004-06-15 | CE
CN
|  |  |  | St. Joseph |  | Elkhart County | 2004-06-15 | CN
|  |  | 0100629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 010062C |  |  |  | -339679.2083
|  |  | 0100630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100631 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100632 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100633 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100634 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0100635 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100636 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0100637 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100638 | Marion | DCD Consulting LLC | Indianapolis | 2006-02-22 | CE
CN
|  |  | 0100639 | Marion |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0100640 | Marion | DCD Consulting LLC | Indianapolis | 2006-02-22 | CE
CN
|  |  | 0100641 | Newton |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0100642 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100643 | Rush |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  | 0100644 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0100645 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100646 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100647 | Marion | DCD Consulting LLC | Indiana Department of Natural Resources | 2006-08-16 | CE
CN
|  |  | 0100648 | Elkhart |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
PE
ROW
UT
|  |  | 0100649 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2005-04-20 | CE
CN
UT
|  |  | 0100650 | Noble | Debbie L. Morris | Kendallville | 2004-01-21 | CE
CN
|  |  | 0100651 | Wabash | M-E Companies, Inc. | Wabash | 2004-08-17 | CE
CN
|  |  | 0100652 | Posey | GRL Engineers, Inc. | Mount Vernon | -339679.2083 | CE
CN
PE
RR
|  |  | 0100653 |  |  | Tell City | -339679.2083
|  |  | 0100654 | Jasper | Independent Land Surveying, Inc. | Rensselaer | 2008-03-05 | CE
CN
|  |  | 0100655 | Hendricks |  | Avon | 2009-04-15 | CE
CN
UT
|  |  | 0100656 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 0100657 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 0100658 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100659 | Gibson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0100660 | Dubois |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
PE
UT
|  |  | 0100661 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100662 | Gibson |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
RR
UT
|  |  | 0100663 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | CE
CN
|  |  | 0100664 | Miami | Holloway Engineering, LLC | Peru | 2005-01-19 | CE
CN
|  |  | 0100665 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100666 | Greene |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100667 | Ripley | ARCADIS | Batesville | 2008-09-04 | CE
CN
|  |  | 0100668 | Posey |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
UT
|  |  | 0100669 | Boone | E.J. Breneman, LP | Lebanon | 2005-07-20 | CE
CN
|  |  | 0100670 | Hamilton |  | Hamilton County | -339679.2083 | CN
|  |  | 0100671 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0100672 | Boone | E.J. Breneman, LP | Lebanon | 2005-07-20 | CE
CN
|  |  | 0100673 |  | Danch Harner and Associates, Inc. | Jasper | -339679.2083
|  |  | 0100674 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100675 | Gibson |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100676 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100677 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0100678 |  | Dyer Environmental Services | Lawrence | -339679.2083
|  |  | 0100679 | Marion | Another Test Company | Indiana Department of Transportation | 2009-11-06 | ROW
UT
|  |  | 0100680 | Adams | Bidinfo | Decatur | 2004-10-19 | CE
CN
UT
|  |  | 0100681 | Scott |  | Scott County | -339679.2083 | CN
|  |  | 0100682 |  | Cheri K. Lewis Engineers | Garrett | -339679.2083
|  |  | 0100683 | Shelby | Jeffrey S. Juday | Shelbyville | 2005-05-25 | CE
CN
RR
|  |  | 0100684 | Madison | Central Diving Contractors | Indiana Department of Transportation | 2003-11-18 | CE
CN
RR
|  |  | 0100685 | Madison |  | Indiana Department of Transportation | 2003-11-18 | RR
|  |  | 0100686 | Delaware |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0100687 | LaGrange |  | LaGrange County | 2009-02-11 | CE
CN
|  |  | 0100688 | Carroll |  | Carroll County | -339679.2083 | CN
|  |  | 0100689 | Marshall |  | Marshall County | -339679.2083 | CN
|  |  | 0100690 |  | ASA Land Surveying | Indiana Department of Transportation | 2014-12-10
|  |  | 0100691 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100692 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100693 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100694 | Johnson |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100695 | Morgan |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0100696 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100697 | Morgan |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100698 | Vigo |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
ROW
UT
|  |  | 0100699 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
RR
|  |  | 0100700 | Wayne | Cambridge Systematics, Inc. | Indiana Department of Transportation | 2014-08-06 | CE
CN
PE
|  |  | 0100701 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
|  |  | 0100702 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0100703 | Madison | Central Diving Contractors | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0100704 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100705 |  |  | Indiana Department of Transportation | 2001-06-19
|  |  | 0100706 | Allen |  | Allen County | 2009-05-06 | CE
CN
PE
ROW
UT
|  |  | 0100707 |  | EFI Global, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100709 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100710 |  |  | Indiana Department of Transportation | 2002-07-16
|  |  | 0100711 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100712 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100713 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100714 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100715 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
ROW
|  |  | 0100716 | Jay | Hilton Property Management, LLC | Indiana Department of Transportation | 2007-11-13 | UT
|  |  | 0100717 | Wayne | Appraisal Office of Central Indiana | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0100718 |  | CGI | Indiana Department of Transportation | 2001-07-17
|  |  | 0100719 |  | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100720 |  | CE Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100721 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 0100722 | Jackson |  | Jackson County | 2010-01-27 | PE
|  |  | 0100723 | Parke |  | Parke County | 2008-05-08 | CN
PE
|  |  | 0100724 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0100725 |  | CTLGroup | Indiana Department of Transportation | -339679.2083
|  |  | 0100726 | Benton |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0100727 | Rush |  | Rush County | 2004-05-25 | CE
CN
PE
|  |  | 0100728 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100729 |  | Hydrogeology, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100730 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100731 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100732 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100733 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100734 | Tipton | Land Construction Corp | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 0100735 | Miami |  | Miami County | -339679.2083 | CN
|  |  | 0100736 |  | Copperhead Environmental Consulting | Indiana Department of Transportation | -339679.2083
|  |  | 0100737 | Marion | DCD Consulting LLC | Indianapolis | 2004-05-25 | CE
CN
RR
|  |  | 0100738 |  | CEI Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100739 | Marion | DCD Consulting LLC | Indianapolis | 2004-05-25 | CE
CN
RR
|  |  | 0100740 | Marion | DCD Consulting LLC | Indianapolis | 2004-05-25 | CE
CN
RR
|  |  | 0100741 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100742 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100743 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100744 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100745 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100746 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100747 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100748 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100749 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100750 | Morgan |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
ROW
UT
|  |  | 0100751 | Brown | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100752 | Harrison |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
ROW
|  |  | 0100753 | Jennings |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
UT
|  |  | 0100754 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 0100755 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 0100756 | Jackson |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
ROW
UT
|  |  | 0100757 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0100758 | Brown |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100759 | Bartholomew |  | Indiana Department of Transportation | 2013-05-31 | CN
PE
ROW
|  |  | 0100760 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0100761 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0100762 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100763 | Brown |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100764 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100765 | Brown |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100766 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100767 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0100768 | Brown |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100770 | Brown |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100771 | Brown |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0100772 | Jackson |  | Indiana Department of Transportation | 2014-03-12 | PE
|  |  | 0100773 | Monroe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100774 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100775 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2001-10-02 | CE
CN
|  |  | 0100776 |  |  | Newburgh | 2001-08-14
|  |  | 0100777 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100778 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100779 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100780 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100781 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100782 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100783 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0100784 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0100785 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 0100786 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0100787 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100788 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0100789 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0100790 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0100791 | Cass | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0100792 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | 2006-05-24 | CE
CN
PE
ROW
RR
UT
|  |  | 0100793 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-06-18 | CE
CN
UT
|  |  | 0100794 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100795 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100796 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0100797 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100798 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100799 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100800 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100801 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100802 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100803 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2009-03-11
|  |  | 0100804 | Montgomery |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
UT
|  |  | 0100805 | Montgomery |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
UT
|  |  | 0100806 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100807 | Clinton |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0100808 |  |  | Indiana State Agencies | 2001-09-11
|  |  | 0100809 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0100810 | Grant |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100811 | Adams |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  |  | Jay |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  | 0100812 | Adams |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  | 0100813 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100814 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100815 | Spencer |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100816 | Perry |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0100817 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100818 | Rush |  | Indiana Department of Transportation | -339679.2083 | CE
CN
OT
PE
ROW
|  |  | 0100819 | Rush |  | Indiana Department of Transportation | -339679.2083 | CE
CN
OT
PE
ROW
|  |  | 0100820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100821 | Franklin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Rush |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100822 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 2008-02-06
|  |  | 0100823 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100824 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0100825 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100826 | Lake |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0100827 | Lake |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0100828 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 0100829 |  |  | South Bend | 2004-01-21
|  |  | 0100830 | St. Joseph |  | South Bend | 2006-07-19 | CE
CN
|  |  | 0100831 | St. Joseph |  | St. Joseph County | 2002-06-18 | CE
CN
|  |  | 0100832 |  |  | St. Joseph County | -339679.2083
|  |  | 0100833 |  |  | St. Joseph County | 2003-11-18
|  |  | 0100834 |  |  | St. Joseph County | -339679.2083
|  |  | 0100835 | Morgan | EnviroScience, Inc. | Martinsville | 2013-12-11 | CE
CN
ROW
|  |  | 0100836 | Knox | Louis Joyner, Architect | Vincennes | 2005-11-16 | CE
CN
|  |  | 0100837 | Elkhart |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  |  | Noble |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
|  |  | 0100838 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100839 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0100840 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0100841 |  | Accurate Group, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0100842 | Boone |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0100843 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
UT
|  |  | 0100844 | Gibson |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  | 0100845 |  | CMF Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100846 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 2001-08-14
|  |  | 0100847 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100848 |  |  | Indiana Department of Transportation | 2001-07-17
|  |  | 0100849 | Posey |  | Indiana Department of Transportation | 2002-01-15 | CE
CN
PE
|  |  | 0100850 | Posey |  | Indiana Department of Transportation | 2002-01-15 | CE
CN
PE
|  |  | 0100851 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0100852 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100853 | Greene | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0100854 | Dubois |  | Indiana Department of Transportation | 2004-07-20 | CE
CN
|  |  | 0100855 | Dubois | Aarcher, Inc. | Indiana Department of Transportation | 2003-12-17 | CE
CN
UT
|  |  |  | Perry | Aarcher, Inc. | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0100856 | Madison |  | Alexandria | 2012-01-11 | CE
CN
PE
|  |  | 0100857 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0100858 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2005-09-14 | CE
CN
|  |  | 0100859 |  | CMF Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100860 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100861 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0100862 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0100863 | Perry |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0100864 |  | Applied Pavement Technology, Inc. | Cedar Lake | -339679.2083
|  |  | 0100865 |  | Duesler Realty House | Indiana Department of Transportation | 2001-08-14
|  |  | 0100866 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0100867 | Ohio |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
UT
|  |  | 0100868 | Knox |  | Knox County | -339679.2083 | CN
|  |  | 0100869 | Marion | DCD Consulting LLC | Indianapolis | 2006-04-19 | CE
CN
|  |  | 0100870 |  | DCD Consulting LLC | Indianapolis | 2002-09-17
|  |  | 0100871 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2001-09-11
|  |  | 0100872 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100873 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100874 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100875 | Spencer |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100876 | Vigo | Indiana Infrastructure Partners, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0100877 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0100878 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100879 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0100880 |  |  | Indiana Department of Transportation | 2001-08-14
|  |  | 0100881 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2007-08-22 | CE
CN
ROW
|  |  | 0100882 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100883 |  | ABt SRBI | Indiana Department of Transportation | 2001-10-16
|  |  | 0100884 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0100885 | Monroe |  | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0100886 | Perry |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100887 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100888 | Perry |  | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0100889 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2003-04-22 | CE
CN
|  |  | 0100890 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2002-01-15 | CE
CN
|  |  | 0100891 | Delaware |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
PE
ROW
UT
|  |  | 0100892 | Marion | DCD Consulting LLC | Indianapolis | 2005-03-16 | CE
CN
PE
RR
|  |  | 0100893 |  |  | Indiana Department of Transportation | 2002-10-22
|  |  | 0100894 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0100895 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0100896 |  | Clayton L. Roots | Indiana Department of Transportation | 2002-08-13
|  |  | 0100897 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0100898 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2002-06-18
|  |  | 0100899 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2002-06-18
|  |  | 0100900 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0100901 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0100902 |  |  | Indiana Department of Transportation | 2002-06-11
|  |  | 0100903 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0100904 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100905 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 0100906 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0100907 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0100908 | Gibson |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0100909 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0100910 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2008-02-06 | CE
CN
PE
|  |  | 0100911 | Vanderburgh |  | Indiana Department of Transportation | 2003-04-22 | PE
ROW
|  |  |  | Warrick |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
UT
|  |  | 0100912 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100913 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0100914 | Fulton |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100915 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0100916 | Lake |  | Indiana Department of Transportation | 2002-04-23 | CE
CN
|  |  | 0100917 | Daviess |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
UT
|  |  | 0100918 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2002-03-19
|  |  | 0100919 |  | Domain Architecture, Inc. | Indiana Department of Transportation | 2002-11-19
|  |  | 0100920 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0100921 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2002-11-19
|  |  | 0100922 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100923 |  | Farah and Sons, Inc. | Indiana State Agencies | 2002-04-23
|  |  | 0100924 |  |  | Indiana State Agencies | 2002-04-23
|  |  | 0100925 |  |  | Indiana State Agencies | -339679.2083
|  |  | 0100926 |  |  | Indiana State Agencies | 2002-03-19
|  |  | 0100927 |  |  | Indiana State Agencies | 2002-05-21
|  |  | 0100928 |  |  | Indiana State Agencies | 2002-11-19
|  |  | 0100929 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0100930 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0100931 |  | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2004-11-16
|  |  | 0100932 | Tippecanoe |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
|  |  | 0100933 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
RR
UT
|  |  | 0100934 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2009-05-06 | CE
CN
|  |  | 0100935 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100936 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100937 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0100938 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2009-05-06 | CE
CN
|  |  | 0100939 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100940 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100941 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 0100942 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0100943 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0100944 | Various |  | Indiana Department of Transportation | 2002-07-16 | CE
CN
|  |  | 0100945 | Kosciusko |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100946 | Marion | DCD Consulting LLC | Indianapolis | 2006-02-15 | CE
CN
RR
|  |  | 0100947 | Marion | DCD Consulting LLC | Indianapolis | 2006-02-15 | CE
CN
RR
|  |  | 0100948 | Marion | DCD Consulting LLC | Indianapolis | 2007-01-24 | CE
CN
|  |  | 0100949 |  | B. L. A., Inc. | Indiana Department of Transportation | 2001-09-11
|  |  | 0100950 | Marion | DCD Consulting LLC | Indianapolis | 2003-09-16 | CE
CN
|  |  | 0100951 | Marion | DCD Consulting LLC | Indianapolis | 2005-02-16 | CE
CN
PE
|  |  | 0100952 | Marion | DCD Consulting LLC | Indianapolis | 2004-04-20 | CE
CN
|  |  | 0100953 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0100954 |  |  | Indiana State Agencies | 2002-09-17
|  |  | 0100955 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100956 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0100957 | Vanderburgh | CGI | Indiana Department of Transportation | 2018-09-19 | PE
RR
UT
|  |  | 0100958 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100959 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100960 |  |  | Sullivan | -339679.2083
|  |  | 0100961 | Knox |  | Indiana Department of Transportation | 2011-09-08 | PE
ROW
|  |  | 0100962 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100963 | Knox |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
PE
RR
UT
|  |  | 0100964 | Greene |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
PE
|  |  | 0100965 | Greene |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
PE
|  |  | 0100966 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100967 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100968 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
|  |  | 0100969 |  |  | Indiana Department of Transportation | 2001-10-16
|  |  | 0100970 | Dekalb |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
|  |  | 0100971 | Elkhart |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100972 | Kosciusko | FPBH, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0100973 |  | Franco Consulting Engineers, LLC | Indiana Department of Transportation | 2002-01-15
|  |  | 0100974 | Sullivan |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
PE
|  |  | 0100975 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100976 | Perry |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0100977 | Crawford |  | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  |  | Perry |  | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  | 0100978 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0100979 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0100980 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0100981 | Greene |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
RR
|  |  | 0100982 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0100983 | Spencer |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0100984 | Crawford |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0100985 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2005-06-01
|  |  | 0100986 |  |  | Indiana Department of Transportation | 2001-09-11
|  |  | 0100987 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-05-31 | CE
CN
ROW
UT
|  |  |  | Various | Consolidated Test Company | Indiana Department of Transportation | 2016-05-31 | CN
|  |  | 0100988 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0100989 |  | M-E Companies, Inc. | Indiana Department of Transportation | 2002-09-17
|  |  | 0100990 |  |  | Johnson County | -339679.2083
|  |  | 0100991 |  |  | Brown County | -339679.2083
|  |  | 0100992 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2002-09-17
|  |  | 0100993 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2002-09-17
|  |  | 0100994 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0100995 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0100996 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  | 0100997 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0100998 |  | CGI | Indiana Department of Transportation | 2002-02-19
|  |  | 0100999 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0101000 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101001 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2002-02-19 | CN
|  |  | 0101002 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101004 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101005 | Vigo |  | Indiana Department of Transportation | 2001-12-19 | CE
CN
|  |  | 0101006 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0101007 |  | Archonsortium, LLC | Indiana Department of Transportation | 2003-02-18
|  |  | 0101008 | Putnam | Clayton L. Roots | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0101009 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101010 |  | Carters Appraisal Service | Indiana Department of Transportation | 2003-05-20
|  |  | 0101011 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | 2003-03-25
|  |  | 0101012 |  | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | 2002-11-19
|  |  | 0101013 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0101014 | Newton |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0101015 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101016 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101017 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0101018 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101019 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101020 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2001-09-11
|  |  | 0101021 | Marion |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0101022 | Warrick |  | Warrick County | 2002-04-23 | CE
PE
|  |  | 0101023 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101024 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0101025 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0101026 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101028 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0101029 | Crawford |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 0101030 |  |  | Indiana Department of Transportation | 2001-08-16
|  |  | 0101031 | Union |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 0101032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101033 | Delaware |  | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0101034 | Marion |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0101035 |  | Harvard Title Searching | Indiana Department of Transportation | -339679.2083
|  |  | 0101036 | Marion |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0101037 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0101038 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0101039 | Gibson | Harvard Title Searching | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0101040 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0101041 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0101042 |  | Harvard Title Searching | Indiana Department of Transportation | -339679.2083
|  |  | 0101043 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 0101044 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 0101045 | Harrison |  | Indiana Department of Natural Resources | 2002-02-19 | CE
CN
|  |  | 0101046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101047 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
UT
|  |  | 0101048 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101049 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-01-15
|  |  | 0101050 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-01-15
|  |  | 0101051 | Montgomery | ETC Institute | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0101052 | Adams |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  |  | Allen |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  |  | Elkhart |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  |  | Noble |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  | 0101053 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101054 | Allen |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
|  |  |  | Huntington |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
|  |  | 0101055 | Miami |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0101056 |  | Bidinfo | Indiana Department of Transportation | -339679.2083
|  |  | 0101057 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101058 | Tippecanoe | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 2009-08-12 | CE
CN
|  |  | 0101059 | Warrick |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0101061 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0101062 |  |  | Huntington County | -339679.2083
|  |  | 0101063 | Grant |  | Grant County | -339679.2083 | CN
|  |  | 0101064 | Tippecanoe |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
ROW
RR
UT
|  |  | 0101065 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0101066 | Allen |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
UT
|  |  | 0101067 | Allen |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
UT
|  |  | 0101068 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-01-21 | CE
CN
PE
RR
UT
|  |  | 0101069 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101070 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101071 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101072 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101074 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101075 |  | DuSABLE, Inc. | Crawfordsville | -339679.2083
|  |  | 0101076 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 2001-12-19
|  |  | 0101077 |  | Clayton L. Roots | Indiana Department of Transportation | 2001-11-20
|  |  | 0101078 |  |  | Indiana Department of Natural Resources | 2001-11-20
|  |  | 0101079 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101080 | Warrick |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0101081 | Warrick |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0101082 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101083 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101084 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101085 | Marion | DCD Consulting LLC | Indianapolis | 2004-04-20 | CE
CN
|  |  | 0101086 | Marion | DCD Consulting LLC | Indianapolis | 2004-04-20 | CE
CN
|  |  | 0101087 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-01-15
|  |  | 0101088 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101089 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-03-19 | CE
CN
PE
UT
|  |  |  | Shelby | DCD Consulting LLC | Indiana Department of Transportation | 2002-03-19 | CE
CN
UT
|  |  | 0101090 | Dubois | Danch Harner and Associates, Inc. | Dubois County | -339679.2083 | CE
CN
|  |  | 0101091 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2002-01-15
|  |  | 0101092 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2002-06-18
|  |  | 0101093 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2003-01-22
|  |  | 0101094 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2002-06-18
|  |  | 0101095 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101096 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0101097 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2002-01-15 | CE
CN
RR
|  |  | 0101098 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101099 | Howard | Dodd Title Corporation | Kokomo | 2008-03-19 | CE
CN
|  |  | 0101100 |  | Lonco, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101101 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2010-03-03 | CE
CN
PE
ROW
|  |  | 0101102 | Floyd |  | Indiana Department of Transportation | 2009-05-06 | PE
RR
|  |  | 0101103 | Fountain | BA Martin Architects, PC | Indiana Department of Transportation | 2004-06-15 | CE
CN
|  |  | 0101104 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0101105 |  | Chicago Title Insurance Company | Indiana Department of Transportation | -339679.2083
|  |  | 0101106 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington | 2002-04-23 | CE
CN
|  |  | 0101107 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101109 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0101110 | Delaware |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0101111 | Gibson |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0101112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101114 | Warrick |  | Vanderburgh County | 2005-03-16 | CE
CN
PE
UT
|  |  | 0101115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101117 | Howard | Dodd Title Corporation | Kokomo | 2002-06-18 | CN
|  |  | 0101118 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-01-15
|  |  | 0101119 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101120 |  | Archaeology and Geomorphology Services | Indiana Department of Transportation | 2002-07-16
|  |  | 0101121 | Starke |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
PE
ROW
RR
UT
|  |  | 0101122 | Starke |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
ROW
|  |  | 0101123 | Various | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0101124 |  | CGI | Evansville | 2002-02-19
|  |  | 0101125 |  | CGI | Evansville | 2002-02-19
|  |  | 0101126 | Marion |  | Indiana Department of Transportation | 2009-02-11 | CE
PE
ROW
UT
|  |  | 0101127 | Knox |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0101128 | White | Fugro Roadware, Inc. | Monticello | 2008-09-04 | CE
CN
PE
ROW
|  |  | 0101129 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-02-19
|  |  | 0101130 | Johnson |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0101131 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0101132 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2003-07-15
|  |  | 0101133 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2003-07-15
|  |  | 0101134 | Union |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0101135 | Union |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
PE
ROW
|  |  | 0101136 | Union |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
PE
ROW
|  |  | 0101137 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2001-11-20 | CE
CN
|  |  | 0101138 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0101139 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0101140 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0101141 |  |  | Indiana Department of Transportation | 2001-11-20
|  |  | 0101142 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101143 |  |  | Indiana Department of Transportation | 2001-12-19
|  |  | 0101144 | Greene |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0101145 | Lawrence |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
PE
ROW
UT
|  |  | 0101146 | Pike |  | Indiana Department of Transportation | 2015-09-11 | PE
|  |  | 0101147 | Knox |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
UT
|  |  | 0101148 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0101149 | Greene |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
|  |  | 0101150 | Hendricks |  | Hendricks County | 2002-03-19 | CE
CN
UT
|  |  | 0101151 | Shelby |  | Shelby County | -339679.2083 | CN
|  |  | 0101152 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2002-01-15
|  |  | 0101153 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101155 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101156 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2002-06-18
|  |  | 0101157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101158 |  | DCD Consulting LLC | Indiana Department of Transportation | 2001-12-19
|  |  | 0101159 | Elkhart |  | Elkhart County | 2003-03-25 | CE
CN
|  |  | 0101160 | Elkhart |  | Elkhart County | 2003-03-25 | CE
CN
|  |  | 0101161 | Elkhart |  | Elkhart County | 2003-03-25 | CE
CN
|  |  | 0101162 | Elkhart |  | Elkhart County | 2004-06-15 | CE
CN
|  |  | 0101163 | Elkhart |  | Elkhart County | 2004-06-15 | CE
CN
[6 empty] | Elkhart County | 2004-06-15
|  |  | 0101164 | Elkhart |  | Elkhart County | 2009-05-06 | CE
CN
UT
|  |  | 0101165 | Elkhart |  | Elkhart County | 2009-05-06 | CE
CN
|  |  | 0101166 | Elkhart |  | Elkhart County | 2009-05-06 | CE
CN
|  |  | 0101167 |  |  | Elkhart County | -339679.2083
|  |  | 0101168 | Wells |  | Wells County | -339679.2083 | CN
|  |  | 0101169 | Clinton |  | Indiana Department of Transportation | 2007-10-17 | PE
|  |  | 0101170 | Gibson | CSR Engineering, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  |  | Vanderburgh | CSR Engineering, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  | 0101171 |  | Dodd Title Corporation | Kokomo | -339679.2083
|  |  | 0101172 | Dekalb |  | Indiana Department of Transportation | 2001-11-20 | PE
RR
|  |  | 0101173 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2004-06-22 | CE
CN
|  |  | 0101174 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2002-08-13 | CE
CN
ROW
|  |  | 0101175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101176 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101178 | Delaware |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0101179 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | 2002-01-15
|  |  | 0101180 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2013-10-09 | CE
CN
|  |  | 0101181 | St. Joseph |  | St. Joseph County | 2007-05-31 | CE
CN
|  |  | 0101182 | St. Joseph |  | St. Joseph County | 2013-07-10 | CE
CN
|  |  | 0101183 | St. Joseph |  | South Bend | 2006-07-19 | CE
CN
|  |  | 0101184 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0101185 |  |  | Huntington County | -339679.2083
|  |  | 0101186 | Jefferson |  | Jefferson County | -339679.2083 | CN
|  |  | 0101187 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101188 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0101189 |  |  | Indiana Department of Natural Resources | 2002-08-13
|  |  | 0101190 | Whitley |  | Whitley County | -339679.2083 | CN
|  |  | 0101191 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-06-18 | CE
CN
UT
|  |  | 0101192 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0101193 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2002-08-13
|  |  | 0101194 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0101195 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101196 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101199 | Clark |  | Indiana Department of Transportation | 2002-09-24 | CN
|  |  | 0101200 | White |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0101201 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101203 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2002-02-19
|  |  | 0101204 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101205 |  |  | Ripley County | -339679.2083
|  |  | 0101206 |  | CGI | Evansville | -339679.2083
|  |  | 0101207 |  |  | Tippecanoe County | -339679.2083
|  |  | 0101208 |  |  | Wayne County | -339679.2083
|  |  | 0101209 |  |  | Indiana Department of Transportation | 2002-01-15
|  |  | 0101210 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0101211 | Jay |  | Jay County | -339679.2083 | CN
|  |  | 0101212 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101213 |  |  | Indiana Department of Transportation | 2002-10-22
|  |  | 0101214 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 0101215 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101216 | Ripley |  | Ripley County | -339679.2083 | CN
|  |  | 0101217 |  |  | Spencer County | -339679.2083
|  |  | 0101218 |  |  | Henry County | -339679.2083
|  |  | 0101219 |  |  | Jasper County | 2002-07-16
|  |  | 0101220 |  |  | Pike County | -339679.2083
|  |  | 0101221 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101224 | Henry |  | Henry County | 2002-05-21 | CE
CN
|  |  | 0101225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101226 |  |  | Indiana Department of Transportation | 2002-07-16
|  |  | 0101227 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101228 | Parke |  | Indiana Department of Natural Resources | 2014-04-02 | CE
CN
|  |  | 0101229 | Brown |  | Indiana Department of Natural Resources | 2004-01-21 | CE
CN
|  |  | 0101230 | Montgomery |  | Indiana Department of Natural Resources | 2008-12-10 | CE
CN
|  |  | 0101231 | Jennings |  | Indiana Department of Natural Resources | 2003-09-16 | RR
|  |  |  | Owen |  | Indiana Department of Natural Resources | 2003-09-16 | CE
CN
|  |  | 0101232 | Monroe |  | Monroe County | 2017-11-15 | CN
|  |  | 0101233 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101234 | Hamilton |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
|  |  | 0101235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101236 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101237 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101238 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101239 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101240 |  | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0101241 |  | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0101242 |  | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0101243 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101244 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101245 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101246 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101247 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101248 | Wayne |  | Wayne County | -339679.2083 | CN
|  |  | 0101249 |  |  | Pike County | -339679.2083
|  |  | 0101250 |  |  | Tippecanoe County | 2002-04-23
|  |  | 0101251 |  | Cambridge Systematics, Inc. | Wayne County | 2002-07-16
|  |  | 0101252 |  |  | Henry County | 2002-07-16
|  |  | 0101253 | Dearborn |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
RR
|  |  | 0101254 | Washington |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0101255 |  | Greenman-Pedersen, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101257 |  |  | Indiana Department of Transportation | 2012-09-20
|  |  | 0101258 | Lake | Greenman-Pedersen, Inc. | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0101259 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101260 | Wabash |  | Wabash County | -339679.2083 | CN
|  |  | 0101261 |  | Greenman-Pedersen, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101262 |  | Greenman-Pedersen, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101263 | Jennings |  | Jennings County | 2015-03-04 | CE
CN
|  |  | 0101264 | Jennings |  | Jennings County | 2012-11-15 | CE
CN
|  |  | 0101265 | Jackson |  | Jackson County | -339679.2083 | CN
|  |  | 0101266 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101268 | Franklin | ARCADIS | Indiana Department of Transportation | 2016-11-02 | PE
|  |  | 0101269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101270 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0101271 | Vanderburgh | CGI | Evansville | 2009-12-09 | CE
CN
|  |  | 0101272 | Warrick |  | Warrick County | 2007-05-02 | CE
CN
UT
|  |  | 0101273 | Lake | Cornerstone Design | Highland | -339679.2083 | CE
CN
|  |  | 0101274 |  | Alliance Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101275 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101276 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0101277 | Benton |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
ROW
|  |  | 0101278 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101279 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2010-01-13 | CE
CN
|  |  | 0101280 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101281 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101282 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101283 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101284 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101285 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0101286 | Clinton |  | Clinton County | -339679.2083 | CN
|  |  | 0101287 | Clay |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0101288 | Morgan |  | Indiana Department of Transportation | 2006-02-22 | CE
CN
|  |  | 0101289 | Hendricks |  | Indiana Department of Transportation | 2005-09-14 | CE
CN
|  |  | 0101290 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101291 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101292 | Lake |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0101293 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0101294 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2008-11-19 | CE
[5 empty] | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2008-11-19
|  |  | 0101295 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101297 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Natural Resources | 2004-06-15 | CE
CN
|  |  | 0101298 | Vigo | Bayswater Company, LLC | Terre Haute | 2013-05-21 | CE
CN
|  |  | 0101299 | Vigo | Bayswater Company, LLC | Terre Haute | 2006-06-21 | CE
CN
|  |  | 0101300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101301 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0101302 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0101303 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101304 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101305 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-02-19
|  |  | 0101306 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0101307 | Warren |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0101308 |  | McKee Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101309 | Clinton |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
ROW
|  |  | 0101310 | Hendricks |  | Indiana Department of Transportation | 2009-05-27 | CE
CN
|  |  | 0101311 | Boone |  | Indiana Department of Transportation | 2013-07-10 | PE
ROW
|  |  | 0101312 | Boone |  | Indiana Department of Transportation | 2013-07-10 | PE
ROW
|  |  | 0101313 | Boone |  | Indiana Department of Transportation | 2013-07-10 | PE
ROW
|  |  | 0101314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101315 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101316 | St. Joseph |  | St. Joseph County | 2002-06-18 | CE
CN
|  |  | 0101317 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101318 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101319 | Marshall | Active Environmental Services, Inc. | Bourbon | -339679.2083 | CE
CN
|  |  | 0101320 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101321 | Vermillion |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  |  | Warren |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 0101322 |  | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101323 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 0101324 |  | Alfred Benesch & Company | Indiana Department of Transportation | 2002-08-13
|  |  | 0101325 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0101326 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0101327 |  | Martin Riley, Inc. | Indiana Department of Transportation | 2002-08-13
|  |  | 0101328 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 0101329 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101330 |  |  | La Porte | -339679.2083
|  |  | 0101331 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101332 | Hancock |  | Cumberland | 2010-01-27 | CE
CN
|  |  | 0101333 | Lake | Baxter & Woodman, Inc. | Crown Point | 2010-01-27 | CE
CN
[5 empty] | Baxter & Woodman, Inc. | Crown Point | 2010-01-27
|  |  | 0101334 | Porter | Hy-Tech Response, Inc. | Porter | 2010-11-10 | CN
|  |  | 0101335 |  |  | Porter County | -339679.2083
|  |  | 0101336 | Delaware | GS-IN P.C. | Muncie | 2003-08-12 | CE
CN
|  |  | 0101337 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2007-05-02 | CE
CN
|  |  | 0101338 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2006-05-24 | CE
CN
|  |  | 0101339 |  | Dodd Title Corporation | Kokomo | -339679.2083
|  |  | 0101340 | Putnam | Clayton L. Roots | Greencastle | 2010-01-13 | CE
CN
|  |  | 0101341 | Tippecanoe |  | Lafayette | -339679.2083 | CN
|  |  | 0101342 | Delaware | Michael Baker International, Inc. | Yorktown | 2006-06-28 | CE
CN
|  |  | 0101343 |  | C Blair Enterprises, Inc. | Elkhart County | -339679.2083
|  |  | 0101344 | Fountain | BA Martin Architects, PC | Covington | 2004-06-15 | CE
CN
UT
|  |  | 0101345 | Bartholomew |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
|  |  |  | Jackson |  | Indiana Department of Transportation | 2002-03-19 | CE
CN
RR
|  |  | 0101346 |  | 2IM Group, LLC | Akron | -339679.2083
|  |  | 0101347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101348 | Knox | Louis Joyner, Architect | Vincennes | -339679.2083 | CN
|  |  | 0101349 |  | CGI | Evansville | -339679.2083
|  |  | 0101350 | Perry |  | Perry County | 2007-11-28 | CE
CN
|  |  | 0101351 | St. Joseph |  | South Bend | 2006-04-19 | CE
CN
|  |  | 0101352 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0101353 |  |  | Richmond | -339679.2083
|  |  | 0101354 | Clinton |  | Clinton County | 2008-06-18 | CE
CN
|  |  | 0101355 | Crawford |  | Crawford County | 2008-11-19 | CE
CN
|  |  | 0101356 | Decatur |  | Decatur County | 2003-11-18 | CE
CN
|  |  | 0101357 | Franklin |  | Franklin County | 2009-01-14 | CE
CN
|  |  | 0101358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101359 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
PE
|  |  | 0101360 | Johnson |  | Indiana Department of Natural Resources | 2005-10-19 | CE
CN
|  |  | 0101361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101362 |  |  | Indianapolis | -339679.2083
|  |  | 0101363 | Ripley |  | Ripley County | 2004-08-17 | CE
CN
|  |  | 0101364 | Warren |  | Warren County | 2008-11-19 | CE
CN
|  |  | 0101365 | Dearborn |  | Lawrenceburg | 2004-02-17 | CE
CN
PE
|  |  | 0101366 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0101367 | Orange |  | Orange County | 2007-10-03 | CN
|  |  | 0101368 | Posey |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0101369 | Union |  | Union County | -339679.2083 | CN
|  |  | 0101370 | Steuben |  | Steuben County | -339679.2083 | CE
CN
ROW
|  |  | 0101371 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0101372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101373 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101374 | Harrison |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0101375 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0101376 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0101377 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0101378 |  |  | Warrick County | -339679.2083
|  |  | 0101379 |  |  | Dubois County | -339679.2083
|  |  | 0101380 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2015-11-17 | CE
CN
PE
|  |  | 0101381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101382 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101383 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0101384 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101385 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101386 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 0101387 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-02-21 | CE
CN
RR
|  |  | 0101388 | Jackson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0101389 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101391 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101392 |  | IXOYE, Limited | Indiana Department of Transportation | -339679.2083
|  |  | 0101393 |  | American Resources Group, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 0101394 | Scott |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
PE
ROW
UT
|  |  | 0101395 |  |  | Indiana Department of Transportation | 2002-02-19
|  |  | 0101396 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0101397 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2002-12-18
|  |  | 0101398 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2002-12-18
|  |  | 0101399 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2002-12-18
|  |  | 0101400 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2002-12-18
|  |  | 0101401 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0101402 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2002-12-18
|  |  | 0101403 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2002-12-18
|  |  | 0101404 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0101405 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101406 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101407 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2003-03-25
|  |  | 0101408 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101409 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101410 | Hancock | DKA Associates, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
|  |  |  | Madison | DKA Associates, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0101411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101412 | Brown |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
ROW
UT
|  |  | 0101413 | Jackson |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
UT
|  |  | 0101414 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101415 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101416 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101417 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101418 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101419 | Hamilton |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0101420 | Madison |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
ROW
|  |  | 0101421 | Hamilton |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
ROW
UT
|  |  | 0101422 | Hamilton |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
ROW
|  |  | 0101423 | Randolph |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0101424 | Tipton |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
PE
ROW
|  |  | 0101425 | Shelby |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0101426 | Henry |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
PE
|  |  | 0101427 | Marion |  | Indiana Department of Transportation | 2009-10-07 | CE
CN
PE
UT
|  |  | 0101428 | Madison |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
PE
|  |  | 0101429 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0101430 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0101431 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2009-10-07 | CE
CN
|  |  | 0101432 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 0101433 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 0101434 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101435 | St. Joseph | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0101436 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101437 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0101438 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0101439 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0101440 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0101441 | St. Joseph |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 0101442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101443 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101444 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0101445 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0101446 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101447 | Cass |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
PE
|  |  | 0101448 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101450 | Lake | Edwards and Kelcey | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
|  |  | 0101451 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101452 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101453 | LaPorte |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0101454 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101455 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101456 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101458 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101459 |  |  | Indiana Department of Transportation | 2007-01-04
|  |  | 0101460 |  |  | Indiana Department of Transportation | 2007-01-04
|  |  | 0101461 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101462 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101463 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101467 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101468 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101469 | Lake |  | Indiana Department of Transportation | 2016-11-21 | PE
|  |  |  | Newton |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
PE
|  |  | 0101470 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101471 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101472 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101473 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101474 |  | Haas & Associates, L.L.C. | Indiana Department of Transportation | 2002-03-19
|  |  | 0101475 | Johnson |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0101476 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101477 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0101478 | Fountain |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
PE
|  |  | 0101479 | Kosciusko |  | Kosciusko County | -339679.2083 | CN
|  |  | 0101480 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0101481 |  |  | Union County | -339679.2083
|  |  | 0101482 | Clay |  | Shelby County | -339679.2083 | CN
|  |  | 0101483 | Allen |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
ROW
|  |  | 0101484 | LaGrange |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
ROW
|  |  | 0101485 | Kosciusko |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
ROW
|  |  | 0101486 | Whitley |  | Indiana Department of Transportation | 2009-08-26 | CE
CN
PE
ROW
UT
|  |  | 0101487 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101488 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101489 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101490 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | -339679.2083
|  |  | 0101491 |  | Debbie L. Morris | Indiana Department of Transportation | -339679.2083
|  |  | 0101492 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101493 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101494 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101495 | Noble |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
|  |  | 0101496 | Miami |  | Indiana Department of Transportation | 2009-08-26 | CE
CN
PE
|  |  | 0101497 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0101498 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101499 |  | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101500 | Elkhart |  | Indiana Department of Transportation | 2009-08-26 | CE
CN
PE
ROW
|  |  | 0101501 | Elkhart |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 0101502 |  | Alliance Survey Company | Indiana Department of Transportation | -339679.2083
|  |  | 0101503 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101505 | Grant |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
ROW
|  |  | 0101506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101507 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0101508 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2002-06-18
|  |  | 0101509 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0101510 |  | AES Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0101511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101512 | Adams |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 0101513 | Adams |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
ROW
|  |  | 0101514 | Jennings |  | Jennings County | -339679.2083 | CN
|  |  | 0101515 | Steuben |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0101516 | Steuben |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0101517 | Steuben |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0101518 | Steuben |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0101519 | Miami | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0101520 | Elkhart | Farren Real Estate Services | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0101521 | Blackford |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
|  |  | 0101522 | Steuben | ABt SRBI | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
|  |  | 0101523 | Kosciusko |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 0101524 | Jay |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0101525 | Elkhart |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
ROW
|  |  | 0101526 | Steuben | ABt SRBI | Indiana Department of Transportation | 2010-09-01 | CE
CN
PE
|  |  | 0101527 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
|  |  | 0101528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101529 |  | Debbie L. Morris | Indiana Department of Transportation | -339679.2083
|  |  | 0101530 | Noble |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
PE
ROW
|  |  | 0101531 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101532 | Lake | Consolidated Test Company | Hammond | 2004-03-23 | CE
CN
PE
RR
|  |  | 0101533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101534 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0101535 | Washington |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
ROW
|  |  | 0101536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200001 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0200002 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0200003 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200004 | Tippecanoe |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
ROW
|  |  | 0200005 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200006 |  |  | Indiana Department of Transportation | 2002-06-11
|  |  | 0200007 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2011-04-13
|  |  | 0200008 |  |  | Indiana Department of Transportation | 2002-07-16
|  |  | 0200009 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0200010 | Jackson |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
PE
ROW
UT
|  |  | 0200011 | Jennings |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
ROW
UT
|  |  | 0200012 | Scott |  | Indiana Department of Transportation | 2005-09-14 | CE
CN
|  |  | 0200013 | Morgan |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0200014 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200015 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0200016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200017 | Blackford |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
|  |  | 0200018 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200021 |  | Beam, Longest and Neff, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200022 |  | MainLine Management, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200023 |  | Farren Real Estate Services | Indiana Department of Transportation | 2002-06-18
|  |  | 0200024 |  | Duesler Realty House | Indiana Department of Transportation | 2002-06-18
|  |  | 0200025 | Jay |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0200026 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0200027 |  | Consolidated Test Company | Indiana Department of Transportation | 2002-03-19
|  |  | 0200028 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200029 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0200030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200032 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200033 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-07-01 | PE
ROW
|  |  | 0200034 | Marion | DCD Consulting LLC | Indiana State Agencies | 2002-03-19 | CE
CN
|  |  | 0200035 | Jefferson | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2013-03-06 | PE
ROW
UT
|  |  |  | Scott | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
ROW
UT
|  |  | 0200036 | Marion |  | Indiana Department of Transportation | 2002-06-18 | CE
CN
|  |  | 0200037 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200038 |  | Lorenz Williams Clinton | Indiana Department of Transportation | 2002-08-13
|  |  | 0200039 |  | Chicago Testing Laboratory, Inc. | Lake County | -339679.2083
|  |  | 0200040 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200041 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200042 |  | Martin Riley, Inc. | Indiana Department of Transportation | 2002-08-13
|  |  | 0200043 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200044 | Bartholomew |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0200045 | Elkhart |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0200046 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0200047 | Allen |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
ROW
|  |  | 0200048 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200049 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0200050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200051 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200053 | Marshall |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0200054 | Lake |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0200055 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CE
PE
RR
|  |  | 0200056 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CE
RR
|  |  | 0200057 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CE
CN
|  |  | 0200058 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0200059 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0200060 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0200061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200063 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200064 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200065 | White |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
ROW
|  |  | 0200066 | White |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0200067 | White |  | Indiana Department of Transportation | 2009-10-21 | CE
CN
PE
|  |  | 0200068 | Newton | Civil Engineering Consultants | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
UT
|  |  | 0200069 | Newton |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
PE
ROW
|  |  | 0200070 | Newton |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
PE
ROW
RR
|  |  | 0200071 | White |  | Indiana Department of Transportation | 2009-10-21 | CE
CN
PE
|  |  | 0200072 | White |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0200073 | Jasper |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
PE
|  |  | 0200074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200075 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200076 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200077 | Posey |  | Indiana Department of Transportation | 2002-01-15 | CE
CN
PE
[6 empty] | Indiana Department of Transportation | 2002-01-15
|  |  | 0200078 | Starke |  | Starke County | -339679.2083 | CN
|  |  | 0200079 | LaGrange |  | LaGrange County | -339679.2083 | CN
|  |  | 0200080 | Adams |  | Adams County | -339679.2083 | CN
|  |  | 0200081 | White | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200082 |  | Another Test Company | Hamilton County | -339679.2083
|  |  | 0200083 |  | Another Test Company | Hamilton County | -339679.2083
|  |  | 0200084 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0200085 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200086 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0200087 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0200088 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0200089 | Boone |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0200090 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200091 | Fountain |  | Fountain County | -339679.2083 | CN
|  |  | 0200092 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200093 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200094 | Howard | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200095 | Knox |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
RR
|  |  | 0200096 | Montgomery |  | Montgomery County | -339679.2083 | CN
|  |  | 0200097 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2002-04-23
|  |  | 0200098 |  | ABt SRBI | Indiana Department of Transportation | 2002-04-23
|  |  | 0200099 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2005-10-19 | CE
CN
ROW
|  |  | 0200100 | Franklin |  | Franklin County | -339679.2083 | CN
|  |  | 0200101 | Monroe |  | Monroe County | -339679.2083 | CN
|  |  | 0200102 |  |  | Martin County | -339679.2083
|  |  | 0200103 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200104 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 0200105 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 0200106 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200107 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 0200108 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 0200109 |  |  | Lake County | -339679.2083
|  |  | 0200110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200118 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200120 | Clark |  | Clarksville | 2016-12-14 | CE
CN
PE
ROW
|  |  | 0200121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200122 | Jasper |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0200123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200126 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200129 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200134 |  |  | Indiana Department of Transportation | 2007-01-04
|  |  | 0200135 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0200136 |  |  | Indiana Department of Transportation | 2007-01-04
|  |  | 0200137 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-04-23
|  |  | 0200138 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200139 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0200140 | Lake |  | Indiana Department of Transportation | 2016-11-21 | PE
|  |  |  | Newton |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 0200141 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200142 |  | EHI Consultants, Inc. | Indiana Department of Transportation | 2003-02-18
|  |  | 0200143 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2003-02-18
|  |  | 0200144 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200145 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200146 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200147 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  |  | Wayne | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0200148 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200149 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200150 | Madison |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200151 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200152 | Grant |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200153 | Jay |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200154 | Randolph |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200156 | Tipton |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200157 | Hamilton |  | Indiana Department of Transportation | 2004-09-14 | CE
CN
|  |  | 0200158 | Randolph |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200159 | Hamilton | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  |  | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0200160 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200161 | Delaware |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0200162 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200163 | Randolph |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200164 | Hamilton |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0200165 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0200166 | Henry |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
|  |  | 0200167 | Rush |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200168 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200169 | Hancock |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0200170 | Hancock |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  |  | Henry |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200171 |  | McCullouch Consulting, LLC | Indiana Department of Transportation | 2003-01-22
|  |  | 0200172 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0200173 | Randolph |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200174 | Vigo | Indiana Infrastructure Partners, LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
|  |  | 0200175 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2002-07-16
|  |  | 0200176 |  | Dodd Title Corporation | Indiana Department of Transportation | 2002-04-23
|  |  | 0200177 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0200178 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200179 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-06-18 | CE
CN
UT
|  |  | 0200180 | Clinton |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0200181 |  | Anelena Ackerly | Indiana Department of Transportation | -339679.2083
|  |  | 0200182 | Sullivan |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
RR
|  |  | 0200183 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083 | CE
OT
RR
UT
|  |  | 0200184 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
OT
RR
UT
|  |  | 0200185 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
OT
RR
UT
|  |  | 0200186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200187 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200188 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2010-04-14 | CE
CN
PE
ROW
RR
[5 empty] | Browning Day Mullins Dierdorf Architects | East Chicago | 2010-04-14
|  |  | 0200189 | Delaware |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0200190 | Johnson |  | Indiana Department of Transportation | 2002-08-13 | CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0200191 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0200192 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0200193 |  |  | Indiana Department of Transportation | 2002-05-24
|  |  | 0200194 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
UT
[6 empty] | Indiana Department of Transportation | 2003-06-17
|  |  | 0200195 | Union |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0200196 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0200197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200198 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200199 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200200 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-06-11
|  |  | 0200201 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0200202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200204 | Daviess |  | Indiana Department of Transportation | 2009-10-07 | CE
CN
PE
ROW
UT
|  |  | 0200205 |  |  | Gibson County | -339679.2083
|  |  | 0200206 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | 2002-08-13
|  |  | 0200207 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0200208 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200209 | Posey |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
ROW
UT
|  |  |  | Spencer |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
ROW
UT
|  |  | 0200210 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200211 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0200212 | Marion |  | Indiana Department of Transportation | 2002-06-18 | CE
CN
UT
|  |  | 0200213 | Daviess |  | Dubois County | 2006-12-13 | CE
CN
|  |  |  | Dubois |  | Dubois County | 2006-12-13 | CE
CN
|  |  | 0200214 | Posey |  | Posey County | -339679.2083 | CN
|  |  | 0200215 |  |  | Pulaski County | 2002-06-18
|  |  | 0200216 |  |  | Porter County | 2003-07-15
|  |  | 0200217 |  |  | Jefferson County | 2003-05-20
|  |  | 0200218 |  |  | Owen County | 2003-05-20
|  |  | 0200219 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0200220 |  | Engineering Resources, Inc. | Jefferson County | 2005-06-22
|  |  | 0200221 |  |  | Monroe County | -339679.2083
|  |  | 0200222 | Allen |  | Indiana Department of Transportation | 2009-03-11 | PE
ROW
|  |  | 0200223 | Various |  | Indiana State Agencies | -339679.2083 | CN
|  |  | 0200224 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0200225 |  |  | Morgan County | -339679.2083
|  |  | 0200226 |  |  | Porter County | -339679.2083
|  |  | 0200227 |  | CGI | Vanderburgh County | -339679.2083
|  |  | 0200228 | Hamilton |  | Indiana Department of Transportation | 2005-06-01 | CE
CN
|  |  | 0200229 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0200230 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200231 | Huntington |  | Indiana Department of Transportation | 2013-08-14 | CE
CN
PE
ROW
UT
|  |  | 0200232 | Hancock |  | Indiana Department of Transportation | 2002-08-13 | CE
CN
|  |  | 0200233 | Hancock |  | Hancock County | -339679.2083 | CN
|  |  | 0200234 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0200235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200236 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 0200237 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 0200238 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0200239 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0200240 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0200241 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200242 | Tipton | Land Construction Corp | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200243 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200244 | Whitley |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200245 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2007-12-12 | CE
CN
PE
ROW
|  |  | 0200246 | Rush |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
PE
ROW
|  |  | 0200247 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200248 | Greene | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200249 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
PE
ROW
RR
UT
[5 empty] | GeoSolutions, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0200250 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200251 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200252 |  |  | Hancock County | -339679.2083
|  |  | 0200253 | Allen |  | Allen County | -339679.2083 | CN
|  |  | 0200254 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200255 |  | Kristine Fallon Associates, Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0200256 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2002-09-24 | CN
RR
UT
|  |  | 0200257 | St. Joseph |  | Indiana Department of Transportation | 2003-09-16 | CE
CN
RR
|  |  | 0200258 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200259 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0200260 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200261 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0200262 | St. Joseph |  | St. Joseph County | 2005-05-25 | CE
CN
|  |  | 0200263 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2002-08-13 | CE
CN
ROW
|  |  | 0200264 |  |  | Indiana Department of Transportation | 2002-06-11
|  |  | 0200265 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200266 |  |  | Indiana Department of Transportation | 2002-06-11
|  |  | 0200267 |  | MHM Associates, Inc. | Indiana Department of Transportation | 2002-08-13
|  |  | 0200268 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  | 0200269 | Hendricks | A & A Consultants, Inc. | Amo | -339679.2083 | CN
|  |  | 0200270 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | 2003-03-25
|  |  | 0200271 | Ohio |  | Ohio County | -339679.2083 | CN
|  |  | 0200272 |  |  | Clark County | -339679.2083
|  |  | 0200273 | Fulton |  | Fulton County | -339679.2083 | CN
|  |  | 0200274 |  |  | Morgan County | -339679.2083
|  |  | 0200275 | Porter |  | Porter County | -339679.2083 | CN
|  |  | 0200276 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0200277 |  |  | Indiana Department of Transportation | 2002-06-18
|  |  | 0200278 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-06-18
|  |  | 0200279 |  |  | Indiana Department of Transportation | 2001-05-22
|  |  | 0200280 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200281 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200282 | Hendricks | GAI Consultants, Inc. | Indiana Department of Transportation | 2007-06-06 | CE
CN
RR
|  |  |  | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2007-06-06 | CE
CN
PE
ROW
UT
|  |  | 0200283 |  |  | Indiana Department of Transportation | 2002-04-23
|  |  | 0200285 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200286 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200287 | Adams |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0200288 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0200289 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2002-11-19
|  |  | 0200290 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2002-10-22
|  |  | 0200291 |  | Collier Transport Inc. | Indiana Department of Transportation | 2002-05-21
|  |  | 0200292 |  | CGI | Indiana Department of Transportation | 2002-04-23
|  |  | 0200293 |  | Debbie L. Morris | Indiana Department of Transportation | -339679.2083
|  |  | 0200294 | Harrison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  |  | Washington |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0200295 | Lawrence |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  |  | Orange |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200296 |  |  | Indiana Department of Natural Resources | 2002-05-21
|  |  | 0200297 |  |  | Indiana Department of Natural Resources | 2002-05-21
|  |  | 0200298 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200299 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200300 | Lake | Karen | Indiana Department of Transportation | 2002-09-17 | CE
CN
|  |  | 0200301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200302 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200303 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200305 | Vigo |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  | 0200306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200307 | Shelby |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200308 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200309 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200310 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  |  | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200312 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200313 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200315 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200316 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200317 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200318 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200319 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200320 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200321 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200322 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200323 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200324 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200325 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200326 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200327 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200328 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200329 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Porter |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200330 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200331 | Porter |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200332 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200333 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200334 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200335 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200336 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200337 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200338 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200339 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200340 | Marion |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
UT
|  |  | 0200341 | Dekalb |  | Indiana Department of Transportation | 2002-07-16 | CE
UT
|  |  | 0200342 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2002-06-11
|  |  | 0200343 | Martin |  | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0200344 | Lawrence |  | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0200345 | Sullivan |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0200346 | Jasper |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
PE
UT
|  |  | 0200347 |  |  | Bartholomew County | -339679.2083
|  |  | 0200348 | Floyd |  | Floyd County | -339679.2083 | CN
|  |  | 0200349 | Switzerland |  | Switzerland County | -339679.2083 | CN
|  |  | 0200350 | Marshall |  | Marshall County | -339679.2083 | CN
|  |  | 0200351 | Johnson |  | Johnson County | -339679.2083 | CN
|  |  | 0200352 | Orange |  | Orange County | -339679.2083 | CN
|  |  | 0200353 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200354 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2002-05-21
|  |  | 0200355 |  |  | Indiana Department of Transportation | 2002-05-21
|  |  | 0200356 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0200357 | Wabash |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  | 0200358 |  | Home Guide Realty Services | Indiana Department of Transportation | 2003-01-22
|  |  | 0200359 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200360 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200362 | Martin |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
PE
ROW
UT
|  |  | 0200363 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200364 | Fountain |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0200365 | Fountain |  | Indiana Department of Transportation | 2004-06-15 | CE
CN
|  |  | 0200366 | Noble |  | Noble County | -339679.2083 | CN
|  |  | 0200367 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200368 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0200369 | Vanderburgh | CGI | Evansville | 2004-12-14 | CE
CN
|  |  | 0200370 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2006-11-01 | CE
CN
|  |  | 0200371 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | CN
|  |  | 0200372 |  |  | Indiana Department of Transportation | 2002-07-16
|  |  | 0200373 |  |  | Indiana Department of Transportation | 2002-07-16
|  |  | 0200374 | Dekalb | Quantum Spatial, Inc. | Auburn | -339679.2083 | CN
|  |  | 0200375 | Vigo |  | Vigo County | 2007-10-31 | CE
CN
ROW
RR
UT
|  |  | 0200376 | Vigo |  | Vigo County | 2007-10-31 | CE
CN
ROW
RR
UT
|  |  | 0200377 | LaPorte |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
PE
ROW
RR
UT
|  |  | 0200378 | Vigo |  | Vigo County | 2009-02-11 | CN
RR
|  |  | 0200379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200382 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200383 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200384 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2012-11-20 | CE
CN
PE
ROW
RR
UT
|  |  | 0200385 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200386 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200387 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200388 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200389 | Hendricks |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0200390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200391 | Wabash |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0200392 | Hendricks |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
PE
ROW
UT
|  |  | 0200393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200394 | Lake |  | Indiana Department of Transportation | 2003-08-12 | CE
CN
PE
RR
UT
|  |  | 0200395 | Lake |  | Indiana Department of Transportation | 2003-08-12 | CE
CN
PE
RR
UT
|  |  | 0200396 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200397 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200398 | Lake |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
UT
|  |  | 0200399 | Lake |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
UT
|  |  | 0200400 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200401 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200402 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200403 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200404 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200405 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200406 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200407 | Lake |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
UT
|  |  | 0200408 | Lake |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
UT
|  |  | 0200409 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200410 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200412 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200413 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200414 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200415 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200416 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200417 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | 2007-04-18 | CE
CN
PE
ROW
|  |  | 0200418 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200419 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200421 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200422 | Owen |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0200423 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0200424 |  | IXOYE, Limited | Indiana Department of Transportation | 2003-02-18
|  |  | 0200425 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0200426 | Hamilton | Appraising Indiana, LLC | Indiana Department of Transportation | 2005-05-25 | CE
CN
RR
|  |  |  | Tipton | Appraising Indiana, LLC | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0200427 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0200428 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0200429 | Putnam |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0200430 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200431 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200432 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200433 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200434 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200435 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200436 | St. Joseph |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
PE
ROW
|  |  | 0200437 | Jasper |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200438 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0200439 | Pulaski |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  |  | Starke |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200440 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200441 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200443 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200444 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0200445 | Lake |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200446 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200447 | Newton |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0200448 | Fulton | InfoTech | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200450 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200451 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200452 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200453 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200454 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200455 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200456 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200458 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200459 |  |  | Indiana Department of Transportation | 2009-05-31
|  |  | 0200460 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200461 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200462 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200463 | Hendricks |  | Indiana Department of Transportation | 2009-05-27 | CE
CN
|  |  | 0200464 | Hendricks |  | Indiana Department of Transportation | 2009-05-27 | CE
CN
|  |  | 0200465 | Dubois |  | Indiana Department of Transportation | 2002-08-13 | PE
|  |  | 0200466 | LaGrange | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
|  |  | 0200467 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200468 | LaGrange | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0200469 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2002-09-17
|  |  | 0200470 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200471 |  | Burns & McDonnell Engineering Company, Inc. | Indiana Department of Transportation | 2002-11-19
|  |  | 0200472 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200473 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200474 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200475 | Sullivan | Klug Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200476 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200477 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200478 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200479 | Vermillion | Apex Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200480 | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200481 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200482 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200483 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200484 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200485 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200486 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200487 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200488 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200489 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200490 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200491 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200492 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200494 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200495 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200496 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200497 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200498 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200499 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200500 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200501 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200502 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200503 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200504 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200505 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2003-06-10
|  |  | 0200506 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200507 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200508 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200509 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200510 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200511 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200512 | Porter |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200513 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0200514 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200515 | Hancock |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200516 | Hancock |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200517 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200518 | Hancock |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200519 | Marion | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200520 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200521 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200522 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200523 | Putnam |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200524 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200525 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200526 | Spencer |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200527 | Porter |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200528 | Delaware |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200529 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200530 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0200531 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-10 | CE
CN
|  |  |  | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-10 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-10 | CE
CN
|  |  | 0200532 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200533 |  | Lorenz Williams Clinton | Indiana Department of Transportation | 2002-08-13
|  |  | 0200534 | Vanderburgh | CGI | Indiana Department of Transportation | 2003-10-21 | CE
CN
|  |  | 0200535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200538 | Vanderburgh |  | Indiana Department of Transportation | 2003-05-20 | CN
PE
ROW
RR
UT
|  |  |  | Warrick |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  | 0200539 | Johnson |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0200540 | Lake | Brenner Design Incorporated | Dyer | 2002-05-21 | CE
CN
|  |  | 0200541 |  | Brenner Design Incorporated | Dyer | 2002-05-21
|  |  | 0200542 |  |  | Indiana Department of Transportation | 2002-08-13
|  |  | 0200543 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200544 |  | Eco Logic, LLC | Indiana Department of Transportation | 2002-09-17
|  |  | 0200545 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200546 | Steuben | ABt SRBI | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0200547 | Wabash |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  | 0200548 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200549 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200550 | Morgan |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0200551 | Perry |  | Perry County | -339679.2083 | CN
|  |  | 0200552 | Vermillion |  | Vermillion County | -339679.2083 | CN
|  |  | 0200553 | Marion |  | Marion County | -339679.2083 | CN
|  |  | 0200554 | Jennings |  | Jennings County | -339679.2083 | CN
PE
|  |  | 0200555 | Lawrence |  | Lawrence County | -339679.2083 | CN
|  |  | 0200556 | Washington |  | Washington County | -339679.2083 | CN
|  |  | 0200557 | Harrison |  | Harrison County | -339679.2083 | CN
|  |  | 0200558 |  |  | Newton County | -339679.2083
|  |  | 0200559 | Benton |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0200560 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2003-08-12
|  |  | 0200561 |  | AECON, Inc. | Indiana Department of Transportation | 2004-01-21
|  |  | 0200562 | Jasper |  | Jasper County | -339679.2083 | CN
|  |  | 0200563 | Steuben | ABt SRBI | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0200564 |  |  | Indiana Department of Transportation | 2002-11-26
|  |  | 0200565 | Hendricks |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
UT
|  |  | 0200566 | Hendricks |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
UT
|  |  | 0200567 | Porter |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
RR
|  |  | 0200568 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0200569 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0200570 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0200571 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200572 | Marion |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200573 | Marion |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200574 | Montgomery |  | Indiana Department of Transportation | 2003-02-18 | CE
CN
|  |  | 0200575 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200576 | Marion |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200577 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0200578 | Vermillion |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  |  | Warren |  | Indiana Department of Transportation | 2002-12-18 | CE
CN
|  |  | 0200579 | Hendricks |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
UT
|  |  | 0200580 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200581 | Hendricks |  | Indiana Department of Transportation | 2002-11-19 | CE
CN
|  |  | 0200582 |  | Consolidated Test Company | Indiana Department of Transportation | 2003-11-18
|  |  | 0200583 | Hendricks |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
[6 empty] | Indiana Department of Transportation | 2003-09-25
|  |  | 0200584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200585 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200586 | Spencer |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0200587 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0200588 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0200589 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200590 | Clark | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083 | RR
|  |  | 0200591 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0200592 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0200593 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0200594 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0200595 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0200596 | Clay |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0200597 | Benton |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0200598 | Clinton |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0200599 | Madison | AAC Environmental Consulting, LLC | Anderson | 2015-03-04 | CE
CN
UT
|  |  | 0200600 | Lake |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0200601 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0200602 | Clark |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0200603 | Rush |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
ROW
[6 empty] | Indiana Department of Transportation | 2016-01-13
|  |  | 0200604 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0200605 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0200606 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
|  |  | 0200607 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0200608 | Lake |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0200609 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-31 | CN
[5 empty] | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-31
|  |  | 0200610 | Clark |  | Indiana Department of Transportation | 2005-05-31 | CN
|  |  | 0200611 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200612 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2010-05-31 | CN
|  |  | 0200613 | Clark |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0200614 | Crawford |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
ROW
RR
UT
[6 empty] | Indiana Department of Transportation | 2005-02-16
|  |  | 0200615 | Crawford |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
ROW
RR
UT
[6 empty] | Indiana Department of Transportation | 2005-02-16
|  |  | 0200616 | Crawford |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
ROW
RR
UT
[6 empty] | Indiana Department of Transportation | 2005-02-16
|  |  | 0200617 | Crawford |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
ROW
RR
UT
[6 empty] | Indiana Department of Transportation | 2005-02-16
|  |  | 0200618 | Crawford |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
ROW
RR
UT
[6 empty] | Indiana Department of Transportation | 2005-02-16
|  |  | 0200619 | Crawford |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0200620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200621 | Marion |  | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200622 | Hendricks |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0200623 | Hendricks |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0200624 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200625 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200626 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200627 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200628 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200629 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2006-03-15 | CE
CN
ROW
UT
|  |  | 0200630 |  | Hatch Mott MacDonald | Indiana Department of Transportation | 2003-03-25
|  |  | 0200631 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200632 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200633 | Vanderburgh |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0200634 | Vanderburgh |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0200635 | Vanderburgh |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0200636 | Vanderburgh |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0200637 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200638 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200639 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200640 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200641 | Warrick |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
ROW
UT
|  |  | 0200642 | Boone |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  |  | Montgomery |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0200643 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200644 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200645 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200646 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200647 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200648 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0200649 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0200650 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200651 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200652 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2003-06-17
|  |  | 0200653 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200654 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200655 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200656 | Tippecanoe |  | Tippecanoe County | 2006-11-15 | CE
CN
PE
ROW
UT
|  |  | 0200657 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0200658 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200659 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200660 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200661 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200662 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0200663 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200664 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200665 |  | EcoTec, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0200666 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200667 |  | ASA Land Surveying | Indiana Department of Transportation | 2003-05-20
|  |  | 0200668 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200669 |  | CHA, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0200670 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200672 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200673 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200674 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200675 |  | Charles Hendricks & Associates PC | Indiana Department of Transportation | 2003-01-22
|  |  | 0200676 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200677 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200678 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200679 |  | Casteel Real Estate | Indiana Department of Transportation | 2003-03-25
|  |  | 0200680 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0200681 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200682 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200683 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200684 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0200685 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200686 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200687 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200688 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200689 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0200690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200691 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200692 |  |  | Indiana Department of Transportation | 2002-10-22
|  |  | 0200693 |  |  | Indiana Department of Transportation | 2002-10-22
|  |  | 0200694 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200695 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0200696 |  |  | Indiana Department of Transportation | 2002-09-17
|  |  | 0200697 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0200698 | Hendricks |  | Indiana Department of Transportation | 2002-10-08 | CE
CN
PE
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2002-10-08 | CE
CN
PE
UT
|  |  | 0200699 | Hancock |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
PE
UT
|  |  | 0200700 | Hancock |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
|  |  | 0200701 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2003-02-18
|  |  | 0200702 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0200703 |  | ASA Land Surveying | Bedford | -339679.2083
|  |  | 0200704 |  |  | Avon | -339679.2083
|  |  | 0200705 | Hendricks | All About Pavements, Inc. | Brownsburg | 2013-12-18 | CE
CN
RR
UT
|  |  | 0200706 | Vermillion | Archaeology and Geomorphology Services | Clinton | 2005-07-20 | CE
CN
|  |  | 0200707 |  | Associated Appraisal Group, Inc. | Columbia City | -339679.2083
|  |  | 0200708 |  | Associated Right-of-Way Services, Inc. | Columbus | -339679.2083
|  |  | 0200709 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 0200710 | Hancock | CoCal Consulting, LLC | Greenfield | 2006-06-21 | CE
CN
UT
|  |  | 0200711 |  |  | Blackford County | -339679.2083
|  |  | 0200712 | Steuben |  | Indiana Department of Transportation | 2003-02-18 | CE
CN
|  |  | 0200713 |  |  | Boone County | -339679.2083
|  |  | 0200714 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0200715 | Porter |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
RR
|  |  | 0200716 | Blackford | Continental Mapping Consultants, LLC | Hartford City | 2005-09-14 | CE
CN
|  |  | 0200717 |  |  | Huntingburg | -339679.2083
|  |  | 0200718 | Dubois |  | Huntingburg | 2009-05-06 | CE
CN
|  |  | 0200719 | Porter |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
RR
|  |  | 0200720 | Clinton | Carters Appraisal Service | Clinton County | 2006-02-15 | CE
CN
|  |  | 0200721 | White | Fugro Roadware, Inc. | Monticello | 2007-02-21 | CE
CN
PE
ROW
|  |  | 0200722 | Dearborn |  | Dearborn County | 2008-11-19 | CE
CN
|  |  | 0200723 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 0200724 | Grant | Dave Helton & Associates, Inc. | Grant County | 2009-08-12 | CE
CN
|  |  | 0200725 | Franklin |  | Franklin County | 2008-09-04 | CE
CN
|  |  | 0200726 | Grant | ERES International, Inc. | Grant County | 2005-06-22 | CE
CN
|  |  | 0200727 | Greene | Abonmarche Consultants of Indiana L.L.C. | Greene County | 2007-10-03 | CE
CN
|  |  | 0200728 |  |  | Huntington County | -339679.2083
|  |  | 0200729 | Jackson | Janssen & Spaans Engineering, Inc. | Jackson County | 2013-08-07 | CE
CN
PE
ROW
UT
|  |  | 0200730 | LaPorte |  | LaPorte County | 2009-03-11 | CE
CN
|  |  | 0200731 |  |  | Lawrence County | -339679.2083
|  |  | 0200732 |  |  | Marshall County | -339679.2083
|  |  | 0200733 | Vanderburgh |  | Vanderburgh County | -339679.2083 | CN
|  |  | 0200734 | Clay |  | Clay County | -339679.2083 | CN
|  |  | 0200735 | Lake |  | Lake County | -339679.2083 | CN
|  |  | 0200736 | Elkhart |  | Elkhart County | -339679.2083 | CN
|  |  | 0200737 | Hendricks |  | Hendricks County | -339679.2083 | CN
|  |  | 0200738 | Owen |  | Owen County | -339679.2083 | CN
|  |  | 0200739 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2014-03-05 | CE
CN
PE
ROW
RR
|  |  | 0200740 |  |  | Marshall County | -339679.2083
|  |  | 0200741 |  |  | Owen County | -339679.2083
|  |  | 0200742 | Owen |  | Owen County | 2008-02-06 | CE
CN
RR
|  |  | 0200743 |  |  | Owen County | -339679.2083
|  |  | 0200744 | Parke |  | Parke County | 2006-08-16 | CE
CN
|  |  | 0200745 | Putnam |  | Putnam County | 2007-12-12 | CE
CN
|  |  | 0200746 |  |  | Starke County | -339679.2083
|  |  | 0200747 | Sullivan |  | Sullivan County | 2008-09-04 | CE
CN
UT
|  |  | 0200748 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 0200749 | Greene |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
ROW
UT
|  |  |  | Knox |  | Indiana Department of Transportation | 2011-02-09 | CE
ROW
UT
|  |  | 0200750 |  |  | St. Joe | -339679.2083
|  |  | 0200751 | Vigo |  | Vigo County | 2008-07-09 | CE
CN
|  |  | 0200752 | Wabash |  | Wabash County | 2005-05-25 | CE
CN
RR
|  |  | 0200753 | Warren |  | Warren County | 2010-04-14 | CE
CN
|  |  | 0200754 |  |  | Wells County | -339679.2083
|  |  | 0200755 |  |  | Wells County | -339679.2083
|  |  | 0200756 | Vermillion |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200757 | Johnson | Casteel Real Estate | Franklin | 2012-01-11 | CE
CN
|  |  | 0200758 | Gibson | Harvard Title Searching | Indiana Department of Transportation | 2014-11-12 | PE
ROW
|  |  | 0200759 |  |  | Rush County | -339679.2083
|  |  | 0200760 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200761 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200762 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200763 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
|  |  | 0200764 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200766 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200767 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200768 | Madison |  | Indiana Department of Transportation | 2003-04-22 | CE
PE
|  |  | 0200769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200770 | Tippecanoe | ASA Engineering Consultants, Inc. | Battle Ground | 2008-07-16 | CE
CN
RR
UT
|  |  | 0200771 |  | ATSI Engineering Services | Beverly Shores | -339679.2083
|  |  | 0200772 | Marshall | Active Environmental Services, Inc. | Bourbon | 2006-01-18 | CE
CN
RR
|  |  | 0200773 | Starke |  | Knox | 2005-10-19 | CE
CN
|  |  | 0200774 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200775 | Lawrence | ICA Engineering, Inc. | Mitchell | 2007-10-17 | CE
CN
PE
ROW
|  |  | 0200776 | Dekalb | Mader Design, LLC | Waterloo | 2005-03-16 | CE
CN
RR
|  |  | 0200777 | Lake |  | Porter County | 2008-08-20 | CE
CN
RR
|  |  |  | Porter |  | Porter County | 2008-08-20 | CE
CN
RR
|  |  | 0200778 | Cass | Eco Logic, LLC | Logansport | 2004-10-19 | CE
CN
|  |  | 0200779 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
RR
|  |  | 0200780 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0200781 |  | Civil Designs, LLP | Indiana Department of Transportation | -339679.2083
|  |  | 0200782 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200783 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0200784 | Hancock |  | Indiana Department of Transportation | 2008-12-10 | PE
|  |  | 0200785 |  | Consolidated Test Company | Indiana Department of Transportation | 2003-10-21
|  |  | 0200786 | Floyd |  | Floyd County | 2014-03-05 | CE
CN
ROW
UT
|  |  | 0200787 | Grant |  | Grant County | 2006-03-15 | CE
CN
|  |  | 0200788 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200789 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | -339679.2083
|  |  | 0200790 |  | Certified Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200791 |  |  | Morgan County | -339679.2083
|  |  | 0200792 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2004-06-15 | CE
CN
RR
UT
|  |  | 0200793 |  |  | Morgan County | -339679.2083
|  |  | 0200794 |  |  | Newton County | -339679.2083
|  |  | 0200795 | Hendricks |  | Indiana Department of Transportation | 2002-10-08 | CE
CN
|  |  | 0200796 | Hendricks |  | Indiana Department of Transportation | 2002-10-08 | CE
CN
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2002-10-08 | CE
CN
|  |  | 0200797 | Warren |  | Indiana Department of Transportation | 2003-05-20 | PE
RR
|  |  | 0200798 | Clinton | Iteris, Inc. | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0200799 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0200800 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0200801 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0200802 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200803 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200804 | Sullivan |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0200805 |  | Ball State University | Indiana Department of Transportation | 2003-05-20
|  |  | 0200806 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200807 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200808 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200809 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0200810 | Porter | Huff & Huff, Inc. | Portage | -339679.2083 | CN
|  |  | 0200811 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2013-02-06 | CE
CN
RR
UT
|  |  | 0200812 | Clark |  | Clark County | 2009-08-12 | CE
CN
ROW
UT
|  |  | 0200813 | Hendricks |  | Hendricks County | 2004-10-19 | PE
|  |  | 0200814 | Hendricks |  | Hendricks County | 2009-11-04 | CE
CN
PE
|  |  | 0200815 |  |  | Tipton County | -339679.2083
|  |  | 0200816 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200817 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200818 | Jackson |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
ROW
|  |  | 0200819 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200821 | Montgomery |  | Montgomery County | 2007-10-17 | CE
CN
|  |  | 0200822 | Marshall |  | Marshall County | 2009-11-04 | CE
CN
RR
UT
|  |  | 0200823 |  |  | Shelby County | -339679.2083
|  |  | 0200824 | Hancock |  | Hancock County | 2009-02-11 | CE
CN
|  |  | 0200825 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0200826 |  | Wilcox Environmental Engineering, Inc. | Fayette County | -339679.2083
|  |  | 0200827 |  |  | Fayette County | -339679.2083
|  |  | 0200828 | Cass |  | Cass County | 2006-05-10 | CE
CN
|  |  | 0200829 | Cass | Eco Logic, LLC | Cass County | 2006-05-10 | CE
CN
|  |  | 0200830 | Marion | DCD Consulting LLC | Indianapolis | 2003-06-17 | CE
CN
|  |  | 0200831 |  |  | Spencer County | -339679.2083
|  |  | 0200832 |  | ABt SRBI | Indiana Department of Transportation | 2002-11-19
|  |  | 0200833 |  |  | Grant County | -339679.2083
|  |  | 0200834 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200835 |  | Bidinfo | Indiana Department of Transportation | 2003-03-25
|  |  | 0200836 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0200837 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200838 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200839 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200840 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200841 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200842 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200843 |  | Casteel Real Estate | Indiana Department of Transportation | 2003-03-25
|  |  | 0200844 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0200845 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0200846 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200847 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2003-08-12
|  |  | 0200848 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2003-08-12
|  |  | 0200849 | Vanderburgh | CGI | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
RR
|  |  | 0200850 | Elkhart |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0200851 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0200852 |  | Lonco, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0200853 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0200854 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2007-05-02
|  |  | 0200855 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0200856 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0200857 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0200858 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0200859 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0200860 | Marion | DCD Consulting LLC | Indianapolis | 2004-11-16 | CN
|  |  | 0200861 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2011-03-09 | CE
CN
PE
ROW
|  |  | 0200862 |  |  | Indiana Department of Natural Resources | 2002-12-18
|  |  | 0200863 |  |  | Indiana Department of Transportation | 2002-11-19
|  |  | 0200864 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200865 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0200866 | Dubois |  | Indiana Department of Transportation | 2004-09-14 | CE
CN
|  |  | 0200867 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2004-04-20
|  |  | 0200868 | Spencer |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Warrick |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0200869 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0200870 | Vanderburgh | CGI | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0200871 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200872 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
RR
UT
|  |  | 0200873 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200874 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2010-03-03 | PE
ROW
UT
[5 empty] | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2010-03-03
|  |  | 0200875 | St. Joseph |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0200876 | Vanderburgh |  | Indiana Department of Transportation | 2003-04-22 | PE
ROW
|  |  |  | Warrick |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
UT
|  |  | 0200877 | LaPorte |  | LaPorte County | 2003-04-22 | CE
CN
|  |  | 0200878 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200879 |  |  | Ohio County | -339679.2083
|  |  | 0200880 | Warrick |  | Indiana Department of Transportation | 2010-03-03 | CE
CN
|  |  | 0200881 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0200882 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200883 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200884 | Allen |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0200885 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200886 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200887 | Huntington |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
ROW
|  |  | 0200888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200889 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200890 | Adams |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
PE
ROW
|  |  | 0200891 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200892 |  | HE-BFS, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200893 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0200894 | Wells | Linebach Funkhouser, Inc. | Indiana Department of Transportation | 2009-07-29 | CE
CN
PE
ROW
|  |  | 0200895 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0200896 | Hancock |  | Hancock County | 2006-06-21 | CE
CN
|  |  | 0200897 | Miami | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0200898 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200899 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200900 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2002-03-19
|  |  | 0200901 | LaPorte |  | LaPorte County | 2003-09-16 | CE
CN
PE
|  |  | 0200902 |  |  | LaPorte County | 2003-04-22
|  |  | 0200903 | Boone |  | Indiana Department of Transportation | 2009-09-24 | CE
CN
PE
RR
|  |  | 0200904 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200905 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 0200906 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200907 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200908 |  |  | Indiana Department of Transportation | 2002-09-24
|  |  | 0200909 |  |  | Scottsburg | -339679.2083
|  |  | 0200910 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2003-09-16 | CE
CN
|  |  | 0200911 |  | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200912 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0200913 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200914 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
|  |  | 0200915 | Wabash |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
ROW
|  |  | 0200916 |  | Franco Consulting Engineers, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200917 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-05-12 | CE
CN
PE
|  |  | 0200918 | Steuben | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
ROW
|  |  | 0200919 | Wabash |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
|  |  | 0200920 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200921 | Elkhart |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0200922 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0200923 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2015-02-18 | CE
CN
PE
|  |  | 0200924 | Miami |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
|  |  | 0200925 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200926 | Miami | Atlas Appraisals, LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0200927 | Whitley |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
|  |  | 0200928 |  | Foresight Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200929 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200930 | Elkhart |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0200931 | Elkhart |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0200932 | Allen |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
PE
|  |  | 0200933 | Jay |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
|  |  | 0200934 | Dekalb |  | Indiana Department of Transportation | 2009-10-21 | CE
CN
PE
|  |  | 0200935 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
RR
|  |  | 0200936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200937 | Kosciusko |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
PE
ROW
RR
|  |  | 0200938 | Kosciusko |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0200939 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200940 | Wells | Hardlines Design Company | Indiana Department of Transportation | 2007-03-21 | CE
CN
UT
|  |  | 0200941 | Montgomery |  | Montgomery County | 2003-07-15 | CE
CN
RR
UT
|  |  | 0200942 | Montgomery |  | Montgomery County | 2004-09-14 | CE
CN
|  |  | 0200943 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0200944 | Pulaski |  | Pulaski County | -339679.2083 | CN
|  |  | 0200945 | Howard |  | Howard County | -339679.2083 | CN
|  |  | 0200946 | Tipton |  | Tipton County | -339679.2083 | CN
|  |  | 0200947 | Madison |  | Madison County | -339679.2083 | CN
|  |  | 0200948 | Tippecanoe |  | Tippecanoe County | -339679.2083 | CN
|  |  | 0200949 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0200950 | Gibson |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
RR
|  |  | 0200951 | Gibson |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0200952 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0200953 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200954 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200955 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0200956 | Allen |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0200957 |  | Alfred Benesch & Company | Indiana Department of Transportation | 2003-04-22
|  |  | 0200958 | Warren |  | Indiana Department of Transportation | 2003-05-20 | PE
RR
|  |  | 0200959 | Scott | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
PE
RR
UT
|  |  |  | Washington | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
ROW
|  |  | 0200960 | Elkhart | Booth & Associates | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
ROW
RR
UT
|  |  | 0200961 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200962 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0200963 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 0200964 | Madison | CE Solutions, Inc. | Madison County | 2010-05-12 | CE
CN
|  |  | 0200965 | Blackford |  | Blackford County | -339679.2083 | CN
PE
|  |  | 0200966 |  | B. L. A., Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0200967 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0200968 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2003-01-22
|  |  | 0200969 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2003-01-22
|  |  | 0200970 | St. Joseph |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
PE
ROW
|  |  | 0200971 | St. Joseph |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
ROW
UT
|  |  | 0200972 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0200973 |  | C Blair Enterprises, Inc. | Elkhart County | -339679.2083
|  |  | 0200974 |  | Huff & Huff, Inc. | Porter County | -339679.2083
|  |  | 0200975 |  | C Blair Enterprises, Inc. | Elkhart County | -339679.2083
|  |  | 0200976 |  | Farren Real Estate Services | Indiana Department of Transportation | 2007-09-06
|  |  | 0200977 | Porter |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 0200978 | Hendricks | Horner and Shifrin, Inc. | Plainfield | 2009-07-29 | CN
|  |  | 0200979 | Monroe |  | Ellettsville | 2005-05-25 | CE
CN
|  |  | 0200980 |  | Michael Baker International, Inc. | Yorktown | -339679.2083
|  |  | 0200981 |  | ASA Engineering Consultants, Inc. | Indiana Department of Natural Resources | -339679.2083
|  |  | 0200982 | Delaware | GS-IN P.C. | Muncie | 2005-07-20 | CE
CN
|  |  |  | Henry | GS-IN P.C. | Muncie | 2005-07-20 | CE
CN
|  |  |  | Randolph | GS-IN P.C. | Muncie | 2005-07-20 | CE
CN
|  |  | 0200983 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200984 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2013-07-10 | CE
CN
|  |  | 0200985 | Clark |  | Charlestown | -339679.2083 | PE
|  |  | 0200986 |  | Dodd Title Corporation | Kokomo | -339679.2083
|  |  | 0200987 | Monroe | Absolute Title Services, LLC | Bloomington | 2010-01-27 | CE
CN
|  |  | 0200988 | Vigo | Bayswater Company, LLC | Vigo County | 2013-01-09 | PE
|  |  | 0200989 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
RR
UT
|  |  | 0200990 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2002-11-19
|  |  | 0200991 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0200992 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200993 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0200994 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0200995 | Carroll |  | Carroll County | 2005-03-16 | CE
CN
PE
|  |  | 0200996 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200997 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200998 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0200999 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201001 | Elkhart | Farren Real Estate Services | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 0201002 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201003 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0201004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201005 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0201006 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201007 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201008 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201009 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201010 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0201011 |  | Hardlines Design Company | Indiana Department of Transportation | -339679.2083
|  |  | 0201012 | LaGrange | John A. Doyle Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201013 |  | Hambleton LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0201014 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201015 | White |  | White County | -339679.2083 | CN
|  |  | 0201016 | Putnam |  | Putnam County | -339679.2083 | CN
|  |  | 0201017 | Cass |  | Clark County | 2012-10-11 | CN
|  |  |  | Clark |  | Clark County | 2012-10-11 | CE
CN
|  |  | 0201018 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201019 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0201020 | Allen | Global Management Group, Inc. | New Haven | 2006-04-19 | CE
CN
|  |  | 0201021 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0201022 | Vanderburgh |  | Indiana Department of Transportation | 2003-04-22 | PE
ROW
|  |  |  | Warrick |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
UT
|  |  | 0201023 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201024 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201025 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0201026 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0201027 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0201028 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
UT
|  |  | 0201029 | Johnson |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0201030 | Carroll |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
PE
|  |  | 0201031 |  | DCD Consulting LLC | Indiana Department of Transportation | 2002-12-18
|  |  | 0201032 | Newton |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 0201033 | Newton |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 0201034 | Carroll |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
|  |  | 0201035 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201036 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201037 | Newton |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 0201038 | Starke |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 0201039 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
|  |  | 0201040 | LaPorte |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
|  |  | 0201041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201042 | Fulton |  | Indiana Department of Transportation | 2013-07-10 | PE
|  |  | 0201043 | White |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0201044 | Porter |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0201045 | Lake |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
|  |  | 0201046 | Jasper |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 0201047 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0201048 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
UT
|  |  | 0201049 | Jasper |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 0201050 | Jasper |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
|  |  | 0201051 | Jasper |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0201052 | Jasper |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
RR
|  |  | 0201053 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0201054 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201055 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201056 | Jasper |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
RR
|  |  | 0201057 | Newton |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
RR
|  |  | 0201058 | Newton |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
RR
|  |  | 0201059 | Jasper |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 0201060 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0201061 | Jasper |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 0201062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201063 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
RR
|  |  | 0201064 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-04-08 | CE
CN
ROW
UT
|  |  | 0201065 |  |  | Indiana Department of Transportation | 2003-02-18
|  |  | 0201066 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  | 0201067 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0201068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201069 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0201070 | Jasper |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0201071 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201072 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0201073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201074 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0201075 |  | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2003-12-17
|  |  | 0201076 |  |  | Indiana Department of Transportation | 2003-12-17
|  |  | 0201077 |  |  | Indiana Department of Transportation | 2003-12-17
|  |  | 0201078 |  | Eco Logic, LLC | Indiana Department of Transportation | 2003-12-17
|  |  | 0201079 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | 2004-05-25
|  |  | 0201080 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0201081 |  | Wilcox Environmental Engineering, Inc. | Fayette County | -339679.2083
|  |  | 0201082 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2016-01-13 | CE
CN
ROW
|  |  | 0201083 | Pulaski |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  |  | Starke |  | Indiana Department of Transportation | 2003-03-25 | CE
CN
|  |  | 0201084 | Allen |  | Allen County | 2009-11-04 | CE
CN
PE
ROW
RR
UT
|  |  | 0201085 | Hendricks |  | Hendricks County | 2005-12-14 | CE
CN
|  |  | 0201086 | Dekalb |  | Dekalb County | -339679.2083 | CN
|  |  | 0201087 |  | First Group Engineering, Inc. | Crawford County | -339679.2083
|  |  | 0201088 |  | First Group Engineering, Inc. | Crawford County | -339679.2083
|  |  | 0201089 |  |  | Indiana Department of Transportation | 2003-12-17
|  |  | 0201090 | Sullivan |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
PE
[6 empty] | Indiana Department of Transportation | 2009-04-22
|  |  | 0201091 | Hancock |  | Hancock County | 2007-05-31 | CE
CN
PE
UT
|  |  | 0201092 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201093 | Tippecanoe |  | Tippecanoe County | -339679.2083 | CN
PE
|  |  | 0201094 | White |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
ROW
|  |  | 0201095 |  | Consolidated Test Company | Indiana Department of Transportation | 2003-03-25
|  |  | 0201096 |  | Certified Engineering, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0201097 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0201098 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0201099 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2003-06-17
|  |  | 0201100 | Jackson |  | Jackson County | -339679.2083 | CN
|  |  | 0201101 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2003-10-21
|  |  | 0201102 | Warrick |  | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0201103 | Spencer |  | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0201104 |  | Dodd Title Corporation | Kokomo | 2004-06-22
|  |  | 0201105 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201106 |  | AECOM Technical Services, Inc. | Indiana Department of Transportation | 2003-01-22
|  |  | 0201107 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201108 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201109 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201110 | Hamilton |  | Hamilton County | 2004-02-17 | CE
CN
|  |  | 0201111 | Spencer |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0201112 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0201113 | Marion | DCD Consulting LLC | Indianapolis | 2003-01-22 | CE
CN
RR
|  |  | 0201114 | Warrick |  | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0201115 | Spencer |  | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0201116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201117 |  |  | Indiana Department of Natural Resources | 2003-05-20
|  |  | 0201118 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201126 | Madison |  | Elwood | 2003-05-20 | CE
CN
ROW
UT
|  |  | 0201127 |  |  | Hamilton County | -339679.2083
|  |  | 0201128 | Spencer |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0201129 |  |  | Hamilton County | -339679.2083
|  |  | 0201130 |  |  | Hamilton County | -339679.2083
|  |  | 0201131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201133 | Spencer |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0201134 |  |  | Noblesville | -339679.2083
|  |  | 0201135 |  |  | Noblesville | -339679.2083
|  |  | 0201136 |  |  | Hamilton County | -339679.2083
|  |  | 0201137 |  |  | Hamilton County | -339679.2083
|  |  | 0201138 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2006-06-28 | CE
CN
|  |  | 0201139 | Hamilton | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201140 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2013-07-10 | CE
CN
PE
ROW
|  |  | 0201141 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201142 | Wayne |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
PE
ROW
|  |  | 0201143 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201146 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201148 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201149 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0201150 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0201151 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0201152 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0201153 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0201154 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0201155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201156 |  |  | Tippecanoe County | 2003-02-18
|  |  | 0201157 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0201158 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0201159 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2004-06-22
|  |  | 0201160 | Delaware |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0201161 | Henry |  | Indiana Department of Transportation | 2004-03-23 | CE
PE
RR
|  |  | 0201162 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-22
|  |  | 0201163 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0201164 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-22
|  |  | 0201165 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201166 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2004-06-22
|  |  | 0201167 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2004-06-22
|  |  | 0201168 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201169 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201170 | Dearborn |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
RR
|  |  | 0201171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201172 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201173 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2006-03-29
|  |  | 0201174 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201175 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0201176 | Lake | Consolidated Test Company | Hammond | 2008-02-27 | CE
CN
|  |  | 0201177 | Lake | Consolidated Test Company | Hammond | 2013-02-06 | CE
CN
|  |  | 0201178 |  |  | Columbus | 2003-01-22
|  |  | 0201179 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2006-03-29 | CE
CN
RR
|  |  | 0201180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201181 | Floyd |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0201182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201183 | Harrison |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0201184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201185 | Lawrence |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0201186 | Lawrence |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0201187 | Martin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201188 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201189 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201190 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201191 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201195 |  | Aurora | Aurora | -339679.2083
|  |  | 0201196 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201197 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201198 |  |  | Indiana Department of Transportation | 2003-01-22
|  |  | 0201199 |  | Bayswater Company, LLC | Vigo County | -339679.2083
|  |  | 0201200 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0201201 | Montgomery |  | Indiana Department of Transportation | 2007-09-19 | CE
CN
|  |  | 0201202 | Parke |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0201203 | Benton |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0201204 | Benton |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0201205 |  |  | Indiana Department of Transportation | 2003-06-10
|  |  | 0201206 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201207 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0201208 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201209 | Montgomery |  | Indiana Department of Transportation | 2014-06-16 | PE
|  |  | 0201210 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
RR
|  |  | 0201211 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
RR
|  |  | 0201212 | Vigo |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0201213 | Clinton |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0201214 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-07-15
|  |  | 0201215 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2003-04-22 | CE
CN
|  |  | 0201216 | Warren |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
ROW
|  |  | 0201217 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201218 |  | Foresight Land Surveying, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0201219 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201220 |  | InfoTech | Indiana Department of Transportation | 2003-01-22
|  |  | 0201221 | Marshall | Howard J. Barth & Associates, Inc. | Marshall County | 2006-01-18 | CE
CN
|  |  | 0201222 | Hamilton | H. Stewart Kline & Associates, Inc. | Hamilton County | 2006-07-19 | CE
CN
PE
|  |  | 0201223 |  |  | Grant County | -339679.2083
|  |  | 0201224 | Delaware |  | Delaware County | -339679.2083 | CN
|  |  | 0201225 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  | 0201226 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  | 0201227 | Madison |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
ROW
UT
|  |  | 0201228 | White |  | Indiana Department of Transportation | 2006-03-29 | CE
CN
PE
ROW
RR
|  |  | 0201229 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0201230 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201231 |  | Collier Transport Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0201232 | Dearborn |  | Aurora | 2005-09-14 | CE
CN
|  |  | 0201233 |  | ASA Engineering Consultants, Inc. | Indiana Department of Natural Resources | -339679.2083
|  |  | 0201234 |  |  | Porter County | -339679.2083
|  |  | 0201235 |  | Blood Hound, Inc. (former) | Carroll County | -339679.2083
|  |  | 0201236 |  | Carters Appraisal Service | Clinton County | -339679.2083
|  |  | 0201237 |  |  | Vigo County | -339679.2083
|  |  | 0201238 | Posey |  | Posey County | 2007-05-31 | PL
|  |  | 0201239 | Lawrence |  | Lawrence County | 2012-02-08 | CE
CN
|  |  | 0201240 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2011-07-13 | CE
CN
PE
|  |  | 0201241 | Lawrence |  | Lawrence County | -339679.2083 | CE
CN
|  |  | 0201242 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2007-07-11 | CE
CN
|  |  | 0201243 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201244 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201245 | Ohio |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
UT
|  |  | 0201246 | Warren |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0201247 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0201248 |  | CH2M HILL, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201249 | Montgomery |  | Montgomery County | 2007-10-17 | CE
CN
|  |  | 0201250 | Vigo | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201252 | Tippecanoe |  | Indiana Department of Transportation | 2012-06-24 | PE
|  |  |  | Warren |  | Indiana Department of Transportation | 2012-06-24 | PE
|  |  | 0201253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201254 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201255 | Lake | Edwards and Kelcey | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0201256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201258 | LaPorte |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
RR
|  |  | 0201259 | LaPorte |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
RR
|  |  | 0201260 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2007-10-17 | CE
CN
RR
|  |  | 0201261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201262 | Lake |  | Indiana Department of Transportation | 2005-03-16 | CE
CN
RR
|  |  | 0201263 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201264 | Lake |  | Indiana Department of Transportation | 2005-03-16 | CE
CN
RR
|  |  | 0201265 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201266 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201267 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201268 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201269 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201270 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201271 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201272 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201273 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201274 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0201275 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201276 | Ohio |  | Indiana Department of Transportation | 2006-02-22 | CE
CN
|  |  | 0201277 | Jefferson | Engineering Resources, Inc. | Madison | -339679.2083 | CN
PE
|  |  | 0201278 |  | H W Lochner, Inc. | Vermillion County | -339679.2083
|  |  | 0201279 | Randolph | CKW Land Surveying, Inc. | Farmland | 2006-05-24 | CE
CN
ROW
UT
|  |  | 0201280 | Franklin | Alfred Benesch & Company | Franklin County | 2010-05-12 | CE
CN
|  |  | 0201281 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201282 | Owen | Garcia LE & Associates, L.L.C. | Indiana Department of Natural Resources | -339679.2083 | CE
CN
|  |  | 0201283 | Crawford | First Group Engineering, Inc. | Milltown | -339679.2083 | CN
|  |  | 0201284 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201285 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0201286 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0201287 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0201288 | Marion | DCD Consulting LLC | Indianapolis | 2005-06-22 | CE
CN
PE
|  |  | 0201289 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2003-02-18
|  |  | 0201290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201291 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201292 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201293 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201294 | Clark |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 0201295 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201296 | Clark |  | Indiana Department of Transportation | 2013-05-31 | CE
CN
PE
|  |  | 0201297 | Clark |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
ROW
UT
|  |  | 0201298 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201299 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201302 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
ROW
UT
|  |  | 0201303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201304 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0201305 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201306 |  | Edwards and Kelcey | Indiana Department of Transportation | -339679.2083
|  |  | 0201307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201308 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201309 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0201310 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 0201311 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201312 | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201313 | Hendricks |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0201314 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0201315 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0201316 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2003-08-12
|  |  | 0201317 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2003-08-12
|  |  | 0201318 | Jackson |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0201319 | Marion |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0201320 | Johnson |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
ROW
UT
|  |  | 0201321 |  | Marine Solutions, Inc. | Indiana Department of Transportation | 2003-10-21
|  |  | 0201322 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0201323 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0201324 | Porter |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 0201325 | Monroe |  | Indiana Department of Transportation | -339679.2083 | CE
PE
ROW
UT
|  |  | 0201326 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201327 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201329 | Benton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201330 | Hendricks |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0201331 | Tippecanoe |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0201332 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2008-01-09
|  |  | 0201333 | Monroe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0201334 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201335 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2008-05-07 | CE
CN
PE
ROW
RR
UT
|  |  | 0201336 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201337 |  | CKW Land Surveying, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0201338 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201339 |  |  | Indiana Department of Transportation | 2003-06-10
|  |  | 0201340 |  | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201341 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0201342 |  |  | Indiana Department of Transportation | 2003-06-10
|  |  | 0201343 | Jennings |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
ROW
UT
|  |  | 0201344 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201345 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0201346 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201347 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201348 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201349 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201350 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0201351 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201352 | Lake |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0201353 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201354 | Harrison |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0201355 | White | Meridian Title Corporation | Indiana Department of Transportation | 2010-02-24 | CE
CN
PE
RR
|  |  | 0201356 | Owen |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0201357 |  | B. L. A., Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0201358 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0201359 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201362 | Vanderburgh | CGI | Indiana Department of Transportation | 2008-03-05 | CN
PE
ROW
RR
UT
|  |  | 0201363 | Vanderburgh | CGI | Indiana Department of Transportation | 2008-03-05 | CN
PE
ROW
RR
UT
|  |  | 0201364 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | CN
PE
ROW
RR
UT
|  |  | 0201365 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201366 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201367 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201368 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201369 | Clark |  | Indiana Department of Transportation | 2013-05-31 | PE
ROW
|  |  | 0201370 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201371 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201373 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0201374 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201375 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0201376 | Dearborn |  | Dearborn County | -339679.2083 | CN
|  |  | 0201377 | Sullivan |  | Sullivan County | -339679.2083 | CN
|  |  | 0201378 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201379 |  | 2IM Group, LLC | Indiana Department of Transportation | 2003-03-25
|  |  | 0201380 | Hamilton |  | Hamilton County | 2005-10-19 | CE
CN
|  |  | 0201381 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201382 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201383 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | RR
|  |  | 0201384 |  | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | 2003-05-20
|  |  | 0201385 | St. Joseph |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0201386 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0201387 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-04-22
|  |  | 0201388 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-04-22
|  |  | 0201389 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2003-04-22
|  |  | 0201390 | Various |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0201391 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
ROW
|  |  | 0201392 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201396 | Benton |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  |  | Warren |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0201397 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0201398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0201399 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0201400 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0201401 | Porter |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0201402 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300001 |  | Jeffrey S. Juday | Shelbyville | -339679.2083
|  |  | 0300002 | Madison |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 0300003 | Johnson |  | Indiana Department of Transportation | 2003-03-25 | CN
PE
|  |  | 0300004 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0300005 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300006 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0300007 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0300008 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0300009 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2005-05-25
|  |  | 0300010 | Harrison |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0300011 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28 | PE
ROW
RR
UT
|  |  | 0300012 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28 | PE
ROW
RR
UT
|  |  | 0300013 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-04-22
|  |  | 0300014 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0300015 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 0300016 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2003-03-25
|  |  | 0300017 | Marion | DCD Consulting LLC | Indianapolis | 2008-05-08 | CE
CN
|  |  | 0300018 | Clark |  | Charlestown | -339679.2083 | CN
|  |  | 0300019 | Marion | DCD Consulting LLC | Indianapolis | 2008-03-05 | CE
CN
|  |  | 0300020 | Marion | DCD Consulting LLC | Indianapolis | 2004-05-25 | CE
CN
|  |  | 0300021 | Marion | DCD Consulting LLC | Indianapolis | 2007-05-31 | CN
|  |  | 0300022 |  | Data Transfer Solutions, LLC | Clark County | -339679.2083
|  |  | 0300023 | Marion | DCD Consulting LLC | Indianapolis | 2005-12-14 | CE
CN
RR
|  |  | 0300024 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300025 | Marion | DCD Consulting LLC | Indianapolis | 2008-12-10 | CE
CN
|  |  | 0300026 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300027 |  | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0300028 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300029 | Johnson |  | Johnson County | 2009-05-06 | CE
CN
|  |  | 0300030 |  | Bidinfo | Indiana Department of Transportation | 2003-03-25
|  |  | 0300031 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300032 | Allen |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
|  |  | 0300033 | Boone |  | Zionsville | 2008-07-09 | CE
CN
UT
|  |  | 0300034 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300038 | Brown |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0300039 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300040 |  | Mader Design, LLC | Indiana Department of Transportation | 2003-05-20
|  |  | 0300041 |  | CGI | Indiana Department of Transportation | 2003-02-04
|  |  | 0300042 |  | CGI | Indiana Department of Transportation | 2003-02-04
|  |  | 0300043 | Steuben | ABt SRBI | Angola | 2008-05-08 | CE
CN
|  |  | 0300044 | Martin | EcoTec, Inc. | Loogootee | 2009-03-11 | CE
CN
|  |  | 0300045 | Knox | Louis Joyner, Architect | Vincennes | 2015-11-10 | CE
CN
PE
|  |  | 0300046 |  | John A. Doyle Associates, Inc. | Shipshewana | -339679.2083
|  |  | 0300047 | Daviess | Frost Engineering & Consulting Company | Daviess County | 2013-05-01 | CE
CN
PE
ROW
UT
|  |  | 0300048 |  |  | Orange County | 2007-10-03
|  |  | 0300049 | Lake | Cornerstone Design | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0300050 | Johnson |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0300051 | Marion | DCD Consulting LLC | Indianapolis | 2006-04-19 | CE
CN
|  |  | 0300052 |  | Another Test Company | Carmel | -339679.2083
|  |  | 0300053 | Marion | DCD Consulting LLC | Indianapolis | 2003-06-17 | CE
CN
|  |  | 0300054 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0300055 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300056 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300057 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2003-03-25
|  |  | 0300058 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300059 | Hamilton | Another Test Company | Carmel | 2008-05-14 | CE
CN
[5 empty] | Another Test Company | Carmel | 2008-05-14
|  |  | 0300060 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300061 |  | CTLGroup | Indiana Department of Transportation | 2004-01-21
|  |  | 0300062 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300063 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300064 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0300065 | Madison |  | Indiana Department of Transportation | 2003-04-22 | CE
CN
PE
|  |  | 0300066 | Dekalb |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
ROW
UT
|  |  | 0300067 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300068 | Madison |  | Indiana Department of Transportation | 2007-10-03 | CE
CN
|  |  | 0300069 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0300070 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-09-16
|  |  | 0300071 |  | GS-IN P.C. | Indiana Department of Transportation | 2003-05-20
|  |  | 0300072 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2003-06-10
|  |  | 0300073 | Grant |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
|  |  | 0300074 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300075 |  | Douglass Environmental Services, Inc. | LaPorte County | -339679.2083
|  |  | 0300076 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2004-09-14 | CE
CN
|  |  | 0300077 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300078 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0300079 | Grant |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300080 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0300081 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0300082 |  | ACME | Indiana Department of Transportation | -339679.2083
|  |  | 0300083 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2004-06-15 | CE
CN
UT
|  |  |  | Randolph | Hydrogeology, Inc. | Indiana Department of Transportation | 2004-06-15 | CE
CN
|  |  | 0300084 | Allen |  | Indiana Department of Transportation | 2009-07-29 | CN
|  |  |  | Dekalb |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0300085 | Allen |  | Indiana Department of Transportation | 2012-01-13 | CE
CN
PE
|  |  | 0300086 | Allen |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 0300087 | Allen |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 0300088 |  | Douglass Environmental Services, Inc. | LaPorte County | -339679.2083
|  |  | 0300089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300091 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300092 | Dekalb |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
PE
|  |  | 0300093 | Dekalb |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
PE
|  |  | 0300094 | Perry | Andrews Engineering, Inc. | Perry County | 2006-01-18 | CE
CN
|  |  | 0300095 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0300096 |  |  | Indiana Department of Transportation | 2003-06-10
|  |  | 0300097 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0300098 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2003-07-15
|  |  | 0300099 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300100 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300101 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0300102 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300103 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0300104 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300105 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2003-06-10
|  |  | 0300106 | Perry |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
ROW
|  |  | 0300107 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300108 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2003-06-10
|  |  | 0300109 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2003-06-17 | CE
CN
RR
|  |  | 0300110 |  | Debbie L. Morris | Indiana Department of Transportation | 2003-06-17
|  |  | 0300111 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2004-05-25
|  |  | 0300112 |  | Knies Constr/Calcar Paving J/V | Indiana Department of Transportation | 2003-10-21
|  |  | 0300113 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300114 | Various |  | Madison | 2009-09-10 | CE
CN
PE
|  |  | 0300115 | Elkhart |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
UT
|  |  | 0300116 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
RR
|  |  | 0300117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300118 |  | Consolidated Test Company | Indiana Department of Transportation | 2003-06-17
|  |  | 0300119 | Posey |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300120 | St. Joseph |  | St. Joseph County | 2005-03-16 | CE
CN
|  |  | 0300121 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300122 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
[5 empty] | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25
|  |  | 0300123 |  | Durham Engineering, Inc. | Indiana Department of Transportation | 2003-06-10
|  |  | 0300124 |  |  | Indiana Department of Transportation | 2003-04-22
|  |  | 0300125 |  | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2006-09-13
|  |  | 0300126 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300127 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300128 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300129 | Marion | DCD Consulting LLC | Indianapolis | 2003-06-17 | CE
CN
|  |  | 0300130 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300131 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300132 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300133 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300134 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-17 | CE
CN
UT
|  |  | 0300135 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0300136 | Marion | DCD Consulting LLC | Indiana State Agencies | 2003-06-10 | CE
CN
|  |  | 0300137 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0300138 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 0300139 | Perry |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 0300140 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300141 | Perry |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
ROW
UT
|  |  | 0300142 |  |  | St. Joseph County | -339679.2083
|  |  | 0300143 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300144 |  |  | St. Joseph County | -339679.2083
|  |  | 0300145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300146 |  |  | St. Joseph County | -339679.2083
|  |  | 0300147 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300148 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0300149 |  |  | Clarksville | -339679.2083
|  |  | 0300150 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-07-15 | CE
CN
|  |  | 0300151 |  | CKW Land Surveying, Inc. | Indiana Department of Transportation | 2003-04-22
|  |  | 0300152 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-06-17 | CE
CN
UT
|  |  | 0300153 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2003-05-20
|  |  | 0300154 |  |  | Indiana State Agencies | 2003-09-16
|  |  | 0300155 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-07-15 | CE
CN
UT
|  |  | 0300156 | Benton |  | Benton County | -339679.2083 | CN
|  |  | 0300158 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-04-22
|  |  | 0300159 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300160 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
RR
|  |  | 0300161 |  | Alfred Benesch & Company | Indiana Department of Transportation | 2006-05-24
|  |  | 0300162 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0300163 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300164 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2003-11-18
|  |  | 0300165 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2003-11-18
|  |  | 0300166 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2003-09-16
|  |  | 0300167 |  | Carters Appraisal Service | Indiana Department of Transportation | 2004-03-23
|  |  | 0300168 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300169 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300170 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2006-07-19
|  |  | 0300171 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300172 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300173 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300174 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0300175 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300176 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2004-11-16
|  |  | 0300177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300179 |  | Dodd Title Corporation | Kokomo | 2006-05-24
|  |  | 0300180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300181 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-03-25
|  |  | 0300190 |  | Mackie Consultants, LLC | Warsaw | -339679.2083
|  |  | 0300191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300192 | Kosciusko | McLane Realty, Inc. | Winona Lake | 2006-06-21 | CE
CN
|  |  | 0300193 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300194 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300195 |  |  | Indian Heights | 2004-04-20
|  |  | 0300196 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300199 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2004-01-21
|  |  | 0300200 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300201 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300202 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300203 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300204 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300205 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300206 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300207 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300208 | Allen |  | Fort Wayne | 2005-10-19 | CE
CN
PE
ROW
UT
|  |  | 0300209 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300210 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0300211 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0300212 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300213 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300214 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0300215 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0300216 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0300217 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0300218 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2003-05-25
|  |  | 0300219 | Cass |  | Cass County | -339679.2083 | CN
|  |  | 0300220 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0300221 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300222 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300225 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300226 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300227 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-05-20
|  |  | 0300228 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2003-10-21
|  |  | 0300229 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2003-10-21
|  |  | 0300230 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300231 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300232 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300233 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0300234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300237 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300238 | Marion | DCD Consulting LLC | Indianapolis | 2003-06-17 | CE
CN
|  |  | 0300239 | Spencer |  | Indiana Department of Transportation | 2008-03-05 | PE
|  |  |  | Warrick |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
ROW
UT
|  |  | 0300240 |  |  | South Bend | -339679.2083
|  |  | 0300241 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300242 | Grant |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
|  |  | 0300243 | Hancock |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300244 | Hancock |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300245 |  |  | Indiana Department of Natural Resources | 2004-04-20
|  |  | 0300246 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300247 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2004-04-20 | CE
CN
ROW
UT
|  |  |  | Various | Dynasty Group, Inc. | Indiana Department of Transportation | 2004-04-20 | CN
|  |  | 0300248 | Vanderburgh |  | Indiana Department of Transportation | 2003-05-20 | CN
PE
ROW
RR
UT
|  |  |  | Warrick |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  | 0300249 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300253 |  |  | Indiana Department of Transportation | 2003-05-20
|  |  | 0300254 |  | DCD Consulting LLC | Indiana State Agencies | -339679.2083
|  |  | 0300255 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
ROW
UT
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
UT
|  |  | 0300256 | Adams |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300257 | Warrick |  | Indiana Department of Transportation | 2003-08-12 | CE
CN
|  |  | 0300258 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0300259 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
UT
|  |  | 0300260 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
|  |  | 0300261 |  | CGI | Vanderburgh County | -339679.2083
|  |  | 0300262 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0300263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300264 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300265 | Johnson |  | Indiana Department of Transportation | 2004-09-14 | CE
CN
|  |  | 0300266 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25
|  |  | 0300267 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2004-09-14
|  |  | 0300268 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300271 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  | 0300272 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300273 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300274 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300275 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300276 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0300277 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300278 |  |  | Decatur County | -339679.2083
|  |  | 0300279 | Decatur |  | Decatur County | 2005-07-20 | CE
CN
UT
|  |  | 0300280 | Hancock |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300281 | Hancock |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300282 | Pike |  | Pike County | -339679.2083 | CN
|  |  | 0300283 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300284 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0300285 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300286 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300287 | Elkhart | ERES International, Inc. | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0300288 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0300289 | Elkhart |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0300290 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0300291 | Allen |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
ROW
|  |  | 0300292 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0300293 |  | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083
|  |  | 0300294 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 0300295 | Clinton | Carters Appraisal Service | Frankfort | 2005-11-16 | CE
CN
|  |  | 0300296 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 0300297 | Allen |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0300298 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
RR
UT
|  |  | 0300299 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300301 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0300302 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0300303 | Adams |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
|  |  | 0300304 | Adams |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0300305 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2012-02-08 | PE
ROW
RR
|  |  | 0300306 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0300307 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0300308 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0300309 | Allen |  | Indiana Department of Transportation | 2010-02-10 | PE
ROW
UT
|  |  | 0300310 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0300311 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300312 | Lake | Cornerstone Design | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0300313 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
RR
|  |  | 0300314 | Allen |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
ROW
UT
|  |  | 0300315 | Allen |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
PE
|  |  | 0300316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300317 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300319 | Madison |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 0300320 | Madison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0300321 | Kosciusko |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0300322 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300323 | Porter |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 0300324 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0300325 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300326 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300327 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300328 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300329 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300330 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300331 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300332 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300333 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300334 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300335 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300336 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300337 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300338 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300339 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300340 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300341 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300342 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300343 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300344 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300345 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300346 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300347 | Daviess |  | Daviess County | -339679.2083 | CN
|  |  | 0300348 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0300349 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300350 |  |  | Indiana Department of Transportation | 2011-04-20
|  |  | 0300351 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
ROW
RR
UT
|  |  | 0300352 | Howard | J.F. New & Associates, Inc. | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
ROW
RR
UT
|  |  | 0300353 | Howard |  | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
ROW
RR
UT
[6 empty] | Indiana Department of Transportation | 2010-07-09
|  |  | 0300354 | Hamilton |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0300355 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300356 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300357 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300359 | Steuben |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0300360 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0300361 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2025-05-31
|  |  | 0300362 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0300363 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0300364 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0300365 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0300366 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0300367 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0300368 | Warrick | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2005-09-14 | CE
CN
RR
UT
|  |  | 0300369 | Fayette |  | Fayette County | -339679.2083 | CN
|  |  | 0300370 | Warrick |  | Indiana Department of Transportation | 2005-09-14 | CE
CN
RR
UT
|  |  | 0300371 | Marion |  | Indiana Department of Transportation | 2014-05-31 | PE
ROW
|  |  | 0300372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300373 | Warrick |  | Indiana Department of Transportation | 2005-09-14 | CE
CN
RR
UT
|  |  | 0300374 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300375 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2003-10-21 | CE
CN
PE
ROW
UT
|  |  | 0300376 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300377 | Gibson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300378 | Daviess |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Gibson |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  |  | Pike |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300379 | Daviess |  | Indiana Department of Transportation | 2009-05-31 | PE
|  |  | 0300380 | Daviess |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Greene |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Johnson |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Monroe |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Morgan |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Pike |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Warrick |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0300381 | Daviess | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Greene | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Johnson | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Marion | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Morgan | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Pike | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Various | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Warrick | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0300382 | Johnson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Morgan |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
UT
|  |  | 0300383 | Newton |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
|  |  | 0300384 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0300385 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  |  | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0300386 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0300387 | Hendricks |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
ROW
|  |  | 0300388 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
RR
|  |  | 0300389 | Marion |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
|  |  | 0300390 | Whitley |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300391 | Kosciusko |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300392 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0300393 | Grant |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300394 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300395 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2004-01-21
|  |  | 0300396 | Steuben | ABt SRBI | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300397 | Steuben | ABt SRBI | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300398 |  | Duesler Realty House | Indiana Department of Transportation | 2004-01-21
|  |  | 0300399 | Gibson |  | Indiana Department of Transportation | 2003-09-16 | CE
CN
|  |  | 0300400 |  | GMG INC. | Indiana Department of Transportation | -339679.2083
|  |  | 0300401 |  | ERES International, Inc. | Indiana Department of Transportation | 2004-01-21
|  |  | 0300402 |  | ABt SRBI | Indiana Department of Transportation | 2005-01-19
|  |  | 0300403 |  | ABt SRBI | Indiana Department of Transportation | 2005-01-19
|  |  | 0300404 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0300405 | Huntington |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300406 | Huntington | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  |  | Wabash | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0300407 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300408 |  |  | Indiana Department of Transportation | 2003-06-17
|  |  | 0300409 | Madison | AAC Environmental Consulting, LLC | Anderson | -339679.2083 | CN
|  |  | 0300410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300411 | Knox |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
UT
|  |  | 0300412 | Clark |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0300413 |  |  | Indiana Department of Transportation | 2003-07-15
|  |  | 0300414 |  | Finley Engineering Group, Inc. | Indiana Department of Transportation | 2003-08-12
|  |  | 0300415 |  | Wessler Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300416 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300417 |  |  | Indiana Department of Transportation | 2009-05-31
|  |  | 0300418 | Various |  | Indiana Department of Transportation | 2003-08-12 | CN
|  |  | 0300419 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0300420 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0300421 | Floyd |  | Indiana Department of Transportation | 2007-06-01 | CN
|  |  | 0300422 | Harrison | Environmental Management Associatese | Indiana Department of Transportation | 2007-06-01 | CN
|  |  | 0300423 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2007-06-01 | CN
|  |  | 0300424 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0300425 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0300426 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2004-04-20
|  |  | 0300427 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0300428 | Monroe | Absolute Title Services, LLC | Bloomington | 2008-04-02 | CE
CN
ROW
UT
|  |  | 0300429 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-05-10 | CE
CN
PE
UT
|  |  | 0300431 | Tippecanoe |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
UT
|  |  | 0300432 | Allen | Global Management Group, Inc. | New Haven | 2006-03-15 | CE
CN
|  |  | 0300433 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300434 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300435 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300436 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300437 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300438 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300439 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300440 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2007-11-28 | CE
CN
PE
ROW
RR
|  |  | 0300441 | Jay |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
PE
ROW
|  |  | 0300442 | Warrick |  | Warrick County | 2005-09-14 | CE
CN
UT
|  |  | 0300443 | Hamilton |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0300444 | Hancock |  | Hancock County | -339679.2083 | CE
CN
PE
UT
|  |  | 0300445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300446 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2015-03-04 | CE
CN
ROW
|  |  | 0300447 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300449 |  | Clarksville | Indiana Department of Transportation | -339679.2083
|  |  | 0300450 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300451 | Union |  | Indiana Department of Transportation | 2013-09-25 | RR
|  |  | 0300452 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300453 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0300454 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0300455 | Jasper |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
RR
|  |  |  | White |  | Indiana Department of Transportation | 2015-08-05 | PE
|  |  | 0300456 | Jasper |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 0300457 | Spencer | Appraisers, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0300458 | Crawford |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
ROW
UT
|  |  |  | Perry |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
ROW
UT
|  |  | 0300459 | Jay |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0300460 | Wayne |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0300461 | Madison |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0300462 | White |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
[6 empty] | Indiana Department of Transportation | 2015-08-05
|  |  | 0300463 | Hamilton |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0300464 | Howard |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0300465 | Delaware |  | Indiana Department of Transportation | 2005-06-01 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2005-06-01 | CE
CN
|  |  | 0300466 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0300467 | Clay |  | Indiana Department of Transportation | 2003-08-12 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2003-08-12 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2003-08-12 | CE
CN
|  |  | 0300468 | Wayne |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0300469 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0300470 | Wayne |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0300471 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0300472 | Hendricks |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0300473 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2005-06-01 | CE
CN
|  |  | 0300474 | Howard |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0300475 | White |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 0300476 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300477 | Grant |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  |  | Howard |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0300478 | Henry |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
RR
|  |  |  | Madison |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
RR
|  |  | 0300479 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2006-11-01 | CE
CN
RR
|  |  |  | Wayne | GeoSolutions, Inc. | Indiana Department of Transportation | 2006-11-01 | CE
CN
|  |  | 0300480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300481 | Henry |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0300482 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0300483 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  |  | Shelby | DCD Consulting LLC | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0300484 | Delaware |  | Indiana Department of Transportation | 2007-10-17 | CE
CN
|  |  | 0300485 | White |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 0300486 | Hamilton |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0300487 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300488 | White |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 0300489 | Randolph |  | Indiana Department of Transportation | 2007-10-17 | CE
CN
|  |  | 0300490 | Hamilton | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0300491 | Howard |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0300492 | Jasper |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
|  |  | 0300493 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2003-08-12
|  |  | 0300494 | Cass |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300495 | Pulaski |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
|  |  | 0300496 | Marshall | ACMS Group, Inc. | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0300497 | Lake |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300498 |  |  | Fulton County | -339679.2083
|  |  | 0300499 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300500 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0300501 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300502 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300503 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2004-12-14
|  |  | 0300504 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300505 | Crawford |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
ROW
UT
|  |  |  | Perry |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
ROW
UT
|  |  | 0300506 | Carroll |  | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  |  | Clinton |  | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0300507 | Newton |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0300508 | Various |  | Indiana Department of Transportation | 2003-05-31 | CN
|  |  | 0300509 |  | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0300510 | Dearborn |  | Indiana Department of Transportation | 2013-05-03 | CE
CN
PE
ROW
RR
|  |  | 0300511 | Monroe |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0300512 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300513 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2014-01-15 | PE
RR
|  |  | 0300514 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0300515 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300516 | Ripley |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300517 | Jefferson |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300518 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300519 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300520 | Clark |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300521 |  | March Environmental Services, LLC | Indiana Department of Transportation | 2004-01-21
|  |  | 0300522 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300523 | Hendricks |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-07-15 | CE
CN
PE
UT
|  |  | 0300524 | Hendricks |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0300525 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300526 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300527 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300528 | Clay |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
|  |  |  | Parke |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
|  |  | 0300529 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2004-03-23
|  |  | 0300530 |  | Eco Logic, LLC | Indiana Department of Transportation | 2003-09-16
|  |  | 0300531 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300532 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300534 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0300535 | Johnson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0300536 | Johnson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0300537 | Johnson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0300538 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2004-02-17
|  |  | 0300539 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0300540 | Vigo |  | Vigo County | 2009-02-11 | RR
|  |  | 0300541 | Vigo |  | Vigo County | 2009-02-11 | RR
|  |  | 0300542 | Vigo |  | Vigo County | 2009-02-11 | RR
|  |  | 0300543 | Delaware |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0300544 | Vigo |  | Vigo County | 2009-02-11 | RR
|  |  | 0300545 | Vigo |  | Vigo County | 2009-02-11 | RR
|  |  | 0300546 |  |  | Indiana Department of Transportation | 2003-08-12
|  |  | 0300547 |  | Garcia LE & Associates, L.L.C. | Brown County | -339679.2083
|  |  | 0300548 | Cass |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300549 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300550 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300551 | Hendricks |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0300552 | Hendricks |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0300553 | Hendricks |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0300554 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-09-25 | CE
CN
|  |  | 0300555 |  |  | Warrick County | -339679.2083
|  |  | 0300556 | Greene |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
ROW
UT
|  |  | 0300557 | Delaware |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300558 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300560 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300561 | Various |  | Indiana State Agencies | -339679.2083 | PE
|  |  | 0300562 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300563 | Lake | Edwards and Kelcey | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300564 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0300565 | Hamilton | Burns & McDonnell Engineering Company, Inc. | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  |  | Madison | Burns & McDonnell Engineering Company, Inc. | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0300566 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-01-21
|  |  | 0300567 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0300568 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0300569 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300571 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300572 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2004-07-20 | CE
CN
|  |  | 0300573 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300574 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300575 |  |  | Hamilton County | -339679.2083
|  |  | 0300576 |  |  | Scott County | -339679.2083
|  |  | 0300577 | Vanderburgh |  | Vanderburgh County | 2008-05-08 | CN
|  |  | 0300578 | Warrick |  | Newburgh | 2010-01-13 | CE
CN
[6 empty] | Newburgh | 2010-01-13
|  |  | 0300579 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0300580 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300581 |  |  | Rush County | -339679.2083
|  |  | 0300582 |  |  | Miami County | -339679.2083
|  |  | 0300583 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0300584 | Gibson |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0300585 | Monroe |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  | 0300586 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300588 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300589 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300591 | Bartholomew |  | Indiana Department of Transportation | 2003-10-21 | CE
CN
UT
|  |  | 0300592 | Howard | Dodd Title Corporation | Howard County | 2004-08-17 | CE
CN
|  |  | 0300593 | Tippecanoe |  | Tippecanoe County | -339679.2083 | PE
|  |  | 0300594 |  |  | Tippecanoe County | -339679.2083
|  |  | 0300595 | Tippecanoe |  | Tippecanoe County | 2012-11-15 | CE
CN
ROW
|  |  | 0300596 |  |  | Tippecanoe County | -339679.2083
|  |  | 0300597 |  | Manhard Consulting, Ltd. | West Lafayette | -339679.2083
|  |  | 0300598 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0300599 | Various |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300600 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2007-12-12 | CE
CN
RR
|  |  | 0300601 | Lake | Chicago Testing Laboratory, Inc. | Lake County | -339679.2083 | CN
|  |  | 0300602 | Porter | Huff & Huff, Inc. | Portage | 2017-08-09 | CE
CN
PE
|  |  | 0300603 | Porter | Hy-Tech Response, Inc. | Porter | 2013-04-03 | CE
CN
PE
ROW
|  |  | 0300604 |  | Data Transfer Solutions, LLC | Clark County | -339679.2083
|  |  | 0300605 |  | CGI | Evansville | -339679.2083
|  |  | 0300606 | Vanderburgh | CGI | Evansville | 2008-09-17 | CE
CN
|  |  | 0300607 | Vanderburgh | CGI | Vanderburgh County | 2008-07-09 | CE
CN
|  |  | 0300608 | Marion | DCD Consulting LLC | Indianapolis | 2005-04-20 | CE
CN
|  |  | 0300609 | Marion | DCD Consulting LLC | Indianapolis | 2008-09-04 | CE
CN
RR
|  |  | 0300610 | Marion | DCD Consulting LLC | Indianapolis | 2004-03-23 | CE
CN
|  |  | 0300611 |  | DCD Consulting LLC | Marion County | -339679.2083
|  |  | 0300612 |  | DCD Consulting LLC | Marion County | -339679.2083
|  |  | 0300613 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300614 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2003-10-21
|  |  | 0300615 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300616 |  | Eel River Abstract | Indiana Department of Transportation | 2004-04-20
|  |  | 0300617 |  |  | Indiana Department of Transportation | 2003-09-16
|  |  | 0300618 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0300619 |  |  | Indiana Department of Natural Resources | 2002-11-19
|  |  | 0300620 | Putnam |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300621 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0300622 | Crawford |  | Crawford County | -339679.2083 | CN
|  |  | 0300623 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300624 | Lake | Consolidated Test Company | MPO - Northwest | -339679.2083 | PE
|  |  | 0300625 |  | Eco Logic, LLC | Indiana Department of Transportation | 2003-11-18
|  |  | 0300626 | White | Fugro Roadware, Inc. | Monticello | 2009-04-08 | CE
CN
PE
ROW
|  |  | 0300627 | White | Fugro Roadware, Inc. | White County | 2006-02-22 | CE
CN
PE
ROW
|  |  | 0300628 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300629 | Owen |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0300630 | Owen |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0300631 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0300632 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0300633 | Switzerland |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300634 | Ohio |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  |  | Switzerland |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300635 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300636 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300637 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300638 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0300639 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300640 | Boone |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0300641 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0300642 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300643 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300644 | Henry |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0300645 | Delaware |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300646 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0300647 | Madison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300648 | Porter |  | Indiana Department of Transportation | 2007-07-25 | CN
|  |  | 0300649 | Johnson |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Shelby |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0300650 | Floyd |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0300651 | Vanderburgh | CGI | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0300652 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300653 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300654 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2004-04-20
|  |  | 0300655 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0300656 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300657 | Floyd |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0300658 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300661 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300662 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300663 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300664 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300665 | Cass |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300666 |  |  | Indiana Department of Transportation | 2003-10-21
|  |  | 0300667 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0300668 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-09-14
|  |  | 0300669 |  | Blue Sky Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300672 | Jefferson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300673 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | CN
|  |  | 0300674 | Pulaski |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
|  |  | 0300675 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300676 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300677 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300678 | Dearborn | Dynasty Group, Inc. | Lawrenceburg | -339679.2083 | PE
|  |  | 0300679 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2005-12-14 | CE
CN
RR
|  |  | 0300680 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300681 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300682 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300683 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300684 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0300685 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300686 | St. Joseph |  | South Bend | -339679.2083 | PE
|  |  | 0300687 | LaGrange |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
PE
ROW
UT
|  |  | 0300688 | Grant |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300689 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300690 |  | Lorenz Williams Clinton | Indiana Department of Transportation | 2004-01-21
|  |  | 0300691 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300692 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300693 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0300694 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
ROW
UT
|  |  | 0300695 | Cass |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
PE
ROW
RR
UT
|  |  | 0300696 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 2004-01-21
|  |  | 0300697 |  |  | Indiana Department of Transportation | 2003-11-18
|  |  | 0300698 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300699 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300700 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0300701 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2004-05-25 | CE
CN
PE
RR
|  |  | 0300702 | Johnson |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0300703 | St. Joseph |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0300704 | St. Joseph |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0300705 | St. Joseph |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
UT
|  |  | 0300706 | St. Joseph |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
UT
|  |  | 0300707 | St. Joseph |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
|  |  | 0300708 | St. Joseph |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
|  |  | 0300709 | Various |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0300710 |  | ABNA of Illinois | Indiana Department of Transportation | 2004-07-20
|  |  | 0300711 | Shelby | Jeffrey S. Juday | Shelbyville | 2007-02-07 | CE
CN
|  |  | 0300712 | Shelby | Jeffrey S. Juday | Shelbyville | 2009-07-01 | CE
CN
|  |  | 0300713 |  | IXOYE, Limited | Indiana Department of Transportation | -339679.2083
|  |  | 0300714 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300715 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 0300716 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300717 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2004-04-20 | CE
CN
|  |  | 0300718 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2004-04-20 | CE
CN
|  |  | 0300719 | Dearborn |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
PE
|  |  | 0300720 | Hancock |  | Indiana Department of Transportation | 2004-02-17 | CE
CN
|  |  | 0300721 | Warrick |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0300722 | Franklin |  | Indiana Department of Transportation | 2007-04-04 | CE
CN
PE
ROW
UT
|  |  | 0300723 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300724 | Jasper |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
PE
UT
|  |  | 0300725 | Vigo |  | Indiana Department of Transportation | 2005-08-17 | CE
CN
|  |  | 0300726 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300735 |  | Vincennes | Vincennes | -339679.2083
|  |  | 0300736 |  | Louis Joyner, Architect | Vincennes | -339679.2083
|  |  | 0300737 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2004-07-20
|  |  | 0300738 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300739 | Various |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
|  |  | 0300740 |  |  | Indiana Department of Transportation | 2003-12-17
|  |  | 0300741 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0300742 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0300743 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0300744 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0300745 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0300746 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0300747 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-05-31 | CE
CN
|  |  | 0300748 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-01-09 | CE
CN
ROW
RR
UT
|  |  | 0300749 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-01-09 | CE
CN
ROW
RR
UT
|  |  | 0300750 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-01-09 | CE
CN
ROW
RR
UT
|  |  | 0300751 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300752 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
RR
UT
|  |  | 0300753 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
RR
UT
|  |  | 0300754 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
RR
UT
|  |  | 0300755 | Greene |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
UT
|  |  | 0300756 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300757 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300758 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0300759 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0300760 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0300761 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0300762 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300763 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300764 | Steuben | Hambleton LLC | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
|  |  | 0300765 |  | KZF Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300766 | Monroe | Absolute Title Services, LLC | Bloomington | 2009-04-08 | CN
PE
ROW
RR
UT
|  |  | 0300767 | Hancock |  | Hancock County | 2009-02-11 | CE
CN
|  |  | 0300768 |  | Bureau Veritas North America | Indiana Department of Transportation | 2004-04-20
|  |  | 0300769 | Hamilton | Land Construction Corp | Indiana Department of Transportation | 2005-05-25 | CE
CN
RR
|  |  |  | Tipton | Land Construction Corp | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0300770 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300771 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300772 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300773 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
RR
|  |  | 0300774 | Hancock |  | Hancock County | 2009-02-11 | CE
CN
|  |  | 0300775 | Hancock |  | Hancock County | 2009-02-11 | CE
CN
|  |  | 0300776 | Floyd |  | New Albany | -339679.2083 | PE
|  |  | 0300777 |  | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2004-02-17
|  |  | 0300778 |  | GMG INC. | Indiana Department of Transportation | 2003-12-17
|  |  | 0300779 | Floyd |  | New Albany | 2015-09-02 | CE
CN
PE
ROW
RR
|  |  | 0300780 | Huntington | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  |  | Wabash | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2003-12-17 | CE
CN
|  |  | 0300781 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300782 | Porter |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 0300783 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300784 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0300785 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300786 | Lake |  | Lake County | 2007-03-21 | CE
CN
|  |  | 0300787 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0300788 | Vermillion |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0300789 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300790 |  | MCIS LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300791 |  | MCIS LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300792 | Various |  | Indiana Department of Transportation | 2004-03-23 | CE
CN
|  |  | 0300793 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300794 |  | Lorenz Williams Clinton | Indiana Department of Transportation | 2004-01-21
|  |  | 0300795 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300796 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2004-01-21
|  |  | 0300797 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-01-22
|  |  | 0300798 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2015-05-31 | CN
PE
ROW
UT
|  |  | 0300799 | Clark |  | Indiana Department of Transportation | 2013-05-31 | CN
PE
RR
|  |  | 0300800 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300801 |  |  | Indiana Department of Natural Resources | 2004-07-20
|  |  | 0300802 |  |  | Indiana Department of Natural Resources | 2005-07-20
|  |  | 0300803 |  |  | Indiana Department of Natural Resources | 2004-05-25
|  |  | 0300804 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2005-01-19
|  |  | 0300805 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300806 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300807 | Jasper |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300808 | Monroe |  | Monroe County | 2006-10-18 | CE
CN
|  |  | 0300809 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300810 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2004-06-22
|  |  | 0300811 | Harrison | Dreibelbiss Title Company, Inc. | Indiana Department of Transportation | 2013-02-06 | PE
|  |  | 0300812 | Harrison |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300813 | Howard | Dodd Title Corporation | Howard County | 2008-05-08 | CE
CN
PE
|  |  | 0300814 | Hamilton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0300815 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0300816 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0300817 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0300818 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0300819 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0300820 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0300821 | Delaware | GS-IN P.C. | Muncie | -339679.2083 | PE
RR
|  |  | 0300822 |  |  | Indiana Department of Natural Resources | 2004-06-15
|  |  | 0300823 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300824 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0300825 | Hendricks |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
|  |  | 0300826 | Hendricks |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
|  |  | 0300827 | Hendricks |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
|  |  | 0300828 | Hendricks |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
|  |  | 0300829 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2004-06-22
|  |  | 0300830 |  | EFI Global, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300831 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300832 |  | Duesler Realty House | Indiana Department of Transportation | 2004-03-23
|  |  | 0300833 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300835 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300836 |  | Douglass Environmental Services, Inc. | LaPorte County | -339679.2083
|  |  | 0300837 |  | Duesler Realty House | Indiana Department of Transportation | 2004-07-20
|  |  | 0300838 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0300839 | Warrick |  | Warrick County | 2008-09-04 | CE
CN
|  |  | 0300840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300841 |  | Douglass Environmental Services, Inc. | LaPorte County | -339679.2083
|  |  | 0300842 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300843 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300844 | Orange |  | West Baden Springs | 2005-12-14 | CN
PE
|  |  | 0300845 | Ripley |  | Ripley County | 2007-01-24 | CE
CN
|  |  | 0300846 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300847 | LaPorte |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0300848 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2004-01-21
|  |  | 0300849 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300850 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300851 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 0300852 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0300853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300854 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300855 | Various |  | Indiana Department of Transportation | 2013-06-04 | CN
|  |  | 0300856 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300857 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 0300858 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 0300859 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25 | ROW
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25 | CE
CN
PE
ROW
RR
|  |  | 0300860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300861 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300863 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300864 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0300865 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0300866 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300867 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2005-08-17 | CE
CN
|  |  | 0300868 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300869 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300870 | Spencer |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 0300871 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300872 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300873 |  | CGI | Indiana Department of Transportation | 2004-05-25
|  |  | 0300874 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300875 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300876 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300877 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300878 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300879 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300880 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300881 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300882 |  | DCD Consulting LLC | Indiana Department of Transportation | 2003-11-05
|  |  | 0300883 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300884 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300885 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300886 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300887 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300889 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300890 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300891 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300892 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300893 |  | MHM Associates, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300894 |  | ABt SRBI | Indiana Department of Transportation | 2004-01-21
|  |  | 0300895 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0300896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300897 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300898 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300899 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300900 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300901 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300902 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300903 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300904 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300905 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0300906 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300907 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300908 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300909 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2009-08-12 | CE
CN
RR
|  |  | 0300910 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300911 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2005-12-14 | CE
CN
RR
|  |  | 0300912 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300913 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300914 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300915 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300916 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0300917 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300918 | Lake |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
UT
|  |  | 0300919 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300920 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300921 | Dekalb |  | Indiana Department of Transportation | 2005-06-01 | CE
CN
|  |  |  | Noble |  | Indiana Department of Transportation | 2005-06-01 | CE
CN
|  |  | 0300922 | Noble | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300923 | Noble | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-05-25 | CE
CN
|  |  | 0300924 |  | Consolidated Test Company | Indiana Department of Transportation | 2003-11-25
|  |  | 0300925 |  |  | Knox | -339679.2083
|  |  | 0300926 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300927 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300928 | Various |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0300929 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300930 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300931 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300932 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 0300933 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300934 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0300935 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300936 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2004-03-23
|  |  | 0300937 | Various |  | Indiana Department of Transportation | 2004-05-25 | CN
|  |  | 0300938 |  |  | Indiana Department of Transportation | 2003-12-11
|  |  | 0300939 | Allen |  | Indiana Department of Transportation | -339679.2083 | CN
PE
ROW
UT
|  |  | 0300940 | Monroe |  | Monroe County | 2006-10-18 | CE
CN
RR
|  |  | 0300941 | Randolph |  | Randolph County | 2005-02-16 | CE
CN
|  |  | 0300942 | Steuben |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
ROW
UT
|  |  | 0300943 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0300944 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-06-01
|  |  | 0300945 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2007-09-06 | PE
ROW
UT
|  |  | 0300946 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2007-09-06 | PE
ROW
UT
|  |  | 0300947 | Lake |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300948 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300949 | Jasper |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0300950 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0300951 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300952 | LaPorte |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0300953 | Switzerland |  | Indiana Department of Transportation | 2004-04-20 | CE
CN
|  |  | 0300954 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300955 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300956 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300957 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2004-04-20
|  |  | 0300958 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300959 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300960 | Various |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2004-08-17 | RR
|  |  | 0300961 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2004-05-25 | RR
|  |  | 0300962 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300963 | Lake | Huff & Huff, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
|  |  |  | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
UT
|  |  | 0300964 | Allen |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0300965 | Huntington |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  |  | Wabash |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0300966 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300967 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300968 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300969 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0300970 | Steuben |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
ROW
|  |  | 0300971 | Grant |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
ROW
|  |  | 0300972 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2007-05-16 | CE
CN
PE
ROW
UT
|  |  | 0300973 | Huntington |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
ROW
|  |  | 0300974 | Kosciusko |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 0300975 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0300976 |  | Hambleton LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300977 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2007-05-31 | CE
CN
UT
|  |  | 0300978 |  | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300979 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-22
|  |  | 0300980 | Kosciusko | CET, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0300981 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-22
|  |  | 0300982 | Adams |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
|  |  | 0300983 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2004-06-22
|  |  | 0300984 | St. Joseph |  | Indiana Department of Transportation | 2004-09-14 | CE
CN
|  |  | 0300985 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  | 0300986 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 0300987 |  | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0300988 | Henry | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0300989 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0300990 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2004-06-22
|  |  | 0300991 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0300992 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0300993 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 0300994 | Lake |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300995 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0300996 | Lake |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0300997 | Bartholomew |  | Bartholomew County | 2008-07-09 | CE
CN
UT
|  |  | 0300998 | Carroll |  | Carroll County | 2009-10-07 | CE
CN
|  |  | 0300999 | Cass |  | Cass County | 2006-07-19 | CE
CN
|  |  | 0301000 | Clinton |  | Clinton County | 2007-10-31 | CE
CN
|  |  | 0301001 |  |  | Delaware County | -339679.2083
|  |  | 0301002 |  |  | Gibson County | -339679.2083
|  |  | 0301003 | Orange |  | Jefferson County | -339679.2083 | CE
CN
|  |  | 0301004 | Knox |  | Knox County | 2015-10-07 | CE
CN
PE
ROW
|  |  | 0301006 |  |  | LaPorte County | -339679.2083
|  |  | 0301007 | Monroe |  | Monroe County | 2009-10-07 | CE
CN
UT
|  |  | 0301008 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301009 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301013 | Porter |  | Porter County | 2008-02-06 | CE
CN
|  |  | 0301014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301015 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301018 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301022 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301023 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301024 | Pulaski |  | Pulaski County | 2012-10-11 | CE
CN
|  |  | 0301025 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301026 | Rush |  | Rush County | 2010-05-26 | CE
CN
|  |  | 0301027 | St. Joseph |  | St. Joseph County | 2009-04-08 | CE
CN
|  |  | 0301028 | St. Joseph |  | St. Joseph County | 2008-03-05 | CE
CN
|  |  | 0301029 | Steuben | Hambleton LLC | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0301030 |  |  | Indiana Department of Transportation | 2004-10-19
|  |  | 0301031 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301032 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0301033 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301034 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301035 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301036 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301037 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301038 | Miami |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0301039 | LaGrange | Hambleton LLC | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0301040 | LaGrange | Hambleton LLC | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0301041 | Adams | Accidental Discoveries, LLC | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  |  | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0301042 | Miami |  | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  | 0301043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301045 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0301046 | LaPorte |  | LaPorte County | 2009-09-10 | CE
CN
|  |  | 0301047 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301048 | Lake |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  | 0301049 | Lake |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 0301050 | Porter |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
RR
|  |  | 0301051 | St. Joseph |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
PE
|  |  | 0301052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301053 | Newton |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
PE
ROW
|  |  | 0301054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301055 | Fulton |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0301056 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2008-03-26 | CE
CN
PE
|  |  | 0301057 | Marshall |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0301058 |  | AMEC E&I, Inc. | Daviess County | 2004-03-23
|  |  | 0301059 | White |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 0301060 | Fulton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0301061 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0301062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301063 | Marion |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0301064 | Marion |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0301065 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0301066 | White |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0301067 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0301068 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0301069 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0301070 | White |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0301071 | White |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0301072 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0301073 | Lake |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
ROW
|  |  | 0301074 | LaPorte |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
PE
ROW
|  |  | 0301075 | Cass |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0301076 | Newton |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
PE
|  |  | 0301077 | Porter |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
PE
|  |  | 0301078 | Bartholomew |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  |  | Jackson |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  |  | Johnson |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0301079 | LaPorte |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
PE
ROW
|  |  | 0301080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301081 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0301082 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0301083 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0301084 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0301085 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0301086 | Porter |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0301087 | Cass |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0301088 | Marshall | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0301089 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2005-06-01
|  |  | 0301090 | LaPorte |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0301091 | Carroll | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Cass | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Miami | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0301092 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
ROW
UT
|  |  | 0301093 | St. Joseph |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
ROW
|  |  | 0301094 | Cass |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  |  | Fulton |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0301095 | Marshall |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  |  | Starke |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0301096 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2005-05-25
|  |  | 0301097 | LaPorte |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0301098 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0301099 | Jasper |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0301100 | Marshall |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0301101 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0301102 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0301103 | Dubois |  | Dubois County | -339679.2083 | CN
PE
ROW
|  |  | 0301104 | Fountain | BA Martin Architects, PC | Covington | 2006-08-16 | CE
CN
|  |  | 0301105 | Marion | DCD Consulting LLC | Indianapolis | 2015-09-02 | CE
CN
PE
|  |  | 0301106 | Carroll |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0301107 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2004-05-25
|  |  | 0301108 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301109 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301110 |  |  | Indiana Department of Transportation | 2004-03-23
|  |  | 0301111 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301112 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2014-04-09 | CE
CN
PE
UT
|  |  | 0301113 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0301114 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0301115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301116 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301117 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0301118 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0301119 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301120 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0301121 |  |  | Indiana Department of Transportation | 2004-10-19
|  |  | 0301122 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301123 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301127 | Huntington | MHM Associates, Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
ROW
UT
|  |  | 0301128 | Huntington |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
ROW
|  |  | 0301129 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301130 | Wabash |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
ROW
|  |  | 0301131 | Wabash |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
ROW
|  |  | 0301132 | Wabash |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
ROW
|  |  | 0301133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301135 | Wabash |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
|  |  | 0301136 | Miami |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
ROW
|  |  | 0301137 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301138 | Grant |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0301139 | Grant |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0301140 | Kosciusko |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
PE
ROW
|  |  | 0301141 | Elkhart |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
ROW
UT
|  |  | 0301142 | Elkhart |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0301143 | Elkhart |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0301144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301145 | Allen |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 0301146 | Allen |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0301147 | Allen |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0301148 | Allen |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0301149 | Allen |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 0301150 | Allen |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0301151 | Jay | Alliance Survey Company | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
ROW
|  |  | 0301152 | Allen |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0301153 |  | KZF Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301154 | Huntington |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
ROW
|  |  |  | Whitley |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
PE
ROW
|  |  | 0301155 | Wells |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
ROW
|  |  | 0301156 | Miami | Atlas Appraisals, LLC | Converse | -339679.2083 | CN
|  |  | 0301157 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0301158 | Henry | GeoSolutions, Inc. | Henry County | 2012-09-12 | CE
CN
|  |  | 0301159 | Hamilton |  | Westfield | 2008-09-04 | CE
CN
PE
|  |  | 0301160 | Marion | DCD Consulting LLC | Indianapolis | 2009-05-13 | CE
CN
|  |  | 0301161 | Putnam | Clayton L. Roots | Greencastle | 2018-03-14 | CN
PE
|  |  | 0301162 | Vigo | Bayswater Company, LLC | Terre Haute | 2009-05-06 | CE
CN
|  |  | 0301163 | Cass |  | Cass County | -339679.2083 | PE
|  |  | 0301164 | Delaware | GS-IN P.C. | Muncie | 2009-05-06 | CE
CN
RR
|  |  | 0301165 | LaPorte | Farah and Sons, Inc. | Michigan City | 2019-05-09 | CE
CN
|  |  | 0301166 | Lake | Consolidated Test Company | Hammond | 2013-08-07 | CE
CN
|  |  | 0301167 | Monroe |  | Ellettsville | -339679.2083 | PE
|  |  | 0301168 | Madison | AAC Environmental Consulting, LLC | Anderson | 2011-05-11 | CE
CN
|  |  | 0301169 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 0301170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301172 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0301173 | Clark |  | Indiana Department of Natural Resources | 2014-05-08 | CE
CN
PE
|  |  | 0301174 | Monroe |  | Ellettsville | -339679.2083 | CN
|  |  | 0301175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0301180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400001 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0400002 | Harrison |  | Lanesville | 2011-04-13 | CE
CN
|  |  | 0400003 |  | Michael Baker International, Inc. | Yorktown | -339679.2083
|  |  | 0400004 | Ripley |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0400005 |  | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2006-07-19
|  |  | 0400006 | Newton |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0400007 | Newton |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
|  |  | 0400008 |  |  | Clarksville | -339679.2083
|  |  | 0400009 | Jefferson | Engineering Resources, Inc. | Madison | 2008-08-20 | CE
CN
|  |  | 0400010 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 0400011 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2010-11-10 | CE
CN
UT
|  |  | 0400012 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2008-03-05 | PE
|  |  | 0400013 | Rush | J. Williams Appraisal Group, LLC | Rushville | 2013-07-10 | CE
CN
RR
|  |  | 0400014 | Fayette | Wilcox Environmental Engineering, Inc. | Connersville | 2009-04-08 | CE
CN
|  |  | 0400015 |  | Cheri K. Lewis Engineers | Garrett | -339679.2083
|  |  | 0400016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400017 | Decatur | Collier Transport Inc. | Greensburg | 2015-02-04 | CE
CN
UT
|  |  | 0400018 |  | Eagle Ridge Civil Engineering Services, LLC | Linton | -339679.2083
|  |  | 0400019 | Jennings |  | North Vernon | 2013-05-01 | CE
CN
PE
|  |  | 0400020 | Various |  | Wayne County | 2004-03-04 | CN
|  |  |  | Wayne |  | Wayne County | 2004-03-04 | CN
PE
|  |  | 0400021 | Elkhart | Gandhi and Associates, Inc. | Nappanee | 2006-05-24 | CE
CN
|  |  | 0400022 | Carroll | Blood Hound, Inc. (former) | Delphi | -339679.2083 | CN
|  |  | 0400023 | Jennings |  | North Vernon | -339679.2083 | PE
|  |  | 0400024 |  | Hydrogeology, Inc. | Portland | -339679.2083
|  |  | 0400025 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2011-05-11 | CE
CN
RR
|  |  | 0400026 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 0400027 | Randolph | Apex Consulting & Surveying, Inc. | Winchester | 2008-07-09 | CE
CN
RR
|  |  | 0400028 | Harrison |  | Harrison County | 2011-05-11 | CE
CN
PE
UT
|  |  | 0400029 | Wayne |  | Indiana Department of Natural Resources | 2015-05-31 | CN
|  |  | 0400030 |  |  | Putnam County | -339679.2083
|  |  | 0400031 | Fountain | AECON, Inc. | Attica | 2008-04-02 | CE
CN
|  |  | 0400032 | Cass |  | Cass County | 2007-12-12 | CE
CN
|  |  | 0400033 | Wayne | Appraisal Office of Central Indiana | Centerville | 2010-07-07 | CE
CN
UT
|  |  | 0400034 | Dekalb | Quantum Spatial, Inc. | Dekalb County | 2007-10-03 | CE
CN
|  |  | 0400035 |  | Christopher B. Burke Engineering, Ltd. | Gaston | -339679.2083
|  |  | 0400036 | Howard | Collins Engineers Incorporated | Greentown | 2007-04-18 | CE
CN
|  |  | 0400037 | Hancock |  | Hancock County | 2015-12-16 | CE
CN
ROW
UT
|  |  | 0400038 |  |  | Porter County | -339679.2083
|  |  | 0400039 | Spencer | Infrastructure Engineering, Inc. | Rockport | 2016-08-10 | CE
CN
|  |  | 0400040 | Rush |  | Rush County | 2009-05-06 | CE
CN
|  |  | 0400041 |  | McAlister Excavating Co., Inc. | Williamsport | -339679.2083
|  |  | 0400042 | Dubois |  | Dubois County | 2007-10-03 | CN
|  |  | 0400043 | Fayette | Wilcox Environmental Engineering, Inc. | Fayette County | 2007-05-16 | CE
CN
|  |  | 0400044 |  |  | Rush County | -339679.2083
|  |  | 0400045 | Jay | Hydrogeology, Inc. | Jay County | 2006-06-21 | CE
CN
|  |  | 0400046 | Marshall | Advanced Engineering Consultants, Ltd. | Bremen | 2008-05-08 | CE
CN
RR
|  |  | 0400047 | Hendricks |  | Hendricks County | 2004-10-19 | CE
CN
PE
|  |  | 0400048 | Steuben |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0400049 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400050 |  |  | Clark County | -339679.2083
|  |  | 0400051 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400052 | St. Joseph |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
PE
ROW
|  |  | 0400053 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400054 | Lake | Consolidated Test Company | Lake County | 2004-03-23 | CE
CN
PE
RR
|  |  | 0400055 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400056 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0400057 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0400058 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400059 | Vigo |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400060 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0400061 | LaPorte |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400062 | Lake |  | Indiana Department of Transportation | 2005-03-16 | CE
CN
RR
|  |  | 0400063 | LaPorte |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
|  |  | 0400064 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2012-05-31 | CN
PE
|  |  | 0400065 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400067 | Tippecanoe |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0400068 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400069 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0400070 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-15
|  |  | 0400071 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400072 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400074 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0400075 | Wayne | Indiana Appraisal Group, Inc. | Wayne County | 2010-01-13 | CE
CN
|  |  | 0400076 | Lawrence |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400077 | Lawrence |  | Indiana Department of Transportation | 2021-08-11 | CN
PE
|  |  | 0400078 | Johnson |  | Johnson County | 2009-05-06 | CE
CN
|  |  | 0400079 | Johnson |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0400080 | Dearborn |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0400081 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400082 |  | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083
|  |  | 0400083 | St. Joseph | Flexible H.R. Solutions, LLC | St. Joseph County | 2008-05-08 | CE
CN
|  |  | 0400084 | St. Joseph |  | South Bend | 2008-03-05 | CE
CN
|  |  | 0400085 | Jackson |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  | 0400086 | St. Joseph |  | South Bend | 2008-03-05 | CE
CN
|  |  | 0400087 | Sullivan |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
|  |  | 0400088 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0400089 | Knox |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
[6 empty] | Indiana Department of Transportation | 2015-08-05
|  |  | 0400090 | Greene |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 0400091 | Greene |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
PE
ROW
UT
|  |  | 0400092 |  | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | -339679.2083
|  |  | 0400093 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400094 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400095 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0400096 | Various |  | Indiana Department of Transportation | 2008-06-18 | CE
CN
|  |  | 0400097 | Greene |  | Indiana Department of Transportation | 2016-04-20 | CE
CN
PE
ROW
UT
|  |  | 0400098 | Greene |  | Indiana Department of Transportation | 2016-04-20 | CE
CN
PE
ROW
UT
|  |  | 0400099 | Greene |  | Indiana Department of Transportation | 2016-04-20 | CE
CN
PE
ROW
UT
|  |  | 0400100 | Greene |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
|  |  | 0400101 | Sullivan |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
ROW
UT
|  |  | 0400102 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 0400103 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400104 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400105 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400106 | Fayette |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400107 | Parke |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
PE
|  |  | 0400108 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400109 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-04-20
|  |  | 0400110 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400111 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0400112 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25
|  |  | 0400113 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0400114 |  |  | Indiana Department of Transportation | 2004-04-20
|  |  | 0400115 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400116 | Hamilton |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0400117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400118 | Newton |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400119 | Lake |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400120 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400121 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400122 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400123 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400125 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-15
|  |  | 0400126 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-15
|  |  | 0400127 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-06-15
|  |  | 0400128 | Various | Absolute Title Services, LLC | Indiana Department of Transportation | 2011-05-31 | PE
|  |  |  | Warrick | Absolute Title Services, LLC | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 0400129 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400130 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | PE
RR
UT
|  |  | 0400131 | Hamilton | H. Stewart Kline & Associates, Inc. | Noblesville | 2006-07-19 | CE
CN
|  |  | 0400132 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0400133 | Jefferson | Engineering Resources, Inc. | Madison | 2009-06-24 | CE
CN
|  |  | 0400134 | Crawford | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400135 | Sullivan |  | Indiana Department of Transportation | 2004-05-25 | CE
CN
RR
|  |  | 0400136 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400137 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400138 | Sullivan | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400139 | Sullivan | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400140 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400141 | Gibson | Coor Consulting | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400142 | Harrison | B. L. A., Inc. | Harrison County | 2010-11-10 | CE
CN
UT
|  |  | 0400143 | Randolph | CKW Land Surveying, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
ROW
UT
|  |  | 0400144 | Dubois | CMF Engineering, Inc. | Ferdinand | 2004-09-14 | CE
CN
PE
ROW
UT
|  |  | 0400145 | Morgan |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
RR
|  |  | 0400146 | Hendricks | Horner and Shifrin, Inc. | Plainfield | 2011-08-10 | CE
CN
UT
|  |  | 0400147 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25 | CE
CN
|  |  | 0400148 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 0400149 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400150 | Gibson | Coor Consulting | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400151 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400152 | Warrick |  | Warrick County | 2013-05-01 | CE
CN
UT
|  |  | 0400153 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400154 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0400155 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0400156 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400157 | Vanderburgh | Coor Consulting | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400158 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 0400159 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400160 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400161 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400162 | Blackford | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400163 | Blackford | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400164 | Blackford | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400165 | Wells | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400166 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400167 | Whitley | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400168 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400169 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400170 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400171 | Wells | Accidental Discoveries, LLC | Indiana Department of Natural Resources | -339679.2083 | PE
RR
|  |  | 0400172 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400173 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400174 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400175 | Wells | Hardlines Design Company | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400176 | Wells | Hardlines Design Company | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400177 | Wells | Hardlines Design Company | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400178 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0400179 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0400180 | Wells | Hardlines Design Company | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400181 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0400182 | Wayne |  | Wayne County | 2006-04-19 | CE
CN
|  |  | 0400183 | Lawrence | ICA Engineering, Inc. | Mitchell | 2009-06-10 | CE
CN
PE
RR
|  |  | 0400184 | Allen | Hardlines Design Company | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400185 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0400186 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400187 | Adams | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Allen | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0400188 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400189 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400190 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0400191 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400192 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400193 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400194 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400195 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400196 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400197 | Whitley |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400198 | Kosciusko | Jones & Henry Engineers, Ltd. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400199 | Kosciusko | Jones & Henry Engineers, Ltd. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400200 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0400201 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400202 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400203 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400204 | Kosciusko | AquaTerra Consulting, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400205 | Kosciusko | AquaTerra Consulting, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400206 | Marshall |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0400207 | Kosciusko | AquaTerra Consulting, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400208 | Kosciusko | FPBH, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400209 | Marshall | FPBH, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400210 | Jasper | Consolidated Test Company | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
RR
|  |  |  | Lake | Consolidated Test Company | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
RR
|  |  |  | Newton | Consolidated Test Company | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
|  |  | 0400211 | Lake |  | Indiana Department of Transportation | 2005-03-16 | CE
CN
RR
|  |  | 0400212 | Marshall | FPBH, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400213 | Marshall | FPBH, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400214 | Gibson | CSR Engineering, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
RR
UT
|  |  | 0400215 | Steuben |  | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  | 0400216 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400217 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2005-05-25
|  |  | 0400218 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400219 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400220 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400221 |  | Collier Transport Inc. | Indiana Department of Transportation | 2005-05-25
|  |  | 0400222 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400223 |  |  | Indiana Department of Transportation | 2005-03-16
|  |  | 0400224 |  |  | Indiana Department of Transportation | 2005-03-16
|  |  | 0400225 | Vanderburgh |  | Indiana Department of Transportation | 2012-04-17 | CN
PE
|  |  | 0400226 | Spencer |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
|  |  | 0400227 | Marshall | ACMS Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400228 | St. Joseph |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
PE
|  |  | 0400229 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0400230 | Starke |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400231 | LaPorte |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0400232 | LaPorte |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Starke |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400233 | Starke |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400235 | Starke |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400236 | LaPorte | MCIS LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400237 | Porter | MCIS LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400238 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400239 | Noble | ERES International, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400240 | Dekalb | American Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400241 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400242 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400243 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400244 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400245 | Dubois | Aarcher, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400246 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400247 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0400248 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400249 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2004-11-16
|  |  | 0400250 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2004-05-25
|  |  | 0400251 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2004-11-16
|  |  | 0400252 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2004-11-16
|  |  | 0400253 |  |  | Indiana Department of Natural Resources | 2004-05-25
|  |  | 0400254 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2004-11-16
|  |  | 0400255 | Decatur |  | Decatur County | 2008-05-08 | CE
CN
|  |  | 0400256 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400257 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400258 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-04-20
|  |  | 0400259 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400260 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0400261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400263 |  |  | Indiana Department of Transportation | 2007-02-21
|  |  | 0400264 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400265 |  |  | Shelby County | -339679.2083
|  |  | 0400266 | Johnson |  | Johnson County | 2007-05-31 | CE
CN
UT
|  |  | 0400267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400271 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400272 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400273 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2004-12-14 | CE
CN
|  |  | 0400274 | Madison |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0400275 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0400276 | Randolph |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400277 |  | Civil Designs, LLP | Indiana Department of Transportation | -339679.2083
|  |  | 0400278 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-06-22 | CE
CN
|  |  | 0400279 |  | Fleis & VandenBrink Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400280 | Tipton |  | Indiana Department of Transportation | 2005-09-14 | CE
CN
|  |  | 0400281 | Randolph |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400282 | Randolph |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400283 | Marion |  | Indiana Department of Transportation | 2014-05-31 | PE
RR
|  |  | 0400284 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400285 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2015-04-15 | CE
CN
PE
ROW
|  |  | 0400286 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-08-05 | PE
|  |  | 0400287 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400288 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2004-09-14
|  |  | 0400289 | Marion |  | Indiana Department of Transportation | 2009-11-06 | PE
ROW
UT
|  |  | 0400290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400291 |  | B. L. A., Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400292 | Howard |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
PE
ROW
|  |  | 0400293 | Franklin |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
ROW
|  |  | 0400294 | Randolph |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
PE
ROW
UT
|  |  | 0400295 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400296 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400297 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400298 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400299 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400300 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400301 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2008-02-27 | CE
CN
|  |  | 0400302 | Hamilton |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 0400303 | Randolph |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
|  |  | 0400304 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400305 |  |  | Indiana Department of Transportation | 2017-08-02
|  |  | 0400306 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400307 |  |  | Tippecanoe County | -339679.2083
|  |  | 0400308 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400309 |  | DuSABLE, Inc. | Lafayette | 2006-04-19
|  |  | 0400310 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25
|  |  | 0400311 | Tippecanoe |  | Tippecanoe County | 2010-09-01 | CE
CN
|  |  | 0400312 | Lawrence |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
PE
|  |  | 0400313 | Greene |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
ROW
|  |  | 0400314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400315 | Delaware |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Grant |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  | 0400316 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2004-03-23 | CE
CN
PE
ROW
RR
UT
|  |  | 0400317 | Madison |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0400318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400319 | Monroe | Absolute Title Services, LLC | Bloomington | -339679.2083 | PE
|  |  | 0400320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400321 | Various |  | Indiana State Agencies | -339679.2083 | CN
|  |  | 0400322 | Monroe |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
PE
|  |  | 0400323 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400324 | Monroe |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0400325 | Jennings |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
ROW
RR
UT
|  |  | 0400326 | Boone |  | Boone County | 2009-09-10 | CE
CN
|  |  | 0400327 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2007-10-03 | CE
CN
UT
|  |  | 0400328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400329 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400331 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400332 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0400333 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400334 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2004-07-20
|  |  | 0400335 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400336 |  |  | Indiana Department of Natural Resources | 2004-06-22
|  |  | 0400337 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400338 | Crawford |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 0400339 | Crawford |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 0400340 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400341 | Crawford |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 0400342 | Vermillion |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 0400343 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400344 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400345 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400346 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400348 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400349 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400351 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400352 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400353 |  |  | Clark County | -339679.2083
|  |  | 0400354 | Wells |  | Wells County | 2011-05-11 | CE
CN
|  |  | 0400355 | Parke |  | Parke County | -339679.2083 | CN
|  |  | 0400356 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400357 | Wayne |  | Indiana Department of Transportation | 2005-06-22 | CE
CN
|  |  | 0400358 | Vigo |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
RR
UT
|  |  | 0400359 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0400360 |  | C Blair Enterprises, Inc. | Elkhart County | -339679.2083
|  |  | 0400361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400362 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400363 | Elkhart | C Blair Enterprises, Inc. | Elkhart County | 2009-08-12 | CN
|  |  | 0400364 |  | Alliance Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400365 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 0400366 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400367 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400368 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400369 | Fountain |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0400370 | Clay |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Owen |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400371 | Vigo |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400372 | Boone |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0400373 | Morgan |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0400374 | Parke |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400375 | Vermillion |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400376 | Hendricks |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0400377 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400378 | Clinton |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400379 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400382 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400383 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400384 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2005-06-22
|  |  | 0400385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400386 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400387 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400388 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400389 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400390 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Henry | DCD Consulting LLC | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  |  | Wayne | DCD Consulting LLC | Indiana Department of Transportation | 2004-08-17 | CE
CN
|  |  | 0400391 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400392 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0400393 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400394 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0400395 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0400396 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400397 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 0400398 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400399 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400400 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400401 |  |  | Indiana Department of Transportation | 2004-06-22
|  |  | 0400402 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0400403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400404 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0400405 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400407 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2013-08-07 | PE
ROW
|  |  | 0400408 | Marion |  | Indiana Department of Transportation | 2014-05-31 | ROW
|  |  | 0400409 | Marion |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
ROW
UT
|  |  | 0400410 | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
UT
|  |  | 0400411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400412 |  |  | Indiana Department of Transportation | 2017-08-02
|  |  | 0400413 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0400414 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0400415 | Marion |  | Indiana Department of Transportation | 2004-06-22 | CE
CN
|  |  | 0400416 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400417 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400418 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  | 0400419 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400420 | Greene |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0400421 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400422 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400423 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400424 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
ROW
|  |  | 0400425 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400426 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400427 | Clark | Data Transfer Solutions, LLC | Jeffersonville | 2005-03-16 | CE
CN
|  |  | 0400428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400429 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400430 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400431 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0400432 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400433 | Miami |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0400434 | Huntington |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400435 | Huntington |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400436 | Noble |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0400437 | Noble |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400438 | LaGrange |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400439 | Huntington |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400440 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0400441 | Allen |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Huntington |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400442 | Grant |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400443 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400444 | Warrick |  | Warrick County | 2008-09-04 | CE
CN
PE
UT
|  |  | 0400445 | Warrick |  | Indiana Department of Transportation | 2009-03-11 | PE
ROW
UT
|  |  | 0400446 | Pike |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
UT
|  |  | 0400447 |  | ABt SRBI | Indiana Department of Transportation | 2004-08-17
|  |  | 0400448 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0400449 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400450 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400451 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400452 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400453 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400454 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0400455 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0400456 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0400458 | Dearborn |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
RR
|  |  | 0400459 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0400460 |  |  | Indiana Department of Natural Resources | 2004-08-17
|  |  | 0400461 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0400462 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400463 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400464 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400467 | Marshall | Active Environmental Services, Inc. | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400468 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400469 |  |  | Indiana Department of Transportation | 2004-07-20
|  |  | 0400470 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400471 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400472 | Daviess |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0400473 | Warrick |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
RR
|  |  | 0400474 | Warrick |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 0400475 | Hendricks | Horner and Shifrin, Inc. | Plainfield | 2007-05-02 | CE
CN
|  |  | 0400476 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400477 | Whitley |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0400478 | Washington | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | 2004-10-19 | CE
CN
|  |  | 0400479 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400481 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400482 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400483 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400484 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400485 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400486 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400487 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400488 |  |  | Indiana Department of Natural Resources | 2004-09-14
|  |  | 0400489 |  |  | Indiana Department of Natural Resources | 2004-08-17
|  |  | 0400490 |  |  | Indiana Department of Natural Resources | 2004-08-17
|  |  | 0400491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400493 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2013-05-31 | CN
PE
|  |  | 0400494 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0400495 | Henry |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 0400496 |  | McCullouch Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400497 | Hancock |  | Hancock County | 2006-06-21 | CE
CN
UT
|  |  | 0400498 |  | Dyer Environmental Services | Lawrence | -339679.2083
|  |  | 0400499 |  | Dyer Environmental Services | Lawrence | -339679.2083
|  |  | 0400500 |  | Dyer Environmental Services | Lawrence | -339679.2083
|  |  | 0400501 |  | Duesler Realty House | Indiana Department of Transportation | 2004-08-17
|  |  | 0400502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400503 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400504 | White | Fugro Roadware, Inc. | White County | 2006-02-22 | CE
CN
PE
ROW
|  |  | 0400505 | White |  | White County | 2009-08-12 | CE
CN
PE
ROW
RR
UT
|  |  | 0400506 | White | Fugro Roadware, Inc. | Monticello | 2009-04-08 | CE
CN
PE
ROW
|  |  | 0400507 | White | Fugro Roadware, Inc. | White County | 2015-09-02 | PE
ROW
|  |  | 0400508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400510 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400512 |  | Consolidated Test Company | Indiana Department of Transportation | 2004-07-15
|  |  | 0400513 | Vigo |  | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
|  |  | 0400514 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400515 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400516 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400517 | Randolph |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0400518 | Wayne |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400519 | Wayne |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0400520 | Henry |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0400521 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2007-10-17 | CE
CN
RR
|  |  |  | Shelby | CoCal Consulting, LLC | Indiana Department of Transportation | 2007-10-17 | CE
CN
|  |  | 0400522 | Hancock |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  |  | Henry |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0400523 | Hamilton |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400524 | Hamilton |  | Indiana Department of Transportation | 2007-01-24 | CE
CN
|  |  | 0400525 | Porter |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0400526 | LaPorte |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0400527 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400528 | Starke |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0400529 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0400530 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400531 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0400532 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400533 | Marshall |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0400534 | Spencer |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
ROW
UT
|  |  | 0400535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400537 | Vigo |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0400538 | Vigo |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
|  |  | 0400539 | Vigo |  | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
UT
|  |  | 0400540 | Vigo |  | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
|  |  | 0400541 | Vigo |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
|  |  | 0400542 | Vigo |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0400543 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400544 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400545 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400546 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0400547 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400548 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2004-09-14
|  |  | 0400549 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400550 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400551 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400552 | Huntington |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0400553 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 0400554 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400555 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0400556 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0400557 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400558 | Spencer |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
ROW
|  |  | 0400559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400560 | Hendricks |  | Hendricks County | 2009-11-04 | CE
CN
|  |  | 0400561 | Hendricks |  | Hendricks County | 2009-11-04 | CE
CN
|  |  | 0400562 | Hendricks |  | Hendricks County | 2009-11-04 | CE
CN
RR
|  |  | 0400563 | Hendricks |  | Indiana Department of Transportation | 2007-03-07 | CE
CN
PE
ROW
UT
|  |  | 0400564 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2007-06-06
|  |  | 0400565 | Vermillion | Archaeology and Geomorphology Services | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400566 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400567 |  |  | Indiana State Agencies | 2006-06-21
|  |  | 0400568 | Owen |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0400569 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2008-02-27
|  |  | 0400570 | Hancock | CGI | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
ROW
UT
|  |  | 0400571 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2004-08-17
|  |  | 0400572 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2004-08-17
|  |  | 0400573 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0400574 |  | CGI | Indiana Department of Transportation | 2004-09-14
|  |  | 0400575 | Warren |  | Warren County | -339679.2083 | CN
|  |  | 0400576 |  |  | Indiana Department of Natural Resources | 2004-08-17
|  |  | 0400577 |  |  | Indiana Department of Natural Resources | 2004-08-17
|  |  | 0400578 |  |  | Indiana Department of Natural Resources | 2004-08-17
|  |  | 0400579 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400580 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2004-09-14
|  |  | 0400581 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0400582 | Allen | CTL Engineering of Indiana, Inc. | Allen County | -339679.2083 | PE
|  |  | 0400583 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0400584 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2015-11-10 | CE
CN
PE
ROW
UT
|  |  | 0400585 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0400586 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2011-04-13 | CE
CN
PE
ROW
RR
|  |  | 0400587 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083 | PE
ROW
|  |  | 0400588 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0400589 | Allen | Global Management Group, Inc. | New Haven | 2012-05-02 | CE
CN
PE
ROW
|  |  | 0400590 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0400591 | Warren |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0400592 | Vermillion |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0400593 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2010-10-06 | CE
CN
ROW
UT
|  |  | 0400594 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400595 | Hancock |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 0400596 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400597 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400598 |  |  | Indiana Department of Transportation | 2006-11-01
|  |  | 0400599 | Boone |  | Indiana Department of Transportation | 2007-04-04 | CE
CN
|  |  | 0400600 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400601 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400602 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400603 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
|  |  | 0400604 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400605 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0400606 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-08-17
|  |  | 0400607 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400608 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400609 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 0400610 | Henry |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 0400611 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0400612 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400613 |  | Chicago Title Insurance Company | Indiana Department of Transportation | -339679.2083
|  |  | 0400614 | Grant |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  |  | Huntington |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0400615 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400616 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400617 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400618 | Marshall |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0400619 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400620 |  |  | Indiana Department of Transportation | 2005-03-16
|  |  | 0400621 | Shelby | Jeffrey S. Juday | Shelbyville | 2005-05-25 | CE
CN
RR
|  |  | 0400622 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-09-14
|  |  | 0400623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400624 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400625 |  |  | Indiana Department of Transportation | 2004-08-17
|  |  | 0400626 | Hendricks |  | Avon | 2006-10-18 | CE
CN
UT
|  |  | 0400627 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2005-06-22
|  |  | 0400628 |  | Empower Results, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400629 | Gibson | K & S Engineers, Inc. | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  |  | Warrick | K & S Engineers, Inc. | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0400630 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0400631 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400632 | LaPorte |  | Indiana Department of Transportation | 2009-10-07 | CE
CN
|  |  | 0400633 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400634 | Porter | Domain Architecture, Inc. | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 0400635 | Allen |  | Allen County | 2009-11-04 | CE
CN
PE
ROW
RR
UT
|  |  | 0400636 | Allen |  | Allen County | 2009-11-04 | CE
CN
PE
ROW
RR
UT
[6 empty] | Allen County | 2009-11-04
|  |  | 0400637 | Allen |  | Allen County | 2009-11-04 | CE
CN
PE
ROW
RR
UT
|  |  | 0400638 | Allen |  | Allen County | 2009-11-04 | CE
CN
PE
ROW
RR
UT
|  |  | 0400639 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0400640 | Lake | Consolidated Test Company | Hammond | 2013-05-01 | CE
CN
|  |  | 0400641 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-03-16 | CE
CN
|  |  | 0400642 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400643 | Various |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0400644 | Noble |  | Noble County | 2007-08-22 | CE
CN
|  |  | 0400645 | Marion | DCD Consulting LLC | Indianapolis | 2007-01-10 | CE
CN
|  |  | 0400646 | Marion | DCD Consulting LLC | Indianapolis | 2008-07-09 | CE
CN
|  |  | 0400647 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400648 | Marion | DCD Consulting LLC | Indianapolis | 2007-10-17 | CN
|  |  | 0400649 | Marion | DCD Consulting LLC | Indianapolis | 2009-04-08 | CE
CN
|  |  | 0400650 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400651 | Noble | Bartlett & Associates, Inc. | Indiana Department of Transportation | 2005-03-16 | CE
CN
|  |  | 0400652 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0400653 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 0400654 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400655 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400656 | Clark |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0400657 | Jennings |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0400658 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400659 | Morgan |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400660 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400661 | Jackson |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Washington |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400662 |  | Marine Solutions, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0400663 |  | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2004-10-19
|  |  | 0400664 |  | Consolidated Test Company | Indiana Department of Transportation | 2005-05-25
|  |  | 0400665 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2005-05-25
|  |  | 0400666 |  | Consolidated Test Company | Indiana Department of Transportation | 2005-05-25
|  |  | 0400667 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | 2005-05-25
|  |  | 0400668 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2005-05-25
|  |  | 0400669 |  | Horn and Associates, Inc. | Indiana Department of Transportation | 2005-06-22
|  |  | 0400670 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2005-05-25
|  |  | 0400671 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2005-05-25
|  |  | 0400672 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2005-05-25
|  |  | 0400673 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2005-05-25
|  |  | 0400674 | Shelby |  | Shelby County | -339679.2083 | PE
|  |  | 0400675 |  | Basin Field Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400676 | Gibson |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0400677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400678 | Marion |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0400679 | Morgan |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400680 | Dearborn |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400681 |  |  | Indiana Department of Transportation | 2004-09-14
|  |  | 0400682 | Jackson |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400683 | Clark |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  |  | Washington |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400684 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400685 | Clark |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400686 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400687 | Ripley |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400688 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400689 | Floyd |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0400690 | Clark | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Scott | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400691 | Scott |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400692 | Ripley | GSG Consultants, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0400693 | Floyd |  | Indiana Department of Transportation | 2005-03-16 | CE
CN
|  |  |  | Washington |  | Indiana Department of Transportation | 2005-03-16 | CE
CN
|  |  | 0400694 | Jefferson |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400695 | Jefferson |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400696 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400697 |  | Merle Edward Orem | Indiana Department of Transportation | 2005-04-20
|  |  | 0400698 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400699 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400700 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0400701 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400702 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400703 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2005-05-25
|  |  | 0400704 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0400705 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0400706 |  | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0400707 |  | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2005-07-20
|  |  | 0400708 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 0400709 |  |  | Lake County | -339679.2083
|  |  | 0400710 | Lake |  | Lake County | 2008-08-20 | CE
CN
|  |  | 0400711 | Lake | Cornerstone Design | Highland | 2010-02-24 | CE
CN
|  |  | 0400712 | Lake | Compliance Consulting Service, Inc. | Griffith | 2010-05-12 | CE
CN
UT
|  |  | 0400713 | Lake | Compliance Consulting Service, Inc. | Griffith | 2009-07-15 | CE
CN
UT
|  |  | 0400714 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2006-03-15 | CE
CN
|  |  | 0400715 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2009-04-08 | CE
CN
|  |  | 0400716 | Lake |  | Lake County | 2011-04-13 | CE
CN
|  |  | 0400717 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0400718 | Vigo |  | Terre Haute | 2008-11-19 | CN
|  |  | 0400719 | Various |  | Indiana Department of Transportation | 2013-05-31 | CN
|  |  | 0400720 | Vigo |  | Vigo County | -339679.2083 | CN
|  |  | 0400721 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400722 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400723 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400724 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400725 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0400726 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400727 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0400728 |  | LFR, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400729 |  | LFR, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400730 |  |  | South Bend | -339679.2083
|  |  | 0400731 | Vanderburgh | CGI | Vanderburgh County | 2014-11-13 | CE
CN
|  |  | 0400732 |  | CGI | Evansville | -339679.2083
|  |  | 0400733 |  | CGI | Evansville | 2015-07-08
|  |  | 0400734 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 0400735 |  |  | Avon | -339679.2083
|  |  | 0400736 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400737 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
RR
UT
|  |  | 0400738 |  | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400739 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400740 | St. Joseph |  | St. Joseph County | 2008-11-19 | CE
CN
|  |  | 0400741 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400742 |  | Donohue & Associates, Inc. | Indiana Department of Transportation | 2005-10-19
|  |  | 0400743 |  | Engineering Technologies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400744 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0400745 |  |  | Indiana Department of Transportation | 2004-10-19
|  |  | 0400746 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400747 |  |  | Elkhart County | -339679.2083
|  |  | 0400748 |  |  | Elkhart County | -339679.2083
|  |  | 0400749 |  |  | Elkhart County | -339679.2083
|  |  | 0400750 | Marion | DCD Consulting LLC | Indiana Department of Natural Resources | 2005-04-20 | CE
CN
|  |  | 0400751 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2004-09-14
|  |  | 0400752 | Clinton |  | Indiana Department of Transportation | 2007-10-17 | PE
|  |  | 0400753 | Hendricks | AI Engineers, Inc. | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  |  | Putnam | AI Engineers, Inc. | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0400754 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2007-05-02 | CE
CN
|  |  | 0400755 | Benton |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400756 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2008-07-09 | CE
CN
|  |  | 0400757 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0400758 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400759 |  |  | Indiana Department of Transportation | 2004-10-19
|  |  | 0400760 | Porter | Leitner and Associates, Inc. | Valparaiso | 2006-03-29 | CE
CN
|  |  | 0400761 | Porter | Leitner and Associates, Inc. | Valparaiso | 2006-03-29 | CE
CN
|  |  | 0400762 | LaPorte |  | LaPorte County | -339679.2083 | CN
|  |  | 0400763 |  |  | Indiana Department of Transportation | 2004-10-19
|  |  | 0400764 | Starke | H.R. Gray | North Judson | -339679.2083 | CN
|  |  | 0400765 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0400766 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16 | CE
CN
UT
|  |  | 0400767 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0400768 | Various |  | Indiana Department of Transportation | 2005-06-22 | CN
|  |  | 0400769 | Various |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0400770 | Starke |  | Indiana Department of Transportation | 2011-06-01 | PE
|  |  | 0400771 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400772 | Benton |  | Indiana Department of Transportation | 2014-07-09 | PE
|  |  | 0400773 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400774 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 0400775 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400776 | Fountain |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
ROW
|  |  | 0400777 | Newton |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0400778 | Pulaski |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0400779 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400780 | St. Joseph |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0400781 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400782 | Newton |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0400783 | Lake |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0400784 | Lake |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  | 0400785 | Benton |  | Indiana Department of Transportation | 2009-08-12 | CE
CN
PE
ROW
|  |  | 0400786 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0400787 | Jasper |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0400788 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400789 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400790 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400792 | Jasper |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0400793 | Jasper |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 0400794 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400795 | Jasper |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 0400796 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400797 | Lake |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 0400798 | Lake |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0400799 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400800 | Lake |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0400801 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0400802 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400803 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400804 | LaPorte |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0400805 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400806 | LaPorte |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0400807 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400808 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400809 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400810 | St. Joseph | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0400811 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400812 | Vermillion |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
PE
|  |  | 0400813 | Warren |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
PE
|  |  | 0400814 |  |  | Indiana Department of Transportation | 2004-10-19
|  |  | 0400815 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0400816 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0400817 | Warren |  | Indiana Department of Transportation | 2008-02-27 | CE
CN
|  |  | 0400818 |  |  | Indiana Department of Transportation | 2004-07-30
|  |  | 0400819 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400821 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400822 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400823 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400824 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400825 | Vermillion |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
ROW
|  |  | 0400826 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
RR
|  |  | 0400827 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2006-10-18 | CE
CN
RR
|  |  | 0400828 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0400829 | Morgan |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0400830 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400831 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0400832 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0400833 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400834 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0400835 | Various |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0400836 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400837 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0400838 |  |  | Indiana Department of Transportation | 2011-07-13
|  |  | 0400839 | White |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
PE
|  |  | 0400840 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2005-09-14
|  |  | 0400841 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2004-12-14
|  |  | 0400842 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0400843 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0400844 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0400845 | Knox | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0400846 | Spencer | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2007-12-12 | CE
CN
RR
|  |  |  | Warrick | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2007-12-12 | CE
CN
RR
|  |  | 0400847 | Greene |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  | 0400848 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400849 | Perry |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
RR
|  |  |  | Spencer |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
RR
|  |  | 0400850 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400851 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0400852 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400854 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400855 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400856 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
ROW
UT
|  |  | 0400857 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0400858 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-06-01
|  |  | 0400859 | Spencer |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400860 | Knox |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0400861 | Gibson | III FFC | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0400862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400863 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0400864 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400865 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-05-25
|  |  | 0400866 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0400867 | Spencer | CivCon Services, Inc. | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0400868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400869 | Perry |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0400870 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400871 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2009-02-27 | CE
CN
RR
|  |  | 0400872 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 0400873 | Jasper |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0400874 | Carroll | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Cass | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Miami | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400875 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2005-03-16
|  |  | 0400876 |  | ABt SRBI | Indiana Department of Transportation | 2005-03-16
|  |  | 0400877 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2005-06-22
|  |  | 0400878 |  |  | Indiana Department of Transportation | 2004-11-16
|  |  | 0400879 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2005-06-01
|  |  | 0400880 |  |  | Indiana Department of Transportation | 2003-08-01
|  |  | 0400881 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400882 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400883 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400884 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400885 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400886 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400887 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2005-02-16
|  |  | 0400888 |  | Duesler Realty House | Indiana Department of Transportation | 2005-02-16
|  |  | 0400889 | Lake | Edwards and Kelcey | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0400890 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0400891 |  | Eel River Abstract | Indiana Department of Transportation | -339679.2083
|  |  | 0400892 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400893 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400894 |  | Civil Designs, LLP | Indiana Department of Transportation | -339679.2083
|  |  | 0400895 |  | Coates Field Service, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400897 | Lake | Compliance Consulting Service, Inc. | Griffith | 2009-05-06 | CE
CN
|  |  | 0400898 | Lake |  | Griffith | -339679.2083 | RR
|  |  | 0400900 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0400901 |  | CGI | Indiana Department of Transportation | 2004-10-19
|  |  | 0400902 | Steuben |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0400903 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0400904 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400905 |  | CBRE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400906 |  | CBRE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400907 | Boone |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2004-11-16 | CE
CN
|  |  | 0400908 | Clark | Data Transfer Solutions, LLC | Jeffersonville | 2004-08-13 | PE
|  |  | 0400909 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400910 | Elkhart |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
UT
|  |  | 0400911 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400912 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400913 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0400914 |  | Empower Results, LLC | Indiana Department of Transportation | 2004-12-14
|  |  | 0400915 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400916 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400917 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0400918 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0400919 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0400920 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400921 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400922 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0400923 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0400924 | Allen |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0400925 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400926 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400927 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0400928 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400929 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400930 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400931 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0400932 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400933 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0400934 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0400935 | Clark |  | Clark County | 2025-07-09 | PE
|  |  | 0400936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400937 |  |  | Jeffersonville | -339679.2083
|  |  | 0400938 | Tippecanoe |  | Tippecanoe County | 2011-01-12 | CE
CN
|  |  | 0400939 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400940 | Dubois |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0400941 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400942 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400943 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400944 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400945 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0400946 | Hamilton | CTLGroup | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock | CTLGroup | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison | CTLGroup | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph | CTLGroup | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400947 | Hamilton | Hey and Associates, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock | Hey and Associates, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph | Hey and Associates, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400948 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15
|  |  | 0400949 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15
|  |  | 0400950 | Hamilton |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400951 | Hamilton |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400952 | Hamilton |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400953 | Jackson |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0400954 | Hamilton |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400955 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400956 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400957 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400958 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400959 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400960 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400961 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0400962 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 0400963 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400964 | Hamilton |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Hancock |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0400965 | Hamilton |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
|  |  | 0400966 | Hancock |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
PE
|  |  | 0400967 | Wayne |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0400968 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400969 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400971 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400972 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400973 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400974 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400975 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400976 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400977 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400978 | Various |  | Indiana Department of Transportation | 2007-01-24 | CE
CN
|  |  | 0400979 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0400980 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0400981 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0400982 | Johnson |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0400983 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  | 0400984 | LaPorte |  | Indiana Department of Transportation | 2014-07-09 | PE
|  |  | 0400985 | LaPorte |  | Indiana Department of Transportation | 2014-07-09 | PE
RR
|  |  | 0400986 | Gibson |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
UT
|  |  | 0400987 | Hendricks |  | Plainfield | 2011-08-10 | CE
CN
|  |  | 0400988 | Hendricks |  | Plainfield | 2011-08-10 | CE
CN
|  |  | 0400989 |  | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0400990 |  | M-E Companies, Inc. | Wabash | -339679.2083
|  |  | 0400991 | Tippecanoe |  | Indiana Department of Transportation | 2009-03-11 | ROW
RR
UT
|  |  | 0400992 | Tippecanoe |  | Indiana Department of Transportation | 2008-11-19 | CE
ROW
RR
|  |  | 0400993 |  | Holloway Engineering, LLC | Peru | -339679.2083
|  |  | 0400994 |  | Holloway Engineering, LLC | Peru | -339679.2083
|  |  | 0400995 | Tippecanoe |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0400996 | Montgomery |  | Indiana Department of Transportation | 2009-05-06 | ROW
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2009-05-06 | CE
ROW
RR
|  |  | 0400997 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0400998 | Tippecanoe |  | Indiana Department of Transportation | 2008-10-01 | CE
ROW
|  |  | 0400999 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0401000 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0401001 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0401002 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2008-09-04 | CE
RR
|  |  | 0401003 | Tippecanoe |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0401004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401005 |  | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083
|  |  | 0401006 |  | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083
|  |  | 0401007 | Benton |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0401008 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0401009 | Wabash |  | Wabash | 2004-08-17 | CE
CN
|  |  | 0401010 | Miami |  | Peru | 2005-01-19 | CE
CN
|  |  | 0401012 | Miami |  | Peru | 2005-01-19 | CE
CN
|  |  | 0401013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401014 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0401015 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0401016 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0401017 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0401018 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0401019 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0401020 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0401021 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
RR
|  |  | 0401022 | LaPorte |  | La Porte | 2004-11-05 | CE
CN
|  |  | 0401023 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401024 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401025 | Warrick |  | Newburgh | 2008-11-19 | CE
CN
PE
|  |  | 0401026 | Johnson |  | Johnson County | 2007-07-11 | CE
CN
|  |  | 0401027 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401029 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401031 | Pike |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 0401032 | Miami | Holloway Engineering, LLC | Peru | 2010-10-06 | CE
CN
PE
ROW
|  |  | 0401033 | Hendricks |  | Avon | 2012-03-07 | CN
PE
|  |  | 0401034 |  | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401035 |  | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401038 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2015-10-07 | CE
CN
|  |  | 0401039 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401041 | Hamilton | H. Stewart Kline & Associates, Inc. | Hamilton County | 2008-02-06 | CE
CN
PE
|  |  | 0401042 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401043 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0401044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401047 |  | DCD Consulting LLC | Indiana Department of Transportation | 2004-12-14
|  |  | 0401048 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0401049 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 0401050 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 0401051 | Carroll |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
RR
UT
|  |  |  | Cass |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
RR
|  |  | 0401052 | Cass |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0401053 | Cass |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0401054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401055 |  |  | Elkhart County | -339679.2083
|  |  | 0401056 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0401057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401058 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401059 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401062 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2004-11-17 | PE
ROW
|  |  | 0401063 | Brown | Garcia LE & Associates, L.L.C. | Brown County | 2012-11-15 | CE
CN
ROW
|  |  | 0401064 | Dubois | Danch Harner and Associates, Inc. | Jasper | -339679.2083 | CE
CN
|  |  | 0401065 | Dubois | Danch Harner and Associates, Inc. | Jasper | 2008-07-09 | CE
CN
|  |  | 0401066 | Elkhart | Farren Real Estate Services | Elkhart County | 2010-07-07 | CE
CN
PE
|  |  | 0401067 | Wayne | Indiana Appraisal Group, Inc. | Wayne County | 2009-05-06 | CE
CN
|  |  | 0401068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401069 | Harrison | B. L. A., Inc. | Harrison County | 2010-09-01 | CE
CN
|  |  | 0401070 | Steuben | ABt SRBI | Steuben County | 2014-05-08 | CE
CN
PE
|  |  | 0401071 | White | Fugro Roadware, Inc. | White County | 2006-02-22 | CE
CN
PE
ROW
|  |  | 0401072 | Wabash | M-E Companies, Inc. | Wabash | 2009-04-08 | CE
CN
|  |  | 0401073 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2007-09-19 | CE
CN
|  |  | 0401074 | Posey | GRL Engineers, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
UT
|  |  | 0401075 | Greene | Metropolitan Title of Indiana, LLC | Worthington | 2008-03-05 | CE
CN
|  |  | 0401076 | Delaware | GS-IN P.C. | Muncie | 2013-07-10 | CE
CN
PE
|  |  | 0401077 |  |  | South Bend | -339679.2083
|  |  | 0401078 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2007-08-22 | CE
CN
|  |  | 0401079 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401080 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401081 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401082 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
|  |  | 0401083 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401084 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401085 |  | Hardlines Design Company | Indiana Department of Transportation | -339679.2083
|  |  | 0401086 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401087 |  | Mader Design, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401088 |  | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401090 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0401091 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401092 |  | Land Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401093 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401094 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 0401095 | Parke |  | Parke County | 2006-09-13 | CE
CN
|  |  | 0401096 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0401097 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0401098 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401099 | Whitley |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 0401100 | Jay |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0401101 | Miami |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 0401102 | Kosciusko |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0401103 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0401104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401105 | Jay | Alliance Survey Company | Indiana Department of Transportation | 2010-02-24 | CE
CN
PE
|  |  | 0401106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401107 |  | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083
|  |  | 0401108 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2005-05-25
|  |  | 0401109 |  |  | Indiana Department of Transportation | 2004-12-14
|  |  | 0401110 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0401111 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 0401112 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 0401113 | Dubois |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  |  | Elkhart |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0401114 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0401115 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0401116 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0401117 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0401118 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0401119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401120 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0401121 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0401122 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0401123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401124 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0401125 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0401126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401129 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401132 |  | Clyde L. Hawkins | Indiana Department of Transportation | -339679.2083
|  |  | 0401133 | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0401134 | Floyd |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0401135 | Floyd |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0401136 |  | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401138 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2008-03-26 | CE
CN
|  |  | 0401139 | Jackson |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0401140 | Vermillion |  | Indiana Department of Transportation | 2008-03-26 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2008-03-26 | CE
CN
|  |  |  | Warren |  | Indiana Department of Transportation | 2008-03-26 | CE
CN
|  |  | 0401141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401142 | Miami |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0401143 |  | Iteris, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401144 | Vermillion |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0401145 | Jackson |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
|  |  | 0401146 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401148 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401149 | Starke |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0401150 | Starke |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0401151 | White |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0401152 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401153 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401154 |  | Chicago Title Insurance Company | Indiana Department of Transportation | -339679.2083
|  |  | 0401155 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401156 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401158 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401159 | LaGrange |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0401160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401161 | Johnson |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0401162 | Johnson |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0401163 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401164 | Monroe |  | Indiana Department of Transportation | 2008-05-08 | CE
PE
|  |  | 0401165 | Morgan |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
|  |  | 0401166 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401167 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401168 |  | Heartland Recycling LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0401169 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0401170 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2005-06-01
|  |  | 0401171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401172 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401173 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401174 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401176 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0401177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401178 |  | InfoTech | Indiana Department of Transportation | -339679.2083
|  |  | 0401179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401181 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0401182 |  | Bidinfo | Indiana Department of Transportation | -339679.2083
|  |  | 0401183 |  | Debbie L. Morris | Indiana Department of Transportation | -339679.2083
|  |  | 0401184 |  | Debbie L. Morris | Indiana Department of Transportation | -339679.2083
|  |  | 0401185 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401187 | Noble | AES Services, Inc. | Indiana Department of Transportation | 2013-07-10 | PE
|  |  | 0401188 | Marion | DCD Consulting LLC | Indianapolis | 2012-05-02 | CE
CN
|  |  | 0401189 | Marion | DCD Consulting LLC | Indianapolis | 2012-03-15 | CE
CN
|  |  | 0401190 |  |  | Aurora | -339679.2083
|  |  | 0401191 | Vigo | Bayswater Company, LLC | Terre Haute | 2008-11-19 | CE
CN
|  |  | 0401192 | Carroll |  | Carroll County | -339679.2083 | PE
|  |  | 0401193 | Vanderburgh | CGI | Evansville | 2008-11-19 | CE
CN
|  |  | 0401194 | Dearborn |  | Dearborn County | 2011-03-09 | CE
CN
|  |  | 0401195 |  |  | Indiana Department of Natural Resources | 2008-12-15
|  |  | 0401196 | Bartholomew | Associated Right-of-Way Services, Inc. | Bartholomew County | 2017-02-08 | CE
CN
PE
|  |  | 0401197 |  |  | Indiana Department of Transportation | 2005-03-16
|  |  | 0401198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401199 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401200 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401201 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401205 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401206 | Wells |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
ROW
|  |  | 0401207 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401208 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401209 | Wabash |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
ROW
|  |  | 0401210 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401211 | Blackford |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0401212 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401213 | Miami |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0401214 | Noble |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
UT
|  |  | 0401215 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401216 | Allen |  | Indiana Department of Transportation | 2009-07-29 | CN
|  |  |  | Dekalb |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0401217 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401218 | Whitley |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0401219 | Whitley | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0401220 | Whitley | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0401221 | Whitley | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0401222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401223 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401225 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0401226 | Delaware |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0401227 | Marion | DCD Consulting LLC | Indianapolis | 2008-05-08 | CN
PE
RR
|  |  | 0401228 | Marion | DCD Consulting LLC | Indianapolis | 2007-10-17 | CE
CN
PE
ROW
RR
UT
|  |  | 0401229 | Randolph |  | Randolph County | -339679.2083 | CN
|  |  | 0401230 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0401231 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0401232 | Putnam |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0401233 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0401234 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083 | CN
PE
|  |  | 0401235 | Henry | Dillabaugh, Inc. | Henry County | 2007-06-25 | CN
|  |  | 0401236 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0401237 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 0401238 | LaPorte |  | Indiana Department of Transportation | 2007-08-22 | CN
|  |  |  | Posey |  | Indiana Department of Transportation | 2007-08-22 | CE
CN
|  |  | 0401239 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0401240 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2005-01-19
|  |  | 0401241 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0401242 |  |  | Indiana Department of Transportation | 2005-01-19
|  |  | 0401243 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0401245 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0401246 |  |  | Indiana Department of Natural Resources | 2005-07-20
|  |  | 0401247 | LaPorte |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2005-01-19 | CE
CN
|  |  | 0401248 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401249 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0401250 | St. Joseph |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0401251 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
ROW
RR
|  |  | 0401252 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-05-25
|  |  | 0401253 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-05-25
|  |  | 0401254 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0401255 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0401256 | Hendricks | Horner and Shifrin, Inc. | Plainfield | -339679.2083 | PE
|  |  | 0401257 |  |  | Indiana Department of Transportation | 2005-02-16
|  |  | 0401258 | Dubois |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0401259 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0401260 | Various |  | Indiana Department of Transportation | 2005-04-20 | CE
CN
|  |  | 0401261 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0401262 |  | CGI | Indiana Department of Transportation | 2005-02-16
|  |  | 0401263 | Jasper | Independent Appraisers-Consultants, Inc. | Indiana Department of Transportation | 2005-02-16 | CE
CN
|  |  | 0401264 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0401265 | Cass |  | Logansport | 2004-10-19 | CE
CN
|  |  | 0401266 | Marion | DCD Consulting LLC | Indianapolis | 2008-02-06 | CE
CN
|  |  | 0401267 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401268 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401269 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401270 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401271 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401272 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401273 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401274 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401275 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401276 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401277 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401278 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401279 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2005-11-16 | CE
CN
RR
|  |  | 0401280 | Marion |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0401281 | Marion |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0401282 | Knox |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
RR
|  |  | 0401283 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0401284 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0401285 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0401286 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0401287 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2009-03-25 | CN
|  |  | 0401288 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0401289 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0401290 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0401291 | Madison |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0401292 | Wayne |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0401293 | Wayne |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0401294 | LaPorte |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0401295 | Warrick |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0401296 | Carroll |  | Indiana Department of Transportation | 2011-02-11 | CE
CN
|  |  | 0401297 | Carroll |  | Indiana Department of Transportation | 2011-02-11 | CE
CN
|  |  | 0401298 | Carroll |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
RR
|  |  | 0401299 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
RR
|  |  | 0401300 | Cass |  | Indiana Department of Transportation | 2009-11-04 | RR
|  |  | 0401301 | Cass |  | Indiana Department of Transportation | 2009-11-04 | RR
|  |  | 0401302 | Cass |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
RR
|  |  | 0401303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401304 |  |  | Dubois County | -339679.2083
|  |  | 0401305 | Martin |  | Martin County | -339679.2083 | CN
|  |  | 0401306 | Greene |  | Greene County | -339679.2083 | CN
|  |  | 0401307 | St. Joseph |  | St. Joseph County | -339679.2083 | CN
|  |  | 0401308 | Monroe | Absolute Title Services, LLC | Bloomington | 2008-05-08 | CE
CN
|  |  | 0401309 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 0401310 | Clark |  | Clark County | -339679.2083 | CN
|  |  | 0401311 | Hendricks |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0401312 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-03-16
|  |  | 0401313 | Hamilton |  | Hamilton County | 2006-07-19 | CE
CN
PE
|  |  | 0401314 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0401315 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0401316 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-07-19
|  |  | 0401317 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-09-14
|  |  | 0401318 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401319 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0401320 | Hamilton |  | Hamilton County | 2006-07-19 | CE
CN
PE
|  |  | 0401321 |  |  | Hamilton County | -339679.2083
|  |  | 0401322 |  |  | Hamilton County | -339679.2083
|  |  | 0401323 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0401324 | Clark |  | Clark County | 2009-08-12 | CE
CN
ROW
UT
|  |  | 0401325 | Posey |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 0401326 | Spencer |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 0401327 | Hendricks |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
ROW
|  |  | 0401328 | Hendricks |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
ROW
|  |  | 0401329 | Hendricks |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
ROW
|  |  | 0401330 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 0401331 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401332 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0401333 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 0401334 |  | Archonsortium, LLC | Indiana Department of Transportation | 2005-06-22
|  |  | 0401335 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0401336 | Hamilton |  | Noblesville | 2006-07-19 | CE
CN
|  |  | 0401337 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0401338 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2006-05-24
|  |  | 0401339 | Union |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0401340 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401341 | Bartholomew |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
PE
ROW
UT
|  |  | 0401342 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2005-06-22
|  |  | 0401343 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2005-06-22
|  |  | 0401344 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-02-16
|  |  | 0401345 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401346 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401347 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401348 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401349 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401350 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401351 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401352 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401353 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401354 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401355 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401356 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401357 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401358 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401359 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401360 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401361 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401362 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401363 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401364 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0401365 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0401366 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0401367 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0401368 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0401369 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0401370 | Marion |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401371 | Marion |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0401372 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0401373 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0401374 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0401375 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0401376 | Marshall |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0401377 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401378 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401381 | Orange |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 0401382 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0401383 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 0401384 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 0401385 | Knox | Louis Joyner, Architect | Vincennes | 2006-03-29 | CE
CN
PE
RR
|  |  | 0401386 | St. Joseph |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
ROW
UT
|  |  | 0401387 | Hamilton | Another Test Company | Carmel | 2005-12-14 | CE
CN
|  |  | 0401388 | Hamilton | CPS Acquisitions, LLC | Fishers | 2009-05-27 | CE
CN
|  |  | 0401389 |  |  | Indiana Department of Transportation | 2005-03-16
|  |  | 0401390 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0401391 | Clay |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0401392 | Tippecanoe |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0401393 | Putnam |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0401394 | Harrison |  | Indiana Department of Transportation | 2021-04-01 | PE
|  |  | 0401395 | Warren |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0401396 | Boone |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0401397 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0401398 | Parke |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0401399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401401 | Jackson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Jennings |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0401402 | Jennings |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
UT
|  |  | 0401403 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0401404 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0401405 |  | CE Solutions, Inc. | Elwood | -339679.2083
|  |  | 0401406 | Elkhart | Gandhi and Associates, Inc. | Nappanee | 2010-07-07 | CE
CN
|  |  | 0401407 | Henry | GeoSolutions, Inc. | New Castle | 2011-02-09 | CE
CN
PE
RR
|  |  | 0500001 | Morgan |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500002 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2005-04-20
|  |  | 0500003 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500004 | Boone |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
RR
|  |  | 0500005 | Clinton |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0500006 | Fountain |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0500007 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0500008 | Vermillion |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0500009 |  |  | Monroe County | 2011-03-09
|  |  | 0500010 | Dearborn |  | Lawrenceburg | 2007-09-19 | CE
CN
PE
|  |  | 0500011 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500012 | Noble |  | Indiana Department of Transportation | 2006-06-01 | CE
CN
PE
ROW
UT
|  |  | 0500013 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0500014 | Shelby |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
|  |  | 0500015 |  |  | Posey County | -339679.2083
|  |  | 0500016 | Miami | Holloway Engineering, LLC | Miami County | 2010-07-07 | CE
CN
PE
|  |  | 0500017 | Dekalb |  | Dekalb County | 2009-05-06 | CE
CN
PE
ROW
|  |  | 0500018 | Hamilton |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
|  |  | 0500019 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500022 | LaPorte |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 0500023 | LaPorte |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 0500024 | Marshall |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 0500025 | Marshall |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 0500026 | Porter |  | Indiana Department of Transportation | 2015-08-19 | CE
CN
|  |  | 0500027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500028 | Lake |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 0500029 | Porter |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0500030 | St. Joseph |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
PE
|  |  | 0500031 |  |  | Hamilton County | -339679.2083
|  |  | 0500032 |  |  | Indiana Department of Transportation | 2005-04-06
|  |  | 0500033 |  |  | Indiana Department of Transportation | 2005-04-06
|  |  | 0500034 |  | CTLGroup | Indiana Department of Transportation | -339679.2083
|  |  | 0500035 |  |  | Indiana Department of Transportation | 2005-03-16
|  |  | 0500036 | Cass | Eco Logic, LLC | Logansport | 2008-01-09 | CE
CN
|  |  | 0500037 | Cass | Eco Logic, LLC | Logansport | 2008-01-09 | CE
CN
|  |  | 0500038 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0500039 | Hancock | CTLGroup | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
|  |  | 0500040 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500041 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500042 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2021-01-01 | PE
|  |  | 0500043 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500044 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2005-04-06
|  |  | 0500045 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0500046 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0500047 |  |  | Indiana Department of Transportation | 2005-04-20
|  |  | 0500048 |  |  | Spencer County | -339679.2083
|  |  | 0500049 | Noble |  | Albion | 2008-03-19 | CE
CN
ROW
|  |  | 0500050 |  |  | Porter County | -339679.2083
|  |  | 0500051 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2005-05-25
|  |  | 0500052 | Decatur |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  |  | Franklin |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500053 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500054 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500055 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500056 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500058 | White |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0500059 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500060 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2005-06-22
|  |  | 0500061 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 0500062 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0500063 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 0500064 | LaPorte | Farah and Sons, Inc. | Michigan City | 2009-06-10 | CE
CN
PE
|  |  | 0500065 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2009-10-07 | CE
CN
PE
ROW
RR
|  |  | 0500066 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2005-06-22
|  |  | 0500067 | Boone |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
UT
|  |  | 0500068 | Starke |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
RR
|  |  | 0500069 | Allen |  | Allen County | 2011-11-16 | CE
CN
PE
|  |  | 0500070 | Allen |  | Allen County | 2010-07-07 | CE
CN
PE
|  |  | 0500071 | Blackford |  | Blackford County | 2009-10-07 | CE
CN
|  |  | 0500072 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500073 | Floyd | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  | 0500074 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500075 |  | Bayswater Company, LLC | Vigo County | -339679.2083
|  |  | 0500076 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0500077 | Elkhart |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
|  |  | 0500078 | Delaware |  | Delaware County | 2015-07-08 | CE
CN
|  |  | 0500079 |  | Bayswater Company, LLC | Vigo County | -339679.2083
|  |  | 0500080 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0500081 |  | Bayswater Company, LLC | Vigo County | -339679.2083
|  |  | 0500082 | Fulton |  | Fulton County | 2011-04-13 | CE
CN
|  |  | 0500083 | Gibson |  | Gibson County | 2011-10-13 | CE
CN
UT
|  |  | 0500084 | Hamilton |  | Hamilton County | 2009-02-11 | CE
CN
|  |  | 0500085 | Hamilton |  | Hamilton County | 2009-02-11 | CE
CN
|  |  | 0500086 | Henry |  | Henry County | 2009-08-12 | CE
CN
|  |  | 0500087 | Jefferson |  | Jefferson County | 2011-07-13 | CE
CN
|  |  | 0500088 |  |  | Johnson County | -339679.2083
|  |  | 0500089 | Marshall | Howard J. Barth & Associates, Inc. | Marshall County | 2007-10-03 | CE
CN
|  |  | 0500090 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0500091 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0500092 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2010-01-13 | CE
CN
PE
RR
|  |  | 0500093 | Porter |  | Porter County | 2008-02-06 | CE
CN
RR
|  |  | 0500094 |  |  | Porter County | -339679.2083
|  |  | 0500095 |  |  | Randolph County | -339679.2083
|  |  | 0500096 | Rush |  | Rush County | 2010-09-01 | CE
CN
|  |  | 0500097 |  |  | Scott County | -339679.2083
|  |  | 0500098 |  |  | Starke County | -339679.2083
|  |  | 0500099 | Wabash |  | Wabash County | 2007-07-11 | CE
CN
|  |  | 0500100 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2021-01-01 | PE
|  |  | 0500101 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500102 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500103 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500104 | Various |  | Indiana Department of Transportation | 2005-05-25 | CE
CN
|  |  | 0500105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500106 |  |  | Indiana Department of Transportation | 2005-11-16
|  |  | 0500107 | Tippecanoe |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
|  |  | 0500108 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500109 | Decatur |  | Decatur County | -339679.2083 | CN
|  |  |  | Various |  | Decatur County | -339679.2083 | PE
|  |  | 0500110 | Delaware | GS-IN P.C. | Muncie | 2006-03-15 | CE
CN
|  |  | 0500111 | Various | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500112 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500114 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500115 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500116 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2007-04-04
|  |  | 0500117 |  |  | Decatur County | -339679.2083
|  |  | 0500118 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500119 | St. Joseph |  | Indiana Department of Transportation | 2009-04-08 | PE
ROW
RR
UT
|  |  | 0500120 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500122 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500123 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500129 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | -339679.2083
|  |  | 0500130 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | -339679.2083
|  |  | 0500131 | Lake | Huff & Huff, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
|  |  |  | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
UT
|  |  | 0500132 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500133 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500134 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0500135 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0500136 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500137 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500138 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500139 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500140 |  | CGI | Indiana Department of Transportation | 2005-07-20
|  |  | 0500141 | Floyd |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500142 | Floyd |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
ROW
|  |  | 0500143 | Vanderburgh |  | Vanderburgh County | 2009-11-04 | CE
CN
ROW
UT
|  |  | 0500144 | Vanderburgh |  | Vanderburgh County | 2010-12-08 | CE
CN
ROW
UT
|  |  | 0500145 | Vanderburgh |  | Vanderburgh County | 2010-12-08 | CE
CN
|  |  | 0500146 | Dearborn |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0500147 | Jefferson |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0500148 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Floyd |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500149 | Spencer |  | Indiana Department of Transportation | -339679.2083 | CN
PE
|  |  | 0500150 |  | CTLGroup | Indiana Department of Transportation | 2005-05-25
|  |  | 0500151 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0500152 | Vanderburgh | CGI | Indiana Department of Transportation | 2007-09-06 | CE
CN
RR
|  |  | 0500153 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500154 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500156 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2005-10-19
|  |  | 0500157 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2005-10-19
|  |  | 0500158 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0500159 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0500160 | Madison |  | Madison County | 2005-09-14 | CE
CN
UT
|  |  | 0500161 | Hamilton |  | Hamilton County | 2016-10-05 | CN
|  |  | 0500162 | Knox | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
ROW
UT
|  |  | 0500163 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500164 |  |  | Indiana Department of Transportation | 2005-05-25
|  |  | 0500165 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500167 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500168 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 0500169 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500170 |  | Bruce S. Grimes | Indiana Department of Transportation | -339679.2083
|  |  | 0500171 | Hamilton |  | Hamilton County | 2005-10-19 | CE
CN
|  |  | 0500172 | Various |  | Indiana Department of Transportation | 2005-06-22 | CE
CN
|  |  | 0500173 | Clark |  | Clark County | 2025-07-09 | PE
|  |  | 0500174 | Floyd |  | New Albany | 2006-06-21 | CE
CN
PE
ROW
UT
|  |  | 0500175 | Clark |  | Clark County | 2012-05-02 | CE
CN
PE
ROW
UT
[6 empty] | Clark County | 2012-05-02
|  |  | 0500176 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 0500177 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500178 | Marion |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
|  |  | 0500179 | Porter |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0500180 | St. Joseph |  | St. Joseph County | 2009-04-08 | CE
CN
|  |  | 0500181 | Elkhart | Civil Inspection Services, LLC | Goshen | 2007-02-07 | CE
CN
|  |  | 0500182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500183 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 0500184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500185 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500186 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0500187 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0500188 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0500189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500190 |  |  | Indiana Department of Natural Resources | 2005-07-20
|  |  | 0500191 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0500192 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500193 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500194 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
ROW
RR
UT
|  |  | 0500195 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500196 | Porter |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500197 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500198 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500199 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500200 | Vermillion |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500201 | Starke |  | Indiana Department of Transportation | -339679.2083 | CN
RR
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 0500202 | Vermillion |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500203 | Vermillion | Apex Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500204 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500205 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500206 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500207 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500208 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500209 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500210 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500211 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500212 | Lawrence | ICA Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500213 | Lawrence | ICA Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500214 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500215 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500216 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500217 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500218 | Porter | ATSI Engineering Services | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500219 | Montgomery | ETC Institute | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500220 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500221 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500222 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500223 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500224 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500225 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500226 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500227 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500228 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500229 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500230 | Vermillion | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500231 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500232 | Clark |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500233 | Clark |  | Indiana Department of Transportation | 2005-05-20 | RR
|  |  | 0500234 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500235 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 0500236 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500237 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500238 | Whitley |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500239 | Whitley |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500240 | Marshall | ACMS Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500241 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500242 | Starke |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500243 | LaPorte | Dennison and Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500244 | LaPorte | Dennison and Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500245 | LaPorte | Dennison and Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500246 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500247 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500248 | Lake | Applied Pavement Technology, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500249 | Gibson |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500250 | Gibson | HNTB Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500251 | Gibson | HNTB Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500252 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500253 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500254 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0500256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500257 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 0500258 | LaPorte |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500259 | LaPorte |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
RR
|  |  | 0500260 | LaPorte |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0500261 | Grant |  | Indiana Department of Transportation | 2007-05-31 | CE
CN
|  |  | 0500262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500264 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500265 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500266 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500269 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500270 | LaPorte |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500271 | LaPorte |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  |  | Starke |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500272 | Jasper |  | Indiana Department of Transportation | 2008-07-16 | CE
CN
|  |  | 0500273 | Cass |  | Indiana Department of Transportation | 2006-12-13 | CE
CN
|  |  | 0500274 | Pulaski |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0500275 | Marshall |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0500276 | Pulaski |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0500277 | White |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
RR
|  |  | 0500278 | Carroll |  | Indiana Department of Transportation | 2008-04-09 | CE
CN
|  |  | 0500279 | Cass |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0500280 | Fulton |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0500281 | Pulaski |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0500282 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500283 | Starke |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0500284 | Lake |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
RR
|  |  |  | Newton |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0500285 | Marshall |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0500286 | White |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 0500287 | LaPorte |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
RR
|  |  | 0500288 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500289 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500291 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500292 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500294 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500295 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500296 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500297 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500298 |  | Iteris, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500299 |  | Archonsortium, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500302 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500304 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
ROW
UT
|  |  | 0500305 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500307 | Floyd |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
|  |  | 0500308 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500309 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500312 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500313 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500315 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500317 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500318 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500319 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500320 |  | Farren Real Estate Services | Indiana Department of Transportation | -339679.2083
|  |  | 0500321 |  | Farren Real Estate Services | Indiana Department of Transportation | -339679.2083
|  |  | 0500322 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500323 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500324 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500326 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500327 |  | Farren Real Estate Services | Indiana Department of Transportation | -339679.2083
|  |  | 0500328 | Elkhart |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
ROW
UT
|  |  | 0500329 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500331 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500332 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500333 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500334 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500335 |  |  | Cass County | -339679.2083
|  |  | 0500336 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500337 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500338 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500339 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500340 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500341 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500342 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500343 |  | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500344 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500345 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500346 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500347 |  | Debbie L. Morris | Indiana Department of Transportation | -339679.2083
|  |  | 0500348 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500349 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500350 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0500351 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0500352 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500353 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500354 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500355 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0500356 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0500357 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500358 | Rush |  | Rush County | -339679.2083 | CN
|  |  | 0500359 |  | DCD Consulting LLC | MPO - Indianapolis | 2009-05-31
|  |  | 0500360 |  | B. L. A., Inc. | Indiana Department of Transportation | 2006-04-19
|  |  | 0500361 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500362 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500363 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500364 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500365 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500366 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500367 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500368 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500369 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0500370 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0500371 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500373 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500374 |  | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500375 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2005-10-19
|  |  | 0500376 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500377 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2005-10-19
|  |  | 0500378 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500380 |  | Edwards and Kelcey | Indiana Department of Transportation | -339679.2083
|  |  | 0500381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500382 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2005-10-19
|  |  | 0500383 |  | Dummy Consulting Firm | Indiana Department of Transportation | -339679.2083
|  |  | 0500384 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500385 |  | InfoTech | Indiana Department of Transportation | 2005-09-14
|  |  | 0500386 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500387 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500388 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500389 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500390 |  |  | Indiana Department of Transportation | 2007-10-31
|  |  | 0500391 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500392 |  |  | Indiana Department of Transportation | 2007-10-31
|  |  | 0500393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500396 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500397 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500401 | Jennings |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0500402 | Scott |  | Scott County | -339679.2083 | CN
|  |  | 0500403 |  | Eel River Abstract | Indiana Department of Transportation | -339679.2083
|  |  | 0500404 | Randolph |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0500405 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  |  | Randolph | Hydrogeology, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0500406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500407 | Hamilton |  | Indiana Department of Transportation | 2020-03-15 | PE
|  |  | 0500408 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500409 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500411 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500412 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500413 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500414 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500415 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500416 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500417 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500418 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500419 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500420 |  | Home Guide Realty Services | Indiana Department of Transportation | 2005-10-19
|  |  | 0500421 |  | Home Guide Realty Services | Indiana Department of Transportation | 2005-10-19
|  |  | 0500422 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500424 |  | Fink Roberts & Petrie | Indiana Department of Transportation | 2005-10-19
|  |  | 0500425 |  | Fink Roberts & Petrie | Indiana Department of Transportation | 2005-10-19
|  |  | 0500426 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500427 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500429 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500430 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
UT
|  |  | 0500431 | Monroe |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
PE
UT
|  |  |  | Morgan |  | Indiana Department of Transportation | 2020-01-29 | PE
UT
|  |  | 0500432 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
PE
|  |  | 0500433 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500434 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500435 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500436 | Gibson |  | Indiana Department of Transportation | 2008-04-02 | CN
PE
ROW
UT
|  |  | 0500437 | Gibson |  | Indiana Department of Transportation | 2009-04-08 | PE
ROW
|  |  |  | Marion |  | Indiana Department of Transportation | 2009-04-08 | CN
PE
PL
UT
|  |  | 0500438 | Gibson |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
UT
|  |  | 0500439 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | 2005-10-19
|  |  | 0500440 | Gibson |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
ROW
RR
UT
|  |  | 0500441 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
RR
UT
|  |  | 0500442 | Daviess |  | Indiana Department of Transportation | 2011-01-12 | CN
UT
|  |  |  | Pike |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
UT
|  |  | 0500443 | Daviess |  | Indiana Department of Transportation | 2010-04-29 | CE
CN
ROW
UT
|  |  | 0500444 | Daviess |  | Indiana Department of Transportation | 2010-06-09 | UT
|  |  | 0500445 | Daviess |  | Indiana Department of Transportation | 2010-08-27 | ROW
UT
|  |  |  | Greene |  | Indiana Department of Transportation | 2010-08-27 | UT
|  |  | 0500446 | Greene |  | Indiana Department of Transportation | 2011-10-26 | CE
CN
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2011-10-26 | CN
|  |  | 0500447 | Greene |  | Indiana Department of Transportation | 2013-03-20 | CE
CN
ROW
UT
|  |  | 0500448 | Greene |  | Indiana Department of Transportation | 2011-12-21 | CE
CN
UT
|  |  | 0500449 | Greene |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
ROW
UT
|  |  | 0500450 | Monroe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
PE
ROW
UT
|  |  | 0500451 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | 2005-10-19
|  |  | 0500452 |  |  | Indiana Department of Transportation | 2034-04-15
|  |  | 0500453 |  |  | Indiana Department of Transportation | 2035-04-15
|  |  | 0500454 |  |  | Indiana Department of Transportation | 2036-04-14
|  |  | 0500455 |  |  | New Albany | -339679.2083
|  |  | 0500456 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500457 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 0500458 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500459 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 0500460 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500461 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500462 | Lake |  | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
|  |  | 0500463 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500464 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500465 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500467 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500468 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2009-05-27 | CE
CN
PE
ROW
UT
|  |  | 0500469 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500470 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500471 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0500472 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0500473 |  | Beacon Surveying and Engineering | Indiana Department of Transportation | -339679.2083
|  |  | 0500474 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0500475 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500476 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500477 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500478 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500479 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500480 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
RR
UT
|  |  | 0500481 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0500482 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500483 |  | Beacon Surveying and Engineering | Indiana Department of Transportation | -339679.2083
|  |  | 0500484 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500485 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500486 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500487 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500488 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500489 |  | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083
|  |  | 0500490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500493 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 0500494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500495 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500497 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500498 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500499 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500500 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 0500501 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500503 |  | American Commercial Title & Escrow | Indiana Department of Transportation | -339679.2083
|  |  | 0500504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500507 |  |  | Adams County | -339679.2083
|  |  | 0500508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500511 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0500512 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2005-10-19
|  |  | 0500513 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500514 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2005-10-19
|  |  | 0500515 |  | Merle Edward Orem | Indiana Department of Transportation | 2005-12-14
|  |  | 0500516 |  | Merle Edward Orem | Indiana Department of Transportation | 2005-12-14
|  |  | 0500517 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500518 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500519 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500520 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0500521 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500522 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500523 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500524 | Noble |  | Indiana Department of Transportation | 2006-06-01 | CE
CN
PE
ROW
UT
|  |  | 0500525 | White |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
ROW
UT
|  |  | 0500526 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0500527 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500528 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2005-08-17
|  |  | 0500529 |  | Duesler Realty House | Indiana Department of Transportation | -339679.2083
|  |  | 0500530 | Decatur | Collier Transport Inc. | Greensburg | 2009-08-12 | CE
CN
UT
|  |  | 0500531 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500532 | Dearborn |  | Dearborn County | 2012-05-02 | CE
CN
ROW
UT
|  |  | 0500533 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500534 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500535 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 0500536 |  |  | Elkhart County | -339679.2083
|  |  | 0500537 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0500538 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2010-04-01 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2010-04-01 | CE
CN
|  |  | 0500539 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0500540 | Boone |  | Indiana Department of Transportation | 2005-09-14 | CE
CN
|  |  | 0500541 | Hendricks |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0500542 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2006-03-15
|  |  | 0500543 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2006-03-15
|  |  | 0500544 |  |  | Indiana Department of Transportation | 2005-06-22
|  |  | 0500545 | Clark |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500546 | Various |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500547 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500548 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0500549 |  |  | Indiana Department of Transportation | 2005-11-16
|  |  | 0500550 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500551 | Jackson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0500552 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500561 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500562 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500563 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500564 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500566 | Benton |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0500567 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500568 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500569 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500571 | Floyd |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0500572 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0500573 | Bartholomew | Burrell Appraisal Service, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  |  | Johnson | Burrell Appraisal Service, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0500574 | Ripley |  | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0500575 | Floyd |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500576 | Harrison | B. L. A., Inc. | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500577 | Jackson |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500578 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500579 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0500580 |  |  | Indiana Department of Transportation | 2005-06-01
|  |  | 0500581 | Vigo |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
RR
UT
|  |  | 0500582 | Vigo |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
RR
UT
|  |  | 0500583 |  | ERES International, Inc. | Indiana Department of Transportation | 2005-06-01
|  |  | 0500584 |  | DCD Consulting LLC | Indiana Department of Transportation | 2005-09-14
|  |  | 0500585 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2005-06-01
|  |  | 0500586 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0500587 |  | CGI | Vanderburgh County | 2005-09-14
|  |  | 0500588 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0500589 | Bartholomew |  | Bartholomew County | 2008-07-09 | CE
CN
UT
|  |  | 0500590 | Lake |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
UT
|  |  | 0500591 | Lake |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
UT
|  |  | 0500592 | Lake |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
UT
|  |  | 0500593 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0500594 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0500595 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0500596 | Lake |  | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0500597 | Montgomery |  | Indiana Department of Transportation | 2009-05-20 | CN
ROW
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
ROW
RR
|  |  | 0500598 | Tippecanoe |  | Indiana Department of Transportation | 2008-09-04 | CE
ROW
UT
|  |  | 0500599 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
RR
UT
|  |  | 0500600 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
RR
UT
|  |  | 0500601 | Warrick |  | Warrick County | -339679.2083 | CN
|  |  | 0500602 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500603 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500604 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0500605 |  |  | Hendricks County | -339679.2083
|  |  | 0500606 |  |  | Decatur County | -339679.2083
|  |  | 0500607 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500608 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0500609 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500610 | Greene |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  |  | Owen |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0500611 | Clark | Data Transfer Solutions, LLC | Jeffersonville | 2007-10-11 | PE
|  |  | 0500612 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2005-08-17
|  |  | 0500613 |  | Chicago Testing Laboratory, Inc. | Lake County | -339679.2083
|  |  | 0500614 |  | DCD Consulting LLC | Indiana State Agencies | -339679.2083
|  |  | 0500615 |  |  | Indiana Department of Transportation | 2005-07-20
|  |  | 0500616 | Jackson |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  | 0500617 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500618 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500619 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500620 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
ROW
RR
UT
|  |  | 0500621 | Carroll |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
ROW
|  |  |  | Cass |  | Indiana Department of Transportation | 2010-05-19 | CE
ROW
RR
|  |  | 0500622 |  |  | Indiana Department of Transportation | 2006-09-13
|  |  | 0500623 | Boone |  | Boone County | -339679.2083 | CN
|  |  | 0500624 | Miami |  | Miami County | -339679.2083 | CN
|  |  | 0500625 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500626 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500627 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500628 | Cass |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
ROW
|  |  | 0500629 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0500630 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500631 | LaGrange | InspectTech Systems, Inc. | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  |  | Noble | InspectTech Systems, Inc. | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0500632 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0500633 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500634 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0500635 | Clark |  | Clark County | -339679.2083 | PE
|  |  |  | Floyd |  | Clark County | -339679.2083 | PE
|  |  | 0500636 | Warrick |  | Warrick County | 2016-11-16 | CE
CN
ROW
UT
|  |  | 0500637 | Warrick |  | Warrick County | 2012-05-02 | CE
CN
UT
|  |  | 0500638 | Warrick |  | Warrick County | 2009-01-14 | CE
CN
UT
|  |  | 0500639 | Hamilton |  | Hamilton County | 2015-05-31 | CN
PE
|  |  | 0500640 | Warrick |  | Warrick County | 2015-09-02 | CE
CN
ROW
UT
|  |  | 0500641 | Warrick |  | Warrick County | 2018-01-18 | CE
CN
ROW
UT
|  |  | 0500642 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500643 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2005-09-14
|  |  | 0500644 | Carroll |  | Carroll County | -339679.2083 | CN
|  |  | 0500645 |  | Hydrogeology, Inc. | Indiana Department of Transportation | 2005-09-14
|  |  | 0500646 |  | Commonwealth Engineers, Inc. | Johnson County | -339679.2083
|  |  | 0500647 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0500648 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-06 | ROW
RR
UT
|  |  | 0500649 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0500650 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0500651 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500652 | Clark |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500653 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500654 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500655 | Marion |  | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0500656 | Allen |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0500657 | Allen |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0500658 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500659 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500660 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500661 | Porter | Farah and Sons, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500662 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500663 | Allen |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0500664 | Allen |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0500665 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500666 | Vigo |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0500667 | Vigo |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0500668 | Vigo |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0500669 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500670 | Ripley | ARCADIS | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0500671 |  | Douglass Environmental Services, Inc. | LaPorte County | -339679.2083
|  |  | 0500672 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2005-08-17
|  |  | 0500673 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2006-06-21
|  |  | 0500674 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2006-06-21
|  |  | 0500675 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2006-06-21
|  |  | 0500676 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2006-06-21
|  |  | 0500677 |  | AECON, Inc. | Indiana Department of Transportation | 2006-07-19
|  |  | 0500678 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0500679 |  | AECON, Inc. | Indiana Department of Transportation | 2006-07-19
|  |  | 0500680 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2006-07-19
|  |  | 0500681 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2006-01-18
|  |  | 0500682 | Hendricks |  | Hendricks County | 2005-12-14 | CE
CN
|  |  | 0500683 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500684 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500685 |  | ICA Engineering, Inc. | Indiana Department of Transportation | 2006-01-18
|  |  | 0500686 |  |  | Indiana Department of Transportation | 2006-04-19
|  |  | 0500687 |  | Home Equity Appraisals | Indiana Department of Transportation | 2006-04-19
|  |  | 0500688 |  | Home Equity Appraisals | Indiana Department of Transportation | 2006-04-19
|  |  | 0500689 |  | Home Equity Appraisals | Indiana Department of Transportation | 2006-04-19
|  |  | 0500690 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2006-04-19
|  |  | 0500691 | Madison | AAC Environmental Consulting, LLC | Anderson | 2006-01-18 | CE
CN
RR
UT
|  |  | 0500692 | Bartholomew | Associated Right-of-Way Services, Inc. | Bartholomew County | 2009-11-18 | CE
CN
PE
[5 empty] | Associated Right-of-Way Services, Inc. | Bartholomew County | 2009-11-18
|  |  | 0500693 |  |  | Clark County | -339679.2083
|  |  | 0500694 |  | CTL Engineering of Indiana, Inc. | Allen County | -339679.2083
|  |  | 0500695 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0500696 | Various |  | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500697 | Various |  | Indiana Department of Transportation | 2006-05-24 | CN
|  |  | 0500698 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500699 | Various |  | Indiana Department of Transportation | 2005-09-15 | CN
|  |  | 0500700 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500701 | Various |  | Indiana Department of Transportation | 2006-05-24 | CN
|  |  | 0500702 | Madison | AAC Environmental Consulting, LLC | Anderson | -339679.2083 | PE
|  |  | 0500703 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0500704 | Lake |  | Indiana Department of Transportation | 2014-05-21 | CE
CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2014-05-21 | CE
CN
|  |  | 0500705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500706 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500707 | Marshall |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
RR
|  |  | 0500708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500709 | Henry |  | Henry County | -339679.2083 | CN
|  |  | 0500710 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500711 |  |  | Indiana Department of Natural Resources | 2005-09-14
|  |  | 0500712 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0500713 | Hendricks |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
|  |  | 0500714 | Rush |  | Rush County | 2009-05-06 | CE
CN
|  |  | 0500715 | Greene |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0500716 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500717 | Lawrence |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0500718 | Warrick |  | Indiana Department of Transportation | 2007-09-06 | CE
CN
|  |  | 0500719 | Jay |  | Jay County | 2010-08-04 | CE
CN
|  |  | 0500720 |  |  | Putnam County | -339679.2083
|  |  | 0500721 | Dubois |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
UT
|  |  |  | Orange |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
UT
|  |  | 0500722 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500723 | Pike |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0500724 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500725 | St. Joseph |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0500726 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0500727 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500728 | Various |  | Indiana Department of Transportation | 2016-05-31 | CN
|  |  | 0500729 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500730 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500731 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0500732 | Marshall |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
ROW
|  |  | 0500733 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500734 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500735 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500736 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500737 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500738 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500739 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500740 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500741 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500742 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500743 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500744 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500745 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500746 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500747 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500748 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500749 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500750 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500751 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500752 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 0500753 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500754 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500755 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500756 | Starke |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500757 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500758 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500759 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500760 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500761 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500762 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500763 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500764 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500765 | Floyd |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500766 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500767 | Kosciusko | Fink Roberts & Petrie | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500768 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500770 | Porter |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500771 | Starke |  | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0500772 | Starke |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0500773 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0500774 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500775 | Marion |  | Indianapolis | 2007-01-24 | CE
CN
|  |  | 0500776 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500777 | LaGrange | Fink Roberts & Petrie | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500778 | Adams | Accidental Discoveries, LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  |  | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0500779 | Adams | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0500780 | Adams | Bidinfo | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  |  | Wells | Bidinfo | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500781 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2007-05-31 | CE
CN
|  |  | 0500782 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0500783 | Miami |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0500784 | Various |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0500785 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500786 | Various |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0500787 | Delaware | Michael Baker International, Inc. | Yorktown | 2006-06-28 | CE
CN
|  |  | 0500788 | Elkhart | Farren Real Estate Services | Indiana Department of Transportation | 2007-04-04 | CE
CN
|  |  | 0500789 | Owen |  | Indiana Department of Transportation | -339679.2083 | PE
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 0500790 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
|  |  | 0500791 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
PE
|  |  | 0500792 | Newton | Advantage Appraisal Services | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500793 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500794 | Clark |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0500795 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2006-05-24
|  |  | 0500796 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2006-04-19
|  |  | 0500797 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2006-05-24
|  |  | 0500798 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500799 | Hamilton |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
PE
|  |  | 0500800 | Clark |  | Clark County | 2006-03-15 | CE
CN
|  |  | 0500801 |  | AMEC E&I, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500802 | Franklin |  | Franklin County | 2008-09-04 | CE
CN
|  |  | 0500803 | Carroll | Blood Hound, Inc. (former) | Delphi | 2008-08-06 | CE
CN
|  |  | 0500804 | Dekalb | Mader Design, LLC | Waterloo | 2009-10-07 | CE
CN
|  |  | 0500806 | Porter |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
RR
|  |  | 0500808 | Porter |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
|  |  | 0500809 | Porter |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
|  |  | 0500810 | Crawford |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0500811 |  |  | Indiana Department of Transportation | 2005-08-17
|  |  | 0500812 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500813 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500814 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500815 | Fountain | BA Martin Architects, PC | Covington | 2006-08-16 | CE
CN
|  |  | 0500816 | Gibson | III FFC | Gibson County | 2008-04-02 | CE
CN
|  |  | 0500817 | Washington | H. Stewart Kline & Associates, Inc. | Hamilton County | 2015-08-05 | CE
CN
|  |  | 0500818 | Jay | Hydrogeology, Inc. | Portland | 2008-08-06 | CE
CN
|  |  | 0500819 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2009-11-18 | CE
CN
|  |  | 0500820 | LaGrange | John A. Doyle Associates, Inc. | Shipshewana | 2010-07-07 | CE
CN
PE
|  |  | 0500821 | Lake | Consolidated Test Company | Hammond | 2015-10-07 | CE
CN
|  |  | 0500822 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 0500823 | Madison | AAC Environmental Consulting, LLC | Anderson | 2007-12-12 | CE
CN
|  |  | 0500824 |  | DCD Consulting LLC | Marion | -339679.2083
|  |  | 0500825 | Marshall | Howard J. Barth & Associates, Inc. | Marshall County | 2008-04-09 | CE
CN
|  |  | 0500826 | Morgan | GAI Consultants, Inc. | Morgan County | 2012-12-12 | CE
CN
|  |  | 0500827 | Ohio | Indiana Search Technologies | Rising Sun | 2013-05-01 | CE
CN
|  |  | 0500828 |  |  | Indiana Department of Transportation | 2005-11-16
|  |  | 0500829 | Rush |  | Rush County | 2007-03-07 | CE
CN
|  |  | 0500830 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-05-31 | CN
[5 empty] | DCD Consulting LLC | Indiana Department of Transportation | 2006-05-31
|  |  | 0500831 |  | Appraisal Office of Central Indiana | Centerville | -339679.2083
|  |  | 0500832 |  | Appraisal Office of Central Indiana | Centerville | -339679.2083
|  |  | 0500833 | Wayne | American Resources Group, Ltd. | Cambridge City | 2006-05-24 | CE
CN
|  |  | 0500834 | Wayne |  | Dublin | 2006-05-24 | CE
CN
|  |  | 0500835 | Elkhart |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
UT
|  |  | 0500836 | Wells | Accidental Discoveries, LLC | Bluffton | 2016-04-06 | CE
CN
PE
|  |  | 0500837 |  | Accidental Discoveries, LLC | Bluffton | -339679.2083
|  |  | 0500838 | LaPorte | Douglass Environmental Services, Inc. | La Porte | -339679.2083 | PE
|  |  | 0500839 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2008-01-24 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-01-24 | CE
CN
|  |  | 0500840 | Hendricks |  | Indiana Department of Transportation | 2008-01-24 | CE
CN
PE
|  |  |  | Marion |  | Indiana Department of Transportation | 2008-01-24 | CE
CN
PE
|  |  | 0500841 | Hendricks | DCD Consulting LLC | Indiana Department of Transportation | 2008-01-24 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-01-24 | CE
CN
|  |  | 0500842 | Lake | Chicago Testing Laboratory, Inc. | Lake County | 2009-04-08 | CE
CN
|  |  | 0500843 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2008-05-08 | CE
CN
PE
|  |  | 0500844 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500845 | Sullivan | Klug Engineering, Inc. | Sullivan | 2007-08-22 | CE
CN
RR
|  |  | 0500846 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500847 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0500848 | LaGrange | InspectTech Systems, Inc. | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  |  | Noble | InspectTech Systems, Inc. | Indiana Department of Transportation | 2005-10-19 | CE
CN
|  |  | 0500849 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0500850 | LaGrange | Fink Roberts & Petrie | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500851 | Adams | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0500852 |  |  | Indiana Department of Transportation | 2005-09-14
|  |  | 0500853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500854 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500855 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-02-06 | CE
CN
PE
|  |  | 0500856 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-05-31 | CE
CN
UT
|  |  |  | Various | Consolidated Test Company | Indiana Department of Transportation | 2016-05-31 | CN
|  |  | 0500857 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-05-31 | CE
CN
PE
RR
UT
|  |  | 0500858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500859 | Brown |  | Brown County | -339679.2083 | CN
|  |  | 0500860 | Adams |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
|  |  | 0500861 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2005-11-16 | CE
CN
|  |  | 0500862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500863 |  | Home Equity Appraisals | Indiana Department of Transportation | 2006-08-30
|  |  | 0500864 |  |  | Indiana Department of Transportation | 2005-11-16
|  |  | 0500865 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500866 | Bartholomew |  | Columbus | 2016-01-13 | CE
CN
PE
|  |  | 0500867 | Bartholomew |  | Columbus | 2008-04-02 | CE
CN
PE
|  |  | 0500868 | Bartholomew |  | Columbus | 2019-04-03 | CE
CN
PE
|  |  | 0500869 | Marion | DCD Consulting LLC | Indianapolis | 2015-05-31 | CN
ROW
|  |  | 0500870 | Wabash |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
RR
|  |  | 0500871 |  |  | Indianapolis | 2009-08-12
|  |  | 0500872 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2005-11-16
|  |  | 0500873 |  |  | Indiana Department of Transportation | 2005-11-16
|  |  | 0500874 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2008-02-27 | CN
|  |  | 0500875 | Bartholomew |  | Columbus | 2021-01-13 | CE
CN
PE
ROW
|  |  | 0500876 | Bartholomew |  | Columbus | 2014-08-06 | CE
CN
PE
|  |  | 0500877 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500878 | Cass | Eco Logic, LLC | Logansport | 2006-03-15 | CE
CN
|  |  | 0500879 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0500880 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2006-02-15
|  |  | 0500881 |  |  | Putnam County | -339679.2083
|  |  | 0500882 |  |  | South Bend | 2009-05-15
|  |  | 0500883 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0500884 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0500885 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2006-03-15
|  |  | 0500886 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500887 | Warrick |  | Indiana Department of Transportation | 2009-02-11 | PE
ROW
UT
|  |  | 0500888 | Hendricks |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
|  |  | 0500889 | Fayette | Wilcox Environmental Engineering, Inc. | Connersville | 2013-10-09 | CE
CN
|  |  | 0500890 | Montgomery | Banning Engineering, P.C. | Crawfordsville | 2010-05-12 | CE
CN
UT
|  |  | 0500891 | Washington | JCI Bridge Group, Inc. | Salem | 2012-09-12 | CE
CN
PE
UT
|  |  | 0500892 | Allen |  | Allen County | 2013-09-11 | CE
CN
PE
ROW
|  |  | 0500893 |  |  | Bartholomew County | -339679.2083
|  |  | 0500894 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 0500895 | Johnson | Casteel Real Estate | Johnson County | 2008-12-10 | CE
CN
|  |  | 0500896 | Madison |  | Madison County | 2012-03-07 | CE
CN
|  |  | 0500897 | Noble | Debbie L. Morris | Kendallville | 2011-05-11 | CE
CN
PE
|  |  | 0500898 | Putnam |  | Roachdale | 2009-02-11 | CE
CN
RR
|  |  | 0500899 |  |  | Starke County | -339679.2083
|  |  | 0500900 | Steuben |  | Steuben County | 2011-05-11 | CE
CN
PE
|  |  | 0500901 | Hamilton |  | Hamilton County | 2008-11-19 | CE
CN
|  |  | 0500902 | Montgomery |  | Montgomery County | 2007-11-14 | CE
CN
UT
|  |  | 0500903 | Dekalb | Quantum Spatial, Inc. | Auburn | 2013-01-24 | CE
CN
PE
ROW
|  |  | 0500904 | Allen |  | Allen County | 2010-10-06 | CE
CN
PE
|  |  | 0500905 |  |  | Clay County | -339679.2083
|  |  | 0500906 | Clinton |  | Clinton County | 2009-08-12 | CE
CN
|  |  | 0500907 | Decatur |  | Decatur County | 2011-11-16 | CE
CN
UT
|  |  | 0500908 | Hamilton |  | Hamilton County | 2013-08-07 | CE
CN
|  |  | 0500909 | Henry |  | Henry County | 2011-01-12 | CE
CN
|  |  | 0500910 | Johnson |  | Johnson County | 2007-05-16 | CE
CN
UT
|  |  | 0500911 | Marshall |  | Marshall County | 2010-05-12 | CE
CN
|  |  | 0500912 | Montgomery |  | Montgomery County | 2012-05-02 | CE
CN
|  |  | 0500913 |  | III FFC | Princeton | -339679.2083
|  |  | 0500914 | Hancock | CoCal Consulting, LLC | Greenfield | 2014-09-10 | CE
CN
ROW
|  |  | 0500915 |  |  | Hamilton County | -339679.2083
|  |  | 0500916 |  |  | Randolph County | -339679.2083
|  |  | 0500917 |  |  | Ripley County | -339679.2083
|  |  | 0500918 | Rush |  | Rush County | 2010-12-08 | CE
CN
|  |  | 0500919 | St. Joseph |  | St. Joseph County | 2011-05-11 | CE
CN
|  |  | 0500920 |  |  | Scott County | -339679.2083
|  |  | 0500921 |  |  | Hancock County | -339679.2083
|  |  | 0500922 |  |  | Switzerland County | -339679.2083
|  |  | 0500923 | Tipton |  | Tipton County | 2009-09-10 | CE
CN
|  |  | 0500924 | Tipton |  | Tipton County | 2010-10-06 | CE
CN
|  |  | 0500925 | White |  | White County | 2010-07-07 | CE
CN
|  |  | 0500926 | White |  | White County | 2010-07-07 | CE
CN
|  |  | 0500927 | Noble | ERES International, Inc. | Indiana Department of Transportation | 2005-12-14 | CE
CN
|  |  | 0500928 | Elkhart | Farren Real Estate Services | Indiana Department of Transportation | 2007-04-04 | CE
CN
|  |  | 0500929 | Huntington | GMG INC. | Indiana Department of Transportation | 2006-01-18 | CE
CN
|  |  | 0500930 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0500932 |  |  | Indiana Department of Transportation | 2005-10-19
|  |  | 0500933 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500934 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0500935 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0500936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500937 | Gibson |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0500938 | Vanderburgh | CGI | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0500939 | Knox |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0500940 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500941 |  |  | Parke County | -339679.2083
|  |  | 0500942 | Shelby |  | Shelby County | -339679.2083 | CN
|  |  | 0500943 | Montgomery |  | Montgomery County | -339679.2083 | CN
|  |  | 0500944 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0500945 |  | All About Pavements, Inc. | Brownsburg | 2007-05-02
|  |  | 0500946 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500947 | Martin |  | Martin County | -339679.2083 | CN
|  |  | 0500948 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500949 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500950 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500951 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500952 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500953 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500954 | Madison |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
RR
|  |  | 0500955 | Various |  | Bloomington | -339679.2083 | PE
|  |  | 0500956 | Fayette |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  |  | Union |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0500957 |  | CTLGroup | Fortville | -339679.2083
|  |  | 0500958 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0500959 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 0500960 | Monroe | Absolute Title Services, LLC | Bloomington | 2008-05-08 | CE
CN
|  |  | 0500961 | Monroe | Absolute Title Services, LLC | Bloomington | 2006-08-16 | CE
CN
|  |  | 0500963 |  | Terre Haute | Terre Haute | -339679.2083
|  |  | 0500964 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500965 | Vigo | Bayswater Company, LLC | Terre Haute | 2009-08-26 | CE
CN
|  |  | 0500966 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0500967 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0500968 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0500969 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0500970 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0500971 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0500972 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-04-19
|  |  | 0500973 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0500974 | Vigo | Bayswater Company, LLC | Terre Haute | 2011-04-13 | CE
CN
ROW
|  |  | 0500975 | Vigo | Bayswater Company, LLC | Terre Haute | 2020-03-04 | CN
ROW
RR
|  |  | 0500976 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0500977 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500978 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500979 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500980 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500981 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 0500982 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0500983 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0500984 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0500985 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2007-03-21 | CE
CN
RR
|  |  | 0500986 | Monroe | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  |  | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0500987 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0500988 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0500989 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16
|  |  | 0500990 | Johnson |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
UT
|  |  | 0500991 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0500992 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0500993 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0500994 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0500995 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0500996 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0500997 | Wells |  | Wells County | -339679.2083 | CN
|  |  | 0500998 |  | Durham Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0500999 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501000 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0501001 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0501002 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0501003 | Lake |  | Merrillville | 2009-02-11 | CE
CN
UT
|  |  | 0501004 | Parke |  | Parke County | 2012-02-08 | CE
CN
ROW
|  |  | 0501005 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-01-18
|  |  | 0501006 |  |  | Indiana Department of Transportation | 2006-01-18
|  |  | 0501007 |  |  | Monroe County | 2008-12-10
|  |  | 0501008 | Grant |  | Grant County | -339679.2083 | CN
|  |  | 0501009 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0501010 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501011 | Clay |  | Clay County | 2011-04-13 | CE
CN
|  |  | 0501012 |  |  | Anderson | -339679.2083
|  |  | 0501013 |  |  | Anderson | -339679.2083
|  |  | 0501014 | Madison |  | Anderson | 2015-03-04 | CE
CN
|  |  | 0501015 | Madison |  | Anderson | 2015-03-04 | CE
CN
|  |  | 0501016 | Various |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501017 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0501018 |  |  | Indiana Department of Natural Resources | 2006-03-15
|  |  | 0501019 |  |  | Indiana Department of Natural Resources | 2006-06-21
|  |  | 0501020 |  |  | Indiana Department of Natural Resources | 2006-05-24
|  |  | 0501021 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2006-03-15
|  |  | 0501022 | Tippecanoe |  | Indiana Department of Transportation | 2007-07-25 | CE
CN
|  |  | 0501023 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2007-08-22 | CE
CN
|  |  | 0501024 | Warren |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  | 0501025 | Fountain |  | Indiana Department of Transportation | 2007-06-06 | CE
CN
|  |  |  | Vermillion |  | Indiana Department of Transportation | 2007-06-06 | CE
CN
|  |  | 0501026 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501027 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0501028 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501029 | Madison | AAC Environmental Consulting, LLC | Anderson | 2009-04-08 | CE
CN
|  |  | 0501030 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501031 | Delaware | GS-IN P.C. | Muncie | 2013-12-07 | PE
|  |  | 0501032 | Delaware | GS-IN P.C. | Muncie | 2011-05-11 | CE
CN
PE
[5 empty] | GS-IN P.C. | Muncie | 2011-05-11
|  |  | 0501033 | Delaware | GS-IN P.C. | Muncie | 2015-12-09 | CE
CN
PE
ROW
|  |  | 0501034 | Delaware | GS-IN P.C. | Delaware County | 2011-01-26 | CE
CN
PE
ROW
UT
|  |  | 0501035 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2006-06-21 | CE
CN
|  |  | 0501036 | Parke | Infrastructure Engineers, Inc. | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0501037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501038 |  | Digital Appraisals, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501039 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 0501040 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501041 | Clay |  | Indiana Department of Transportation | 2007-08-08 | CE
CN
|  |  | 0501042 | Cass |  | Cass County | 2007-08-22 | CE
CN
|  |  | 0501043 | Vigo |  | Indiana Department of Transportation | 2008-05-14 | CE
CN
|  |  | 0501044 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-08-16 | CE
CN
PE
RR
UT
|  |  | 0501045 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
UT
|  |  | 0501046 |  |  | Indiana Department of Transportation | 2007-10-03
|  |  | 0501047 |  |  | Indiana Department of Transportation | 2007-10-03
|  |  | 0501048 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0501049 | Madison | AAC Environmental Consulting, LLC | Anderson | 2010-08-04 | CE
CN
RR
|  |  | 0501050 | Clay |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  |  | Owen |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0501051 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501052 |  |  | Fowler | -339679.2083
|  |  | 0501053 | Clay |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0501054 |  |  | Benton County | 2012-12-18
|  |  | 0501055 | Montgomery |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0501056 | Wayne |  | Wayne County | -339679.2083 | CN
|  |  | 0501057 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
UT
|  |  | 0501058 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
UT
|  |  | 0501059 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2006-03-15
|  |  | 0501060 | Marion | DCD Consulting LLC | Indianapolis | 2006-02-15 | CE
CN
RR
|  |  | 0501061 | Fountain |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  |  | Montgomery |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0501062 | Bartholomew |  | Bartholomew County | 2013-04-03 | CE
CN
UT
|  |  | 0501063 | Benton |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  |  | Warren |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  | 0501064 | Marion |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0501065 | Clay |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  |  | Owen |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0501066 | Clay |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0501067 | Montgomery |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
PE
|  |  | 0501068 | Knox | Louis Joyner, Architect | Vincennes | 2018-05-31 | PE
|  |  | 0501069 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0501070 |  |  | Elkhart County | -339679.2083
|  |  | 0501071 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 0501072 | Vanderburgh | CGI | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501073 | Vanderburgh | CGI | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501074 |  |  | Indiana Department of Transportation | 2006-04-19
|  |  | 0501075 |  | Casteel Real Estate | Indiana Department of Transportation | 2006-04-19
|  |  | 0501076 |  | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 2006-04-19
|  |  | 0501077 |  |  | Indiana Department of Transportation | 2006-04-19
|  |  | 0501078 |  | Martin Riley, Inc. | Indiana Department of Transportation | 2006-04-19
|  |  | 0501079 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2006-07-19
|  |  | 0501080 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0501081 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0501082 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0501083 | Allen |  | Indiana Department of Transportation | 2006-10-18 | CE
CN
|  |  | 0501084 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501085 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501086 | Warrick |  | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501087 | Hamilton | CPS Acquisitions, LLC | Fishers | 2011-04-13 | CE
CN
PE
|  |  | 0501088 | Marion | DCD Consulting LLC | Indianapolis | 2010-05-31 | CN
ROW
RR
|  |  | 0501089 | Lawrence | ASA Land Surveying | Bedford | 2015-03-04 | CE
CN
PE
ROW
UT
|  |  | 0501090 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501091 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0501092 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  | 0501093 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0501094 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501095 |  |  | Indiana Department of Transportation | 2006-03-29
|  |  | 0501096 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501097 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501098 | Lake |  | Indiana Department of Transportation | 2009-09-24 | CN
|  |  | 0501099 | Lake |  | Indiana Department of Transportation | 2009-09-24 | CN
|  |  | 0501100 | Lake |  | Merrillville | 2009-09-24 | CN
|  |  | 0501101 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501102 | Lake |  | Indiana Department of Transportation | 2009-09-24 | CN
|  |  | 0501103 | Wayne |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
PE
ROW
RR
UT
|  |  | 0501104 |  | DuSABLE, Inc. | Lafayette | -339679.2083
|  |  | 0501105 |  | GS-IN P.C. | Delaware County | 2006-04-03
|  |  | 0501106 | Clinton |  | Clinton County | -339679.2083 | CN
|  |  | 0501107 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0501108 | Hamilton |  | Hamilton County | 2006-07-19 | CE
CN
PE
|  |  | 0501109 |  |  | New Albany | -339679.2083
|  |  | 0501110 | Miami | A & Z Engineering, LLC | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0501111 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
|  |  | 0501112 | Knox |  | Knox County | -339679.2083 | CN
|  |  | 0501113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501114 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2014-05-31 | CN
PE
RR
|  |  | 0501115 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2010-09-16 | CE
CN
PE
RR
|  |  | 0501116 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
RR
|  |  | 0501117 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2011-11-30 | CE
CN
PE
UT
|  |  | 0501118 |  |  | Indiana Department of Transportation | 2005-12-07
|  |  | 0501119 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2013-05-31 | CE
CN
PE
RR
|  |  | 0501120 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2013-05-31 | PE
RR
|  |  | 0501121 | Marion | DCD Consulting LLC | Indianapolis | 2007-10-17 | CE
CN
PE
ROW
RR
UT
|  |  | 0501122 | Marion | DCD Consulting LLC | Indianapolis | 2007-10-17 | CN
PE
ROW
RR
|  |  | 0501123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501127 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 0501128 |  |  | Elkhart County | -339679.2083
|  |  | 0501129 |  |  | Shelby County | -339679.2083
|  |  | 0501130 |  |  | Shelby County | -339679.2083
|  |  | 0501131 | Newton |  | Kentland | 2011-07-13 | CE
CN
PE
|  |  | 0501132 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0501133 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0501134 |  |  | Porter County | -339679.2083
|  |  | 0501135 |  | Karen | Indiana Department of Transportation | -339679.2083
|  |  | 0501136 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-02-15
|  |  | 0501137 |  |  | Munster | -339679.2083
|  |  | 0501138 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0501139 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0501140 | Porter | Leitner and Associates, Inc. | Valparaiso | 2009-02-11 | CE
CN
|  |  | 0501141 | Lake | Matt L. Nepote, MAI | Whiting | 2010-08-04 | CE
CN
PE
|  |  | 0501142 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0501143 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2015-01-06 | CN
|  |  | 0501144 | LaPorte |  | LaPorte County | 2009-07-15 | CE
CN
|  |  | 0501145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501146 | Gibson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0501147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501148 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501149 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0501150 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0501151 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2013-05-31 | PE
PL
|  |  | 0501152 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0501153 |  |  | Indiana Department of Transportation | 2019-11-05
|  |  | 0501154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501156 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501157 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501158 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 0501159 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501160 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0501161 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0501162 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 0501163 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0501164 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0501165 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-07-19
|  |  | 0501166 |  |  | Shelby County | -339679.2083
|  |  | 0501167 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-04-19
|  |  | 0501168 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-04-19
|  |  | 0501169 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0501170 |  |  | Vincennes | 2006-03-15
|  |  | 0501171 | LaPorte |  | Indiana Department of Transportation | 2006-03-15 | CE
CN
|  |  | 0501172 | Cass |  | Cass County | 2008-04-02 | CE
CN
|  |  | 0501173 | Fountain | AECON, Inc. | Attica | 2009-04-08 | CE
CN
|  |  | 0501174 | Dekalb |  | Dekalb County | 2012-07-11 | CE
CN
PE
ROW
|  |  | 0501175 |  |  | Indiana Department of Transportation | 2006-04-19
|  |  | 0501176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501177 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | CN
|  |  | 0501178 | Gibson | CGI | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  |  | Vanderburgh | CGI | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
|  |  | 0501179 | Clark |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0501180 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0501181 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501182 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501183 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0501184 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501185 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501186 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501187 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501188 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0501189 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0501190 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501191 | Dekalb | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  |  | Noble | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501192 | Dekalb | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  |  | Noble | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501193 | Kosciusko | Home Guide Realty Services | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501194 | Kosciusko | Durham Engineering, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  |  | Whitley | Durham Engineering, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501195 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2006-04-19 | CE
CN
|  |  | 0501196 | Dekalb | August Mack Environmental, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0501197 | Jay | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501198 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501199 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2006-11-15 | CE
CN
|  |  | 0501200 | Kosciusko |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0501201 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0501202 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0501203 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0501204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501205 | Warrick |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
PE
|  |  | 0501206 | Gibson |  | Indiana Department of Transportation | 2014-12-10 | CE
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 0501207 | Spencer |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0501208 | Floyd |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0501209 | Floyd |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0501210 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0501211 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501212 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-06-22 | CE
CN
PE
ROW
RR
|  |  |  | Jackson | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-06-22 | ROW
RR
|  |  | 0501213 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0501214 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0501215 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2008-12-17 | CE
CN
|  |  | 0501216 |  |  | Franklin County | -339679.2083
|  |  | 0501217 | Dekalb | Cheri K. Lewis Engineers | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0501218 | LaGrange |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0501219 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501220 | Elkhart | Fink Roberts & Petrie | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  |  | Kosciusko | Fink Roberts & Petrie | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501221 | Noble | InspectTech Systems, Inc. | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501222 | Noble |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501223 | Kosciusko |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  |  | Wabash |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0501224 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  |  | Steuben | Mader Design, LLC | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501225 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0501226 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0501227 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  |  | Whitley | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0501228 | Wabash |  | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0501229 | Grant |  | Indiana Department of Transportation | 2007-04-18 | CE
CN
|  |  | 0501230 | LaGrange | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2006-05-10 | CE
CN
|  |  | 0501231 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0501232 |  | ABt SRBI | Indiana Department of Transportation | -339679.2083
|  |  | 0501233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0501234 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0501235 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
|  |  |  | Henry | CoCal Consulting, LLC | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
|  |  | 0501236 | Henry |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  |  | Wayne |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
|  |  | 0501237 | Wayne |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0501238 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0501239 | Fountain | Linda F. Russell | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  |  | Vermillion | Linda F. Russell | Indiana Department of Transportation | 2010-04-14 | CE
CN
[5 empty] | Linda F. Russell | Indiana Department of Transportation | 2010-04-14
|  |  | 0501240 | Fountain |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  |  | Montgomery |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0501241 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 0501242 | Boone |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  |  | Montgomery |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0501243 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0501244 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0501245 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  |  | Shelby | Collier Transport Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 0501246 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  |  | Franklin | Collier Transport Inc. | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0501247 | Dearborn | Kaskaskia Engineering Group | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0501248 | Dearborn | Kaskaskia Engineering Group | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0501249 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2010-01-29 | CE
CN
PE
|  |  | 0501250 | LaPorte | Huff & Huff, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  |  | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0501251 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0501252 | Shelby |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 0501253 | Vigo |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0501254 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2006-03-15
|  |  | 0501255 | Elkhart |  | Nappanee | 2007-05-16 | CE
CN
|  |  | 0501256 | Warrick |  | Newburgh | 2008-11-19 | CE
CN
|  |  | 0501257 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0501258 |  | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2006-03-15
|  |  | 0501259 | Dubois |  | Dubois County | -339679.2083 | CN
|  |  | 0501260 |  |  | Dearborn County | -339679.2083
|  |  | 0501261 |  |  | Morgan County | -339679.2083
|  |  | 0501262 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0501263 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0501264 | LaPorte |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0501265 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0501266 | LaPorte |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
RR
|  |  | 0501267 | LaPorte |  | Indiana Department of Transportation | 2008-04-09 | CE
CN
PE
|  |  |  | Lake |  | Indiana Department of Transportation | 2008-04-09 | CE
CN
PE
RR
|  |  |  | Porter |  | Indiana Department of Transportation | 2008-04-09 | CE
CN
PE
|  |  | 0501268 | Starke |  | Indiana Department of Transportation | 2006-12-13 | CE
CN
|  |  | 0501269 | Porter |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0501270 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2007-07-25 | CE
CN
RR
|  |  | 0501271 | Porter |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
|  |  | 0501272 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0501273 |  |  | Indiana Department of Transportation | 2006-06-01
|  |  | 0501274 |  |  | Indiana Department of Transportation | 2006-06-01
|  |  | 0501275 |  | Lamac Engineering Company | Indiana Department of Transportation | -339679.2083
|  |  | 0501276 | Fountain |  | Fountain County | -339679.2083 | CN
|  |  | 0501277 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0501278 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0501279 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0501280 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0501281 |  |  | Indiana Department of Transportation | 2008-03-26
|  |  | 0501282 |  |  | Indiana Department of Transportation | 2006-06-01
|  |  | 0501283 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0501284 |  |  | Indiana Department of Transportation | 2006-06-01
|  |  | 0501285 |  |  | Indiana Department of Transportation | 2006-06-01
|  |  | 0501286 |  |  | Indiana Department of Transportation | 2006-06-01
|  |  | 0600001 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-04-19
|  |  | 0600002 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600003 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-03-26 | CE
CN
|  |  | 0600004 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0600005 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0600006 | Fulton |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0600007 | Fulton | InfoTech | Indiana Department of Transportation | 2007-09-19 | CE
CN
|  |  | 0600008 | Fulton | InfoTech | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0600009 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600010 |  |  | Indiana Department of Transportation | 2006-04-19
|  |  | 0600011 |  |  | Indiana Department of Transportation | 2009-05-20
|  |  | 0600025 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600026 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600027 |  |  | Indiana Department of Transportation | 2006-04-19
|  |  | 0600028 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0600029 | Washington |  | Indiana Department of Transportation | 2006-08-16 | CE
CN
|  |  | 0600030 | Floyd |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0600031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600032 | Jackson | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  |  | Washington | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0600033 | Hancock | CoCal Consulting, LLC | Greenfield | 2013-07-10 | CE
CN
PE
|  |  | 0600034 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0600035 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 0600036 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 0600038 | Hendricks |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0600039 | Switzerland |  | Switzerland County | -339679.2083 | CN
|  |  | 0600040 | Hendricks |  | Hendricks County | -339679.2083 | CN
|  |  | 0600041 | Steuben |  | Steuben County | -339679.2083 | CN
|  |  | 0600042 |  |  | Indiana Department of Transportation | 2006-06-05
|  |  | 0600043 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2007-05-16
|  |  | 0600044 |  |  | Indiana Department of Transportation | 2006-02-22
|  |  | 0600045 |  |  | Indiana Department of Natural Resources | 2006-05-24
|  |  | 0600046 |  |  | Indiana Department of Transportation | 2008-02-27
|  |  | 0600047 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0600048 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0600049 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600050 | Harrison |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0600051 | Jackson | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Scott | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Washington | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0600052 | Clay |  | Clay County | 2012-02-08 | CE
CN
|  |  | 0600053 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600054 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0600055 | Ripley | ARCADIS | Indiana Department of Transportation | 2007-04-18 | CE
CN
RR
|  |  | 0600056 |  |  | Indiana Department of Transportation | 2007-01-10
|  |  | 0600057 | Posey |  | Posey County | -339679.2083 | CN
|  |  | 0600058 | Wabash |  | Wabash County | -339679.2083 | CN
|  |  | 0600060 | Huntington |  | Huntington County | -339679.2083 | CN
|  |  | 0600061 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0600062 | Porter |  | Porter County | -339679.2083 | CN
|  |  | 0600063 | Noble |  | Noble County | -339679.2083 | CN
|  |  | 0600064 | LaGrange |  | LaGrange County | -339679.2083 | CN
|  |  | 0600065 | Jay |  | Jay County | -339679.2083 | CN
|  |  | 0600066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600068 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0600069 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0600070 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600071 |  | ERES International, Inc. | Indiana Department of Transportation | 2006-09-13
|  |  | 0600072 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2007-09-19
|  |  | 0600073 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600074 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-05-24
|  |  | 0600075 |  | Hardlines Design Company | Indiana Department of Transportation | -339679.2083
|  |  | 0600076 |  |  | Indiana Department of Transportation | 2006-06-21
|  |  | 0600077 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2006-08-16
|  |  | 0600078 |  |  | Indiana Department of Natural Resources | 2006-04-19
|  |  | 0600079 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600080 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
RR
UT
|  |  | 0600081 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
|  |  | 0600082 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0600083 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0600084 |  |  | Ripley County | -339679.2083
|  |  | 0600085 | Clay |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0600086 | Whitley |  | Whitley County | -339679.2083 | CN
|  |  | 0600087 | Boone |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  | 0600088 | Marion |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
PE
|  |  | 0600089 | Hancock | DCD Consulting LLC | Indiana Department of Transportation | 2009-03-11 | CE
CN
PE
|  |  | 0600090 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600091 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600092 | Hendricks |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
RR
|  |  | 0600093 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2007-04-18 | CE
CN
|  |  | 0600094 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600095 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600096 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600097 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600098 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600099 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600100 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600101 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0600102 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0600103 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0600104 | Parke |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0600105 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0600106 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0600107 | Hendricks |  | Indiana Department of Transportation | 2006-10-18 | CE
CN
|  |  | 0600108 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0600109 | Fountain |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0600110 | Hamilton |  | Fishers | 2009-05-27 | CE
CN
|  |  | 0600111 | Boone |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0600112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600113 |  |  | Fishers | 2009-05-31
|  |  | 0600114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600116 | Miami | Holloway Engineering, LLC | Peru | 2006-10-18 | CE
CN
|  |  | 0600117 | Shelby |  | Shelby County | 2014-02-12 | CE
CN
ROW
UT
|  |  | 0600118 | Shelby |  | Shelby County | 2016-10-05 | CE
CN
PE
ROW
UT
|  |  | 0600119 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2009-11-04 | CE
CN
|  |  | 0600120 | Kosciusko |  | Kosciusko County | -339679.2083 | CN
|  |  | 0600121 |  | Bidinfo | Indiana Department of Transportation | 2006-08-16
|  |  | 0600122 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0600123 | LaGrange |  | Shipshewana | 2006-07-19 | CE
CN
|  |  | 0600124 | LaGrange |  | Shipshewana | 2006-07-19 | CE
CN
|  |  | 0600125 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0600126 | Henry |  | Indiana Department of Transportation | 2006-05-24 | CE
OT
RR
UT
|  |  | 0600127 | Madison | AAC Environmental Consulting, LLC | Anderson | 2011-01-12 | CE
CN
|  |  | 0600128 | Madison | AAC Environmental Consulting, LLC | Anderson | 2011-01-12 | CE
CN
RR
UT
|  |  | 0600129 | Hendricks |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
PE
|  |  | 0600130 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0600131 |  |  | MPO - Lafayette | -339679.2083
|  |  | 0600132 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 0600133 | St. Joseph |  | Indiana Department of Transportation | 2006-05-24 | CE
CN
|  |  | 0600134 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0600135 |  |  | Indiana Department of Transportation | 2006-06-21
|  |  | 0600136 |  |  | Indiana Department of Transportation | 2006-06-21
|  |  | 0600137 | St. Joseph |  | South Bend | 2010-07-07 | CE
CN
RR
|  |  | 0600138 | Whitley |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600139 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0600143 | Miami |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600145 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2007-04-04
|  |  | 0600146 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600147 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600150 |  |  | Indiana Department of Transportation | 2006-03-15
|  |  | 0600151 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600152 |  | ABt SRBI | Indiana Department of Transportation | 2007-04-04
|  |  | 0600153 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0600154 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0600155 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2007-04-04
|  |  | 0600156 | Dubois |  | Vincennes | 2006-09-13 | CE
CN
RR
|  |  | 0600157 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600158 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2007-04-04
|  |  | 0600159 |  | Wessler Engineering, Inc. | Indiana Department of Transportation | 2007-04-04
|  |  | 0600160 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600161 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600162 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600163 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600164 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600165 | Cass |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
PE
ROW
UT
|  |  | 0600166 | Cass |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0600167 |  | Franco Consulting Engineers, LLC | Indiana Department of Transportation | 2006-07-19
|  |  | 0600168 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0600169 | Rush |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0600170 | Madison |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0600171 | Hamilton |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
RR
|  |  |  | Tipton |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
RR
|  |  | 0600172 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2011-02-09 | CE
CN
|  |  | 0600173 | Monroe |  | Monroe County | 2009-02-11 | CN
|  |  | 0600174 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 0600175 |  |  | Indiana Department of Transportation | 2006-05-10
|  |  | 0600176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600177 |  | GS-IN P.C. | Indiana Department of Transportation | 2006-06-21
|  |  | 0600178 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  | 0600179 | Gibson |  | Gibson County | -339679.2083 | CN
PE
|  |  | 0600180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600181 |  |  | Indiana Department of Transportation | 2006-09-13
|  |  | 0600182 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2007-08-22
|  |  | 0600183 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2007-08-22
|  |  | 0600184 |  |  | Indiana Department of Transportation | 2007-10-17
|  |  | 0600185 |  |  | Indiana Department of Transportation | 2006-06-21
|  |  | 0600186 |  |  | Indiana Department of Transportation | 2007-06-06
|  |  | 0600187 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0600188 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600192 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600193 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600194 | St. Joseph | Integrated Environmental Solutions, Inc. | Indiana Department of Transportation | 2008-10-01 | CE
CN
RR
|  |  | 0600195 |  |  | Indiana Department of Transportation | 2006-06-21
|  |  | 0600196 | Hamilton |  | Hamilton County | 2010-07-07 | CE
CN
UT
|  |  | 0600197 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0600198 | Delaware | GS-IN P.C. | Muncie | 2009-05-06 | CE
CN
|  |  | 0600199 | Orange |  | Orange County | -339679.2083 | CN
|  |  | 0600200 | Clinton |  | Indiana Department of Transportation | 2007-04-18 | CE
CN
|  |  | 0600201 |  |  | Martin County | 2008-06-11
|  |  | 0600202 | Delaware | GS-IN P.C. | Muncie | 2009-05-06 | CE
CN
|  |  | 0600203 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0600204 | Hancock |  | Hancock County | -339679.2083 | CN
|  |  | 0600205 |  | Bowman, Barrett & Associates, Inc. | Indiana Department of Transportation | 2007-07-25
|  |  | 0600206 |  | Coates Field Service, Inc. | Indiana Department of Transportation | 2006-08-16
|  |  | 0600207 | Morgan |  | Morgan County | -339679.2083 | CN
PE
|  |  | 0600208 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600209 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0600210 | Monroe |  | Monroe County | -339679.2083 | CN
|  |  | 0600211 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0600212 | Carroll |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  |  | Cass |  | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0600213 | Orange |  | Indiana Department of Transportation | 2006-04-29 | RR
|  |  | 0600214 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2006-07-19 | CE
CN
|  |  | 0600215 | Clay |  | Indiana Department of Transportation | 2006-10-18 | CE
CN
|  |  | 0600216 | Tippecanoe |  | Indiana Department of Transportation | 2007-10-31 | CE
CN
|  |  | 0600217 | Clay |  | Indiana Department of Transportation | 2006-10-18 | CE
CN
|  |  | 0600218 | Fulton |  | Fulton County | -339679.2083 | CN
|  |  | 0600219 | Clark |  | Clark County | -339679.2083 | CN
|  |  | 0600220 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600221 | Vanderburgh | CGI | Evansville | 2009-12-09 | CE
CN
|  |  | 0600222 | Johnson |  | Johnson County | 2008-12-10 | CE
CN
|  |  | 0600223 | Adams |  | Adams County | -339679.2083 | CN
|  |  | 0600224 | Ripley |  | Ripley County | -339679.2083 | CN
|  |  | 0600225 | Harrison |  | Harrison County | -339679.2083 | CN
|  |  | 0600226 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0600227 | Rush |  | Rush County | 2010-12-08 | CE
CN
|  |  | 0600228 |  |  | Indiana Department of Transportation | 2006-06-21
|  |  | 0600229 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600230 | Randolph |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0600231 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2007-05-16 | CE
CN
RR
|  |  | 0600232 |  | Afram Corporation | Indiana Department of Transportation | 2007-05-02
|  |  | 0600233 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0600234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600235 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2006-09-13 | CE
CN
|  |  | 0600236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600237 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600238 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2011-02-09 | CE
CN
PE
|  |  | 0600239 | Lawrence |  | Lawrence County | -339679.2083 | CN
|  |  | 0600240 | Elkhart |  | Indiana Department of Transportation | 2008-07-16 | CE
CN
PE
ROW
|  |  | 0600241 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 0600242 | Clinton |  | Indiana Department of Transportation | 2006-09-01 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2006-09-01 | CE
CN
|  |  | 0600243 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600244 | Jefferson |  | Jefferson County | -339679.2083 | CN
PE
|  |  | 0600245 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0600246 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-15 | PE
|  |  | 0600247 | Marshall |  | Marshall County | -339679.2083 | CN
|  |  | 0600248 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600249 |  |  | Indiana Department of Transportation | 2006-08-16
|  |  | 0600250 | Marion |  | Marion County | -339679.2083 | CN
|  |  | 0600251 | Union |  | Union County | -339679.2083 | CN
|  |  | 0600252 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0600253 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0600254 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2006-09-13
|  |  | 0600255 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  | 0600256 |  |  | Indiana Department of Transportation | 2006-07-19
|  |  | 0600257 | Bartholomew |  | Bartholomew County | -339679.2083 | CN
|  |  | 0600258 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600259 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600260 | Dearborn |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
RR
|  |  | 0600261 |  |  | Indiana Department of Transportation | 2006-11-15
|  |  | 0600262 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600263 | Harrison |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
RR
|  |  | 0600264 | Franklin |  | Franklin County | -339679.2083 | CN
PE
|  |  | 0600265 |  |  | Indiana Department of Transportation | 2006-12-13
|  |  | 0600266 |  | DCD Consulting LLC | Indiana Department of Transportation | 2006-06-13
|  |  | 0600267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600268 | Ripley |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0600269 |  |  | Indiana Department of Transportation | 2006-09-27
|  |  | 0600270 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2007-03-07 | CE
CN
|  |  | 0600271 | Morgan |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0600272 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2007-03-07 | CE
CN
|  |  | 0600273 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2007-02-07 | CE
CN
RR
|  |  | 0600274 |  |  | Indiana Department of Transportation | 2006-11-15
|  |  | 0600275 |  |  | Indiana Department of Transportation | 2006-11-15
|  |  | 0600276 |  |  | Indiana Department of Transportation | 2006-11-15
|  |  | 0600277 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600278 | Allen |  | Allen County | -339679.2083 | CN
|  |  | 0600279 | Clay |  | Clay County | -339679.2083 | CN
|  |  | 0600280 | Floyd |  | Floyd County | -339679.2083 | CN
|  |  | 0600281 |  | CHA, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600282 |  |  | Indiana Department of Transportation | 2006-10-18
|  |  | 0600283 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0600284 | Grant |  | Grant County | 2014-07-09 | CE
CN
PE
ROW
UT
|  |  | 0600285 | Newton |  | Newton County | -339679.2083 | CN
|  |  | 0600286 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600287 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600288 | Morgan |  | Indiana Department of Transportation | 2008-08-01 | CE
CN
|  |  | 0600289 |  |  | Indiana Department of Transportation | 1998-05-12
|  |  | 0600290 |  |  | Indiana Department of Transportation | 2006-06-02
|  |  | 0600291 |  |  | Indiana Department of Transportation | 2002-03-19
|  |  | 0600292 |  |  | Indiana Department of Transportation | 2002-12-18
|  |  | 0600293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600294 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600295 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600296 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600297 |  | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600298 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600299 |  | CGI | Indiana Department of Transportation | 2018-10-22
|  |  | 0600300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600302 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600303 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2007-07-25 | CE
CN
|  |  | 0600304 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2011-04-13 | CE
CN
ROW
|  |  | 0600305 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600307 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2007-07-25 | CE
CN
|  |  | 0600308 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600309 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600310 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600311 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600312 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600313 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600314 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600315 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600316 |  | Cornerstone Design | Indiana Department of Transportation | 2007-05-16
|  |  | 0600317 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16 | PE
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16 | PE
|  |  | 0600318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600319 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600321 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600322 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600323 | LaGrange |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0600324 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600326 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600327 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600329 | Grant |  | Indiana Department of Transportation | 2007-04-04 | CE
CN
RR
|  |  | 0600330 | Kosciusko |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0600331 |  |  | Indiana Department of Transportation | 2006-09-13
|  |  | 0600332 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0600333 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0600334 | Vigo | Bayswater Company, LLC | MPO - Terre Haute | 2009-10-09 | CE
CN
|  |  | 0600335 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2008-08-06 | CE
ROW
|  |  | 0600336 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2009-02-11 | ROW
|  |  | 0600337 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-02-10 | ROW
|  |  | 0600338 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
ROW
|  |  | 0600339 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-04-14 | CE
CN
ROW
|  |  | 0600340 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2011-11-16 | CN
ROW
UT
|  |  |  | Tipton | Dodd Title Corporation | Indiana Department of Transportation | 2011-11-16 | CE
CN
ROW
UT
|  |  | 0600341 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-08-06 | ROW
UT
|  |  | 0600342 | Howard |  | Indiana Department of Transportation | 2013-05-31 | ROW
|  |  | 0600343 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2012-05-04 | CE
CN
ROW
|  |  | 0600344 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2007-04-04
|  |  | 0600345 | Miami |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0600346 | Elkhart | Finley Engineering Group, Inc. | Indiana Department of Transportation | 2007-12-12 | CE
CN
RR
|  |  | 0600347 | Wabash |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0600348 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600349 | Brown |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600350 | Brown |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600351 | Brown |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600352 | Brown |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600353 | Brown |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600354 | Brown |  | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600355 | Marshall |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
PE
ROW
|  |  | 0600356 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600357 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2011-02-09 | CE
CN
PE
|  |  | 0600358 | Marshall |  | Indiana Department of Transportation | 2008-09-04 | CE
PE
ROW
UT
|  |  | 0600359 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600360 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600361 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0600362 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0600363 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0600364 | Marion | DCD Consulting LLC | Indianapolis | 2011-05-11 | CE
CN
|  |  | 0600365 |  |  | Indiana Department of Transportation | 2007-05-31
|  |  | 0600366 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 0600367 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0600368 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-09-10 | CE
CN
PE
|  |  | 0600369 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 0600370 | Monroe |  | Monroe County | 2014-05-08 | CE
CN
|  |  | 0600371 | St. Joseph |  | South Bend | 2008-11-19 | CE
CN
|  |  | 0600372 | Wabash | M-E Companies, Inc. | Wabash | 2011-04-13 | CE
CN
PE
|  |  | 0600373 | Washington | JCI Bridge Group, Inc. | Salem | 2012-09-12 | CE
CN
PE
|  |  | 0600374 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2011-07-06 | ROW
|  |  | 0600375 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-05-06 | CN
PE
ROW
|  |  | 0600376 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600377 | Marion | DCD Consulting LLC | Indiana State Agencies | 2008-08-06 | CE
CN
|  |  | 0600378 | Jasper | Independent Land Surveying, Inc. | Rensselaer | 2012-04-04 | CE
CN
|  |  | 0600379 |  |  | Dubois County | -339679.2083
|  |  | 0600380 | Allen | Global Management Group, Inc. | New Haven | 2011-05-11 | CE
CN
PE
|  |  | 0600381 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2012-03-07 | CE
CN
PE
|  |  | 0600382 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 0600383 | Hancock | CoCal Consulting, LLC | Greenfield | 2011-08-10 | CE
CN
|  |  | 0600384 | Posey | GRL Engineers, Inc. | Mount Vernon | 2009-11-04 | CE
CN
|  |  | 0600385 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2008-11-19 | CE
CN
|  |  | 0600386 |  |  | Dearborn County | -339679.2083
|  |  | 0600387 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2008-03-05 | CE
CN
|  |  | 0600388 |  | August Mack Environmental, Inc. | Corunna | -339679.2083
|  |  | 0600389 | Jefferson |  | Jefferson County | -339679.2083 | PE
|  |  | 0600390 | Hamilton | Another Test Company | Carmel | 2011-02-09 | CE
CN
|  |  | 0600391 | Johnson |  | Johnson County | -339679.2083 | CN
|  |  | 0600392 | LaPorte |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0600393 | White | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0600394 | White | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0600395 | White |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0600396 | White |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0600397 | Lake | Huff & Huff, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
|  |  |  | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2007-04-25 | CE
CN
ROW
UT
|  |  | 0600398 |  |  | Indiana Department of Transportation | 2006-12-13
|  |  | 0600399 |  |  | Indiana Department of Transportation | 2006-12-13
|  |  | 0600400 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600401 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0600402 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600403 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0600404 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600405 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600407 | Hendricks |  | Hendricks County | 2015-05-07 | CE
CN
PE
UT
|  |  | 0600408 |  | KZF Design, Inc. | Indiana Department of Transportation | 2007-03-07
|  |  | 0600409 |  |  | Indiana Department of Natural Resources | 2007-02-21
|  |  | 0600410 |  |  | Indiana Department of Transportation | 2006-09-13
|  |  | 0600411 |  | GS-IN P.C. | MPO - Muncie | -339679.2083
|  |  | 0600412 |  |  | Indiana State Agencies | 2006-09-13
|  |  | 0600413 | Jasper |  | Jasper County | -339679.2083 | CN
PE
|  |  | 0600414 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0600415 | Hendricks |  | Indiana Department of Transportation | 2007-03-07 | CE
CN
PE
ROW
UT
|  |  | 0600416 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0600417 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16
|  |  | 0600418 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16
|  |  | 0600419 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600420 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16
|  |  | 0600421 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600422 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600423 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600424 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0600425 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2009-02-11 | CE
CN
RR
|  |  | 0600426 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600427 | Starke |  | Starke County | -339679.2083 | CN
|  |  | 0600428 | Ohio |  | Ohio County | -339679.2083 | CN
|  |  | 0600429 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 0600430 | Hamilton | Another Test Company | Indiana Department of Transportation | 2015-05-31 | UT
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2015-05-31 | UT
|  |  | 0600431 | Hamilton |  | Indiana Department of Transportation | 2015-05-31 | CN
PE
UT
|  |  | 0600432 | Hamilton | Another Test Company | Indiana Department of Transportation | 2015-05-31 | UT
|  |  | 0600433 | LaPorte |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
UT
|  |  | 0600434 |  | DCD Consulting LLC | MPO - Indianapolis | 2010-05-31
|  |  | 0600435 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600436 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0600437 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0600438 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0600439 |  |  | Indiana Department of Transportation | 2006-11-01
|  |  | 0600440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600441 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600442 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600443 | Marion | DCD Consulting LLC | Indianapolis | 2009-05-06 | CE
CN
|  |  | 0600444 |  | C Blair Enterprises, Inc. | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0600445 | St. Joseph |  | St. Joseph County | 2011-03-23 | CE
CN
|  |  | 0600446 |  |  | Hammond | 2007-01-24
|  |  | 0600447 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0600448 |  |  | Hammond | 2007-01-24
|  |  | 0600449 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0600450 | Lake |  | Hammond | 2007-01-24 | CE
CN
RR
|  |  | 0600451 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0600452 | St. Joseph |  | MPO - South Bend / Elkhart | 2013-07-10 | CE
CN
|  |  | 0600453 | St. Joseph |  | St. Joseph County | 2013-10-09 | CE
CN
|  |  | 0600454 | St. Joseph |  | South Bend | 2009-03-11 | CE
CN
|  |  | 0600455 | St. Joseph |  | St. Joseph County | 2009-08-12 | CN
|  |  | 0600456 | Elkhart | Civil Inspection Services, LLC | Goshen | 2009-11-04 | CE
CN
|  |  | 0600457 | Elkhart | Civil Inspection Services, LLC | Goshen | 2012-01-11 | CE
CN
RR
|  |  | 0600458 | Clark |  | Clark County | -339679.2083 | CN
|  |  |  | Floyd |  | Clark County | -339679.2083 | CN
|  |  | 0600459 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0600460 | Marshall | Bayer & Becker, Inc. | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0600461 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0600462 | St. Joseph |  | South Bend | 2010-05-26 | CN
PE
|  |  | 0600463 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2014-01-15 | CE
CN
PE
ROW
RR
|  |  | 0600465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600466 |  |  | Indiana Department of Transportation | 2006-08-04
|  |  | 0600467 | Various |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
|  |  | 0600468 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2009-07-15
|  |  | 0600469 | Starke |  | Indiana Department of Transportation | 2006-12-13 | CE
CN
|  |  | 0600470 | Elkhart |  | Elkhart County | -339679.2083 | CN
|  |  | 0600471 |  | Flexible H.R. Solutions, LLC | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0600472 | Brown |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0600473 | Brown |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0600474 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600475 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600476 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600477 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600478 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600479 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0600480 | Perry |  | Perry County | -339679.2083 | CN
|  |  | 0600481 | Washington |  | Washington County | -339679.2083 | CN
|  |  | 0600482 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600483 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600484 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-10-03
|  |  | 0600485 |  |  | Indiana Department of Transportation | 2006-02-15
|  |  | 0600486 | Boone |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600487 | Jackson |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
PE
ROW
|  |  | 0600488 | Bartholomew |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0600489 | Lake |  | Lake County | -339679.2083 | CN
|  |  | 0600490 | Brown |  | Indiana Department of Transportation | 2007-05-02 | CE
CN
|  |  | 0600491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600492 | Marion | DCD Consulting LLC | Indiana State Agencies | 2008-05-31 | CN
|  |  | 0600493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600494 | Owen |  | Owen County | -339679.2083 | CN
|  |  | 0600495 | Johnson |  | Johnson County | -339679.2083 | PE
|  |  | 0600496 | Monroe | Absolute Title Services, LLC | Bloomington | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0600497 | Vanderburgh | CGI | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0600498 | Marshall |  | Marshall | -339679.2083 | CN
|  |  | 0600499 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 0600500 | Cass |  | Indiana Department of Transportation | 2006-12-13 | CE
CN
|  |  | 0600501 | Starke |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0600502 | Pulaski |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0600503 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0600504 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0600505 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0600506 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0600507 |  |  | Indiana Department of Transportation | 2006-10-18
|  |  | 0600508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600512 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600515 | Various |  | White County | -339679.2083 | PE
|  |  |  | White |  | White County | -339679.2083 | CN
|  |  | 0600516 | Marshall |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0600517 | Tippecanoe |  | Tippecanoe County | -339679.2083 | CN
|  |  | 0600518 | Spencer |  | Spencer County | -339679.2083 | CN
|  |  | 0600519 |  | Collier Transport Inc. | Indiana Department of Transportation | 2007-04-18
|  |  | 0600520 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0600521 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600522 |  |  | Indiana Department of Transportation | 2007-04-18
|  |  | 0600523 |  |  | Indiana Department of Transportation | 2007-02-21
|  |  | 0600524 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600525 | Decatur |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0600526 |  |  | Indiana Department of Transportation | 2007-04-18
|  |  | 0600527 |  |  | Indiana Department of Transportation | 2007-04-18
|  |  | 0600528 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600529 |  |  | Indiana Department of Transportation | 2007-03-07
|  |  | 0600530 | St. Joseph |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 0600531 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600532 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600534 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600537 |  |  | South Bend | 2015-05-31
|  |  | 0600538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600539 | Scott |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
|  |  | 0600540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600541 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600542 |  |  | Indiana Department of Transportation | 2007-02-21
|  |  | 0600543 |  | Central Indiana Land Solutions | Indiana Department of Transportation | 2007-04-18
|  |  | 0600544 |  |  | Indiana Department of Transportation | 2007-03-07
|  |  | 0600545 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2006-11-15
|  |  | 0600546 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-05-31 | CE
CN
|  |  | 0600547 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-01-09 | CE
CN
ROW
RR
UT
|  |  | 0600548 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 0600549 | Elkhart |  | Indiana Department of Transportation | 2014-10-08 | PE
|  |  | 0600550 |  |  | Indiana Department of Transportation | 2008-03-26
|  |  | 0600551 |  |  | Indiana Department of Transportation | 2008-03-26
|  |  | 0600552 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2008-03-26
|  |  | 0600553 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2008-03-26
|  |  | 0600554 |  | Mader Design, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600555 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0600556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600557 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0600558 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600559 |  |  | Indiana Department of Transportation | 2007-01-24
|  |  | 0600560 | Howard | Dodd Title Corporation | Kokomo | 2010-02-24 | CE
CN
|  |  | 0600561 |  |  | Indiana Department of Transportation | 2007-01-24
|  |  | 0600562 |  |  | Indiana Department of Transportation | 2007-01-24
|  |  | 0600563 | Tipton |  | Tipton County | -339679.2083 | CN
|  |  | 0600564 | Vanderburgh |  | Vanderburgh County | -339679.2083 | CN
|  |  | 0600565 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2008-04-02 | RR
|  |  | 0600566 | Howard |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0600567 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0600568 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0600569 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0600570 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0600571 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600572 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600574 | Madison | CPS Acquisitions, LLC | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0600575 | Howard |  | Indiana Department of Transportation | 2012-05-04 | CE
CN
|  |  | 0600576 | Harrison |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
|  |  | 0600577 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600578 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0600579 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0600580 | Howard |  | Indiana Department of Transportation | 2012-05-04 | CE
CN
|  |  | 0600581 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600582 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600583 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600584 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
RR
|  |  | 0600585 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
RR
|  |  | 0600586 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0600587 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0600588 | Howard |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0600589 | Howard |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
RR
|  |  | 0600590 | Howard |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
RR
|  |  | 0600591 | Howard |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 0600592 | Tipton |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0600593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600594 | Howard |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0600595 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0600596 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600597 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0600598 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0600599 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0600600 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0600601 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0600602 |  |  | Indiana Department of Transportation | 2007-01-10
|  |  | 0600603 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0600604 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0600605 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0600606 | Jennings |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0600607 | Jennings |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
RR
|  |  | 0600608 | Floyd |  | New Albany | -339679.2083 | CN
|  |  | 0600609 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-02-07
|  |  | 0600610 |  |  | Indiana Department of Transportation | 2007-03-07
|  |  | 0600611 |  |  | Indiana Department of Transportation | 2007-04-18
|  |  | 0600612 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600613 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0600614 | Parke |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
PE
ROW
|  |  | 0600615 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0600616 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600617 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600618 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600619 |  |  | Terre Haute | -339679.2083
|  |  | 0600620 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
PE
|  |  | 0600621 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600628 | Madison |  | Madison County | -339679.2083 | CN
|  |  | 0600629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600630 | Elkhart |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 0600631 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600632 |  |  | Indiana Department of Transportation | 2007-01-10
|  |  | 0600633 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0600634 | Greene |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0600635 | Various |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0600636 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600637 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-10-31
|  |  | 0600638 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2013-05-31 | PE
UT
|  |  | 0600639 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-31
|  |  | 0600640 |  |  | Indiana Department of Transportation | 2009-05-31
|  |  | 0600641 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-31
|  |  | 0600642 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-11-24 | PE
|  |  | 0600643 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-05-31 | CN
PE
|  |  | 0600644 | Franklin |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0600645 | Marion |  | Indiana Department of Transportation | 2009-11-24 | PE
UT
|  |  | 0600646 |  |  | Indiana Department of Transportation | 2009-11-24
|  |  | 0600647 |  |  | Indiana Department of Transportation | 2009-11-24
|  |  | 0600648 |  |  | Indiana Department of Transportation | 2009-11-24
|  |  | 0600649 |  |  | Indiana Department of Transportation | 2009-11-24
|  |  | 0600650 | Marion |  | Indiana Department of Transportation | 2010-02-10 | CE
PE
ROW
UT
|  |  | 0600651 | Marion | All About Pavements, Inc. | Indiana Department of Transportation | 2009-04-29 | CE
CN
UT
|  |  | 0600652 | Marion |  | Indiana Department of Transportation | 2010-02-10 | PE
|  |  | 0600653 | Marion |  | Indiana Department of Transportation | 2009-04-29 | CE
CN
|  |  | 0600654 | Marion |  | Indiana Department of Transportation | 2009-04-29 | CE
CN
|  |  | 0600655 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0600656 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0600657 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0600658 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0600659 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0600660 | Vigo | Bayswater Company, LLC | Vigo County | 2010-12-08 | CE
CN
|  |  | 0600661 | Various |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0600662 | Various |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0600663 | Various |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
PE
|  |  | 0600664 | Various | EnviroScience, Inc. | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0600665 | St. Joseph | Flexible H.R. Solutions, LLC | St. Joseph County | 2009-08-12 | CE
CN
|  |  | 0600666 | Various | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0600667 | Brown |  | Indiana Department of Transportation | 2010-01-27 | CE
CN
|  |  |  | Monroe |  | Indiana Department of Transportation | 2010-01-27 | CE
CN
|  |  | 0600668 | Various |  | Indiana Department of Transportation | 2007-04-04 | CE
CN
|  |  | 0600669 | Porter |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
ROW
UT
|  |  | 0600670 | LaPorte |  | Indiana Department of Transportation | 2007-04-04 | CE
CN
PE
ROW
UT
|  |  | 0600671 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 0600672 | Lake |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
RR
UT
|  |  | 0600673 | Lake |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
RR
UT
|  |  | 0600674 | Madison |  | Indiana Department of Transportation | 2009-03-11 | PE
RR
|  |  | 0600675 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600676 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600677 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0600678 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600679 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-02-07
|  |  | 0600680 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600681 |  |  | Indiana Department of Transportation | 2007-03-07
|  |  | 0600682 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600683 |  |  | Indiana Department of Transportation | 2007-03-07
|  |  | 0600684 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600685 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600686 | Lake | Courtland Title & Escrow, Inc. | Lake County | 2009-03-11 | CE
CN
|  |  | 0600687 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600688 |  |  | Indiana Department of Transportation | 2007-03-21
|  |  | 0600689 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600690 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-03-07
|  |  | 0600691 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0600692 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2007-04-18
|  |  | 0600693 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0600694 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0600695 |  | ABNA of Illinois | Indiana Department of Transportation | 2007-04-18
|  |  | 0600696 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2011-11-16 | CE
CN
PE
ROW
|  |  | 0600697 | Howard |  | Howard County | -339679.2083 | CN
|  |  | 0600698 |  |  | Indiana Department of Transportation | 2007-02-07
|  |  | 0600699 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0600700 | Lake |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0600701 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600702 |  | Dodd Title Corporation | Indiana Department of Transportation | 2007-04-25
|  |  | 0600703 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2007-05-31
|  |  | 0600704 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600705 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
UT
|  |  | 0600706 | Grant |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600707 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600709 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600711 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600712 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600713 |  | C Blair Enterprises, Inc. | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0600714 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600715 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600716 | Vanderburgh | CGI | Vanderburgh County | 2009-03-11 | CN
|  |  | 0600717 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600718 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600719 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600720 | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600721 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600722 |  |  | Indiana Department of Transportation | 2007-08-22
|  |  | 0600723 |  |  | Indiana Department of Transportation | 2007-08-22
|  |  | 0600724 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0600725 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0600726 |  | Dynasty Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600727 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
ROW
|  |  | 0600728 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2007-05-16
|  |  | 0600729 |  |  | Indiana Department of Transportation | 2007-01-10
|  |  | 0600730 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600731 | Morgan |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
|  |  | 0600732 | Blackford |  | Blackford County | -339679.2083 | CN
|  |  | 0600733 |  |  | Indiana Department of Transportation | 2007-04-18
|  |  | 0600734 | Jackson | EnviroScience, Inc. | Indiana Department of Transportation | 2007-08-22 | CE
CN
|  |  | 0600735 | Marion | DCD Consulting LLC | Indianapolis | 2009-08-12 | CE
CN
|  |  | 0600736 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600737 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0600738 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600739 | Jackson |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  |  | Jennings |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0600740 |  |  | Harrison County | -339679.2083
|  |  | 0600741 |  |  | Harrison County | -339679.2083
|  |  | 0600742 |  |  | Harrison County | -339679.2083
|  |  | 0600743 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600744 | Pulaski |  | Pulaski County | -339679.2083 | CN
|  |  | 0600745 | Dekalb |  | Dekalb County | -339679.2083 | CN
|  |  | 0600746 | Vermillion |  | Vermillion County | -339679.2083 | CN
|  |  | 0600747 | Jackson |  | Jackson County | -339679.2083 | CN
|  |  | 0600748 |  | Douglass Environmental Services, Inc. | LaPorte County | -339679.2083
|  |  | 0600749 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2009-09-10 | CE
CN
RR
|  |  | 0600750 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2011-04-13 | CE
CN
|  |  | 0600751 | Lake |  | Lake County | 2012-05-02 | CE
CN
|  |  | 0600752 | Lake |  | Lake County | 2015-07-08 | CE
CN
|  |  | 0600753 | Lake |  | Lake County | 2012-07-11 | CE
CN
|  |  | 0600754 | Porter | Huff & Huff, Inc. | Portage | 2018-03-21 | CE
CN
ROW
|  |  | 0600755 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0600756 | Clark |  | Clark County | 2012-05-02 | CE
CN
RR
|  |  | 0600757 | Porter |  | Indiana Department of Transportation | 2007-02-21 | CE
CN
ROW
UT
|  |  | 0600758 |  |  | Indiana Department of Transportation | 2008-01-09
|  |  | 0600759 |  |  | Indiana Department of Transportation | 2007-03-21
|  |  | 0600760 |  |  | Indiana Department of Transportation | 2007-03-21
|  |  | 0600761 |  |  | Indiana Department of Transportation | 2007-04-25
|  |  | 0600762 |  |  | Indiana Department of Transportation | 2007-04-25
|  |  | 0600763 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0600764 | Various |  | Indiana Department of Transportation | 2007-05-31 | CE
CN
|  |  | 0600765 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2007-02-07 | CE
CN
|  |  | 0600766 |  |  | Indiana Department of Transportation | 2007-01-23
|  |  | 0600767 | Madison |  | Madison County | 2012-03-07 | CE
CN
|  |  | 0600768 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600769 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0600770 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0600771 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2007-10-17 | CE
CN
RR
|  |  | 0600772 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600773 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0600774 |  |  | Indiana Department of Transportation | 2007-06-06
|  |  | 0600775 | Vigo | Bayswater Company, LLC | Terre Haute | 2007-08-22 | CE
CN
|  |  | 0600776 | Wayne | Indiana Appraisal Group, Inc. | Wayne County | 2011-05-31 | PE
|  |  | 0600777 | Hamilton |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0600778 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Hancock |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Henry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Putnam |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Wayne |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600779 |  |  | Indiana Department of Transportation | 2007-03-21
|  |  | 0600780 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600781 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600782 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600783 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0600784 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Crawford |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Dearborn |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Harrison |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Jefferson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Perry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Posey |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Spencer |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Warrick |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600785 |  |  | Indiana Department of Transportation | 2007-04-18
|  |  | 0600786 | Clark |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Crawford |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Dearborn |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Harrison |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Jefferson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Perry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Posey |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Spencer |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Warrick |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0600787 |  |  | Indiana Department of Transportation | 2007-01-23
|  |  | 0600788 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600789 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0600790 |  | DCD Consulting LLC | MPO - Indianapolis | 2008-05-31
|  |  | 0600791 |  |  | Indiana Department of Transportation | 2007-05-31
|  |  | 0600792 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2009-05-06 | CE
CN
|  |  | 0600793 | Elkhart |  | Indiana Department of Transportation | 2008-03-05 | PE
|  |  |  | Fulton |  | Indiana Department of Transportation | 2008-03-05 | PE
|  |  |  | Kosciusko |  | Indiana Department of Transportation | 2008-03-05 | PE
|  |  |  | Miami |  | Indiana Department of Transportation | 2008-03-05 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0600794 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0600795 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0600796 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0600797 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0600798 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0600799 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0600800 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600801 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16
|  |  | 0600802 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0600803 | Montgomery |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0600804 | Lake |  | Hammond | 2008-03-26 | CE
CN
|  |  | 0600805 |  |  | Indiana Department of Natural Resources | 2008-03-05
|  |  | 0600806 |  |  | Indiana Department of Natural Resources | 2009-01-14
|  |  | 0600807 | Various |  | Indiana Department of Transportation | 2007-08-22 | CE
CN
|  |  | 0600808 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0600809 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0600810 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0600811 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2010-05-19 | CE
CN
PE
|  |  | 0600812 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0600813 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0600814 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600815 | Dearborn |  | Indiana Department of Transportation | 2007-09-06 | CE
CN
|  |  | 0600816 |  |  | Indiana Department of Transportation | 2007-02-21
|  |  | 0600817 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0600818 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0600819 | Owen |  | Indiana Department of Transportation | 2008-09-04 | CE
PE
|  |  | 0600820 |  |  | Indiana Department of Transportation | 2007-05-02
|  |  | 0600821 | Various |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
PE
|  |  | 0700001 | Various |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0700002 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 0700003 | Allen |  | Indiana Department of Transportation | 2008-02-06 | RR
|  |  | 0700004 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0710000 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2007-08-08
|  |  | 0710001 | Various |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0710002 |  | GS-IN P.C. | MPO - Muncie | -339679.2083
|  |  | 0710003 | Clark |  | Clark County | 2018-05-10 | CE
CN
PE
ROW
RR
UT
|  |  | 0710004 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-16
|  |  | 0710005 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0710006 |  |  | Indiana Department of Transportation | 2007-05-02
|  |  | 0710007 |  |  | MPO - Northwest | -339679.2083
|  |  | 0710008 | Dearborn |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
|  |  | 0710009 |  |  | Indiana Department of Transportation | 2007-03-21
|  |  | 0710010 | Various | Dynasty Group, Inc. | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0710011 | Monroe |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
UT
|  |  | 0710012 | Monroe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710013 | Warrick |  | Warrick County | 2009-03-11 | CE
CN
|  |  | 0710014 |  |  | Boone County | -339679.2083
|  |  | 0710015 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-05-02
|  |  | 0710016 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-10-03
|  |  | 0710017 |  |  | Indiana Department of Transportation | 2007-04-04
|  |  | 0710018 |  |  | Boone County | -339679.2083
|  |  | 0710019 | Daviess |  | Daviess County | -339679.2083 | CN
|  |  | 0710020 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710021 | Howard | Dodd Title Corporation | Howard County | 2019-01-16 | CE
CN
PE
ROW
UT
|  |  | 0710022 |  |  | Indiana Department of Transportation | 2007-05-02
|  |  | 0710023 | Howard | Dodd Title Corporation | Howard County | 2010-08-04 | CE
CN
ROW
|  |  | 0710024 |  | Data Transfer Solutions, LLC | MPO - Louisville | -339679.2083
|  |  | 0710025 | Howard |  | Howard County | 2016-12-14 | CE
CN
PE
ROW
|  |  | 0710026 | Howard |  | Howard County | 2015-11-10 | CE
CN
PE
ROW
UT
|  |  | 0710027 | St. Joseph |  | Indiana Department of Transportation | 2010-01-27 | CE
CN
RR
|  |  | 0710028 | Lake |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0710029 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0710030 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2009-10-07 | CE
CN
|  |  | 0710031 | Lake |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0710032 | Lake |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0710033 | Lake |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0710034 | Porter |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
RR
|  |  | 0710035 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0710036 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710037 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710038 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710039 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 0710040 | St. Joseph |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710042 | Pulaski |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710043 | Cass |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710044 | St. Joseph | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2010-01-27 | CE
CN
RR
|  |  | 0710045 | Lake |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
RR
|  |  | 0710046 | Jasper |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0710047 |  |  | Indiana Department of Transportation | 2008-03-05
|  |  | 0710048 | Starke |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0710049 | Jasper |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0710050 |  |  | Indiana Department of Transportation | 2007-10-17
|  |  | 0710051 | Porter | Huff & Huff, Inc. | Porter County | 2010-07-07 | CE
CN
|  |  | 0710052 | Porter |  | Porter County | 2011-05-11 | CE
CN
|  |  | 0710053 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CE
CN
RR
|  |  | 0710054 | Lake |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0710055 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 0710056 | Adams |  | Munster | 2019-02-20 | CN
|  |  |  | Lake |  | Munster | 2019-02-20 | CN
PE
ROW
RR
|  |  | 0710057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710058 | Lake |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0710059 | Various |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
PE
|  |  | 0710060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710061 | Dearborn | CGI | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 0710062 | Lake | Consolidated Test Company | Hammond | 2012-11-15 | CE
CN
|  |  | 0710063 |  | Karen | St. John | -339679.2083
|  |  | 0710064 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0710065 | Porter | Leitner and Associates, Inc. | Valparaiso | 2012-02-08 | CE
CN
|  |  | 0710066 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 0710067 |  | Compliance Consulting Service, Inc. | Lake County | -339679.2083
|  |  | 0710068 | Lake | Cornerstone Design | Highland | 2018-02-07 | CE
CN
ROW
|  |  | 0710069 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0710070 |  |  | Indiana Department of Transportation | 2007-05-31
|  |  | 0710071 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710072 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710073 | Perry |  | Indiana Department of Transportation | 2008-01-30 | CE
CN
PE
|  |  | 0710074 | Lawrence |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710075 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2013-05-01 | CE
CN
|  |  | 0710076 |  |  | Indiana Department of Transportation | 2009-01-14
|  |  | 0710077 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2013-05-01 | CE
CN
|  |  | 0710078 | Perry |  | Indiana Department of Transportation | 2012-08-15 | CE
CN
PE
ROW
|  |  | 0710079 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710080 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  | 0710081 | Lake |  | Indiana Department of Transportation | 2007-09-19 | CE
CN
|  |  | 0710082 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710083 | Dearborn |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
|  |  | 0710084 | Dearborn |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
PE
|  |  | 0710085 |  |  | Indiana Department of Natural Resources | 2008-02-06
|  |  | 0710086 | Grant |  | Indiana Department of Transportation | 2007-05-16 | CE
CN
|  |  | 0710087 | Johnson |  | Indiana Department of Transportation | 2007-08-22 | CE
CN
|  |  | 0710088 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | 2007-05-16
|  |  | 0710089 | Delaware | GS-IN P.C. | Muncie | 2014-09-10 | CE
CN
PE
|  |  | 0710090 |  | Michael Baker International, Inc. | Yorktown | -339679.2083
|  |  | 0710091 | Delaware | GS-IN P.C. | Delaware County | 2011-05-11 | CE
CN
PE
|  |  | 0710092 | Delaware |  | Delaware County | 2013-07-17 | CE
CN
PE
ROW
UT
|  |  | 0710093 |  |  | Delaware County | -339679.2083
|  |  | 0710094 | Various |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
|  |  | 0710095 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0710096 | Various |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
PE
|  |  | 0710097 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710098 | Delaware | Michael Baker International, Inc. | Delaware County | 2018-05-10 | CE
CN
PE
ROW
|  |  | 0710099 |  |  | Indiana Department of Transportation | 2007-05-31
|  |  | 0710100 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710101 |  | EcoTec, Inc. | Indiana Department of Transportation | 2008-04-02
|  |  | 0710102 | Various |  | Indiana Department of Transportation | 2007-07-25 | CE
CN
|  |  | 0710103 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710104 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0710105 | Sullivan |  | Indiana Department of Transportation | 2008-03-26 | CE
CN
|  |  | 0710106 | Daviess |  | Indiana Department of Transportation | 2009-10-07 | CE
CN
ROW
|  |  | 0710107 | Allen |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
PE
|  |  | 0710108 | Daviess |  | Indiana Department of Transportation | 2009-10-21 | CE
CN
|  |  | 0710109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710113 | Perry |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
PE
|  |  | 0710114 | Orange |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
|  |  | 0710115 | Jasper |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0710116 | Jasper |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0710117 |  | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2007-05-16
|  |  | 0710118 | Jasper |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0710119 |  |  | Lake County | -339679.2083
|  |  | 0710120 | Clay | Bayswater Company, LLC | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  |  | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2012-07-11 | CN
|  |  | 0710121 | Lake |  | Indiana Department of Transportation | 2008-08-22 | CE
CN
|  |  | 0710122 | LaPorte |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0710123 | Hendricks |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0710124 | Clay |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0710125 | Montgomery |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0710126 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0710127 | Hendricks |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0710128 | Dubois |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
PE
|  |  |  | Perry |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0710129 | Warrick |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0710130 | Vanderburgh |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0710131 | Vanderburgh |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0710132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710135 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710136 | Allen |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0710137 | Allen |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0710138 | Lawrence |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710139 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0710140 | Delaware |  | Delaware County | -339679.2083 | PE
|  |  | 0710141 | Huntington |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
PE
|  |  | 0710142 | Huntington |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710143 | Hancock |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  |  | Wayne |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0710144 | Dekalb |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
PE
|  |  | 0710145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710146 | Jasper |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0710147 | Hendricks |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0710148 | Hendricks |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0710149 | Boone |  | Indiana Department of Transportation | 2008-11-19 | CE
|  |  |  | Clark |  | Indiana Department of Transportation | 2008-11-19 | CN
|  |  |  | Clinton |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0710150 | Clark |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
|  |  |  | Jackson |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
|  |  |  | Johnson |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
|  |  |  | Shelby |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
PE
|  |  | 0710151 | Floyd |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710152 | Clark |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  |  | Floyd |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710156 |  |  | Indiana Department of Transportation | 2007-05-31
|  |  | 0710157 |  | Dynasty Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710158 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710159 |  | Engineering Resources, Inc. | Jefferson County | 2007-05-16
|  |  | 0710160 | Orange |  | Orange County | 2012-05-31 | CN
|  |  | 0710161 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0710162 | Hancock |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 0710163 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0710164 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710165 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710167 | Clark |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  | 0710168 | Harrison |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  | 0710169 | Switzerland |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0710170 | St. Joseph |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 0710171 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CN
|  |  | 0710172 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0710173 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0710174 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2011-11-17
|  |  | 0710175 |  |  | St. Joseph County | 2007-05-31
|  |  | 0710176 | Vanderburgh | CGI | Evansville | -339679.2083 | PE
|  |  | 0710177 |  | GS-IN P.C. | MPO - Muncie | -339679.2083
|  |  | 0710178 |  | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710179 |  | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710180 |  | Hy-Tech Response, Inc. | MPO - Northwest | 2009-05-31
|  |  | 0710181 |  | Farah and Sons, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710182 |  | Huff & Huff, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710183 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710184 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710186 |  | ERES International, Inc. | Indiana Department of Natural Resources | 2008-01-09
|  |  | 0710187 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710188 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710189 |  | III FFC | Indiana Department of Transportation | 2008-03-05
|  |  | 0710190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710192 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710193 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710194 | Sullivan |  | Sullivan County | -339679.2083 | CN
PE
|  |  | 0710195 | Pike |  | Pike County | -339679.2083 | CN
|  |  | 0710196 | Putnam | Clayton L. Roots | Greencastle | 2010-01-13 | CE
CN
ROW
|  |  | 0710197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710198 | Cass | Eco Logic, LLC | Logansport | 2012-07-11 | CE
CN
PE
|  |  | 0710199 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2013-03-06 | CE
CN
|  |  | 0710200 |  | Atlas Appraisals, LLC | Converse | -339679.2083
|  |  | 0710201 | Ripley | Hardcore Concrete Sawing Inc. | Osgood | 2011-04-13 | CE
CN
|  |  | 0710202 | Dekalb | KZF Design, Inc. | St. Joe | 2009-08-26 | CE
CN
PE
|  |  | 0710203 | Elkhart | Civil Inspection Services, LLC | Goshen | 2009-10-21 | CE
CN
PE
|  |  | 0710204 | Monroe |  | Monroe County | 2011-04-13 | CE
CN
PE
|  |  | 0710205 |  | Gandhi and Associates, Inc. | Nappanee | -339679.2083
|  |  | 0710206 | Monroe |  | Ellettsville | -339679.2083 | PE
|  |  | 0710207 | Hamilton | Another Test Company | Carmel | -339679.2083 | PE
|  |  | 0710208 | Monroe | Absolute Title Services, LLC | Monroe County | -339679.2083 | PE
|  |  | 0710209 | Elkhart | Civil Inspection Services, LLC | Goshen | -339679.2083 | PE
|  |  | 0710210 | Bartholomew | Associated Right-of-Way Services, Inc. | Bartholomew County | -339679.2083 | PE
|  |  | 0710211 | Lake | Brenner Design Incorporated | Lake County | -339679.2083 | PE
|  |  | 0710212 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | PE
|  |  | 0710213 |  | DCD Consulting LLC | Indianapolis | 2008-01-24
|  |  | 0710214 | Marion | DCD Consulting LLC | Indianapolis | 2011-05-11 | CE
CN
|  |  | 0710215 | Hamilton |  | Indiana Department of Transportation | 2007-03-07 | PE
ROW
|  |  | 0710216 | Hamilton |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0710217 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710218 | Putnam |  | Putnam County | -339679.2083 | CN
|  |  | 0710219 | Benton |  | Benton County | -339679.2083 | CN
|  |  | 0710220 | Adams |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710221 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
UT
|  |  | 0710222 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
RR
|  |  | 0710223 | Noble | ERES International, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710224 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710225 |  |  | Indiana Department of Transportation | 2007-09-19
|  |  | 0710226 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710227 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710228 |  | Booth & Associates | Indiana Department of Transportation | -339679.2083
|  |  | 0710229 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710230 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710231 | Vigo | EFI Global, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710232 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710233 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710234 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710235 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710236 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710237 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710238 | Tipton | Land Construction Corp | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710239 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710240 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710241 | Gibson | III FFC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710242 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710243 | Delaware | GS-IN P.C. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710244 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0710245 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710246 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710247 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0710248 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710249 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 0710250 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710251 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710252 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2012-04-16 | RR
|  |  | 0710253 | St. Joseph |  | Indiana Department of Transportation | 2007-07-11 | CE
CN
|  |  | 0710254 | St. Joseph |  | Indiana Department of Transportation | 2007-08-22 | CE
CN
|  |  | 0710255 | St. Joseph |  | Indiana Department of Transportation | 2007-10-17 | CE
CN
|  |  | 0710256 | St. Joseph |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0710257 | St. Joseph |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0710258 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2007-10-17 | CE
CN
|  |  | 0710259 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  | 0710260 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
RR
|  |  | 0710261 |  | Environmental Management Associatese | Indiana Department of Transportation | -339679.2083
|  |  | 0710262 |  | Dynasty Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710263 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710264 | Floyd |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
PE
RR
|  |  | 0710265 | Floyd |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
PE
|  |  | 0710266 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710268 |  |  | Indiana Department of Transportation | 2007-08-08
|  |  | 0710269 | Brown |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
RR
|  |  |  | Monroe |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
RR
|  |  | 0710270 | Dearborn |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  |  | Ohio |  | Indiana Department of Transportation | 2008-05-08 | CE
CN
|  |  | 0710271 | Floyd |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0710272 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710273 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710274 |  | CGI | Vanderburgh County | 2008-04-23
|  |  | 0710275 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 0710276 | Allen |  | Indiana Department of Transportation | 2015-05-31 | CN
PE
|  |  | 0710277 | Various |  | Indiana Department of Transportation | 2012-04-17 | CN
|  |  | 0710278 | Marion |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
|  |  | 0710279 | Marion |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0710280 | White |  | Indiana Department of Transportation | 2008-09-17 | CE
CN
RR
|  |  | 0710281 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710282 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710283 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710284 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710285 | Greene |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0710286 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710287 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 0710288 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 0710289 |  |  | Boone County | -339679.2083
|  |  | 0710290 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 0710291 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710292 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2008-03-05
|  |  | 0710293 | Dearborn |  | Dearborn County | -339679.2083 | PE
|  |  | 0710294 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0710295 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0710296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710297 | Jefferson |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0710298 | Tippecanoe |  | Tippecanoe County | 2009-08-12 | CE
CN
|  |  | 0710299 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710300 | Various |  | Indiana Department of Transportation | 2008-05-31 | CN
|  |  | 0710301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710302 |  |  | Indiana Department of Transportation | 2013-07-17
|  |  | 0710303 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0710304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710305 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-31 | PE
|  |  | 0710306 |  |  | Indiana Department of Transportation | 2013-07-17
|  |  | 0710307 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-02-23 | CE
CN
ROW
UT
|  |  | 0710308 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0710309 | Vanderburgh | CGI | Indiana Department of Transportation | 2007-07-25 | CE
CN
|  |  | 0710310 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710311 |  |  | Indianapolis | -339679.2083
|  |  | 0710312 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710313 | Various | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2010-05-31 | CN
|  |  | 0710314 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-05-31 | CN
|  |  | 0710315 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  |  | Marion | Casteel Real Estate | Indiana Department of Transportation | 2012-12-12 | CE
|  |  | 0710316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710317 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-01-14 | CN
|  |  | 0710318 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | PE
|  |  | 0710319 | Allen | Global Management Group, Inc. | New Haven | 2014-09-10 | CE
CN
PE
ROW
|  |  | 0710320 | Allen | Global Management Group, Inc. | New Haven | 2010-05-12 | CE
CN
PE
|  |  | 0710321 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0710322 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2019-01-16 | CE
CN
PE
ROW
|  |  | 0710323 | Tippecanoe |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0710324 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0710325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710326 | Cass |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0710327 | Jefferson |  | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0710328 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0710329 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710330 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0710331 | Huntington |  | Indiana Department of Transportation | 2007-11-14 | CE
CN
RR
|  |  | 0710332 | LaGrange |  | Indiana Department of Transportation | 2008-01-24 | CE
CN
|  |  | 0710333 | Noble |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0710334 | Steuben |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0710335 |  |  | Indiana Department of Transportation | 2010-07-21
|  |  | 0710336 |  |  | Indiana Department of Transportation | 2007-07-25
|  |  | 0710337 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710338 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 0710339 | Johnson |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
UT
|  |  | 0710340 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2008-03-19
|  |  | 0710341 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710342 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710343 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710344 | Allen |  | Allen County | 2013-09-11 | CE
CN
|  |  | 0710345 | Allen |  | Allen County | 2013-09-11 | CE
CN
|  |  | 0710346 | Clinton |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 0710347 |  |  | Marion | -339679.2083
|  |  | 0710348 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2008-07-09 | PE
|  |  | 0710349 | Noble |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0710350 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0710351 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0710352 | Decatur |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0710353 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710354 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0710355 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710356 | St. Joseph |  | St. Joseph County | 2010-05-12 | CE
CN
|  |  | 0710357 | St. Joseph |  | St. Joseph County | 2013-10-09 | CE
CN
|  |  | 0710358 | St. Joseph |  | MPO - South Bend / Elkhart | 2009-08-12 | CE
CN
|  |  | 0710359 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0710360 | St. Joseph |  | St. Joseph County | 2012-02-08 | CE
CN
UT
|  |  | 0710361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710362 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 0710363 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 0710364 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0710365 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710366 |  | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710367 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710368 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710369 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710370 | Clark |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
|  |  |  | Floyd |  | Indiana Department of Transportation | 2012-02-08 | CN
PE
|  |  | 0710371 | Various |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
PE
|  |  | 0710372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710373 |  |  | Indiana Department of Transportation | 2007-07-11
|  |  | 0710374 | Vermillion | Archaeology and Geomorphology Services | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 0710375 |  |  | Indiana Department of Transportation | 2007-05-16
|  |  | 0710376 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710377 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 0710378 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2015-05-31
|  |  | 0710379 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 0710380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710381 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 0710382 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 0710383 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 0710384 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2009-03-11 | CE
CN
|  |  | 0710385 | Shelby |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
PE
|  |  | 0710386 | Sullivan |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0710387 | Greene |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
PE
|  |  |  | Lawrence |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710388 | Spencer |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710389 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0710390 | Daviess |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  |  | Knox |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710391 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  |  | Putnam | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 0710392 | Marion |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 0710393 | Putnam | Clayton L. Roots | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 0710394 | Montgomery |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710395 | Boone | Digital Appraisals, LLC | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  |  | Clinton | Digital Appraisals, LLC | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 0710396 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710397 | Clinton |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 0710398 |  |  | Indiana Department of Transportation | 2008-03-13
|  |  | 0710399 | Benton |  | Indiana Department of Transportation | 2014-01-29 | CE
CN
PE
ROW
|  |  | 0710400 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2015-11-10 | CE
CN
ROW
|  |  | 0710401 | Porter |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710402 | St. Joseph |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0710403 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2010-07-07 | CE
CN
|  |  | 0710404 | Hendricks |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0710405 | Gibson |  | Indiana Department of Transportation | 2008-04-02 | ROW
|  |  | 0710406 |  |  | Crawfordsville | -339679.2083
|  |  | 0710407 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710408 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710409 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710410 |  |  | Indiana Department of Natural Resources | 2008-01-09
|  |  | 0710411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710412 |  |  | Indiana Department of Transportation | 2007-09-06
|  |  | 0710413 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0710414 |  |  | Indiana Department of Transportation | 2007-08-22
|  |  | 0710415 | Allen |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710416 | Cass |  | Cass County | -339679.2083 | PE
|  |  | 0710417 | Kosciusko |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710418 | Vanderburgh | CGI | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 0710419 |  | DCD Consulting LLC | Indiana Department of Transportation | 2007-11-14
|  |  | 0710420 |  |  | Shelby County | -339679.2083
|  |  | 0710421 | Clinton |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
UT
|  |  | 0710422 |  |  | Shelby County | -339679.2083
|  |  | 0710423 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0710424 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710425 | Various |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0710426 | Jackson | FAA National, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710427 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710428 | Various |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 0710429 | Jefferson |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  |  | Switzerland |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710430 | Various |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 0710431 | Jackson |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  |  | Jennings |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710432 | Jackson |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710433 | Washington |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710434 | Jackson |  | Indiana Department of Transportation | 2009-08-26 | CE
CN
|  |  | 0710435 | Clark |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  |  | Floyd |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  | 0710436 | Johnson |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710437 | Monroe |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710438 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710439 |  |  | Indiana Department of Transportation | 2008-03-05
|  |  | 0710440 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710441 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710443 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710444 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710446 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710447 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710448 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710449 | Wayne |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0710450 | Noble | Bartlett & Associates, Inc. | Indiana Department of Transportation | 2010-07-07 | CE
CN
RR
|  |  | 0710451 | Huntington |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710452 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0710453 | Whitley |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710454 | Whitley |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710455 | LaGrange |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710456 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710458 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 0710459 | Clinton |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 0710460 | Clinton |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 0710461 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710462 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710463 | Martin |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  |  | Orange |  | Indiana Department of Transportation | 2017-04-05 | CE
|  |  | 0710464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710467 | Porter |  | Indiana Department of Transportation | 2014-10-08 | PE
|  |  |  | Putnam |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0710468 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710469 | Parke |  | Indiana Department of Transportation | 2012-09-14 | CE
CN
|  |  | 0710470 | Various |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0710471 | Tippecanoe |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 0710472 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 0710473 | Parke |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 0710474 | Hancock |  | Hancock County | 2011-05-11 | CE
CN
|  |  | 0710475 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  |  | Madison | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0710476 | Clinton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710477 | Clinton |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 0710478 | Hendricks |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 0710479 | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710481 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710482 | Marion |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 0710483 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710484 | Knox |  | Indiana Department of Transportation | 2007-11-28 | CE
CN
|  |  | 0710485 | Daviess |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  |  | Martin |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710486 | Posey |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0710487 | Grant |  | Grant County | 2014-07-09 | CE
CN
|  |  | 0710488 |  |  | Grant County | -339679.2083
|  |  | 0710489 |  |  | Grant County | -339679.2083
|  |  | 0710490 |  |  | Albion | 2008-01-03
|  |  | 0710491 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
RR
|  |  | 0710492 | Hancock |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710493 | Delaware |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  |  | Jay |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0710494 | Vanderburgh | CGI | Evansville | 2013-05-01 | CE
CN
ROW
|  |  | 0710495 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2011-12-14 | CE
CN
PE
ROW
|  |  | 0710496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710497 | Rush |  | Rush County | 2008-07-09 | CE
CN
|  |  | 0710498 | Henry |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
RR
|  |  | 0710499 |  |  | Indiana Department of Transportation | 2007-10-17
|  |  | 0710500 | Dearborn |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710501 | Jefferson |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710502 | Jennings |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0710503 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710506 |  | Courtland Title & Escrow, Inc. | Hobart | 2007-08-22
|  |  | 0710507 | Hendricks |  | Avon | 2010-05-12 | CE
CN
PE
|  |  | 0710508 | Hendricks |  | Avon | 2010-12-08 | CE
CN
ROW
UT
|  |  | 0710509 |  | DCD Consulting LLC | MPO - Indianapolis | 2009-05-31
|  |  | 0710510 | Various |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0710511 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0710512 | Fayette |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0710513 | Fayette | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
ROW
|  |  | 0710514 | Hamilton |  | Indiana Department of Transportation | 2015-07-01 | ROW
|  |  | 0710515 | Wayne |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0710516 | Randolph |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
ROW
|  |  | 0710517 | Wayne |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
|  |  | 0710518 |  | Boomerang Ventures, LLC | Indiana Department of Transportation | 2007-09-19
|  |  | 0710519 | Wayne |  | Indiana Department of Transportation | -339679.2083 | CE
UT
|  |  | 0710520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710521 | Wayne |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
ROW
|  |  | 0710522 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710523 |  |  | Indiana Department of Transportation | 2007-09-06
|  |  | 0710524 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710525 | Grant |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710526 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710527 | Shelby |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 0710528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710529 | Lake |  | Indiana Department of Transportation | 2008-03-26 | CE
UT
|  |  | 0710530 |  | Farah and Sons, Inc. | MPO - Northwest | 2008-05-31
|  |  | 0710531 |  | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710532 |  | Farah and Sons, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710533 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 0710534 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0710535 |  | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083
|  |  | 0710536 |  | Chicago Testing Laboratory, Inc. | MPO - Northwest | 2010-05-31
|  |  | 0710537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710538 | Johnson |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
ROW
|  |  | 0710539 | Monroe |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
|  |  | 0710540 | Hancock |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0710541 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710542 | Greene |  | Indiana Department of Transportation | 2007-09-19 | CE
CN
|  |  | 0710543 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710544 |  |  | Indiana Department of Transportation | 2008-08-20
|  |  | 0710545 |  |  | Indiana Department of Transportation | 2007-11-28
|  |  | 0710546 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 0710547 | Delaware | GS-IN P.C. | Delaware County | 2007-06-14 | PE
|  |  | 0710548 | Rush |  | Rush County | 2014-07-09 | CE
CN
|  |  | 0710549 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0710550 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710551 |  |  | Indiana Department of Transportation | 2007-09-19
|  |  | 0710552 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2006-05-24
|  |  | 0710553 | Greene |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
|  |  | 0710554 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2007-10-31
|  |  | 0710555 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710556 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2008-01-09 | CE
CN
ROW
RR
UT
|  |  | 0710557 | Allen |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0710558 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0710559 | Allen |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0710560 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0710561 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | ROW
|  |  | 0710562 | Warren |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710563 | Marion | DCD Consulting LLC | Indianapolis | 2008-10-01 | CE
CN
|  |  | 0710564 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2008-04-02 | CE
CN
RR
|  |  | 0710565 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0710566 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0710567 | Washington |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710568 | Warrick |  | Indiana Department of Transportation | 2010-03-03 | CE
CN
UT
|  |  | 0710569 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710570 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
RR
|  |  | 0710571 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0710572 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0710573 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0710574 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0710575 | Gibson |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
|  |  | 0710576 | Gibson |  | Indiana Department of Transportation | 2007-12-12 | CE
CN
PE
|  |  | 0710577 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710578 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 0710579 |  |  | Indiana Department of Transportation | 2008-01-09
|  |  | 0710580 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710581 | Miami |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
|  |  | 0710582 | Miami |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
PE
|  |  | 0710583 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2007-07-19 | CN
|  |  | 0710584 | Various |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0710585 |  | Bidinfo | Indiana Department of Transportation | 2008-12-10
|  |  | 0710586 | Marion |  | Indianapolis | 2007-10-17 | CN
PE
ROW
RR
[6 empty] | Indianapolis | 2007-10-17
|  |  | 0710587 | Various |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
PE
|  |  | 0710588 | Marion | DCD Consulting LLC | Indianapolis | 2009-04-08 | CN
|  |  | 0710589 | Fayette |  | Fayette County | -339679.2083 | CN
|  |  | 0710590 | Steuben |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
RR
|  |  | 0710591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710592 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710593 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2008-03-05 | CE
CN
|  |  | 0710594 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 0710595 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710596 | Huntington |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
|  |  | 0710597 |  |  | Indiana Department of Transportation | 2008-11-19
|  |  | 0710598 |  |  | Indiana Department of Transportation | 2011-01-11
|  |  | 0710599 |  | Leitner and Associates, Inc. | Valparaiso | 2007-10-17
|  |  | 0710600 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2010-04-14
|  |  | 0710601 |  |  | Indiana Department of Transportation | 2008-01-09
|  |  | 0710602 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0710603 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 0710604 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710605 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
RR
UT
|  |  | 0710606 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710607 |  | Leitner and Associates, Inc. | Valparaiso | 2007-10-17
|  |  | 0710608 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2008-07-09 | CE
|  |  | 0710609 | Knox |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
ROW
UT
|  |  | 0710610 | Daviess |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Harrison |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Martin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Washington |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710611 |  | Commonwealth Engineers, Inc. | Greenwood | 2007-10-03
|  |  | 0710612 | Lake |  | Indiana Department of Transportation | 2007-10-26 | CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2007-10-26 | CN
|  |  | 0710613 | Lake |  | Indiana Department of Transportation | 2007-10-26 | CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2007-10-26 | CN
|  |  | 0710614 | Lake |  | Indiana Department of Transportation | 2007-10-26 | CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2007-10-26 | CN
|  |  | 0710615 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 0710616 | Gibson |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0710617 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2007-12-12 | CE
UT
|  |  | 0710618 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710619 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710620 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710621 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710622 | Boone |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  |  | Clinton |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710624 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710625 |  | Hardcore Concrete Sawing Inc. | Osgood | 2011-04-13
|  |  | 0710626 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-02-27
|  |  | 0710627 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-01-12 | CE
CN
UT
|  |  | 0710628 |  |  | Indiana Department of Transportation | 2008-02-27
|  |  | 0710629 | Bartholomew |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
PE
ROW
|  |  | 0710630 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2014-12-13 | PE
|  |  | 0710631 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710632 | Jackson |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
ROW
UT
|  |  | 0710633 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 0710634 | Jennings |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710635 | Jackson |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
UT
|  |  | 0710636 | Switzerland |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
UT
|  |  | 0710637 | Ripley |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
|  |  | 0710638 | Franklin |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0710639 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
UT
|  |  | 0710640 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710641 | Bartholomew |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0710642 | Brown |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  | 0710643 | Scott | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0710644 | Scott |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
UT
|  |  | 0710645 | Jefferson |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0710646 | Franklin |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0710647 | Franklin |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0710648 | Franklin |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0710649 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710650 | Lawrence |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710651 |  |  | Indiana Department of Transportation | 2008-01-09
|  |  | 0710652 |  | Land Construction Corp | Indiana Department of Transportation | 2008-04-23
|  |  | 0710653 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2008-04-23
|  |  | 0710654 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710655 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 0710656 |  |  | Indiana Department of Natural Resources | 2008-07-09
|  |  | 0710657 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2010-07-09 | CE
CN
|  |  | 0710658 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
RR
|  |  | 0710659 |  |  | Indiana Department of Natural Resources | 2008-07-09
|  |  | 0710660 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
RR
|  |  | 0710661 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 0710662 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2010-07-09 | CE
CN
|  |  | 0710663 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0710664 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710665 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0710666 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710667 |  |  | Indiana Department of Transportation | 2008-03-05
|  |  | 0710668 |  |  | Indiana Department of Transportation | 2008-04-23
|  |  | 0710669 |  |  | Indiana Department of Transportation | 2008-01-09
|  |  | 0710670 | Johnson |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0710671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710672 | Lawrence | ICA Engineering, Inc. | Mitchell | 2009-04-08 | CE
CN
|  |  | 0710673 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-03-26
|  |  | 0710674 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-04-02
|  |  | 0710675 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 0710676 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0710677 |  | Appraisal Office of Central Indiana | Indiana Department of Transportation | -339679.2083
|  |  | 0710678 | Bartholomew |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  | 0710679 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710680 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710681 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0710682 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0710683 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710684 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0710685 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710686 | Wabash |  | Wabash County | 2013-02-06 | CE
CN
PE
|  |  | 0710687 | Jackson |  | Jackson County | 2014-10-08 | CE
CN
PE
|  |  | 0710688 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2009-05-27 | CE
|  |  | 0710689 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2009-05-27 | CE
|  |  | 0710690 |  |  | Indiana Department of Transportation | 2008-06-18
|  |  | 0710691 |  |  | Indiana Department of Transportation | 2007-11-28
|  |  | 0710692 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0710693 |  |  | Indiana Department of Natural Resources | 2008-07-09
|  |  | 0710694 | Washington |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710695 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710696 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710697 | Bartholomew | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710698 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710699 |  |  | Indiana Department of Natural Resources | 2008-01-09
|  |  | 0710700 | Knox |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0710701 |  | Mark Keutzer, Appraiser | Indiana Department of Transportation | -339679.2083
|  |  | 0710702 |  |  | Indiana Department of Transportation | 2008-03-05
|  |  | 0710703 | Lake |  | Lake County | 2009-05-06 | CE
CN
|  |  | 0710704 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Newton |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710705 | Gibson |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Martin |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710706 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Warren |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710707 | Huntington |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
PE
|  |  | 0710708 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0710709 |  |  | Indiana Department of Transportation | 2007-11-28
|  |  | 0710710 | Randolph |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710711 | Miami |  | Miami County | 2015-07-08 | CE
CN
PE
ROW
|  |  | 0710712 |  |  | Indiana Department of Transportation | 2007-11-28
|  |  | 0710713 |  |  | Indiana Department of Transportation | 2007-11-28
|  |  | 0710714 | Crawford |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0710715 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710716 | Lake |  | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0710717 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0710718 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0710719 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0710720 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2007-11-28
|  |  | 0710721 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-07-09
|  |  | 0710722 | Marshall |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0710723 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0710724 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0710725 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0710726 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0710727 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710728 | St. Joseph |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
|  |  | 0710729 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0710730 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0710731 | Marshall |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2010-08-04 | CN
|  |  | 0710732 | St. Joseph |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0710733 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0710734 | Marshall |  | Indiana Department of Transportation | 2010-08-04 | CE
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2010-08-04 | CN
|  |  | 0710735 | St. Joseph |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0710736 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0710737 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0710738 |  |  | Indiana Department of Transportation | 2009-05-27
|  |  | 0710739 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0710740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710741 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0710742 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0710743 | Marshall |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
RR
|  |  | 0710744 | Marshall |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
RR
|  |  | 0710745 | Marshall |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
|  |  | 0710746 | Marshall |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
|  |  | 0710747 | Hamilton |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0710748 | St. Joseph | Dummy Consulting Firm Too | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0710749 | St. Joseph | Dummy Consulting Firm Too | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0710750 | Marshall |  | Indiana Department of Transportation | 2011-04-13 | CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0710751 | Marshall |  | Indiana Department of Transportation | 2011-04-13 | CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0710752 | Marshall |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CN
|  |  | 0710753 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710754 | St. Joseph |  | Indiana Department of Transportation | 2009-08-12 | PE
UT
|  |  | 0710755 | Marshall |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0710756 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710757 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
UT
|  |  | 0710758 | Marshall |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
PE
ROW
|  |  | 0710759 |  |  | Indiana Department of Transportation | 2009-05-27
|  |  | 0710760 | Marshall |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CN
|  |  | 0710761 | Marshall |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CN
|  |  | 0710762 | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 0710763 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 0710764 | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 0710765 | Marshall |  | Indiana Department of Transportation | 2012-02-08 | PE
ROW
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
UT
|  |  | 0710766 | Marshall |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2012-02-08 | CN
|  |  | 0710767 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710768 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 0710769 | Marshall |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0710770 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 0710771 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 0710772 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 0710773 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 0710774 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710775 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2009-11-04 | CE
CN
PE
|  |  | 0710776 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710777 | Marshall |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2013-10-09 | CE
|  |  | 0710778 | Marshall |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
UT
|  |  | 0710779 | Fulton |  | Indiana Department of Transportation | 2013-04-10 | CN
|  |  |  | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 0710780 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 0710781 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710782 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 0710783 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
|  |  | 0710784 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
UT
|  |  | 0710785 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710786 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710787 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710788 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710790 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710792 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710793 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710794 | St. Joseph |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0710795 | St. Joseph |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0710796 | Marshall |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
ROW
|  |  | 0710797 | Whitley |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0710798 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0710799 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0710800 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-03-11 | CE
|  |  | 0710801 | Grant |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0710802 |  | Marine Solutions, Inc. | Indiana Department of Transportation | 2008-05-08
|  |  | 0710803 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0710804 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0710805 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0710806 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0710807 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0710808 | Floyd |  | New Albany | 2018-02-07 | CE
CN
PE
ROW
UT
|  |  | 0710809 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0710810 | Floyd |  | New Albany | 2018-03-14 | CE
CN
PE
|  |  | 0710811 |  |  | Indiana Department of Natural Resources | 2008-05-08
|  |  | 0710812 |  |  | Indiana Department of Natural Resources | 2008-05-08
|  |  | 0710813 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710814 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2016-01-13 | CE
CN
PE
|  |  | 0710815 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710816 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710817 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710818 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0710819 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710821 | Hendricks |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0710822 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710823 | Lawrence |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0710824 | Warrick |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0710825 | Dubois |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0710826 | Greene |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
RR
|  |  | 0710827 | Perry |  | Indiana Department of Transportation | 2009-05-06 | CE
CN
|  |  | 0710828 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710829 |  |  | Indiana Department of Transportation | 2008-04-23
|  |  | 0710830 | Miami |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
|  |  | 0710831 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0710832 | Elkhart |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
|  |  | 0710833 | Steuben |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710834 | Daviess | EcoTec, Inc. | Indiana Department of Transportation | 2012-11-15 | CE
CN
RR
|  |  |  | Martin | EcoTec, Inc. | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 0710835 | Pike |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0710836 |  | CBRE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710837 | Adams |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0710838 |  |  | Indiana Department of Natural Resources | 2008-10-01
|  |  | 0710839 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
RR
|  |  | 0710840 | Cass | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2010-01-27 | CE
CN
|  |  | 0710841 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710842 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710843 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710844 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0710845 |  |  | Indiana Department of Natural Resources | 2008-07-09
|  |  | 0710846 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710847 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710848 | Franklin |  | Indiana Department of Transportation | 2010-07-09 | CE
CN
PE
|  |  | 0710849 | Warrick |  | Newburgh | 2009-12-09 | CE
CN
PE
|  |  | 0710850 | Warrick |  | Newburgh | 2018-10-11 | CE
CN
PE
ROW
|  |  | 0710851 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710852 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0710853 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2008-04-23 | CE
CN
|  |  | 0710854 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710855 | Steuben |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
|  |  | 0710856 | Steuben |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
|  |  | 0710857 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0710858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710859 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710860 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710861 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710862 | Greene |  | Indiana Department of Transportation | 2009-05-27 | PE
ROW
|  |  | 0710863 |  | CH2M HILL, Inc. | Indiana Department of Transportation | 2008-02-06
|  |  | 0710864 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
ROW
|  |  | 0710865 | Jasper |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0710866 |  | InfoTech | Indiana Department of Transportation | -339679.2083
|  |  | 0710867 | Scott |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
ROW
UT
|  |  | 0710868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710869 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710870 | Floyd |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
|  |  | 0710871 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-07-09
|  |  | 0710872 | Tippecanoe |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0710873 | Delaware |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  | 0710874 |  | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710875 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710876 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0710877 | Marion |  | Indiana Department of Transportation | 2008-08-06 | CE
CN
|  |  | 0710878 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0710879 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
ROW
UT
|  |  | 0710880 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-01-09 | CE
CN
|  |  | 0710881 | Clark |  | Indiana Department of Transportation | 2008-05-31 | CN
|  |  | 0710882 | Dearborn |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710883 | Hamilton |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0710884 | Harrison |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0710885 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710886 | Elkhart |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710887 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0710888 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0710889 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 0710890 | Johnson |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
|  |  | 0710891 | Johnson |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
|  |  | 0710892 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
UT
|  |  | 0710893 | White | Fugro Roadware, Inc. | White County | 2013-04-03 | CE
CN
ROW
|  |  | 0710894 | Knox |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
ROW
|  |  | 0710895 | Knox |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 0710896 |  |  | Indiana Department of Transportation | 2010-05-12
|  |  | 0710897 | Pike |  | Indiana Department of Transportation | 2012-05-31 | PE
ROW
|  |  | 0710898 | Daviess |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0710899 | Daviess |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
ROW
|  |  | 0710900 | Daviess |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
ROW
|  |  | 0710901 | Daviess |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0710902 | Gibson |  | Indiana Department of Transportation | 2009-03-11 | PE
ROW
|  |  | 0710903 | Daviess |  | Indiana Department of Transportation | 2009-03-11 | PE
ROW
|  |  | 0710904 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710905 | Pike |  | Indiana Department of Transportation | 2009-03-11 | PE
ROW
|  |  | 0710906 |  |  | Indiana Department of Transportation | 2009-09-10
|  |  | 0710907 | Daviess |  | Indiana Department of Transportation | 2008-08-20 | CE
CN
|  |  | 0710908 |  | DCD Consulting LLC | Indianapolis | 2008-05-31
|  |  | 0710909 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0710910 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710911 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710912 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710913 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0710914 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710915 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710916 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710917 | Montgomery |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710918 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710919 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 0710920 | Warren |  | Warren County | -339679.2083 | CN
|  |  | 0710921 | Blackford |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710922 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710923 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710924 |  |  | Indiana Department of Transportation | 2008-08-27
|  |  | 0710925 | Various |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0710926 | Various |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0710927 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 0710928 | Jay |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
PE
|  |  | 0710929 | Spencer |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 0710930 | Knox |  | Indiana Department of Transportation | 2017-01-01 | PE
|  |  | 0710931 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710932 |  |  | Indiana Department of Transportation | 2010-08-04
|  |  | 0710933 | Grant |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
RR
|  |  | 0710934 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710935 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710936 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2008-05-14
|  |  | 0710937 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2008-05-14
|  |  | 0710938 | Jackson |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
UT
|  |  | 0710939 | Parke |  | Parke County | -339679.2083 | CN
|  |  | 0710940 | Putnam |  | Putnam County | 2011-05-11 | CE
CN
ROW
|  |  | 0710941 |  | GS-IN P.C. | MPO - Muncie | -339679.2083
|  |  | 0710942 |  | GS-IN P.C. | MPO - Muncie | -339679.2083
|  |  | 0710943 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0710944 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0710945 | Fulton |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  |  | Kosciusko |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
RR
|  |  |  | Various |  | Indiana Department of Transportation | 2012-02-08 | CE
|  |  | 0710946 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710947 | Adams |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0710948 | Carroll |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  |  | Howard |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0710949 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
|  |  | 0710951 | Spencer |  | Indiana Department of Transportation | 2008-11-19 | CE
|  |  | 0710952 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710953 | Elkhart | C Blair Enterprises, Inc. | Elkhart County | 2010-02-24 | CE
CN
|  |  | 0710954 |  |  | Kosciusko County | -339679.2083
|  |  | 0710955 | Kosciusko |  | Kosciusko County | 2012-04-04 | CE
CN
|  |  | 0710956 | Kosciusko |  | Kosciusko County | 2011-02-09 | CE
CN
|  |  | 0710957 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710958 |  | Manhard Consulting, Ltd. | West Lafayette | -339679.2083
|  |  | 0710959 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2008-04-02
|  |  | 0710960 | Pike |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0710961 |  | Quantum Spatial, Inc. | Auburn | -339679.2083
|  |  | 0710962 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0710963 | Howard | Dodd Title Corporation | Kokomo | 2010-05-31 | CN
|  |  | 0710964 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0710965 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0710966 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710967 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0710968 | Clark |  | Indiana Department of Natural Resources | 2010-03-03 | CE
CN
|  |  | 0710969 |  |  | Indiana Department of Transportation | 2008-09-04
|  |  | 0710970 | Various |  | Indiana Department of Transportation | 2009-02-11 | CE
CN
|  |  | 0710971 | LaPorte |  | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0710972 | Various |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0710973 | Various |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0710974 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-07-09
|  |  | 0710975 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-07-30
|  |  | 0710976 |  |  | Indiana Department of Transportation | 2008-05-31
|  |  | 0710977 | Orange |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
ROW
|  |  | 0710978 | Orange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
PE
ROW
UT
|  |  | 0710979 | Orange |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
ROW
UT
|  |  | 0710980 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 0710981 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 0710982 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
UT
|  |  | 0710983 | Vanderburgh | CGI | Vanderburgh County | 2010-01-13 | CE
CN
|  |  | 0710984 | Posey | GRL Engineers, Inc. | Mount Vernon | 2012-02-08 | CE
CN
PE
|  |  | 0710985 |  | Quantum Spatial, Inc. | Auburn | -339679.2083
|  |  | 0710986 | Dearborn |  | Aurora | 2011-01-12 | CE
CN
PE
|  |  | 0710987 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 0710988 | Wayne |  | Wayne County | 2009-05-06 | CE
CN
PE
|  |  | 0710989 | Elkhart | Farren Real Estate Services | Middlebury | 2012-09-12 | CE
CN
PE
|  |  | 0710990 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2017-02-08 | CE
CN
PE
ROW
|  |  | 0710991 | Hamilton | Another Test Company | Hamilton County | 2015-08-05 | CE
CN
|  |  | 0710992 | Hamilton | Another Test Company | Hamilton County | 2015-08-05 | CE
CN
PE
|  |  | 0710993 | Clark | Data Transfer Solutions, LLC | Jeffersonville | 2012-02-08 | CE
CN
PE
|  |  | 0710994 |  | Blood Hound, Inc. (former) | Delphi | -339679.2083
|  |  | 0710995 |  | John A. Doyle Associates, Inc. | Shipshewana | -339679.2083
|  |  | 0710996 | Marion | DCD Consulting LLC | Indianapolis | 2014-03-05 | CE
CN
PE
|  |  | 0710997 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2010-07-07 | CE
CN
|  |  | 0710998 |  | ASC Group, Inc. | Beech Grove | -339679.2083
|  |  | 0710999 | Decatur | Collier Transport Inc. | Greensburg | 2009-08-12 | CE
CN
|  |  | 0711000 | Harrison | B. L. A., Inc. | Harrison County | 2009-06-03 | CE
CN
|  |  | 0711001 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2010-11-10 | CE
CN
|  |  | 0711002 | Tippecanoe | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0711003 | Tippecanoe |  | Indiana Department of Transportation | 2008-04-02 | CE
CN
|  |  | 0711004 | Delaware | GS-IN P.C. | MPO - Muncie | -339679.2083 | CN
|  |  | 0711005 | Delaware | GS-IN P.C. | MPO - Muncie | -339679.2083 | CN
|  |  | 0711006 | Delaware | GS-IN P.C. | MPO - Muncie | -339679.2083 | CN
|  |  | 0711007 | Delaware | GS-IN P.C. | MPO - Muncie | -339679.2083 | CN
|  |  | 0711008 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0711009 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-12-10 | CE
CN
UT
|  |  | 0711010 | Crawford |  | Crawford County | -339679.2083 | CN
|  |  | 0711011 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0711012 | Dearborn |  | Indiana Department of Transportation | 2008-12-10 | CE
CN
|  |  | 0711013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0711014 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0711015 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0711016 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0711017 | Clark | Gregg A. Townsend | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 0711018 | Starke |  | Indiana Department of Natural Resources | 2011-01-12 | CE
CN
PE
ROW
|  |  | 0711019 |  |  | Indiana Department of Natural Resources | 2007-12-31
|  |  | 0711020 | White |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0711021 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0711022 | Kosciusko |  | Kosciusko County | 2009-02-27 | CE
CN
|  |  | 0711023 |  |  | La Porte | 2008-05-08
|  |  | 0711024 | Noble |  | Indiana Department of Transportation | 2009-02-27 | RR
|  |  |  | Various |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
RR
|  |  | 0711025 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0711026 |  |  | Indiana Department of Transportation | 2011-03-09
|  |  | 0711027 | Whitley |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0800001 | Lake |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0800002 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800003 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0800004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800005 | Orange |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800006 | Dubois |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800007 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0800008 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800009 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | -339679.2083 | PE
|  |  | 0800010 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2010-10-06 | CE
CN
|  |  | 0800011 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2009-05-06 | CN
|  |  | 0800012 | Monroe | Absolute Title Services, LLC | Monroe County | -339679.2083 | PE
|  |  | 0800013 | Pike | Home Equity Appraisals | Petersburg | 2009-11-04 | CE
CN
PE
|  |  | 0800014 | Monroe | Absolute Title Services, LLC | Bloomington | 2009-05-06 | CN
|  |  | 0800015 | Perry |  | Tell City | 2010-11-10 | CE
CN
PE
|  |  | 0800016 | Marion | DCD Consulting LLC | Other | -339679.2083 | PE
|  |  | 0800017 | Cass |  | Cass County | 2011-12-14 | CE
CN
PE
|  |  | 0800018 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-07-03 | CN
|  |  | 0800019 | Warrick |  | Newburgh | 2014-07-09 | CE
CN
PE
|  |  | 0800020 |  |  | Johnson County | -339679.2083
|  |  | 0800021 | Monroe |  | Other | 2011-02-09 | CE
CN
PE
UT
|  |  | 0800022 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0800023 | Cass | Eco Logic, LLC | Logansport | 2011-07-13 | CE
CN
|  |  | 0800024 | Madison | CE Solutions, Inc. | Elwood | 2012-11-29 | PE
|  |  | 0800025 | Hancock |  | Cumberland | 2016-12-14 | CE
CN
PE
ROW
|  |  | 0800026 |  |  | Bloomington | 2008-04-02
|  |  | 0800027 |  |  | Shelby County | -339679.2083
|  |  | 0800028 | Tippecanoe |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0800029 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800030 | Wells |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800031 | Grant |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
ROW
|  |  | 0800032 | White |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
ROW
|  |  | 0800033 |  | Lorenz Williams Clinton | Indiana Department of Transportation | -339679.2083
|  |  | 0800034 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800035 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800037 | Delaware |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0800038 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0800039 | Delaware |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0800040 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0800041 |  |  | Bloomington | 2009-05-06
|  |  | 0800042 | Allen |  | Indiana Department of Transportation | 2008-05-08 | CE
|  |  | 0800043 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0800044 | St. Joseph |  | South Bend | 2010-01-13 | CE
CN
|  |  | 0800045 | Elkhart | C Blair Enterprises, Inc. | Elkhart County | 2010-04-14 | CE
CN
RR
|  |  | 0800046 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2009-08-12 | CE
CN
|  |  | 0800047 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0800048 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 0800049 | Gibson |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
PE
ROW
|  |  | 0800050 | Pike |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800051 | Hamilton |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0800052 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2008-05-08
|  |  | 0800053 | St. Joseph |  | South Bend | 2010-01-13 | CE
CN
|  |  | 0800054 |  | C Blair Enterprises, Inc. | Elkhart County | -339679.2083
|  |  | 0800055 | Marion | Another Test Company | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0800056 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800057 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-11-06
|  |  | 0800058 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-11-06
|  |  | 0800059 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800060 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800061 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800062 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800063 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-11-06
|  |  | 0800064 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800065 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800066 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800067 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800068 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800069 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800070 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800071 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800072 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
UT
|  |  | 0800073 | Scott |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 0800074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800075 | Monroe |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
ROW
UT
|  |  | 0800076 | Bartholomew |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
ROW
|  |  | 0800077 | Jefferson |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
|  |  | 0800078 | Scott |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
UT
|  |  | 0800079 | Scott |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 0800080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800081 | Various |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800082 |  | Beacon Surveying and Engineering | Indiana Department of Transportation | -339679.2083
|  |  | 0800083 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800084 | Pike |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
RR
|  |  | 0800085 | Dubois |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0800086 | Posey |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0800087 | Knox |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
RR
|  |  | 0800088 | Vanderburgh | CGI | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0800089 | Delaware | GS-IN P.C. | MPO - Muncie | 2014-07-09 | CE
CN
PE
|  |  | 0800090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800091 | Dubois |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
|  |  | 0800092 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
RR
|  |  | 0800093 | Grant |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
|  |  | 0800094 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0800095 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800096 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800097 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800098 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800099 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0800100 | Marion | Another Test Company | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0800101 | Marion | Another Test Company | Indiana Department of Transportation | 2010-10-20 | CE
CN
|  |  | 0800102 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800103 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800104 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800105 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800106 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800107 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800108 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800109 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800110 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800111 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800112 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800115 | Putnam |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800116 |  | Archonsortium, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800118 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0800119 | Greene | Bonar Group, LLC | Indiana Department of Transportation | 2013-12-11 | CE
CN
RR
|  |  |  | Sullivan | Bonar Group, LLC | Indiana Department of Transportation | 2013-12-11 | CE
CN
RR
|  |  | 0800120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800121 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2012-10-03 | CE
CN
RR
|  |  | 0800122 | Dubois |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0800123 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
RR
|  |  | 0800124 | Greene | LFR, Inc. | Indiana Department of Transportation | 2016-04-20 | CE
CN
PE
RR
|  |  | 0800125 | Lawrence |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0800126 | Greene | LFR, Inc. | Indiana Department of Transportation | 2014-07-09 | CE
CN
RR
|  |  | 0800127 | Greene |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800129 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 0800130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800132 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
ROW
RR
|  |  | 0800133 | White | Afram Corporation | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 0800134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800135 | Howard | Dodd Title Corporation | Howard County | -339679.2083 | PE
|  |  | 0800136 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800138 | Huntington |  | Indiana Department of Transportation | 2010-02-10 | RR
|  |  |  | Various |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
RR
|  |  | 0800139 | Elkhart |  | Indiana Department of Transportation | 2010-12-08 | RR
|  |  |  | Various |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
|  |  | 0800140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800141 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0800142 | Allen |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0800143 | Allen |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 0800144 | Various |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0800145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800146 | Brown |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
ROW
|  |  | 0800147 | Brown |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
ROW
|  |  | 0800148 | Morgan |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
ROW
|  |  | 0800149 | Franklin |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  |  | Rush |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0800150 | Johnson |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 0800151 |  | IXOYE, Limited | Indiana Department of Transportation | 2008-07-16
|  |  | 0800152 | Johnson |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 0800153 | Allen |  | Indiana Department of Transportation | 2008-05-14 | CE
UT
|  |  | 0800154 | Grant |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
|  |  | 0800155 | Switzerland |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
UT
|  |  | 0800156 | Jackson |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
UT
|  |  | 0800157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800158 | Elkhart |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0800159 | Elkhart |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  |  | LaGrange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800161 | Wabash |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
ROW
|  |  | 0800162 | Huntington |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0800163 | Morgan |  | Indiana Department of Transportation | 2020-11-10 | PE
|  |  | 0800164 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800165 | Various |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0800166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800167 | Various |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0800168 | Kosciusko |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 0800169 | Elkhart |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0800170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800172 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800173 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800176 | Wabash |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  | 0800177 | Wayne |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0800178 | Jennings |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0800179 | Huntington |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800181 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800183 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0800184 | Various |  | Indiana Department of Transportation | 2009-05-31 | PE
|  |  | 0800185 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0800186 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-04-02
|  |  | 0800187 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800188 |  |  | Indiana Department of Natural Resources | 2009-08-12
|  |  | 0800189 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0800190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800191 | Wayne |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0800192 |  |  | Indiana Department of Natural Resources | 2010-12-08
|  |  | 0800193 |  |  | Indiana Department of Natural Resources | 2009-08-12
|  |  | 0800194 | Various |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0800195 |  |  | Indiana Department of Natural Resources | 2010-07-07
|  |  | 0800196 | Allen |  | Indiana Department of Transportation | 2009-06-24 | CN
PE
|  |  | 0800197 | Clark | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2012-03-07 | CE
CN
ROW
|  |  |  | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0800198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800199 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800200 | Henry |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
RR
|  |  | 0800201 | Bartholomew |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800202 |  | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800203 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2009-06-24 | CE
CN
RR
|  |  | 0800204 | Clark |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
ROW
|  |  |  | Washington |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
ROW
|  |  | 0800205 | Switzerland |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 0800206 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2013-01-16 | CE
CN
RR
|  |  | 0800207 | Rush |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0800208 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0800209 |  |  | Indiana Department of Transportation | 2008-05-08
|  |  | 0800210 | St. Joseph |  | St. Joseph County | -339679.2083 | CN
|  |  | 0800213 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
|  |  | 0800214 | LaPorte |  | LaPorte County | -339679.2083 | CN
PE
|  |  | 0800215 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800216 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800217 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0800218 |  |  | Westfield | -339679.2083
|  |  | 0800219 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
PE
RR
|  |  | 0800220 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
RR
|  |  | 0800221 | Allen |  | Indiana Department of Transportation | 2008-04-02 | CE
|  |  | 0800222 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0800223 | Porter |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
UT
|  |  | 0800224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800225 | Clark |  | MPO - Louisville | -339679.2083 | PE
|  |  | 0800226 |  | Cornerstone Civil Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800227 |  |  | Indiana Department of Transportation | 2008-08-06
|  |  | 0800228 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800229 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0800230 | Wells | Accidental Discoveries, LLC | Bluffton | 2012-08-08 | CE
CN
PE
ROW
RR
UT
|  |  | 0800231 |  | Holloway Engineering, LLC | Peru | -339679.2083
|  |  | 0800232 | Noble | Debbie L. Morris | Kendallville | 2009-05-06 | CE
CN
|  |  | 0800233 | Elkhart | Gandhi and Associates, Inc. | Nappanee | 2011-04-13 | CE
CN
PE
|  |  | 0800234 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-08-06 | CE
CN
ROW
UT
|  |  | 0800236 | Various |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0800237 | Various |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800238 | Various |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
|  |  | 0800239 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800240 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
RR
|  |  | 0800241 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0800242 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-04-28 | CN
|  |  | 0800243 |  | CTL Engineering of Indiana, Inc. | MPO - Fort Wayne | -339679.2083
|  |  | 0800244 |  |  | North Vernon | -339679.2083
|  |  | 0800245 | Newton | Advantage Appraisal Services | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800246 | Gibson | III FFC | Princeton | -339679.2083 | PE
|  |  | 0800247 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0800248 | Cass | Eco Logic, LLC | Logansport | 2011-07-13 | CE
CN
PE
ROW
|  |  | 0800249 | Jefferson |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800250 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 0800251 | Jackson |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
UT
|  |  | 0800252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800254 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800255 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800256 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2011-07-13 | CE
CN
ROW
UT
|  |  | 0800257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800258 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800259 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800260 | Grant |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0800261 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800262 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800263 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800265 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
ROW
|  |  | 0800267 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0800268 | Howard |  | Indiana Department of Transportation | 2010-04-14 | ROW
|  |  | 0800269 | LaPorte |  | Indiana Department of Transportation | 2014-03-12 | PE
|  |  | 0800270 | Huntington |  | Indiana Department of Transportation | 2015-04-15 | CE
CN
PE
|  |  | 0800271 | Huntington |  | Indiana Department of Transportation | 2015-04-15 | CE
CN
ROW
|  |  | 0800272 | White |  | Indiana Department of Transportation | 2021-03-01 | CN
PE
UT
|  |  | 0800273 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800274 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800275 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0800276 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0800277 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0800278 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0800279 | Decatur |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0800280 | Ripley |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 0800281 | Vigo | Bayswater Company, LLC | Terre Haute | 2009-08-12 | CE
CN
|  |  | 0800282 | Monroe |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
|  |  | 0800283 | Orange |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0800284 | Gibson |  | Indiana Department of Transportation | 2010-02-10 | PE
ROW
|  |  | 0800285 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
ROW
UT
|  |  | 0800286 | Orange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800287 | Orange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800288 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800289 | Orange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800290 | St. Joseph |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800291 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0800292 | St. Joseph |  | Indiana Department of Transportation | 2008-09-04 | CE
CN
|  |  | 0800293 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0800294 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800295 | Delaware | GS-IN P.C. | Muncie | 2017-04-05 | CE
CN
PE
|  |  | 0800296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800297 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800298 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800299 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800300 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800301 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800302 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800303 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800304 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-04-15
|  |  | 0800305 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800306 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-04-15
|  |  | 0800307 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800308 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-07-15
|  |  | 0800309 | Vigo | Bayswater Company, LLC | MPO - Terre Haute | 2008-11-19 | CE
CN
|  |  | 0800310 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800312 |  |  | Indiana Department of Transportation | 2008-08-20
|  |  | 0800313 |  |  | Indiana Department of Transportation | 2011-12-14
|  |  | 0800314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800315 | Allen |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0800316 |  | DCD Consulting LLC | Indiana Department of Transportation | 2012-05-31
|  |  | 0800317 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
PE
RR
|  |  | 0800318 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
RR
|  |  | 0800319 | Various |  | Indiana Department of Transportation | 2009-08-12 | CE
CN
|  |  | 0800320 | Floyd |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
|  |  | 0800321 | Scott |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
PE
|  |  | 0800322 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0800323 | Lake |  | Indiana Department of Transportation | 2009-05-27 | CE
|  |  | 0800324 |  |  | Indiana Department of Transportation | 2008-09-04
|  |  | 0800325 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800326 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800327 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800328 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800329 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800330 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800331 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0800332 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0800333 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800334 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800335 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800336 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800337 |  |  | Zionsville | 2008-07-09
|  |  | 0800338 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0800339 | Porter |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800340 | LaPorte |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800341 | Starke |  | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800342 | Delaware | GS-IN P.C. | Muncie | 2010-04-14 | CE
CN
|  |  | 0800343 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2013-08-07 | CE
CN
PE
ROW
|  |  | 0800344 | Henry | GeoSolutions, Inc. | New Castle | -339679.2083 | PE
|  |  | 0800345 | Randolph | Apex Consulting & Surveying, Inc. | Winchester | 2016-10-05 | CE
CN
PE
RR
|  |  | 0800346 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0800347 | Delaware | GS-IN P.C. | MPO - Muncie | -339679.2083 | CN
|  |  | 0800348 | Delaware | GRW Engineers, Inc. | MPO - Muncie | -339679.2083 | CN
|  |  | 0800349 | Delaware | GRW Engineers, Inc. | MPO - Muncie | -339679.2083 | CN
|  |  | 0800350 | Delaware | GRW Engineers, Inc. | MPO - Muncie | -339679.2083 | CN
|  |  | 0800351 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800352 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800353 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  | 0800354 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0800355 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800356 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800357 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0800358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800359 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800360 | Vigo | Bayswater Company, LLC | Vigo County | 2015-03-04 | CE
CN
ROW
|  |  | 0800361 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2008-07-09 | CE
CN
|  |  | 0800362 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800363 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800364 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800365 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
UT
|  |  | 0800366 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800367 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800368 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800369 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800371 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800372 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0800373 | Jackson |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  | 0800374 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800375 | Floyd |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  | 0800376 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2009-08-12 | CE
CN
|  |  | 0800377 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800378 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800381 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800382 | Shelby |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  | 0800383 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800384 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800386 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800387 | Jay | Hydrogeology, Inc. | Portland | 2013-09-11 | CE
CN
PE
|  |  | 0800388 | Steuben | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0800389 | Jackson |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0800390 |  |  | Indiana Department of Transportation | 2009-07-15
|  |  | 0800391 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800393 | Allen |  | Indiana Department of Transportation | 2008-09-19 | CE
|  |  | 0800394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800395 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-10-01 | CE
|  |  | 0800396 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800397 | Delaware |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0800398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800400 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0800401 | Hendricks | DCD Consulting LLC | Avon | -339679.2083 | RR
|  |  | 0800402 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0800403 |  | DCD Consulting LLC | MPO - Indianapolis | -339679.2083
|  |  | 0800404 | Hendricks | All About Pavements, Inc. | Brownsburg | 2012-05-02 | CE
CN
|  |  | 0800405 | Hendricks | DCD Consulting LLC | Avon | 2011-08-10 | CE
CN
PE
ROW
UT
|  |  | 0800406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800407 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0800408 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2009-11-04
|  |  | 0800409 |  | B. L. A., Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800410 |  |  | Indiana Department of Transportation | 2008-08-06
|  |  | 0800411 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2008-08-06
|  |  | 0800412 |  |  | Indiana Department of Transportation | 2008-07-09
|  |  | 0800414 | Hamilton |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0800415 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800416 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800417 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800418 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800419 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0800420 | Floyd |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0800421 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800422 |  | DCD Consulting LLC | Indiana Department of Transportation | 2016-08-03
|  |  | 0800423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800424 | Franklin |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 0800425 |  |  | Indiana Department of Transportation | 2009-09-24
|  |  | 0800426 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0800427 | Various |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0800428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800429 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800430 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
ROW
|  |  | 0800431 |  |  | Indiana Department of Transportation | 2009-10-07
|  |  | 0800432 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800433 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0800434 | Jasper |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800435 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2008-11-19 | CE
CN
|  |  | 0800436 |  | Eco Logic, LLC | Indiana Department of Transportation | 2010-05-12
|  |  | 0800437 |  |  | Indiana Department of Transportation | 2010-05-12
|  |  | 0800438 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800439 | Starke |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800440 | Jasper |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800441 |  |  | Indiana Department of Transportation | 2008-11-19
|  |  | 0800442 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-11-19
|  |  | 0800443 | Monroe | Absolute Title Services, LLC | Bloomington | 2010-10-06 | CE
CN
|  |  | 0800444 | Boone |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 0800445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800446 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800447 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0800448 | Hamilton | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  |  | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 0800449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800450 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2008-08-06
|  |  | 0800451 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800452 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800453 | Lake | Huff & Huff, Inc. | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  |  | Various | Huff & Huff, Inc. | Indiana Department of Transportation | 2015-02-04 | CE
|  |  | 0800454 |  |  | Indiana Department of Transportation | 2008-08-06
|  |  | 0800455 |  |  | Winchester | 2008-07-09
|  |  | 0800456 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | 2009-05-31 | CN
|  |  | 0800457 | Porter | Huff & Huff, Inc. | MPO - Northwest | 2009-05-31 | CN
|  |  | 0800458 |  | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083
|  |  | 0800459 | LaPorte |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
RR
|  |  |  | Porter |  | Indiana Department of Transportation | 2016-04-06 | PE
RR
|  |  | 0800460 |  |  | Crawfordsville | -339679.2083
|  |  | 0800461 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2008-09-04
|  |  | 0800462 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800463 |  |  | Indiana Department of Transportation | 2008-11-19
|  |  | 0800464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800466 | Marion | Another Test Company | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 0800467 |  |  | Indiana Department of Transportation | 2011-11-16
|  |  | 0800468 |  |  | Indiana Department of Transportation | 2010-11-10
|  |  | 0800469 |  |  | Indiana Department of Transportation | 2011-11-16
|  |  | 0800470 |  |  | Indiana Department of Transportation | 2011-11-16
|  |  | 0800471 |  |  | Indiana Department of Transportation | 2011-11-16
|  |  | 0800472 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800473 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800474 | LaPorte | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
RR
|  |  |  | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2016-04-06 | PE
|  |  | 0800475 | Kosciusko |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0800476 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800477 | Boone |  | Indiana Department of Transportation | 2010-11-24 | CE
CN
PE
RR
|  |  | 0800478 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800479 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800481 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0800482 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0800483 |  |  | Indiana Department of Transportation | 2009-09-24
|  |  | 0800484 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800485 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800486 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800487 | Spencer |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
ROW
|  |  | 0800488 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800489 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800491 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0800492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800495 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800497 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800498 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800499 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0800500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800501 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800503 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0800504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800507 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0800508 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 0800509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800510 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800512 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800514 | Various |  | Indiana Department of Transportation | 2008-07-15 | CN
PE
|  |  | 0800515 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0800516 | Bartholomew |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0800517 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0800518 | Various |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 0800519 | Various |  | Indiana Department of Transportation | 2013-09-09 | PE
|  |  | 0800520 | Various |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 0800521 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800522 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800523 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800524 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800525 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800526 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800527 | Benton | Action Title and Escrow, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800528 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800529 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800530 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800531 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800532 | Tipton |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800533 | Shelby |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800534 | Union |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800535 | Union |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800536 | Union |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800537 | Union |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800538 | Lake | Compliance Consulting Service, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800539 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800540 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800542 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800543 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800544 | St. Joseph |  | Indiana Department of Transportation | 2016-05-31 | CN
RR
|  |  | 0800545 | St. Joseph |  | Indiana Department of Transportation | 2016-05-31 | CN
RR
|  |  | 0800546 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800547 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800548 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800549 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800550 | Carroll |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800551 | Carroll |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800552 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800553 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800554 | Johnson |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800555 | Knox | HOH Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800556 | Knox | HOH Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800557 | Knox | HOH Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800558 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0800559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800560 | Daviess | CBRE, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800561 |  |  | Indiana Department of Transportation | 2010-01-13
|  |  | 0800562 | Jay |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0800563 | Dubois |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800564 |  |  | Indiana Department of Transportation | 2010-01-13
|  |  | 0800565 | Daviess | AMEC E&I, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800566 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0800567 | Daviess | Houseal Lavigne Associates | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800568 | Dubois |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800569 | Dubois |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800570 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2011-01-12
|  |  | 0800571 | Knox | HOH Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800572 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2011-01-12
|  |  | 0800573 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0800574 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800575 | Various |  | Indiana Department of Transportation | 2014-09-09 | PE
|  |  | 0800576 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800577 |  |  | Indiana Department of Transportation | 2010-12-08
|  |  | 0800578 | Gibson |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
|  |  | 0800579 | Knox |  | Indiana Department of Transportation | 2023-01-19 | PE
ROW
UT
|  |  | 0800580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800581 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0800583 | Howard |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
ROW
|  |  | 0800584 | Various |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 0800585 | Various |  | Indiana Department of Transportation | 2014-04-29 | PE
|  |  | 0800586 | Various |  | Indiana Department of Transportation | 2016-04-29 | PE
|  |  | 0800587 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2011-10-13
|  |  | 0800588 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800589 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800592 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800594 |  | DCD Consulting LLC | Indiana Department of Transportation | 2010-03-03
|  |  | 0800595 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800596 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800597 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800598 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800599 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800600 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800601 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800602 |  | DCD Consulting LLC | Indiana Department of Transportation | 2011-01-12
|  |  | 0800603 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800604 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800605 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800606 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800607 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800608 |  | CoCal Consulting, LLC | Greenfield | -339679.2083
|  |  | 0800609 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800611 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0800612 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800613 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800614 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800615 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800616 |  |  | Indiana Department of Transportation | 2011-03-11
|  |  | 0800617 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800618 |  | DCD Consulting LLC | Indiana Department of Transportation | 2011-01-12
|  |  | 0800619 |  | DCD Consulting LLC | Indiana Department of Transportation | 2012-01-11
|  |  | 0800620 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800621 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800622 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800624 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800625 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800626 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800627 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800628 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800631 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 0800632 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 0800633 |  | DCD Consulting LLC | Indiana Department of Transportation | 2012-01-11
|  |  | 0800634 |  |  | Remington | 2009-05-31
|  |  | 0800635 | Bartholomew |  | Indiana Department of Transportation | 2010-03-03 | CE
CN
|  |  | 0800636 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0800637 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0800638 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0800639 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0800640 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0800641 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
RR
|  |  | 0800642 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
RR
|  |  | 0800643 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0800644 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800645 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800646 | Porter |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 0800647 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800648 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800649 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800650 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-11-12
|  |  | 0800651 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800652 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0800653 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800654 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0800655 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800656 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800657 | Porter |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
RR
|  |  | 0800658 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800659 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2008-11-12 | CN
PE
|  |  | 0800660 | Porter |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
RR
|  |  | 0800661 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800662 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800663 |  |  | Indiana Department of Transportation | 2008-11-12
|  |  | 0800664 | LaPorte |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
RR
|  |  |  | Porter |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0800665 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 0800666 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800667 |  | DCD Consulting LLC | Indiana Department of Transportation | 2012-07-11
|  |  | 0800668 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 0800669 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800670 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800672 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800673 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800674 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800675 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800676 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800678 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800679 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800680 |  | DCD Consulting LLC | Indiana Department of Transportation | 2013-01-16
|  |  | 0800681 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800682 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800683 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800684 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800685 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800686 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800687 |  |  | Indiana Department of Transportation | 2013-07-10
|  |  | 0800688 |  |  | Indiana Department of Transportation | 2013-07-10
|  |  | 0800689 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800691 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800692 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800693 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 0800694 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 0800695 |  | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05
|  |  | 0800696 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-03-18
|  |  | 0800697 |  | DCD Consulting LLC | Indiana Department of Transportation | 2014-07-09
|  |  | 0800698 |  |  | Indiana Department of Transportation | 2014-07-09
|  |  | 0800699 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800700 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800701 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800702 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800703 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 0800704 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800706 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800707 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800708 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 0800709 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 0800710 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800711 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800712 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800713 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800714 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800715 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800716 | Parke |  | Parke County | 2013-04-03 | CE
CN
PE
ROW
|  |  | 0800717 | Hendricks |  | Hendricks County | 2014-08-06 | CE
CN
RR
|  |  | 0800718 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0800719 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0800720 | LaPorte |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0800721 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2009-07-15 | CE
CN
UT
|  |  | 0800722 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2009-07-15 | CE
UT
|  |  | 0800723 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2009-03-25
|  |  | 0800724 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2009-03-25
|  |  | 0800725 | Elkhart |  | Elkhart County | 2014-09-10 | CE
CN
PE
|  |  | 0800726 | Grant |  | Grant County | 2011-12-14 | CE
CN
PE
ROW
|  |  | 0800727 |  |  | Kosciusko County | -339679.2083
|  |  | 0800728 | Wabash |  | Wabash County | 2011-10-13 | CE
CN
PE
|  |  | 0800729 | Crawford |  | Crawford County | 2016-03-02 | CE
CN
PE
ROW
RR
UT
|  |  | 0800730 |  |  | Lawrence County | -339679.2083
|  |  | 0800731 |  |  | Spencer County | -339679.2083
|  |  | 0800732 | Warrick |  | Warrick County | 2013-05-01 | CE
CN
PE
|  |  | 0800733 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800734 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800735 | Warrick |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
ROW
|  |  | 0800736 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800737 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800738 |  | DCD Consulting LLC | Indiana Department of Transportation | 2008-12-10
|  |  | 0800739 |  |  | Cumberland | -339679.2083
|  |  | 0800740 | Lake |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Porter |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0800741 | Various |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0800742 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800743 | Noble |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0800744 | Allen |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  |  | Dekalb |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  |  | Noble |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0800745 | Floyd |  | New Albany | 2017-05-10 | CE
CN
PE
ROW
|  |  | 0800746 | Floyd |  | Floyd County | 2011-08-10 | CE
CN
|  |  | 0800747 | Grant |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
|  |  | 0800748 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800749 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800751 | Gibson | HNTB Indiana, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
RR
|  |  | 0800752 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800753 | Spencer |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
RR
|  |  | 0800754 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 0800755 |  | I. T. Business Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0800756 |  | CMF Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800757 |  | JJR, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800758 | Spencer | Clark Dietz, Inc. | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
UT
|  |  | 0800759 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800761 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800762 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800763 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800764 |  | CEI Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800766 | Spencer |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0800767 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800768 | Monroe |  | Monroe County | 2013-07-10 | CE
CN
PE
ROW
UT
|  |  | 0800769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800770 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800771 |  |  | Indiana Department of Transportation | 2009-11-19
|  |  | 0800772 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2011-09-08 | CN
|  |  |  | Tipton | Dodd Title Corporation | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0800773 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2013-08-23 | RR
|  |  | 0800774 | Jefferson | Engineering Resources, Inc. | Jefferson County | 2013-04-03 | CE
CN
PE
|  |  | 0800775 | Porter |  | Porter County | 2011-09-08 | CE
CN
|  |  | 0800776 | Morgan |  | Morgan County | 2011-01-12 | CE
CN
PE
|  |  | 0800777 | Carroll |  | Carroll County | 2012-07-11 | CE
CN
PE
|  |  | 0800778 | Johnson |  | Johnson County | 2013-07-10 | CE
CN
PE
|  |  | 0800779 | Marshall |  | Marshall County | 2011-05-11 | CE
CN
|  |  | 0800780 | Owen |  | Owen County | -339679.2083 | PE
|  |  | 0800781 | Brown |  | Brown County | -339679.2083 | PE
|  |  | 0800782 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800783 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800784 |  | American Resources Group, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 0800785 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800786 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800787 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800788 |  | Collins Engineers Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 0800789 | Greene |  | Greene County | 2012-02-08 | CE
CN
PE
|  |  | 0800790 |  | Foresight Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800791 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2009-02-11 | CE
PE
|  |  | 0800792 | Spencer |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0800793 | Spencer |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 0800794 | Spencer |  | Indiana Department of Transportation | 2010-03-23 | CE
CN
|  |  | 0800795 | Gibson | III FFC | Indiana Department of Transportation | 2012-03-07 | CE
CN
ROW
|  |  | 0800796 | Warrick |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800797 | Warrick |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800798 | Warrick |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800799 | Lawrence |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
|  |  | 0800800 | Greene |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
|  |  | 0800801 | Crawford | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  |  | Orange | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  |  | Perry | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0800802 | Orange |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
ROW
|  |  | 0800803 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800804 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 0800805 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800806 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800807 | Warrick |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
ROW
|  |  | 0800808 | Perry |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 0800809 | Perry |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 0800810 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800811 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
UT
|  |  | 0800812 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800813 | Martin |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 0800814 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800815 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800816 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800817 | Gibson |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0800818 | Greene | Dan Moore Real Estate Services, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
RR
|  |  | 0800819 |  | Global Land Surveying, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800820 | Posey |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0800821 | Posey |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0800822 |  | CEI Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800823 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 0800824 | Daviess | Home Equity Appraisals | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 0800825 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800826 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800829 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800830 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800831 | Tippecanoe |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0800832 | Vermillion | BA Martin Architects, PC | Indiana Department of Transportation | 2009-06-10 | PE
|  |  | 0800833 |  | BA Martin Architects, PC | Indiana Department of Transportation | 2009-06-10
|  |  | 0800834 | Warren |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
ROW
|  |  | 0800835 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800836 | Benton |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 0800837 | Hendricks |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
ROW
UT
|  |  | 0800838 | Clay |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
ROW
|  |  | 0800839 | Benton |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
|  |  | 0800840 | Fountain |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
ROW
|  |  | 0800841 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800842 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800843 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800844 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800845 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800846 | Clay |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
UT
|  |  | 0800847 | Montgomery |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
ROW
|  |  | 0800848 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800849 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2008-07-30
|  |  | 0800850 | Fountain |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800851 | Putnam |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
ROW
|  |  | 0800852 | Putnam |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 0800853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800854 | Fountain |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
|  |  | 0800855 | Fountain |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
ROW
|  |  | 0800856 | Putnam |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
ROW
|  |  | 0800857 |  |  | Indiana Department of Transportation | 2009-09-10
|  |  | 0800858 | Owen |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 0800859 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800860 | Owen |  | Indiana Department of Transportation | 2008-07-18 | CE
CN
|  |  | 0800861 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800862 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800863 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0800864 |  | GRW Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800865 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800866 |  | MBP Appraisals, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800867 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800869 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800870 | Clay |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 0800871 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800872 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800873 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800874 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800875 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
PE
ROW
|  |  | 0800876 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 0800877 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800878 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800879 | Fountain |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 0800880 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800881 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800882 | Putnam |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 0800883 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800884 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800885 | Tippecanoe |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
UT
|  |  | 0800886 | Hendricks |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
ROW
|  |  | 0800887 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800889 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800890 | Benton |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
ROW
|  |  | 0800891 | Benton |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
ROW
|  |  | 0800892 | Fayette | EHI Consultants, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
RR
|  |  |  | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 0800893 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 0800894 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800895 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800897 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800898 | Madison |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0800899 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800901 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800902 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800903 | Vermillion | Archaeology and Geomorphology Services | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800904 | Warren |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
|  |  | 0800905 | Warren |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 0800906 | Tippecanoe |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  | 0800907 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800908 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800909 | Tippecanoe |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
ROW
|  |  | 0800910 | Clay |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
ROW
|  |  | 0800911 | Vigo |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 0800912 | Vigo |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 0800913 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800914 | White |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 0800915 | Wabash |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
RR
|  |  | 0800916 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2014-12-17 | PE
|  |  | 0800917 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2014-12-17
|  |  | 0800918 | Morgan |  | Indiana Department of Transportation | 2008-08-01 | CE
CN
|  |  | 0800919 | Clinton |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
ROW
|  |  | 0800920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800921 | Benton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800922 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
RR
|  |  | 0800923 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800924 | Owen |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
ROW
|  |  | 0800925 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800926 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800927 | Boone |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800928 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0800929 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0800930 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800931 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800932 | Wayne |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 0800933 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800934 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800935 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800937 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
RR
|  |  | 0800938 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800939 | Allen |  | Indiana Department of Transportation | 2010-01-27 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2010-01-27 | CE
CN
|  |  | 0800940 | Wayne |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
ROW
|  |  | 0800941 | Whitley |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0800942 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800943 | Howard |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  |  | Jay |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2013-04-03 | CE
|  |  | 0800944 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800945 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800946 | Madison |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 0800947 |  |  | Indiana Department of Transportation | 2008-08-06
|  |  | 0800948 | Delaware |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 0800949 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0800950 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0800951 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0800952 | Franklin |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0800953 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800954 | Various |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 0800955 | Henry |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0800956 | Hancock |  | Indiana Department of Transportation | 2013-12-18 | CE
CN
|  |  | 0800957 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
ROW
|  |  | 0800958 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 0800959 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800960 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800961 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2021-01-01 | ROW
|  |  | 0800962 | Wayne |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0800963 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0800964 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
|  |  | 0800965 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0800966 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
RR
|  |  | 0800967 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
RR
|  |  | 0800968 | Wells |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0800969 | Grant |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
|  |  | 0800970 | Grant |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0800971 | Various |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0800972 | Various |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0800973 | Blackford |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
RR
|  |  | 0800974 | Dekalb |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  |  | Noble |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  | 0800975 | Huntington |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0800976 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
RR
|  |  | 0800977 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 0800978 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800979 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
RR
|  |  | 0800980 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 0800981 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800982 | Blackford |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  |  | Wells |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0800983 | Noble |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 0800984 | Allen |  | Indiana Department of Transportation | 2009-02-27 | CE
CN
|  |  | 0800985 | Various |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 0800986 | Wells |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0800987 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800988 |  | Appraisal Office of Central Indiana | Indiana Department of Transportation | -339679.2083
|  |  | 0800989 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800990 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0800991 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800992 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0800993 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0800994 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 0800995 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800996 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800997 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0800998 |  | Bowman, Barrett & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0800999 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801001 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801002 | Randolph |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0801003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801004 | Delaware | IXOYE, Limited | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  |  | Jay | IXOYE, Limited | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 0801005 |  | Maten (Bob) Gabor Gerdenich II | Indiana Department of Transportation | -339679.2083
|  |  | 0801006 |  | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | -339679.2083
|  |  | 0801007 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801008 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801009 | Hamilton | Appraising Indiana, LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
RR
|  |  | 0801010 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0801011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801012 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0801013 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0801014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801015 | Cass |  | Cass County | 2010-05-26 | CE
CN
RR
UT
|  |  | 0801016 | LaPorte |  | Michigan City | 2010-04-14 | CE
CN
RR
|  |  | 0801017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801018 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801022 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801023 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801024 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801025 | Various |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0801026 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801027 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0801028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801029 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801032 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0801033 | Marion |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 0801034 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0801035 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0801036 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0801037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801038 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0801039 | Porter |  | Indiana Department of Transportation | 2009-04-24 | CE
CN
|  |  | 0801040 | Pulaski |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0801041 | Jasper |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0801042 | Jasper |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0801043 | Lake |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0801044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801045 |  |  | Indiana Department of Transportation | 2015-09-02
|  |  | 0801046 |  |  | Indiana Department of Transportation | 2015-09-02
|  |  | 0801047 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0801048 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801049 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801051 |  |  | Indiana Department of Transportation | 2008-08-12
|  |  | 0801052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801053 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2013-05-31 | ROW
|  |  | 0801054 | Morgan |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
|  |  | 0801055 | Hendricks |  | Hendricks County | 2015-05-07 | CE
CN
|  |  | 0801056 | Hendricks |  | Hendricks County | 2015-05-07 | CE
CN
RR
|  |  | 0801057 | Hendricks |  | Hendricks County | 2015-05-07 | CE
CN
|  |  | 0801058 | Hendricks |  | Hendricks County | 2015-05-07 | CE
CN
|  |  | 0801059 | Monroe | Absolute Title Services, LLC | Monroe County | 2016-12-14 | CE
CN
UT
|  |  | 0801060 | Monroe | Absolute Title Services, LLC | Monroe County | 2015-04-01 | CE
CN
UT
|  |  | 0801061 | Lake | ABt SRBI | Indiana Department of Transportation | 2009-02-11 | CN
[5 empty] | ABt SRBI | Indiana Department of Transportation | 2009-02-11
|  |  | 0801062 | Union |  | Wayne County | 2014-11-13 | CN
|  |  |  | Wayne |  | Wayne County | 2014-11-13 | CE
CN
PE
|  |  | 0801063 | Henry |  | Henry County | 2012-08-08 | CE
CN
PE
|  |  |  | Wayne |  | Henry County | 2012-08-08 | CE
CN
|  |  | 0801064 | Hancock |  | Hancock County | 2013-08-07 | CE
CN
PE
UT
|  |  | 0801065 | Madison |  | Madison County | 2013-04-03 | CE
CN
PE
|  |  | 0801066 | Vigo |  | Indiana Department of Transportation | 2008-08-15 | CE
CN
|  |  | 0801067 |  |  | Lawrence County | -339679.2083
|  |  | 0801068 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2008-11-19
|  |  | 0801069 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801070 |  |  | Brownstown | -339679.2083
|  |  | 0801071 | Vigo |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
UT
|  |  | 0801072 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2008-07-30 | PE
|  |  | 0801073 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0801074 | Tippecanoe | Manhard Consulting, Ltd. | Tippecanoe County | -339679.2083 | PE
|  |  | 0801075 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0801076 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0801077 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0801078 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0801079 | Jennings |  | Indiana Department of Transportation | 2012-04-04 | PE
|  |  |  | Ripley |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
ROW
|  |  | 0801080 | Tippecanoe |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0801081 | Tippecanoe |  | Indiana Department of Transportation | 2008-09-04 | CE
|  |  | 0801082 | Marion |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  | 0801083 | Randolph |  | Randolph County | -339679.2083 | CN
|  |  | 0801084 | Porter |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0801085 | Steuben |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0801086 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Hancock |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Henry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Morgan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Putnam |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Vigo |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Wayne |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0810002 | Miami |  | Miami County | -339679.2083 | CN
|  |  | 0810003 | Marion | DCD Consulting LLC | Indianapolis | 2009-08-12 | CE
CN
|  |  | 0810004 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0810005 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0810006 | Carroll |  | Carroll County | -339679.2083 | CN
|  |  | 0810007 | Cass | Eco Logic, LLC | Logansport | -339679.2083 | PE
|  |  | 0810008 | Spencer |  | Indiana Department of Transportation | 2009-07-22 | PE
|  |  | 0810009 |  |  | Indiana Department of Transportation | 2008-12-10
|  |  | 0810010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810012 | Vanderburgh | CGI | Evansville | 2009-05-06 | CN
|  |  | 0810013 | Spencer |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
ROW
UT
|  |  | 0810014 | Owen |  | Owen County | -339679.2083 | PE
|  |  | 0810015 | Spencer |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0810016 |  |  | Dearborn County | -339679.2083
|  |  | 0810017 | Marion |  | Indiana Department of Transportation | 2009-10-07 | CE
CN
|  |  | 0810018 | Clark |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  |  | Jackson |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  | 0810019 | Various |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
|  |  | 0810020 | Various |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810021 | Various | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2012-05-31 | CN
|  |  | 0810022 | Boone |  | Boone County | 2014-05-08 | CE
CN
PE
ROW
UT
|  |  | 0810023 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810024 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810025 |  |  | Indiana Department of Transportation | 2009-02-11
|  |  | 0810026 | Boone |  | Boone County | -339679.2083 | CN
|  |  | 0810027 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0810028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810029 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0810030 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0810031 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0810032 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  |  | Jackson | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  |  | Johnson | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  |  | Shelby | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2010-05-19 | CE
CN
|  |  | 0810033 | Various |  | Indiana Department of Transportation | 2009-01-14 | CE
CN
|  |  | 0810034 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0810035 | Various |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0810036 |  |  | Indiana Department of Transportation | 2011-03-09
|  |  | 0810037 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0810038 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810039 | Various |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 0810040 | Lake | Karen | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0810041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810042 | Marshall |  | Indiana Department of Transportation | 2010-01-13 | CE
CN
|  |  | 0810043 | Vanderburgh | CGI | Evansville | 2009-09-10 | CE
CN
|  |  | 0810044 | St. Joseph | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2010-01-13 | CE
CN
|  |  | 0810045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810047 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0810048 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0810049 |  | Michael Baker International, Inc. | Indiana Department of Transportation | 2009-10-07
|  |  | 0810050 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-05-31 | PE
ROW
|  |  | 0810051 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-05-31 | PE
ROW
|  |  | 0810052 | Starke |  | Starke County | 2014-05-08 | CE
CN
PE
ROW
|  |  | 0810053 | Warrick |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
|  |  | 0810054 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0810055 |  |  | Indiana Department of Transportation | 2010-05-31
|  |  | 0810056 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810057 |  |  | Steuben County | -339679.2083
|  |  | 0810058 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810059 | Various |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
RR
|  |  |  | Whitley |  | Indiana Department of Transportation | 2012-01-11 | RR
|  |  | 0810060 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
ROW
UT
|  |  | 0810061 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 0810062 |  | Major Engineering & Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0810063 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0810064 |  |  | Knox County | -339679.2083
|  |  | 0810065 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810067 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810068 | Clark |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0810069 | Johnson |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810070 | Johnson |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810071 | Clark |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0810072 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810073 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810074 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810075 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810076 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810077 | Johnson |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810078 | Johnson |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810079 | Jackson |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0810080 | Jackson |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0810081 | Johnson |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810082 | Shelby |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810083 | Franklin |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810084 | Jackson |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0810085 | Bartholomew |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810086 | White |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810087 | Carroll |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810088 | Starke |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810089 | Newton |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810090 | Jasper |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810091 | Porter |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810092 | St. Joseph |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810093 |  |  | Indiana Department of Transportation | 2009-09-10
|  |  | 0810094 | Steuben | ABt SRBI | Angola | 2009-05-06 | CE
CN
|  |  | 0810095 | Daviess |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
ROW
|  |  | 0810096 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 0810097 | LaGrange |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  | 0810098 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 0810099 | Adams |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  |  | Jay |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0810100 | Huntington |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  |  | Miami |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  |  | Wabash |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
RR
|  |  | 0810101 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810102 | LaGrange | Duesler Realty House | LaGrange County | 2010-07-07 | CE
CN
|  |  | 0810103 | Kosciusko | Mackie Consultants, LLC | Kosciusko County | 2011-07-13 | CE
CN
PE
ROW
|  |  | 0810104 | Steuben |  | Steuben County | 2015-02-04 | CE
CN
PE
ROW
|  |  | 0810105 | Vanderburgh |  | University of Southern Indiana | 2012-10-11 | CE
CN
|  |  | 0810106 | Fayette | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083 | PE
|  |  | 0810107 | Rush |  | Rush County | -339679.2083 | CN
PE
|  |  | 0810108 | Various |  | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0810109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810110 | Various |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 0810111 | Various |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0810112 | Allen |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
RR
|  |  | 0810113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810115 | Steuben |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
ROW
UT
|  |  | 0810116 | Dekalb |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
ROW
|  |  | 0810117 | Various |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 0810118 | Various |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 0810119 | Sullivan |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810120 | Greene |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810121 | Greene |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810122 | Greene |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810123 | Warrick |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810124 | Crawford |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Warrick |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810125 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0810126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810127 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2012-05-31 | CN
|  |  | 0810128 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2015-03-03 | CN
OT
|  |  | 0810129 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-03-03 | OT
|  |  | 0810130 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2017-05-31 | CN
|  |  | 0810131 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-05-31 | CN
|  |  | 0810132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810135 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810136 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810138 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810139 | Carroll |  | Carroll County | -339679.2083 | PE
|  |  | 0810140 | Marshall |  | Marshall County | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0810141 | Delaware | CPS Acquisitions, LLC | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810142 | Delaware | CPS Acquisitions, LLC | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810143 | Hancock |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810146 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810148 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810149 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810150 | Various |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 0810151 | White |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 0810152 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810153 |  |  | Indiana Department of Transportation | 2012-11-15
|  |  | 0810154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810155 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 0810156 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 0810157 | Various |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0810158 | Various |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 0810159 | Various |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 0810160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810161 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810162 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810163 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810164 | Various |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 0810165 | Various |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 0810166 | Various |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 0810167 | Clay |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 0810168 | Various |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 0810169 | Various |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
ROW
|  |  | 0810170 |  |  | Indiana Department of Transportation | 2012-03-07
|  |  | 0810171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810172 | Cass |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
PE
|  |  | 0810173 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810174 | Shelby |  | Shelbyville | 2009-07-01 | CN
|  |  | 0810175 | Boone |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810176 | Boone |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810177 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0810178 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0810179 | Wayne |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810180 | Madison |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810181 | Madison |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810182 | Hamilton |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810183 | Hamilton |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810184 | Delaware |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810185 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0810186 | Henry |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810187 | Hancock |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810188 | Hancock |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810189 | Allen |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810190 | Allen |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810191 | Grant |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810192 | Kosciusko |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810193 | Wabash |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810194 | Wabash |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810195 | Noble |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810196 | Wabash |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810197 | Whitley |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810198 | Whitley |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810199 | Allen |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810200 | Steuben |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810201 | Floyd |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0810202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810205 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810206 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810207 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810208 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810211 | Putnam |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810212 | Montgomery |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810213 | Putnam |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810214 | Putnam |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810215 | Hendricks |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810216 | Hendricks |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810217 | Marion | All About Pavements, Inc. | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810218 | Marion | All About Pavements, Inc. | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0810219 | Grant |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
PE
|  |  | 0810220 | Grant |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 0810221 | Dekalb | American Engineers, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 0810222 | Gibson |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
UT
|  |  | 0810223 | Allen |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2013-12-11 | CE
|  |  | 0810224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810226 | Grant |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0810227 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0810228 | Whitley |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  | 0810229 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810230 | Blackford | Fusion by Design, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
RR
|  |  | 0810231 | Steuben |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
|  |  | 0810232 | Tippecanoe |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
ROW
|  |  | 0810233 | Adams |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 0810234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810240 | Steuben |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0810241 | Grant |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
ROW
RR
|  |  | 0810242 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810243 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810244 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810245 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810246 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 0810247 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810248 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0810249 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2012-05-31
|  |  | 0810250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810251 | Hamilton |  | Hamilton County | -339679.2083 | CN
|  |  | 0810252 | Madison |  | Summitville | 2011-11-30 | CE
CN
PE
|  |  | 0810253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810254 | Warren |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0810255 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810258 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810259 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810263 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0810264 | Floyd |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0810265 |  |  | Indiana Department of Transportation | 2009-01-14
|  |  | 0810266 |  |  | Indiana Department of Transportation | 2009-02-11
|  |  | 0810267 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2014-12-10 | CE
CN
PE
|  |  | 0810268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810271 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2014-02-12 | CE
CN
PE
|  |  | 0810272 | Clark |  | MPO - Louisville | -339679.2083 | PE
|  |  | 0810273 | Knox |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 0810274 | Warrick |  | Warrick County | 2013-05-01 | CE
CN
|  |  | 0810275 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 0810276 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810277 | Marion | Another Test Company | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0810278 | Ripley | Lonco, Inc. | Indiana Department of Transportation | 2010-11-10 | CE
CN
PE
|  |  | 0810279 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2009-07-15
|  |  | 0810280 | Clark | Data Transfer Solutions, LLC | Jeffersonville | 2017-04-05 | CN
PE
ROW
RR
|  |  | 0810281 | Hendricks |  | Avon | 2009-08-12 | CE
CN
|  |  | 0810282 |  |  | Lawrence County | -339679.2083
|  |  | 0810283 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 0810284 | LaPorte |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 0810285 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0810286 | Putnam |  | Greencastle | 2016-02-03 | CE
CN
PE
|  |  | 0810287 | Hamilton |  | Hamilton County | 2014-05-08 | CE
CN
|  |  | 0810288 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2012-10-11 | CE
CN
PE
ROW
|  |  | 0810289 | Hamilton |  | Hamilton County | 2011-05-11 | CE
CN
|  |  | 0810290 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0810291 | Dearborn |  | Indiana Department of Transportation | 2009-10-07 | CE
CN
|  |  | 0810292 | Dearborn |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0810293 | Porter | Huff & Huff, Inc. | Portage | 2011-01-12 | CE
CN
PE
|  |  | 0810294 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0810295 | Porter | Leitner and Associates, Inc. | Valparaiso | 2013-03-06 | CE
CN
PE
ROW
|  |  | 0810296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810297 | Gibson |  | Indiana Department of Transportation | 2010-05-31 | PE
ROW
|  |  |  | Greene |  | Indiana Department of Transportation | 2010-05-31 | PE
ROW
|  |  | 0810298 | Porter | Huff & Huff, Inc. | Portage | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0810299 | Lake | Compliance Consulting Service, Inc. | Griffith | 2014-04-02 | CE
CN
PE
ROW
|  |  | 0810300 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 0810301 |  | Courtland Title & Escrow, Inc. | Lake County | -339679.2083
|  |  | 0810302 | LaPorte | Farah and Sons, Inc. | Michigan City | 2012-05-02 | CE
CN
PE
ROW
|  |  | 0810303 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 0810304 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 0810305 |  |  | Indiana Department of Transportation | 2010-08-04
|  |  | 0810306 |  |  | Indiana Department of Transportation | 2011-08-10
|  |  | 0810307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810308 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810309 | Allen |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  |  | Whitley |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0810310 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0810311 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2009-05-06
|  |  | 0810312 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810313 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810314 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810315 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810316 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810317 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810318 |  |  | Monticello | -339679.2083
|  |  | 0810319 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 0810320 |  | Fugro Roadware, Inc. | White County | -339679.2083
|  |  | 0810321 | Vigo |  | Vigo County | -339679.2083 | CN
|  |  | 0810322 | Marion | ASC Group, Inc. | Beech Grove | 2012-09-12 | CE
CN
|  |  | 0810323 | Marion | DCD Consulting LLC | Indianapolis | 2013-12-11 | CE
CN
|  |  | 0810324 | Marion | DCD Consulting LLC | Indianapolis | 2013-12-11 | CE
CN
|  |  | 0810325 | Johnson |  | Johnson County | 2010-05-12 | CE
CN
UT
|  |  | 0810326 | Hamilton |  | Hamilton County | 2012-05-02 | CE
CN
UT
|  |  | 0810327 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 0810328 | Morgan | Aerial Services, Inc. | Morgan County | 2014-07-09 | CE
CN
PE
|  |  | 0810329 | Hamilton | Appraising Indiana, LLC | Cicero | 2013-07-17 | CE
CN
PE
UT
|  |  | 0810330 |  | GAI Consultants, Inc. | Morgan County | -339679.2083
|  |  | 0810331 | Marion | Dyer Environmental Services | Lawrence | 2010-12-08 | CE
CN
|  |  | 0810332 | Johnson | Casteel Real Estate | Johnson County | 2011-01-12 | CE
CN
|  |  | 0810333 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0810334 | Dearborn |  | Dearborn County | 2009-11-04 | CE
CN
PE
|  |  | 0810335 | Greene |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0810336 | Dekalb |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  |  | Grant |  | Indiana Department of Transportation | 2015-07-08 | CE
|  |  | 0810337 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0810338 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0810339 | Various |  | Indiana Department of Transportation | 2009-08-12 | CE
CN
|  |  | 0810340 | Vigo | Bayswater Company, LLC | Terre Haute | 2014-05-30 | CE
CN
PE
ROW
|  |  | 0810341 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 0810342 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2009-03-25 | CE
CN
|  |  | 0810343 |  |  | Rockville | -339679.2083
|  |  | 0810344 | Hendricks |  | Hendricks County | 2014-10-07 | PE
ROW
|  |  | 0810345 | Greene |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0810346 | Greene |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0810347 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2011-05-11 | CE
CN
|  |  | 0810348 | Greene |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0810349 | Clark |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0810350 | Brown |  | Brown County | -339679.2083 | PE
|  |  | 0810351 | Franklin |  | Franklin County | -339679.2083 | CN
|  |  | 0810352 | Jay | Boomerang Ventures, LLC | Dunkirk | 2013-10-09 | CE
CN
PE
|  |  | 0810353 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810354 | Dearborn |  | Indiana Department of Transportation | 2013-05-03 | CE
CN
|  |  | 0810355 | Dearborn |  | Indiana Department of Transportation | 2013-05-03 | CE
CN
|  |  | 0810356 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 0810357 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0810358 | St. Joseph |  | Indiana Department of Transportation | 2011-03-11 | CE
CN
|  |  | 0810359 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810361 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2009-05-06
|  |  | 0810362 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2009-05-06
|  |  | 0810363 | Wayne | Fleis & VandenBrink Engineering, Inc. | Milton | 2015-07-08 | CE
CN
PE
|  |  | 0810364 |  |  | Terre Haute | -339679.2083
|  |  | 0810365 | Dearborn |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810366 | Franklin |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810367 | Switzerland |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810368 | Franklin |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810369 | Monroe |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810370 | Bartholomew |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810372 | Lawrence |  | Lawrence County | 2009-02-11 | CE
CN
|  |  | 0810373 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0810374 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0810375 | Dekalb | Cheri K. Lewis Engineers | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 0810376 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 0810377 | Delaware | Michael Baker International, Inc. | Yorktown | 2009-10-07 | CE
CN
|  |  | 0810378 | Noble |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0810379 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2009-05-06 | CE
CN
|  |  | 0810380 | Warrick |  | Warrick County | -339679.2083 | CN
|  |  | 0810381 | Greene |  | Greene County | -339679.2083 | CN
|  |  | 0810382 | LaPorte |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0810383 | Tippecanoe |  | Indiana Department of Natural Resources | 2015-11-10 | CE
CN
|  |  | 0810384 | Posey |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
PE
|  |  | 0810385 | Franklin |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
|  |  | 0810386 | Boone |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
ROW
|  |  | 0810387 | Clinton |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810388 | Putnam |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810389 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2011-01-12
|  |  | 0810390 | Jefferson |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810391 | Jefferson |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810392 | Vanderburgh |  | Vanderburgh County | 2011-01-12 | CE
CN
|  |  | 0810393 | Union |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  |  | Wayne |  | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  | 0810394 | Perry |  | Tell City | 2010-11-10 | CE
CN
PE
|  |  | 0810395 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810396 | Morgan |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
PE
|  |  | 0810397 | Spencer | Beals-Moore & Associates, Inc. | Dale | 2012-02-08 | CE
CN
PE
|  |  | 0810398 | Jefferson |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810399 | Jefferson |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0810400 | Jackson |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810401 | Jackson |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810402 | Harrison |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810404 | Jackson |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810405 | Jackson |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810406 | Adams | CityWise Real Estate Services, LLC | Adams County | 2016-04-06 | CE
CN
PE
ROW
|  |  | 0810407 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2009-07-15 | CE
CN
|  |  | 0810408 | Steuben | ABt SRBI | Angola | 2010-08-04 | CE
CN
PE
|  |  | 0810409 | Kosciusko | McLane Realty, Inc. | Winona Lake | 2014-12-10 | CE
CN
|  |  | 0810410 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0810411 | Brown |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Monroe |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810412 | Jackson |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0810413 | Jefferson |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Jennings |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0810414 | Jefferson |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  |  | Jennings |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0810415 | Dearborn |  | Indiana Department of Transportation | 2009-03-25 | CN
|  |  | 0810416 | Vigo |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0810417 | Vigo |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0810418 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0810419 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0810420 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0810421 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0810422 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0810423 | Marion | DCD Consulting LLC | Indianapolis | 2010-04-14 | CE
CN
RR
UT
|  |  | 0810424 | Marion | DCD Consulting LLC | Indianapolis | 2010-04-14 | CE
CN
RR
UT
|  |  | 0810425 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0810426 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0810427 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0810428 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0810429 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 0810430 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 0810431 | Fulton |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0810432 | Starke |  | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0810433 | Wayne |  | Wayne County | -339679.2083 | PE
|  |  | 0810434 | Porter | Leitner and Associates, Inc. | Valparaiso | 2016-03-16 | CE
CN
ROW
|  |  | 0810435 |  |  | Madison | -339679.2083
|  |  | 0810436 |  | Michael Baker International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0810437 |  | John A. Doyle Associates, Inc. | Shipshewana | -339679.2083
|  |  | 0810438 | Johnson |  | Johnson County | 2014-04-02 | CE
CN
PE
|  |  | 0810439 | Posey | GRL Engineers, Inc. | Mount Vernon | 2014-01-15 | CE
CN
PE
|  |  | 0810440 | Warrick | Appraisal Specialists, Inc. | Chandler | -339679.2083 | CN
|  |  | 0810441 | Boone | E.J. Breneman, LP | Lebanon | 2015-01-14 | CE
CN
PE
ROW
|  |  | 0810442 | Daviess | AMEC E&I, Inc. | Washington | 2010-03-03 | CE
CN
PE
|  |  | 0810443 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2016-03-02 | CE
CN
ROW
|  |  | 0810444 | Washington | JCI Bridge Group, Inc. | Salem | 2012-09-12 | CE
CN
PE
|  |  | 0810445 | Wayne | American Resources Group, Ltd. | Cambridge City | 2012-05-02 | CE
CN
PE
|  |  | 0810446 |  |  | Allen County | -339679.2083
|  |  | 0810447 | Jasper | Bettina Settles Realty, LLC | De Motte | 2014-03-05 | CE
CN
|  |  | 0810448 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2017-02-08 | CE
CN
|  |  | 0810449 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 0810450 | Monroe | Absolute Title Services, LLC | Monroe County | -339679.2083 | PE
|  |  | 0810451 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0810452 | Warrick |  | Indiana Department of Transportation | 2009-03-11 | CE
CN
|  |  | 0810453 | Fountain | BA Martin Architects, PC | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0810454 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810455 | Clark |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0810456 |  |  | Jefferson County | -339679.2083
|  |  | 0810457 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2016-08-10 | CE
CN
PE
ROW
|  |  | 0810458 | Madison |  | Madison County | 2013-07-10 | CE
CN
PE
ROW
|  |  | 0810459 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0810460 |  |  | Jackson County | 2013-05-31
|  |  | 0810461 |  |  | Jackson County | 2013-05-31
|  |  | 0810462 | Owen |  | Owen County | 2009-03-11 | CE
CN
|  |  | 0810463 |  |  | Bartholomew County | 2009-05-31
|  |  | 0810464 |  |  | Bartholomew County | 2009-05-31
|  |  | 0810465 |  |  | Bartholomew County | 2009-05-31
|  |  | 0810466 | Monroe |  | Monroe County | 2013-03-31 | CN
|  |  | 0810467 |  | Absolute Title Services, LLC | Bloomington | 2009-05-31
|  |  | 0810468 |  | Associated Right-of-Way Services, Inc. | Columbus | 2009-05-31
|  |  | 0810469 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2009-05-09 | CN
|  |  | 0810470 | Johnson | Casteel Real Estate | Franklin | 2009-05-31 | CN
|  |  | 0810471 | Johnson | Casteel Real Estate | Franklin | 2009-05-31 | CN
|  |  | 0810472 | Henry |  | Henry County | -339679.2083 | CN
|  |  | 0810473 |  |  | Johnson County | 2011-05-11
|  |  | 0810474 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 0810475 |  | Majestic Real Estate, Inc. US Land Acquisitions | West College Corner | -339679.2083
|  |  | 0810476 |  |  | Johnson County | 2009-05-31
|  |  | 0810477 |  |  | Brown County | 2009-05-31
|  |  | 0810478 |  |  | Decatur County | 2009-05-31
|  |  | 0810479 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810480 |  |  | Decatur County | 2009-05-31
|  |  | 0810481 |  |  | Decatur County | 2009-05-31
|  |  | 0810482 |  |  | Decatur County | 2009-05-31
|  |  | 0810483 |  |  | Morgan County | -339679.2083
|  |  | 0810484 |  |  | Morgan County | -339679.2083
|  |  | 0810485 |  |  | Morgan County | -339679.2083
|  |  | 0810486 |  |  | Morgan County | -339679.2083
|  |  | 0810487 |  |  | Morgan County | 2013-03-31
|  |  | 0810488 |  |  | Decatur County | 2009-05-31
|  |  | 0810489 | Howard |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0810490 | Hancock | CoCal Consulting, LLC | Hancock County | 2013-07-10 | CE
CN
|  |  | 0810491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810492 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2011-04-13
|  |  | 0810493 | Hancock |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0810494 | Hancock |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0810495 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810497 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0810498 | Marion | DCD Consulting LLC | Indianapolis | 2014-05-08 | CE
CN
|  |  | 0810499 | Hancock |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 0810500 | Hancock |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810501 | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810502 | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810503 | Hancock |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810504 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-09-10 | CE
CN
|  |  | 0810505 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0810506 | Hancock |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0810507 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810512 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810513 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2016-04-06 | CE
CN
PE
ROW
|  |  | 0810514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810515 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810516 | Johnson | Wood Environment & Infrastructure Solutions, Inc. | Johnson County | 2012-07-11 | CE
CN
UT
|  |  | 0810517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810521 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810522 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810523 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810524 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810525 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810526 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810527 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810529 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810530 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810531 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810532 | Various |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0810533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810534 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810539 | Howard |  | Indiana Department of Transportation | 2010-08-06 | CE
CN
|  |  | 0810540 | Lake |  | Munster | 2012-11-15 | CE
CN
|  |  | 0810541 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2017-02-08 | CE
CN
PE
ROW
|  |  | 0810542 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810543 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810544 | Howard |  | Indiana Department of Transportation | 2012-05-04 | CE
CN
|  |  | 0810545 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810546 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810547 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810548 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810549 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810550 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810551 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810552 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810553 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810554 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810555 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810557 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810558 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810560 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810561 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810562 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810563 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810564 | Porter | Leitner and Associates, Inc. | Valparaiso | 2009-09-10 | CE
CN
|  |  | 0810565 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810566 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810567 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810569 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810571 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810572 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810573 | Decatur |  | Decatur County | -339679.2083 | CN
|  |  | 0810574 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810575 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810576 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810577 | Scott |  | Scott County | -339679.2083 | CN
PE
|  |  | 0810578 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810579 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810581 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810582 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810583 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810585 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810586 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810588 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810589 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810592 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810594 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810595 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810596 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810597 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810598 | Carroll | Blood Hound, Inc. (former) | Delphi | 2009-06-03 | CE
CN
|  |  | 0810599 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810600 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0810601 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900001 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2010-07-07 | CE
CN
PE
|  |  | 0900002 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2014-07-09 | CE
CN
PE
|  |  | 0900003 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0900004 |  |  | Indiana Department of Transportation | 2009-04-08
|  |  | 0900005 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0900006 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 0900008 | Shelby |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0900009 | Various |  | Indiana State Agencies | -339679.2083 | PE
|  |  | 0900010 | Marion | DCD Consulting LLC | Indianapolis | 2010-10-06 | CE
CN
|  |  | 0900011 | Marion | DCD Consulting LLC | Indianapolis | 2011-08-10 | CE
CN
RR
|  |  | 0900012 | Hancock |  | Hancock County | 2014-03-05 | CE
CN
|  |  | 0900013 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0900014 | Martin |  | Martin County | -339679.2083 | CN
|  |  | 0900015 | Vanderburgh | CGI | Evansville | -339679.2083 | PE
|  |  | 0900018 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2013-01-16 | CE
CN
|  |  | 0900019 | Crawford |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
PE
ROW
|  |  | 0900020 | Porter | Leitner and Associates, Inc. | Valparaiso | 2011-07-13 | CE
CN
|  |  | 0900021 | Jasper |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
RR
|  |  | 0900022 | Boone |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Warren |  | Indiana Department of Transportation | 2011-03-09 | PE
ROW
|  |  | 0900023 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900024 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2011-04-13 | CN
|  |  | 0900025 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0900026 |  | CTL Engineering of Indiana, Inc. | Allen County | -339679.2083
|  |  | 0900027 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-05-19 | CE
CN
|  |  | 0900028 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0900029 | Hamilton |  | Westfield | 2013-09-20 | PE
|  |  | 0900030 | Marion |  | Indianapolis | 2013-12-11 | CE
CN
PE
|  |  | 0900031 | Hancock |  | New Palestine | 2014-04-02 | CN
|  |  |  | Howard |  | New Palestine | 2014-04-02 | CE
|  |  | 0900032 | Fountain |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0900033 |  |  | Indiana Department of Transportation | 2009-05-31
|  |  | 0900034 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900036 | Gibson |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
UT
[6 empty] | Indiana Department of Transportation | 2011-01-26
|  |  | 0900037 | Gibson |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
UT
[6 empty] | Indiana Department of Transportation | 2011-01-26
|  |  | 0900038 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900039 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900040 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900041 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900042 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900043 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900045 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0900046 | Gibson |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
PE
ROW
UT
[6 empty] | Indiana Department of Transportation | 2011-01-26
|  |  | 0900047 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0900048 | Posey |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Spencer |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0900049 | Dubois |  | Jasper | 2009-10-21 | CE
CN
|  |  | 0900050 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0900051 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0900052 | St. Joseph |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0900053 | Hamilton | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2012-09-12 | CE
CN
|  |  |  | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2012-09-12 | CE
CN
|  |  | 0900054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900055 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900056 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900058 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0900059 | Jefferson |  | Madison | -339679.2083 | PE
|  |  | 0900060 | Lake | Cornerstone Design | Highland | 2012-08-08 | CE
CN
PE
|  |  | 0900061 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2014-11-13 | CE
CN
PE
|  |  | 0900062 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2013-09-11 | CE
CN
PE
RR
|  |  | 0900063 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2016-07-13 | PE
|  |  | 0900064 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2022-03-09 | PE
|  |  | 0900065 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 0900066 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2010-04-22 | PE
|  |  | 0900067 | Lake |  | Merrillville | 2014-11-13 | CE
CN
ROW
|  |  | 0900068 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 0900069 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 0900070 | Lake | Consolidated Test Company | Hammond | 2010-01-13 | CE
CN
|  |  | 0900071 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2015-05-07 | CE
CN
PE
ROW
UT
|  |  | 0900072 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 0900073 |  |  | Lake County | -339679.2083
|  |  | 0900074 | Porter | Leitner and Associates, Inc. | Valparaiso | 2016-03-16 | CE
CN
ROW
|  |  | 0900075 | Porter | Leitner and Associates, Inc. | Valparaiso | 2020-02-05 | CE
CN
ROW
RR
|  |  | 0900076 | Porter | Leitner and Associates, Inc. | Valparaiso | -339679.2083 | PE
|  |  | 0900077 | Lake | Baxter & Woodman, Inc. | Crown Point | 2010-12-08 | CE
CN
|  |  | 0900078 | Lake | Baxter & Woodman, Inc. | Crown Point | 2010-12-08 | CE
CN
|  |  | 0900079 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900080 | Porter | Huff & Huff, Inc. | Portage | 2019-11-14 | CE
CN
PE
ROW
|  |  | 0900081 | Greene |  | Indiana Department of Transportation | 2011-05-31 | PE
ROW
|  |  | 0900082 | LaPorte |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
RR
|  |  | 0900083 | Shelby |  | Shelbyville | 2009-07-01 | CE
CN
|  |  | 0900084 | Newton |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900085 | Jasper | Independent Land Surveying, Inc. | Rensselaer | 2009-07-15 | CE
CN
RR
|  |  | 0900086 | Marshall | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0900087 | Marshall | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2009-06-03 | CE
CN
|  |  | 0900088 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900089 | LaPorte |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
RR
|  |  | 0900090 | Lake | Edwards and Kelcey | Indiana Department of Transportation | 2011-08-10 | CE
CN
RR
|  |  | 0900091 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900092 | Dearborn |  | Dearborn County | 2009-06-24 | CE
CN
|  |  | 0900093 | Dearborn |  | Dearborn County | 2009-10-21 | CE
CN
|  |  | 0900094 | Dearborn |  | Dearborn County | -339679.2083 | CN
|  |  | 0900095 | Dearborn |  | Dearborn County | 2009-07-29 | CE
CN
|  |  | 0900096 | Dearborn |  | Dearborn County | 2009-07-29 | CN
|  |  | 0900097 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900098 | Montgomery | ETC Institute | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  |  | Tippecanoe | ETC Institute | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0900099 | Perry |  | Tell City | 2013-08-07 | CE
CN
PE
UT
|  |  | 0900100 | Knox | Louis Joyner, Architect | Vincennes | 2015-05-31 | PE
|  |  | 0900101 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900102 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0900103 | Allen | CPS Acquisitions, LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  |  | Dekalb | CPS Acquisitions, LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  |  | Grant | CPS Acquisitions, LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  |  | Steuben | CPS Acquisitions, LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0900104 | Jasper |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  |  | Lake |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0900105 | Bartholomew |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Clark |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Jackson |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0900106 | Franklin |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0900107 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0900108 | Montgomery |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0900109 | Clinton |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  |  | Jasper |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0900110 | Crawford |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | Gibson |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | Perry |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | Warrick |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0900111 | Delaware |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0900112 | Hancock |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  |  | Henry |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  |  | Wayne |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0900113 | Hancock | CoCal Consulting, LLC | Greenfield | 2012-07-13 | CE
CN
PE
|  |  | 0900114 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2014-01-15 | CE
CN
PE
|  |  | 0900115 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 0900116 | Boone | E.J. Breneman, LP | Lebanon | 2015-01-14 | CN
PE
ROW
|  |  | 0900117 | Pulaski |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
PE
|  |  | 0900118 | Brown |  | Brown County | -339679.2083 | CN
|  |  | 0900119 | Vigo |  | Terre Haute | 2009-08-26 | CE
CN
|  |  | 0900120 |  |  | Vigo County | -339679.2083
|  |  | 0900121 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0900122 | Vigo |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900123 | Lake |  | Winfield | -339679.2083 | PE
|  |  | 0900124 | Grant | ERES International, Inc. | Marion | 2013-07-10 | CE
CN
ROW
|  |  | 0900125 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington | 2017-02-08 | CE
CN
PE
ROW
|  |  | 0900126 |  |  | Mitchell | -339679.2083
|  |  | 0900127 |  |  | Shelby County | -339679.2083
|  |  | 0900128 | St. Joseph | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
RR
|  |  | 0900129 | Boone |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900130 | Howard |  | Kokomo | 2014-07-09 | CE
CN
PE
ROW
|  |  | 0900131 | Vigo |  | Terre Haute | 2009-08-12 | CE
CN
|  |  | 0900132 | Tippecanoe |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0900133 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900134 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900135 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900136 | Tippecanoe |  | Indiana Department of Transportation | 2009-05-20 | CE
CN
|  |  | 0900137 | Carroll |  | Indiana Department of Transportation | 2012-03-07 | RR
|  |  |  | Cass |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
RR
|  |  | 0900138 | Cass |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0900139 | Cass |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0900140 | Carroll |  | Indiana Department of Transportation | 2011-02-11 | CE
CN
|  |  | 0900141 |  |  | Indiana Department of Transportation | 2009-11-04
|  |  | 0900142 | Cass |  | Indiana Department of Transportation | 2009-11-04 | RR
|  |  | 0900143 | Clark |  | Clark County | 2012-05-02 | CE
CN
|  |  | 0900144 | Dearborn |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900145 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900146 | Ripley |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0900147 | Jackson | FAA National, Inc. | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0900148 |  |  | Columbus | 2009-11-18
|  |  | 0900149 | Marion |  | Indiana Department of Transportation | 2010-01-13 | UT
|  |  | 0900150 | Various |  | Indiana Department of Transportation | 2009-05-31 | CN
|  |  | 0900151 |  |  | Indiana Department of Natural Resources | 2009-05-31
|  |  | 0900152 | Starke |  | Indiana Department of Natural Resources | 2011-01-12 | CE
CN
|  |  | 0900153 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900154 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0900155 | Gibson |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0900156 | St. Joseph | HDR Engineering, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0900157 | St. Joseph | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0900158 | St. Joseph | HDR Engineering, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0900159 | Dearborn |  | Greendale | 2009-06-24 | CN
|  |  | 0900160 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0900161 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900162 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0900163 | Howard |  | Howard County | 2014-11-13 | CE
CN
PE
ROW
|  |  | 0900165 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900167 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0900168 | Cass |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0900169 | Steuben | ABt SRBI | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0900170 | Boone |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900171 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900172 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0900173 | Vigo |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0900174 | Boone |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0900175 | Montgomery |  | Indiana Department of Transportation | 2011-09-13 | CE
CN
ROW
|  |  | 0900176 | Starke |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0900177 | Vigo |  | Vigo County | 2009-12-09 | CE
CN
|  |  | 0900178 | Tippecanoe |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  |  | Warren |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 0900179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900180 | Montgomery |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900181 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 0900182 | Clay |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 0900183 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0900184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900185 | Vigo |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0900186 | Warren |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 0900187 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900188 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900190 | Vermillion |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0900191 | Warren |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0900192 | Fountain | AECON, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
RR
|  |  |  | Warren | AECON, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
|  |  | 0900193 | Fountain |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900194 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900195 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900196 | Clinton |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 0900197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900198 | Clinton | Iteris, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 0900199 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900200 | Parke | Entran, PLC | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 0900201 | Parke | Frontline Construction Inspection, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 0900202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900203 | Hendricks |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0900204 | Warren |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0900205 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900206 | Clinton |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0900207 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900208 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900210 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0900211 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900212 | Hendricks |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0900213 | Monroe |  | Bloomington | 2012-04-18 | CE
CN
|  |  | 0900214 | Clay | Advanced Appraisals, LLC | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 0900215 |  | Indiana University | Indiana Department of Transportation | -339679.2083
|  |  | 0900216 | Monroe |  | Bloomington | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0900217 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 0900218 | Carroll |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  |  | Cass |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0900219 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900221 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900226 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900227 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900228 | Jackson |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0900229 | Washington |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0900230 | Harrison |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900231 | Washington |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0900232 | Decatur |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  |  | Franklin |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0900233 | Dearborn |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 0900234 | Johnson |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0900235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900237 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900238 | Johnson |  | Indiana Department of Transportation | 2009-04-22 | CE
CN
|  |  | 0900239 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900240 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900241 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900242 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900243 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900244 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900245 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900246 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900247 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900248 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900249 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900250 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900251 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900252 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900253 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 0900254 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0900255 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900258 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900259 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 0900260 | Decatur |  | Indiana Department of Transportation | 2010-03-17 | CE
CN
|  |  | 0900261 | Bartholomew |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  |  | Jennings |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 0900262 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2009-08-12 | CE
CN
|  |  | 0900263 |  | Land Construction Corp | Tipton County | -339679.2083
|  |  | 0900264 | Marshall |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0900265 | Clark |  | Indiana Department of Transportation | 2015-05-31 | UT
|  |  |  | Hamilton |  | Indiana Department of Transportation | 2015-05-31 | UT
|  |  | 0900266 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 0900267 | Hamilton | Another Test Company | Indiana Department of Transportation | 2015-05-31 | UT
|  |  | 0900268 | Clark | Another Test Company | Indiana Department of Transportation | 2015-05-31 | UT
|  |  |  | Hamilton | Another Test Company | Indiana Department of Transportation | 2015-05-31 | UT
|  |  | 0900269 | Hamilton |  | Indiana Department of Transportation | 2015-05-31 | PE
UT
|  |  | 0900270 |  | Another Test Company | Indiana Department of Transportation | 2015-05-31
|  |  | 0900271 |  | Another Test Company | Indiana Department of Transportation | 2015-05-31
|  |  | 0900272 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900273 | Hamilton | Another Test Company | Indiana Department of Transportation | 2012-08-08 | CE
CN
UT
|  |  | 0900274 |  |  | Ripley County | -339679.2083
|  |  | 0900275 |  |  | Ripley County | -339679.2083
|  |  | 0900276 |  |  | Ripley County | -339679.2083
|  |  | 0900278 |  |  | Ripley County | -339679.2083
|  |  | 0900279 |  |  | Ripley County | -339679.2083
|  |  | 0900280 |  |  | Ripley County | -339679.2083
|  |  | 0900281 | Marion |  | Indianapolis | -339679.2083 | PE
|  |  | 0900282 | Hamilton |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
UT
|  |  | 0900283 | Jackson | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
|  |  | 0900284 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900285 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900286 | Clay |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 0900287 | Vigo |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 0900288 | Vigo |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 0900289 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0900290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900291 | Morgan |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0900292 | Owen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0900293 | Putnam |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
PE
|  |  | 0900294 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900295 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900296 | Perry |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900297 | Knox |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900298 | Knox |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900299 | Greene |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900300 | Owen |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900301 | Huntington |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900302 | Huntington |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900303 | Bartholomew |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0900304 | Bartholomew |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0900305 | Brown |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900306 | Brown |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900307 | Decatur |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900308 | Ripley |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0900309 | Scott |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900310 | Vermillion |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0900311 | Warren |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900312 | Vermillion |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0900313 |  |  | Indiana Department of Transportation | 2009-05-06
|  |  | 0900314 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900315 | LaPorte |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  |  | Marshall |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  |  | Porter |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  |  | Starke |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900316 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900317 | Porter |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900318 | LaPorte |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900319 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
RR
|  |  | 0900320 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2012-03-07 | CE
CN
RR
|  |  | 0900321 | Bartholomew |  | Bartholomew County | 2009-07-29 | CE
CN
|  |  | 0900322 | Parke |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900323 | Warren |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900324 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-05-12 | CE
CN
PE
|  |  | 0900325 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900326 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900327 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900328 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900329 | Porter |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900330 | Marion |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
PE
|  |  | 0900331 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900332 | Marion |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
|  |  | 0900333 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900334 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900335 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900336 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CE
CN
|  |  | 0900337 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900338 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900339 | Porter |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900340 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900341 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900342 | Lake |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900343 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900344 | St. Joseph |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900345 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900346 | Lake |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900347 | Marshall |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900348 | Jennings |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900349 | Porter |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900350 | Harrison |  | Indiana Department of Transportation | 2009-07-01 | CN
|  |  | 0900351 | Bartholomew |  | Indiana Department of Transportation | 2009-07-01 | CE
CN
|  |  | 0900352 | Bartholomew |  | Indiana Department of Transportation | 2009-07-01 | CN
|  |  | 0900353 | Knox |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900354 | LaPorte |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900355 | Knox |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900356 | Lawrence |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900357 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0900358 | Lawrence |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900359 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-05-12 | CE
CN
PE
|  |  | 0900360 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900361 |  |  | Indiana Department of Transportation | 2015-05-08
|  |  | 0900362 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900363 | Floyd |  | Indiana Department of Transportation | 2009-08-26 | CN
RR
|  |  | 0900364 | Cass |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0900365 | Floyd |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900366 | Floyd |  | Indiana Department of Transportation | 2009-08-26 | CN
|  |  | 0900367 | Newton |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0900368 | Clark |  | Indiana Department of Transportation | 2009-07-01 | CN
|  |  | 0900369 | Jasper |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0900370 | Lake | Jacobi, Toombs & Lanz, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 0900371 | Marshall |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0900372 |  |  | Hamilton County | -339679.2083
|  |  | 0900373 |  |  | Hamilton County | -339679.2083
|  |  | 0900374 |  |  | Hamilton County | -339679.2083
|  |  | 0900375 |  |  | Hamilton County | -339679.2083
|  |  | 0900376 |  |  | Hamilton County | -339679.2083
|  |  | 0900377 |  |  | Westfield | -339679.2083
|  |  | 0900378 |  |  | Brown County | -339679.2083
|  |  | 0900379 |  |  | Hamilton County | -339679.2083
|  |  | 0900380 |  |  | Greensburg | -339679.2083
|  |  | 0900381 |  |  | Hamilton County | -339679.2083
|  |  | 0900382 |  |  | Greensburg | -339679.2083
|  |  | 0900383 |  |  | Hamilton County | -339679.2083
|  |  | 0900384 | Vanderburgh |  | Evansville | 2010-02-24 | CE
CN
|  |  | 0900385 |  |  | Hamilton County | -339679.2083
|  |  | 0900386 |  |  | Westfield | -339679.2083
|  |  | 0900387 |  |  | Hamilton County | -339679.2083
|  |  | 0900388 |  | DCD Consulting LLC | Indiana Department of Transportation | 2009-10-07
|  |  | 0900389 |  |  | Greensburg | -339679.2083
|  |  | 0900390 |  | DCD Consulting LLC | Indiana Department of Transportation | 2010-10-06
|  |  | 0900391 |  |  | Greensburg | -339679.2083
|  |  | 0900392 |  |  | Greensburg | -339679.2083
|  |  | 0900393 |  |  | Greensburg | -339679.2083
|  |  | 0900394 |  |  | Decatur | -339679.2083
|  |  | 0900395 |  |  | Decatur County | -339679.2083
|  |  | 0900396 |  |  | Hamilton County | -339679.2083
|  |  | 0900397 |  |  | Hamilton County | -339679.2083
|  |  | 0900398 |  |  | Hamilton County | -339679.2083
|  |  | 0900399 |  |  | Hamilton County | -339679.2083
|  |  | 0900400 |  |  | Hamilton County | -339679.2083
|  |  | 0900401 |  |  | Hamilton County | -339679.2083
|  |  | 0900402 |  |  | Hamilton County | -339679.2083
|  |  | 0900403 |  |  | Hamilton County | -339679.2083
|  |  | 0900404 |  |  | Hamilton | -339679.2083
|  |  | 0900405 |  |  | Westfield | -339679.2083
|  |  | 0900406 | Hamilton |  | Westfield | 2009-10-21 | CE
CN
|  |  | 0900407 |  |  | Decatur County | -339679.2083
|  |  | 0900408 |  |  | Hamilton County | -339679.2083
|  |  | 0900409 |  |  | Decatur County | -339679.2083
|  |  | 0900410 |  |  | Westfield | -339679.2083
|  |  | 0900411 |  |  | Hamilton County | -339679.2083
|  |  | 0900412 |  |  | Decatur County | -339679.2083
|  |  | 0900413 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 0900414 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 0900415 |  |  | Wayne County | -339679.2083
|  |  | 0900416 |  |  | Wayne County | -339679.2083
|  |  | 0900417 |  |  | Wayne County | -339679.2083
|  |  | 0900418 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 0900419 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0900420 | Lake | Consolidated Test Company | Hammond | 2010-02-24 | CE
CN
|  |  | 0900421 | Shelby |  | Shelby County | -339679.2083 | CN
|  |  | 0900422 | Whitley | Associated Appraisal Group, Inc. | Columbia City | 2014-12-10 | CE
CN
PE
ROW
|  |  | 0900423 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2009-12-09 | CE
CN
|  |  | 0900424 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2009-12-09 | CE
CN
|  |  | 0900425 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2009-12-09 | CE
CN
|  |  | 0900426 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2009-12-09 | CE
CN
|  |  | 0900427 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2009-12-09 | CE
CN
|  |  | 0900428 |  |  | Merrillville | -339679.2083
|  |  | 0900429 | Lake |  | Merrillville | 2010-01-27 | CE
CN
|  |  | 0900430 | Lake |  | Merrillville | 2009-12-09 | CE
CN
|  |  | 0900431 |  |  | Newton County | -339679.2083
|  |  | 0900432 |  |  | Newton County | -339679.2083
|  |  | 0900433 |  |  | Greensburg | -339679.2083
|  |  | 0900434 | Crawford |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900435 | Perry |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0900436 | Vanderburgh |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900437 | Posey |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  |  | Warrick |  | Indiana Department of Transportation | 2010-02-10 | CE
CN
|  |  | 0900438 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900439 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900441 | Marshall | Advanced Engineering Consultants, Ltd. | Bremen | 2009-11-18 | CE
CN
|  |  | 0900442 | Marshall | Howard J. Barth & Associates, Inc. | Marshall County | 2009-11-18 | CE
CN
|  |  | 0900443 | Lake | Matt L. Nepote, MAI | Whiting | 2009-12-09 | CE
CN
|  |  | 0900444 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900446 | Dekalb |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  |  | Steuben |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
RR
|  |  | 0900447 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900448 | St. Joseph |  | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0900449 | Fountain |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900450 | Parke |  | Indiana Department of Transportation | 2009-06-24 | CE
CN
|  |  | 0900451 | Wabash |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900452 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2009-07-29 | CE
CN
|  |  | 0900453 | Adams |  | Indiana Department of Transportation | 2009-06-24 | CN
|  |  | 0900454 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900455 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900456 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900458 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 0900459 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 0900460 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 0900461 | Clark |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 0900462 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 0900463 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0900464 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0900465 | Marshall |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 0900466 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0900467 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900468 |  |  | Jasper County | -339679.2083
|  |  | 0900469 | Jasper |  | Jasper County | 2009-12-09 | CE
CN
|  |  | 0900470 | Jasper |  | Jasper County | 2009-12-09 | CE
CN
|  |  | 0900471 |  |  | Jasper County | -339679.2083
|  |  | 0900472 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2009-12-09 | CE
CN
|  |  | 0900473 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2009-12-09 | CE
CN
|  |  | 0900474 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2009-12-09 | CE
CN
|  |  | 0900475 |  |  | Newton County | -339679.2083
|  |  | 0900476 |  |  | Newton County | -339679.2083
|  |  | 0900477 |  |  | Newton County | -339679.2083
|  |  | 0900478 |  |  | Newton County | -339679.2083
|  |  | 0900479 |  |  | Newton County | -339679.2083
|  |  | 0900480 |  |  | Newton County | -339679.2083
|  |  | 0900481 |  |  | Newton County | -339679.2083
|  |  | 0900482 |  |  | Newton County | -339679.2083
|  |  | 0900483 |  |  | Newton County | -339679.2083
|  |  | 0900484 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0900485 |  |  | Marshall County | -339679.2083
|  |  | 0900486 |  |  | Marshall County | -339679.2083
|  |  | 0900487 |  |  | Marshall County | -339679.2083
|  |  | 0900488 |  |  | Marshall County | -339679.2083
|  |  | 0900489 |  |  | Marshall County | -339679.2083
|  |  | 0900490 |  |  | Marshall County | -339679.2083
|  |  | 0900491 |  |  | Marshall County | -339679.2083
|  |  | 0900492 |  |  | Marshall County | -339679.2083
|  |  | 0900493 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900494 |  |  | Marshall County | -339679.2083
|  |  | 0900495 |  |  | Marshall County | -339679.2083
|  |  | 0900496 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900497 |  |  | Marshall County | -339679.2083
|  |  | 0900498 |  |  | Marshall County | -339679.2083
|  |  | 0900499 |  |  | Marshall County | -339679.2083
|  |  | 0900500 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900501 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900502 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900503 |  |  | Marshall County | -339679.2083
|  |  | 0900504 |  |  | Marshall County | -339679.2083
|  |  | 0900505 |  |  | Marshall County | -339679.2083
|  |  | 0900506 |  |  | Marshall County | -339679.2083
|  |  | 0900507 |  |  | Marshall County | -339679.2083
|  |  | 0900508 |  |  | Marshall County | -339679.2083
|  |  | 0900509 |  |  | Marshall County | -339679.2083
|  |  | 0900510 |  |  | Marshall County | -339679.2083
|  |  | 0900511 |  |  | Marshall County | -339679.2083
|  |  | 0900512 |  |  | Marshall County | -339679.2083
|  |  | 0900513 |  |  | Marshall County | -339679.2083
|  |  | 0900514 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900515 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 0900516 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 0900517 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 0900518 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2009-11-18 | CE
CN
|  |  | 0900519 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 0900520 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2009-12-09 | CE
CN
|  |  | 0900521 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2009-09-23 | CE
CN
|  |  | 0900522 |  | Civil Engineering Consultants | Goodland | -339679.2083
|  |  | 0900523 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 0900524 | White |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
|  |  | 0900525 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0900526 | Washington |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0900527 |  |  | Indiana Department of Transportation | 2011-02-23
|  |  | 0900528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900529 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900530 | Ohio |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900531 | Ohio | Indiana Search Technologies | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0900532 | Ripley | GSG Consultants, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0900533 |  | Hardcore Concrete Sawing Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0900534 | Ripley | Hardcore Concrete Sawing Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 0900535 | Brown |  | Brown County | 2009-10-21 | CE
CN
|  |  | 0900536 | Brown |  | Brown County | 2009-10-21 | CE
CN
|  |  | 0900537 | Knox |  | Knox County | 2009-07-29 | CE
CN
|  |  | 0900538 | Knox |  | Knox County | 2009-07-29 | CE
CN
|  |  | 0900539 | Knox |  | Knox County | 2009-07-29 | CN
|  |  | 0900540 | Daviess |  | Daviess County | 2009-07-29 | CE
CN
|  |  | 0900541 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2009-11-18 | CE
CN
|  |  | 0900542 | Gibson | Eagle Ridge Civil Engineering Services, LLC | Linton | 2009-11-18 | CE
CN
|  |  | 0900543 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2009-11-18 | CE
CN
|  |  | 0900544 | Cass |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 0900545 | Clark |  | Clarksville | 2009-10-21 | CE
CN
|  |  | 0900546 | Spencer |  | Spencer County | 2009-07-29 | CE
CN
|  |  | 0900547 | Daviess |  | Daviess County | 2009-07-29 | CE
CN
|  |  | 0900548 | Perry |  | Perry County | 2009-07-29 | CE
CN
|  |  | 0900549 | Perry |  | Perry County | 2009-07-29 | CN
|  |  | 0900550 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900551 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900552 |  |  | Marshall County | -339679.2083
|  |  | 0900553 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 0900554 | White | Fugro Roadware, Inc. | Monticello | 2010-01-27 | CE
CN
|  |  | 0900555 | White | Fugro Roadware, Inc. | Monticello | 2010-01-27 | CE
CN
|  |  | 0900556 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900557 |  | Applied Pavement Technology, Inc. | Cedar Lake | -339679.2083
|  |  | 0900558 | Allen |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0900559 |  |  | Batesville | -339679.2083
|  |  | 0900560 | Carroll |  | Carroll County | 2009-08-26 | CE
CN
|  |  | 0900561 | Carroll |  | Carroll County | 2009-07-29 | CE
CN
|  |  | 0900562 | Cass |  | Cass County | 2009-07-29 | CE
CN
|  |  | 0900563 | Cass |  | Cass County | 2009-07-29 | CE
CN
|  |  | 0900564 | Cass |  | Cass County | 2009-08-26 | CE
CN
|  |  | 0900565 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900566 | Spencer |  | Spencer County | 2009-07-29 | CN
|  |  | 0900567 | Spencer |  | Spencer County | 2009-07-29 | CN
|  |  | 0900568 | Spencer |  | Spencer County | 2009-07-29 | CN
|  |  | 0900569 |  |  | Spencer County | -339679.2083
|  |  | 0900570 |  |  | Spencer County | -339679.2083
|  |  | 0900571 |  |  | Spencer County | 2009-07-29
|  |  | 0900572 | Montgomery |  | Montgomery County | 2009-07-29 | CE
CN
|  |  | 0900573 | Gibson |  | Gibson County | 2009-07-29 | CE
CN
|  |  | 0900574 | Montgomery |  | Montgomery County | 2009-07-29 | CE
CN
|  |  | 0900575 | Gibson |  | Gibson County | 2009-07-29 | CN
|  |  | 0900576 | Gibson |  | Gibson County | 2009-07-29 | CN
|  |  | 0900577 | Warrick |  | Warrick County | 2009-07-29 | CN
|  |  | 0900578 | Warrick |  | Warrick County | 2009-07-29 | CE
CN
|  |  | 0900579 | Warrick |  | Warrick County | 2009-07-29 | CN
|  |  | 0900580 | Warrick |  | Warrick County | 2009-07-29 | CN
|  |  | 0900581 | Warrick |  | Warrick County | 2009-07-29 | CE
CN
|  |  | 0900582 | Warrick |  | Warrick County | 2009-07-29 | CN
|  |  | 0900583 |  | Eagle Ridge Civil Engineering Services, LLC | Linton | -339679.2083
|  |  | 0900584 | Hendricks |  | Plainfield | 2009-07-29 | CE
CN
|  |  | 0900585 | Knox | Louis Joyner, Architect | Vincennes | 2009-08-26 | CE
CN
|  |  | 0900586 | Switzerland |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 0900587 | Switzerland |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0900588 | Madison |  | Anderson | 2010-08-04 | CE
CN
|  |  | 0900589 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900592 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0900593 | Delaware |  | Delaware County | -339679.2083 | CN
|  |  | 0900594 | Hendricks |  | Plainfield | 2009-07-29 | CN
|  |  | 0900595 | Delaware |  | Delaware County | -339679.2083 | CN
|  |  | 0900596 | Delaware |  | Yorktown | 2016-03-02 | CE
CN
PE
ROW
|  |  | 0900597 | Delaware |  | Selma | -339679.2083 | CN
|  |  | 0900598 | Delaware |  | Muncie | -339679.2083 | CN
|  |  | 0900599 | Madison | Engineering Resources, Inc. | Madison County | 2009-08-05 | CE
CN
|  |  | 0900600 | Delaware |  | Muncie | -339679.2083 | CN
|  |  | 0900601 | Delaware |  | Delaware County | -339679.2083 | CN
|  |  | 0900602 | Delaware |  | Selma | -339679.2083 | CN
|  |  | 0900603 | Delaware |  | Muncie | -339679.2083 | CN
|  |  | 0900604 |  | Engineering Resources, Inc. | Madison County | -339679.2083
|  |  | 0900605 | Madison | Engineering Resources, Inc. | Madison County | 2009-08-26 | CE
CN
|  |  | 0900606 | Noble |  | Noble County | 2009-07-29 | CE
CN
|  |  | 0900607 | Madison | Engineering Resources, Inc. | Madison County | 2009-08-05 | CE
CN
|  |  | 0900608 | Madison | Engineering Resources, Inc. | Madison County | 2009-08-05 | CE
CN
|  |  | 0900609 | Shelby |  | Shelby County | 2009-07-29 | CE
CN
|  |  | 0900610 | Putnam |  | Roachdale | 2009-07-29 | CE
CN
|  |  | 0900611 |  |  | Shelby County | -339679.2083
|  |  | 0900612 | Fountain |  | Attica | 2009-07-29 | CE
CN
|  |  | 0900613 | Hamilton |  | Hamilton County | 2009-10-21 | CE
CN
|  |  | 0900614 | Rush |  | Rush County | 2009-07-29 | CE
CN
|  |  | 0900615 | Rush |  | Rush County | 2009-07-29 | CE
CN
|  |  | 0900616 | Hancock |  | Hancock County | 2009-07-29 | CE
CN
|  |  | 0900617 | Hancock |  | Hancock County | 2009-07-29 | CE
CN
|  |  | 0900618 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900619 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900621 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900622 | Vanderburgh | CGI | Evansville | 2010-09-01 | CE
CN
|  |  | 0900623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900624 | Lawrence | Hagerty Engineering, Inc. | Oolitic | 2009-07-29 | CE
CN
|  |  | 0900625 |  |  | Elwood | -339679.2083
|  |  | 0900626 | Sullivan |  | Sullivan County | 2009-07-29 | CE
CN
|  |  | 0900627 |  |  | Jeffersonville | -339679.2083
|  |  | 0900628 | Sullivan |  | Sullivan County | 2009-07-29 | CN
|  |  | 0900629 |  |  | Sullivan County | -339679.2083
|  |  | 0900630 |  |  | Madison County | -339679.2083
|  |  | 0900631 |  |  | Sullivan County | -339679.2083
|  |  | 0900632 |  |  | Sullivan County | -339679.2083
|  |  | 0900633 |  |  | Floyd County | -339679.2083
|  |  | 0900634 |  |  | Sullivan County | -339679.2083
|  |  | 0900635 | Madison |  | Madison County | 2009-08-26 | CE
CN
|  |  | 0900636 | Marion |  | Beech Grove | 2011-05-11 | CE
CN
|  |  | 0900637 | Floyd |  | New Albany | 2009-12-09 | CE
CN
RR
|  |  | 0900638 | Madison |  | Madison County | 2009-08-26 | CE
CN
|  |  | 0900639 | Floyd |  | New Albany | 2009-11-18 | CE
CN
|  |  | 0900640 |  |  | MPO - Louisville | -339679.2083
|  |  | 0900641 |  |  | MPO - Louisville | -339679.2083
|  |  | 0900642 | Tipton |  | Tipton County | 2009-07-29 | CE
CN
|  |  | 0900643 | Tipton |  | Tipton County | 2009-07-29 | CE
CN
|  |  | 0900644 | Floyd |  | New Albany | 2009-11-18 | CE
CN
|  |  | 0900645 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900646 | Clark |  | Jeffersonville | 2012-11-27 | CN
|  |  | 0900647 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900648 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900649 |  |  | Putnam County | -339679.2083
|  |  | 0900650 | Carroll |  | Carroll County | 2009-07-29 | CE
CN
|  |  | 0900651 | Carroll |  | Carroll County | 2009-07-29 | CE
CN
|  |  | 0900652 | Carroll |  | Carroll County | 2009-08-26 | CE
CN
|  |  | 0900653 | Carroll |  | Carroll County | 2009-07-29 | CN
|  |  | 0900654 |  |  | Carroll County | -339679.2083
|  |  | 0900655 | Carroll |  | Carroll County | 2009-08-26 | CE
CN
|  |  | 0900656 | Carroll |  | Carroll County | 2009-08-26 | CE
CN
|  |  | 0900657 | Cass |  | Cass County | 2009-07-29 | CE
CN
|  |  | 0900658 |  |  | Cass County | -339679.2083
|  |  | 0900659 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 0900660 | Lake | Consolidated Test Company | Hammond | 2009-12-09 | CE
CN
|  |  | 0900661 | Lake | Cornerstone Design | Highland | 2009-12-09 | CE
CN
|  |  | 0900662 |  | HRV Conformance Verification Associates, Inc. | Ogden Dunes | -339679.2083
|  |  | 0900663 | Lake | Compliance Consulting Service, Inc. | Griffith | 2009-12-09 | CE
CN
|  |  | 0900664 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 0900665 |  | H.R. Gray | North Judson | -339679.2083
|  |  | 0900666 |  | H.R. Gray | North Judson | -339679.2083
|  |  | 0900667 |  | H.R. Gray | North Judson | -339679.2083
|  |  | 0900668 |  | H.R. Gray | North Judson | -339679.2083
|  |  | 0900669 |  |  | Marshall County | -339679.2083
|  |  | 0900670 |  |  | Marshall County | -339679.2083
|  |  | 0900671 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900672 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0900673 | Jasper |  | Jasper County | 2009-12-09 | CE
CN
|  |  | 0900674 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2009-12-09 | CE
CN
|  |  | 0900675 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2009-12-09 | CE
CN
|  |  | 0900676 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2009-12-09 | CE
CN
|  |  | 0900677 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 0900678 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 0900679 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 0900680 | Jasper | Bettina Settles Realty, LLC | De Motte | 2014-03-05 | CE
CN
|  |  | 0900681 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900682 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900683 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900684 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900685 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900686 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900687 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900688 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900689 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900690 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900691 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0900692 | Clay |  | Clay County | 2009-07-29 | CE
CN
|  |  | 0900693 | Warren |  | Williamsport | 2009-07-29 | CE
CN
|  |  | 0900694 | Vigo |  | Vigo County | 2009-07-29 | CE
CN
|  |  | 0900695 | Vigo |  | Vigo County | 2009-07-29 | CN
|  |  | 0900696 | Putnam |  | Putnam County | 2009-07-29 | CE
CN
|  |  | 0900697 | Elkhart |  | Elkhart County | 2009-11-18 | CE
CN
|  |  | 0900698 | Elkhart |  | Elkhart County | 2009-11-18 | CE
CN
|  |  | 0900699 | Elkhart |  | Elkhart County | 2009-11-18 | CE
CN
|  |  | 0900700 | Elkhart |  | Elkhart County | 2009-11-18 | CE
CN
|  |  | 0900701 | Vigo |  | Vigo County | 2009-07-29 | CN
|  |  | 0900702 | Clark |  | Charlestown | 2009-12-09 | CE
CN
|  |  | 0900703 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0900704 | Vermillion |  | Clinton | 2009-07-29 | CE
CN
|  |  | 0900705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900706 |  |  | Brazil | -339679.2083
|  |  | 0900707 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900709 | Posey |  | Posey County | 2009-11-18 | CE
CN
|  |  | 0900710 | Posey |  | Posey County | 2009-11-18 | CE
CN
|  |  | 0900711 | Posey |  | Posey County | 2009-07-29 | CE
CN
|  |  | 0900712 | Starke |  | Starke County | 2009-08-26 | CE
CN
|  |  | 0900713 | Starke |  | Starke County | 2009-08-26 | CE
CN
|  |  | 0900714 | Starke |  | Starke County | 2009-08-26 | CE
CN
|  |  | 0900715 |  | Karen | St. John | -339679.2083
|  |  | 0900716 | Lake | Karen | St. John | 2010-01-27 | CE
CN
|  |  | 0900717 | Noble |  | Noble County | 2009-07-29 | CE
CN
RR
|  |  | 0900718 | Noble |  | Noble County | 2009-07-29 | CE
CN
|  |  | 0900719 |  |  | Shelby County | -339679.2083
|  |  | 0900720 | Shelby |  | Shelby County | 2009-08-26 | CE
CN
|  |  | 0900721 | Boone |  | Boone County | 2009-08-26 | CE
CN
|  |  | 0900722 | Boone |  | Boone County | 2009-08-26 | CE
CN
|  |  | 0900723 | Boone |  | Boone County | 2009-08-26 | CE
CN
|  |  | 0900724 | Boone |  | Boone County | 2009-08-26 | CE
CN
|  |  | 0900725 | Steuben |  | Steuben County | -339679.2083 | CN
|  |  | 0900726 |  |  | MPO - Louisville | -339679.2083
|  |  | 0900727 | Knox |  | Knox County | 2009-07-29 | CN
|  |  | 0900728 | Knox |  | Knox County | 2009-07-29 | CN
|  |  | 0900729 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900730 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0900731 |  |  | Randolph County | -339679.2083
|  |  | 0900732 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0900733 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0900734 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0900735 | Warren |  | Warren County | 2009-07-29 | CE
CN
|  |  | 0900736 | Warren |  | Warren County | 2009-07-29 | CE
CN
|  |  | 0900737 | Warren |  | Warren County | 2009-07-29 | CE
CN
|  |  | 0900738 | Noble |  | Noble County | 2009-07-29 | CE
CN
|  |  | 0900739 | Clinton |  | Clinton County | 2009-10-21 | CE
CN
|  |  | 0900740 | Noble |  | Noble County | 2009-07-29 | CE
CN
|  |  | 0900741 | Shelby |  | Shelby County | 2009-08-26 | CE
CN
|  |  | 0900742 | Clinton |  | Clinton County | 2009-10-21 | CE
CN
|  |  | 0900743 | Clinton |  | Clinton County | 2009-10-21 | CE
CN
|  |  | 0900744 |  |  | Randolph County | -339679.2083
|  |  | 0900745 | LaPorte |  | LaPorte County | 2009-12-09 | CE
CN
|  |  | 0900746 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900747 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0900748 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0900749 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0900750 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900751 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900752 | Hamilton |  | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900753 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900754 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900755 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900756 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900757 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900758 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900759 |  |  | Madison | -339679.2083
|  |  | 0900760 |  |  | Randolph County | -339679.2083
|  |  | 0900761 |  |  | Randolph County | -339679.2083
|  |  | 0900762 |  |  | Randolph County | -339679.2083
|  |  | 0900763 |  |  | Sunman | -339679.2083
|  |  | 0900764 | Hamilton | Another Test Company | Indiana Department of Transportation | 2011-09-23 | CE
CN
|  |  | 0900765 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0900766 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0900767 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0900768 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0900769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900770 |  |  | Madison | -339679.2083
|  |  | 0900771 | Jackson |  | Jackson County | 2009-09-23 | CE
CN
|  |  | 0900772 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0900773 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900774 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0900775 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0900776 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900777 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 0900778 | Posey | GRL Engineers, Inc. | Mount Vernon | 2009-07-29 | CE
CN
|  |  | 0900779 | Posey | GRL Engineers, Inc. | Mount Vernon | 2009-07-29 | CN
|  |  | 0900780 | Elkhart | Civil Inspection Services, LLC | Goshen | 2009-10-21 | CE
CN
|  |  | 0900781 | Posey | GRL Engineers, Inc. | Mount Vernon | 2009-07-29 | CN
|  |  | 0900782 | Elkhart | Civil Inspection Services, LLC | Goshen | 2009-10-21 | CE
CN
|  |  | 0900783 | Gibson | III FFC | Princeton | 2009-08-05 | CE
CN
|  |  | 0900784 | Gibson | III FFC | Princeton | 2009-08-05 | CN
|  |  | 0900785 | Gibson | III FFC | Princeton | 2009-08-05 | CN
|  |  | 0900786 | Elkhart | Civil Inspection Services, LLC | Goshen | 2010-02-24 | CE
CN
|  |  | 0900787 |  |  | Jackson County | -339679.2083
|  |  | 0900788 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 0900789 |  |  | Indiana Department of Transportation | 2013-07-17
|  |  | 0900790 |  |  | Indiana Department of Transportation | 2013-07-17
|  |  | 0900791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900792 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900793 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900794 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2009-11-18 | CE
CN
|  |  | 0900795 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | -339679.2083 | CE
CN
|  |  | 0900796 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0900797 | Rush |  | Rush County | 2009-08-26 | CE
CN
|  |  | 0900798 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0900799 | Fayette |  | Fayette County | 2009-08-26 | CN
|  |  | 0900800 |  |  | Jackson County | -339679.2083
|  |  | 0900801 |  |  | Jackson County | -339679.2083
|  |  | 0900802 | Kosciusko |  | Kosciusko County | 2009-08-26 | CE
CN
|  |  | 0900803 | Kosciusko |  | Kosciusko County | 2009-08-26 | CE
CN
|  |  | 0900804 |  |  | Kosciusko County | -339679.2083
|  |  | 0900805 |  |  | Indiana Department of Natural Resources | 2012-06-15
|  |  | 0900806 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0900807 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0900808 |  |  | Jennings County | -339679.2083
|  |  | 0900809 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900810 | Porter | Leitner and Associates, Inc. | Valparaiso | 2009-12-09 | CE
CN
|  |  | 0900811 | Porter | Leitner and Associates, Inc. | Valparaiso | 2009-12-09 | CE
CN
|  |  | 0900812 | Porter | Leitner and Associates, Inc. | Valparaiso | 2009-12-09 | CE
CN
|  |  | 0900813 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-01-27 | CE
CN
|  |  | 0900814 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-01-27 | CE
CN
|  |  | 0900815 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-01-27 | CE
CN
|  |  | 0900816 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-01-27 | CE
CN
|  |  | 0900817 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-01-27 | CE
CN
|  |  | 0900818 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-01-27 | CE
CN
|  |  | 0900819 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-02-24 | CE
CN
|  |  | 0900820 |  | Gensic Engineering, Inc. | New Carlisle | -339679.2083
|  |  | 0900821 |  | Gensic Engineering, Inc. | New Carlisle | -339679.2083
|  |  | 0900822 |  | Gensic Engineering, Inc. | New Carlisle | -339679.2083
|  |  | 0900823 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900824 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900825 | Dubois |  | Dubois County | 2009-07-29 | CE
CN
|  |  | 0900826 | Dubois |  | Dubois County | 2009-07-29 | CE
CN
|  |  | 0900827 |  |  | Dubois County | -339679.2083
|  |  | 0900828 |  |  | Indiana Department of Transportation | 2009-09-24
|  |  | 0900829 |  |  | Dubois County | -339679.2083
|  |  | 0900830 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900831 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0900832 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0900833 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900834 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900835 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900836 | Clinton |  | Clinton County | 2015-07-08 | CE
CN
PE
ROW
|  |  | 0900837 | Clinton |  | Clinton County | 2015-05-07 | CE
CN
PE
ROW
|  |  | 0900838 | Hendricks |  | Hendricks County | 2013-09-11 | CE
CN
PE
|  |  | 0900839 | Parke |  | Parke County | 2013-09-11 | CE
CN
PE
ROW
RR
|  |  | 0900840 | Porter | Hy-Tech Response, Inc. | Porter | 2009-11-18 | CE
CN
|  |  | 0900841 | Porter | Hy-Tech Response, Inc. | Porter | 2009-11-18 | CE
CN
|  |  | 0900842 | Porter |  | Porter County | 2009-12-09 | CE
CN
|  |  | 0900843 | Porter |  | Porter County | 2009-12-09 | CE
CN
|  |  | 0900844 | Porter |  | Porter County | 2009-12-09 | CE
CN
|  |  | 0900845 |  |  | Porter County | -339679.2083
|  |  | 0900846 | Porter |  | Porter County | 2010-01-27 | CE
CN
|  |  | 0900847 |  |  | Porter County | -339679.2083
|  |  | 0900848 | Porter |  | Porter County | 2010-01-27 | CE
CN
|  |  | 0900849 | Porter |  | Porter County | 2010-01-27 | CE
CN
|  |  | 0900850 |  |  | Porter County | -339679.2083
|  |  | 0900851 | Porter | Huff & Huff, Inc. | Portage | 2009-12-09 | CE
CN
|  |  | 0900852 | Porter | Huff & Huff, Inc. | Portage | 2009-12-09 | CE
CN
|  |  | 0900853 | Porter | Huff & Huff, Inc. | Portage | 2009-12-09 | CE
CN
|  |  | 0900854 |  | Huff & Huff, Inc. | Portage | -339679.2083
|  |  | 0900855 | Porter | Huff & Huff, Inc. | Portage | 2009-12-09 | CE
CN
|  |  | 0900856 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2010-01-27 | CE
CN
|  |  | 0900857 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2010-01-27 | CE
CN
|  |  | 0900858 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2009-12-09 | CE
CN
|  |  | 0900859 |  | Edwards and Kelcey | Lowell | -339679.2083
|  |  | 0900860 | Lake |  | Winfield | 2010-01-27 | CE
CN
|  |  | 0900861 |  |  | Winfield | -339679.2083
|  |  | 0900862 | Lake |  | Winfield | 2010-01-27 | CE
CN
|  |  | 0900863 |  |  | Winfield | -339679.2083
|  |  | 0900864 | St. Joseph |  | South Bend | 2009-09-23 | CE
CN
|  |  | 0900865 | St. Joseph |  | South Bend | 2009-10-21 | CE
CN
|  |  | 0900866 | St. Joseph |  | South Bend | 2009-09-23 | CE
CN
|  |  | 0900867 | St. Joseph |  | South Bend | 2009-09-23 | CE
CN
|  |  | 0900868 | St. Joseph |  | South Bend | 2009-10-21 | CE
CN
|  |  | 0900869 | St. Joseph |  | South Bend | 2009-09-23 | CE
CN
|  |  | 0900870 | St. Joseph |  | South Bend | 2009-09-23 | CE
CN
|  |  | 0900871 | St. Joseph |  | South Bend | 2009-10-21 | CE
CN
|  |  | 0900872 | St. Joseph |  | South Bend | 2009-10-21 | CE
CN
|  |  | 0900873 | St. Joseph |  | South Bend | 2009-10-21 | CE
CN
|  |  | 0900874 | St. Joseph |  | South Bend | 2009-09-23 | CE
CN
|  |  | 0900875 |  |  | South Bend | -339679.2083
|  |  | 0900876 | St. Joseph |  | South Bend | 2010-01-27 | CE
CN
|  |  | 0900877 | St. Joseph |  | South Bend | 2010-01-27 | CE
CN
|  |  | 0900878 |  |  | South Bend | -339679.2083
|  |  | 0900879 |  |  | South Bend | -339679.2083
|  |  | 0900880 |  |  | South Bend | -339679.2083
|  |  | 0900881 |  |  | South Bend | -339679.2083
|  |  | 0900882 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0900883 |  |  | Jennings County | -339679.2083
|  |  | 0900884 |  |  | Jennings County | -339679.2083
|  |  | 0900885 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900886 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900887 |  |  | Jennings County | -339679.2083
|  |  | 0900888 |  |  | Jennings County | -339679.2083
|  |  | 0900889 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900890 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2009-12-09 | CE
CN
|  |  | 0900891 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2009-12-09 | CE
CN
|  |  | 0900892 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0900893 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0900894 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0900895 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0900896 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 0900897 | Ohio |  | Ohio County | 2009-10-21 | CE
CN
|  |  | 0900898 | Ohio |  | Ohio County | 2009-10-21 | CE
CN
|  |  | 0900899 | Ohio |  | Ohio County | 2009-10-21 | CE
CN
|  |  | 0900900 | Morgan |  | Morgan County | 2009-10-21 | CE
CN
|  |  | 0900901 | Morgan |  | Morgan County | 2009-10-21 | CE
CN
|  |  | 0900902 | Morgan |  | Morgan County | 2009-10-21 | CE
CN
|  |  | 0900903 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0900904 | Wells | Accidental Discoveries, LLC | Bluffton | 2009-09-23 | CE
CN
|  |  | 0900905 | Wells | Accidental Discoveries, LLC | Bluffton | 2009-09-23 | CE
CN
|  |  | 0900906 | Wells | Accidental Discoveries, LLC | Bluffton | 2009-09-23 | CE
CN
|  |  | 0900907 |  |  | Greensburg | -339679.2083
|  |  | 0900908 | Putnam |  | Putnam County | 2013-07-10 | CE
CN
PE
ROW
|  |  | 0900909 | Putnam |  | Putnam County | 2015-10-07 | CE
CN
PE
ROW
|  |  | 0900910 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2013-07-10 | CE
CN
|  |  | 0900911 | Lake | Karen | St. John | 2010-01-27 | CE
UT
|  |  | 0900912 |  | Karen | St. John | -339679.2083
|  |  | 0900913 |  | Karen | St. John | -339679.2083
|  |  | 0900914 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 0900915 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2009-12-09 | CE
CN
|  |  | 0900916 | Morgan |  | Morgan County | 2009-10-21 | CE
CN
|  |  | 0900917 | Morgan |  | Morgan County | 2009-10-21 | CE
CN
|  |  | 0900918 | Morgan |  | Morgan County | 2009-10-21 | CE
CN
|  |  | 0900919 | Marion | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0900920 | Hamilton | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CN
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CE
|  |  | 0900921 | Hamilton | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CN
|  |  | 0900922 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900923 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0900924 | Hamilton | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CN
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0900925 | Marion | Another Test Company | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0900926 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900927 | Hamilton | Another Test Company | Indiana Department of Transportation | 2010-10-20 | CE
CN
UT
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2010-10-20 | CE
CN
UT
|  |  | 0900928 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0900929 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0900930 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900931 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900932 | Jennings |  | Jennings County | 2010-01-27 | CE
CN
|  |  | 0900933 |  |  | North Vernon | -339679.2083
|  |  | 0900934 |  |  | North Vernon | -339679.2083
|  |  | 0900935 | Jennings |  | North Vernon | 2009-10-21 | CE
CN
|  |  | 0900936 |  |  | North Vernon | -339679.2083
|  |  | 0900937 | Fountain |  | Fountain County | 2010-01-27 | CE
CN
|  |  | 0900938 | Fountain |  | Fountain County | 2010-01-27 | CE
CN
|  |  | 0900939 | Fountain |  | Fountain County | 2010-01-27 | CE
CN
|  |  | 0900940 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0900941 | Jefferson | Engineering Resources, Inc. | Madison | 2009-07-29 | CE
CN
|  |  | 0900942 |  |  | North Vernon | -339679.2083
|  |  | 0900943 |  |  | North Vernon | -339679.2083
|  |  | 0900944 | Cass | Chemical Dependency Program of Indiana | Galveston | 2009-08-26 | CN
|  |  | 0900945 | Cass | J. H. Rudolph & Co., Inc. | Galveston | 2009-08-26 | CN
|  |  | 0900946 | Cass | MCCARTIN - ASSOCIATES | Galveston | 2009-08-26 | CN
|  |  | 0900947 |  |  | Starke County | -339679.2083
|  |  | 0900948 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900949 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900950 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900951 |  |  | St. Joseph County | -339679.2083
|  |  | 0900952 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900953 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900954 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900955 | St. Joseph | M.A.T. Consulting, Inc. | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900956 | St. Joseph | HDR Engineering, Inc. | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900957 | St. Joseph | M.A.T. Consulting, Inc. | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900958 | St. Joseph | Dummy Consulting Firm Too | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900959 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900960 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900961 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900962 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900963 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900964 | St. Joseph | M.A.T. Consulting, Inc. | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900965 | St. Joseph | HDR Engineering, Inc. | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900966 | St. Joseph | Gensic Engineering, Inc. | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900967 | St. Joseph | Dummy Consulting Firm Too | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900968 | St. Joseph |  | St. Joseph County | 2009-08-26 | CE
CN
|  |  | 0900969 | Lake |  | Lake County | 2009-12-09 | CE
CN
|  |  | 0900970 | Lake |  | Lake County | 2009-12-09 | CE
CN
|  |  | 0900971 |  |  | Vermillion County | -339679.2083
|  |  | 0900972 |  |  | Vermillion County | -339679.2083
|  |  | 0900973 |  |  | Vermillion County | -339679.2083
|  |  | 0900974 |  |  | Vermillion County | -339679.2083
|  |  | 0900975 |  |  | Vermillion County | -339679.2083
|  |  | 0900976 |  |  | Vermillion County | -339679.2083
|  |  | 0900977 |  |  | Vermillion County | -339679.2083
|  |  | 0900978 |  |  | Vermillion County | -339679.2083
|  |  | 0900979 |  |  | Parke County | -339679.2083
|  |  | 0900980 |  |  | Parke County | -339679.2083
|  |  | 0900981 |  |  | Parke County | -339679.2083
|  |  | 0900982 | Pike |  | Pike County | 2009-11-18 | CE
CN
|  |  | 0900983 | Pike |  | Pike County | 2009-11-18 | CE
CN
|  |  | 0900984 |  |  | Pike County | -339679.2083
|  |  | 0900985 |  |  | Pike County | -339679.2083
|  |  | 0900986 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0900987 | Perry |  | Tell City | 2009-11-18 | CE
CN
|  |  | 0900988 | Dekalb |  | Dekalb County | 2009-08-26 | CE
CN
|  |  | 0900989 | Grant |  | Grant County | -339679.2083 | CN
|  |  | 0900990 | Delaware |  | Delaware County | 2018-03-14 | CE
CN
PE
ROW
|  |  | 0900991 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0900992 |  |  | Scottsburg | -339679.2083
|  |  | 0900993 | Dekalb | Mader Design, LLC | Waterloo | 2009-07-29 | CE
CN
|  |  | 0900994 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0900995 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0900996 | Dekalb | Mader Design, LLC | Waterloo | 2009-07-29 | CE
CN
|  |  | 0900997 | Dekalb | Mader Design, LLC | Waterloo | 2009-07-29 | CE
CN
|  |  | 0900998 | Dekalb | Mader Design, LLC | Waterloo | 2009-07-29 | CE
CN
|  |  | 0900999 | Dekalb | Mader Design, LLC | Waterloo | 2009-07-29 | CE
CN
|  |  | 0901000 | Dekalb | Mader Design, LLC | Waterloo | 2009-07-29 | CE
CN
|  |  | 0901001 |  | Mader Design, LLC | Waterloo | -339679.2083
|  |  | 0901002 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901003 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26 | CE
CN
|  |  | 0901004 | Lake | Edwards and Kelcey | Lake County | 2009-11-18 | CE
CN
|  |  | 0901005 | Lake | Edwards and Kelcey | Lake County | 2009-11-18 | CE
CN
|  |  | 0901006 |  |  | Lake County | -339679.2083
|  |  | 0901007 |  |  | Lake County | -339679.2083
|  |  | 0901008 |  |  | Lake County | -339679.2083
|  |  | 0901009 |  |  | Lake County | -339679.2083
|  |  | 0901010 |  |  | Lake County | -339679.2083
|  |  | 0901011 |  |  | Lake County | -339679.2083
|  |  | 0901012 |  |  | Lake County | -339679.2083
|  |  | 0901013 |  |  | Lake County | -339679.2083
|  |  | 0901014 |  |  | Lake County | -339679.2083
|  |  | 0901015 |  |  | Lake County | -339679.2083
|  |  | 0901016 |  |  | Lake County | -339679.2083
|  |  | 0901017 |  |  | Lake County | -339679.2083
|  |  | 0901018 |  |  | Lake County | -339679.2083
|  |  | 0901019 |  |  | Lake County | -339679.2083
|  |  | 0901020 |  |  | Lake County | -339679.2083
|  |  | 0901021 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0901022 | Scott |  | Scottsburg | 2010-01-27 | CE
CN
|  |  | 0901023 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0901024 | Perry |  | Perry County | 2009-11-18 | CE
CN
|  |  | 0901025 |  |  | Howard County | -339679.2083
|  |  | 0901026 | Clark |  | Clark County | 2009-08-26 | CE
CN
|  |  | 0901027 | Clark |  | Clark County | 2009-07-29 | CE
CN
|  |  | 0901028 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 0901029 | Clark |  | Clark County | 2009-08-26 | CE
CN
|  |  | 0901030 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0901031 | Howard |  | Howard County | 2009-08-26 | CE
CN
|  |  | 0901032 | Hamilton |  | Hamilton County | 2010-02-24 | CE
CN
|  |  | 0901033 |  |  | Hamilton County | -339679.2083
|  |  | 0901034 |  |  | Elwood | -339679.2083
|  |  | 0901035 |  |  | Elwood | -339679.2083
|  |  | 0901036 | Wayne |  | Richmond | 2009-08-26 | CE
CN
|  |  | 0901037 | Wayne |  | Richmond | 2009-08-26 | CE
CN
|  |  | 0901038 | Wayne |  | Richmond | 2009-08-26 | CE
CN
|  |  | 0901039 | Fulton |  | Fulton County | 2009-08-26 | CE
CN
|  |  | 0901040 | Fulton |  | Fulton County | 2009-09-23 | CE
CN
|  |  | 0901041 | Lake | Baxter & Woodman, Inc. | Crown Point | 2009-11-18 | CE
CN
|  |  | 0901042 | Lake | Baxter & Woodman, Inc. | Crown Point | 2009-11-18 | CE
CN
|  |  | 0901043 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2009-11-18 | CE
CN
|  |  | 0901044 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2009-11-18 | CE
CN
|  |  | 0901045 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2009-11-18 | CE
CN
|  |  | 0901046 | Fulton |  | Fulton County | 2009-09-23 | CE
CN
|  |  | 0901047 | Fulton |  | Fulton County | 2009-08-26 | CE
CN
|  |  | 0901048 | Fulton |  | Fulton County | 2009-09-23 | CE
CN
|  |  | 0901049 | Fulton |  | Fulton County | 2009-09-23 | CE
CN
|  |  | 0901050 | Clark |  | Clark County | 2009-08-26 | CE
CN
|  |  | 0901051 | Clark |  | Clark County | 2009-09-23 | CE
CN
|  |  | 0901052 | Clark |  | Clark County | 2009-08-26 | CE
CN
|  |  | 0901053 |  |  | Clark County | -339679.2083
|  |  | 0901054 |  |  | Jefferson County | -339679.2083
|  |  | 0901055 |  |  | Jefferson County | -339679.2083
|  |  | 0901056 |  |  | Jefferson County | -339679.2083
|  |  | 0901057 | Jefferson |  | Jefferson County | 2009-09-23 | CE
CN
|  |  | 0901058 |  |  | Winchester | -339679.2083
|  |  | 0901059 | Rush |  | Carthage | 2009-09-23 | CE
CN
|  |  | 0901060 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0901061 |  |  | Jennings County | -339679.2083
|  |  | 0901062 | Clark |  | Clark County | 2009-07-29 | CE
CN
|  |  | 0901063 | Clark |  | Clark County | 2009-08-26 | CE
CN
|  |  | 0901064 |  |  | Huntingburg | -339679.2083
|  |  | 0901065 | Grant | ERES International, Inc. | Marion | 2009-09-23 | CE
CN
|  |  | 0901066 | Grant | ERES International, Inc. | Marion | 2009-09-23 | CE
CN
|  |  | 0901067 | Grant | ERES International, Inc. | Marion | 2009-09-23 | CE
CN
|  |  | 0901068 | Jackson | ERES International, Inc. | Marion | 2009-09-23 | CE
CN
|  |  | 0901069 | Grant | ERES International, Inc. | Marion | 2009-09-23 | CE
CN
|  |  | 0901070 | Grant | ERES International, Inc. | Marion | 2009-08-26 | CE
CN
|  |  | 0901071 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901072 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901073 | Floyd |  | New Albany | 2009-12-09 | CE
CN
|  |  | 0901074 | Monroe |  | Monroe County | 2009-11-18 | CE
CN
|  |  | 0901075 |  |  | Monroe County | -339679.2083
|  |  | 0901076 | Monroe |  | Monroe County | 2009-10-21 | CE
CN
|  |  | 0901077 | Monroe |  | Monroe County | 2009-10-21 | CE
CN
|  |  | 0901078 | Monroe |  | Monroe County | 2009-10-21 | CE
CN
|  |  | 0901079 | Monroe |  | Monroe County | 2009-10-21 | CE
CN
|  |  | 0901080 | Marion |  | Beech Grove | 2010-01-27 | CE
CN
|  |  | 0901081 | Hamilton |  | Noblesville | 2009-12-09 | CE
CN
|  |  | 0901082 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901083 | Floyd |  | Floyd County | 2009-12-09 | CE
CN
|  |  | 0901084 | Floyd |  | Floyd County | 2009-10-21 | CE
CN
|  |  | 0901085 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901086 | Grant |  | Grant County | 2009-07-29 | CE
CN
|  |  | 0901087 | Grant | ERES International, Inc. | Grant County | 2009-07-29 | CE
CN
|  |  | 0901088 | Grant |  | Grant County | 2009-07-29 | CE
CN
|  |  | 0901089 | Grant |  | Grant County | 2009-07-29 | CE
CN
|  |  | 0901090 | Grant |  | Grant County | 2009-07-29 | CE
CN
|  |  | 0901091 | Grant |  | Grant County | 2009-07-29 | CE
CN
|  |  | 0901092 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901093 | Marshall |  | Marshall County | 2009-08-26 | CE
CN
|  |  | 0901094 |  |  | Greencastle | -339679.2083
|  |  | 0901095 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 0901096 | Blackford | Continental Mapping Consultants, LLC | Hartford City | 2009-07-29 | CE
CN
|  |  | 0901097 | Dekalb |  | Dekalb County | 2009-07-29 | CE
CN
|  |  | 0901098 | Dekalb | Quantum Spatial, Inc. | Auburn | 2009-07-29 | CE
CN
|  |  | 0901099 | Dekalb | Quantum Spatial, Inc. | Auburn | 2009-07-29 | CE
CN
|  |  | 0901100 | Hendricks |  | Avon | 2009-11-18 | CE
CN
|  |  | 0901101 | Hendricks |  | Avon | 2009-09-23 | CE
CN
|  |  | 0901102 | Tippecanoe |  | West Lafayette | 2009-10-21 | CE
CN
|  |  | 0901103 |  |  | Tippecanoe County | -339679.2083
|  |  | 0901104 |  |  | Tippecanoe County | -339679.2083
|  |  | 0901105 | Crawford | First Group Engineering, Inc. | Crawford County | 2016-08-10 | CE
CN
PE
ROW
RR
|  |  | 0901106 | Hamilton |  | Noblesville | 2010-04-28 | CE
CN
|  |  | 0901107 | Gibson | CSR Engineering, Inc. | Gibson County | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  | 0901108 |  |  | Martin County | -339679.2083
|  |  | 0901109 | Knox |  | Knox County | -339679.2083 | PE
|  |  | 0901110 | Marion |  | Indianapolis | 2009-11-18 | CE
CN
RR
|  |  | 0901111 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0901112 | Tippecanoe |  | Tippecanoe County | 2009-12-09 | CE
CN
|  |  | 0901113 | Lake |  | Lake County | 2009-12-09 | CE
CN
|  |  | 0901114 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 0901115 | Ripley |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0901116 | Noble |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 0901117 | Rush | CoCal Consulting, LLC | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0901118 | Perry |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0901119 | Perry |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 0901120 | Vigo |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 0901121 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2014-05-31 | PE
|  |  | 0901122 | Daviess | AMEC E&I, Inc. | Washington | 2009-11-18 | CE
CN
|  |  | 0901123 | Daviess | AMEC E&I, Inc. | Washington | 2009-11-18 | CE
CN
|  |  | 0901124 | Daviess | AMEC E&I, Inc. | Washington | 2009-11-18 | CE
CN
|  |  | 0901125 | Daviess | AMEC E&I, Inc. | Washington | 2009-11-18 | CE
CN
|  |  | 0901126 | Scott |  | Scott County | 2009-10-21 | CE
CN
|  |  | 0901127 | Marion |  | Lawrence | 2010-02-24 | CE
CN
|  |  | 0901128 | Marion |  | Indianapolis | 2009-11-18 | CE
CN
|  |  | 0901129 | Floyd |  | Floyd County | 2010-01-27 | CE
CN
|  |  | 0901130 | Washington |  | Salem | 2009-09-23 | CE
CN
|  |  | 0901131 | Marion |  | Indianapolis | 2009-12-09 | CE
CN
|  |  | 0901132 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901133 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901134 | Marion |  | Indianapolis | 2009-12-09 | CE
CN
|  |  | 0901135 | Jasper |  | Jasper County | 2012-12-12 | CE
CN
PE
|  |  | 0901136 | Lake | Dummy Consulting Firm | Lake Station | 2009-12-09 | CE
CN
|  |  | 0901137 | LaPorte |  | LaPorte County | 2009-12-09 | CE
CN
|  |  | 0901138 | Lake | Baxter & Woodman, Inc. | Crown Point | 2010-01-27 | CE
CN
|  |  | 0901139 | Pulaski |  | Pulaski County | 2009-12-09 | CE
CN
|  |  | 0901140 | Porter |  | Chesterton | 2009-12-09 | CE
CN
|  |  | 0901141 | Porter |  | Chesterton | 2009-12-09 | CE
CN
|  |  | 0901142 | Porter |  | Chesterton | 2009-12-09 | CE
CN
|  |  | 0901143 |  |  | Switzerland County | -339679.2083
|  |  | 0901144 |  |  | Decatur County | -339679.2083
|  |  | 0901145 | Washington |  | Salem | 2009-09-23 | CE
CN
|  |  | 0901146 |  |  | Batesville | -339679.2083
|  |  | 0901147 |  |  | Washington County | -339679.2083
|  |  | 0901148 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901149 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901150 |  |  | Washington County | -339679.2083
|  |  | 0901151 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901152 | Hamilton |  | Hamilton County | 2010-01-27 | CE
CN
|  |  | 0901153 | Marion |  | Southport | 2009-12-09 | CE
CN
|  |  | 0901154 | Hamilton |  | Fishers | 2009-10-21 | CE
CN
|  |  | 0901155 | Wabash |  | Wabash County | 2009-08-26 | CE
CN
|  |  | 0901156 | Hamilton |  | Fishers | 2009-10-21 | CE
CN
|  |  | 0901157 | Hamilton |  | Fishers | 2009-10-21 | CE
CN
|  |  | 0901158 |  |  | Monroe County | -339679.2083
|  |  | 0901159 | Hamilton |  | Fishers | 2009-10-21 | CE
CN
|  |  | 0901160 | Hamilton |  | Fishers | 2009-10-21 | CE
CN
|  |  | 0901161 |  |  | Monroe County | -339679.2083
|  |  | 0901162 | Hamilton |  | Fishers | 2009-10-21 | CE
CN
|  |  | 0901163 | Hamilton |  | Carmel | 2010-01-29 | CE
CN
|  |  | 0901164 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 0901165 | Marion |  | Meridian Hills | 2009-11-18 | CE
CN
|  |  | 0901166 | Blackford | Continental Mapping Consultants, LLC | Hartford City | 2009-08-26 | CE
CN
|  |  | 0901167 | Marion |  | Beech Grove | 2009-12-09 | CE
CN
|  |  | 0901168 | Johnson |  | Johnson County | 2009-11-18 | CE
CN
|  |  | 0901169 | Johnson |  | Johnson County | 2009-11-18 | CE
CN
|  |  | 0901170 | Johnson |  | Johnson County | 2009-11-18 | CE
CN
|  |  | 0901171 | Johnson |  | Johnson County | 2009-11-18 | CE
CN
|  |  | 0901172 | Morgan |  | Morgan County | 2009-12-09 | CE
CN
|  |  | 0901173 | Delaware |  | Muncie | 2009-10-21 | CE
CN
|  |  | 0901174 | Delaware |  | Muncie | 2009-10-21 | CE
CN
|  |  | 0901175 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0901176 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0901177 | Wayne |  | Wayne County | 2009-10-21 | CE
CN
|  |  | 0901178 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0901179 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0901180 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0901181 | Wayne |  | Wayne County | 2009-08-26 | CE
CN
|  |  | 0901182 | Wayne |  | Richmond | 2009-08-26 | CE
CN
|  |  | 0901183 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901184 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0901185 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 0901186 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 0901187 | Steuben |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 0901188 | Hancock |  | Indiana Department of Transportation | 2009-09-23 | CE
CN
|  |  | 0901189 |  |  | Crawford County | -339679.2083
|  |  | 0901190 |  |  | Gibson County | -339679.2083
|  |  | 0901191 |  |  | Gibson County | -339679.2083
|  |  | 0901192 |  |  | Gibson County | -339679.2083
|  |  | 0901193 |  |  | Gibson County | -339679.2083
|  |  | 0901194 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0901195 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901196 | Boone |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
ROW
|  |  | 0901197 |  |  | Jennings County | -339679.2083
|  |  | 0901198 | Jackson |  | Jackson County | 2010-01-27 | CE
CN
|  |  | 0901199 |  |  | Noble County | -339679.2083
|  |  | 0901200 | Jefferson |  | Jefferson County | 2009-12-09 | CE
CN
|  |  | 0901201 | Dekalb | KZF Design, Inc. | St. Joe | 2009-08-26 | CE
CN
|  |  | 0901202 |  |  | Jefferson County | -339679.2083
|  |  | 0901203 | Dekalb |  | Dekalb County | 2009-08-26 | CE
CN
|  |  | 0901204 |  |  | Orange County | -339679.2083
|  |  | 0901205 |  |  | Orange County | -339679.2083
|  |  | 0901206 |  |  | Orange County | -339679.2083
|  |  | 0901207 |  |  | Morgan County | -339679.2083
|  |  | 0901208 | Clay |  | Clay County | 2009-11-18 | CE
CN
|  |  | 0901209 | Tippecanoe |  | Tippecanoe County | 2010-03-17 | CE
CN
|  |  | 0901210 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901211 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901212 | Cass | Eco Logic, LLC | Logansport | 2010-01-27 | CE
CN
|  |  | 0901213 | Cass | Eco Logic, LLC | Logansport | 2010-01-27 | CE
CN
|  |  | 0901214 |  |  | LaPorte County | -339679.2083
|  |  | 0901215 |  |  | Washington County | -339679.2083
|  |  | 0901216 | Monroe |  | Monroe County | 2010-01-27 | CE
CN
|  |  | 0901217 |  |  | Greencastle | -339679.2083
|  |  | 0901218 | Monroe |  | Monroe County | 2010-01-27 | CE
CN
|  |  | 0901219 |  |  | Monroe County | -339679.2083
|  |  | 0901220 | Monroe |  | Monroe County | 2010-01-27 | CE
CN
|  |  | 0901221 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901222 | Tippecanoe |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
|  |  | 0901223 | Tippecanoe |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
PE
|  |  | 0901224 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901225 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0901226 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0901227 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2010-02-24 | CE
CN
PE
|  |  | 0901228 | Marion |  | Indianapolis | 2009-12-09 | CE
CN
|  |  | 0901229 | Marion |  | Indianapolis | 2009-10-21 | CE
CN
|  |  | 0901230 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901231 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901232 |  |  | Tippecanoe County | -339679.2083
|  |  | 0901233 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901234 | Marion |  | Indianapolis | 2010-01-27 | CE
CN
|  |  | 0901235 | Hamilton |  | Hamilton County | 2009-11-18 | CE
CN
|  |  | 0901236 | Hamilton |  | Hamilton County | 2009-12-09 | CE
CN
|  |  | 0901237 | Hamilton |  | Hamilton County | 2009-12-09 | CE
CN
|  |  | 0901238 | Hamilton |  | Hamilton County | 2009-12-09 | CE
CN
|  |  | 0901239 | Hamilton |  | Hamilton County | 2009-11-18 | CE
CN
|  |  | 0901240 | Hancock |  | Hancock County | 2009-12-09 | CE
CN
|  |  | 0901241 | Hancock |  | Hancock County | 2009-12-09 | CE
CN
|  |  | 0901242 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0901243 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901244 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901245 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901246 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901247 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901248 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901249 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901250 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901252 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901253 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901254 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901255 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901256 | Steuben |  | Steuben County | 2009-09-23 | CE
CN
|  |  | 0901257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901258 | Kosciusko | Fink Roberts & Petrie | Milford (Kosciusko Co) | -339679.2083 | PE
|  |  | 0901259 | Daviess | AMEC E&I, Inc. | Washington | -339679.2083 | PE
|  |  | 0901260 | Marion |  | Indianapolis | -339679.2083 | PE
|  |  | 0901261 | Adams | Bidinfo | Adams County | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0901262 | Steuben | ABt SRBI | Angola | -339679.2083 | PE
|  |  | 0901263 | Warrick | Appraisal Specialists, Inc. | Chandler | -339679.2083 | PE
|  |  | 0901264 | Perry |  | Tell City | -339679.2083 | PE
|  |  | 0901265 | Madison | CE Solutions, Inc. | MPO - Anderson | -339679.2083 | PE
|  |  | 0901266 | Wabash |  | Wabash County | 2013-09-11 | CE
CN
PE
ROW
|  |  | 0901267 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  |  | White | McCormick Engineering, LLC | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 0901268 | Noble |  | Noble County | 2009-08-14 | PE
|  |  | 0901269 |  |  | Madison County | -339679.2083
|  |  | 0901270 |  |  | Hamilton County | -339679.2083
|  |  | 0901271 | Jay |  | Portland | 2009-10-21 | CE
CN
|  |  | 0901272 | Jay |  | Portland | 2009-10-21 | CE
CN
|  |  | 0901273 |  |  | Portland | -339679.2083
|  |  | 0901274 |  |  | Indiana Department of Transportation | 2009-06-03
|  |  | 0901275 | Floyd |  | New Albany | 2017-03-01 | CE
CN
PE
RR
|  |  | 0901276 | Floyd |  | New Albany | 2018-03-14 | CE
CN
PE
ROW
|  |  | 0901277 | Porter | Leitner and Associates, Inc. | Valparaiso | 2010-04-14 | CE
CN
|  |  | 0901278 | Johnson |  | Johnson County | 2010-02-24 | CE
CN
|  |  | 0901279 | Johnson |  | Johnson County | 2010-02-24 | CE
CN
|  |  | 0901280 | Johnson |  | Johnson County | 2010-02-24 | CE
CN
|  |  | 0901281 | Warrick |  | Newburgh | 2009-12-09 | CE
CN
PE
|  |  | 0901282 | Gibson | III FFC | Princeton | 2014-03-05 | CE
CN
PE
ROW
UT
|  |  | 0901283 | Hamilton |  | Hamilton | 2010-02-24 | CE
CN
|  |  | 0901284 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2009-09-23 | CE
CN
|  |  | 0901285 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2009-09-23 | CE
CN
|  |  | 0901286 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2009-09-23 | CE
CN
|  |  | 0901287 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2009-09-23 | CE
CN
|  |  | 0901288 | Hamilton |  | Hamilton | 2010-02-24 | CE
CN
|  |  | 0901289 | Hamilton |  | Hamilton County | 2010-02-24 | CE
CN
|  |  | 0901290 | Hamilton |  | Hamilton County | 2009-11-18 | CE
CN
|  |  | 0901291 | Shelby |  | Shelby County | 2008-11-15 | CN
|  |  | 0901292 | Shelby |  | Shelby County | 2008-11-15 | CN
|  |  | 0901293 | Wayne |  | Wayne County | 2009-09-04 | CN
|  |  | 0901294 |  | Mackie Consultants, LLC | Warsaw | -339679.2083
|  |  | 0901295 |  | Mackie Consultants, LLC | Warsaw | -339679.2083
|  |  | 0901296 |  | Mackie Consultants, LLC | Warsaw | -339679.2083
|  |  | 0901297 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901298 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
UT
|  |  | 0901299 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901300 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901301 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901302 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901303 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901304 |  |  | Crawfordsville | -339679.2083
|  |  | 0901305 |  |  | Crawfordsville | -339679.2083
|  |  | 0901306 |  |  | Crawfordsville | -339679.2083
|  |  | 0901307 |  |  | Cumberland | -339679.2083
|  |  | 0901308 |  |  | Crawfordsville | -339679.2083
|  |  | 0901309 |  |  | Crawfordsville | -339679.2083
|  |  | 0901310 |  |  | Crawfordsville | -339679.2083
|  |  | 0901311 |  |  | Crawfordsville | -339679.2083
|  |  | 0901312 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2009-09-01
|  |  | 0901313 | Delaware |  | Selma | 2010-01-27 | CE
CN
|  |  | 0901314 | Delaware |  | Yorktown | 2010-03-31 | CE
CN
|  |  | 0901315 | Delaware |  | Delaware County | 2010-01-27 | CE
CN
|  |  | 0901316 | Lake | Brenner Design Incorporated | Dyer | 2009-12-09 | CE
CN
|  |  | 0901317 | Lake | Brenner Design Incorporated | Dyer | 2009-12-09 | CE
CN
|  |  | 0901318 |  | Consolidated Test Company | Hammond | 2010-01-13
|  |  | 0901319 | Wayne |  | Indiana State Agencies | -339679.2083 | PE
|  |  | 0901320 |  |  | Darmstadt | -339679.2083
|  |  | 0901321 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 0901322 | Switzerland |  | Indiana Department of Transportation | 2011-08-24 | CE
CN
|  |  | 0901323 | Huntington |  | Huntington County | 2009-08-26 | CE
CN
|  |  | 0901324 | Huntington |  | Huntington County | 2009-08-26 | CE
CN
|  |  | 0901325 | Huntington |  | Huntington County | 2009-09-23 | CE
CN
|  |  | 0901326 | Orange |  | Orange County | -339679.2083 | CN
|  |  | 0901327 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901328 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901329 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901330 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901331 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901332 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901333 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901334 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901335 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 0901336 | St. Joseph |  | St. Joseph County | 2010-01-27 | CE
CN
|  |  | 0901337 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901338 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901339 | St. Joseph |  | St. Joseph County | 2010-01-27 | CE
CN
|  |  | 0901340 | St. Joseph |  | St. Joseph County | 2010-01-27 | CE
CN
|  |  | 0901341 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901342 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901343 | St. Joseph |  | St. Joseph County | 2010-01-27 | CE
CN
|  |  | 0901344 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901345 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901346 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901347 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901348 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901349 |  |  | St. Joseph County | -339679.2083
|  |  | 0901350 |  |  | St. Joseph County | -339679.2083
|  |  | 0901351 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901352 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901353 | St. Joseph |  | St. Joseph County | 2009-11-18 | CE
CN
|  |  | 0901354 | St. Joseph |  | St. Joseph County | 2009-11-18 | CE
CN
|  |  | 0901355 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901356 | Tippecanoe |  | Tippecanoe County | 2010-02-24 | CE
CN
|  |  | 0901357 | St. Joseph |  | St. Joseph County | 2010-01-27 | CE
CN
|  |  | 0901358 | St. Joseph |  | St. Joseph County | 2009-10-21 | CE
CN
|  |  | 0901359 | Clinton |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0901360 | Hendricks |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0901361 | Boone |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0901362 | Jay |  | Jay County | 2009-09-23 | CE
CN
|  |  | 0901363 | Owen |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0901364 |  |  | Wayne County | -339679.2083
|  |  | 0901365 | Jay |  | Jay County | 2009-11-18 | CE
CN
|  |  | 0901366 | Jay |  | Jay County | 2009-09-23 | CE
CN
|  |  | 0901367 | Jay |  | Jay County | 2009-11-18 | CE
CN
|  |  | 0901368 |  |  | Elkhart County | -339679.2083
|  |  | 0901369 |  |  | Elkhart County | -339679.2083
|  |  | 0901370 |  |  | Elkhart County | -339679.2083
|  |  | 0901371 |  |  | Elkhart County | -339679.2083
|  |  | 0901372 |  |  | Portland | -339679.2083
|  |  | 0901373 |  |  | Portland | -339679.2083
|  |  | 0901374 | Jay |  | Portland | 2009-11-18 | CE
CN
|  |  | 0901375 | Jay |  | Portland | 2009-11-18 | CE
CN
|  |  | 0901376 |  |  | Portland | -339679.2083
|  |  | 0901377 |  |  | Portland | -339679.2083
|  |  | 0901378 |  |  | Portland | -339679.2083
|  |  | 0901379 | Jay |  | Portland | 2009-11-18 | CE
CN
|  |  | 0901380 |  |  | Portland | -339679.2083
|  |  | 0901381 |  |  | Portland | -339679.2083
|  |  | 0901382 |  |  | Portland | -339679.2083
|  |  | 0901383 |  |  | Portland | -339679.2083
|  |  | 0901384 | Rush |  | Rush County | 2009-09-23 | CE
CN
|  |  | 0901385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901386 | Rush |  | Rush County | 2009-09-23 | CE
CN
|  |  | 0901387 |  |  | Indiana Department of Transportation | 2009-08-12
|  |  | 0901388 | Rush |  | Rushville | 2009-09-23 | CE
CN
|  |  | 0901389 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901390 | Rush |  | Rushville | 2009-09-23 | CE
CN
|  |  | 0901391 | Gibson |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0901392 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901394 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0901395 | Grant |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0901396 | Kosciusko |  | Indiana Department of Transportation | 2009-09-21 | RR
|  |  | 0901397 |  |  | Clark County | -339679.2083
|  |  | 0901398 |  |  | Indiana Department of Transportation | 2009-11-04
|  |  | 0901399 | Wabash |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0901400 | Wabash |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0901401 | White |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0901402 | White |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 0901404 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0901405 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0901406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901407 | Hamilton |  | Indiana Department of Transportation | 2011-02-23 | CE
CN
|  |  | 0901408 | Vigo |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 0901409 | Elkhart |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0901410 | Fulton |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  |  | Miami |  | Indiana Department of Transportation | 2009-11-18 | CE
CN
|  |  | 0901411 | Elkhart |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  |  | Noble |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0901412 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901413 | Howard |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
PE
ROW
|  |  | 0901414 | Howard |  | Indiana Department of Transportation | 2011-05-13 | CE
CN
PE
ROW
|  |  | 0901415 | Howard |  | Indiana Department of Transportation | 2011-05-13 | CE
CN
PE
ROW
|  |  | 0901416 | Floyd |  | Floyd County | 2010-01-27 | CE
CN
|  |  | 0901417 | Howard |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901418 | Floyd |  | Floyd County | 2010-01-27 | CE
CN
|  |  | 0901419 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901420 |  |  | Indiana Department of Transportation | 2009-10-07
|  |  | 0901421 | LaPorte |  | Indiana Department of Transportation | 2009-09-10 | CE
CN
|  |  | 0901422 | Monroe |  | Bloomington | 2010-02-24 | CE
CN
|  |  | 0901423 | Wells |  | Wells County | -339679.2083 | CN
|  |  | 0901424 |  | Driesenga & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901425 |  |  | Elkhart County | -339679.2083
|  |  | 0901426 |  |  | Elkhart County | -339679.2083
|  |  | 0901427 |  |  | Elkhart County | -339679.2083
|  |  | 0901428 | Starke |  | Starke County | 2010-02-24 | CE
CN
|  |  | 0901429 |  |  | Seymour | -339679.2083
|  |  | 0901430 |  | LONCO, Inc. | Syracuse | -339679.2083
|  |  | 0901431 |  | LONCO, Inc. | Syracuse | -339679.2083
|  |  | 0901432 |  |  | Martin County | -339679.2083
|  |  | 0901433 |  |  | Martin County | -339679.2083
|  |  | 0901434 |  |  | Martin County | -339679.2083
|  |  | 0901435 |  |  | Elkhart County | -339679.2083
|  |  | 0901436 |  |  | Elkhart County | -339679.2083
|  |  | 0901437 |  |  | Elkhart County | -339679.2083
|  |  | 0901438 |  |  | Elkhart County | -339679.2083
|  |  | 0901439 | Tippecanoe |  | Tippecanoe County | 2009-12-09 | CE
CN
|  |  | 0901440 |  |  | Elkhart County | -339679.2083
|  |  | 0901441 | Tippecanoe |  | Tippecanoe County | 2009-11-18 | CE
CN
|  |  | 0901442 |  |  | Elkhart County | -339679.2083
|  |  | 0901443 |  |  | Elkhart County | -339679.2083
|  |  | 0901444 |  |  | Elkhart County | -339679.2083
|  |  | 0901445 |  |  | Elkhart County | -339679.2083
|  |  | 0901446 |  |  | Elkhart County | -339679.2083
|  |  | 0901447 |  |  | Indiana Department of Transportation | 2009-06-05
|  |  | 0901448 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0901449 | Dekalb | Quantum Spatial, Inc. | Auburn | 2010-01-27 | CE
CN
|  |  | 0901450 | Dekalb |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  |  | Steuben |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901451 | Steuben |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901452 |  |  | LaPorte County | -339679.2083
|  |  | 0901453 | LaPorte |  | LaPorte County | 2011-11-16 | CE
CN
PE
|  |  | 0901454 | Lake |  | Merrillville | 2012-03-07 | CE
CN
ROW
|  |  | 0901455 | Fountain |  | Covington | 2010-01-27 | CE
CN
|  |  | 0901456 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901458 | Tippecanoe |  | Tippecanoe County | 2009-11-18 | CE
CN
|  |  | 0901459 |  |  | Gibson County | -339679.2083
|  |  | 0901460 | Knox |  | Knox County | -339679.2083 | CN
PE
|  |  | 0901461 | Posey |  | Posey County | -339679.2083 | CN
PE
|  |  | 0901462 | Floyd |  | Indiana Department of Transportation | 2014-05-31 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2014-05-31 | PE
|  |  | 0901463 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901464 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 0901465 | Pulaski |  | Pulaski County | 2009-12-09 | CE
CN
|  |  | 0901466 | Porter | ATSI Engineering Services | Beverly Shores | 2009-12-09 | CE
CN
|  |  | 0901467 | Howard |  | Kokomo | 2013-05-01 | CE
CN
|  |  | 0901468 | Grant | Chicago Title Insurance Company | Gas City | 2010-02-24 | CE
CN
|  |  | 0901469 | Grant | Chicago Title Insurance Company | Gas City | 2010-02-24 | CE
CN
|  |  | 0901470 | Grant | Chicago Title Insurance Company | Gas City | 2010-02-24 | CE
CN
|  |  | 0901471 | Grant | Chicago Title Insurance Company | Gas City | 2010-02-24 | CE
CN
|  |  | 0901472 | Grant | Chicago Title Insurance Company | Gas City | 2010-02-24 | CE
CN
|  |  | 0901473 | Dekalb | KZF Design, Inc. | St. Joe | 2009-12-09 | CE
CN
|  |  | 0901474 |  |  | Greencastle | -339679.2083
|  |  | 0901475 |  |  | Greencastle | -339679.2083
|  |  | 0901476 |  |  | Seymour | -339679.2083
|  |  | 0901477 |  |  | Cumberland | -339679.2083
|  |  | 0901478 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0901479 |  | Another Test Company | Indiana Department of Transportation | 2009-11-06
|  |  | 0901480 | Elkhart | Civil Inspection Services, LLC | Goshen | 2009-10-21 | CE
CN
|  |  | 0901481 | Elkhart | Civil Inspection Services, LLC | Goshen | 2009-10-21 | CE
CN
|  |  | 0901482 | Adams |  | Adams County | 2010-02-24 | CE
CN
|  |  | 0901483 | Adams |  | Adams County | 2010-02-24 | CE
CN
|  |  | 0901484 | Adams |  | Adams County | 2010-02-24 | CE
CN
|  |  | 0901485 | Adams |  | Adams County | 2010-02-24 | CE
CN
|  |  | 0901486 | Adams |  | Adams County | 2010-02-24 | CE
CN
|  |  | 0901487 | Wayne |  | Centerville | 2009-10-21 | CE
CN
|  |  | 0901488 |  |  | Greencastle | -339679.2083
|  |  | 0901489 | Steuben |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 0901490 | Steuben |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 0901491 | Grant |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0901492 |  |  | Greencastle | -339679.2083
|  |  | 0901493 | Tippecanoe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 0901494 | Dekalb | Cheri K. Lewis Engineers | Garrett | 2010-02-24 | CE
CN
|  |  | 0901495 | Dekalb | Cheri K. Lewis Engineers | Garrett | 2010-02-24 | CE
CN
|  |  | 0901496 | Allen | Metropolitan Abstracting Consultants, LLC | Woodburn | 2010-02-24 | CE
CN
|  |  | 0901497 | Allen | Metropolitan Abstracting Consultants, LLC | Woodburn | 2010-02-24 | CE
CN
|  |  | 0901498 | Allen | Metropolitan Abstracting Consultants, LLC | Woodburn | 2010-02-24 | CE
CN
|  |  | 0901499 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901500 | Various |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
[6 empty] | Indiana Department of Transportation | 2014-05-31
|  |  | 0901501 | Various |  | Indiana Department of Transportation | 2014-05-31 | CE
PE
[6 empty] | Indiana Department of Transportation | 2014-05-31
|  |  | 0901502 | Hancock |  | Hancock County | 2010-02-24 | CE
CN
|  |  | 0901503 | Hancock |  | Hancock County | 2010-02-24 | CE
CN
|  |  | 0901504 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0901505 | LaPorte | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2010-01-27 | CE
CN
|  |  | 0901506 | Monroe |  | Bloomington | 2009-12-09 | CE
CN
|  |  | 0901507 | Kosciusko |  | Kosciusko County | -339679.2083 | CN
|  |  | 0901508 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901509 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901510 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 0901511 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901512 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901513 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901514 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901515 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0901516 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 0901517 | Madison |  | Pendleton | 2009-12-09 | CE
CN
|  |  | 0901518 | Madison |  | Alexandria | 2009-12-09 | CE
CN
|  |  | 0901519 | Madison |  | Madison County | 2010-02-24 | CE
CN
|  |  | 0901520 | St. Joseph |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0901521 | Madison |  | Madison County | 2010-02-24 | CE
CN
|  |  | 0901522 | Madison |  | Madison County | 2010-02-24 | CE
CN
|  |  | 0901523 | Madison |  | Madison County | 2010-02-24 | CE
CN
|  |  | 0901524 | Madison |  | Madison County | 2010-02-24 | CE
CN
|  |  | 0901525 |  |  | Ingalls | -339679.2083
|  |  | 0901526 | St. Joseph |  | South Bend | 2012-01-11 | CE
CN
|  |  | 0901527 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2012-09-12 | CE
CN
|  |  | 0901528 |  |  | Anderson | -339679.2083
|  |  | 0901529 | Hamilton |  | Noblesville | 2010-02-24 | CE
CN
|  |  | 0901530 | Hamilton |  | Noblesville | 2010-02-24 | CE
CN
|  |  | 0901531 | Hamilton |  | Noblesville | 2010-02-24 | CE
CN
|  |  | 0901532 | Switzerland |  | Switzerland County | -339679.2083 | CN
|  |  | 0901533 | Noble | Debbie L. Morris | Kendallville | 2010-02-24 | CE
CN
|  |  | 0901534 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901535 | Noble | Debbie L. Morris | Kendallville | 2010-02-24 | CE
CN
RR
|  |  | 0901536 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901537 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901538 | Noble | Debbie L. Morris | Kendallville | 2010-02-24 | CE
CN
|  |  | 0901539 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901540 | Monroe |  | Monroe County | 2009-12-09 | CE
CN
|  |  | 0901541 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901542 | Noble | Debbie L. Morris | Kendallville | 2010-02-24 | CE
CN
|  |  | 0901543 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901544 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901545 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901546 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901547 | Clark |  | Clarksville | 2009-12-09 | CE
CN
|  |  | 0901548 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901549 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901550 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 0901551 | Noble | Debbie L. Morris | Kendallville | 2010-02-24 | CE
CN
|  |  | 0901552 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901553 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901554 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901555 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901556 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901557 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901558 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901559 | Allen | Global Management Group, Inc. | New Haven | 2009-10-21 | CE
CN
|  |  | 0901560 |  |  | Fishers | -339679.2083
|  |  | 0901561 | Hendricks |  | Avon | 2010-03-17 | CE
CN
|  |  | 0901562 |  |  | Carmel | -339679.2083
|  |  | 0901563 | Tippecanoe |  | Tippecanoe County | 2009-11-18 | CE
CN
|  |  | 0901564 |  | AES Services, Inc. | Avilla | -339679.2083
|  |  | 0901565 |  |  | Frankfort | -339679.2083
|  |  | 0901566 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2011-11-02 | CE
CN
PE
|  |  | 0901567 | Hamilton |  | Fishers | 2011-05-11 | CE
CN
|  |  | 0901568 |  |  | Plainfield | -339679.2083
|  |  | 0901569 |  |  | Winchester | -339679.2083
|  |  | 0901570 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901571 | Lake |  | Munster | 2009-11-18 | CE
CN
|  |  | 0901572 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901573 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901574 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901575 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901576 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901577 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901578 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901579 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901580 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901581 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901582 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901583 |  |  | Noble County | -339679.2083
|  |  | 0901584 |  | ERES International, Inc. | Ligonier | -339679.2083
|  |  | 0901585 | Wayne |  | Wayne County | -339679.2083 | CN
|  |  | 0901586 |  | Bartlett & Associates, Inc. | Cromwell | -339679.2083
|  |  | 0901587 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901588 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901589 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901590 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901591 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901592 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901593 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901594 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901595 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901596 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901597 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901598 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901599 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901600 | LaPorte |  | LaPorte County | 2009-10-21 | CE
CN
|  |  | 0901601 |  |  | Jeffersonville | -339679.2083
|  |  | 0901602 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901603 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901604 | Harrison |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 0901605 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901606 | Jefferson |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0901607 |  | M.A.T. Consulting, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901608 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 0901609 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901611 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 0901612 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901613 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0901614 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901615 |  | Bidinfo | Decatur | -339679.2083
|  |  | 0901616 |  | Bidinfo | Decatur | -339679.2083
|  |  | 0901617 | Newton |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 0901618 | White |  | White County | -339679.2083 | CN
|  |  | 0901619 | LaPorte |  | Michigan City | 2010-03-17 | CE
CN
|  |  | 0901620 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0901621 | Hamilton |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0901622 | Vanderburgh |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901623 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0901624 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901625 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 0901626 | Posey |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0901627 | Crawford |  | Indiana Department of Transportation | 2010-03-17 | CE
CN
|  |  | 0901628 | Tippecanoe |  | Tippecanoe County | 2009-12-09 | CE
CN
|  |  | 0901629 | Tippecanoe |  | Lafayette | 2010-01-27 | CE
CN
|  |  | 0901630 | Knox |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0901631 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901632 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901633 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901634 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901635 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901636 | St. Joseph | DB Management | St. Joseph County | 2009-11-18 | CE
CN
|  |  | 0901637 | St. Joseph | Integrated Environmental Solutions, Inc. | St. Joseph County | 2009-11-18 | CE
CN
|  |  | 0901638 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901639 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901640 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901641 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0901642 | Lake |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901643 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901644 | Jasper |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0901645 | Lake |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 0901646 | Jasper |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  |  | Lake |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0901647 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901648 | Marion |  | Lawrence | 2010-02-24 | CE
CN
|  |  | 0901649 | Marion |  | Lawrence | 2009-12-09 | CE
CN
|  |  | 0901650 |  |  | Lawrence | -339679.2083
|  |  | 0901651 |  |  | Lawrence | -339679.2083
|  |  | 0901652 | Dearborn | Clyde L. Hawkins | Greendale | 2010-01-27 | CE
CN
|  |  | 0901653 |  |  | Brown County | 2016-12-14
|  |  | 0901654 |  |  | Brown County | 2018-01-18
|  |  | 0901655 | Hendricks |  | Hendricks County | 2010-03-17 | CE
CN
|  |  | 0901656 | Lake | Dummy Consulting Firm | Lake Station | 2009-12-09 | CE
CN
|  |  | 0901657 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901658 | Jefferson |  | Madison | 2010-05-12 | CE
CN
|  |  | 0901659 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0901660 |  |  | Centerville | -339679.2083
|  |  | 0901661 |  |  | Delaware County | -339679.2083
|  |  | 0901662 |  |  | Speedway | -339679.2083
|  |  | 0901663 | Fulton |  | Peru | 2010-01-29 | CE
CN
|  |  |  | Miami |  | Peru | 2010-01-29 | CE
CN
|  |  | 0901664 | Tippecanoe |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
PE
|  |  | 0901665 | Tippecanoe |  | Indiana Department of Transportation | 2010-05-19 | CE
PE
|  |  | 0901666 | Carroll |  | Indiana Department of Transportation | 2010-05-21 | CE
PE
|  |  | 0901667 | Wayne |  | Centerville | 2010-07-07 | CE
CN
|  |  | 0901668 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0901669 | Carroll |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0901670 | Cass |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0901671 | Cass |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0901672 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0901673 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 0901674 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2010-01-13
|  |  | 0901675 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901676 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 0901677 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-11-29 | CN
|  |  | 0901678 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901679 | Elkhart |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 0901680 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 0901681 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0901682 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 0901683 |  |  | Indiana Department of Transportation | 2009-11-04
|  |  | 0901684 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0901685 | Monroe | Absolute Title Services, LLC | Bloomington | 2010-01-27 | CE
CN
|  |  | 0901686 | Jefferson | Engineering Resources, Inc. | Madison | 2009-12-09 | CE
CN
|  |  | 0901687 | Elkhart |  | Elkhart County | 2010-01-27 | CE
CN
|  |  | 0901688 |  |  | Hamilton County | -339679.2083
|  |  | 0901689 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901690 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901691 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901692 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901693 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901694 | Marion |  | Indianapolis | 2010-03-17 | CE
CN
|  |  | 0901695 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901696 |  | CGI | Evansville | 2010-09-01
|  |  | 0901697 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901698 |  | Anelena Ackerly | Carlisle | -339679.2083
|  |  | 0901699 |  | Anelena Ackerly | Carlisle | -339679.2083
|  |  | 0901700 | Marion |  | Indianapolis | 2010-05-12 | CE
CN
|  |  | 0901701 | Dekalb | Quantum Spatial, Inc. | Auburn | 2013-05-01 | CE
CN
PE
|  |  | 0901702 | Jasper |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
RR
|  |  |  | Lake |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  |  | Newton |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 0901703 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0901704 | Marion |  | Indianapolis | 2010-05-12 | CE
CN
|  |  | 0901705 | Hendricks |  | Hendricks County | 2012-05-02 | CE
CN
PE
ROW
|  |  | 0901706 | Marion |  | Indianapolis | 2011-08-10 | CE
CN
PE
|  |  | 0901707 |  |  | LaGrange County | -339679.2083
|  |  | 0901708 |  |  | LaGrange County | -339679.2083
|  |  | 0901709 |  |  | LaGrange County | -339679.2083
|  |  | 0901710 | Monroe |  | Bloomington | 2015-02-04 | CE
CN
|  |  | 0901711 |  |  | Carmel | -339679.2083
|  |  | 0901712 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901713 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901714 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901715 |  |  | Indianapolis | -339679.2083
|  |  | 0901716 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901717 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901718 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901719 | Whitley |  | Whitley County | -339679.2083 | CN
|  |  | 0901720 |  |  | Indiana Department of Transportation | 2010-01-13
|  |  | 0901721 | Dubois |  | Dubois County | -339679.2083 | CN
|  |  | 0901722 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901723 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901724 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901725 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901726 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901727 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901728 | Allen |  | Allen County | 2009-10-21 | CE
CN
|  |  | 0901729 |  |  | Bloomington | -339679.2083
|  |  | 0901730 | Monroe |  | Bloomington | 2018-03-14 | CE
CN
PE
ROW
|  |  | 0901731 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901732 |  |  | Indianapolis | -339679.2083
|  |  | 0901733 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901734 | Adams | Bidinfo | Decatur | 2010-01-27 | CE
CN
|  |  | 0901735 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2010-01-13 | CE
CN
|  |  | 0901736 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2010-01-13 | CE
CN
|  |  | 0901737 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 0901738 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901739 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901740 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901741 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901742 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901743 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901744 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901745 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901746 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901747 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901748 | Madison |  | Anderson | 2009-12-09 | CE
CN
|  |  | 0901749 |  |  | Pendleton | -339679.2083
|  |  | 0901750 | Floyd |  | Floyd County | 2010-02-24 | CE
CN
|  |  | 0901751 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 0901752 |  |  | Whitestown | -339679.2083
|  |  | 0901753 | Vigo |  | Vigo County | 2012-10-11 | CE
CN
PE
|  |  | 0901754 | Adams | Bidinfo | Decatur | 2010-01-27 | CE
CN
|  |  | 0901755 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
PE
RR
|  |  | 0901756 | Tippecanoe |  | Lafayette | 2009-12-09 | CE
CN
|  |  | 0901757 | Ripley |  | Indiana Department of Transportation | 2009-12-09 | CE
CN
|  |  | 0901758 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901759 | Lake | Chicago Testing Laboratory, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901760 | Lake | Chicago Testing Laboratory, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901761 | Lake | Chicago Testing Laboratory, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901762 | Lake | Chicago Testing Laboratory, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901763 | Lake | Baxter & Woodman, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901764 | Lake | Browning Day Mullins Dierdorf Architects | MPO - Northwest | -339679.2083 | CN
|  |  | 0901765 | Lake | Browning Day Mullins Dierdorf Architects | MPO - Northwest | -339679.2083 | CN
|  |  | 0901766 | Porter | ATSI Engineering Services | MPO - Northwest | -339679.2083 | CN
|  |  | 0901767 | Lake | Dummy Consulting Firm | MPO - Northwest | -339679.2083 | CN
|  |  | 0901768 | Porter | Dummy Consulting Firm | MPO - Northwest | -339679.2083 | CN
|  |  | 0901769 | Porter | Dummy Consulting Firm | MPO - Northwest | -339679.2083 | CN
|  |  | 0901770 | Porter | Huff & Huff, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901771 | Porter | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901772 | Porter | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901773 | Porter | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901774 | Porter | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901775 | Porter | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901776 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901777 | Grant | ERES International, Inc. | Marion | 2009-12-09 | CE
CN
|  |  | 0901778 |  |  | Vigo County | 2011-05-27
|  |  | 0901779 |  |  | Vigo County | 2011-05-27
|  |  | 0901780 | Lake |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0901781 | Randolph | Langworthy, Strader, LeBlanc & Associates, Inc. | Indiana Department of Transportation | 2010-02-24 | CE
CN
RR
|  |  | 0901782 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901783 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-01-27 | CE
CN
|  |  | 0901784 | Newton |  | Indiana Department of Transportation | 2014-07-09 | PE
|  |  | 0901785 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2009-12-09 | CE
CN
|  |  | 0901786 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-11-18 | CE
CN
|  |  | 0901787 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901788 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901789 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901790 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901791 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0901792 |  |  | Harrison County | -339679.2083
|  |  | 0901793 | Wayne |  | Wayne County | 2010-02-24 | CE
CN
|  |  | 0901794 | Monroe |  | Monroe County | 2013-07-10 | CE
CN
|  |  | 0901795 | Wayne |  | Wayne County | 2010-01-27 | CE
CN
|  |  | 0901796 | Lake |  | Winfield | 2009-12-09 | CE
CN
|  |  | 0901797 | Lake |  | Winfield | 2009-12-09 | CE
CN
|  |  | 0901798 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2017-10-12 | CE
CN
PE
ROW
|  |  | 0901799 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2011-04-13 | CN
|  |  | 0901800 | Porter |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0901801 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0901802 | LaPorte |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0901803 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2012-01-11 | CE
CN
|  |  | 0901804 |  |  | Henry County | -339679.2083
|  |  | 0901805 | LaPorte |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0901806 |  |  | Henry County | -339679.2083
|  |  | 0901807 |  |  | Henry County | -339679.2083
|  |  | 0901808 | Monroe |  | Bloomington | 2010-01-27 | CE
CN
|  |  | 0901809 | Monroe |  | Bloomington | 2010-01-27 | CE
CN
|  |  | 0901810 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901811 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901812 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901813 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901814 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901815 | Allen |  | Allen County | 2009-12-09 | CE
CN
|  |  | 0901816 | Boone |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0901817 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 0901818 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2010-02-24 | CE
CN
|  |  | 0901819 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CE
CN
|  |  | 0901820 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2010-02-24 | CE
CN
|  |  | 0901821 | Blackford |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0901822 | Grant |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
ROW
|  |  | 0901823 | Madison |  | Madison County | 2010-02-24 | CE
CN
|  |  | 0901824 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2010-02-24 | CE
CN
|  |  | 0901825 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901826 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901827 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0901828 | Marion |  | Indianapolis | 2010-02-24 | CE
CN
|  |  | 0901829 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0901830 | Lake | Brenner Design Incorporated | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 0901831 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-01-27 | CE
CN
|  |  | 0901832 | Various |  | Indiana Department of Transportation | 2020-05-31 | CN
OT
|  |  | 0901833 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901834 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901835 | Porter | Huff & Huff, Inc. | Portage | 2010-01-27 | CE
CN
|  |  | 0901836 | Porter | Leitner and Associates, Inc. | Valparaiso | 2009-12-09 | CE
CN
|  |  | 0901837 | Delaware |  | Yorktown | 2010-01-27 | CE
CN
|  |  | 0901838 |  |  | Yorktown | -339679.2083
|  |  | 0901839 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901840 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901841 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901842 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901843 | Benton |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0901844 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0901845 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901846 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901847 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901848 | Elkhart |  | Elkhart County | 2010-01-27 | CE
CN
|  |  | 0901849 | Elkhart |  | Elkhart County | 2010-01-27 | CE
CN
|  |  | 0901850 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-01-27 | CE
CN
|  |  | 0901851 |  |  | Union City | -339679.2083
|  |  | 0901852 |  |  | Union City | -339679.2083
|  |  | 0901853 |  |  | Union City | -339679.2083
|  |  | 0901854 |  |  | Connersville | -339679.2083
|  |  | 0901855 |  |  | Connersville | -339679.2083
|  |  | 0901856 |  |  | Connersville | -339679.2083
|  |  | 0901857 |  |  | Connersville | -339679.2083
|  |  | 0901858 |  | Meridian Title Corporation | White County | 2010-02-24
|  |  | 0901859 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0901860 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0901861 |  |  | Muncie | 2010-04-14
|  |  | 0901862 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2010-10-20 | CE
CN
|  |  | 0901863 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0901864 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 0901865 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0901866 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901867 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2009-12-09 | CE
CN
|  |  | 0901868 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2009-12-09 | CE
CN
|  |  | 0901869 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2009-12-09 | CE
CN
|  |  | 0901870 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2009-12-09 | CE
CN
|  |  | 0901871 | Floyd |  | New Albany | 2010-01-27 | CE
CN
|  |  | 0901872 | Orange |  | Orange County | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0901873 | Dubois | Craig E. Townsend | Dubois County | 2014-08-06 | CE
CN
PE
ROW
UT
|  |  | 0901874 |  |  | New Albany | -339679.2083
|  |  | 0901875 | Fulton |  | Fulton County | -339679.2083 | CN
|  |  | 0901876 | Henry |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0901877 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2010-01-27 | CE
CN
|  |  | 0901878 | Elkhart | Civil Inspection Services, LLC | Goshen | 2010-01-27 | CE
CN
|  |  | 0901879 | Elkhart | Civil Inspection Services, LLC | Goshen | 2010-01-27 | CE
CN
|  |  | 0901880 | Elkhart | Civil Inspection Services, LLC | Goshen | 2010-01-27 | CE
CN
|  |  | 0901881 | Harrison |  | Harrison County | -339679.2083 | CN
|  |  | 0901882 | Crawford |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  |  | Perry |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 0901883 | Crawford |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  |  | Orange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0901884 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 0901885 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901886 | Warrick |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
RR
[6 empty] | Indiana Department of Transportation | 2010-05-12
|  |  | 0901887 |  |  | Floyd County | -339679.2083
|  |  | 0901888 | Various |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 0901889 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901891 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 0901892 |  |  | Indiana Department of Transportation | 2011-11-16
|  |  | 0901893 |  |  | Plainfield | -339679.2083
|  |  | 0901894 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901895 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901897 |  |  | Indiana Department of Transportation | 2015-12-09
|  |  | 0901898 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901899 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901901 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901902 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901903 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901904 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901905 | LaPorte | Farah and Sons, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901906 | LaPorte | Farah and Sons, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901907 | LaPorte | Farah and Sons, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 0901908 | LaPorte |  | MPO - Northwest | -339679.2083 | CN
|  |  | 0901909 | Posey |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
ROW
|  |  | 0901910 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 0901911 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 0901912 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 0901913 |  |  | Indiana Department of Transportation | 2014-12-10
|  |  | 0901914 | Allen |  | Allen County | 2010-01-27 | CE
CN
|  |  | 0901915 | Lake | Karen | St. John | 2010-02-24 | CE
CN
|  |  | 0901916 | Delaware |  | MPO - Muncie | 2014-07-09 | CE
CN
|  |  | 0901917 |  |  | Muncie | -339679.2083
|  |  | 0901918 |  |  | Vigo County | -339679.2083
|  |  | 0901919 |  |  | Vigo County | -339679.2083
|  |  | 0901920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901921 |  |  | Vigo County | -339679.2083
|  |  | 0901922 |  |  | Vigo County | -339679.2083
|  |  | 0901923 | Vigo |  | Vigo County | 2010-02-24 | CE
CN
[6 empty] | Vigo County | 2010-02-24
|  |  | 0901924 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0901925 | Clark |  | MPO - Louisville | -339679.2083 | PE
|  |  | 0901926 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2009-12-09 | CE
CN
|  |  | 0901927 | Hamilton |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 0901928 | Porter | Huff & Huff, Inc. | Portage | 2010-05-31 | PE
|  |  | 0901929 | Wabash |  | Wabash County | -339679.2083 | CN
PE
|  |  | 0901930 | Marion |  | Lawrence | 2010-02-24 | CE
CN
|  |  | 0901931 | Marion |  | Lawrence | 2010-02-24 | CE
CN
|  |  | 0901932 | Monroe |  | Monroe County | -339679.2083 | CN
|  |  | 0901933 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 0901934 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901935 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 0901936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901937 | Huntington |  | Huntington County | -339679.2083 | CN
|  |  | 0901938 | Brown |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0901939 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-01-27 | CE
CN
|  |  | 0901940 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 0901941 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 0901942 |  |  | Terre Haute | -339679.2083
|  |  | 0901943 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 0901944 | Allen | Global Management Group, Inc. | New Haven | 2010-02-24 | CE
CN
|  |  | 0901945 | Allen | Global Management Group, Inc. | New Haven | 2010-02-24 | CE
CN
|  |  | 0901946 | Tippecanoe |  | Lafayette | 2010-03-17 | CE
CN
|  |  | 0901947 | Tippecanoe |  | Lafayette | 2010-03-17 | CE
CN
|  |  | 0901948 | Tippecanoe |  | Lafayette | 2010-03-17 | CE
CN
|  |  | 0901949 |  |  | Indiana Department of Natural Resources | 2010-04-29
|  |  | 0901950 | Randolph |  | Indiana Department of Transportation | 2010-02-24 | CE
CN
|  |  | 0901951 | Marion |  | Indiana Department of Transportation | -339679.2083 | UT
|  |  | 0901952 | Clay | Advanced Appraisals, LLC | Brazil | 2013-05-01 | CE
CN
ROW
|  |  | 0901953 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 0901954 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2010-01-27 | CE
CN
|  |  | 0901955 | Marion |  | Indianapolis | 2010-11-10 | CE
CN
PE
|  |  | 0901956 | Hamilton |  | Indiana Department of Transportation | 2009-11-20 | CN
|  |  | 0901957 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901958 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901959 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 0901960 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901961 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901962 |  |  | Clark County | -339679.2083
|  |  | 0901963 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901964 | Various | DCD Consulting LLC | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0901965 |  |  | Indiana Department of Transportation | 2011-10-13
|  |  | 0901966 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0901967 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0901968 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0901969 | Daviess |  | Indiana Department of Transportation | 2010-02-10 | ROW
UT
|  |  |  | Various |  | Indiana Department of Transportation | 2010-02-10 | PE
|  |  | 0901970 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0901971 |  |  | Indiana Department of Transportation | 2010-02-10
|  |  | 0901972 | Elkhart |  | Elkhart County | 2010-05-12 | CE
CN
|  |  | 0901973 | Allen | D & D Consulting Services, Inc. | Huntertown | 2017-01-19 | CE
CN
PE
ROW
|  |  | 0901974 | Allen | Landstory, Inc. | Grabill | 2014-12-10 | CE
CN
PE
ROW
UT
|  |  | 0901975 | LaPorte |  | MPO - Northwest | -339679.2083 | CN
|  |  | 0901976 | LaPorte |  | MPO - Northwest | -339679.2083 | CN
|  |  | 0901977 | LaPorte |  | MPO - Northwest | -339679.2083 | CN
|  |  | 0901978 | Lawrence |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0901979 | Allen |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0901980 | Allen |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0901981 | Delaware |  | MPO - Muncie | 2010-02-24 | CE
CN
|  |  | 0901982 | Madison |  | Madison County | 2013-07-10 | CE
CN
PE
ROW
|  |  | 0901984 | Miami |  | Miami County | -339679.2083 | PE
|  |  | 0901985 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901986 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901987 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901988 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0901989 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 0901990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901991 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0901992 | Morgan |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 0901993 | Allen | Clyde L. Hawkins | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 0901994 |  |  | Allen County | -339679.2083
|  |  | 0901995 | Allen |  | Allen County | 2010-02-24 | CE
CN
RR
|  |  | 0901996 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901997 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901998 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0901999 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0902000 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0902001 |  |  | Greenwood | -339679.2083
|  |  | 0902002 |  |  | Greenwood | -339679.2083
|  |  | 0902003 | Marion |  | Indianapolis | 2011-01-12 | CE
CN
|  |  | 0902004 | Marion |  | Indianapolis | 2011-03-09 | CE
CN
|  |  | 0902005 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2011-07-13 | CE
CN
PE
UT
|  |  | 0902006 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0902007 | Marion |  | Indianapolis | 2010-12-08 | CE
CN
|  |  | 0902008 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0902009 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2010-01-13
|  |  | 0902010 | Hendricks |  | Plainfield | 2012-12-12 | CE
CN
|  |  | 0902011 | Marion | Another Test Company | Indiana Department of Transportation | 2010-10-20 | CE
CN
|  |  | 0902012 | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 0902013 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0902014 | Johnson |  | Johnson County | -339679.2083 | CN
PE
|  |  | 0902015 |  |  | Plainfield | -339679.2083
|  |  | 0902016 |  |  | Indiana Department of Transportation | 2010-05-12
|  |  | 0902017 | LaPorte |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 0902018 | LaPorte |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0902019 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 0902020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902021 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0902022 | White |  | White County | -339679.2083 | CN
PE
|  |  | 0902023 |  |  | Indiana Department of Transportation | 2010-07-07
|  |  | 0902024 | Hancock |  | Indiana Department of Transportation | 2010-07-07 | CE
CN
|  |  | 0902025 | Vanderburgh |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902026 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902027 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 0902028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902029 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902033 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902034 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902035 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902037 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902038 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902039 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902040 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902042 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902043 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902044 | Vanderburgh |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902045 | Vanderburgh |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902046 | Vanderburgh |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902047 | Gibson |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902048 | Gibson |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902049 | Gibson |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902050 | Gibson |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 0902051 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902052 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902053 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902054 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902055 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902056 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902057 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902058 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902059 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902060 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902061 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902063 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902064 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902065 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902069 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902070 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902071 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902072 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902073 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902074 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902075 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902076 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902077 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902078 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902079 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902080 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902081 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902082 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902083 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902084 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902085 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902086 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902087 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902088 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902089 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902090 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902091 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902092 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902093 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902094 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902095 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902096 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902097 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902098 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902099 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902100 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902101 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902102 | Gibson |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0902103 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902104 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902105 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902106 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902109 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902110 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902113 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902114 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902117 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902118 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902119 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902120 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902121 | Morgan |  | Morgan County | -339679.2083 | CN
|  |  | 0902122 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902123 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902126 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902127 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902128 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902129 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902130 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902131 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902132 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902133 | Pike |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0902134 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902135 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 0902136 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 0902137 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902138 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 0902139 | Pike |  | Indiana Department of Transportation | 2011-02-11 | CE
CN
ROW
UT
|  |  | 0902140 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902141 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 0902142 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902143 | Pike |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 0902144 |  |  | Indiana Department of Transportation | 2010-08-04
|  |  | 0902145 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902146 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 0902147 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 0902148 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902149 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 0902150 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902151 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902152 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902153 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902154 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902156 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902157 | Daviess |  | Indiana Department of Transportation | 2011-01-12 | CN
UT
|  |  |  | Pike |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
UT
|  |  | 0902158 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902159 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902160 | LaPorte | Farah and Sons, Inc. | Michigan City | 2010-07-07 | CE
CN
|  |  | 0902161 | Marion |  | Indiana Department of Transportation | 2010-08-04 | CE
CN
PE
|  |  | 0902162 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26 | CE
UT
|  |  | 0902163 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 0902164 | Posey | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2012-05-31 | PE
|  |  |  | Warrick | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 0902165 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0902166 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0902167 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902168 |  |  | Indiana Department of Transportation | 2010-04-14
|  |  | 0902169 |  |  | Indiana Department of Transportation | 2010-04-14
|  |  | 0902170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902171 | Clinton |  | Clinton County | 2013-07-10 | CE
CN
|  |  | 0902172 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 2011-05-11
|  |  | 0902173 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
|  |  | 0902174 | Daviess |  | Indiana Department of Transportation | 2010-04-29 | UT
|  |  | 0902175 | Daviess |  | Indiana Department of Transportation | 2010-06-09 | CE
CN
UT
|  |  | 0902176 | Daviess |  | Indiana Department of Transportation | 2010-08-27 | CE
CN
PE
RR
UT
|  |  | 0902177 |  |  | Indiana Department of Transportation | 2010-01-13
|  |  | 0902178 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0902179 | Dekalb |  | Dekalb County | -339679.2083 | CN
|  |  | 0902180 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0902181 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0902182 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0902183 | Allen |  | Allen County | 2010-02-24 | CE
CN
|  |  | 0902184 | Tippecanoe |  | Tippecanoe County | -339679.2083 | CN
|  |  | 0902185 | Clinton |  | Clinton County | -339679.2083 | CN
|  |  | 0902186 | LaPorte |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 0902187 |  |  | Indiana Department of Transportation | 2011-10-13
|  |  | 0902190 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0902191 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2010-11-10
|  |  | 0902192 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0902193 |  |  | Indiana Department of Transportation | 2011-01-26
|  |  | 0902194 |  |  | Indianapolis | -339679.2083
|  |  | 0902195 | St. Joseph |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0902196 | Boone |  | Lebanon | 2015-01-14 | CE
CN
PE
|  |  | 0902197 | Jay |  | Jay County | -339679.2083 | CN
|  |  | 0902198 | Howard |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | Tipton |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0902199 | Jackson |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 0902200 | Madison | Central Diving Contractors | Frankton | 2013-11-06 | CE
CN
PE
|  |  | 0902201 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
ROW
UT
|  |  | 0902202 | Pike |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
ROW
UT
|  |  | 0902203 |  |  | Jackson County | -339679.2083
|  |  | 0902204 | Pike |  | Indiana Department of Transportation | 2011-02-11 | CE
CN
ROW
UT
|  |  | 0902205 | Daviess |  | Indiana Department of Transportation | 2011-01-12 | ROW
RR
UT
|  |  | 0902206 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902207 | Floyd |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
ROW
|  |  | 0902208 | Franklin | Alfred Benesch & Company | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0902209 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 0902210 | Vigo | Bayswater Company, LLC | Terre Haute | 2014-05-30 | CE
CN
|  |  | 0902211 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2013-05-01 | CE
CN
PE
|  |  | 0902212 | Tippecanoe |  | West Lafayette | 2014-07-09 | CE
CN
|  |  | 0902213 | Decatur |  | Decatur County | 2013-12-11 | CE
CN
PE
|  |  | 0902214 | Floyd | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  |  | Harrison | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 0902215 | Monroe |  | Monroe County | 2022-03-09 | PE
ROW
|  |  | 0902216 | Benton |  | Jackson County | 2010-07-07 | CN
|  |  |  | Newton |  | Jackson County | 2010-07-07 | CN
[6 empty] | Jackson County | 2010-07-07
|  |  | 0902217 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 0902218 |  | Civil Inspection Services, LLC | Elkhart County | -339679.2083
|  |  | 0902219 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0902220 |  |  | Indiana Department of Transportation | 2010-03-03
|  |  | 0902221 | Marion | Another Test Company | Indiana Department of Transportation | 2010-07-07 | CE
CN
RR
|  |  | 0902222 | Allen |  | Indiana Department of Transportation | 2012-01-13 | CE
CN
OT
PE
ROW
UT
|  |  | 0902223 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902224 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902225 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902226 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902227 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902228 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902229 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902230 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902231 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902232 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902233 | Howard |  | Indiana Department of Transportation | 2010-04-14 | CE
CN
|  |  | 0902234 | Montgomery |  | Montgomery | -339679.2083 | PE
|  |  | 0902235 | Marshall | Bayer & Becker, Inc. | Culver | 2012-08-08 | CE
CN
PE
|  |  | 0902236 | St. Joseph |  | St. Joseph County | 2013-01-16 | CE
CN
PE
ROW
|  |  | 0902237 | Carroll | Blood Hound, Inc. (former) | Delphi | 2013-04-03 | CE
CN
PE
|  |  | 0902238 | Allen |  | Allen County | 2016-11-30 | CE
CN
ROW
RR
UT
|  |  | 0902239 |  |  | Allen County | -339679.2083
|  |  | 0902240 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902241 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902242 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902243 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0902244 | Wabash | M-E Companies, Inc. | Wabash | 2010-09-01 | CE
CN
PE
|  |  | 0902245 | Orange |  | French Lick | 2015-02-25 | CN
|  |  | 0902246 | Floyd |  | Floyd County | -339679.2083 | PE
|  |  | 0902247 | Gibson | III FFC | Princeton | 2015-01-14 | CE
CN
PE
|  |  | 0902248 | Jasper |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0902249 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 0902250 | Dubois | CMF Engineering, Inc. | Ferdinand | 2013-05-01 | CE
CN
PE
|  |  | 0902251 | Pike | Meca Engineering Corporation of America Incorporated | Pike County | 2015-11-10 | CE
CN
PE
ROW
|  |  | 0902252 | Orange |  | Orange County | 2014-02-05 | CE
CN
PE
ROW
|  |  | 0902253 | Vigo |  | Vigo County | 2010-08-04 | CE
CN
|  |  | 0902254 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0902255 | Vigo |  | Vigo County | 2010-08-04 | CE
CN
|  |  | 0902256 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2010-09-22 | CE
CN
ROW
|  |  | 0902257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902258 | Monroe |  | Bloomington | 2014-05-08 | CN
|  |  | 0902259 | Daviess |  | Indiana Department of Transportation | 2014-05-31 | UT
|  |  |  | Gibson |  | Indiana Department of Transportation | 2014-05-31 | UT
|  |  |  | Greene |  | Indiana Department of Transportation | 2014-05-31 | UT
|  |  |  | Pike |  | Indiana Department of Transportation | 2014-05-31 | UT
|  |  | 0902260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902261 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-09 | PE
|  |  | 0902262 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 0902263 | Monroe | Absolute Title Services, LLC | Monroe County | 2014-08-06 | CE
CN
|  |  | 0902264 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 0902265 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902266 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902267 | Pike |  | Indiana Department of Transportation | 2010-11-30 | CE
CN
|  |  | 0902268 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 0902269 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 0902270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902271 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902272 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 0902273 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902274 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 0902275 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902276 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 0902277 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902278 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902279 | Elkhart | Civil Inspection Services, LLC | Goshen | 2013-08-07 | CE
CN
PE
RR
|  |  | 0902280 | Hendricks |  | Hendricks County | 2010-05-12 | CE
UT
|  |  | 0902281 | Dekalb |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0902282 | Ripley |  | Ripley County | -339679.2083 | CN
|  |  | 0902283 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 0902284 |  |  | Porter | 2010-05-12
|  |  | 0902285 | Bartholomew |  | Columbus | -339679.2083 | PE
|  |  | 0902286 | St. Joseph |  | St. Joseph County | 2022-08-10 | ROW
|  |  | 0902287 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902288 | Rush |  | Rushville | 2011-01-12 | CE
CN
|  |  | 0902289 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
ROW
|  |  | 0902290 | Wells |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 0902291 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0902292 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 0902293 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 0902294 | Newton |  | Newton County | -339679.2083 | PE
|  |  | 0902295 | Kosciusko |  | Kosciusko County | 2013-03-06 | CE
CN
PE
ROW
|  |  | 0902296 |  |  | Yorktown | -339679.2083
|  |  | 0902297 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
PE
ROW
UT
|  |  | 0902298 | Orange |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
|  |  | 0902299 | Lawrence |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
ROW
|  |  |  | Orange |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0902300 |  |  | Indiana Department of Natural Resources | 2010-03-03
|  |  | 0902301 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 0902302 |  |  | Hamilton County | -339679.2083
|  |  | 0902303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902304 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 0902305 | Elkhart | C Blair Enterprises, Inc. | Elkhart County | 2012-07-11 | CE
CN
|  |  | 0902306 | LaGrange |  | LaGrange County | -339679.2083 | CN
|  |  | 0902307 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 0902308 |  | CGI | Evansville | -339679.2083
|  |  | 0902309 | Marion | DCD Consulting LLC | Indianapolis | 2016-02-03 | CE
CN
PE
|  |  | 0902310 | Delaware |  | Delaware County | 2011-05-11 | CE
CN
PE
|  |  | 0902311 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 0902312 | Daviess | AMEC E&I, Inc. | Washington | 2012-03-07 | CE
CN
PE
|  |  | 0902313 | Dekalb | Quantum Spatial, Inc. | Auburn | 2012-02-08 | CE
CN
PE
|  |  | 0902314 |  | Applied Pavement Technology, Inc. | Cedar Lake | -339679.2083
|  |  | 0902315 | Marion | DCD Consulting LLC | Indianapolis | 2016-04-06 | CE
CN
PE
|  |  | 0902316 | Lawrence | ICA Engineering, Inc. | Mitchell | 2013-01-16 | CE
CN
PE
|  |  | 0902317 | Gibson | CSR Engineering, Inc. | Fort Branch | 2012-02-08 | CE
CN
PE
|  |  | 0902318 | Lawrence | Hagerty Engineering, Inc. | Oolitic | 2014-03-05 | CE
CN
PE
ROW
|  |  | 0902319 | Posey | I. T. Business Corporation | Poseyville | 2011-09-08 | CE
CN
PE
|  |  | 0902320 | Henry | Debbie Mann Consulting, Inc. | Kennard | 2012-07-11 | CE
CN
PE
|  |  | 0902321 |  | Brenner Design Incorporated | Dyer | -339679.2083
|  |  | 0902322 | Newton |  | Kentland | 2013-03-06 | CE
CN
PE
|  |  | 0902323 |  |  | Lafayette | -339679.2083
|  |  | 0902324 | Delaware |  | MPO - Muncie | -339679.2083 | PE
|  |  | 0902325 | Floyd |  | New Albany | 2016-05-05 | CE
CN
|  |  | 0902326 |  |  | Westfield | -339679.2083
|  |  | 0902327 |  |  | Plainfield | -339679.2083
|  |  | 0902328 | Kosciusko |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 0902329 |  |  | Anderson | -339679.2083
|  |  | 0902330 | Hamilton |  | Hamilton County | 2013-02-20 | CE
CN
|  |  | 0902331 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 0902332 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 0902333 | Kosciusko |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1000001 | Johnson |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
ROW
UT
|  |  | 1000002 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000003 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000004 | Porter | Leitner and Associates, Inc. | Valparaiso | 2012-10-11 | CE
CN
|  |  | 1000005 | Perry | Andrews Engineering, Inc. | Cannelton | 2014-03-05 | CE
CN
PE
|  |  | 1000006 |  | Another Test Company | Carmel | -339679.2083
|  |  | 1000007 | Dekalb | Mader Design, LLC | Waterloo | -339679.2083 | PE
|  |  | 1000008 | Marion | DCD Consulting LLC | Indianapolis | 2011-07-22 | PE
|  |  | 1000009 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 1000010 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington | -339679.2083 | PE
|  |  | 1000011 | Bartholomew |  | Bartholomew County | -339679.2083 | CN
|  |  | 1000012 |  |  | South Bend | -339679.2083
|  |  | 1000013 | Hamilton |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
UT
|  |  | 1000014 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 1000015 | Clay | Bayswater Company, LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Hendricks | Bayswater Company, LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Morgan | Bayswater Company, LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Putnam | Bayswater Company, LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 1000016 | Morgan | Archonsortium, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  |  | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2011-12-14 | CE
|  |  | 1000017 | Putnam |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1000018 | Jefferson |  | Jefferson County | -339679.2083 | CN
|  |  | 1000019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000020 |  |  | Indiana Department of Transportation | 2010-06-09
|  |  | 1000021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000022 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000023 | Adams |  | Adams County | -339679.2083 | CN
|  |  | 1000024 | Allen |  | Allen County | -339679.2083 | CN
PE
|  |  | 1000025 | Franklin |  | Franklin County | -339679.2083 | CN
|  |  | 1000026 | Jasper |  | Jasper County | -339679.2083 | CN
|  |  | 1000027 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1000028 | Perry |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
PE
|  |  | 1000029 |  |  | Wells County | -339679.2083
|  |  | 1000030 |  |  | Wells County | -339679.2083
|  |  | 1000031 |  |  | Wells County | -339679.2083
|  |  | 1000032 |  |  | Wells County | -339679.2083
|  |  | 1000033 |  |  | Wells County | -339679.2083
|  |  | 1000034 |  |  | Wells County | -339679.2083
|  |  | 1000035 |  |  | Wells County | -339679.2083
|  |  | 1000036 |  |  | Wells County | -339679.2083
|  |  | 1000037 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1000038 | Carroll | Dodd Title Corporation | Indiana Department of Transportation | 2011-05-31 | CN
|  |  | 1000039 | Various |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1000040 |  | DCD Consulting LLC | Indiana Department of Transportation | 2010-04-14
|  |  | 1000041 | Warrick |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1000042 | Spencer |  | Spencer County | -339679.2083 | CN
|  |  | 1000043 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1000044 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1000045 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1000046 | Madison |  | Madison County | -339679.2083 | CN
|  |  | 1000047 | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 1000048 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000049 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000050 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1000051 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1000052 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1000053 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1000054 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1000055 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1000056 | Vermillion |  | Clinton | 2013-01-16 | CE
CN
PE
|  |  | 1000057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000058 | Jay |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  |  | Randolph |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1000059 | Fayette |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1000060 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1000061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000063 | Tippecanoe |  | Indiana Department of Transportation | 2010-05-26 | CE
CN
|  |  | 1000064 | Henry |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 1000065 | Marion |  | Indiana Department of Transportation | 2010-10-28 | CE
CN
|  |  | 1000068 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26
|  |  | 1000069 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1000070 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1000071 | Hendricks |  | Hendricks County | -339679.2083 | CN
|  |  | 1000072 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1000073 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1000074 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1000075 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1000076 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1000077 | Lake | Edwards and Kelcey | Lowell | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1000078 | St. Joseph | Gensic Engineering, Inc. | New Carlisle | 2013-04-03 | CE
CN
PE
|  |  | 1000079 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000080 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000081 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000082 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000083 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000084 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1000085 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1000086 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1005087 |  |  | Ohio County | -339679.2083
|  |  | 1005088 | Marion |  | Indianapolis | -339679.2083 | CN
|  |  | 1005089 | St. Joseph |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1005090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005091 | Hamilton | Another Test Company | Indiana Department of Transportation | 2010-08-04 | CE
CN
|  |  | 1005092 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005093 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005094 |  |  | Kosciusko County | -339679.2083
|  |  | 1005095 |  |  | Kosciusko County | -339679.2083
|  |  | 1005096 |  |  | Kosciusko County | -339679.2083
|  |  | 1005097 |  |  | Kosciusko County | -339679.2083
|  |  | 1005098 |  |  | Kosciusko County | -339679.2083
|  |  | 1005099 |  |  | Kosciusko County | -339679.2083
|  |  | 1005100 |  |  | Elkhart County | -339679.2083
|  |  | 1005101 |  |  | Elkhart County | -339679.2083
|  |  | 1005102 |  |  | LaPorte County | -339679.2083
|  |  | 1005103 | Marshall |  | Marshall County | -339679.2083 | CN
|  |  | 1005104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005117 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 1005118 | Lawrence |  | Lawrence County | -339679.2083 | CN
|  |  | 1005119 | Marshall |  | Indiana Department of Transportation | 2010-05-12 | CE
CN
|  |  | 1005120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005122 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1005123 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1005124 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1005125 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1005126 |  | Quantum Spatial, Inc. | Auburn | -339679.2083
|  |  | 1005127 |  | Quantum Spatial, Inc. | Auburn | -339679.2083
|  |  | 1005128 |  |  | Clinton County | -339679.2083
|  |  | 1005129 |  |  | Clinton County | -339679.2083
|  |  | 1005130 |  |  | Clinton County | -339679.2083
|  |  | 1005131 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1005132 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1005133 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1005134 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005135 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005136 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005137 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005138 |  |  | Carroll County | -339679.2083
|  |  | 1005139 |  |  | Carroll County | -339679.2083
|  |  | 1005140 |  |  | Carroll County | -339679.2083
|  |  | 1005141 | Porter |  | Porter County | -339679.2083 | CN
|  |  | 1005142 |  |  | Steuben County | -339679.2083
|  |  | 1005143 |  |  | Fountain County | -339679.2083
|  |  | 1005144 |  |  | Fountain County | -339679.2083
|  |  | 1005145 |  |  | Fountain County | -339679.2083
|  |  | 1005146 |  |  | Fountain County | -339679.2083
|  |  | 1005147 |  |  | Fountain County | -339679.2083
|  |  | 1005148 |  |  | Fountain County | -339679.2083
|  |  | 1005150 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 1005151 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2017-08-09 | CE
CN
|  |  | 1005152 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2019-02-06 | CN
|  |  | 1005154 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2019-02-06 | CE
CN
UT
|  |  | 1005155 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2019-02-06 | CN
|  |  | 1005156 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1005157 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1005158 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2013-07-10 | CE
CN
PE
|  |  | 1005159 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2013-04-03 | CE
CN
PE
ROW
|  |  | 1005160 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1005161 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005162 |  |  | Dekalb County | -339679.2083
|  |  | 1005163 |  |  | Dekalb County | -339679.2083
|  |  | 1005164 |  |  | Dekalb County | -339679.2083
|  |  | 1005165 | Jackson |  | Seymour | 2015-04-01 | CE
CN
PE
ROW
|  |  | 1005166 |  |  | Dekalb County | -339679.2083
|  |  | 1005167 | Jefferson |  | Madison | -339679.2083 | PE
|  |  | 1005168 |  |  | Dekalb County | -339679.2083
|  |  | 1005169 |  |  | Dekalb County | -339679.2083
|  |  | 1005170 |  |  | Indiana Department of Transportation | 2008-02-06
|  |  | 1005171 |  |  | Indiana Department of Transportation | 2008-04-23
|  |  | 1005172 |  |  | Indiana Department of Transportation | 2007-11-28
|  |  | 1005173 |  |  | Indiana Department of Transportation | 2007-12-12
|  |  | 1005174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005176 |  |  | Indiana Department of Transportation | 2008-03-05
|  |  | 1005177 |  |  | Indiana Department of Transportation | 2004-01-21
|  |  | 1005178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005180 |  |  | Indiana Department of Transportation | 2004-02-17
|  |  | 1005181 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2012-08-08
|  |  | 1005182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005183 | Harrison |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1005184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005185 | Scott |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
ROW
UT
|  |  | 1005186 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005187 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005188 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005189 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005190 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005191 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1005192 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1005193 | Clinton |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 1005194 |  |  | Steuben County | -339679.2083
|  |  | 1005195 |  |  | Steuben County | -339679.2083
|  |  | 1005196 |  |  | Steuben County | -339679.2083
|  |  | 1005197 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1005198 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1005199 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1005200 |  | Bidinfo | Decatur | -339679.2083
|  |  | 1005201 |  | Bidinfo | Decatur | -339679.2083
|  |  | 1005202 | Wabash | M-E Companies, Inc. | Wabash | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1005203 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 1005204 |  | Applied Pavement Technology, Inc. | Cedar Lake | -339679.2083
|  |  | 1005205 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1005206 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1005207 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1005208 |  |  | Pulaski County | -339679.2083
|  |  | 1005209 |  |  | Pulaski County | -339679.2083
|  |  | 1005210 |  |  | Pulaski County | -339679.2083
|  |  | 1005211 |  |  | Pulaski County | -339679.2083
|  |  | 1005212 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 1005213 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005214 | Elkhart | Dave Helton & Associates, Inc. | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005215 | Steuben |  | Indiana Department of Transportation | 2018-05-31 | CE
PE
|  |  | 1005216 | Union |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1005217 | Gibson |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005218 | Knox |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005219 | Marion |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005220 | Marshall |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005221 | Spencer |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 1005222 | Noble |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1005223 | Delaware |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005224 | Perry |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 1005225 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005226 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005227 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005228 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005229 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005230 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 1005231 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 1005232 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 1005233 | Bartholomew |  | Columbus | 2012-07-11 | CE
CN
|  |  | 1005234 |  |  | Miami County | -339679.2083
|  |  | 1005235 |  |  | Miami County | -339679.2083
|  |  | 1005236 |  |  | Miami County | -339679.2083
|  |  | 1005237 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1005238 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005239 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005240 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005241 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005242 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005243 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005244 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005245 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005246 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005247 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005248 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005249 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005250 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005251 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005252 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005253 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005254 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005255 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005256 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005257 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005258 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005259 | Marion | DCD Consulting LLC | Indianapolis | 2011-05-11 | CE
CN
|  |  | 1005260 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005261 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005262 | Various |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005263 | Perry |  | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 1005264 |  |  | Adams County | -339679.2083
|  |  | 1005265 |  |  | Adams County | -339679.2083
|  |  | 1005266 |  |  | Adams County | -339679.2083
|  |  | 1005267 |  |  | Adams County | -339679.2083
|  |  | 1005268 |  |  | Adams County | -339679.2083
|  |  | 1005269 |  |  | Kosciusko County | -339679.2083
|  |  | 1005270 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005271 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005272 |  |  | Steuben County | -339679.2083
|  |  | 1005273 |  |  | Steuben County | -339679.2083
|  |  | 1005274 | Wayne |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1005275 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26 | CE
CN
|  |  | 1005276 |  |  | Indiana Department of Transportation | 2010-08-04
|  |  | 1005277 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005278 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1005279 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1005280 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1005281 |  |  | Pulaski County | -339679.2083
|  |  | 1005282 |  |  | Pulaski County | -339679.2083
|  |  | 1005283 |  |  | Pulaski County | -339679.2083
|  |  | 1005284 |  |  | Pulaski County | -339679.2083
|  |  | 1005285 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005286 |  |  | Howard County | -339679.2083
|  |  | 1005287 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005288 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005289 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005290 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005291 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005292 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1005293 |  |  | Howard County | -339679.2083
|  |  | 1005294 |  |  | Howard County | -339679.2083
|  |  | 1005295 |  |  | Howard County | -339679.2083
|  |  | 1005296 |  |  | Howard County | -339679.2083
|  |  | 1005297 |  | Consolidated Test Company | Hammond | 2013-03-06
|  |  | 1005298 |  |  | Howard County | -339679.2083
|  |  | 1005299 | Marion |  | Indianapolis | 2012-10-11 | CE
CN
|  |  | 1005300 |  |  | Howard County | -339679.2083
|  |  | 1005301 | Jackson |  | Jackson County | -339679.2083 | CN
|  |  | 1005302 |  |  | Fayette County | -339679.2083
|  |  | 1005303 |  |  | Fayette County | -339679.2083
|  |  | 1005304 |  |  | Fayette County | -339679.2083
|  |  | 1005305 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005306 |  | Hy-Tech Response, Inc. | Porter | 2010-07-07
|  |  | 1005307 | Fountain |  | Fountain County | -339679.2083 | CN
|  |  | 1005308 | Dearborn |  | Dearborn County | -339679.2083 | CN
|  |  | 1005309 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1005310 |  | Advanced Engineering Consultants, Ltd. | Bremen | -339679.2083
|  |  | 1005311 |  |  | Whitley County | -339679.2083
|  |  | 1005312 |  |  | Whitley County | -339679.2083
|  |  | 1005313 |  |  | Whitley County | -339679.2083
|  |  | 1005314 |  |  | Whitley County | -339679.2083
|  |  | 1005315 |  | Hy-Tech Response, Inc. | Porter | 2010-07-07
|  |  | 1005316 | Starke |  | Starke County | -339679.2083 | CN
|  |  | 1005317 |  |  | Madison County | -339679.2083
|  |  | 1005318 |  |  | Madison County | -339679.2083
|  |  | 1005319 | Vigo |  | Terre Haute | 2010-10-06 | CE
CN
|  |  | 1005320 | Allen |  | Allen County | 2014-08-06 | CE
CN
PE
ROW
|  |  | 1005321 |  |  | Madison County | -339679.2083
|  |  | 1005322 |  |  | Madison County | -339679.2083
|  |  | 1005323 |  |  | Madison County | -339679.2083
|  |  | 1005324 |  |  | Madison County | -339679.2083
|  |  | 1005325 |  |  | Madison County | -339679.2083
|  |  | 1005326 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005327 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005328 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005329 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005330 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1005331 | Warren |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1005332 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1005333 | Boone |  | Boone County | 2014-05-08 | CE
CN
PE
|  |  | 1005334 | Warren |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1005335 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005336 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005337 | Warren |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1005338 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005339 | Warren |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1005340 | Warren |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1005341 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | -339679.2083
|  |  | 1005342 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | -339679.2083
|  |  | 1005343 |  |  | Dearborn County | -339679.2083
|  |  | 1005344 |  |  | Indiana Department of Transportation | 2011-05-31
|  |  | 1005345 | Lake | Baxter & Woodman, Inc. | Crown Point | 2011-09-08 | CE
CN
PE
|  |  | 1005346 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005348 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005349 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005350 |  |  | Indiana Department of Transportation | 2010-11-10
|  |  | 1005351 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1005352 |  | DCD Consulting LLC | Indiana Department of Transportation | 2010-10-28
|  |  | 1005353 |  |  | Franklin County | -339679.2083
|  |  | 1005354 | Ripley | ARCADIS | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005355 |  |  | Scottsburg | -339679.2083
|  |  | 1005356 | Ripley | ARCADIS | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005357 | Ripley | ARCADIS | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005358 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005359 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 1005360 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005361 | Warren | McCord, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005362 |  | Ken Herceg & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005363 | Warren | Ken Herceg & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005364 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005365 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005366 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005367 | Elkhart | Green 3, LLC | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1005368 | Elkhart | Green 3, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005369 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005370 | Wabash | HE-BFS, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005371 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005372 | Wabash | HE-BFS, LLC | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1005373 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2011-07-01 | RR
|  |  | 1005374 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005375 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005376 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005377 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005378 | Henry | KPFF, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005379 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 1005380 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005381 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1005382 | Franklin |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 1005383 | Cass |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005384 | Cass |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005385 | Cass |  | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1005386 | Lake |  | Lake County | 2010-11-10 | CN
PE
|  |  | 1005387 | Porter |  | Porter County | 2013-04-03 | CE
CN
PE
|  |  | 1005388 | Franklin |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 1005389 | Johnson |  | Greenwood | 2012-05-02 | CE
CN
|  |  | 1005390 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1005391 |  | MCIS LLC | Wanatah | -339679.2083
|  |  | 1005392 |  | Bayer & Becker, Inc. | Culver | -339679.2083
|  |  | 1005393 |  |  | Howard County | -339679.2083
|  |  | 1005394 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 1005395 |  |  | Merrillville | -339679.2083
|  |  | 1005396 |  |  | Merrillville | -339679.2083
|  |  | 1005397 |  |  | Merrillville | -339679.2083
|  |  | 1005398 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1005399 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 1005400 |  | Karen | St. John | -339679.2083
|  |  | 1005401 |  | Karen | St. John | -339679.2083
|  |  | 1005402 |  | Karen | St. John | -339679.2083
|  |  | 1005403 |  | Karen | St. John | -339679.2083
|  |  | 1005404 |  | Karen | St. John | -339679.2083
|  |  | 1005405 |  | Karen | St. John | -339679.2083
|  |  | 1005406 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1005407 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1005408 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1005409 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1005410 | Clay |  | Clay County | -339679.2083 | CN
|  |  | 1005411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005412 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005413 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1005414 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1005415 |  |  | Blackford County | -339679.2083
|  |  | 1005416 |  |  | Blackford County | -339679.2083
|  |  | 1005417 | Monroe |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
|  |  | 1005418 |  |  | Blackford County | -339679.2083
|  |  | 1005419 |  |  | Blackford County | -339679.2083
|  |  | 1005420 | Greene |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
ROW
|  |  | 1005421 | Greene |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  | 1005422 | Monroe |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005423 | Monroe |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005424 | Monroe |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  | 1005425 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005426 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005427 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005428 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005429 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005430 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005431 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1005432 | Washington |  | Washington County | -339679.2083 | CN
PE
|  |  | 1005433 | Ohio |  | Ohio County | -339679.2083 | CN
|  |  | 1005434 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005435 | Delaware |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Union |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1005436 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005437 | Harrison |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 1005438 |  |  | Hancock County | -339679.2083
|  |  | 1005439 |  |  | Hancock County | -339679.2083
|  |  | 1005440 |  |  | Hancock County | -339679.2083
|  |  | 1005441 | Greene |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
ROW
|  |  | 1005442 | Greene |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005443 | Greene |  | Indiana Department of Transportation | 2012-07-11 | CE
PE
ROW
|  |  | 1005444 | Monroe |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
|  |  | 1005445 | Greene |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
PE
ROW
|  |  | 1005446 | Clark |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1005447 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 1005448 | Greene |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
ROW
|  |  | 1005449 | Monroe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
ROW
|  |  | 1005450 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005451 | Monroe |  | Indiana Department of Transportation | 2011-12-21 | ROW
|  |  | 1005452 | Monroe |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
ROW
|  |  | 1005453 | Greene |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  | 1005454 | Greene |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
PE
ROW
|  |  | 1005455 | Greene |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
ROW
|  |  | 1005456 | Greene |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
ROW
|  |  | 1005457 | Greene |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
ROW
|  |  | 1005458 | Daviess |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
ROW
|  |  | 1005459 | Greene |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  | 1005460 | Greene |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005461 | Greene |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005462 | Greene |  | Indiana Department of Transportation | 2011-12-21 | ROW
|  |  | 1005463 | Greene |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
ROW
|  |  | 1005464 |  |  | Jay County | -339679.2083
|  |  | 1005465 |  |  | Jay County | -339679.2083
|  |  | 1005466 |  |  | Indianapolis | -339679.2083
|  |  | 1005467 |  |  | Shelby County | -339679.2083
|  |  | 1005468 | Marion |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1005469 | Delaware |  | Muncie | -339679.2083 | CN
|  |  | 1005470 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005471 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005472 | Marion |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005473 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 1005474 | Boone | DCD Consulting LLC | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1005475 | Henry |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1005476 | Randolph |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
ROW
|  |  | 1005477 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2010-08-04
|  |  | 1005478 | White |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
ROW
|  |  | 1005479 | Tipton |  | Tipton County | -339679.2083 | CN
|  |  | 1005480 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-09-21 | PE
|  |  | 1005481 | LaPorte |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1005482 |  | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005483 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005484 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005485 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005486 | Jasper |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1005487 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005488 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1005489 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005490 | Dearborn |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1005491 | Daviess |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  |  | Gibson |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  |  | Pike |  | Indiana Department of Transportation | 2012-05-31 | ROW
|  |  | 1005492 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005494 | Clark |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1005495 |  |  | Indiana Department of Transportation | 2010-04-22
|  |  | 1005496 | Harrison | B. L. A., Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1005497 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005498 | Scott |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1005499 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  |  | Morgan | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1005500 | Tippecanoe |  | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 1005501 | Tippecanoe |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1005502 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1005503 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005504 |  |  | Federal Lands Highway | -339679.2083
|  |  | 1005505 |  | Hy-Tech Response, Inc. | Federal Lands Highway | 2011-05-31
|  |  | 1005506 |  |  | Federal Lands Highway | -339679.2083
|  |  | 1005507 |  | Hy-Tech Response, Inc. | Federal Lands Highway | 2011-05-31
|  |  | 1005508 |  |  | Federal Lands Highway | -339679.2083
|  |  | 1005509 |  |  | Jay County | -339679.2083
|  |  | 1005510 |  |  | Jay County | -339679.2083
|  |  | 1005513 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1005514 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1005515 | Porter |  | MPO - Northwest | -339679.2083 | CN
|  |  | 1005516 | Allen |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  |  | Newton |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1005517 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1005518 | Franklin |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1005519 | Owen |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1005520 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1005521 | Lake |  | Lake County | 2013-02-06 | CE
CN
PE
|  |  | 1005522 |  |  | Lake County | -339679.2083
|  |  | 1005523 |  |  | Lake County | -339679.2083
|  |  | 1005524 |  |  | Lake County | -339679.2083
|  |  | 1005525 |  |  | Lake County | -339679.2083
|  |  | 1005526 |  |  | Lake County | -339679.2083
|  |  | 1005527 |  |  | Lake County | -339679.2083
|  |  | 1005528 |  |  | Lake County | -339679.2083
|  |  | 1005529 |  |  | Lake County | -339679.2083
|  |  | 1005530 |  |  | Lake County | -339679.2083
|  |  | 1005531 |  |  | Lake County | -339679.2083
|  |  | 1005532 |  |  | Lake County | -339679.2083
|  |  | 1005533 |  |  | Lake County | -339679.2083
|  |  | 1005534 |  |  | Lake County | -339679.2083
|  |  | 1005535 |  |  | Lake County | -339679.2083
|  |  | 1005536 |  |  | Lake County | -339679.2083
|  |  | 1005537 |  |  | Lake County | -339679.2083
|  |  | 1005538 |  |  | Lake County | -339679.2083
|  |  | 1005539 |  |  | Lake County | -339679.2083
|  |  | 1005540 |  |  | Lake County | -339679.2083
|  |  | 1005541 |  |  | Lake County | -339679.2083
|  |  | 1005542 |  |  | Lake County | -339679.2083
|  |  | 1005543 |  |  | Lake County | -339679.2083
|  |  | 1005544 |  |  | Lake County | -339679.2083
|  |  | 1005545 |  |  | Lake County | -339679.2083
|  |  | 1005546 |  |  | Lake County | -339679.2083
|  |  | 1005547 |  |  | Carroll County | -339679.2083
|  |  | 1005548 | Henry | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1005549 |  |  | Aurora | 2009-09-10
|  |  | 1005550 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1005551 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1005552 | Boone |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1005553 | Hendricks |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 1005554 | Elkhart | Dummy Consulting Firm Too | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  |  | St. Joseph | Dummy Consulting Firm Too | Indiana Department of Transportation | 2011-04-13 | CN
|  |  | 1005555 |  |  | Zionsville | -339679.2083
|  |  | 1005556 |  |  | Zionsville | -339679.2083
|  |  | 1005557 |  |  | Zionsville | -339679.2083
|  |  | 1005558 |  | Clyde L. Hawkins | Indiana Department of Transportation | -339679.2083
|  |  | 1005559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005560 | Greene |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
ROW
|  |  | 1005561 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2014-05-31
|  |  | 1005562 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2015-05-31
|  |  | 1005563 | Daviess |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005564 | Greene |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005565 | Monroe |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1005566 | Monroe |  | Indiana Department of Transportation | 2012-12-04 | ROW
|  |  | 1005567 | Greene |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
ROW
|  |  | 1005568 | Boone |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1005569 | Warrick |  | Indiana Department of Natural Resources | 2016-08-05 | CN
PE
|  |  | 1005570 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Natural Resources | 2015-05-28 | CN
PE
ROW
|  |  | 1005571 | Vigo | Bayswater Company, LLC | Indiana Department of Natural Resources | 2011-05-31 | CN
|  |  | 1005572 | Marion | KERAMIDA Environmental, Inc. | Indiana Department of Natural Resources | 2015-12-14 | CN
PE
|  |  | 1005573 | LaGrange |  | Indiana Department of Natural Resources | 2015-07-30 | CN
PE
|  |  | 1005574 | Marion | DCD Consulting LLC | Indiana Department of Natural Resources | 2016-08-05 | CN
PE
|  |  | 1005575 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 1005576 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1005577 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 1005578 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 1005579 | Warrick |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1005580 | Hamilton | Hey and Associates, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1005581 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005582 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005583 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005585 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005586 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005588 | Various |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1005589 | LaPorte |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1005591 | Elkhart |  | Elkhart County | 2012-10-11 | CE
CN
PE
|  |  | 1005592 | Various |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 1005593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005594 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1005595 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1005596 | Whitley |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1005597 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1005598 | Gibson |  | Gibson County | -339679.2083 | CN
|  |  | 1005599 | White |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005600 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
RR
|  |  | 1005601 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005602 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005603 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005604 | Monroe |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
ROW
|  |  | 1005605 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 1005606 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005607 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005609 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1005610 | Madison |  | Anderson | 2013-05-01 | CE
CN
PE
RR
|  |  | 1005611 | Jennings |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
RR
|  |  | 1005612 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005613 | Jennings |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
UT
|  |  | 1005614 | Jackson |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1005615 | Jackson |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1005616 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005617 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1005618 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005619 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005620 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005621 |  |  | West Lafayette | 2011-01-12
|  |  | 1005622 | Howard |  | Howard County | 2010-04-21 | CN
|  |  | 1005623 | Elkhart |  | Elkhart County | -339679.2083 | CN
|  |  | 1005624 | Noble |  | Noble County | -339679.2083 | CN
|  |  | 1005625 | Perry |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1005626 | Spencer |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1005627 | Perry |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
PE
|  |  | 1005628 | Lake |  | MPO - Northwest | -339679.2083 | CN
|  |  | 1005629 | Lake | Applied Pavement Technology, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005630 | Lake | Baxter & Woodman, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005631 | Lake | Brenner Design Incorporated | Dyer | -339679.2083 | CN
|  |  | 1005632 | Lake | Browning Day Mullins Dierdorf Architects | MPO - Northwest | -339679.2083 | CN
|  |  | 1005633 | Lake | Chicago Testing Laboratory, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005634 | Lake | Compliance Consulting Service, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005635 | Lake | Cornerstone Design | MPO - Northwest | -339679.2083 | CN
|  |  | 1005636 | Lake | Courtland Title & Escrow, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005637 |  | Consolidated Test Company | MPO - Northwest | -339679.2083
|  |  | 1005638 | Lake |  | MPO - Northwest | -339679.2083 | CN
|  |  | 1005639 |  |  | MPO - Northwest | -339679.2083
|  |  | 1005640 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005641 | LaPorte |  | MPO - Northwest | -339679.2083 | PE
|  |  | 1005642 | Porter | Hy-Tech Response, Inc. | Porter | -339679.2083 | CN
|  |  | 1005643 | Porter | Huff & Huff, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005644 | Porter |  | MPO - Northwest | -339679.2083 | CN
|  |  | 1005645 |  | ICx Transportation Group | Pottawattamie Park | -339679.2083
|  |  | 1005646 | LaPorte | Farah and Sons, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005647 | Lake |  | Munster | -339679.2083 | CN
|  |  | 1005648 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083 | CN
|  |  | 1005649 | Lake | Karen | St. John | -339679.2083 | CN
|  |  | 1005650 | Porter | Leitner and Associates, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005651 | Lake | Matt L. Nepote, MAI | Whiting | -339679.2083 | CN
|  |  | 1005652 | Marion |  | Indiana Department of Transportation | 2010-09-01 | CE
CN
|  |  | 1005653 |  |  | Indiana Department of Transportation | 2010-12-08
|  |  | 1005654 |  |  | Indiana Department of Transportation | 2010-11-10
|  |  | 1005655 | Delaware |  | Indiana Department of Transportation | 2011-02-09 | CE
CN
|  |  | 1005656 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005657 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005658 | Huntington |  | Huntington County | 2015-01-14 | CE
CN
PE
ROW
|  |  | 1005659 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 1005660 |  |  | Boone County | -339679.2083
|  |  | 1005662 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1005663 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1005664 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1005665 | Warren |  | Warren County | 2015-05-07 | CE
CN
PE
ROW
|  |  | 1005666 | Owen |  | Owen County | -339679.2083 | PE
|  |  | 1005667 |  |  | Owen County | -339679.2083
|  |  | 1005668 | Vermillion |  | Vermillion County | 2012-11-15 | CE
CN
PE
ROW
|  |  | 1005669 | Fountain |  | Fountain County | 2015-12-09 | PE
ROW
|  |  | 1005670 | Vanderburgh | CGI | Evansville | 2010-12-08 | CE
CN
|  |  | 1005671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005672 | Porter |  | Porter County | 2014-03-05 | CE
CN
PE
ROW
|  |  | 1005673 | Starke |  | Starke County | -339679.2083 | PE
|  |  | 1005674 | Clark |  | St. Joseph County | 2012-07-11 | PE
|  |  |  | St. Joseph |  | St. Joseph County | 2012-07-11 | CE
CN
|  |  | 1005675 | Various |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005676 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 1005677 | Gibson |  | Indiana Department of Transportation | 2010-12-07 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2010-12-07 | CE
CN
|  |  | 1005678 | Wayne |  | Richmond | 2013-01-16 | CE
CN
PE
|  |  | 1005679 | Tippecanoe |  | Indiana Department of Transportation | 2014-12-17 | CE
PE
|  |  | 1005680 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1005681 | Tippecanoe |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1005682 | Tippecanoe |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1005683 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1005684 | Gibson |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1005685 | White |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 1005686 | Putnam |  | Putnam County | 2011-05-31 | CN
|  |  | 1005687 | Jackson |  | Indiana Department of Transportation | -339679.2083 | CE
CN
UT
|  |  | 1005688 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  |  | Tipton | CE Solutions, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1005689 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1005690 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1005691 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1005692 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 1005693 | Hancock |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
UT
|  |  | 1005694 | Marion |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1005695 | Hancock |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
|  |  | 1005696 | Hancock |  | Indiana Department of Transportation | 2012-02-08 | PE
ROW
|  |  |  | Marion |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
|  |  | 1005697 | Hancock |  | Indiana Department of Transportation | 2012-12-19 | PE
ROW
|  |  |  | Marion |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
PE
ROW
|  |  | 1005698 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005699 | Johnson |  | Johnson County | 2020-04-01 | CE
CN
PE
ROW
|  |  | 1005700 | Decatur |  | Decatur County | 2014-02-05 | CE
CN
PE
|  |  | 1005701 | Jackson |  | Jackson County | 2014-09-10 | CE
CN
PE
ROW
UT
|  |  |  | Washington |  | Jackson County | 2014-09-10 | CN
PE
|  |  | 1005702 | Dearborn |  | Dearborn County | 2014-04-02 | CE
CN
PE
ROW
|  |  | 1005703 | Clark |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 1005704 | Marion |  | Indianapolis | 2011-07-13 | CE
CN
|  |  | 1005705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005706 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005707 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005709 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005710 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005711 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005712 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005713 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005714 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005715 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005716 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005717 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005718 | Hancock |  | Hancock County | -339679.2083 | CN
|  |  | 1005719 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2011-08-10 | CE
CN
PE
|  |  | 1005720 |  | CTL Engineering of Indiana, Inc. | Allen County | -339679.2083
|  |  | 1005721 | Tippecanoe |  | Indiana Department of Transportation | 2010-11-10 | CE
CN
|  |  | 1005722 | Montgomery |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
PE
|  |  |  | Various |  | Indiana Department of Transportation | 2014-05-08 | PE
|  |  | 1005723 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2011-01-12
|  |  | 1005724 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005725 | Greene |  | Indiana Department of Transportation | 2012-05-31 | CE
PE
|  |  | 1005726 | Various |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005727 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005728 |  | ACMS Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005729 | Various |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005730 | Various |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005731 | Various |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005732 | Various |  | Indiana Department of Transportation | 2010-09-16 | CE
CN
|  |  | 1005733 |  | GS-IN P.C. | Indiana Department of Transportation | 2011-04-13
|  |  | 1005734 | Elkhart | Civil Inspection Services, LLC | Goshen | 2016-02-03 | CE
CN
|  |  | 1005735 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
PE
|  |  | 1005736 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005737 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005738 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1005739 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005740 | Adams |  | Indiana Department of Transportation | 2011-01-26 | CE
CN
|  |  | 1005741 | Steuben |  | Indiana Department of Transportation | 2010-12-08 | CE
CN
|  |  | 1005742 | Owen |  | Owen County | -339679.2083 | PE
|  |  | 1005743 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2009-10-23 | PE
|  |  | 1005744 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005745 | Carroll | Blood Hound, Inc. (former) | Delphi | 2015-12-09 | CE
CN
PE
|  |  | 1005746 | Pulaski |  | Pulaski County | -339679.2083 | CN
|  |  | 1005747 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1005748 | Adams | Foresight Land Surveying, Inc. | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1005749 | Jefferson | BradsKo Engineering and Surveying Inc. | Indiana Department of Transportation | 2010-10-06 | CE
CN
|  |  | 1005750 |  |  | Indiana Department of Transportation | 2011-05-31
|  |  | 1005751 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1005752 | Dubois | CMF Engineering, Inc. | Indiana Department of Transportation | 2012-05-02 | CE
CN
PE
|  |  | 1005754 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005755 | Tippecanoe | ASA Engineering Consultants, Inc. | Battle Ground | 2017-01-19 | CE
CN
|  |  | 1005756 |  |  | Lafayette | 2011-05-31
|  |  | 1005757 | Tippecanoe |  | Tippecanoe County | -339679.2083 | CN
|  |  | 1005758 |  |  | Lafayette | 2017-05-31
|  |  | 1005759 | Tippecanoe |  | Lafayette | -339679.2083 | CN
|  |  | 1005760 | Tippecanoe |  | Lafayette | -339679.2083 | CN
|  |  | 1005761 |  |  | Lafayette | -339679.2083
|  |  | 1005762 | St. Joseph |  | St. Joseph County | 2013-05-01 | CE
CN
UT
|  |  | 1005763 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2011-08-10 | CE
CN
|  |  | 1005764 | St. Joseph |  | South Bend | 2013-07-10 | CE
CN
|  |  | 1005765 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2011-08-10 | CE
CN
|  |  | 1005766 |  |  | South Bend | -339679.2083
|  |  | 1005767 | St. Joseph |  | St. Joseph County | 2011-07-13 | CE
CN
|  |  | 1005768 |  |  | South Bend | -339679.2083
|  |  | 1005769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005770 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005771 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005772 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005773 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005774 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2010-07-02 | PE
|  |  | 1005775 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005776 | Crawford |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1005777 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005778 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005779 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005780 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005781 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005782 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005783 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005784 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005785 |  |  | Indiana Department of Transportation | 2010-11-10
|  |  | 1005786 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005787 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005788 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005789 |  |  | Indiana Department of Transportation | 2011-05-31
|  |  | 1005790 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005792 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005793 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005794 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005795 | Porter |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1005796 |  |  | Elkhart County | -339679.2083
|  |  | 1005797 | Elkhart | Civil Inspection Services, LLC | Goshen | 2014-05-31 | CN
|  |  | 1005798 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2011-05-11 | CE
CN
|  |  | 1005799 | Elkhart |  | Elkhart County | 2012-10-02 | CN
|  |  | 1005800 | Elkhart | Civil Inspection Services, LLC | Goshen | 2011-08-10 | CE
CN
|  |  | 1005801 | Warrick |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1005802 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2012-03-07 | CE
CN
PE
|  |  | 1005803 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1005804 | Warrick |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1005805 | Warrick |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1005806 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083 | CN
|  |  | 1005807 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083 | CN
|  |  | 1005808 |  |  | Beech Grove | -339679.2083
|  |  | 1005809 | Gibson |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1005810 | Knox |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1005811 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005812 | Marion |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1005813 | Hendricks |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
PE
|  |  | 1005814 | Hendricks |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1005815 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005816 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1005817 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005818 | Marion |  | Indiana Department of Transportation | 2011-08-17 | CE
CN
|  |  | 1005819 | Marion |  | Indiana Department of Transportation | 2011-08-17 | CE
CN
|  |  | 1005820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005821 | Various |  | Indiana Department of Transportation | 2012-03-23 | RR
|  |  | 1005822 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005823 | Hendricks |  | Indiana Department of Natural Resources | 2015-05-31 | CN
PE
|  |  | 1005824 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005825 | Hamilton |  | Indiana Department of Natural Resources | 2012-09-28 | CN
PE
|  |  | 1005826 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005827 | Marion |  | Indiana Department of Natural Resources | 2012-05-31 | CN
PE
|  |  | 1005828 | Various |  | Indiana Department of Natural Resources | 2016-05-17 | CN
PE
|  |  | 1005829 | Warrick |  | Indiana Department of Natural Resources | 2012-05-31 | CN
PE
|  |  | 1005830 | Ripley |  | Indiana Department of Natural Resources | 2013-05-31 | CN
|  |  | 1005831 | Whitley |  | Indiana Department of Natural Resources | 2011-09-28 | CN
ROW
|  |  | 1005832 | Harrison |  | Indiana Department of Natural Resources | 2013-05-31 | CN
PE
|  |  |  | Whitley |  | Indiana Department of Natural Resources | 2013-05-31 | CN
|  |  | 1005833 | Ripley |  | Indiana Department of Natural Resources | 2012-05-31 | CN
|  |  | 1005834 | Various |  | Indiana Department of Natural Resources | 2013-07-29 | CN
|  |  | 1005835 | Various |  | Indiana Department of Natural Resources | 2011-09-28 | OT
|  |  | 1005836 | Various |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 1005837 | Lawrence |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1005838 | Various |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005839 | Gibson |  | Indiana Department of Transportation | 2011-08-10 | CE
CN
RR
|  |  | 1005840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005841 | White |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
RR
|  |  | 1005842 | Owen |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
|  |  | 1005843 | Elkhart |  | Elkhart County | 2013-05-31 | CN
|  |  | 1005844 | Clark |  | Clarksville | 2011-07-13 | CE
CN
|  |  | 1005845 | Greene |  | Indiana Department of Transportation | 2012-06-08 | RR
|  |  | 1005846 | Gibson |  | Pike County | 2015-02-04 | CN
|  |  |  | Pike |  | Pike County | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1005847 | Delaware | GS-IN P.C. | Muncie | 2011-04-13 | CE
CN
|  |  | 1005848 | Pike |  | Pike County | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1005849 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005850 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005851 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005852 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005853 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005854 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005855 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005856 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005857 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005859 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005860 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005861 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005862 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1005863 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005864 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005865 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005866 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005867 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005869 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005870 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005871 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005872 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005873 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005874 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005875 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005876 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005877 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005878 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005879 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005880 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005881 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1005882 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005883 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005884 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005885 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005886 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005887 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005888 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005889 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005890 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1005891 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1005892 | Vanderburgh |  | Vanderburgh County | -339679.2083 | CN
|  |  | 1005893 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1005894 | White |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1005895 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1005896 | Newton |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
|  |  | 1005897 | Blackford |  | Blackford County | -339679.2083 | CN
|  |  | 1005898 |  |  | Fulton County | 2011-04-13
|  |  | 1005899 | Sullivan | Klug Engineering, Inc. | Sullivan | 2012-01-11 | CE
CN
PE
|  |  | 1005900 | Knox | AV Consulting Engineers, Inc. | Bicknell | 2013-04-03 | CE
CN
PE
|  |  | 1005901 | Morgan |  | Morgan County | 2013-02-06 | CE
CN
PE
|  |  | 1005902 | Warren |  | Warren County | 2012-05-02 | CE
CN
PE
|  |  | 1005903 | Fulton |  | Fulton County | 2012-05-02 | CE
CN
PE
|  |  | 1005904 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005905 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005906 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005907 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2011-08-10 | CE
CN
|  |  | 1005908 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2011-08-10 | CE
CN
|  |  | 1005909 |  |  | South Bend | -339679.2083
|  |  | 1005910 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005911 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005912 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005913 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005914 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005915 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005916 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005917 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005918 | Miami |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005919 | Dekalb |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005920 | Dekalb |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005921 | Dekalb |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005922 | Steuben |  | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1005923 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CN
|  |  | 1005924 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1005925 | St. Joseph | Dummy Consulting Firm Too | Lakeville | 2015-08-05 | CE
CN
PE
UT
|  |  | 1005926 | Lake | Baxter & Woodman, Inc. | Crown Point | 2013-08-07 | CE
CN
PE
|  |  | 1005927 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1005928 |  | Hydrogeology, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005929 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-01-11 | CE
CN
RR
|  |  | 1005930 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2017-05-31 | PE
|  |  | 1005931 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2011-04-20 | RR
|  |  | 1005932 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-05-31
|  |  | 1005933 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005934 | LaPorte |  | MPO - Northwest | -339679.2083 | CN
|  |  | 1005935 | LaPorte | Douglass Environmental Services, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005936 | LaPorte | Farah and Sons, Inc. | MPO - Northwest | -339679.2083 | CN
|  |  | 1005937 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005938 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005939 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005940 | Boone | Martinez Corporation | Whitestown | -339679.2083 | PE
|  |  | 1005941 | Elkhart |  | Elkhart County | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1005942 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005943 | Madison |  | Madison County | 2013-07-10 | CE
CN
|  |  | 1005944 | Madison |  | Madison County | 2013-07-10 | CE
CN
|  |  | 1005945 |  |  | Tipton County | -339679.2083
|  |  | 1005946 | Tipton |  | Tipton County | 2013-12-11 | CE
CN
PE
ROW
RR
|  |  | 1005947 | Johnson |  | Johnson County | 2019-12-11 | CE
CN
PE
ROW
UT
|  |  | 1005948 | Scott |  | Scott County | 2013-08-31 | PE
|  |  | 1005949 | Warrick |  | Indiana Department of Transportation | 2010-12-15 | CE
CN
|  |  | 1005950 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1005951 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1005952 | Dekalb |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1005953 | Huntington |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1005954 | Whitley |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1005955 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005956 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005957 | Ripley |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
PE
|  |  | 1005958 | Lawrence |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 1005959 | Scott |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 1005960 | Scott |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
PE
|  |  | 1005961 | Jackson |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 1005962 | Jackson |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 1005963 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2012-05-31 | PE
|  |  | 1005964 | Dearborn |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005965 | Washington |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005966 | Switzerland |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005967 | Franklin |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005968 | Ripley |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005969 | Ripley |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1005970 | Cass | Eco Logic, LLC | Logansport | 2012-11-15 | CE
CN
|  |  | 1005971 |  |  | Indiana Department of Transportation | 2012-05-10
|  |  | 1005972 |  |  | Posey County | -339679.2083
|  |  | 1005973 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1005974 | Daviess | Frost Engineering & Consulting Company | Daviess County | 2015-02-04 | CE
CN
PE
ROW
UT
|  |  | 1005975 | Daviess |  | Daviess County | -339679.2083 | PE
|  |  | 1005976 | Pike |  | Pike County | -339679.2083 | CN
|  |  | 1005977 | Perry |  | Perry County | -339679.2083 | CN
|  |  | 1005978 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1005979 | Shelby |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1005980 | Johnson |  | Johnson County | 2011-01-12 | CE
CN
|  |  | 1005981 |  |  | Dubois County | -339679.2083
|  |  | 1005982 |  |  | Indiana Department of Transportation | 2010-08-28
|  |  | 1005983 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005984 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005985 |  |  | Aurora | -339679.2083
|  |  | 1005986 |  |  | Bainbridge | -339679.2083
|  |  | 1005987 |  | Casteel Real Estate | Bartholomew County | -339679.2083
|  |  | 1005988 |  | Associated Right-of-Way Services, Inc. | Columbus | -339679.2083
|  |  | 1005989 |  |  | Bartholomew County | -339679.2083
|  |  | 1005990 |  |  | Bartholomew County | -339679.2083
|  |  | 1005991 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1005992 |  | American Resources Group, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1005993 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1005994 | Elkhart |  | Elkhart County | 2014-07-09 | CE
CN
PE
ROW
|  |  | 1005995 | Wells | Enginuity Management & Consulting Corporation | Markle | 2016-04-06 | CE
CN
PE
ROW
|  |  | 1005996 | Dekalb | Mader Design, LLC | Waterloo | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1005997 | Vanderburgh | CGI | Evansville | 2011-12-14 | CE
CN
RR
|  |  | 1005998 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1005999 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006000 | Daviess |  | Indiana Department of Transportation | 2011-01-12 | CN
UT
|  |  |  | Pike |  | Indiana Department of Transportation | 2011-01-12 | CE
CN
UT
|  |  | 1006001 |  |  | Indiana Department of Transportation | 2011-01-12
|  |  | 1006002 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006003 | Howard |  | Kokomo | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1006004 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1006005 | Daviess | AMEC E&I, Inc. | Indiana Department of Transportation | 2010-09-15 | PE
|  |  | 1006006 |  | Cornerstone Design | Indiana Department of Transportation | 2011-05-11
|  |  | 1006007 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1006008 | Various |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1006009 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006010 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-05-31 | CN
|  |  | 1006011 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006012 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006013 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006014 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006015 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006017 | Porter | Huff & Huff, Inc. | Portage | 2012-09-12 | CE
CN
|  |  | 1006018 |  |  | Muncie | 2011-04-13
|  |  | 1006019 | Vigo | Bayswater Company, LLC | Terre Haute | 2013-02-06 | CE
CN
PE
ROW
|  |  | 1006020 | Hendricks |  | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1006021 | Dearborn | Clyde L. Hawkins | Dearborn County | -339679.2083 | PE
|  |  | 1006022 | Johnson |  | Johnson County | 2012-12-12 | CE
CN
PE
|  |  | 1006023 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 1006024 | Vanderburgh | CGI | Evansville | 2015-03-18 | CE
CN
PE
ROW
|  |  | 1006025 |  |  | Indiana Department of Transportation | 2011-02-09
|  |  | 1006026 | Marion |  | Southport | 2015-07-08 | CE
CN
PE
|  |  | 1006027 | Hamilton |  | Carmel | 2015-08-05 | CE
CN
|  |  | 1006028 | Randolph |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  |  | Wayne |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 1006029 | Vanderburgh |  | Evansville | 2016-10-05 | CN
PE
|  |  | 1006030 | Warrick |  | Newburgh | 2016-11-16 | CE
CN
PE
|  |  | 1006031 | Vanderburgh | CGI | Evansville | 2015-07-08 | CE
CN
PE
|  |  | 1006032 | Gibson |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1006033 | Jefferson |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  |  | Switzerland |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1006034 | Jefferson |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1006035 | Allen |  | Indiana Department of Transportation | 2012-01-13 | CE
CN
|  |  | 1006036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006037 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 1006038 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 1006039 |  |  | Franklin County | -339679.2083
|  |  | 1006040 |  |  | Indianapolis | -339679.2083
|  |  | 1006041 | Johnson |  | Greenwood | 2012-12-12 | CE
CN
PE
|  |  | 1006042 | Cass |  | Cass County | -339679.2083 | CN
|  |  | 1006043 | Hendricks | Horner and Shifrin, Inc. | Plainfield | 2011-08-10 | CE
CN
|  |  | 1006044 | Howard |  | Kokomo | 2011-09-08 | CE
CN
|  |  | 1006045 | Howard |  | Howard County | 2012-05-31 | CN
|  |  | 1006046 | Floyd |  | New Albany | 2016-02-03 | CE
CN
PE
|  |  | 1006047 | Floyd |  | New Albany | 2014-03-05 | CE
CN
PE
|  |  | 1006048 | Floyd |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
PE
|  |  | 1006049 | Floyd |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
PE
|  |  | 1006050 | Shelby |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1006051 | Shelby |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1006052 |  | Midwest Archaeological Research Services, Inc. | Zionsville | -339679.2083
|  |  | 1006053 |  | Alliance Appraisal Group, LLC | Brownstown | -339679.2083
|  |  | 1006054 | Daviess |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  |  | Gibson |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  |  | Pike |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1006055 | Greene |  | Indiana Department of Transportation | 2010-09-28 | PE
|  |  | 1006056 | Tippecanoe |  | Tippecanoe County | 2012-05-02 | CE
CN
UT
|  |  | 1006057 | Marion |  | Lawrence | -339679.2083 | PE
|  |  | 1006058 | Hamilton |  | Hamilton County | 2011-09-08 | CE
CN
|  |  | 1006059 | Hamilton |  | Hamilton County | 2011-09-08 | CE
CN
|  |  | 1006060 | Hamilton |  | Hamilton County | 2011-09-08 | CE
CN
|  |  | 1006061 | Hamilton |  | Hamilton County | 2013-01-16 | CE
CN
ROW
UT
|  |  | 1006062 | Hamilton |  | Hamilton County | 2011-09-08 | CE
CN
|  |  | 1006063 | Tippecanoe | Bertsch-Frank & Associates, LLC | Dayton | 2014-05-08 | CE
CN
|  |  | 1006064 | Jennings |  | Jennings County | -339679.2083 | PE
|  |  | 1006066 |  |  | Tippecanoe County | 2011-01-12
|  |  | 1006067 |  |  | Clarks Hill | -339679.2083
|  |  | 1006068 | Tippecanoe | ASA Engineering Consultants, Inc. | Battle Ground | 2013-05-01 | CE
CN
PE
|  |  | 1006069 | Tippecanoe | Bertsch-Frank & Associates, LLC | Dayton | 2014-03-05 | CE
CN
|  |  | 1006070 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1006071 |  |  | Indiana Department of Transportation | 2011-07-13
|  |  | 1006072 | Miami | Alt & Witzig Engineering, Inc. | Peru | -339679.2083 | PE
|  |  | 1006073 | Greene |  | Indiana Department of Transportation | 2011-12-21 | ROW
UT
|  |  | 1006074 | Greene |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
ROW
UT
|  |  | 1006075 | Monroe |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
ROW
UT
|  |  | 1006076 | Greene |  | Indiana Department of Transportation | 2012-07-11 | UT
|  |  |  | Monroe |  | Indiana Department of Transportation | 2012-07-11 | ROW
UT
|  |  | 1006077 | Wayne |  | Indiana Department of Transportation | 2013-01-16 | PE
|  |  | 1006078 | Henry | EFI Global, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1006079 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1006080 | Vanderburgh | CGI | Evansville | 2025-01-15 | PE
|  |  | 1006081 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1006082 | Vanderburgh | CGI | Evansville | 2014-09-10 | PE
|  |  | 1006083 | Vanderburgh | CGI | Evansville | 2016-07-13 | PE
|  |  | 1006084 | Vanderburgh | CGI | Evansville | 2019-01-16 | CE
CN
PE
|  |  | 1006085 | Vanderburgh | CGI | Evansville | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1006086 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1006087 | Tippecanoe |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1006088 | Carroll | Dodd Title Corporation | Indiana Department of Transportation | 2011-05-13 | PE
|  |  | 1006089 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1006090 | Ripley |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
ROW
|  |  | 1006091 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006092 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2010-11-24
|  |  | 1006093 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006094 | Hendricks |  | Avon | 2014-08-06 | CE
CN
PE
ROW
|  |  | 1006095 | Hendricks | AFRAM Group, Incorporated | Avon | 2015-02-04 | CE
CN
PE
|  |  | 1006096 | Hendricks |  | Avon | 2012-04-04 | CE
CN
PE
|  |  | 1006097 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006098 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1006099 |  |  | Indiana Department of Transportation | 2011-12-14
|  |  | 1006100 |  |  | Indiana Department of Transportation | 2011-07-13
|  |  | 1006101 |  | ARCADIS | Indiana Department of Transportation | 2012-01-11
|  |  | 1006102 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 1006103 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 1006104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006106 | Hamilton |  | Hamilton | 2011-09-08 | CE
CN
|  |  | 1006107 | Hamilton |  | Hamilton County | 2011-09-08 | CE
CN
|  |  | 1006108 |  |  | Muncie | -339679.2083
|  |  | 1006109 |  |  | Yorktown | -339679.2083
|  |  | 1006110 |  |  | Muncie | -339679.2083
|  |  | 1006111 | Delaware |  | Delaware County | 2016-01-13 | CE
CN
PE
ROW
|  |  | 1006112 | Delaware |  | Delaware County | 2014-04-02 | CE
CN
PE
|  |  | 1006113 | Noble |  | Noble County | 2011-10-13 | CE
CN
PE
|  |  | 1006114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006115 | Lawrence |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
ROW
UT
|  |  | 1006116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006117 | Hancock |  | Indiana Department of Transportation | 2014-05-31 | ROW
|  |  | 1006118 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1006119 | Wells |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1006120 | Hancock |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006121 | Hamilton |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
UT
|  |  | 1006122 | Wells |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1006123 | Whitley |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
ROW
|  |  | 1006124 | Wells |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1006125 | Wells |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
ROW
|  |  | 1006126 | Grant |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
ROW
|  |  | 1006127 | Whitley |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1006128 | Whitley |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
ROW
|  |  | 1006129 | Allen | EDP Consultants | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
ROW
|  |  |  | Dekalb | EDP Consultants | Indiana Department of Transportation | 2016-01-13 | PE
|  |  | 1006130 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1006131 | Miami |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006132 | Miami |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006135 | Wabash |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006136 | Wabash |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006137 | Wabash |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006138 | Henry | Knight E/A, Inc. | Indiana Department of Transportation | 2015-11-17 | CE
CN
|  |  | 1006139 | Wabash |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006140 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006141 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006142 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006143 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006144 | Adams |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1006145 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006146 | Allen |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1006147 | Kosciusko |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1006148 | Kosciusko |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1006149 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006151 | Randolph | Langworthy, Strader, LeBlanc & Associates, Inc. | Indiana Department of Transportation | 2013-10-09 | CE
CN
RR
|  |  | 1006152 | Steuben |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
ROW
|  |  | 1006153 | Noble |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1006154 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006155 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006156 | Dekalb | KZF Design, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  | 1006157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006158 | Allen |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
|  |  | 1006159 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1006160 | Adams |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
|  |  | 1006161 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1006162 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006163 |  | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006164 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  |  | Randolph | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1006165 | Miami |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1006166 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006167 | Miami |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1006168 | Kosciusko |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1006169 | Tipton | Land Construction Corp | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1006170 | Allen |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1006171 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1006172 | Allen |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1006173 | Henry | Enterprise Information Solutions, Inc. | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  |  | Madison | Enterprise Information Solutions, Inc. | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006174 | Whitley |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1006175 |  | Duneland Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006176 | Steuben |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1006177 | Whitley |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1006178 |  | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006179 | Wabash |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1006180 | Elkhart |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1006181 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1006182 | Huntington |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1006183 | Huntington |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
RR
|  |  | 1006184 | Huntington |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1006185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006187 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1006188 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-05-10 | PE
|  |  | 1006189 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1006190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006192 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006193 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2014-12-10 | CE
CN
RR
|  |  | 1006194 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006195 | Adams |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1006196 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2016-07-13 | CE
CN
ROW
|  |  | 1006197 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2016-02-03 | CE
CN
RR
|  |  | 1006198 |  | Home Guide Realty Services | Indiana Department of Transportation | -339679.2083
|  |  | 1006199 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
ROW
|  |  | 1006200 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006201 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006203 | Wells |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1006204 |  | Wessler Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006205 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006206 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  | 1006207 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1006208 |  | Home Guide Realty Services | Indiana Department of Transportation | -339679.2083
|  |  | 1006209 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006210 | Elkhart |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
ROW
UT
|  |  | 1006211 | Allen |  | Indiana Department of Transportation | 2015-05-31 | ROW
|  |  | 1006212 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006213 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1006214 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1006215 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1006216 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1006217 |  | D & D Consulting Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006218 | Noble |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1006219 | Various |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1006220 | Kosciusko |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1006221 | Clark |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
ROW
|  |  | 1006222 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1006223 | Brown |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1006224 | Blackford |  | Indiana Department of Transportation | 2015-01-27 | PE
|  |  | 1006225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006226 | Howard |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1006227 | Boone |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2014-08-20 | CE
|  |  | 1006228 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006229 | Boone |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1006230 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006231 | Switzerland |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1006232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006233 | Marion |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006234 | Marion |  | Indiana Department of Transportation | 2014-04-09 | PE
|  |  | 1006235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006236 | Bartholomew |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1006237 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 1006238 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1006239 | Scott |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1006240 | Franklin |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
ROW
|  |  | 1006241 | Decatur |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
ROW
UT
|  |  | 1006242 | Jefferson |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
UT
|  |  | 1006243 | Bartholomew |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1006244 | Marion |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
ROW
|  |  | 1006245 | Marion |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006246 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006247 | Marion |  | Indiana Department of Transportation | 2015-06-19 | CE
CN
ROW
|  |  | 1006248 | Carroll |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
ROW
|  |  | 1006249 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006250 | Boone |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006251 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006252 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1006253 | Madison |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
ROW
|  |  | 1006254 | Marion |  | Indiana Department of Transportation | 2014-04-02 | PE
|  |  | 1006255 | Marion |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1006256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006257 | Hamilton |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1006258 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006259 | Marion |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
UT
|  |  | 1006260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006261 | Marion |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
PE
|  |  | 1006262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006263 | Marion |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006264 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006265 | Randolph |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1006266 | Rush |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1006267 | Delaware |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1006268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006270 | Blackford |  | Indiana Department of Transportation | 2016-07-13 | PE
|  |  |  | Jay |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 1006271 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006272 | Carroll | Chemical Dependency Program of Indiana | Galveston | 2013-05-01 | CE
CN
PE
|  |  |  | Cass | Chemical Dependency Program of Indiana | Galveston | 2013-05-01 | CE
CN
|  |  | 1006273 | Pulaski | McCormick Engineering, LLC | Winamac | -339679.2083 | PE
|  |  | 1006274 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1006275 | Rush |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
|  |  | 1006276 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1006277 | White |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
ROW
|  |  | 1006278 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006279 | Clinton |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1006280 | Clinton |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1006281 | Tippecanoe |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1006282 | Tippecanoe |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1006283 | Benton |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1006284 | Benton |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1006285 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006286 | Clinton |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1006287 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006288 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006289 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1006290 | Clay |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1006291 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006292 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006294 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006295 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006297 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006298 | Henry |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
|  |  | 1006299 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006302 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006305 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006306 | Rush |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1006307 | Benton |  | Indiana Department of Transportation | 2015-08-19 | CE
CN
PE
|  |  | 1006308 | Clay |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1006309 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006311 | Marion |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006312 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006313 | Wayne |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1006314 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1006315 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006316 | Boone |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
RR
|  |  |  | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
RR
|  |  | 1006317 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006319 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006320 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  | 1006321 | Hendricks | All About Pavements, Inc. | Brownsburg | 2015-11-10 | CE
CN
PE
|  |  | 1006322 | Clinton |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1006323 | Boone |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1006324 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006325 | Fountain |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
ROW
|  |  | 1006326 | Montgomery |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
ROW
|  |  | 1006327 | Putnam |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1006328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006329 | Fountain |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1006330 | Montgomery |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
ROW
|  |  | 1006331 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006332 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006333 | Delaware | GS-IN P.C. | Muncie | 2016-02-03 | CE
CN
PE
|  |  | 1006334 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006335 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006336 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006337 | Delaware |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
ROW
|  |  | 1006338 | Benton |  | Indiana Department of Transportation | 2015-08-19 | CE
CN
|  |  | 1006339 | Clay |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1006340 | Fountain |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
ROW
|  |  | 1006341 | Howard |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1006342 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006343 | Wayne |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
ROW
UT
|  |  | 1006344 | Orange |  | Indiana Department of Transportation | 2017-04-05 | PE
|  |  |  | Owen |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1006345 | Wayne |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1006346 | Owen |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
ROW
|  |  | 1006347 | Clay |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1006348 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006349 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006351 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006353 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1006354 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1006355 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006356 | Wayne |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1006357 | Marion |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
ROW
|  |  | 1006358 | Vermillion |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1006359 | Tipton |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006360 | Rush |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1006361 | Marion |  | Indianapolis | 2016-05-31 | PE
ROW
|  |  | 1006362 | Shelby |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
PE
|  |  | 1006363 | Henry |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1006364 | Dearborn |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
ROW
|  |  | 1006365 | Marion |  | Lawrence | 2015-08-05 | CE
CN
PE
UT
|  |  | 1006366 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006367 | Carroll | Blood Hound, Inc. (former) | Delphi | 2013-04-03 | CE
CN
PE
|  |  | 1006368 | Benton |  | Benton County | -339679.2083 | CN
|  |  | 1006369 | Carroll | Blood Hound, Inc. (former) | Delphi | -339679.2083 | PE
|  |  | 1006370 | Marshall | Active Environmental Services, Inc. | Bourbon | -339679.2083 | PE
|  |  | 1006371 | Porter | Leitner and Associates, Inc. | Valparaiso | 2015-01-14 | CN
|  |  | 1006372 | Vermillion |  | Vermillion County | -339679.2083 | CN
|  |  | 1006373 | St. Joseph |  | St. Joseph County | 2013-01-16 | CE
CN
PE
|  |  | 1006374 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2011-07-13 | CE
CN
PE
|  |  | 1006375 | Fountain |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
ROW
|  |  | 1006376 | Marshall | Bayer & Becker, Inc. | Culver | 2012-05-02 | CE
CN
|  |  | 1006377 | Monroe |  | Monroe County | 2013-07-10 | CE
CN
|  |  | 1006378 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1006379 |  |  | South Bend | -339679.2083
|  |  | 1006380 |  |  | South Bend | -339679.2083
|  |  | 1006381 |  |  | South Bend | -339679.2083
|  |  | 1006382 | Steuben | ABt SRBI | Angola | 2012-01-11 | CE
CN
PE
|  |  | 1006383 | Monroe |  | Bloomington | 2013-05-31 | CN
|  |  | 1006384 | Dekalb |  | Garrett | -339679.2083 | PE
|  |  | 1006385 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | -339679.2083
|  |  | 1006386 | Scott |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
UT
|  |  | 1006387 |  |  | Winamac | -339679.2083
|  |  | 1006388 | Morgan |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
ROW
RR
|  |  | 1006389 | Decatur |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1006390 |  |  | Galveston | -339679.2083
|  |  | 1006391 | Decatur |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
UT
|  |  | 1006392 | Decatur |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1006393 | Jennings |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
UT
|  |  | 1006394 | Clark | Gregg A. Townsend | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1006395 | Johnson |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1006396 | Jennings |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
UT
|  |  | 1006397 | Morgan |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
ROW
RR
|  |  | 1006398 | Brown |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
ROW
|  |  | 1006399 | Randolph |  | Winchester | 2012-09-12 | CE
CN
PE
|  |  | 1006400 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1006401 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2011-04-13 | CE
CN
|  |  | 1006402 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1006403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006404 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2011-01-26 | CE
CN
|  |  | 1006405 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006407 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006408 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2013-05-01
|  |  | 1006409 | Switzerland |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1006410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006411 |  | BradsKo Engineering and Surveying Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006412 | Decatur |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1006414 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006415 | Jennings |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1006416 | Ripley |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1006417 | Jefferson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 1006418 | Henry |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1006419 | Shelby |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
PE
|  |  | 1006420 | Marion |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006421 | Madison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1006422 | Hancock |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1006423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006424 | Jefferson |  | Indiana Department of Transportation | 2020-01-15 | PE
ROW
|  |  | 1006425 | Marion |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1006426 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006427 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006429 | Jackson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
UT
|  |  | 1006430 | Johnson |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  |  | Shelby |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1006431 | Clark |  | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 1006432 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006433 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006434 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006435 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1006436 | Hamilton |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
ROW
|  |  | 1006437 | Marion |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1006438 | Bartholomew |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1006439 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1006440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006441 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1006442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006443 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006444 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006446 | Delaware |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1006447 | Delaware |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1006448 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006449 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006450 | Bartholomew | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  |  | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2015-12-09 | CN
|  |  | 1006451 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006452 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006453 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1006454 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1006455 | Marion |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1006456 | Lake |  | Indiana Department of Transportation | 2016-05-31 | PE
ROW
RR
|  |  | 1006457 | Pike |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
ROW
UT
|  |  | 1006458 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006459 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006460 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006461 | Knox |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1006462 | Knox |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1006463 |  | Lonco, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006464 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006465 |  | Aerofinity, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006466 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1006467 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006468 | Madison |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1006469 | Johnson |  | Johnson County | 2014-04-02 | CE
CN
PE
|  |  | 1006470 | Delaware |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1006471 | Grant |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1006472 | Madison |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
ROW
|  |  | 1006473 | Owen |  | Spencer | 2013-04-03 | CE
CN
PE
|  |  | 1006474 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006475 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006476 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2014-03-05 | CE
CN
|  |  | 1006477 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006478 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006479 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006480 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006481 | Jefferson |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1006482 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006483 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006484 | Ohio |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1006485 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006486 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006487 | Lake |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1006488 | Lake |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1006489 | Madison |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1006490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006491 | Knox |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
|  |  | 1006492 | Daviess |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
ROW
UT
|  |  | 1006493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006494 |  | Eilts Consulting Services | Indiana Department of Transportation | -339679.2083
|  |  | 1006495 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006497 | Warrick |  | Indiana Department of Transportation | 2013-10-09 | CE
UT
|  |  | 1006498 | Dubois |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
ROW
|  |  | 1006499 | Dubois |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
ROW
|  |  | 1006500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006501 | Pike |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
ROW
|  |  | 1006502 | Pike |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
ROW
|  |  | 1006503 | Dubois |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1006504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006505 | Posey |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1006506 | Posey |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1006507 |  | Consulting Management Inspection Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006508 | Gibson | III FFC | Indiana Department of Transportation | 2013-09-11 | CE
CN
RR
|  |  | 1006509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006512 | Gibson | III FFC | Indiana Department of Transportation | 2011-07-13 | CE
CN
|  |  | 1006513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006514 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006515 | Sullivan |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1006516 | Bartholomew |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1006517 |  |  | Dearborn County | -339679.2083
|  |  | 1006518 |  |  | Dearborn County | -339679.2083
|  |  | 1006519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006520 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006521 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006522 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006523 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006524 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006525 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006526 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006527 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006528 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006529 | Greene |  | Linton | -339679.2083 | PE
|  |  | 1006530 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006531 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006532 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006533 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1006534 | Marion | DCD Consulting LLC | Other | 2013-05-31 | PE
|  |  | 1006535 | Madison |  | MPO - Anderson | -339679.2083 | PE
|  |  | 1006536 |  |  | St. Joseph County | 2011-03-23
|  |  | 1006537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006538 |  | Indiana Connect - a Joint Venture | Indiana Department of Transportation | -339679.2083
|  |  | 1006539 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1006540 | Hamilton |  | Fishers | 2011-08-10 | CE
CN
PE
|  |  | 1006541 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1006542 | Hamilton |  | Fishers | 2011-08-10 | CE
CN
|  |  | 1006543 | Warrick |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1006544 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006545 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1006546 | Wayne |  | Wayne County | 2014-07-09 | CE
CN
PE
|  |  | 1006547 | Putnam |  | Putnam County | 2013-07-10 | CE
CN
PE
|  |  | 1006548 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1006549 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006550 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006551 | Hendricks | All About Pavements, Inc. | Brownsburg | 2013-08-14 | CE
CN
RR
|  |  | 1006552 | Dekalb | American Engineers, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1006553 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006554 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1006555 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006557 | Marion |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 1006558 | Marion |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 1006559 | Marion |  | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 1006560 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006561 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006562 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006563 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1006564 |  |  | Indiana Department of Transportation | 2011-07-13
|  |  | 1006565 |  |  | Indiana Department of Transportation | 2011-07-13
|  |  | 1006566 |  |  | Indiana Department of Transportation | 2011-07-13
|  |  | 1006567 | Vigo | Bayswater Company, LLC | Terre Haute | 2013-05-01 | CE
CN
PE
|  |  | 1006568 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1006569 | Owen |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1006570 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1006571 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1006572 | Monroe |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
|  |  | 1006573 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1006574 | Clark |  | Clark County | -339679.2083 | PE
|  |  | 1006575 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-01-06 | PE
|  |  | 1006576 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
ROW
|  |  | 1006577 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006578 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006579 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1006580 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006581 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 1006582 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006583 |  |  | Indiana Department of Transportation | 2011-10-26
|  |  | 1006584 |  |  | Indiana Department of Transportation | 2011-10-26
|  |  | 1006585 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2012-05-11 | CE
CN
|  |  | 1006586 | Dearborn |  | Dearborn County | 2012-01-11 | CE
CN
PE
|  |  | 1006587 | Dearborn |  | Dearborn County | 2012-01-11 | CE
CN
PE
|  |  | 1006588 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006589 | Vanderburgh |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
RR
|  |  | 1006590 | Dearborn |  | Dearborn County | 2012-01-11 | CE
CN
PE
|  |  | 1006591 | Marion |  | Indianapolis | 2013-05-01 | CE
CN
PE
|  |  | 1006592 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 1006593 | Delaware |  | Delaware County | 2014-01-03 | PE
|  |  | 1006594 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 1006595 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006596 |  | Gregg A. Townsend | Indiana Department of Transportation | -339679.2083
|  |  | 1006597 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1006598 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006599 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006600 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006601 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006602 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
UT
|  |  | 1006603 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006604 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006605 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006606 | Starke |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1006607 | Newton |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1006608 | Porter |  | Indiana Department of Transportation | 2021-01-13 | PE
ROW
RR
|  |  | 1006609 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006611 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006612 | Lake |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1006613 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006614 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006615 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006616 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006617 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006618 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006619 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-03-04 | PE
ROW
|  |  | 1006620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006621 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006622 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1006623 |  | Land Title Service Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1006624 | Porter |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1006625 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006626 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006627 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006628 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006629 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006631 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006632 | St. Joseph |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1006633 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
[5 empty] | Collier Transport Inc. | Indiana Department of Transportation | 2012-02-08
|  |  | 1006634 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
ROW
RR
|  |  | 1006635 | Lake | Applied Pavement Technology, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1006636 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
RR
|  |  | 1006637 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1006638 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1006639 | Lake | Cornerstone Design | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1006640 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006641 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1006642 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006643 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006644 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006645 | LaPorte |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
RR
|  |  | 1006646 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006647 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006648 | Porter | Marine Solutions, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
RR
|  |  | 1006649 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006651 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1006652 | LaPorte |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
|  |  | 1006653 | LaPorte |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  | 1006654 | White |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1006655 | White |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1006656 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006657 | Carroll | CRI Construction Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
RR
|  |  | 1006658 | Carroll | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
RR
|  |  | 1006659 |  | J. H. Rudolph & Co., Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006660 |  | J. H. Rudolph & Co., Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006661 | White |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
RR
|  |  | 1006662 | White |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1006663 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1006664 | Marshall | Active Environmental Services, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
RR
|  |  | 1006665 | Marshall |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
RR
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1006666 | LaPorte | Gensic Engineering, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
RR
|  |  |  | St. Joseph | Gensic Engineering, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
RR
|  |  | 1006667 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006668 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1006669 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006670 | Marshall |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
RR
|  |  | 1006671 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1006672 |  | Bayer & Becker, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006673 | Starke |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1006674 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006675 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006676 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006678 |  | GG Consulting, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006679 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006680 | Wayne |  | Richmond | 2012-07-11 | CE
CN
PE
|  |  | 1006681 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006682 | Jasper |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1006683 | LaPorte | Domain Architecture, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  |  | Porter | Domain Architecture, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1006684 | LaPorte | Donohue & Associates, Inc. | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1006685 | Fulton | Deig Bros. Lumber & Construction Co., Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1006686 |  | Bayer & Becker, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006687 | Henry | GeoSolutions, Inc. | New Castle | 2012-05-02 | CE
CN
PE
|  |  | 1006688 | Marshall |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006689 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006691 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006692 | Pulaski |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1006693 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1006694 | Lake |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1006695 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006696 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006697 | Newton |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1006698 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1006699 | Porter |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1006700 | St. Joseph |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1006701 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006702 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006703 | LaPorte |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1006704 | LaPorte |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1006705 | Newton |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1006706 | Cass |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1006707 | Cass |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1006708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006709 | Jasper |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1006710 |  | American Commercial Title & Escrow | Indiana Department of Transportation | -339679.2083
|  |  | 1006711 | Starke |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1006712 | Starke |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006713 |  | American Commercial Title & Escrow | Indiana Department of Transportation | -339679.2083
|  |  | 1006714 | White |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1006715 | Newton |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1006716 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1006717 | LaPorte |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
RR
|  |  | 1006718 | LaPorte |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1006719 | Pulaski |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1006720 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006721 | Marshall |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
RR
|  |  | 1006722 | Porter |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1006723 | Starke |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1006724 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006725 | Porter |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
RR
|  |  | 1006726 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006727 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1006728 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 1006729 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006730 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006731 | LaPorte |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1006732 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1006733 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006734 | St. Joseph |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1006735 | Newton |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1006736 |  | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083
|  |  | 1006737 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1006738 | Lake |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1006739 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006741 | Newton |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1006742 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1006743 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1006744 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1006745 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006746 | LaPorte |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1006747 | LaPorte |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1006748 | Porter |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1006749 | Marshall |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
ROW
|  |  | 1006750 | Porter |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1006751 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2013-11-06 | CE
CN
ROW
|  |  | 1006752 | Newton |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
ROW
|  |  | 1006753 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006754 | LaPorte |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
|  |  | 1006755 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006756 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1006757 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1006758 | LaPorte | MCIS LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
RR
|  |  | 1006759 |  | Donohue & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006760 | LaPorte |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
RR
|  |  | 1006761 | Marshall |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1006762 | Marshall |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1006763 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006764 | Fulton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1006765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006766 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006767 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1006768 | Newton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1006769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006770 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1006771 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1006772 | Lake |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1006773 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1006774 | St. Joseph | Hanson Professional Services, Inc. | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1006775 | Jasper |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1006776 | Jasper |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
RR
|  |  | 1006777 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 1006778 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1006779 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2011-05-11
|  |  | 1006780 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1006781 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1006782 |  | Eco Logic, LLC | Indiana Department of Transportation | 2011-04-13
|  |  | 1006783 |  |  | Indiana Department of Transportation | 2011-04-13
|  |  | 1006784 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1006785 | Allen |  | Indiana Department of Transportation | 2011-09-08 | CE
CN
|  |  | 1006786 | Hancock |  | Mccordsville | 2012-05-31 | CN
|  |  | 1006787 | Lake |  | Merrillville | 2020-11-10 | CE
CN
ROW
|  |  | 1006788 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1006789 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1006790 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1006791 | Switzerland |  | Switzerland County | 2012-11-15 | CE
CN
PE
|  |  | 1006792 |  |  | Indiana Department of Transportation | 2011-05-11
|  |  | 1172000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172001 | Elkhart |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1172002 | Steuben | ABt SRBI | Angola | 2012-03-07 | CE
CN
PE
|  |  | 1172003 | Grant | Chicago Title Insurance Company | Gas City | 2012-03-07 | CE
CN
PE
|  |  | 1172004 | Dekalb | Quantum Spatial, Inc. | Auburn | 2013-04-03 | CE
CN
PE
|  |  | 1172005 | Adams | Bidinfo | Decatur | 2012-03-07 | CE
CN
PE
|  |  | 1172006 | Dekalb | Mader Design, LLC | Waterloo | 2012-01-11 | CE
CN
PE
|  |  | 1172007 | Lake |  | Lake County | 2020-04-01 | CE
CN
ROW
|  |  | 1172008 | Vermillion |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1172009 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2015-09-02 | CE
CN
PE
ROW
|  |  | 1172010 | Union |  | Union County | -339679.2083 | PE
|  |  | 1172011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172013 |  |  | Indiana Department of Transportation | 2011-10-26
|  |  | 1172014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172015 |  |  | Indiana Department of Transportation | 2011-10-26
|  |  | 1172016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172018 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172022 | Greene |  | Indiana Department of Transportation | 2013-03-20 | CE
CN
|  |  | 1172023 | Greene |  | Indiana Department of Transportation | 2013-03-20 | CE
CN
|  |  | 1172024 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1172025 | Greene |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1172026 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172027 |  |  | Indiana Department of Transportation | 2013-03-20
|  |  | 1172028 |  |  | Indiana Department of Transportation | 2013-03-20
|  |  | 1172029 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1172030 | Greene |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1172031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172033 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1172034 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172035 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172038 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172039 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172040 | Greene |  | Indiana Department of Transportation | 2011-12-21 | CE
CN
|  |  | 1172041 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172042 | Greene |  | Indiana Department of Transportation | 2011-12-21 | CE
CN
|  |  | 1172043 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172044 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172045 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172046 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172047 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172048 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1172049 | Lawrence |  | Indiana Department of Transportation | 2011-04-13 | CE
UT
|  |  |  | Orange |  | Indiana Department of Transportation | 2011-04-13 | CE
UT
|  |  | 1172050 | Vermillion | Archaeology and Geomorphology Services | Clinton | -339679.2083 | PE
|  |  | 1172051 | Sullivan |  | Sullivan County | -339679.2083 | PE
|  |  | 1172052 | Cass |  | Cass County | 2012-05-02 | CE
CN
PE
|  |  | 1172053 | White | Fugro Roadware, Inc. | Monticello | 2015-09-02 | CE
CN
PE
|  |  | 1172054 | Carroll |  | Carroll County | 2012-05-02 | CE
CN
PE
|  |  | 1172057 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172058 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172059 | Monroe |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1172060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172061 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172062 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172063 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172064 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172065 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172069 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172070 | Monroe |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1172071 | Greene |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1172072 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172073 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172074 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172075 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172076 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172077 | Greene |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1172078 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 1172079 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172081 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172082 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172083 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172084 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172085 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172086 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172087 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172088 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172089 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172090 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172091 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172092 | Monroe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 1172093 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172094 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172095 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172096 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172097 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172098 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1172099 | Monroe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 1172100 | Monroe |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1172101 |  |  | Indiana Department of Transportation | 2012-10-11
|  |  | 1172102 |  |  | Indiana Department of Transportation | 2012-10-11
|  |  | 1172103 |  | Danch Harner and Associates, Inc. | Jasper | -339679.2083
|  |  | 1172104 |  |  | Indiana Department of Transportation | 2012-10-11
|  |  | 1172105 |  |  | Indiana Department of Transportation | 2012-10-11
|  |  | 1172106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172112 |  |  | Indiana Department of Transportation | 2012-10-11
|  |  | 1172113 |  |  | Indiana Department of Transportation | 2012-10-11
|  |  | 1172114 | Monroe |  | Indiana Department of Transportation | 2012-10-11 | CN
|  |  |  | Morgan |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1172115 | Monroe |  | Monroe County | 2013-07-10 | CE
CN
PE
|  |  | 1172116 |  |  | Lawrence | -339679.2083
|  |  | 1172117 | Franklin |  | Franklin | 2013-07-10 | PE
|  |  |  | Johnson |  | Franklin | 2013-07-10 | CE
CN
|  |  | 1172118 | Marion |  | Indianapolis | 2012-05-31 | PE
|  |  | 1172119 | Marion |  | Indianapolis | 2011-08-09 | CE
CN
|  |  | 1172120 | Marion |  | Indianapolis | 2011-08-09 | CE
CN
|  |  | 1172121 | Monroe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
ROW
|  |  | 1172122 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 1172123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172129 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172130 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1172131 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1172132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172133 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1172134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172135 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1172136 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172138 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172139 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172142 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172143 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172146 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172147 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1172148 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1172149 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172151 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172152 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1172153 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1172154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172156 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172158 | Hancock | CTLGroup | Indiana Department of Transportation | 2011-10-13 | CE
CN
|  |  | 1172159 | Hancock |  | Hancock County | 2012-09-04 | CN
|  |  | 1172160 | Fountain | AECON, Inc. | Attica | 2013-08-07 | CE
CN
PE
|  |  | 1172161 | Monroe |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
PE
ROW
UT
|  |  | 1172162 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1172163 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1172164 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172165 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172166 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1172167 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1172168 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1172169 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172170 | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172172 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172173 | Various |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1172174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172175 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1172176 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1172177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172179 | Various |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1172180 | Various |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1172181 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172182 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1172183 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1172184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172185 | Various |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1172186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172187 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172188 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172191 | Various |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1172192 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172193 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172194 | Various |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1172195 | Various |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
|  |  | 1172196 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172199 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172200 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172201 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172205 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172206 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172207 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1172208 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172211 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1172212 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172213 |  | ACMS Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172214 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172215 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172216 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172217 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172218 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1172219 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172221 | St. Joseph |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1172222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172223 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1172224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172226 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172227 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172228 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172229 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172230 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172231 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172235 | Jasper |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1172236 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | CN
PE
ROW
|  |  | 1172237 | Pulaski |  | Indiana Department of Transportation | 2020-03-04 | PE
ROW
|  |  | 1172238 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172239 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172240 | LaPorte |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1172241 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172242 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172243 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172244 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1172245 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
RR
|  |  | 1172246 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172247 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1172248 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172249 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1172250 | White |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1172251 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1172252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172254 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172255 | Newton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
ROW
|  |  | 1172256 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172257 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1172258 | Jasper |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1172259 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1172260 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1172261 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1172262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172263 | Jasper |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1172264 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172265 | Newton |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1172266 | Porter |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1172267 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1172269 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172270 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1172271 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1172272 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1172273 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172274 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172275 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172276 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172277 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172278 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172280 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172281 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172282 | White |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1172283 | Marshall |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1172284 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172285 | White |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1172286 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172287 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172288 | LaPorte |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
RR
|  |  | 1172289 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-08-06 | PE
|  |  | 1172290 |  | Hanson Professional Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172291 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172292 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172294 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172295 | Lake | Huff & Huff, Inc. | Indiana Department of Transportation | 2016-01-13 | CE
PE
|  |  |  | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1172296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172297 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172298 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172299 | Scott |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1172300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172302 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172305 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172308 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172309 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172312 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172313 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172315 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172317 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1172318 | Hendricks | AFRAM Group, Incorporated | Avon | 2012-07-11 | CE
CN
PE
|  |  | 1172319 |  |  | Avon | -339679.2083
|  |  | 1172320 | Hendricks | AFRAM Group, Incorporated | Avon | 2012-07-11 | CE
CN
PE
|  |  | 1172321 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2011-04-13
|  |  | 1172322 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1172323 | Jasper |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1172324 | Newton |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
|  |  | 1172325 |  | HDR Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172326 | Cass |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1172327 |  | Blood Hound, Inc. (former) | Indiana Department of Transportation | -339679.2083
|  |  | 1172328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172329 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1172330 | Jasper |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1172331 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1172332 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1172333 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172334 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1172335 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172336 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172337 | Lawrence | JCI Bridge Group, Inc. | Salem | 2011-11-16 | CE
CN
|  |  |  | Washington | JCI Bridge Group, Inc. | Salem | 2011-11-16 | CN
|  |  | 1172338 |  | Banning Engineering, P.C. | Crawfordsville | 2016-05-31
|  |  | 1172339 | Orange |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1172340 |  |  | Indiana Department of Transportation | 2012-01-11
|  |  | 1172341 | Clark |  | MPO - Louisville | 2012-05-31 | PE
|  |  | 1172342 |  |  | MPO - Louisville | 2013-05-31
|  |  | 1172343 |  |  | MPO - Louisville | 2014-05-31
|  |  | 1172344 |  |  | MPO - Louisville | -339679.2083
|  |  | 1172345 |  |  | Franklin | 2012-01-11
|  |  | 1172346 |  |  | MPO - Louisville | 2012-05-31
|  |  | 1172347 |  |  | Bloomington | 2012-04-18
|  |  | 1172348 | Steuben |  | Steuben County | -339679.2083 | PE
ROW
|  |  | 1172349 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172351 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172352 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172353 | Allen |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1172354 | Various |  | Indiana State Agencies | -339679.2083 | PE
|  |  | 1172355 | Pike |  | Pike County | 2012-12-12 | CE
CN
PE
|  |  | 1172356 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172357 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172359 | LaGrange | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1172360 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1172361 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172362 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1172363 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172364 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172365 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172366 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172367 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172368 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172369 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172371 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172373 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172374 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172375 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172376 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1172377 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172378 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172380 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1172381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172382 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172383 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172384 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172385 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172386 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172387 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172388 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172389 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1172390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172391 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172392 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172394 | Floyd |  | New Albany | 2016-01-13 | CE
CN
PE
|  |  | 1172395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172396 | Carroll |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1172397 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172398 | LaPorte |  | LaPorte County | -339679.2083 | CN
|  |  | 1172399 | LaPorte |  | LaPorte County | -339679.2083 | CN
|  |  | 1172400 | LaPorte |  | Michigan City | -339679.2083 | PE
|  |  | 1172401 | Lake |  | Hobart | -339679.2083 | PE
|  |  | 1172402 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172403 | Henry |  | Indiana Department of Transportation | 2011-05-11 | CE
CN
|  |  | 1172404 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172405 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172406 | Greene |  | Indiana Department of Transportation | 2011-11-30 | CE
CN
|  |  | 1172409 | Greene |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1172410 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1172411 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1172412 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172413 | Tippecanoe | ASA Engineering Consultants, Inc. | Battle Ground | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1172414 |  |  | Indiana Department of Transportation | 2010-04-29
|  |  | 1172415 | Pike | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2011-05-31 | PE
|  |  | 1172416 |  |  | MPO - Louisville | 2011-05-31
|  |  | 1172417 |  |  | MPO - Louisville | 2011-05-31
|  |  | 1172418 | Lake | Matt L. Nepote, MAI | Whiting | 2014-01-15 | CE
CN
RR
|  |  | 1172419 |  |  | Indiana Department of Transportation | 2010-08-06
|  |  | 1172420 | Tipton |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1172421 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172422 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | -339679.2083
|  |  | 1172423 |  |  | Indiana Department of Transportation | 2011-11-16
|  |  | 1172424 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1172425 | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172426 | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172427 | St. Joseph |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172428 | Lake | Baxter & Woodman, Inc. | Crown Point | 2015-12-09 | CE
CN
PE
ROW
|  |  | 1172429 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172430 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
PE
|  |  | 1172431 | Dekalb | Cheri K. Lewis Engineers | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 1172432 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1172433 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1172434 | Cass | Eco Logic, LLC | Logansport | 2015-12-09 | CE
CN
PE
ROW
|  |  | 1172435 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1172436 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1172437 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1172438 | Porter |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
|  |  | 1172439 | LaGrange |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1172440 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172441 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172442 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172443 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172444 |  |  | Federal Lands Highway | -339679.2083
|  |  | 1172445 | Lake |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1172446 | Lake |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1172447 | Lake |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1172448 | Vanderburgh | CGI | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 1172449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172450 | Marion |  | Speedway | 2012-05-02 | CE
CN
UT
|  |  | 1172451 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172452 | Daviess | Home Equity Appraisals | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  |  | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 1172453 | Monroe |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
ROW
|  |  | 1172454 |  |  | Fort Wayne | -339679.2083
|  |  | 1172457 |  |  | Indiana Department of Transportation | 2011-12-14
|  |  | 1172458 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2014-07-09 | CE
CN
PE
RR
|  |  | 1172459 | Marion |  | Indianapolis | 2014-09-10 | CE
CN
|  |  | 1172460 |  |  | Hendricks County | -339679.2083
|  |  | 1172461 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1172463 |  | I. T. Business Corporation | Posey County | -339679.2083
|  |  | 1172464 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2012-04-04
|  |  | 1172465 |  | CGI | Indiana Department of Transportation | 2012-04-04
|  |  | 1172466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172467 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172468 | Warrick |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172469 | Madison |  | Anderson | 2015-08-26 | PE
|  |  | 1172470 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2011-08-10 | CE
CN
|  |  | 1172471 | Various |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172472 | Randolph |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172473 | Howard |  | Kokomo | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1172474 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172475 | Henry |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1172476 | Henry |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1172477 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1172478 | Marion |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172479 | Various |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1172480 | Jennings |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1172481 | Franklin |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
ROW
|  |  | 1172482 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 1172483 | Hendricks |  | Avon | 2014-05-08 | CE
CN
PE
ROW
UT
|  |  | 1172484 | Hendricks | AFRAM Group, Incorporated | Avon | 2013-05-01 | CE
CN
PE
ROW
|  |  | 1172485 | Hancock |  | Hancock County | 2013-05-05 | CN
|  |  | 1172486 |  |  | West Harrison | 2016-05-31
|  |  | 1172487 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172488 | Jennings |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1172489 |  |  | Federal Lands Highway | -339679.2083
|  |  | 1172490 | Jennings |  | North Vernon | 2012-12-12 | CE
CN
PE
|  |  | 1172491 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172495 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172497 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
|  |  | 1172498 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172499 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172501 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172503 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172505 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172507 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172508 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172509 |  |  | Franklin | -339679.2083
|  |  | 1172510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172512 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172513 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172514 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172515 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172516 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172519 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172520 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172521 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172522 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172523 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172524 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172525 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172526 | Spencer |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1172527 |  |  | Indiana Department of Transportation | 2011-05-31
|  |  | 1172528 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1172529 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172530 | Greene | Bonar Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Sullivan | Bonar Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1172531 | Greene | Bonar Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Sullivan | Bonar Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1172532 | Greene | Bonar Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Sullivan | Bonar Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1172533 | Greene |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1172534 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1172535 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1172536 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172541 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172542 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172543 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172544 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172545 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172546 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172547 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172548 |  |  | MPO - Anderson | -339679.2083
|  |  | 1172549 |  |  | MPO - Kokomo | 2012-09-30
|  |  | 1172556 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1172557 |  |  | MPO - Kokomo | 2012-09-30
|  |  | 1172558 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1172559 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1172563 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172564 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172565 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172566 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172567 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172568 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172569 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172570 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172571 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172572 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172573 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172574 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172575 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172576 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172577 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172578 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172579 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172580 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172581 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172582 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172583 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172584 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172585 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172586 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172587 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172588 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172589 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172590 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172591 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172592 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172593 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172594 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172595 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172596 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172597 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172598 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172599 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172600 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172601 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1172602 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172603 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172604 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1172605 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172612 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172613 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172614 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1172615 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172616 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172617 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172618 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172619 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172620 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1172621 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172622 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172623 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172624 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172625 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1172626 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172627 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172628 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1172629 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1172630 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1172631 |  |  | MPO - Terre Haute | 2011-06-20
|  |  | 1172632 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1172633 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1172634 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1172635 |  |  | MPO - Terre Haute | 2011-06-20
|  |  | 1172636 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1172637 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172638 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172639 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172640 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172641 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172642 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172643 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172644 |  |  | MPO - Evansville | -339679.2083
|  |  | 1172645 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172646 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172647 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172648 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172649 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172650 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172651 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172652 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172653 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172654 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172655 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172656 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172657 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172658 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172659 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172660 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172662 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172664 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172665 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172666 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172667 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172668 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172669 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172670 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172671 | Morgan |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1172672 | Morgan |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1172673 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172674 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172675 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172676 |  |  | MPO - Lafayette | 2011-06-20
|  |  | 1172677 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172678 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172679 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172680 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172681 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172683 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172684 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172685 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172686 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172687 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172688 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172689 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172690 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172691 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172692 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172693 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172694 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172695 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172696 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172697 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172698 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172699 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172700 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172701 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172702 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1172703 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172704 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172705 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172706 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172707 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172708 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172709 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1172710 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1172711 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172712 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172713 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172714 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172715 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172716 |  |  | MPO - Columbus | -339679.2083
|  |  | 1172725 |  |  | MPO - Columbus | -339679.2083
|  |  | 1172726 |  |  | MPO - Columbus | -339679.2083
|  |  | 1172727 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1172728 |  |  | MPO - Columbus | -339679.2083
|  |  | 1172729 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1172730 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172731 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172732 |  |  | MPO - Muncie | 2011-06-20
|  |  | 1172733 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1172734 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172735 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172736 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172737 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172738 |  |  | MPO - Muncie | 2011-06-20
|  |  | 1172739 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1172740 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1172741 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172742 |  |  | MPO - Muncie | 2011-06-20
|  |  | 1172743 |  |  | MPO - Muncie | 2011-06-20
|  |  | 1172744 |  |  | MPO - Muncie | -339679.2083
|  |  | 1172745 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1172746 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1172747 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1172748 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172749 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172750 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172751 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172752 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172753 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172754 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172755 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172756 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172757 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172758 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1172759 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172760 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172761 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172762 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172763 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1172764 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172765 | Knox | AV Consulting Engineers, Inc. | Bicknell | 2014-11-13 | CE
CN
PE
|  |  | 1172766 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172767 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172768 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172769 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172770 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172771 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172772 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172773 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172774 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172775 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172776 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1172777 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172778 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172779 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1172780 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1172781 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172782 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172783 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172784 |  |  | South Bend Transit | -339679.2083
|  |  | 1172785 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172786 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172787 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172788 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172789 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172790 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172791 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172792 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172793 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172794 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172795 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172796 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172797 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172798 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172799 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172800 |  |  | South Bend Transit | -339679.2083
|  |  | 1172801 |  |  | South Bend Transit | -339679.2083
|  |  | 1172802 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172803 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172804 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172805 |  |  | South Bend Transit | -339679.2083
|  |  | 1172806 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172807 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172808 | Clay | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2011-08-04 | CE
CN
|  |  |  | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2011-08-04 | CE
CN
|  |  |  | Morgan | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2011-08-04 | CE
CN
|  |  |  | Putnam | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2011-08-04 | CN
|  |  | 1172809 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172810 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172811 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172812 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172813 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172814 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172815 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172816 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172817 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172818 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1172819 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172820 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172821 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172822 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172823 |  |  | MPO - South Bend / Elkhart | 2011-06-20
|  |  | 1172824 |  |  | South Bend Transit | -339679.2083
|  |  | 1172825 |  |  | South Bend Transit | -339679.2083
|  |  | 1172826 |  |  | South Bend Transit | -339679.2083
|  |  | 1172827 |  |  | Alexandria | -339679.2083
|  |  | 1172829 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172830 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172831 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172832 |  |  | MPO - Northwest | 2011-06-20
|  |  | 1172833 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1172834 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172835 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172836 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172837 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172838 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172839 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172840 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172841 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172842 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172843 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172844 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172845 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172846 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172847 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172848 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172849 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172850 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172851 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172852 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172853 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172854 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172855 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172856 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172857 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172858 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172859 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172860 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172861 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172862 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172863 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172864 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172865 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172866 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172867 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172868 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172869 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172870 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172871 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172872 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172873 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172874 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172875 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172876 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172877 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172878 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172879 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172880 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172881 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172882 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172883 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172884 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172885 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172886 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172887 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172888 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172889 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172890 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172891 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172892 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172893 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172894 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172895 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172896 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172897 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172898 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172899 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172900 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172901 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172902 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172903 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172904 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172905 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172906 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172907 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172908 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172909 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172910 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172911 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172912 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172913 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172914 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172915 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172916 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172917 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172918 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1172919 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1172920 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1172921 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1172922 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1172923 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172924 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1172925 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1172926 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172927 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172928 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172929 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172930 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172931 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172932 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172933 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172934 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172935 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172936 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172937 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172938 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172939 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172940 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172941 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172942 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172943 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1172944 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1172945 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172946 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1172947 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1172948 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1172949 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172950 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172951 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172952 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172953 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1172954 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14
|  |  | 1172955 |  |  | Michigan City Transit | -339679.2083
|  |  | 1172956 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172957 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172958 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172959 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1172960 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172961 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172962 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172963 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172964 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172965 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172966 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172967 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172968 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172969 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172970 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172971 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172972 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172973 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172974 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172975 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172976 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172977 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172978 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1172979 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1172980 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1172981 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172982 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172983 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172984 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172985 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172986 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172987 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172988 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172989 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172990 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1172991 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172992 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172993 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172994 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172995 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172996 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172997 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1172998 |  |  | MPO - Northwest | -339679.2083
|  |  | 1172999 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173000 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173001 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173002 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173003 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173004 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173005 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173006 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173007 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173008 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173009 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173010 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173011 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173012 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173013 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173014 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173015 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173016 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173017 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173018 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173019 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173020 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173021 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173022 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1173023 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1173024 |  |  | MPO - Northwest | 2011-06-21
|  |  | 1173025 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173026 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173027 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173028 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173029 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173030 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173031 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2011-10-13
|  |  | 1173032 | Allen |  | Allen County | 2013-02-06 | CE
CN
PE
ROW
UT
|  |  | 1173033 | Jackson |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173034 | Clinton |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173035 | Clay | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173036 | Jasper |  | Indiana Department of Transportation | 2014-05-31 | PE
RR
|  |  | 1173037 | Boone |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1173038 | White |  | Indiana Department of Transportation | 2013-11-06 | PE
RR
|  |  | 1173039 | White |  | Indiana Department of Transportation | 2014-05-31 | PE
RR
|  |  | 1173040 | White |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
|  |  | 1173041 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2011-08-17 | CE
CN
|  |  | 1173042 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173043 | Hendricks |  | Hendricks County | 2014-03-05 | CE
CN
|  |  | 1173044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173047 | Marion |  | Indianapolis | 2014-02-05 | CE
CN
|  |  | 1173048 | Marion |  | Indianapolis | 2015-01-14 | CE
CN
|  |  | 1173049 | Marion |  | Indianapolis | 2013-08-07 | CE
CN
|  |  | 1173050 | Marion |  | Indianapolis | 2013-07-10 | CE
CN
|  |  | 1173051 | Marion |  | Indianapolis | 2014-05-08 | CE
CN
|  |  | 1173052 |  |  | Indiana Department of Transportation | 2012-05-31
|  |  | 1173053 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1173054 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1173055 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173056 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173057 | Allen | D & D Consulting Services, Inc. | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173058 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1173059 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1173060 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 1173061 | Marshall |  | Indiana Department of Transportation | 2012-04-18 | CE
CN
|  |  | 1173062 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173063 | Marion |  | Indianapolis | 2013-11-06 | CE
CN
|  |  | 1173064 | Marion |  | Indianapolis | 2014-05-21 | CE
CN
RR
|  |  | 1173065 | Marion |  | Indianapolis | 2015-08-05 | CE
CN
|  |  | 1173066 | Monroe |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1173067 | Greene |  | Indiana Department of Transportation | 2011-12-21 | UT
|  |  | 1173068 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1173069 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173070 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173071 | Floyd |  | Indiana Department of Transportation | 2011-08-04 | CE
CN
[6 empty] | Indiana Department of Transportation | 2011-08-04
|  |  | 1173072 | Jasper |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1173073 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2012-02-08 | CE
CN
|  |  | 1173074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173075 | Clark |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1173076 | Monroe |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173077 | Elkhart |  | Elkhart County | 2014-03-05 | CE
CN
|  |  | 1173078 | Marion |  | Speedway | 2014-04-09 | CN
|  |  | 1173079 | Hamilton |  | Westfield | 2015-08-05 | CE
CN
|  |  | 1173080 |  |  | Pendleton | -339679.2083
|  |  | 1173081 | Marion |  | Indianapolis | 2015-02-04 | CE
CN
PE
|  |  | 1173082 | Marion |  | Indianapolis | 2015-02-04 | CE
CN
PE
|  |  | 1173083 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 1173084 | Marion |  | Indianapolis | 2015-01-14 | CE
CN
PE
UT
|  |  | 1173085 | Jennings |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173086 | Jennings |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
RR
|  |  | 1173087 | Jennings |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173088 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173090 | Morgan | DCD Consulting LLC | Morgan County | 2015-03-04 | CE
CN
|  |  | 1173091 | Clay |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1173092 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173093 | Hamilton |  | Hamilton County | 2016-02-03 | CE
CN
|  |  | 1173094 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173095 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173096 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173097 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173098 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173099 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173100 | Hamilton |  | Westfield | 2015-02-04 | CE
CN
PE
ROW
UT
|  |  |  | Various |  | Westfield | 2015-02-04 | CN
|  |  | 1173101 |  |  | Southport | -339679.2083
|  |  | 1173102 | Johnson |  | Johnson County | 2014-03-05 | CE
CN
|  |  | 1173103 | Johnson | Martin Riley, Inc. | Whiteland | 2015-09-02 | CE
CN
PE
ROW
|  |  | 1173104 |  |  | Westfield | -339679.2083
|  |  | 1173105 |  |  | Homecroft | -339679.2083
|  |  | 1173106 | Marion |  | Lawrence | -339679.2083 | PE
|  |  | 1173107 | Hamilton |  | Hamilton County | 2012-03-07 | CE
CN
PE
|  |  | 1173108 |  |  | Bloomington | -339679.2083
|  |  | 1173109 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173110 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1173111 | Marion |  | Indianapolis | 2014-07-09 | CE
CN
PE
|  |  | 1173112 |  |  | Indianapolis | -339679.2083
|  |  | 1173113 |  |  | Indianapolis | -339679.2083
|  |  | 1173114 |  |  | Indianapolis | -339679.2083
|  |  | 1173115 | Marion | DCD Consulting LLC | Indianapolis | 2014-07-09 | CE
CN
PE
|  |  | 1173116 | Marion | DCD Consulting LLC | Indianapolis | 2014-07-09 | CE
CN
PE
|  |  | 1173117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173118 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173119 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173121 | Marion | DCD Consulting LLC | Lawrence | 2016-02-03 | CE
CN
PE
|  |  | 1173122 | Johnson |  | Johnson County | 2017-12-13 | CE
CN
|  |  | 1173123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173124 |  | GS-IN P.C. | Indiana Department of Transportation | 2012-05-31
|  |  | 1173125 |  |  | Indiana Department of Transportation | 2011-12-14
|  |  | 1173126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173127 | Clay |  | Brazil | 2013-09-11 | CE
CN
PE
|  |  | 1173128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173129 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173130 | Clinton | Carters Appraisal Service | Frankfort | 2016-02-03 | CE
CN
PE
ROW
UT
|  |  | 1173131 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2013-12-05 | RR
|  |  | 1173132 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2012-10-04 | RR
|  |  | 1173133 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2012-10-26 | RR
|  |  | 1173134 | Shelby |  | Indiana Department of Transportation | 2012-10-04 | RR
|  |  | 1173135 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173136 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173137 |  |  | Benton County | -339679.2083
|  |  | 1173138 | Marion | ERES International, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173139 | Montgomery |  | Montgomery County | 2016-05-05 | CE
CN
PE
ROW
|  |  | 1173140 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2013-05-31 | RR
|  |  | 1173141 | Grant | CGS Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173142 | Delaware | Burgess & Niple, Inc. | Indiana Department of Transportation | 2013-09-25 | RR
|  |  | 1173143 | Clinton |  | Clinton County | 2014-10-08 | CE
CN
PE
ROW
|  |  | 1173144 | Delaware | Burgess & Niple, Inc. | Indiana Department of Transportation | 2013-09-24 | RR
|  |  | 1173145 | Clinton |  | Clinton County | 2013-04-03 | CE
CN
PE
|  |  | 1173146 | Putnam |  | Putnam County | 2014-07-09 | CE
CN
PE
ROW
|  |  | 1173147 |  |  | Putnam County | -339679.2083
|  |  | 1173148 | Adams | Bidinfo | Indiana Department of Transportation | 2016-09-14 | CE
CN
ROW
|  |  | 1173149 | St. Joseph |  | Indiana Department of Transportation | 2012-05-11 | CE
CN
|  |  | 1173150 | Madison |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
RR
|  |  | 1173151 | Warren |  | Warren County | -339679.2083 | PE
|  |  | 1173152 |  | DCD Consulting LLC | Avon | -339679.2083
|  |  | 1173153 | Hendricks | DCD Consulting LLC | Avon | 2016-12-14 | CE
CN
|  |  | 1173154 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1173155 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1173156 |  |  | Indiana Department of Transportation | 2010-08-27
|  |  | 1173157 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173158 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173159 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173160 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173161 | Hamilton | CPS Acquisitions, LLC | MPO - Indianapolis | 2013-01-18 | CE
CN
UT
|  |  |  | Marion | CPS Acquisitions, LLC | MPO - Indianapolis | 2013-01-18 | CE
CN
PE
|  |  | 1173162 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2020-09-02 | CE
CN
PE
ROW
|  |  | 1173163 | Marion |  | Indianapolis | 2013-03-21 | CE
CN
|  |  | 1173164 |  |  | Indianapolis | -339679.2083
|  |  | 1173165 | Marion | DCD Consulting LLC | Indianapolis | 2014-07-09 | CE
CN
PE
|  |  | 1173166 | Marion |  | Indianapolis | 2011-08-09 | CE
CN
|  |  | 1173167 | Marion |  | Indianapolis | 2013-05-24 | CE
CN
|  |  | 1173168 | Marion |  | Indianapolis | 2012-04-19 | CE
CN
|  |  | 1173169 | Hendricks | All About Pavements, Inc. | Brownsburg | 2013-11-06 | CE
CN
PE
|  |  | 1173170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173171 | Randolph |  | Winchester | 2013-11-06 | CE
CN
PE
|  |  | 1173172 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173173 | Jay |  | Portland | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1173174 | Wayne |  | Richmond | 2016-09-14 | CE
CN
PE
ROW
UT
|  |  | 1173175 | Sullivan |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
|  |  | 1173176 | Owen |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173177 |  |  | New Castle | -339679.2083
|  |  | 1173178 |  |  | Shelbyville | -339679.2083
|  |  | 1173179 | Henry |  | Henry County | 2017-10-12 | CE
CN
PE
ROW
|  |  | 1173180 | Putnam |  | Putnam County | 2014-05-08 | CE
CN
PE
ROW
|  |  | 1173181 |  |  | Indiana Department of Transportation | 2012-04-04
|  |  | 1173182 | Crawford | Aarcher, Inc. | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  |  | Dubois | Aarcher, Inc. | Indiana Department of Transportation | 2011-11-16 | CE
CN
|  |  | 1173183 | Vanderburgh |  | Indiana Department of Transportation | 2011-12-14 | CE
CN
RR
|  |  | 1173184 | Posey | GRL Engineers, Inc. | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173185 | Floyd |  | New Albany | 2014-11-17 | PE
|  |  | 1173186 | Vanderburgh |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173187 | Clark |  | Clarksville | 2016-02-03 | CE
CN
PE
|  |  | 1173188 | Floyd |  | New Albany | 2016-01-13 | CE
CN
PE
|  |  | 1173189 | Posey | I. T. Business Corporation | Indiana Department of Transportation | 2012-01-11 | CE
CN
RR
|  |  | 1173190 |  |  | Southport | -339679.2083
|  |  | 1173191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173192 | Starke | H.R. Gray | North Judson | 2015-01-26 | CN
|  |  | 1173193 | Hamilton |  | Westfield | 2017-11-15 | CN
ROW
|  |  | 1173194 | Hamilton |  | Fishers | 2015-07-08 | CE
CN
PE
|  |  | 1173195 |  | Klug Engineering, Inc. | Sullivan County | -339679.2083
|  |  | 1173199 | Sullivan | Klug Engineering, Inc. | Sullivan County | 2014-07-09 | CE
CN
PE
ROW
|  |  | 1173200 |  |  | Indiana Department of Transportation | 2011-07-08
|  |  | 1173201 | Greene |  | Greene County | 2014-11-13 | CE
CN
PE
ROW
RR
UT
|  |  | 1173202 | Greene |  | Greene County | 2015-09-02 | CE
CN
PE
ROW
RR
|  |  | 1173203 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173204 | Grant | Level 5 Engineering, LLC | Indiana Department of Transportation | 2012-03-07 | CE
CN
RR
|  |  | 1173205 | St. Joseph | HDR Engineering, Inc. | North Liberty | 2013-08-07 | CE
CN
PE
|  |  | 1173206 | White | Meridian Title Corporation | Wolcott | 2014-07-09 | CE
CN
PE
|  |  | 1173207 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1173208 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1173209 | Bartholomew |  | Columbus | 2017-02-08 | CE
CN
|  |  | 1173210 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2015-10-07 | CE
CN
PE
|  |  |  | Various | Associated Right-of-Way Services, Inc. | Columbus | 2015-10-07 | CN
|  |  | 1173211 | Daviess | AMEC E&I, Inc. | Washington | 2014-01-15 | CE
CN
PE
ROW
|  |  | 1173212 | Randolph |  | Randolph County | -339679.2083 | PE
|  |  | 1173213 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173214 | Allen |  | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1173215 | Wabash |  | Indiana Department of Transportation | 2012-02-21 | RR
|  |  | 1173216 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2014-05-30 | RR
|  |  | 1173217 | Steuben | ABt SRBI | Angola | 2013-12-11 | CE
CN
|  |  | 1173218 | Adams |  | Adams County | 2019-09-11 | CE
CN
PE
ROW
|  |  | 1173219 | Allen | CTL Engineering of Indiana, Inc. | Indiana State Agencies | 2017-02-08 | CE
CN
PE
|  |  | 1173220 | Steuben | ABt SRBI | Angola | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1173221 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173222 | Marion |  | Indiana Department of Natural Resources | 2016-05-31 | CN
PE
ROW
[6 empty] | Indiana Department of Natural Resources | 2016-05-31
|  |  | 1173223 | Adams | Bidinfo | Decatur | 2014-11-13 | CE
CN
PE
ROW
|  |  | 1173224 | Grant | Chicago Title Insurance Company | Gas City | 2016-01-13 | CE
CN
PE
ROW
|  |  | 1173225 | Grant | ERES International, Inc. | Marion | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1173226 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173227 | Johnson |  | Greenwood | 2014-01-15 | CE
CN
PE
|  |  | 1173228 |  |  | Muncie | -339679.2083
|  |  | 1173229 | Delaware |  | Muncie | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1173230 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Natural Resources | 2012-05-31 | PE
|  |  |  | Various | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Natural Resources | 2012-05-31 | CN
PE
|  |  | 1173231 | Various |  | Indiana Department of Natural Resources | 2012-01-19 | CN
PE
|  |  | 1173232 | Various |  | Indiana Department of Natural Resources | 2012-01-19 | CN
|  |  | 1173233 | Marion |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 1173234 | Delaware |  | Indiana Department of Natural Resources | 2015-07-27 | CN
PE
ROW
|  |  | 1173235 | Fulton |  | Indiana Department of Natural Resources | 2013-05-31 | CN
PE
ROW
|  |  | 1173236 |  |  | Indiana Department of Natural Resources | 2012-05-31
|  |  | 1173237 |  |  | Indiana Department of Natural Resources | 2013-05-31
|  |  | 1173238 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173239 | Parke |  | Indiana Department of Natural Resources | 2014-08-22 | CN
PE
ROW
|  |  | 1173240 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1173241 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1173242 | Dekalb |  | Dekalb County | -339679.2083 | PE
|  |  | 1173243 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington County | 2016-04-06 | CE
CN
PE
ROW
|  |  | 1173244 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173245 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173246 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173247 |  |  | South Bend | -339679.2083
|  |  | 1173248 | St. Joseph |  | South Bend | 2012-03-07 | CE
CN
|  |  | 1173249 | Morgan |  | Morgan County | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1173250 | Allen |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
ROW
UT
|  |  | 1173251 |  |  | Indiana Department of Transportation | 2011-10-13
|  |  | 1173252 | Putnam | Clayton L. Roots | Greencastle | 2012-05-02 | CE
CN
|  |  | 1173253 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1173254 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173255 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173257 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173258 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1173261 | Ripley |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
|  |  | 1173262 | Dearborn |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
PE
|  |  | 1173263 | Jefferson | Engineering Resources, Inc. | Madison | 2013-12-11 | CE
CN
|  |  | 1173264 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173265 | Washington |  | Washington County | 2020-07-08 | CE
CN
PE
|  |  | 1173266 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173267 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173269 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173271 | St. Joseph |  | St. Joseph County | -339679.2083 | PE
|  |  | 1173272 | Perry |  | Perry County | 2013-08-07 | CE
CN
PE
|  |  | 1173273 | Perry |  | Perry County | 2011-11-02 | CE
CN
PE
|  |  | 1173274 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 1173275 | Daviess |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173276 | Pike |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173277 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 1173278 |  |  | Indiana Department of Transportation | 2011-02-11
|  |  | 1173279 | Delaware |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
RR
|  |  | 1173280 | Marshall |  | Marshall County | 2014-02-05 | CE
CN
|  |  | 1173281 |  |  | Cumberland | -339679.2083
|  |  | 1173282 |  |  | Martin County | -339679.2083
|  |  | 1173283 | Orange |  | West Baden Springs | -339679.2083 | CN
|  |  | 1173284 |  |  | Indiana Department of Transportation | 2011-09-08
|  |  | 1173285 |  |  | Indiana Department of Transportation | 2012-09-12
|  |  | 1173286 | Spencer |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1173287 | Hendricks | AFRAM Group, Incorporated | Avon | 2015-02-04 | CE
CN
PE
|  |  | 1173288 | Boone |  | Whitestown | 2014-04-02 | CE
CN
PE
|  |  | 1173289 | Spencer |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1173290 | Daviess |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
ROW
UT
|  |  | 1173291 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173292 |  |  | Indiana Department of Transportation | 2012-04-04
|  |  | 1173293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173294 |  | ASC Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173295 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1173296 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1173297 | Spencer | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173298 | Marion |  | Indianapolis | 2014-02-05 | CE
CN
|  |  | 1173299 | Marion | DCD Consulting LLC | Indianapolis | 2012-12-12 | CE
CN
|  |  | 1173300 | Marion |  | Indianapolis | 2013-08-07 | CE
CN
|  |  | 1173301 |  |  | Indiana Department of Transportation | 2011-11-02
|  |  | 1173302 | Marion |  | Indianapolis | 2013-04-03 | CE
CN
|  |  | 1173303 | Marion |  | Indianapolis | 2014-11-13 | CE
CN
|  |  | 1173304 |  |  | Lafayette | -339679.2083
|  |  | 1173305 |  |  | Lafayette | -339679.2083
|  |  | 1173306 |  |  | Indianapolis | -339679.2083
|  |  | 1173307 |  |  | South Bend | -339679.2083
|  |  | 1173308 | Dearborn |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  |  | Ohio |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173309 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2013-11-06 | CE
CN
PE
|  |  | 1173310 | Dearborn |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
PE
|  |  | 1173311 | Dearborn |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
PE
ROW
|  |  | 1173312 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173313 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173314 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1173315 | Ripley |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1173316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173317 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173319 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173321 | Ohio |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1173322 |  |  | Lawrence | -339679.2083
|  |  | 1173323 |  |  | Lawrence | -339679.2083
|  |  | 1173324 |  |  | Allen County | 2014-05-07
|  |  | 1173325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173326 | Monroe |  | Monroe County | 2015-11-18 | CE
CN
PE
ROW
|  |  | 1173327 | Parke |  | Parke County | -339679.2083 | PE
|  |  |  | Various |  | Parke County | -339679.2083 | PE
|  |  | 1173328 | Crawford |  | Crawford County | -339679.2083 | PE
|  |  |  | Various |  | Crawford County | -339679.2083 | PE
|  |  | 1173329 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173330 |  |  | Indiana Department of Transportation | 2011-12-14
|  |  | 1173331 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2012-10-11 | CE
CN
RR
|  |  | 1173332 | Jennings |  | North Vernon | 2016-01-13 | CE
CN
PE
ROW
|  |  | 1173333 | Cass | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173334 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  |  | Porter | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173335 | LaPorte |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173336 | Crawford |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173337 |  |  | Fayette County | -339679.2083
|  |  | 1173338 |  |  | Randolph County | -339679.2083
|  |  | 1173339 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173340 |  | CPS Acquisitions, LLC | MPO - Indianapolis | -339679.2083
|  |  | 1173341 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1173342 | Franklin |  | Indiana Department of Transportation | 2011-11-30 | CE
CN
|  |  | 1173343 | Lawrence |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1173344 | Lawrence |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1173345 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173346 | Spencer | JJR, LLC | Santa Claus | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1173347 | Clark |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1173348 | Jackson |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 1173349 | Jackson |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
PE
|  |  | 1173350 | Switzerland |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1173351 | Pike |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1173352 | Howard |  | Indiana Department of Transportation | 2012-05-04 | CE
CN
|  |  | 1173353 | Howard |  | Indiana Department of Transportation | 2012-05-04 | CE
CN
|  |  | 1173354 | Dubois |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1173355 | Warrick |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1173356 | Orange |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
|  |  | 1173357 | Cass |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1173358 |  |  | Clarksville | -339679.2083
|  |  | 1173359 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 1173360 |  |  | Indiana Department of Transportation | 2012-12-19
|  |  | 1173361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173362 | Henry | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | 2015-02-04 | CE
CN
RR
|  |  | 1173363 | Gibson | Harvard Title Searching | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173364 |  |  | Lafayette | -339679.2083
|  |  | 1173365 |  |  | Lafayette | -339679.2083
|  |  | 1173366 |  |  | East Chicago | -339679.2083
|  |  | 1173367 |  |  | East Chicago | -339679.2083
|  |  | 1173368 |  |  | East Chicago | -339679.2083
|  |  | 1173369 |  |  | East Chicago | -339679.2083
|  |  | 1173370 |  |  | Michigan City | -339679.2083
|  |  | 1173371 |  |  | Michigan City | -339679.2083
|  |  | 1173372 |  | Dynasty Group, Inc. | Dearborn County | -339679.2083
|  |  | 1173373 | Clark |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1173374 | Jennings |  | Indiana Department of Transportation | 2015-05-08 | CE
CN
PE
ROW
RR
UT
|  |  | 1173375 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173376 | Montgomery |  | Montgomery County | 2015-07-08 | CE
CN
PE
|  |  | 1173377 | Montgomery |  | Montgomery County | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1173378 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1173379 |  |  | Indiana Department of Transportation | 2011-12-21
|  |  | 1173380 | Montgomery |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1173381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173382 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1173383 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1173384 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173386 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1173387 | Wayne |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1173388 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173389 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 1173390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173391 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1173392 |  |  | Fountain County | -339679.2083
|  |  | 1173393 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1173394 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173395 | Clay | Advanced Appraisals, LLC | Brazil | -339679.2083 | PE
|  |  | 1173396 | Clay | Advanced Appraisals, LLC | Brazil | 2015-08-05 | CE
CN
PE
|  |  | 1173397 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173398 | Floyd |  | Indiana Department of Transportation | 2011-10-18 | CE
CN
PE
|  |  | 1173399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173400 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 1173401 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173402 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1173403 | Jennings |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
UT
|  |  | 1173404 | Jennings |  | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173405 | Tipton |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
UT
|  |  | 1173406 | Jennings |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
|  |  | 1173407 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1173408 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173409 | Various |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1173410 | Various |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1173411 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173412 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173413 | Hamilton |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173414 | Various |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1173415 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173416 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1173417 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173418 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173419 | Newton |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1173420 | Marshall |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1173421 | Porter |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1173422 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1173423 | Starke |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1173424 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2013-10-09 | CE
CN
RR
|  |  | 1173425 | Lake |  | Chesterton | 2014-07-09 | CE
CN
RR
|  |  | 1173426 | Lake |  | Crown Point | 2015-07-08 | CE
CN
|  |  | 1173427 |  |  | Crown Point | -339679.2083
|  |  | 1173428 | Lake |  | Hammond | 2014-05-08 | CE
CN
|  |  | 1173429 | Lake |  | Lake Station | 2019-02-06 | PE
|  |  | 1173430 | Porter | Huff & Huff, Inc. | Portage | 2022-05-31 | PE
|  |  | 1173431 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173432 | Porter |  | Porter County | 2015-01-14 | CE
CN
|  |  | 1173433 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173434 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173435 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173436 |  |  | Jennings County | -339679.2083
|  |  | 1173437 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173438 | Various |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173439 | Various |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1173440 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1173441 | Jackson |  | Indiana Department of Transportation | 2014-05-08 | CN
|  |  |  | Various |  | Indiana Department of Transportation | 2014-05-08 | CE
|  |  | 1173442 | Jasper |  | Jasper County | -339679.2083 | PE
|  |  | 1173443 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173444 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173445 |  |  | Knox | -339679.2083
|  |  | 1173446 | Fulton | InfoTech | Rochester | -339679.2083 | PE
|  |  | 1173447 |  |  | Starke County | -339679.2083
|  |  | 1173448 | Lawrence | ASA Land Surveying | Bedford | -339679.2083 | PE
|  |  | 1173449 | Knox | Louis Joyner, Architect | Vincennes | -339679.2083 | PE
|  |  | 1173450 | Knox |  | Knox County | -339679.2083 | PE
|  |  | 1173451 | Lawrence |  | Lawrence County | -339679.2083 | PE
|  |  | 1173452 | Clinton |  | Clinton County | -339679.2083 | PE
|  |  | 1173453 | Rush |  | Rush County | -339679.2083 | PE
|  |  | 1173454 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173455 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1173456 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173457 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173458 | Ripley |  | Ripley County | -339679.2083 | PE
|  |  | 1173459 | Jefferson |  | Madison | 2013-04-03 | PE
|  |  | 1173460 | Hamilton |  | Hamilton County | 2015-07-08 | CE
CN
|  |  |  | Marion |  | Hamilton County | 2015-07-08 | CN
ROW
|  |  | 1173461 |  |  | Plainfield | 2011-09-25
|  |  | 1173462 | Various |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1173463 | Decatur |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1173464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173466 | Sullivan | Klug Engineering, Inc. | Sullivan | -339679.2083 | PE
|  |  | 1173467 | Daviess | AMEC E&I, Inc. | Washington | 2014-12-10 | CE
CN
PE
|  |  | 1173468 | Hamilton |  | Westfield | 2015-01-14 | CE
CN
|  |  | 1173469 | Marion |  | Indianapolis | 2012-04-23 | PE
|  |  | 1173470 | Hamilton |  | Noblesville | 2013-07-10 | CE
CN
UT
|  |  | 1173471 |  |  | Indianapolis | -339679.2083
|  |  | 1173472 | LaPorte |  | LaPorte County | 2014-05-08 | CE
CN
|  |  | 1173473 | Hamilton |  | Fishers | 2016-10-05 | CE
CN
|  |  | 1173474 | Hamilton |  | Fishers | 2015-07-08 | CE
CN
|  |  | 1173475 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173476 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173477 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173478 | St. Joseph |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1173479 |  |  | Indianapolis | -339679.2083
|  |  | 1173480 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2012-02-08
|  |  | 1173481 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173482 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1173483 | Dekalb |  | Dekalb County | -339679.2083 | PE
|  |  | 1173484 |  |  | Adams County | -339679.2083
|  |  | 1173485 | Wells | Accidental Discoveries, LLC | Bluffton | -339679.2083 | PE
|  |  | 1173486 | Fayette |  | Fayette County | -339679.2083 | PE
|  |  | 1173487 | Whitley |  | Churubusco | -339679.2083 | PE
|  |  | 1173488 | Fayette |  | Connersville | -339679.2083 | PE
|  |  | 1173489 | Tipton |  | Tipton County | -339679.2083 | PE
|  |  | 1173490 | Randolph |  | Union City | -339679.2083 | PE
|  |  | 1173491 |  |  | Jeffersonville | -339679.2083
|  |  | 1173492 |  |  | Indiana Department of Transportation | 2012-09-12
|  |  | 1173493 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington | -339679.2083 | PE
|  |  | 1173494 | Blackford | Fusion by Design, Inc. | Montpelier | -339679.2083 | PE
|  |  | 1173495 | Marion |  | Indianapolis | 2013-10-07 | PE
|  |  | 1173496 | Various |  | Connersville | 2014-02-27 | PE
|  |  | 1173497 | Huntington |  | Huntington County | -339679.2083 | PE
|  |  | 1173498 | Dekalb |  | LaGrange County | -339679.2083 | CN
|  |  | 1173499 |  |  | Miami County | -339679.2083
|  |  | 1173500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173501 | Hamilton | CPS Acquisitions, LLC | MPO - Indianapolis | 2013-01-18 | CE
CN
|  |  |  | Marion | CPS Acquisitions, LLC | MPO - Indianapolis | 2013-01-18 | CE
CN
|  |  | 1173502 | Pike |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
ROW
|  |  | 1173503 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1173504 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1173505 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1173506 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 1173507 |  |  | Indiana Department of Transportation | 2013-09-11
|  |  | 1173508 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 1173509 | Blackford | Continental Mapping Consultants, LLC | Hartford City | -339679.2083 | CN
|  |  | 1173510 | Delaware | Burgess & Niple, Inc. | Eaton | 2017-01-19 | CE
CN
PE
|  |  | 1173511 | Randolph |  | Winchester | -339679.2083 | PE
|  |  | 1173512 |  |  | Randolph County | -339679.2083
|  |  | 1173513 | Marshall |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  |  | St. Joseph |  | Indiana Department of Transportation | 2012-01-11 | CE
CN
|  |  | 1173514 |  | Blood Hound, Inc. (former) | Indiana Department of Transportation | -339679.2083
|  |  | 1173515 |  |  | Franklin County | -339679.2083
|  |  | 1173516 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173518 | Greene |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  |  | Monroe |  | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173519 | Henry |  | Henry County | -339679.2083 | PE
|  |  | 1173520 | Huntington | ABNA of Illinois | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173521 | Wayne |  | Centerville | -339679.2083 | PE
|  |  | 1173522 | Marion |  | Speedway | 2013-09-11 | CE
CN
ROW
UT
|  |  | 1173523 | Shelby |  | Shelby County | -339679.2083 | PE
|  |  | 1173524 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  |  | Marion | CoCal Consulting, LLC | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1173525 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2012-02-08
|  |  | 1173526 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2012-02-08
|  |  | 1173527 | Jackson |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173528 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1173529 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1173530 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1173531 | Newton | Advantage Appraisal Services | Indiana Department of Transportation | 2012-03-07 | CE
CN
|  |  | 1173532 |  |  | Indiana Department of Transportation | 2012-05-02
|  |  | 1173533 |  |  | Indiana Department of Transportation | 2012-11-15
|  |  | 1173534 |  |  | Indiana Department of Transportation | 2012-03-07
|  |  | 1173535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173536 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-05-31 | CN
|  |  |  | Floyd | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-05-31 | CN
|  |  | 1173537 | Spencer | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2011-12-14 | CE
CN
|  |  | 1173538 |  |  | Dearborn County | 2012-05-31
|  |  | 1173539 | Dearborn |  | Dearborn County | 2013-05-31 | CN
|  |  | 1173540 |  |  | Dearborn County | 2012-05-31
|  |  | 1173541 |  |  | Dearborn County | 2012-05-31
|  |  | 1173542 | Dearborn |  | Dearborn County | 2013-01-23 | CN
|  |  | 1173543 |  |  | Clark County | -339679.2083
|  |  | 1173544 |  |  | Franklin County | -339679.2083
|  |  | 1173545 | Blackford |  | Blackford County | -339679.2083 | PE
|  |  | 1173546 | Lake |  | Lake County | 2012-08-08 | CE
CN
|  |  | 1173547 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
ROW
[5 empty] | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2014-01-15
|  |  | 1173548 | Boone | E.J. Breneman, LP | Lebanon | 2013-03-13 | PE
|  |  | 1173549 | Clay |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
UT
|  |  | 1173550 | Clay |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
UT
|  |  | 1173551 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173552 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173553 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173554 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173555 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1173556 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1173557 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173558 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1173559 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1173560 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173561 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173562 |  |  | MPO - Northwest | 2011-10-30
|  |  | 1173563 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173564 |  |  | MPO - Northwest | 2011-10-30
|  |  | 1173565 |  |  | MPO - Northwest | 2011-10-30
|  |  | 1173566 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173567 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173568 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173569 |  | ERES International, Inc. | Ligonier | -339679.2083
|  |  | 1173570 |  |  | Floyd County | -339679.2083
|  |  | 1173571 | Hamilton |  | Noblesville | -339679.2083 | CN
|  |  | 1173572 | Clark |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
ROW
|  |  | 1173573 | Johnson |  | Johnson County | 2017-12-13 | CE
CN
|  |  | 1173574 | Johnson | Casteel Real Estate | Franklin | 2014-02-12 | CE
CN
|  |  | 1173575 |  |  | Indiana Department of Transportation | 2011-11-30
|  |  | 1173576 | Marion |  | Speedway | 2017-12-13 | CE
CN
PE
ROW
|  |  | 1173577 | Clark |  | Indiana Department of Transportation | 2012-02-08 | CE
CN
|  |  | 1173578 | Fayette |  | Fayette County | -339679.2083 | CN
PE
|  |  | 1173579 | Elkhart |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1173580 | Hamilton |  | Fishers | 2013-07-10 | CE
CN
|  |  | 1173581 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1173582 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1173583 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1173584 | Jennings |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
UT
|  |  | 1173585 |  |  | Indiana Department of Transportation | 2012-04-04
|  |  | 1173586 | Various |  | Indiana State Agencies | -339679.2083 | PE
|  |  | 1173587 | Knox | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
ROW
|  |  | 1173588 | Crawford |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1173589 | Wabash | HE-BFS, LLC | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1173590 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1173591 | Dekalb |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1173592 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173593 |  | Dummy Consulting Firm | Lake Station | -339679.2083
|  |  | 1173594 |  | Hy-Tech Response, Inc. | Porter County | 2022-07-13
|  |  | 1173595 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2019-03-06 | CE
CN
|  |  | 1173596 |  |  | MPO - Northwest | -339679.2083
|  |  | 1173597 |  |  | Munster | 2022-04-06
|  |  | 1173598 | Lake |  | Indiana Department of Transportation | 2012-06-08 | CN
|  |  | 1173599 |  | CGI | Evansville | -339679.2083
|  |  | 1173600 | Tippecanoe |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  |  | White |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1173601 | Vanderburgh | CGI | Evansville | -339679.2083 | PE
|  |  | 1173602 | Jackson |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
|  |  |  | Scott |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 1173603 | Jackson |  | Indiana Department of Transportation | 2013-05-01 | PE
|  |  | 1173604 | Johnson |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1173605 | Scott |  | Indiana Department of Transportation | 2013-05-01 | PE
|  |  | 1173606 | Scott |  | Indiana Department of Transportation | 2013-05-01 | PE
|  |  | 1173607 | Hancock |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  | 1173608 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173609 | Knox |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1173610 | Knox |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1173611 | Orange |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1173612 | Dubois |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1173613 | Johnson |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1173614 | Scott |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
RR
|  |  | 1173615 | Clark |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
UT
|  |  | 1173616 | Bartholomew |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
ROW
|  |  | 1173617 | Clark |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1173618 |  | Hy-Tech Response, Inc. | Porter | -339679.2083
|  |  | 1173619 |  |  | Indianapolis | -339679.2083
|  |  | 1173620 | Marion |  | Indianapolis | 2016-01-13 | CE
CN
RR
|  |  | 1173621 | Marion |  | Indianapolis | 2015-03-04 | CE
CN
|  |  | 1173622 |  |  | Indianapolis | -339679.2083
|  |  | 1173623 | Fulton |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1173624 | Fulton |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1173625 | Clay |  | Clay County | 2013-05-31 | PE
|  |  | 1173626 | Tippecanoe |  | Tippecanoe County | 2018-03-14 | CN
PE
ROW
RR
|  |  | 1173627 | Tippecanoe |  | Tippecanoe County | 2021-01-13 | CE
CN
ROW
RR
|  |  | 1173628 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1173629 | Boone |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1173630 | Boone |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1173631 | White |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 1173632 | White |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
|  |  | 1173633 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173634 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173635 | Boone |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1173636 | Marion |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1173637 | Clay |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1173638 | Clay |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1173639 | Montgomery |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1173640 | Montgomery |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1173641 | Putnam |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
PE
|  |  | 1173642 | Miami | Atlas Appraisals, LLC | Converse | -339679.2083 | PE
|  |  | 1173643 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1173644 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | CN
PE
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 1173645 | Bartholomew |  | Indiana Department of Transportation | 2012-05-31 | CN
PE
|  |  | 1173646 |  |  | Columbus | -339679.2083
|  |  | 1173647 | Monroe |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1173648 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173649 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173651 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173652 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173653 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173654 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173655 |  |  | Elkhart County | -339679.2083
|  |  | 1173656 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173657 | Allen |  | Allen County | 2016-11-30 | CN
|  |  | 1173658 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173659 | Delaware |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  |  | Grant |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1173660 | Henry |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  |  | Wayne |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1173661 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173662 | Orange | Hannum, Wagle & Cline Engineering | Indiana Department of Transportation | 2012-02-08 | CE
UT
|  |  | 1173663 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2013-05-31 | PE
|  |  | 1173664 | White | Fugro Roadware, Inc. | Monticello | 2017-03-01 | CE
CN
PE
|  |  | 1173665 | St. Joseph | HDR Engineering, Inc. | North Liberty | 2014-07-09 | CE
CN
PE
|  |  | 1173666 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2012-07-11 | CE
CN
PE
|  |  | 1173667 | Lake | Brenner Design Incorporated | Dyer | 2016-01-13 | CN
PE
|  |  | 1173668 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173669 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1173670 | Daviess | AMEC E&I, Inc. | Washington | 2013-09-11 | CE
CN
PE
|  |  | 1173671 | Knox | AV Consulting Engineers, Inc. | Bicknell | 2014-09-10 | CE
CN
PE
|  |  | 1173672 | Gibson |  | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1173673 | Bartholomew |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  |  | Johnson |  | Indiana Department of Transportation | 2015-04-01 | CN
|  |  |  | Various |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1173674 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1173675 | Franklin | ARCADIS | Batesville | -339679.2083 | PE
|  |  | 1173676 | Posey |  | Indiana Department of Transportation | 2014-03-05 | CE
|  |  |  | Various |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  |  | Warrick |  | Indiana Department of Transportation | 2014-03-05 | CE
|  |  | 1173677 |  |  | Howard County | -339679.2083
|  |  | 1173678 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173679 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173680 |  |  | Howard County | -339679.2083
|  |  | 1173681 | Grant | CGS Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1173682 | Various |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1173683 | Montgomery | Banning Engineering, P.C. | Crawfordsville | 2013-05-01 | PE
|  |  | 1173684 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173685 | Putnam | AI Engineers, Inc. | Bainbridge | 2013-08-07 | CE
CN
PE
|  |  | 1173686 | Various |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1173687 | Clinton | Carters Appraisal Service | Frankfort | -339679.2083 | PE
|  |  | 1173688 | Benton | Harris Miller Miller and Hanson, Inc. | Otterbein | -339679.2083 | PE
|  |  | 1173689 | Jasper |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1173690 | Gibson | III FFC | Indiana Department of Transportation | 2012-03-07 | CE
UT
|  |  | 1173691 | Monroe |  | Bloomington | -339679.2083 | PE
|  |  | 1173692 | Bartholomew |  | Bartholomew County | -339679.2083 | PE
|  |  | 1173693 | Johnson |  | Johnson County | 2014-04-02 | CE
CN
|  |  | 1173694 | Ripley |  | Sunman | 2015-03-04 | CE
CN
PE
ROW
|  |  | 1173695 | Perry | Andrews Engineering, Inc. | Cannelton | 2015-09-02 | CE
CN
PE
|  |  | 1173696 | Vanderburgh | CGI | Evansville | 2015-02-04 | CE
CN
|  |  | 1173697 | Marion |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1173698 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
UT
|  |  | 1173699 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1173700 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1173701 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173702 |  | ASC Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173703 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2013-04-03 | CE
CN
PE
|  |  |  | Knox | Eagle Ridge Civil Engineering Services, LLC | Linton | 2013-04-03 | PE
|  |  | 1173704 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1173705 | Porter | Leitner and Associates, Inc. | Valparaiso | 2016-03-02 | CE
CN
PE
ROW
|  |  | 1173706 | Lake |  | Merrillville | 2016-03-02 | CE
CN
PE
ROW
|  |  | 1173707 |  |  | Munster | 2024-07-10
|  |  | 1173708 | Lake | Baxter & Woodman, Inc. | Crown Point | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1173709 | Porter | Hy-Tech Response, Inc. | Porter | -339679.2083 | PE
|  |  | 1173710 |  | Dummy Consulting Firm | Lake Station | -339679.2083
|  |  | 1173711 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083 | PE
|  |  | 1173712 | Lake | Gibson County Abstract & Title Co., Inc. | New Chicago | -339679.2083 | CN
|  |  | 1173713 | Delaware |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  |  | Grant |  | Indiana Department of Transportation | 2015-01-14 | CN
|  |  | 1173714 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | PE
|  |  | 1173715 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CN
|  |  | 1173716 |  | Huff & Huff, Inc. | Portage | -339679.2083
|  |  | 1173717 | Lake | Gibson County Abstract & Title Co., Inc. | New Chicago | 2014-03-05 | CE
CN
PE
|  |  | 1173718 |  | Martinez Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1173719 | Putnam | Clayton L. Roots | Greencastle | 2014-01-15 | CE
CN
|  |  | 1173720 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173721 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1173722 | Marion | Martinez Corporation | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1173723 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173724 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173725 | Kosciusko | McLane Realty, Inc. | Winona Lake | -339679.2083 | PE
|  |  | 1173726 | Adams |  | Berne | -339679.2083 | PE
|  |  | 1173727 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173728 | Wells | Hardlines Design Company | Ossian | -339679.2083 | PE
|  |  | 1173729 | Adams |  | Berne | 2015-04-01 | CE
CN
PE
|  |  | 1173730 | Dekalb | Mader Design, LLC | Waterloo | 2013-09-11 | CE
CN
PE
|  |  | 1173731 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173732 | Allen |  | Allen County | 2013-05-01 | CE
CN
ROW
UT
|  |  | 1173733 |  | CGI | Indiana Department of Transportation | 2012-03-07
|  |  | 1173734 | Blackford | Continental Mapping Consultants, LLC | Hartford City | 2013-07-10 | CE
CN
PE
|  |  | 1173735 | Washington |  | Salem | -339679.2083 | PE
|  |  | 1173736 | Noble |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1173737 | Henry |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1173738 | Henry | EFI Global, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1173739 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1173740 | Marion |  | Indiana Department of Transportation | 2012-05-31 | CN
|  |  | 1173741 |  |  | Indiana Department of Transportation | 2013-02-06
|  |  | 1173742 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1173743 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1173744 |  |  | Washington | -339679.2083
|  |  | 1173745 |  |  | Evansville | -339679.2083
|  |  | 1173746 |  |  | Cannelton | -339679.2083
|  |  | 1173747 |  |  | Bicknell | -339679.2083
|  |  | 1173748 |  |  | Linton | -339679.2083
|  |  | 1173749 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173750 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1173751 | Jennings |  | North Vernon | 2015-03-04 | CE
CN
PE
ROW
|  |  | 1173754 |  |  | MPO - Evansville | -339679.2083
|  |  | 1173755 | Lawrence |  | Lawrence | 2014-01-03 | PE
|  |  | 1173756 | Jay |  | Pennville | 2014-05-31 | PE
|  |  | 1173757 | Jay |  | Portland | -339679.2083 | PE
|  |  | 1173758 |  |  | MPO - Muncie | -339679.2083
|  |  | 1173759 | Madison |  | Elwood | 2015-09-02 | CE
CN
PE
|  |  | 1173760 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2024-09-11
|  |  | 1173761 | Franklin | Geotechnical & Materials Engineers, Inc. | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173762 |  |  | Clinton County | -339679.2083
|  |  | 1173763 | Various |  | Indiana Department of Transportation | 2012-04-04 | CE
CN
|  |  | 1173764 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173766 | Marion |  | Indianapolis | 2016-05-31 | PE
ROW
|  |  | 1173767 |  |  | Pendleton | -339679.2083
|  |  | 1173768 | Jackson | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1173769 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1173770 | Owen |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1173771 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1173772 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173773 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173774 |  |  | Noble County | 2012-08-08
|  |  | 1173775 | Hendricks | DCD Consulting LLC | Hendricks County | 2016-03-02 | CE
CN
UT
|  |  | 1173776 | Putnam | Clayton L. Roots | Greencastle | 2013-04-03 | CE
CN
|  |  | 1173777 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 1173778 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 1173779 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 1173780 | Putnam | Clayton L. Roots | Greencastle | 2015-04-01 | CE
CN
PE
|  |  | 1173781 | Jackson |  | Indiana Department of Transportation | 2013-05-01 | PE
|  |  | 1173782 | Jackson |  | Indiana Department of Transportation | 2013-05-01 | PE
|  |  | 1173783 | Scott |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173784 | Decatur |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
|  |  | 1173785 | Knox |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1173786 | Knox |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1173787 | Martin |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1173788 | Orange |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 1173789 | Lawrence |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1173790 | Lawrence |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1173791 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1173792 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173793 | Jefferson |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1173794 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173795 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173796 |  | Indiana University | Indiana Department of Transportation | -339679.2083
|  |  | 1173797 |  | Clayton L. Roots | Indiana Department of Transportation | -339679.2083
|  |  | 1173798 |  | AECON, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173799 | Knox |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
|  |  | 1173800 |  | Hitchcock Design Group | Indiana Department of Transportation | -339679.2083
|  |  | 1173801 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 1173802 | Warrick |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
RR
|  |  | 1173803 | Warrick |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173804 |  | Hatch Mott MacDonald | Indiana Department of Transportation | -339679.2083
|  |  | 1173805 | Gibson |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
RR
|  |  | 1173806 | Jefferson |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1173807 | Gibson |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173808 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173809 |  | Archonsortium, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173810 |  | H&H Associates, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173811 | Gibson |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1173812 | Gibson |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173813 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173814 |  | CDM Smith, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173815 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173816 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173817 |  | DLZ Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173818 |  | Griffin Real Estate Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173819 |  | DLZ Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173820 |  | Horn and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173821 | Decatur |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
|  |  | 1173822 | Various |  | Indiana Department of Transportation | 2016-04-06 | PL
|  |  |  | Warrick |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1173823 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1173824 | Warrick |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1173825 | Knox |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 1173826 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173827 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  |  | Marion | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173828 | Gibson |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1173829 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1173830 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
RR
|  |  | 1173831 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173832 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1173833 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173834 | Knox |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1173835 | Knox |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1173836 | Knox |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
RR
|  |  | 1173837 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173838 | Knox |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1173839 | Martin |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1173840 | Martin |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
RR
|  |  | 1173841 | Montgomery | McKee Enterprises, Inc. | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  |  | Tippecanoe | McKee Enterprises, Inc. | Indiana Department of Transportation | 2012-05-02 | CE
CN
|  |  | 1173842 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
RR
|  |  | 1173843 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2012-05-02
|  |  | 1173844 | Johnson |  | Greenwood | 2014-12-10 | CE
CN
|  |  | 1173845 |  |  | Greenwood | -339679.2083
|  |  | 1173846 | Harrison | B. L. A., Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1173847 | Floyd |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1173848 |  | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2017-05-31
|  |  | 1173849 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1173850 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173851 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173852 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173853 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173854 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173855 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173856 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173857 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173858 |  | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173859 | Floyd |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
|  |  | 1173860 | Floyd |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1173861 | Johnson |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
PE
|  |  | 1173862 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2014-07-09 | CE
CN
RR
|  |  | 1173863 | Decatur |  | Indiana Department of Transportation | 2016-01-13 | PE
|  |  |  | Shelby |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1173864 | Steuben |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1173865 | Brown |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173866 | Washington |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173867 | Dearborn |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
PE
|  |  | 1173868 | Switzerland |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1173869 |  | Appraisers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1173870 | Jackson |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
|  |  | 1173871 | Steuben |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1173872 | Huntington |  | Indiana Department of Transportation | 2014-07-10 | PE
|  |  | 1173873 | Wells |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1173874 | Blackford |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1173875 | Jackson |  | Indiana Department of Transportation | 2016-02-17 | CE
CN
PE
|  |  | 1173876 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1173877 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1173878 | Boone |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1173879 | Hendricks |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
|  |  | 1173880 | Hendricks |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
PE
|  |  | 1173881 | Montgomery |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1173882 | Montgomery |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1173883 | Boone |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1173884 | Hendricks |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173885 | Hendricks |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1173886 | Hendricks |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1173887 | Hendricks |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1173888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173889 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173890 | Hendricks |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173891 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173892 | St. Joseph |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1173893 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1173894 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173895 | St. Joseph |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
OT
PE
|  |  | 1173896 | Starke |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1173897 | Clinton |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1173898 | Jasper |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1173899 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  | 1173900 | Fountain |  | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
|  |  | 1173901 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173902 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173903 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173904 | Allen |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173905 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173906 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173907 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173908 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173909 | Allen |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173910 | Allen |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173911 | Porter |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173912 | Carroll |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1173913 | Lake |  | Indiana Department of Transportation | 2015-05-07 | CN
PE
|  |  |  | Newton |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1173914 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173915 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173916 | Jasper |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 1173917 | Miami |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1173918 | Clay |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1173919 | Hendricks |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
ROW
|  |  | 1173920 | Wayne |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173921 | Newton |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1173922 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173923 | Madison |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1173924 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173925 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173926 | Marion |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1173927 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173928 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1173929 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173930 | Warren |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
|  |  | 1173931 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173932 | Warren |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1173933 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173934 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1173935 | Clay |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1173936 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 1173937 | Carroll |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  |  | Cass |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1173938 |  | ATSI Engineering Services | Indiana Department of Transportation | -339679.2083
|  |  | 1296007 | Warren |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1296008 | Tippecanoe |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1296009 | Tippecanoe |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1296010 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 1296011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296014 |  | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296015 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296018 | Vermillion |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296019 | Fountain |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296020 | Vermillion |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296021 | Hamilton |  | Carmel | 2016-08-10 | CN
|  |  | 1296022 | Parke |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296023 | Hendricks |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296024 | Hendricks |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296025 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296026 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296027 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296028 | Vigo |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296029 | Vigo |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296030 | Parke |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296032 | Benton |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296033 | Benton |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296034 | Putnam |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296038 | Benton |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296039 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296043 | Putnam |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296044 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296045 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1296046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296047 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296048 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296049 | Boone |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1296050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296051 | Vigo |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1296052 | Vigo |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1296053 | Allen |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296054 | Allen |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296055 | Putnam |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1296056 | Wells |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296057 | Montgomery |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1296058 | Montgomery |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1296059 | Montgomery |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1296060 | Montgomery |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1296061 | Montgomery |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296062 | Hendricks |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1296063 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1296064 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1296065 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296066 | Wells |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296067 |  | McKee Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296069 | Wells |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296070 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296071 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296072 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296075 | Dekalb |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1296076 | Allen |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1296077 | Whitley |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1296078 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296079 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296080 | Tippecanoe |  | Lafayette | 2016-01-13 | CN
|  |  | 1296081 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296082 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296083 | Lake |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1296084 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296085 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296086 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296087 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296088 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296091 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296092 | Tippecanoe |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 1296093 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296094 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296095 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296096 | Grant |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296097 | Boone |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296098 | Wells |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296099 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296101 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296102 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296103 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296104 | Blackford |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1296105 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296106 | Dekalb |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1296107 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1296108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296109 | Whitley |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1296110 | Noble |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1296111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296112 | Miami |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
ROW
|  |  | 1296113 | Parke |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296118 | Boone |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1296119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296122 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296123 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1296124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296125 | Parke |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296128 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296129 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296131 | Clinton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1296132 | Miami |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1296133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296134 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296135 | Clinton |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1296136 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1296137 | White |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1296138 | Miami |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1296139 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296142 | Montgomery |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1296143 | Boone |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1296144 | Boone |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1296145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296146 | Boone |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1296147 | Boone |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1296148 | Miami |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
UT
|  |  | 1296149 | Miami |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1296150 | Miami |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1296151 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296152 | Noble |  | Indiana Department of Transportation | 2016-12-14 | PE
|  |  | 1296153 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296154 | Whitley |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1296155 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1296156 | Wells |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1296157 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1296158 | Fountain |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1296159 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296160 | Boone |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296161 | Wells |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1296162 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296163 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296164 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296165 | Clinton |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1296166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296167 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 1296168 | Wells |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1296169 | Adams |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1296170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296171 | Blackford |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
|  |  | 1296172 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296173 | Vermillion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296174 | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296175 | Clinton |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
ROW
|  |  | 1296176 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2015-09-02 | CE
CN
RR
|  |  | 1296177 | Various |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1296178 | Kosciusko |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 1296179 | Perry |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
ROW
|  |  | 1296180 | Kosciusko |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
ROW
|  |  | 1296181 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1296182 | Huntington |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  |  | Whitley |  | Indiana Department of Transportation | 2016-12-14 | PE
|  |  | 1296183 | Floyd |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296184 | Floyd |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1296185 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-10-08
|  |  | 1296186 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1296187 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296188 | Huntington |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  |  | Whitley |  | Indiana Department of Transportation | 2016-12-14 | PE
|  |  | 1296189 | Johnson |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296190 | Wells |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 1296191 | Johnson |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296192 | Elkhart |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1296193 | Shelby |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296194 | Morgan |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1296195 | Morgan |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1296196 | Johnson |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296198 | Johnson |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296199 |  | Casteel Real Estate | Indiana Department of Transportation | 2014-10-08
|  |  | 1296200 | Scott |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
ROW
|  |  | 1296201 | Lawrence |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296202 | Lawrence |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296203 | Greene |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1296204 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1296205 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296206 | Lawrence |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296207 | Knox |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 1296208 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296210 | Gibson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1296211 | Lawrence |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296212 | Warrick |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296213 | Lawrence |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
ROW
|  |  | 1296214 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296215 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296216 | Martin |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1296217 | Scott |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
ROW
|  |  | 1296218 | Pike |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
PE
|  |  | 1296219 | Perry |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1296220 |  | Lonco, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296221 | Perry |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1296222 | Benton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1296223 | Spencer |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1296224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296225 | Sullivan |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
PE
|  |  | 1296226 | Clay |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1296227 | Bartholomew |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296228 | Warrick |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1296229 | Clay |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1296230 | Spencer |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1296231 | White |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1296232 | White |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1296233 | Bartholomew |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
ROW
|  |  | 1296234 | Randolph |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1296235 | Bartholomew |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296236 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1296237 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296238 | Montgomery |  | Indiana Department of Transportation | 2022-05-31 | CE
CN
PE
ROW
RR
|  |  | 1296239 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296240 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296241 | Parke |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1296242 | Warren |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1296243 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296244 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296245 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296246 | White |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1296247 |  |  | Indianapolis | -339679.2083
|  |  | 1296248 | Hendricks |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
ROW
|  |  | 1296249 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296250 | Hendricks |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1296251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296252 | Putnam |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1296253 | Warren | Manning Real Estate Services | Indiana Department of Transportation | 2016-03-02 | CE
CN
ROW
|  |  | 1296254 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296255 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296256 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296258 | Various |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1296259 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296260 | Various |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1296261 | Various |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1296262 | Grant | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-02-03 | PE
|  |  |  | Huntington | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  |  | Steuben | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1296263 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-06-22 | PE
|  |  | 1296264 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296265 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1296266 | Bartholomew |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1296267 | Various |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296268 | Various |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296269 |  |  | Bartholomew County | -339679.2083
|  |  | 1296270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296271 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2015-03-04
|  |  | 1296272 |  | Craig eonard Historic Preservation Consultant | Indiana Department of Transportation | -339679.2083
|  |  | 1296273 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296274 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1296275 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296276 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1296277 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
RR
|  |  | 1296278 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296279 | Clay |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296280 | Marion |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1296281 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296282 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296283 | Clinton |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1296284 | Tippecanoe |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  |  | White |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1296285 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296286 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296287 | Clay | Archonsortium, LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
|  |  |  | Hendricks | Archonsortium, LLC | Indiana Department of Transportation | 2014-03-05 | CE
|  |  |  | Morgan | Archonsortium, LLC | Indiana Department of Transportation | 2014-03-05 | CE
|  |  |  | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2014-03-05 | CE
|  |  | 1296288 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296289 |  | Archonsortium, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296291 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296292 | Tippecanoe |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1296293 | Parke |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1296294 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296295 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296296 | Various |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296297 | Various |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296298 | Lake |  | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
ROW
|  |  | 1296299 | Lake |  | Indiana Department of Transportation | 2017-05-12 | CE
CN
|  |  | 1296300 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296301 | Porter |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296302 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296303 | LaPorte |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1296304 | Jasper |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
RR
|  |  | 1296305 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
RR
|  |  | 1296306 | Jasper |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296307 | Fulton |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296308 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1296309 | Porter |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1296310 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1296311 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1296312 | Newton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1296313 | Newton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1296314 | Starke |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1296315 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2015-02-04 | CE
CN
PE
|  |  | 1296316 | St. Joseph |  | Indiana Department of Transportation | 2015-02-18 | CE
CN
PE
|  |  | 1296317 | Lake |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1296318 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
|  |  | 1296319 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296320 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1296321 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
RR
|  |  | 1296322 |  | Level 5 Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296323 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296324 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296326 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1296327 | Wayne |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296328 | Dekalb | KZF Design, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1296329 | Montgomery |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1296330 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 2014-05-31
|  |  | 1296331 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1296332 |  | ARCADIS | Indiana Department of Transportation | -339679.2083
|  |  | 1296333 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296334 | Rush |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296335 | Allen |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296336 | Various |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296337 | Various |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1296338 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1296339 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 1296340 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296341 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296342 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296343 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296344 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296345 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296346 | Jay | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296347 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296348 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296349 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1296350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296351 | Vermillion |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1296352 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296353 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296354 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296355 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296356 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296357 | Porter |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
RR
|  |  | 1296358 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296359 | Porter |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1296360 | Porter |  | Indiana Department of Transportation | 2016-06-15 | CE
CN
RR
|  |  | 1296361 | Porter |  | Indiana Department of Transportation | 2016-06-15 | CE
CN
|  |  | 1296362 | Noble |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
RR
|  |  | 1296363 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 1296364 | Porter |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1296365 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1296366 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296367 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1296368 | Jasper |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1296369 | Marshall |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1296370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296371 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1296372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296373 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296374 | Kosciusko |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296375 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1296376 | Kosciusko |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296377 | Kosciusko |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296378 | Kosciusko |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296379 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296380 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1296381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296382 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296383 |  | HE-BFS, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296384 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296385 | Grant |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296386 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1296387 | Grant |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296388 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296389 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296391 | Putnam |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 1296392 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296395 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296396 | Noble | Bartlett & Associates, Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296397 | Montgomery |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296401 | Grant |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296402 | Adams |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  |  | Allen |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296404 | Clay |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1296405 | Grant |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296407 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296408 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296409 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296412 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296413 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296414 | Grant |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296415 |  | HE-BFS, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296416 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296417 | Steuben | ABt SRBI | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296418 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296419 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1296420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296421 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1296422 | Various |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1296423 | Wabash | Duke Energy Corporation | Indiana Department of Transportation | 2016-02-03 | CE
CN
RR
|  |  | 1296424 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1296425 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296426 | Huntington |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1296427 | Hamilton | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
|  |  | 1296428 | Noble |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
|  |  | 1296429 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296430 | LaPorte |  | Indiana Department of Transportation | 2015-08-19 | CE
CN
PE
|  |  | 1296431 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296432 |  | ACMS Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296433 | Blackford |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
|  |  | 1296434 | Delaware |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
|  |  | 1296435 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296436 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1296437 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296438 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296439 | Howard |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1296440 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2015-07-08 | CE
CN
RR
|  |  | 1296441 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
RR
|  |  | 1296442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296443 |  | Afram Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1296444 |  | American Structurepoint, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296445 |  | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | -339679.2083
|  |  | 1296446 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2017-05-12 | CE
CN
|  |  | 1296447 |  | M.A.T. Consulting, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296448 | Marshall |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1296449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296450 | Fulton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296451 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296452 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296453 | Lake |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296454 | St. Joseph |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1296455 | Huntington |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1296456 | Jasper |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1296457 | Newton |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1296458 | Fulton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296459 | LaGrange | Duesler Realty House | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1296460 | Allen |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1296461 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296462 | Allen |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1296463 | White |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1296464 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-04-05 | CE
CN
RR
|  |  | 1296465 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296466 | Howard |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1296467 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296468 |  | InfoTech | Indiana Department of Transportation | -339679.2083
|  |  | 1296469 | Randolph |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
|  |  | 1296470 | Hamilton |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
ROW
|  |  | 1296471 | Allen |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1296472 |  | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296473 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1296474 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296475 | Dekalb | American Engineers, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
RR
|  |  | 1296476 | Newton |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1296477 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296478 | Dekalb |  | Indiana Department of Transportation | 2019-01-16 | PE
|  |  |  | Steuben |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1296479 | Fulton |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1296480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296481 | LaGrange |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1296482 | Randolph |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1296483 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296484 | Newton |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1296485 | Kosciusko |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296486 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296487 |  |  | Indiana Department of Transportation | 2012-11-15
|  |  | 1296488 | Marshall |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1296489 | Starke |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1296490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296492 |  | Domain Architecture, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296493 | Kosciusko | CET, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296494 | Fulton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296495 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296497 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | -339679.2083
|  |  | 1296498 | Noble | ERES International, Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296499 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | PE
ROW
|  |  | 1296500 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | PE
ROW
|  |  | 1296501 |  | 2IM Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296503 |  | Blue Sky Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296504 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296505 | Miami | Alt & Witzig Engineering, Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296506 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296507 | St. Joseph |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296508 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296509 |  | Independent Appraisers-Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296510 | Wayne |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1296511 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 1296512 | Wayne |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1296513 | Henry |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1296514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296515 | Delaware |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1296516 | Lake |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1296517 | Randolph |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1296518 | LaPorte | MCIS LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
RR
|  |  |  | Starke | MCIS LLC | Indiana Department of Transportation | 2018-05-10 | PE
|  |  | 1296519 | Rush |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1296520 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
RR
|  |  | 1296521 | Union |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1296522 |  | Iteris, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296523 | Wayne |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1296524 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1296525 | Hancock |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1296526 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296527 | Wayne |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 1296528 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1296529 | Carroll | Amereco Incorporated | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1296530 | Wayne |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 1296531 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296532 | Wayne |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1296533 | Wayne |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
ROW
|  |  | 1296534 | Grant |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1296535 | Ripley |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
UT
|  |  | 1296536 | Blackford |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
|  |  | 1296537 | Jefferson | BradsKo Engineering and Surveying Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1296538 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1296539 | Gibson |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1296540 | Ripley |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1296541 | Vanderburgh |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1296542 | Greene |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1296543 | Decatur |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
ROW
|  |  | 1296544 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296545 | Warrick |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1296546 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296547 | Posey |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1296548 | Warrick |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296549 | Dubois |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296550 | Crawford |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296551 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296552 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296553 | Posey |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296554 | Posey |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296555 | Gibson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296556 | Jackson |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296557 | Warrick |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296558 | Dekalb |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1296559 | Spencer |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296560 | Clark |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1296561 | Crawford |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1296562 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296563 | Jennings |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
ROW
UT
|  |  | 1296564 | Crawford |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1296565 | Morgan |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
ROW
|  |  | 1296566 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296567 | Brown |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
|  |  | 1296568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296569 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296570 | Warrick |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296571 | Jackson |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
ROW
UT
|  |  | 1296572 | Lake |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1296573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296574 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296575 | Posey |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1296576 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296577 | Posey | I. T. Business Corporation | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296578 | LaPorte |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296579 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296580 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296581 | Pike |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1296582 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296583 | Perry |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1296584 | Shelby |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296585 | Sullivan |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1296586 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1296587 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1296588 | Sullivan |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
ROW
|  |  | 1296589 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296590 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296591 | Knox |  | Indiana Department of Transportation | 2017-03-01 | PE
|  |  | 1296592 | Marion |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
UT
|  |  | 1296593 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1296594 | Gibson |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
ROW
|  |  | 1296595 | Marion |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1296596 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296597 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296598 | Shelby |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1296599 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296600 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296601 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296602 | Pike |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
ROW
|  |  | 1296603 | Shelby |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296604 | Bartholomew |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1296605 | Daviess |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1296606 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296607 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296608 | Lawrence |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
ROW
UT
|  |  | 1296609 | Parke |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
RR
|  |  |  | Vermillion |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
RR
|  |  | 1296610 | Marion |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1296611 |  | AECOM USA, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296612 | Greene |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
ROW
|  |  | 1296613 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05 | RR
|  |  | 1296614 | Jasper |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1296615 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296616 | Lawrence |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
ROW
|  |  | 1296617 | Fountain |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  |  | Montgomery |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1296618 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296619 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296620 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296621 | Switzerland |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1296622 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296623 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1296624 | Henry |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1296625 | Pulaski |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1296626 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296627 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296628 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296630 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1296631 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1296632 | Warrick |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
ROW
|  |  | 1296633 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296634 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296635 | Henry |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1296636 |  | McCormick Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296637 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296638 | Pulaski |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1296639 | LaPorte |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1296640 | Posey |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
ROW
|  |  | 1296641 | LaPorte |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1296642 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1296643 | Cass |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
|  |  | 1296644 | Gibson |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1296645 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296646 | Carroll | CRI Construction Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296647 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296648 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296649 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1296650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296651 | Marion |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296652 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296653 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296654 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1296655 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296656 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296657 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296658 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296659 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1296660 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296661 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296662 | White | Afram Corporation | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
RR
|  |  | 1296663 |  | Clayton L. Roots | Indiana Department of Transportation | -339679.2083
|  |  | 1296664 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296665 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1296666 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1296667 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296668 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296669 |  | Archonsortium, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296670 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296672 | Brown |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1296673 | Spencer |  | Indiana Department of Transportation | 2016-05-31 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 1296674 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296675 | Lake |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1296676 | Greene |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296677 | Dubois |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1296678 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296679 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296680 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
PE
RR
|  |  | 1296681 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296682 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  | 1296683 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1296684 | Jackson |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
UT
|  |  | 1296685 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1296686 | Warrick |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296687 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296688 | Warrick |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296689 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1296690 | Spencer |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296691 |  | Dummy Consulting Firm Too | Indiana Department of Transportation | -339679.2083
|  |  | 1296692 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1296693 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296694 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1296695 | Spencer |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296696 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296697 | Franklin |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1296698 | Shelby |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296699 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1296700 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296701 |  | Cambridge Systematics, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296702 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296703 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296704 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296705 | Owen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296706 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 1296707 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296708 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296709 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 1296710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296711 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 1296712 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296713 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1296714 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296715 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296716 | Hancock |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1296717 | Bartholomew |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1296718 | Spencer |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
RR
|  |  | 1296719 | Hancock |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1296720 | Delaware |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1296721 | Spencer |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296722 | Delaware |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1296723 | Perry |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296724 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1296725 | Shelby |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296726 |  | Martinez Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1296727 | Perry |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296728 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296729 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296730 | Hancock |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1296731 |  | Eel River Abstract | Indiana Department of Transportation | -339679.2083
|  |  | 1296732 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296733 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296734 | Delaware |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296735 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296736 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296737 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1296738 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296739 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296740 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296741 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1296742 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296743 | Dubois |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1296744 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1296745 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1296746 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296747 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296748 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296749 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296751 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296752 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296753 | Dubois |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1296754 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296755 | Dubois |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1296756 | Spencer |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296757 | Daviess |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296758 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296759 | Franklin |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
|  |  | 1296760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296761 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296762 | Shelby |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296763 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296764 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296766 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296767 | Washington |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1296768 | Henry | GS-IN P.C. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  |  | Randolph | GS-IN P.C. | Indiana Department of Transportation | 2015-01-14 | CE
|  |  | 1296769 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296770 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296771 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296772 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296773 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296774 | Warrick |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296775 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1296776 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296777 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296778 | Warrick |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296779 | Vanderburgh |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1296780 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296781 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296782 | Franklin |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1296783 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296784 | Posey |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296785 |  | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | -339679.2083
|  |  | 1296786 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296787 | Posey |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296788 | Posey |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296789 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296790 | Posey |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296791 | Posey |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296792 | Posey |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296793 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296794 | Posey |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296795 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296796 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296797 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296798 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296799 | Spencer |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296800 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296801 | Spencer |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296802 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296803 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296804 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296805 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296806 | Daviess |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
UT
|  |  | 1296807 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1296808 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296809 | Posey |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1296810 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296811 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 1296812 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296813 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296814 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296815 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2015-02-18 | CE
CN
|  |  | 1296816 |  | American Real Estate Appraisers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296817 |  | Civil Designs, LLP | Indiana Department of Transportation | -339679.2083
|  |  | 1296818 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296819 |  | Jacobi, Toombs & Lanz, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296820 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296821 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1296822 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296823 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296824 |  | Marine Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296825 | Marion |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1296826 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1296827 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296828 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296829 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296830 |  | Brenner Design Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 1296831 |  | Accurate Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296832 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296833 | Cass |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1296834 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296835 | Marion | ASC Group, Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1296836 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296837 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296838 | Steuben |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
PE
|  |  | 1296839 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296840 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296841 | Huntington |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296842 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296843 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296844 | Huntington |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296845 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1296846 | Delaware |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 1296847 | Hamilton |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1296848 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296849 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1296850 | Hancock |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  |  | Madison |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2016-01-13 | PE
|  |  | 1296851 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296852 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296854 |  | Bowman, Barrett & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296855 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296856 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
RR
|  |  | 1296857 |  | ACME | Indiana Department of Transportation | -339679.2083
|  |  | 1296858 |  | Collins Engineers Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 1296859 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 1296860 |  | CGS Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296861 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296863 | Warrick |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296864 | Dubois |  | Indiana Department of Transportation | 2016-04-06 | CE
PE
|  |  |  | Spencer |  | Indiana Department of Transportation | 2016-04-06 | CN
PE
|  |  | 1296865 | Perry |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296866 | Crawford |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1296867 | Crawford |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296868 |  | Heritage Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296869 |  | HOH Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296870 |  | Anelena Ackerly | Indiana Department of Transportation | -339679.2083
|  |  | 1296871 | Dekalb | American Engineers, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
ROW
|  |  | 1296872 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296873 |  | EcoTec, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296874 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 1296875 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 1296876 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296877 | Vigo |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1296878 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296879 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296880 |  | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296881 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
RR
|  |  | 1296882 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296883 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1296884 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 1296885 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296886 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296887 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296888 | Pike | Meca Engineering Corporation of America Incorporated | Indiana Department of Transportation | 2016-02-03 | CE
CN
RR
|  |  | 1296889 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296890 | Steuben | Certified Engineering, Inc. | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296891 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 1296892 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 1296893 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296894 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1296895 | Perry |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296896 |  | Dorochoff Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296897 |  | Engineering Technologies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296898 |  | JJR, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296899 |  | CMF Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296901 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1296902 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296903 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296904 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296905 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1296906 | Elkhart |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1296907 | Posey | GRL Engineers, Inc. | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1296908 | Various |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1296909 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
ROW
RR
|  |  | 1296910 | Various |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1296911 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
|  |  | 1296912 | Bartholomew |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  |  | Various |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1296913 | LaPorte |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1296914 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296915 | Clark |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1296916 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296917 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296918 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296919 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1296920 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1296921 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296922 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1296923 |  | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 1296924 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296925 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1296926 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1296927 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296928 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296929 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296930 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1296931 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1296932 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296933 | Allen |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1296934 | St. Joseph |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1296935 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296937 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296938 |  | Edwards and Kelcey | Indiana Department of Transportation | -339679.2083
|  |  | 1296939 | Jackson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 1296940 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296941 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296942 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296943 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
RR
|  |  | 1296944 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1296945 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296946 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296947 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296948 |  | Kruse Consulting, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296949 | Tippecanoe |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 1296950 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296951 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296952 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296953 | Brown | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1296954 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296955 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296956 | Franklin |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
RR
|  |  | 1296957 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296958 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1296959 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296960 | Various |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296961 | Various | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1296962 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  | 1296963 | Marion |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296964 | Marion |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1296965 |  | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296966 | Marion |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1296967 | Various |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1296968 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 1296969 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1296970 | Clark |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1296971 | Various |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296972 | Various |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1296973 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1296974 | Hendricks |  | Hendricks County | 2016-03-02 | CE
CN
|  |  | 1296975 | Johnson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1296976 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296977 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296978 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296979 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1296980 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1296981 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1296982 |  | GRL Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296983 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1296984 |  | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296985 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296986 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1296987 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296988 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296989 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296990 | Porter |  | Indiana Department of Transportation | 2021-05-05 | PE
|  |  | 1296991 |  | J.F. New & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1296992 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296993 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296994 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296995 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1296996 | Crawford | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
PE
|  |  | 1296997 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296998 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1296999 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1297000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297001 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297002 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297004 | Monroe |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1297005 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1297006 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297007 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1297008 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 1297009 | Lawrence |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1297010 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1297011 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297013 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297015 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 1297016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297017 | Lake | Consolidated Test Company | Hammond | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1297018 | Bartholomew |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1297019 |  | Dynasty Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297021 | Cass |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
RR
|  |  | 1297022 | Cass |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
RR
|  |  | 1297023 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
RR
|  |  | 1297024 | Cass |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1297025 | Noble |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1297026 | Tippecanoe |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
ROW
|  |  | 1297027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297029 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1297030 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1297031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297033 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297034 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297038 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297039 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297043 | Boone |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1297044 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297045 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297046 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297047 | Allen |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1297048 | Wabash |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
|  |  | 1297049 | Clay |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
PE
|  |  | 1297050 | Warrick |  | Indiana Department of Transportation | -339679.2083 | PE
ROW
UT
|  |  | 1297051 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297053 | Huntington |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1297054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297055 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297056 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297057 | Whitley |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1297058 | Wabash |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1297059 | Wabash |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
ROW
|  |  | 1297060 | Monroe | Absolute Title Services, LLC | Bloomington | 2016-04-06 | CE
CN
|  |  | 1297061 |  |  | MPO - Muncie | -339679.2083
|  |  | 1297062 |  |  | MPO - Muncie | -339679.2083
|  |  | 1297063 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297064 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297065 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297066 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297067 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297068 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297069 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297070 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297071 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297072 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297073 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297074 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297075 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297076 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297077 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297078 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297079 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297080 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297081 | Tippecanoe | DuSABLE, Inc. | Tippecanoe County | 2013-05-31 | PE
|  |  | 1297082 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297083 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297084 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297085 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1297086 | Madison |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1297087 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297088 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297090 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1297091 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297092 | LaPorte |  | LaPorte County | -339679.2083 | PE
|  |  | 1297093 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1297094 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1297095 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1297096 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1297097 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297098 | Hancock |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 1297099 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297100 |  |  | Indiana Department of Transportation | 2012-01-20
|  |  | 1297101 |  |  | Indiana Department of Transportation | 2012-01-20
|  |  | 1297102 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297103 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297111 | Various |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1297112 | Various |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1297113 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1297114 | Various |  | Indiana Department of Transportation | 2015-09-15 | OT
|  |  | 1297115 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1297116 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1297117 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 1297118 |  |  | Indianapolis | 2012-03-15
|  |  | 1297119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297122 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297124 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297125 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297126 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297127 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297129 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1297130 |  |  | South Bend | 2016-05-31
|  |  | 1297131 |  | Dummy Consulting Firm Too | Indiana Department of Transportation | -339679.2083
|  |  | 1297132 |  | Dummy Consulting Firm Too | Indiana Department of Transportation | -339679.2083
|  |  | 1297133 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297134 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297135 |  | Eco Logic, LLC | Indiana Department of Transportation | 2016-05-31
|  |  | 1297136 |  |  | Indiana Department of Transportation | 2015-02-23
|  |  | 1297137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297138 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297139 |  | McKee Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297140 | Putnam |  | Putnam County | 2014-02-05 | CE
CN
PE
|  |  | 1297141 | Gibson |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297142 | Whitley |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1297143 | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 1297144 | Hamilton |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
|  |  | 1297145 | Hamilton |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1297146 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297147 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297148 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297149 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297151 | Tippecanoe |  | Indiana Department of Transportation | 2012-05-31 | PE
|  |  | 1297152 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297153 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297156 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297157 | Carroll |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297158 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297159 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297160 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297161 | Madison |  | Pendleton | 2015-09-02 | CE
CN
PE
ROW
|  |  | 1297162 | Carroll |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1297163 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297164 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297165 | Hamilton |  | Carmel | 2013-07-10 | CE
CN
|  |  | 1297166 | Hamilton |  | Carmel | 2016-07-13 | CE
CN
|  |  | 1297167 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1297168 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297169 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297170 | Allen |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297171 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2012-10-11 | CE
CN
PE
|  |  | 1297172 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1297173 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1297174 |  |  | Indiana Department of Transportation | 2012-03-07
|  |  | 1297175 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1297176 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1297177 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1297178 | Lawrence | Hagerty Engineering, Inc. | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1297179 |  | Alliance Environmental Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297180 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2012-10-11 | CE
CN
PE
|  |  | 1297181 | Knox |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  |  | Sullivan |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1297182 | Scott |  | Scott County | 2013-05-31 | PE
|  |  | 1297183 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2022-04-06 | PE
ROW
UT
|  |  | 1297184 | Parke |  | Indiana Department of Natural Resources | 2015-03-04 | CN
PE
|  |  | 1297185 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1297186 | Boone |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
RR
|  |  |  | Clinton |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
RR
|  |  | 1297187 | Hendricks | Horn and Associates, Inc. | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1297188 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1297189 | Marshall |  | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 1297190 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1297191 | Henry |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
|  |  | 1297192 | Hamilton |  | Indiana Department of Transportation | 2013-12-11 | PE
|  |  | 1297193 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1297194 | Miami |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1297195 | Hamilton |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1297196 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1297197 | Randolph |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1297198 | Owen |  | Gosport | 2013-05-31 | PE
|  |  | 1297199 | Johnson |  | Johnson County | 2014-09-10 | CE
CN
OT
PE
ROW
UT
|  |  | 1297200 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1297201 | Madison | Central Diving Contractors | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1297202 | Madison |  | Madison County | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1297203 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1297204 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1297205 | Greene |  | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1297206 |  |  | Columbus | 2012-07-11
|  |  | 1297207 | Clark |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  |  | Floyd |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
ROW
|  |  | 1297208 | Monroe |  | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 1297209 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1297210 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297211 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297212 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297213 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297214 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297215 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297216 | Posey |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1297217 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297218 |  |  | MPO - Evansville | -339679.2083
|  |  | 1297219 |  |  | MPO - Evansville | -339679.2083
|  |  | 1297220 | Madison |  | Pendleton | 2013-03-06 | CE
CN
|  |  | 1297221 |  |  | Pendleton | -339679.2083
|  |  | 1297222 | Hamilton | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
|  |  | 1297223 | Dearborn |  | Indiana Department of Transportation | 2012-07-11 | CE
CN
|  |  | 1297224 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2012-03-28
|  |  | 1297225 | Hamilton | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297226 | Hamilton | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297227 | Boone | Another Test Company | Indiana Department of Transportation | 2013-10-09 | CE
CN
PE
|  |  |  | Hamilton | Another Test Company | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  |  | Marion | Another Test Company | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1297228 | Tippecanoe |  | Lafayette | 2015-09-02 | CE
CN
|  |  | 1297229 | Elkhart | Civil Inspection Services, LLC | Goshen | 2016-02-03 | CE
CN
RR
|  |  | 1297230 | Warren |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1297231 |  | Hardcore Concrete Sawing Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297232 | Hamilton | CPS Acquisitions, LLC | MPO - Indianapolis | 2013-01-18 | CE
CN
|  |  | 1297233 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2012-12-13 | PE
|  |  | 1297234 |  | Linda F. Russell | Veedersburg | -339679.2083
|  |  | 1297235 |  |  | Indiana Department of Transportation | 2012-08-08
|  |  | 1297236 |  |  | Indiana State Agencies | 2013-05-31
|  |  | 1297237 |  |  | Indiana Department of Transportation | 2013-01-16
|  |  | 1297238 | Whitley |  | Allen County | 2017-10-12 | CE
CN
PE
ROW
|  |  | 1297239 | Hamilton | Another Test Company | Indiana Department of Transportation | 2012-08-08 | CE
UT
|  |  | 1297240 | Hamilton | Another Test Company | Indiana Department of Transportation | -339679.2083 | CE
UT
|  |  | 1297241 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297242 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297243 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297244 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297245 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297246 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297247 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1297248 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2012-06-21 | PE
|  |  | 1297249 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-05-01 | CE
CN
PE
|  |  | 1297250 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1297251 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297252 | Spencer | JJR, LLC | Santa Claus | 2020-03-04 | CE
CN
PE
ROW
|  |  | 1297253 | Lake | Consolidated Test Company | Hammond | 2014-11-13 | CE
CN
|  |  | 1297254 | Lake | Baxter & Woodman, Inc. | Crown Point | 2013-05-31 | CN
|  |  | 1297255 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2013-05-31 | CN
|  |  | 1297256 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2012-11-02 | CN
|  |  | 1297257 | LaPorte | Farah and Sons, Inc. | Michigan City | 2013-08-07 | CE
CN
|  |  | 1297258 |  |  | Gary | -339679.2083
|  |  | 1297259 |  |  | MPO - Northwest | 2012-04-14
|  |  | 1297260 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-08-05
|  |  | 1297261 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 1297262 | Henry |  | Indiana Department of Transportation | 2013-01-16 | CE
CN
|  |  | 1297263 | Wayne |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1297264 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1297265 | Wayne |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1297266 | Wayne |  | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1297267 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1297268 | Marshall |  | Marshall County | 2014-12-10 | CE
CN
|  |  | 1297269 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2013-05-03 | CE
CN
|  |  | 1297270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297271 |  |  | South Bend Transit | -339679.2083
|  |  | 1297272 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1297273 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1297274 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1297275 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1297276 |  |  | Indiana Department of Transportation | 2012-07-11
|  |  | 1297277 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297278 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297279 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1297280 | Perry |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1297281 | Martin |  | Martin County | 2016-05-05 | CE
CN
PE
ROW
|  |  | 1297288 | Lake |  | Lake County | 2015-05-07 | CE
CN
|  |  | 1297289 |  |  | Indiana Department of Transportation | 2012-09-12
|  |  | 1297290 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297291 | Hendricks |  | Hendricks County | 2014-03-05 | CE
CN
|  |  | 1297292 | Marion |  | Indianapolis | 2015-01-14 | CE
CN
|  |  | 1297293 | Marion |  | Indianapolis | 2016-05-31 | PE
|  |  | 1297294 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297295 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297296 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297297 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297298 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297299 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297300 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297301 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297302 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1297303 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1297304 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297305 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297306 | Kosciusko | LONCO, Inc. | Indiana Department of Transportation | 2013-04-03 | CE
CN
RR
|  |  | 1297307 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297308 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1297326 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297327 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297328 | Steuben | AECOM Technical Services, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1297329 | Grant | Kruse Consulting, Inc. | Indiana Department of Transportation | 2013-04-03 | CE
CN
RR
|  |  | 1297330 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297331 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297332 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1297333 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1297334 | Vanderburgh | CGI | Evansville | 2014-07-09 | CE
CN
|  |  | 1297335 |  | CGI | Evansville | -339679.2083
|  |  | 1297336 | Vanderburgh | CGI | Evansville | 2014-07-09 | CE
CN
|  |  | 1297337 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297338 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297339 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297340 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297341 | Floyd |  | Indiana Department of Transportation | 2012-09-12 | CE
CN
|  |  | 1297342 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297343 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297344 |  |  | MPO - Evansville | 2012-05-10
|  |  | 1297345 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297346 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297347 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1297348 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297349 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297350 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1297351 |  |  | New Albany | -339679.2083
|  |  | 1297352 |  |  | Indianapolis | 2016-05-31
|  |  | 1297353 | Kosciusko |  | Kosciusko County | 2014-02-05 | CE
CN
PE
|  |  | 1297362 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297363 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297364 |  | JJR, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297365 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297366 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297367 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297368 | Vanderburgh | CGI | Indiana Department of Transportation | 2012-11-15 | CE
CN
|  |  | 1297369 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1297370 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297379 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297388 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297389 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297390 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297391 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297392 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297393 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2013-05-31 | CN
PE
|  |  | 1297394 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297395 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297396 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297397 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297399 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297401 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297402 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297404 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297405 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297406 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297407 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297408 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297409 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297410 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297411 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297412 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297413 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297414 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297415 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297416 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297417 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297418 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297419 | Marion |  | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297420 | Vanderburgh |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 1297421 |  |  | Starke County | -339679.2083
|  |  | 1297422 | Montgomery | ETC Institute | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  |  | Tippecanoe | ETC Institute | Indiana Department of Transportation | 2012-08-08 | CE
CN
|  |  | 1297423 | Brown |  | Brown County | -339679.2083 | PE
|  |  | 1297432 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1297433 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | 2013-05-31
|  |  | 1297447 |  |  | MPO - Northwest | -339679.2083
|  |  | 1297448 |  |  | Indiana Department of Transportation | 2012-12-12
|  |  | 1297449 | Clark |  | Indiana Department of Transportation | 2012-10-10 | CE
CN
|  |  | 1297450 | Clark |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1297451 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297452 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297453 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297454 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1297455 | Vanderburgh |  | Indiana Department of Transportation | 2012-06-20 | PE
|  |  | 1297456 | Vanderburgh |  | Indiana Department of Transportation | 2012-06-20 | PE
|  |  | 1297457 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297458 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297470 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297471 | Jasper |  | Indiana Department of Transportation | 2013-02-06 | CE
CN
|  |  | 1297475 | Hamilton | Another Test Company | Indiana Department of Transportation | 2013-07-17 | CE
CN
|  |  | 1297476 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 1297477 | Dearborn |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297478 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 1297479 |  | Another Test Company | Indiana Department of Transportation | 2013-07-17
|  |  | 1297480 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2016-05-31 | PE
|  |  |  | Floyd | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297481 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297482 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297483 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297484 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297485 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297490 |  |  | Clarksville | 2013-05-31
|  |  | 1297491 | Warrick |  | Warrick County | 2013-08-12 | PE
|  |  | 1297492 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297495 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297496 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297497 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297498 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297499 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297500 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297501 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297503 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297504 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297505 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297506 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1297507 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1297508 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297509 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297510 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297512 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297515 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297516 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297517 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297518 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297519 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297520 |  |  | MPO - Louisville | 2015-05-31
|  |  | 1297521 |  |  | MPO - Louisville | 2015-05-31
|  |  | 1297522 |  |  | MPO - Louisville | -339679.2083
|  |  | 1297523 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297524 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297525 | Hancock |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1297526 | Morgan |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1297527 | Greene | Bruce S. Grimes | Indiana Department of Transportation | 2012-12-12 | CE
CN
|  |  | 1297528 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297529 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297530 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2014-12-05 | RR
|  |  | 1297531 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2014-12-05 | RR
|  |  | 1297532 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2014-12-05 | RR
|  |  | 1297533 | Johnson | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1297534 | Johnson | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1297535 | Pike | Home Equity Appraisals | Petersburg | 2016-05-04 | PE
|  |  | 1297536 | Franklin | ARCADIS | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  |  | Ripley | ARCADIS | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1297537 |  |  | Indianapolis | 2013-08-07
|  |  | 1297538 |  |  | Anderson | -339679.2083
|  |  | 1297539 | Madison |  | Anderson | 2015-03-04 | CE
CN
PE
RR
|  |  | 1297540 | Cass |  | Cass County | 2016-08-10 | CE
CN
PE
ROW
RR
|  |  | 1297541 | Porter |  | Porter County | 2015-09-02 | CE
CN
PE
ROW
UT
|  |  | 1297542 | Newton |  | Newton County | 2015-07-08 | CE
CN
PE
ROW
|  |  | 1297543 | Boone |  | Indiana Department of Natural Resources | 2017-12-31 | CN
PE
ROW
|  |  |  | Clinton |  | Indiana Department of Natural Resources | 2017-12-31 | CN
PE
ROW
|  |  | 1297544 | Boone |  | Indiana Department of Natural Resources | 2013-05-31 | CN
PE
ROW
|  |  | 1297545 | Hancock |  | Indiana Department of Natural Resources | 2015-04-13 | CN
PE
ROW
|  |  | 1297546 |  |  | Indiana Department of Natural Resources | 2013-05-31
|  |  | 1297547 | Pulaski |  | Indiana Department of Natural Resources | 2017-01-24 | CN
|  |  | 1297548 | Marion |  | Indiana Department of Natural Resources | 2015-05-21 | OT
|  |  | 1297549 | Warrick |  | Indiana Department of Natural Resources | 2013-05-31 | CN
|  |  | 1297550 | Wells |  | Wells County | 2015-11-10 | CE
CN
PE
|  |  | 1297551 | Fountain | AECON, Inc. | Attica | 2017-01-19 | CE
CN
PE
ROW
RR
|  |  | 1297552 | Clinton |  | Clinton County | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1297553 |  |  | Indiana Department of Transportation | 2013-02-06
|  |  | 1297554 |  | Clyde L. Hawkins | Indiana Department of Transportation | -339679.2083
|  |  | 1297555 |  |  | Franklin County | -339679.2083
|  |  | 1297556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297557 |  |  | Marion | 2013-05-31
|  |  | 1297558 |  |  | MPO - Indianapolis | 2012-07-31
|  |  | 1297559 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1297560 | Various |  | MPO - Indianapolis | -339679.2083 | CN
|  |  | 1297561 | Hamilton |  | Carmel | 2016-11-16 | CE
CN
ROW
|  |  | 1297562 | Hamilton |  | Hamilton County | 2015-07-08 | CE
CN
|  |  | 1297563 | Hamilton |  | Fishers | 2016-06-15 | CE
CN
|  |  | 1297564 | Randolph | Apex Consulting & Surveying, Inc. | Winchester | 2014-11-13 | CE
CN
PE
|  |  | 1297565 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 1297566 | Bartholomew |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1297567 | Various | Bayswater Company, LLC | Terre Haute | 2014-11-13 | CN
|  |  |  | Vigo | Bayswater Company, LLC | Terre Haute | 2014-11-13 | CE
CN
PE
|  |  | 1297568 | Vigo | Bayswater Company, LLC | Terre Haute | 2014-11-13 | CE
CN
|  |  | 1297569 | Vigo |  | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1297570 | Boone |  | Indiana Department of Transportation | 2012-09-05 | RR
|  |  | 1297571 | Tippecanoe |  | Indiana Department of Transportation | 2012-09-05 | RR
|  |  | 1297572 | Tippecanoe |  | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1297573 | Shelby |  | Indiana Department of Transportation | 2014-02-07 | RR
|  |  | 1297574 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-11-06 | RR
|  |  | 1297575 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-11-06 | RR
|  |  | 1297576 | Huntington |  | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297577 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297578 | Wabash |  | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297579 |  |  | Ellettsville | -339679.2083
|  |  | 1297580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297581 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297582 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297583 | Sullivan | Klug Engineering, Inc. | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1297584 | Greene |  | Indiana Department of Transportation | 2013-05-13 | RR
|  |  | 1297585 | Jackson |  | Seymour | 2015-08-13 | PE
ROW
|  |  | 1297586 | Gibson |  | Indiana Department of Transportation | 2012-09-06 | RR
|  |  | 1297587 | Greene |  | Indiana Department of Transportation | 2012-09-06 | RR
|  |  | 1297588 | Various |  | Indiana Department of Transportation | 2013-03-04 | RR
|  |  | 1297589 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297592 |  |  | Indiana Department of Transportation | 2012-09-12
|  |  | 1297593 | Harrison |  | Indiana Department of Transportation | 2012-10-11 | CE
CN
|  |  | 1297594 | Spencer |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297595 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297596 |  |  | MPO - Louisville | -339679.2083
|  |  | 1297597 | Miami |  | Miami County | 2013-04-25 | PE
|  |  |  | Various |  | Miami County | 2013-04-25 | PE
|  |  | 1297598 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1297599 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1297603 | Bartholomew | Crawford, Murphy & Tilly, Inc. | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1297604 | Bartholomew |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297605 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1297606 |  |  | North Vernon | 2013-05-01
|  |  | 1297607 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1297608 | Hancock |  | Hancock County | 2019-12-11 | CE
CN
ROW
|  |  | 1297609 | Harrison |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1297610 | Adams |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1297611 | Noble | Debbie L. Morris | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1297612 | Floyd | Commonwealth Heritage Group, Inc. | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1297613 | Marion |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1297614 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297615 | Allen |  | Indiana Department of Transportation | 2013-05-31 | CN
|  |  | 1297623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297626 | Posey |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  |  | Vanderburgh |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1297627 | Sullivan |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
RR
|  |  | 1297628 | Perry |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1297629 | Daviess |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  |  | Knox |  | Indiana Department of Transportation | 2014-09-10 | CN
|  |  | 1297630 | Posey |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1297631 |  | Advanced Engineering Services Inc. | Bristol | 2013-05-06
|  |  | 1297632 | Lake | Brenner Design Incorporated | Indiana Department of Transportation | 2014-05-21 | CE
CN
RR
|  |  | 1297633 | Monroe |  | Monroe County | 2017-09-13 | PE
|  |  | 1297634 | Jasper |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297635 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1297636 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2013-07-10 | CE
CN
RR
|  |  | 1297637 |  |  | MPO - Northwest | 2012-09-30
|  |  | 1297638 |  |  | MPO - Anderson | -339679.2083
|  |  | 1297639 |  |  | MPO - Anderson | -339679.2083
|  |  | 1297640 | Porter |  | Indiana Department of Transportation | 2015-04-15 | CE
CN
PE
|  |  | 1297641 | Allen |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1297642 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2015-08-21 | CE
CN
|  |  | 1297643 | St. Joseph |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1297644 | Jasper | Civil Engineering Consultants | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1297645 | Newton | Advantage Appraisal Services | Indiana Department of Transportation | 2015-01-16 | CE
CN
|  |  | 1297646 | Lake | Cornerstone Design | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1297647 | Clinton |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297648 |  | CDM Smith, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297649 | Hendricks |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2015-02-04 | CN
|  |  | 1297650 | Knox | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2013-03-06 | CE
UT
|  |  | 1297651 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1297652 | Marion |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1297653 |  | Banning Engineering, P.C. | Crawfordsville | 2016-05-31
|  |  | 1297654 |  | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2013-03-06
|  |  | 1297655 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1297656 | Decatur | Collier Transport Inc. | Decatur County | 2012-10-20 | PE
|  |  |  | Various | Collier Transport Inc. | Decatur County | 2012-10-20 | PE
|  |  | 1297657 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297658 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 1297659 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1297660 |  |  | Indiana Department of Transportation | 2012-11-15
|  |  | 1297674 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297675 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1297676 |  |  | Indiana Department of Transportation | 2015-08-05
|  |  | 1297677 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1297678 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297679 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297682 |  |  | Indiana Department of Transportation | 2016-08-10
|  |  | 1297683 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297694 | Clark |  | Jeffersonville | 2013-05-01 | CE
CN
|  |  | 1297695 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1297696 |  |  | Brownsburg | -339679.2083
|  |  | 1297697 |  | H W Lochner, Inc. | Indiana Department of Transportation | 2013-02-06
|  |  | 1297698 | Floyd |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1297699 | Perry |  | Indiana Department of Transportation | 2012-08-21 | PE
|  |  | 1297700 | Harrison |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297701 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1297702 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1297703 |  |  | Indiana Department of Transportation | 2013-12-11
|  |  | 1297704 | Various |  | Carroll County | 2013-05-23 | PE
|  |  | 1297705 | Blackford | Continental Mapping Consultants, LLC | Blackford County | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1297706 | LaPorte | Douglass Environmental Services, Inc. | La Porte | -339679.2083 | CN
|  |  | 1297707 | LaPorte |  | LaPorte County | -339679.2083 | CN
|  |  | 1297708 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1297709 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1297710 |  |  | MPO - Northwest | 2012-09-03
|  |  | 1297711 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297714 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297726 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1297740 | Carroll | Blood Hound, Inc. (former) | Delphi | 2015-02-04 | CE
CN
PE
|  |  | 1297741 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1297742 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297743 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297744 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 2013-12-11
|  |  | 1297745 | Carroll | Blood Hound, Inc. (former) | Delphi | 2015-02-04 | CE
CN
PE
|  |  | 1297746 | Carroll | Blood Hound, Inc. (former) | Delphi | 2014-02-12 | CE
CN
PE
|  |  | 1297747 | Carroll | Blood Hound, Inc. (former) | Delphi | 2015-09-02 | CE
CN
PE
RR
|  |  | 1297748 |  |  | Scott County | -339679.2083
|  |  | 1297749 |  |  | Scott County | -339679.2083
|  |  | 1297750 | Rush |  | Rush County | -339679.2083 | PE
|  |  | 1297751 | Greene |  | Greene County | -339679.2083 | PE
|  |  |  | Various |  | Greene County | -339679.2083 | PE
|  |  | 1297752 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297753 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2014-04-02 | CE
CN
PE
|  |  | 1297754 | Knox | Louis Joyner, Architect | Vincennes | 2016-10-05 | CE
CN
PE
ROW
RR
|  |  | 1297755 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2016-12-14 | CE
CN
|  |  | 1297756 | Bartholomew |  | Bartholomew County | 2017-03-01 | CE
CN
PE
|  |  | 1297759 |  | Louis Joyner, Architect | Vincennes | 2018-05-31
|  |  | 1297760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297761 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1297762 | Perry |  | Indiana Department of Transportation | 2013-03-06 | CE
CN
|  |  | 1297763 | Marion |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1297764 | Marion |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1297765 | Randolph |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1297766 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1297767 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  |  | Miami | Dodd Title Corporation | Indiana Department of Transportation | 2013-04-10 | CE
CN
|  |  | 1297768 | Marion |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1297769 | Madison | DKA Associates, Inc. | Indiana Department of Transportation | 2013-02-06 | CE
CN
PE
RR
|  |  | 1297770 | Hamilton |  | Hamilton County | -339679.2083 | PE
|  |  | 1297771 | Knox |  | Knox County | -339679.2083 | PE
|  |  | 1297772 |  |  | MPO - Columbus | -339679.2083
|  |  | 1297773 |  |  | MPO - Columbus | -339679.2083
|  |  | 1297774 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1297775 | Marion |  | Indianapolis | 2013-10-15 | PE
|  |  | 1297776 | Dearborn |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
[6 empty] | Indiana Department of Transportation | 2014-05-31
|  |  | 1297777 | Jefferson |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
[6 empty] | Indiana Department of Transportation | 2014-05-31
|  |  | 1297778 | Clark |  | Indiana Department of Transportation | 2014-05-31 | PE
|  |  |  | Floyd |  | Indiana Department of Transportation | 2014-05-31 | CN
|  |  | 1297779 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Floyd | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1297780 | Spencer |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
|  |  | 1297781 | Vanderburgh |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
|  |  | 1297782 | Vanderburgh |  | Indiana Department of Transportation | 2014-05-31 | CN
PE
|  |  | 1297783 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1297784 | Vanderburgh |  | Indiana Department of Transportation | 2014-04-02 | CN
|  |  |  | Various |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1297785 | Various | CGI | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1297786 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297787 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297788 | Various |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297789 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297790 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297791 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297792 | Various |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297793 | Various |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297794 | Clay |  | Indiana Department of Transportation | 2013-12-11 | CN
|  |  |  | Various |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297795 | Fountain |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
ROW
|  |  | 1297796 | Various | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297797 | Various |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1297798 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297802 | Perry |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1297803 | Various |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297804 | Allen |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297805 | Orange |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297808 | Perry |  | Indiana Department of Transportation | 2014-04-02 | CN
|  |  |  | Spencer |  | Indiana Department of Transportation | 2014-04-02 | CE
|  |  | 1297809 | Various |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1297812 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297813 | Various |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1297815 | Perry |  | Indiana Department of Transportation | 2014-04-02 | CE
|  |  |  | Spencer |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297821 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297822 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297823 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297824 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297825 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297826 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297827 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297828 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297829 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297830 | Martin |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297831 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297832 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297833 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297834 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297835 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297836 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297837 | Crawford |  | Indiana Department of Transportation | 2014-04-02 | CE
|  |  |  | Various |  | Indiana Department of Transportation | 2014-04-02 | CN
|  |  | 1297844 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297845 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297846 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297847 | Lake |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297848 | Lake |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297849 | Jasper |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297850 | Jasper |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297851 | Jasper |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297852 | Jasper |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297853 | Jasper |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1297854 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297855 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297856 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297857 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297858 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297859 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297860 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297861 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297862 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297863 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297864 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1297865 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297866 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1297867 | Henry |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297869 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297870 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297871 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297872 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1297873 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1297874 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297875 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297876 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1297877 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1297878 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297879 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297880 | Marion |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297881 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297882 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297883 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1297884 | Franklin | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2012-10-24 | CE
CN
|  |  |  | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2012-10-24 | CE
CN
|  |  | 1297885 | Monroe |  | Indiana Department of Transportation | 2019-05-31 | CE
CN
PE
ROW
RR
UT
|  |  |  | Morgan |  | Indiana Department of Transportation | 2019-05-31 | CN
PE
ROW
UT
|  |  | 1297886 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1297887 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1297888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297889 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2014-05-31
|  |  | 1297890 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297891 | Spencer |  | Indiana Department of Transportation | 2012-10-15 | CN
|  |  | 1297892 | Greene |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
|  |  | 1297893 | Monroe |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
|  |  | 1297894 | Monroe |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
|  |  | 1297896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297897 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1297898 | Scott |  | Scott County | -339679.2083 | PE
|  |  | 1297899 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1297900 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1297901 | Spencer |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297902 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297903 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297904 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297905 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297906 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297907 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297916 | Marion |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1297917 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  |  | Marion | CPS Acquisitions, LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  | 1297918 | Various |  | Bedford | 2015-07-27 | CN
|  |  | 1297919 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1297923 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1297925 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1297926 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2013-03-06
|  |  | 1297927 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2013-04-03
|  |  | 1297928 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1297929 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1297930 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2013-12-11 | CE
CN
RR
|  |  | 1297931 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2013-12-11 | CE
CN
RR
|  |  | 1297932 | Kosciusko |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1297933 | Kosciusko |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
RR
|  |  | 1297934 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1297935 | Whitley |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1297936 | Morgan |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1297937 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297938 |  | CGI | Indiana Department of Transportation | 2013-02-06
|  |  | 1297939 | Henry |  | Henry County | 2014-05-31 | PE
|  |  | 1297940 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 1297941 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297942 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297943 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297944 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297945 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297946 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297947 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1297948 | Various |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1297949 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297950 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297951 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1297952 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1297953 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297954 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1297955 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297956 | Huntington |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1297957 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297958 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297959 | Kosciusko |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1297960 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297961 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297962 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297963 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297964 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1297965 | Miami |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1297976 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297977 | Miami |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
ROW
|  |  | 1297978 | Miami |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
UT
|  |  | 1297979 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1297980 | Wells |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1297981 |  |  | Vincennes | 2013-02-06
|  |  | 1297982 | Ripley |  | Versailles | 2012-11-08 | PE
|  |  | 1297983 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
PL
|  |  | 1297984 |  | Eel River Abstract | Indiana Department of Transportation | -339679.2083
|  |  | 1297985 | Harrison |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  |  | Various |  | Indiana Department of Transportation | 2017-04-05 | PE
|  |  | 1297986 |  | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1297987 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 1297988 | Howard |  | Indiana Department of Transportation | 2019-01-16 | CE
PE
|  |  |  | Miami |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1297989 | Jefferson |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1297990 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1297991 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1298003 | Adams | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1298004 | Dearborn |  | Aurora | 2014-05-31 | PE
|  |  | 1298005 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298006 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298007 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298008 |  | Midwest Archaeological Research Services, Inc. | Zionsville | -339679.2083
|  |  | 1298009 | Vigo |  | Vigo County | -339679.2083 | PE
|  |  | 1298010 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298011 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298014 | LaGrange |  | LaGrange County | -339679.2083 | PE
|  |  | 1298015 | Adams |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1298016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298017 | Dearborn |  | Indiana Department of Transportation | 2015-05-31 | CN
PE
|  |  | 1298018 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
ROW
|  |  | 1298019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298022 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298023 | Miami |  | Indiana Department of Transportation | 2020-02-05 | PE
ROW
|  |  | 1298024 |  |  | Clark County | 2017-05-31
|  |  | 1298030 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1298031 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1298033 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298035 | Hamilton | CPS Acquisitions, LLC | Hamilton County | 2016-03-02 | CE
CN
PE
ROW
UT
|  |  | 1298036 |  | Collier Transport Inc. | Collegeville | -339679.2083
|  |  | 1298037 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298038 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298039 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298041 | St. Joseph |  | Indiana Department of Transportation | 2014-05-30 | RR
|  |  | 1298042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298044 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298046 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298047 | Marion |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1298048 | Marion |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1298049 | Marion |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1298050 | Various |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1298055 | Allen |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1298057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298058 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298059 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298063 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298064 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298065 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298068 | LaPorte |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1298069 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298070 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1298071 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298072 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298073 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298077 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | -339679.2083
|  |  | 1298078 | Carroll |  | Indiana Department of Transportation | 2014-03-03 | PE
|  |  | 1298079 | Clark |  | Jeffersonville | 2013-05-01 | CE
CN
|  |  | 1298080 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298081 |  |  | MPO - Evansville | -339679.2083
|  |  | 1298082 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1298083 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1298084 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1298085 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298086 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298087 | Marion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1298088 |  | HE-BFS, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298089 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1298090 | Grant |  | Grant County | 2015-04-07 | PE
|  |  | 1298091 |  | Home Guide Realty Services | Indiana Department of Transportation | -339679.2083
|  |  | 1298092 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298093 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298094 | Boone |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1298100 |  | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298101 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298102 | Boone |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1298103 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298104 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1298105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298106 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1298107 | Howard |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1298108 | Wayne | Appraisal Office of Central Indiana | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
UT
|  |  | 1298109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298115 | Bartholomew |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1298116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298118 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298120 | Henry |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1298123 | Jackson |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1298125 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1298128 | LaPorte |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1298129 | Jackson |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1298131 | Pulaski | McCormick Engineering, LLC | Winamac | 2014-11-13 | CE
CN
PE
|  |  | 1298132 | Cass | Eco Logic, LLC | Logansport | 2015-01-14 | CE
CN
PE
|  |  | 1298134 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1298135 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298136 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298139 | Hamilton | Another Test Company | Indiana Department of Transportation | 2012-12-19 | CE
CN
UT
|  |  | 1298140 | Hamilton |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
|  |  | 1298141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298142 | Hamilton |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
|  |  | 1298143 | Hamilton |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
|  |  | 1298144 |  | McCormick Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298145 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298146 | Howard |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1298147 | Jackson |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1298148 | Hamilton |  | Indiana Department of Transportation | 2012-12-19 | CE
CN
|  |  | 1298149 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298150 | Jay |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1298151 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298152 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298153 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1298154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298155 |  |  | Indiana Department of Transportation | 2013-03-06
|  |  | 1298156 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298157 | Knox |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1298158 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1298159 | Marion |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1298160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298161 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298164 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298167 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298168 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298169 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298170 | St. Joseph |  | Indiana Department of Transportation | 2013-04-10 | CE
UT
|  |  | 1298171 | Jackson |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
PE
|  |  | 1298172 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298173 | Porter | Marine Solutions, Inc. | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1298174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298175 | Harrison |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1298176 | Pike |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
ROW
UT
|  |  | 1298177 | Fountain |  | Attica | 2015-07-08 | CE
CN
PE
|  |  | 1298178 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298179 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298180 | Pike |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
ROW
|  |  | 1298181 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298182 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298183 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298184 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298185 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298186 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298187 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298188 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298191 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1298192 | Henry |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298193 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1298194 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298195 | Pike |  | Indiana Department of Transportation | 2020-01-15 | ROW
|  |  | 1298196 | Harrison |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1298197 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 1298198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298199 | Daviess |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
|  |  | 1298200 | Martin |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298201 | Daviess |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1298202 | Dubois |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1298203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298204 | Harrison |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1298205 | Spencer |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1298206 | Jefferson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298207 | Hendricks |  | Danville | 2013-05-31 | PE
|  |  | 1298208 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298211 | Harrison |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1298212 | Lawrence |  | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298221 | Lawrence |  | Indiana Department of Transportation | 2018-02-07 | PE
|  |  | 1298223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298224 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1298225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298226 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298227 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298228 | Delaware |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1298229 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298230 | Marion | Jeffrey S. Juday | Indiana Department of Transportation | 2017-09-13 | CN
|  |  |  | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1298231 | LaGrange | Duesler Realty House | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
UT
|  |  | 1298232 | Steuben | ABt SRBI | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1298233 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298234 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1298235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298237 |  |  | MPO - Evansville | -339679.2083
|  |  | 1298238 |  |  | MPO - Evansville | -339679.2083
|  |  | 1298239 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1298240 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1298241 |  |  | MPO - Bloomington | 2012-11-25
|  |  | 1298242 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1298243 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1298244 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298245 | Sullivan |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
ROW
UT
|  |  | 1298246 | Gibson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1298247 | Harrison |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1298248 | Harrison |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1298249 | Hendricks | Bella Villa Realtors, LLC | Danville | 2016-03-02 | CE
CN
PE
|  |  | 1298250 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298251 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298252 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298253 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298254 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298255 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298256 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298257 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298258 | Dearborn |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
PE
|  |  | 1298259 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2014-08-06 | CE
CN
PE
|  |  | 1298260 |  | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | -339679.2083
|  |  | 1298261 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298262 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298263 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298264 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298265 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298266 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298267 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298268 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298269 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298270 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298271 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298272 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298273 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298274 | Jackson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
UT
|  |  | 1298275 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1298276 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298277 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298278 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298279 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298280 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298281 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298282 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1298283 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298284 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298285 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298286 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298287 | Washington |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
UT
|  |  | 1298288 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298289 | Dekalb | Quantum Spatial, Inc. | Auburn | 2015-04-01 | CE
CN
PE
|  |  | 1298290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298296 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1298302 | Porter |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
UT
|  |  | 1298306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298309 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1298310 | Dekalb | American Engineers, Inc. | Butler | -339679.2083 | PE
|  |  | 1298311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298312 | Porter |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1298313 | LaPorte |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1298314 | Clinton | Iteris, Inc. | Rossville | -339679.2083 | PE
|  |  | 1298315 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298316 | Porter |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1298317 | Various |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1298318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298319 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1298320 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298321 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298322 | Jackson |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
ROW
|  |  | 1298323 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298324 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-02-20 | CE
CN
|  |  | 1298325 |  |  | Indiana Department of Transportation | 2013-09-11
|  |  | 1298326 | Floyd |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1298327 | Floyd |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1298330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298332 | Vermillion |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1298333 | Hendricks |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1298334 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298335 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298336 | Jackson |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
ROW
|  |  | 1298337 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298338 | Boone |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1298339 | Bartholomew |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
UT
|  |  | 1298340 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298341 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298342 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298343 | Clay |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1298344 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298345 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 1298346 | Clay |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1298347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298348 | Clay |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1298349 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298350 | Montgomery |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1298351 | Montgomery |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1298352 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298353 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298354 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298355 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298356 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298357 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298365 | Hendricks |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1298368 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298371 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298372 | Montgomery |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1298373 | Jennings |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
ROW
|  |  | 1298374 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298375 | Hendricks |  | Indiana Department of Transportation | 2018-08-29 | CE
CN
PE
ROW
|  |  | 1298376 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298377 | Clinton |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1298378 | Parke |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
ROW
|  |  | 1298379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298380 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298381 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1298382 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298383 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298384 | Warren |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1298385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298386 | Boone |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1298387 | Tippecanoe |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1298388 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298389 | Vermillion |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1298390 | Vermillion |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1298391 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298392 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 1298393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298394 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1298395 |  | Donohue & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298396 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298397 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
RR
|  |  | 1298398 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
ROW
|  |  | 1298399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298401 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298402 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
RR
|  |  | 1298403 | Lawrence |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
UT
|  |  | 1298404 | LaPorte |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1298405 |  | HDR Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298406 | Lawrence |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
UT
|  |  | 1298407 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298408 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298409 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298411 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298412 | Marshall |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1298414 | Ripley |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298417 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298418 | Marshall |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1298419 | Tippecanoe |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1298423 | Montgomery |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1298424 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298425 | Ripley |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298426 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298427 | Ripley |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298428 | Pulaski |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1298429 | Warren |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1298430 | Ripley |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298431 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298432 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1298433 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298434 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298435 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298437 | Brown |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1298438 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1298440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298443 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1298444 | Lake |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
RR
|  |  | 1298445 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1298446 | Warren |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1298447 | Washington |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298448 | Lake |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1298449 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298450 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298451 | Morgan |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1298454 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
ROW
|  |  | 1298459 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298465 | White |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1298466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298467 | White |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1298468 | Fountain |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
ROW
|  |  | 1298469 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298470 | White |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1298471 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298472 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
ROW
|  |  | 1298473 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298474 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298478 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
PE
|  |  | 1298479 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298480 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298481 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298482 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298483 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298484 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298485 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298486 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298487 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1298488 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298493 | Parke |  | Indiana Department of Transportation | 2018-06-20 | CE
CN
PE
ROW
|  |  | 1298494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298495 | Boone |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
ROW
|  |  | 1298496 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298497 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298498 | Hamilton |  | Westfield | 2015-07-16 | PE
|  |  | 1298499 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298501 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298502 | Greene |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1298503 | Clay |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1298504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298505 | Vigo |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
UT
|  |  | 1298506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298507 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1298510 | Posey | GRL Engineers, Inc. | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
RR
|  |  | 1298511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298512 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298513 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298515 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298516 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298520 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298521 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298522 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1298523 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298524 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298525 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298526 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298527 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298528 |  |  | Indiana Department of Natural Resources | 2014-01-15
|  |  | 1298529 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1298530 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1298531 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1298532 |  |  | Indiana Department of Natural Resources | 2014-01-15
|  |  | 1298533 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1298534 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1298535 |  |  | Indiana Department of Natural Resources | 2013-12-11
|  |  | 1298536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298539 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298541 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1298542 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1298543 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1298544 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1298545 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1298546 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-02-15 | CE
CN
PE
|  |  | 1298547 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1298548 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1298549 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298550 | Daviess |  | Daviess County | 2015-02-04 | CE
CN
|  |  | 1298551 | Fulton |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1298552 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298553 | White |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1298554 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1298555 | Marion | DCD Consulting LLC | Indianapolis | 2014-04-25 | PE
|  |  | 1298556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298559 | Marshall |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1298562 | LaPorte |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1298565 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298566 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
ROW
|  |  | 1298567 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1298568 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298578 | St. Joseph |  | St. Joseph County | 2017-12-13 | CE
CN
ROW
|  |  | 1298579 | St. Joseph |  | St. Joseph County | 2016-02-17 | CE
CN
RR
|  |  | 1298580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298581 | Dearborn |  | Indiana Department of Transportation | 2018-05-16 | CE
CN
PE
ROW
UT
|  |  | 1298582 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298583 | Jefferson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1298584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298585 | Ohio |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1298586 | Dearborn |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1298587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298588 | Dearborn |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1298593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298597 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298598 | Delaware |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1298599 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298607 | Parke |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1298608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298609 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298611 |  | CDM Smith, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298612 |  | H&H Associates, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298613 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298617 | Dearborn |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1298619 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298621 | Lake |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
ROW
|  |  | 1298622 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298624 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298625 |  | Indiana University | Indiana Department of Transportation | -339679.2083
|  |  | 1298626 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298627 |  | Clayton L. Roots | Indiana Department of Transportation | -339679.2083
|  |  | 1298628 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1298629 | Clark |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1298630 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298631 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298632 | Jennings |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1298633 | Jackson |  | Indiana Department of Transportation | 2023-10-12 | PE
ROW
|  |  | 1298634 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298635 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298636 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298637 |  | Clyde L. Hawkins | Indiana Department of Transportation | -339679.2083
|  |  | 1298638 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298639 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298640 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298641 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1298642 | Jackson |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
ROW
|  |  | 1298643 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298644 |  | ETC Institute | Indiana Department of Transportation | -339679.2083
|  |  | 1298645 | Marion | DCD Consulting LLC | Indianapolis | 2020-07-08 | CE
CN
PE
|  |  | 1298647 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298648 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2013-05-31 | CN
|  |  | 1298649 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298650 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1298651 | Marion | DCD Consulting LLC | Indianapolis | 2016-05-31 | PE
ROW
|  |  | 1298657 |  | Martinez Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1298658 |  | Martinez Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1298659 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1298660 | Boone |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1298664 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298665 | Dekalb | Mader Design, LLC | Waterloo | 2015-02-04 | CE
CN
PE
|  |  | 1298666 | Steuben | ABt SRBI | Angola | 2015-01-14 | CE
CN
PE
|  |  | 1298667 | Madison | CE Solutions, Inc. | Elwood | 2015-09-02 | CE
CN
PE
|  |  | 1298668 | Madison |  | Alexandria | 2015-02-04 | CE
CN
PE
ROW
|  |  | 1298669 | Vigo | Bayswater Company, LLC | Vigo County | 2016-03-02 | CE
CN
PE
RR
|  |  | 1298670 | Porter | Leitner and Associates, Inc. | Valparaiso | 2019-01-16 | PE
ROW
RR
|  |  | 1298671 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1298672 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298673 | Gibson | III FFC | Princeton | 2015-03-18 | CE
CN
PE
|  |  | 1298674 | Gibson | III FFC | Princeton | -339679.2083 | PE
|  |  | 1298675 | Gibson | III FFC | Princeton | 2015-03-18 | CE
CN
PE
|  |  | 1298676 | Gibson | III FFC | Princeton | 2015-03-18 | CE
CN
PE
|  |  | 1298677 | Gibson | III FFC | Princeton | 2015-03-18 | CE
CN
PE
|  |  | 1298678 | Gibson | III FFC | Princeton | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1298679 |  |  | Indiana Department of Transportation | 2015-02-18
|  |  | 1298680 | Lake | Consolidated Test Company | Hammond | 2014-04-09 | CE
CN
|  |  | 1298681 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2013-04-03
|  |  | 1298682 | Hamilton |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1298683 | Hamilton |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
|  |  | 1298684 | Hamilton |  | Indiana Department of Transportation | 2013-04-03 | CE
CN
UT
|  |  | 1298685 | Hamilton |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1298686 | Hamilton |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1298687 | Hamilton |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1298688 | Hamilton |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1298689 | Vigo | Bayswater Company, LLC | Terre Haute | 2016-11-16 | CE
CN
PE
ROW
|  |  | 1298690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298691 |  |  | Brown County | 2016-12-14
|  |  | 1298692 |  |  | Brown County | -339679.2083
|  |  | 1298693 |  |  | Brown County | 2018-01-18
|  |  | 1298694 |  |  | Indiana Department of Transportation | 2013-04-03
|  |  | 1298695 | Daviess |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
RR
|  |  | 1298696 | Johnson |  | Johnson County | 2014-09-10 | CE
CN
|  |  | 1298697 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2014-03-05
|  |  | 1298698 | Warrick |  | Indiana Department of Natural Resources | 2013-05-31 | CN
|  |  | 1298699 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1298700 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 1298701 | Wells |  | Wells County | 2014-05-31 | PE
|  |  | 1382003 |  | Another Test Company | Amo | -339679.2083
|  |  | 1382004 | Dearborn |  | Dearborn County | 2014-08-06 | CE
CN
PE
ROW
|  |  | 1382005 |  | KERAMIDA Environmental, Inc. | Indiana Department of Transportation | 2013-09-24
|  |  | 1382006 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382007 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382008 | Marion |  | Indiana State Agencies | 2014-03-19 | CE
CN
PE
|  |  | 1382009 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382010 | Porter | Huff & Huff, Inc. | Portage | 2023-07-13 | PE
|  |  | 1382011 |  |  | Indiana Department of Transportation | 2013-08-07
|  |  | 1382012 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 1382013 | Henry |  | Indiana Department of Transportation | 2013-05-01 | CE
CN
|  |  | 1382014 | Daviess |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1382015 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1382016 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1382017 | Vigo |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
ROW
|  |  | 1382018 | Blackford |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  |  | Grant |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1382019 | Allen |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1382020 | LaGrange |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
ROW
|  |  | 1382021 | Blackford |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1382022 | Warrick | Appraisal Specialists, Inc. | Warrick County | 2013-01-23 | PE
|  |  | 1382023 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1382024 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382025 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382026 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382027 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382028 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382029 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382030 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382031 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382032 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382033 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382034 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382035 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382036 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382037 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382038 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382039 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382040 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382041 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382042 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382043 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382044 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382045 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382046 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382047 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382048 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382049 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382050 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382051 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382052 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382053 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382054 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382055 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382056 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1382057 | Clark | Lee & Ryan Environmental Consulting, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
ROW
UT
|  |  | 1382058 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382059 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382060 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382061 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382062 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382063 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382064 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382065 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382066 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382067 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382068 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2013-09-11 | CE
CN
PE
|  |  | 1382069 | Hancock |  | Cumberland | 2013-10-09 | CE
CN
|  |  | 1382070 | Marion | DCD Consulting LLC | Indianapolis | 2016-11-16 | CE
CN
|  |  | 1382071 | Dubois |  | Dubois County | -339679.2083 | PE
|  |  | 1382072 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1382073 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1382074 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1382075 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1382076 | Lake |  | Gary | 2013-05-31 | PE
|  |  | 1382077 | Lake |  | Gary | 2013-05-31 | PE
|  |  | 1382078 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2013-08-07 | CE
CN
PE
|  |  | 1382079 |  |  | Indiana Department of Transportation | 2013-05-03
|  |  | 1382080 | Shelby |  | Shelby County | -339679.2083 | PE
|  |  |  | Various |  | Shelby County | -339679.2083 | PE
|  |  | 1382081 | Wayne |  | Wayne County | -339679.2083 | PE
|  |  | 1382082 | Jay |  | Jay County | -339679.2083 | PE
|  |  | 1382083 | Hancock |  | Hancock County | -339679.2083 | PE
|  |  | 1382084 | Marion |  | Indianapolis | -339679.2083 | PE
|  |  | 1382085 | Clinton |  | Clinton County | -339679.2083 | PE
|  |  | 1382086 | Fountain |  | Fountain County | -339679.2083 | PE
|  |  | 1382087 | Montgomery |  | Montgomery County | -339679.2083 | PE
|  |  | 1382088 | Vermillion |  | Vermillion County | -339679.2083 | PE
|  |  | 1382089 |  |  | Vigo County | -339679.2083
|  |  | 1382090 | Lake |  | Lake County | 2015-05-31 | PE
|  |  | 1382091 | Starke |  | Starke County | -339679.2083 | PE
|  |  | 1382092 | Porter |  | Porter County | -339679.2083 | PE
|  |  | 1382093 | Pulaski |  | Pulaski County | -339679.2083 | PE
|  |  | 1382094 | Marshall |  | Marshall County | -339679.2083 | PE
|  |  | 1382095 | Fulton |  | Fulton County | -339679.2083 | PE
|  |  | 1382096 | Jasper |  | Jasper County | -339679.2083 | PE
|  |  | 1382097 | Newton |  | Newton County | -339679.2083 | PE
|  |  | 1382098 | White |  | White County | -339679.2083 | PE
|  |  | 1382099 | Adams |  | Adams County | -339679.2083 | CN
PE
|  |  | 1382100 | Allen |  | Allen County | -339679.2083 | PE
|  |  | 1382101 | Dekalb |  | Dekalb County | -339679.2083 | PE
|  |  | 1382102 | Elkhart |  | Elkhart County | -339679.2083 | PE
|  |  | 1382103 | Huntington |  | Huntington County | -339679.2083 | CN
PE
|  |  |  | Various |  | Huntington County | -339679.2083 | PE
|  |  | 1382104 | Kosciusko |  | Kosciusko County | -339679.2083 | PE
|  |  | 1382105 | Bartholomew |  | Bartholomew County | -339679.2083 | PE
|  |  | 1382106 | Clark |  | Clark County | -339679.2083 | PE
|  |  | 1382107 | Dearborn |  | Dearborn County | -339679.2083 | PE
|  |  | 1382108 |  |  | Decatur County | -339679.2083
|  |  | 1382109 | Floyd |  | Floyd County | -339679.2083 | PE
|  |  | 1382110 | Franklin |  | Franklin County | -339679.2083 | PE
|  |  | 1382111 | Noble |  | Noble County | -339679.2083 | PE
|  |  | 1382112 | Harrison |  | Harrison County | -339679.2083 | PE
|  |  | 1382113 | Steuben |  | Steuben County | 2016-05-31 | PE
|  |  | 1382114 | Jackson |  | Jackson County | -339679.2083 | PE
|  |  | 1382115 | Wabash |  | Wabash County | -339679.2083 | PE
|  |  | 1382116 | Whitley |  | Whitley County | 2015-05-31 | PE
|  |  | 1382117 |  |  | Jefferson County | -339679.2083
|  |  | 1382118 |  |  | Shelbyville | 2012-07-10
|  |  | 1382119 | Jennings |  | Jennings County | -339679.2083 | PE
|  |  | 1382120 | Johnson |  | Johnson County | -339679.2083 | PE
|  |  | 1382121 | Monroe |  | Monroe County | -339679.2083 | PE
|  |  | 1382122 | Morgan |  | Morgan County | -339679.2083 | PE
|  |  | 1382123 | Ohio |  | Ohio County | -339679.2083 | PE
|  |  | 1382124 | Ripley |  | Ripley County | -339679.2083 | PE
|  |  | 1382125 | Switzerland |  | Switzerland County | -339679.2083 | PE
|  |  | 1382126 | Washington |  | Washington County | -339679.2083 | PE
|  |  | 1382127 | Jefferson |  | Jefferson County | -339679.2083 | PE
|  |  | 1382128 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  |  | Wabash | Holloway Engineering, LLC | Indiana Department of Transportation | 2015-02-04 | CN
|  |  | 1382129 | Blackford |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382130 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382131 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382132 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382133 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382134 | Harrison |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382135 | Bartholomew |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382136 |  |  | MPO - Northwest | 2013-02-23
|  |  | 1382137 | Jennings |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382138 |  |  | MPO - Northwest | 2013-02-23
|  |  | 1382139 | Jennings |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382140 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382141 |  |  | MPO - Northwest | 2013-02-23
|  |  | 1382142 | Jennings |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382143 |  |  | MPO - Northwest | 2013-02-23
|  |  | 1382144 | Bartholomew |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382145 |  |  | MPO - Northwest | 2013-02-23
|  |  | 1382146 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382148 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382149 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382150 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382151 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382152 | Crawford |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382153 | Crawford |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382154 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382155 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382156 | Lawrence |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382157 | Monroe |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1382158 | Lawrence |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382159 | Adams | Bidinfo | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382160 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382161 | Allen |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382162 | Wabash |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382163 | Adams |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382164 | Miami |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382165 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382166 | Huntington |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382167 | LaGrange |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1382168 |  |  | Daviess County | 2013-08-26
|  |  | 1382169 | Allen |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1382170 | Allen |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1382171 | Allen |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1382172 | Allen |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1382173 | Allen |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1382174 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382175 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382176 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382177 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382178 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382179 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382180 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382181 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382182 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382183 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382184 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382185 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382186 | Elkhart |  | Indiana Department of Transportation | 2014-12-10 | CE
CN
|  |  | 1382187 | Martin |  | Martin County | -339679.2083 | CN
PE
|  |  | 1382188 | Posey |  | Posey County | -339679.2083 | PE
|  |  | 1382189 | Spencer |  | Spencer County | -339679.2083 | PE
|  |  | 1382190 | Daviess |  | Daviess County | -339679.2083 | PE
|  |  | 1382191 | Lawrence |  | Lawrence County | -339679.2083 | PE
|  |  |  | Various |  | Lawrence County | -339679.2083 | PE
|  |  | 1382192 | Pike |  | Pike County | -339679.2083 | PE
|  |  | 1382193 | Gibson |  | Gibson County | -339679.2083 | PE
|  |  | 1382194 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382195 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382196 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382197 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382198 | Decatur |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382199 | Ripley | Lonco, Inc. | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382200 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2014-07-09 | CE
CN
|  |  | 1382201 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2017-02-08 | CN
|  |  | 1382202 |  |  | Rushville | 2013-07-10
|  |  | 1382203 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1382204 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1382205 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2013-08-01 | CE
CN
PE
|  |  | 1382206 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  |  | Madison |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1382207 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1382208 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1382209 | Porter |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382210 | Knox |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382211 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382212 | Henry |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
ROW
|  |  | 1382213 | Hancock |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1382214 | Henry |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1382215 | Henry |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
ROW
|  |  | 1382216 |  |  | Indiana Department of Transportation | 2013-12-11
|  |  | 1382217 | Vanderburgh |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1382218 |  |  | Indiana Department of Transportation | 2013-09-11
|  |  | 1382219 | LaPorte |  | LaPorte County | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1382220 |  |  | LaPorte County | -339679.2083
|  |  | 1382221 | Sullivan |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382222 | Sullivan |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382223 | Sullivan |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382224 | Sullivan |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382226 | Greene | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382227 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382228 | Greene |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382229 | Lawrence |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382230 | Knox |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382231 | Lawrence |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382235 | Orange |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382236 | Orange |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382237 | Crawford |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382238 | Crawford |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382239 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382240 | Orange |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382241 | Perry |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382242 | Spencer |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382243 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1382244 | Dubois |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382245 | Dubois |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382246 | Gibson | Copperhead Environmental Consulting | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382247 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382248 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382249 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382251 | Vanderburgh | CGI | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382254 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382255 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382258 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382259 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382264 | Knox |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382265 | Knox |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382266 | Crawford |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382267 | Crawford |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382268 | Crawford |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382269 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1382270 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1382271 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1382272 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1382273 |  |  | Indiana Department of Transportation | 2015-04-01
|  |  | 1382274 | Perry |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382275 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2019-05-31 | PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1382276 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382277 |  | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083
|  |  | 1382278 |  |  | MPO - Northwest | 2013-03-12
|  |  | 1382279 |  |  | MPO - Northwest | 2013-03-12
|  |  | 1382280 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382281 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382282 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382283 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382284 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382285 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382286 | Vermillion |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382287 | Vermillion |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382288 | Warren |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382289 | Warren |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382290 | Fountain |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382291 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1382292 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1382293 | Fountain |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382294 | Fountain |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382295 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382296 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382297 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382298 | Clay |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382299 | Clay |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382300 | Clay |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382302 | Putnam |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382303 | Putnam |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382304 | Morgan |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382305 | Tippecanoe |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382306 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382307 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1382308 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382309 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382310 |  |  | Indiana Department of Transportation | 2013-05-01
|  |  | 1382311 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1382312 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382313 | Tippecanoe |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1382314 | Tippecanoe |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1382315 | Wayne |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1382316 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2015-05-31
|  |  | 1382317 | Tipton |  | Indiana Department of Transportation | 2015-11-17 | CE
CN
PE
ROW
|  |  | 1382318 | Tipton |  | Indiana Department of Transportation | 2015-11-17 | CE
CN
|  |  | 1382319 | Tipton |  | Indiana Department of Transportation | 2015-11-17 | CE
CN
|  |  | 1382320 | Dubois |  | Huntingburg | 2017-02-08 | CE
CN
|  |  | 1382321 |  |  | Indiana Department of Transportation | 2013-07-10
|  |  | 1382324 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1382325 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382326 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382327 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1382328 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382329 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382330 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382331 | Lake | Consolidated Test Company | Whiting | 2014-04-09 | CE
CN
|  |  | 1382332 | Delaware |  | Delaware County | 2017-01-19 | CE
CN
PE
|  |  | 1382333 |  |  | Indiana Department of Transportation | 2013-09-11
|  |  | 1382334 | St. Joseph |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1382335 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382336 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382337 | Delaware |  | Indiana Department of Transportation | 2013-07-10 | CE
CN
|  |  | 1382338 | Decatur |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382339 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1382340 | Jennings |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
|  |  | 1382341 | Jennings |  | Indiana Department of Transportation | 2013-05-23 | CE
CN
|  |  | 1382342 |  |  | Indiana Department of Transportation | 2013-07-10
|  |  | 1382343 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382344 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382345 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1382346 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382347 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382348 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382349 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382350 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382351 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382352 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382353 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382354 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382355 |  |  | Pendleton | -339679.2083
|  |  | 1382356 |  | A & Z Engineering, LLC | Alfordsville | -339679.2083
|  |  | 1382357 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382359 | Noble |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1382360 | Kosciusko |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382361 |  | KERAMIDA Environmental, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1382366 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
ROW
|  |  | 1382367 | Vigo |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1382368 | Vigo |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1382369 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1382370 | Vigo |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1382371 | Vigo |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1382372 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382373 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382374 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382375 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382376 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382377 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382378 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382379 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382380 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382381 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382382 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382383 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382384 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382385 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382386 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1382387 | Jennings |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1382388 | Vigo |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
UT
|  |  | 1382389 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2014-03-05
|  |  | 1382390 |  |  | Clark County | 2013-04-09
|  |  | 1382391 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382392 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382396 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382397 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382398 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382399 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382400 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382401 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382402 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382404 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382405 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382407 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382408 | Starke |  | Indiana Department of Natural Resources | 2017-05-31 | PE
|  |  | 1382409 | LaPorte |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1382410 |  |  | Indiana Department of Transportation | 2013-12-11
|  |  | 1382411 | LaPorte |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  |  | Starke |  | Indiana Department of Transportation | 2013-05-31 | PE
|  |  | 1382412 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1382413 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382414 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2014-05-21 | CE
CN
|  |  | 1382415 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382416 |  |  | Bloomington | -339679.2083
|  |  | 1382417 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382418 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382419 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382421 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382422 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382423 | Dekalb |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382424 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382425 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382426 |  |  | Indiana Department of Transportation | 2015-05-08
|  |  | 1382427 |  |  | Bloomington | -339679.2083
|  |  | 1382428 | Jennings |  | Indiana Department of Transportation | 2015-05-08 | CE
CN
|  |  | 1382429 | Monroe |  | Bloomington | 2016-03-02 | CE
CN
PE
|  |  | 1382430 | Jennings |  | North Vernon | 2015-05-08 | CE
CN
|  |  | 1382431 | Monroe |  | Monroe County | 2016-04-06 | CE
CN
PE
ROW
|  |  | 1382432 |  |  | Indiana Department of Transportation | 2014-01-15
|  |  | 1382433 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2014-02-05
|  |  | 1382434 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1382435 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382436 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382437 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382438 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382439 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382440 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382441 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382442 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382443 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382444 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382446 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382447 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382448 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382450 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382451 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382452 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382453 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382454 | Boone | Martinez Corporation | Indiana Department of Transportation | 2013-08-28 | CE
CN
ROW
UT
|  |  | 1382455 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382456 | Allen |  | Indiana Department of Transportation | 2013-04-22 | CN
|  |  | 1382457 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382458 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382459 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382460 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1382461 |  |  | Indiana Department of Transportation | 2013-05-31
|  |  | 1382462 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2016-05-31
|  |  | 1382463 |  |  | Indiana Department of Transportation | 2013-10-09
|  |  | 1382464 |  |  | Indiana Department of Transportation | 2013-10-09
|  |  | 1382465 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  |  | Noble | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2014-05-08 | CE
|  |  | 1382466 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382467 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382468 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382469 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382470 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382471 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382472 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382473 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1382474 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382475 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382476 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382477 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382478 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382479 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382480 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382481 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1382482 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382483 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1382484 | Dearborn |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2013-08-07 | CE
CN
|  |  | 1382485 | Jackson |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  |  | Lawrence |  | Indiana Department of Transportation | 2013-10-09 | CN
|  |  | 1382486 | Jefferson |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  |  | Scott |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1382487 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382488 | Harrison | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1382489 | Harrison |  | Indiana Department of Transportation | 2013-11-06 | CE
CN
|  |  | 1382490 | Marion | DCD Consulting LLC | MPO - Indianapolis | 2013-08-01 | CE
CN
UT
|  |  | 1382491 | Allen |  | Indiana Department of Transportation | 2014-05-31 | CN
|  |  | 1382492 | Allen |  | Allen County | 2021-03-10 | CE
CN
ROW
|  |  | 1382493 | Allen |  | Allen County | 2016-11-30 | CE
CN
ROW
|  |  | 1382494 | Marion |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
ROW
UT
|  |  | 1382495 | Marion | DCD Consulting LLC | MPO - Indianapolis | 2013-08-01 | CE
CN
|  |  | 1382496 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2029-03-14
|  |  | 1382497 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1382498 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1382499 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382500 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382501 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382502 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382503 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382504 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382505 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382506 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382507 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382508 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382509 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1382510 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382511 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382512 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382513 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382514 |  |  | Bloomington Public Transportation Corp | 2013-05-06
|  |  | 1382515 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1382516 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1382517 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1382518 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1382519 |  |  | Bloomington Public Transportation Corp | 2013-05-06
|  |  | 1382520 |  |  | Indianapolis | 2014-03-05
|  |  | 1382521 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
|  |  | 1382522 |  |  | St. John | 2014-02-05
|  |  | 1382523 | Knox | Fosse & Associates Architects, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
UT
|  |  | 1382524 | Dubois |  | Huntingburg | 2017-02-08 | CE
CN
PE
ROW
RR
|  |  | 1382525 | Clinton |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2013-09-11 | CE
CN
|  |  | 1382526 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382527 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 1382528 | Jennings |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1382529 | Clark |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1382530 | Clark |  | Indiana Department of Transportation | 2014-05-31 | PE
|  |  | 1382531 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1382532 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382533 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382534 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382535 | Orange |  | Orange County | -339679.2083 | PE
|  |  | 1382536 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382537 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382538 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1382539 | Vanderburgh | CGI | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1382540 | Gibson | III FFC | Princeton | 2014-03-05 | CE
CN
|  |  | 1382541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382542 | Knox |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1382543 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382544 | Vigo |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1382545 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382546 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382547 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382548 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382549 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382550 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382551 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382552 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382553 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382554 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382555 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382556 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382557 |  |  | Indiana Department of Transportation | 2007-10-05
|  |  | 1382558 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382559 | Morgan |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382560 |  |  | Indiana Department of Transportation | 2013-11-06
|  |  | 1382561 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1382562 | Jackson |  | Indiana Department of Transportation | 2019-11-14 | PE
ROW
|  |  | 1382563 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1382564 |  |  | Indiana Department of Transportation | 2013-10-09
|  |  | 1382565 | Monroe |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382566 | Monroe |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382567 | Monroe |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1382568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382569 | Morgan |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382570 | Morgan |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1382571 | Morgan |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1382572 | Morgan |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1382573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382574 | Morgan |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1382575 | Monroe |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1382576 |  |  | Indiana Department of Transportation | 2008-05-30
|  |  | 1382577 | Monroe |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1382578 | Monroe |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1382579 | Monroe |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1382580 | Greene |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1382581 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382582 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382583 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382585 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382586 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382587 | Clay |  | Clay County | -339679.2083 | PE
|  |  | 1382588 | Hendricks |  | Hendricks County | -339679.2083 | PE
|  |  | 1382589 | Owen |  | Owen County | -339679.2083 | PE
|  |  |  | Various |  | Owen County | -339679.2083 | PE
|  |  | 1382590 | Putnam |  | Putnam County | -339679.2083 | PE
|  |  | 1382591 | Tippecanoe |  | Tippecanoe County | -339679.2083 | PE
|  |  | 1382592 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1382593 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1382594 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2018-09-12 | CE
CN
ROW
|  |  | 1382595 | Allen |  | Fort Wayne | 2015-05-31 | PE
|  |  | 1382596 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1382597 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2017-04-12 | CE
CN
|  |  | 1382598 |  | Courtland Title & Escrow, Inc. | Hobart | 2026-07-14
|  |  | 1382599 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2014-05-31 | PE
|  |  | 1382600 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2014-05-31 | CN
|  |  | 1382601 | Porter | Leitner and Associates, Inc. | Valparaiso | 2018-04-11 | CE
CN
ROW
|  |  | 1382602 | Porter | Leitner and Associates, Inc. | Valparaiso | 2015-10-07 | CE
CN
|  |  | 1382603 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2023-07-13
|  |  | 1382604 | LaPorte |  | LaPorte County | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1382605 | LaPorte |  | MPO - Northwest | 2015-05-31 | PE
|  |  | 1382606 |  |  | MPO - Northwest | 2016-05-31
|  |  | 1382607 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1382608 |  |  | Indiana Department of Transportation | 2014-03-05
|  |  | 1382609 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382610 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382611 |  |  | Indiana Department of Transportation | 2014-03-05
|  |  | 1382612 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
ROW
|  |  | 1382613 | Marion |  | Indianapolis | 2015-02-04 | CE
CN
|  |  | 1382614 | Greene | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1382615 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382616 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382617 |  |  | South Bend Transit | -339679.2083
|  |  | 1382618 |  |  | South Bend Transit | -339679.2083
|  |  | 1382619 |  |  | South Bend Transit | -339679.2083
|  |  | 1382620 |  |  | South Bend Transit | -339679.2083
|  |  | 1382621 |  |  | South Bend Transit | -339679.2083
|  |  | 1382622 |  |  | South Bend Transit | -339679.2083
|  |  | 1382623 |  |  | South Bend Transit | -339679.2083
|  |  | 1382624 |  |  | South Bend Transit | -339679.2083
|  |  | 1382625 |  |  | South Bend Transit | -339679.2083
|  |  | 1382626 |  |  | South Bend Transit | -339679.2083
|  |  | 1382627 | Jennings |  | Indiana Department of Transportation | 2015-05-08 | CE
CN
|  |  | 1382628 |  |  | South Bend Transit | -339679.2083
|  |  | 1382629 |  |  | South Bend Transit | -339679.2083
|  |  | 1382630 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382631 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382632 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382633 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382634 |  |  | South Bend Transit | -339679.2083
|  |  | 1382635 |  |  | South Bend Transit | -339679.2083
|  |  | 1382636 |  |  | South Bend Transit | -339679.2083
|  |  | 1382637 |  |  | South Bend Transit | -339679.2083
|  |  | 1382638 |  |  | South Bend Transit | -339679.2083
|  |  | 1382639 |  |  | South Bend Transit | -339679.2083
|  |  | 1382640 |  |  | South Bend Transit | -339679.2083
|  |  | 1382641 |  |  | South Bend Transit | -339679.2083
|  |  | 1382642 |  |  | South Bend Transit | -339679.2083
|  |  | 1382643 |  |  | South Bend Transit | -339679.2083
|  |  | 1382644 |  |  | South Bend Transit | -339679.2083
|  |  | 1382645 |  |  | South Bend Transit | -339679.2083
|  |  | 1382646 |  |  | South Bend Transit | -339679.2083
|  |  | 1382647 |  |  | South Bend Transit | -339679.2083
|  |  | 1382648 |  |  | South Bend Transit | -339679.2083
|  |  | 1382649 |  |  | South Bend Transit | -339679.2083
|  |  | 1382650 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382651 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382652 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382653 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382654 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382655 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1382656 | Clinton |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1382657 | Porter |  | Chesterton | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1382658 | Lake | Compliance Consulting Service, Inc. | Griffith | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1382659 | Lake | Consolidated Test Company | Hammond | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1382660 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2016-03-02 | CE
CN
|  |  | 1382661 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2019-03-06 | CN
RR
|  |  | 1382662 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382663 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382664 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382665 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382666 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382667 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382668 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382669 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382670 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382671 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382672 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382673 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382674 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382675 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1382676 | Jackson |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1382677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382678 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382679 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382680 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382681 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382682 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1382683 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1382684 | Madison |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1382685 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1382686 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382687 | Tipton |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382688 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382689 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382690 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382691 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382692 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382693 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1382694 | Boone |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1382695 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1382696 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382697 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382698 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382699 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382700 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1382701 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382702 |  |  | Indiana Department of Transportation | 2014-01-03
|  |  | 1382703 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382704 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382705 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382706 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382707 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382708 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382709 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382710 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382711 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382712 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382713 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382714 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382715 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382716 | Ripley |  | Indiana Department of Transportation | 2013-07-22 | RR
|  |  | 1382717 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382718 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382719 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382720 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382721 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382722 | Lake |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1382723 | Lake |  | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382724 | Lake |  | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1382725 | Lake |  | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1382726 | Gibson | III FFC | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1382727 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382728 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382729 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382730 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382731 | Gibson |  | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382732 | Tippecanoe |  | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382733 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1382734 | Elkhart |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1382735 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1382736 | Scott |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
UT
|  |  | 1382737 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1382738 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1382739 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1382740 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2014-05-31 | RR
|  |  | 1382741 | Greene |  | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1382742 | Lake |  | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382743 | Lake |  | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382744 | Dubois |  | Indiana Department of Transportation | 2015-05-31 | RR
|  |  | 1382745 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382746 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382747 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382748 | Delaware |  | Indiana Department of Transportation | 2016-05-31 | RR
|  |  | 1382749 | Vanderburgh | CGI | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1382750 | Floyd |  | Indiana Department of Transportation | 2013-10-09 | CE
CN
|  |  | 1382751 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-02-03 | CE
CN
RR
|  |  | 1382752 | Madison |  | Madison County | -339679.2083 | PE
|  |  | 1382753 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1382754 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382755 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382756 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382757 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382758 | St. Joseph |  | South Bend | 2017-09-13 | CE
CN
PE
|  |  | 1382759 | St. Joseph |  | St. Joseph County | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1382760 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2017-03-01 | CN
|  |  | 1382761 | Various |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1382762 |  |  | Kokomo | -339679.2083
|  |  | 1382763 |  |  | Allen County | -339679.2083
|  |  | 1382765 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1382767 | Lawrence | ASA Land Surveying | Bedford | 2016-12-14 | CE
CN
PE
|  |  | 1382768 |  |  | Vanderburgh County | -339679.2083
|  |  | 1382769 |  | DuSABLE, Inc. | Lafayette | -339679.2083
|  |  | 1382770 | Lawrence | ASA Land Surveying | Bedford | 2016-12-14 | CN
PE
|  |  | 1382771 | Lawrence | ASA Land Surveying | Bedford | 2017-11-29 | CN
PE
|  |  | 1382772 | Marion |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
RR
|  |  | 1382773 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382774 | Dearborn |  | Aurora | 2016-03-02 | CE
CN
PE
|  |  | 1382775 | Johnson |  | Johnson County | 2014-05-08 | CE
CN
|  |  | 1382776 | Monroe |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1382777 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1382778 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382779 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1382780 |  |  | Monroe County | -339679.2083
|  |  | 1382781 |  |  | MPO - Cincinnati | -339679.2083
|  |  | 1382782 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382783 | Monroe |  | Indiana Department of Transportation | 2013-12-11 | CE
CN
|  |  | 1382784 |  |  | MPO - South Bend / Elkhart | 2013-07-06
|  |  | 1382785 | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  |  | Various |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1382789 |  |  | Indiana Department of Transportation | 2013-11-06
|  |  | 1382790 | Ripley |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1382791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382792 |  |  | Greensburg | -339679.2083
|  |  | 1382793 | St. Joseph |  | St. Joseph County | 2014-05-08 | CE
CN
|  |  | 1382794 |  |  | St. Joseph County | -339679.2083
|  |  | 1382795 |  |  | St. Joseph County | -339679.2083
|  |  | 1382796 | St. Joseph |  | St. Joseph County | 2014-04-02 | CE
CN
|  |  | 1382797 | St. Joseph |  | St. Joseph County | 2017-02-08 | CE
CN
PE
|  |  | 1382798 | St. Joseph |  | St. Joseph County | 2015-12-09 | CE
CN
PE
|  |  | 1382799 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2014-05-08 | CE
CN
|  |  | 1382800 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2014-04-02 | CE
CN
|  |  | 1382801 | Pike |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1382802 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1382803 | Lawrence |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1382804 | Orange |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1382805 | Clinton | DCD Consulting LLC | Indiana Department of Transportation | 2014-03-05 | PE
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-03-05 | CE
CN
PE
UT
|  |  | 1382806 |  | Home Equity Appraisals | Petersburg | 2016-05-04
|  |  | 1382807 | Johnson |  | Greenwood | 2014-08-06 | CE
CN
|  |  | 1382808 | Jay |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1382809 | Greene |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382810 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2017-10-12 | CE
CN
PE
UT
|  |  | 1382811 | Elkhart | Civil Inspection Services, LLC | Goshen | 2018-03-14 | CE
CN
|  |  | 1382812 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382813 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382814 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382815 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382816 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382817 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1382818 | Allen |  | Allen County | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1382819 |  |  | Indiana Department of Transportation | 2013-11-14
|  |  | 1382820 | Washington |  | Salem | 2015-10-07 | CE
CN
PE
|  |  | 1382821 | Howard |  | MPO - Kokomo | -339679.2083 | PL
|  |  |  | Various |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1382822 | Floyd |  | Indiana Department of Transportation | 2014-05-31 | PE
|  |  | 1382826 | Clinton |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1382831 |  |  | Elkhart County | -339679.2083
|  |  | 1382833 |  |  | Elkhart County | -339679.2083
|  |  | 1382835 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1382839 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2014-01-15
|  |  | 1382843 | Owen |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1382844 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382845 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2014-02-05 | CE
CN
UT
|  |  | 1382846 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1382849 | Washington |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1382855 |  |  | MPO - Louisville | -339679.2083
|  |  | 1382858 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382859 |  |  | MPO - Louisville | -339679.2083
|  |  | 1382860 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  |  | Various |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1382861 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382862 |  |  | MPO - Evansville | -339679.2083
|  |  | 1382863 |  |  | MPO - Louisville | -339679.2083
|  |  | 1382864 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382865 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382866 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1382867 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  |  | Various |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1382868 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1382869 | Hamilton |  | Hamilton County | 2016-09-14 | CE
CN
|  |  | 1382870 | Marion | ASC Group, Inc. | Beech Grove | 2014-09-10 | CE
CN
PE
|  |  | 1382871 | Howard |  | MPO - Kokomo | -339679.2083 | PL
|  |  |  | Various |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1382872 | Hamilton |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1382873 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1382874 | Brown |  | Brown County | 2022-03-09 | PE
ROW
|  |  | 1382875 | Jennings |  | Jennings County | 2017-04-05 | CE
CN
PE
ROW
UT
|  |  | 1382876 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1382877 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1382878 |  |  | Indiana Department of Transportation | 2014-07-09
|  |  | 1382879 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382880 |  |  | Indiana Department of Transportation | 2013-09-17
|  |  | 1382881 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382882 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382883 |  |  | Richmond | 2014-01-15
|  |  | 1382884 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1382885 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382886 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382887 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382888 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382889 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382890 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1382891 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382892 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382893 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382894 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382895 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382896 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382897 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382898 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382899 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382900 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382901 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382902 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382903 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382904 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1382905 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382906 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382907 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382908 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1382909 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1382910 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1382911 | Boone |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2014-04-02 | CE
CN
PE
|  |  | 1382912 | Howard |  | MPO - Kokomo | -339679.2083 | PL
|  |  |  | Various |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1382913 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1382914 | Various |  | Indiana Department of Transportation | 2014-03-05 | CE
CN
|  |  | 1382915 |  |  | MPO - Northwest | 2013-09-23
|  |  | 1382916 |  |  | MPO - Northwest | 2013-09-23
|  |  | 1382917 |  |  | MPO - Northwest | 2013-09-23
|  |  | 1382918 |  |  | MPO - Northwest | 2013-09-23
|  |  | 1382919 |  |  | MPO - Northwest | 2013-09-23
|  |  | 1382920 |  |  | MPO - Northwest | 2013-09-23
|  |  | 1382921 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382922 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382923 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382924 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382925 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382926 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382927 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382928 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382929 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382930 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382931 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382932 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382933 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382934 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382935 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382936 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382937 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382938 | Hendricks | All About Pavements, Inc. | Brownsburg | 2014-11-26 | PE
|  |  | 1382939 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382940 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382941 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382942 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382943 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382944 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382945 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382946 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382947 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382948 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382949 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382950 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382951 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1382952 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382953 | Owen |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
PE
|  |  | 1382954 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382955 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382956 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382957 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382958 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382959 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382960 |  |  | East Chicago | 2013-09-28
|  |  | 1382961 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382962 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382963 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382964 |  |  | East Chicago | 2013-09-28
|  |  | 1382965 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382966 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382967 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382968 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382969 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382970 |  |  | MPO - Northwest | -339679.2083
|  |  | 1382971 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382972 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382973 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382974 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382975 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382976 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382977 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382978 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382979 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382980 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382981 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382982 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382983 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382984 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382985 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382986 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382987 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382988 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382989 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382990 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382991 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382992 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1382993 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1382994 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1382995 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1382996 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1382997 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1382998 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1382999 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383000 |  |  | Michigan City Transit | -339679.2083
|  |  | 1383001 |  |  | Michigan City Transit | -339679.2083
|  |  | 1383002 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383003 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383004 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383005 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383006 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383007 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383008 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383009 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383010 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383011 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383012 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383013 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383014 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383015 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383016 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383017 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383018 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383019 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383020 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383021 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383022 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383023 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383024 | Tippecanoe |  | MPO - Lafayette | -339679.2083 | CN
|  |  |  | Various |  | MPO - Lafayette | -339679.2083 | CN
|  |  | 1383025 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383026 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383027 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383028 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383029 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383030 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383031 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383032 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383033 |  |  | MPO - Northwest | 2013-09-28
|  |  | 1383034 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | 2013-09-28
|  |  | 1383035 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383036 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383037 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383038 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383039 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383040 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383041 | Marion |  | Indiana Department of Transportation | 2014-04-16 | CE
CN
|  |  | 1383042 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383043 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383044 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383045 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383046 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383047 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383048 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383049 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383050 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383051 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1383052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383053 |  | Hydrogeology, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383054 | Madison |  | Alexandria | 2015-10-07 | CE
CN
PE
ROW
|  |  | 1383055 | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 1383056 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1383057 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383058 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383059 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383060 |  | Browning Day Mullins Dierdorf Architects | East Chicago | 2015-05-31
|  |  | 1383061 | Hancock |  | Hancock County | 2015-07-08 | CE
CN
PE
|  |  | 1383062 | Hamilton |  | Hamilton County | 2014-08-06 | CE
CN
|  |  | 1383063 |  |  | Indiana Department of Transportation | 2014-01-15
|  |  | 1383064 | Vanderburgh | CGI | Evansville | 2020-02-05 | CE
CN
PE
ROW
|  |  | 1383065 | Vanderburgh | CGI | Evansville | 2018-09-12 | CE
CN
PE
ROW
|  |  | 1383066 | Vanderburgh | CGI | Evansville | 2019-12-11 | CN
PE
ROW
|  |  | 1383067 |  |  | Warren County | 2014-05-31
|  |  | 1383068 | Marion |  | Homecroft | 2014-11-13 | CE
CN
PE
|  |  | 1383069 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1383070 |  |  | Kokomo Transit | -339679.2083
|  |  | 1383071 |  |  | Kokomo Transit | -339679.2083
|  |  | 1383072 |  |  | Kokomo Transit | -339679.2083
|  |  | 1383073 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1383074 |  |  | Kokomo Transit | -339679.2083
|  |  | 1383075 |  |  | Kokomo Transit | -339679.2083
|  |  | 1383076 |  |  | Kokomo Transit | -339679.2083
|  |  | 1383077 | Various |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1383078 | Various |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1383079 | Allen | Metropolitan Abstracting Consultants, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
RR
|  |  | 1383080 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1383081 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1383082 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1383083 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1383084 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1383085 | Vanderburgh | CGI | MPO - Evansville | 2014-05-08 | CE
CN
|  |  | 1383086 |  |  | Lawrence | -339679.2083
|  |  | 1383087 | Marion |  | Indianapolis | 2015-07-08 | CE
CN
|  |  | 1383088 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383089 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383093 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383094 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2014-02-05
|  |  | 1383095 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2014-02-05
|  |  | 1383096 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383097 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383098 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383099 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2015-05-31 | CN
|  |  | 1383100 | Various |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1383101 | Elkhart | Civil Inspection Services, LLC | Goshen | 2014-10-15 | RR
|  |  | 1383102 |  | ABt SRBI | Indiana Department of Transportation | 2014-06-28
|  |  | 1383103 | Johnson | Martin Riley, Inc. | Whiteland | 2015-07-08 | CE
CN
PE
|  |  | 1383104 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383105 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383106 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383107 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383108 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1383109 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1383110 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383111 |  |  | MPO - Anderson | 2013-10-20
|  |  | 1383112 |  |  | MPO - Anderson | 2013-10-20
|  |  | 1383113 |  |  | MPO - Northwest | 2013-10-21
|  |  | 1383114 |  |  | MPO - Northwest | 2013-10-21
|  |  | 1383115 |  |  | MPO - Northwest | 2013-10-21
|  |  | 1383116 |  |  | MPO - Northwest | 2013-10-21
|  |  | 1383117 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1383118 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1383119 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1383120 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1383122 | Delaware |  | MPO - Muncie | -339679.2083 | PL
|  |  |  | Various |  | MPO - Muncie | -339679.2083 | PL
[6 empty] | MPO - Muncie | -339679.2083
|  |  | 1383123 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383124 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383125 |  |  | MPO - Anderson | -339679.2083
|  |  | 1383126 | Spencer | JJR, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
ROW
|  |  | 1383127 | Johnson |  | Greenwood | 2017-02-08 | CE
CN
|  |  | 1383128 | Johnson |  | Franklin | 2014-05-31 | PE
|  |  | 1383129 | Johnson | Casteel Real Estate | Johnson County | 2016-12-14 | CE
CN
|  |  | 1383130 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1383131 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383132 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383133 | Johnson |  | Johnson County | 2015-12-09 | CE
CN
|  |  | 1383134 | Johnson |  | Johnson County | 2015-12-09 | CE
CN
|  |  | 1383135 |  |  | Indiana Department of Transportation | 2014-03-05
|  |  | 1383136 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383137 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383138 | Delaware |  | Indiana Department of Transportation | 2014-01-15 | CE
CN
|  |  | 1383139 | Clay |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1383140 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1383141 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1383142 |  |  | MPO - Muncie | 2013-10-28
|  |  | 1383143 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1383144 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1383145 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1383146 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383147 | Spencer | JJR, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1383148 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 1383149 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2015-05-31 | CE
CN
|  |  | 1383150 |  |  | Indiana Department of Transportation | 2014-07-09
|  |  | 1383151 |  |  | LaPorte County | -339679.2083
|  |  | 1383152 | Hamilton |  | Hamilton County | 2014-08-06 | CE
CN
|  |  | 1383153 | Hamilton |  | Hamilton County | 2014-11-13 | CE
CN
|  |  | 1383154 | Hamilton |  | Hamilton County | 2016-09-14 | CE
CN
|  |  | 1383155 | Hamilton |  | Hamilton County | 2014-11-13 | CE
CN
|  |  | 1383156 | Hamilton |  | Hamilton County | 2017-01-19 | CE
CN
|  |  | 1383157 | Hamilton |  | Hamilton County | 2016-12-14 | CE
CN
|  |  | 1383158 |  |  | Southport | -339679.2083
|  |  | 1383159 | Marion |  | Indianapolis | 2015-01-14 | CE
CN
|  |  | 1383160 | Marion |  | Indianapolis | 2014-07-09 | CE
CN
|  |  | 1383161 | Hancock |  | Mccordsville | 2016-01-13 | CN
|  |  |  | Marion |  | Mccordsville | 2016-01-13 | CE
CN
|  |  | 1383162 |  |  | Mccordsville | -339679.2083
|  |  | 1383163 | Hamilton |  | Fishers | 2015-07-08 | CE
CN
|  |  | 1383164 | Marion |  | Beech Grove | 2014-07-09 | CE
CN
|  |  | 1383165 | Hamilton |  | Carmel | 2014-08-06 | CE
CN
|  |  | 1383166 | Hamilton |  | Carmel | 2014-08-06 | CE
CN
|  |  | 1383167 | Hamilton |  | Noblesville | 2014-05-08 | CE
CN
|  |  | 1383168 | Hamilton |  | Noblesville | 2013-01-08 | ROW
|  |  | 1383169 | Marion |  | Indianapolis | 2016-11-16 | CE
CN
|  |  | 1383170 | Marion |  | Indianapolis | 2016-12-14 | CE
CN
RR
|  |  | 1383171 | Marion |  | Indianapolis | 2016-11-16 | CE
CN
|  |  | 1383172 | Marion |  | Indianapolis | 2018-01-18 | CE
CN
UT
|  |  | 1383173 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
|  |  | 1383174 | Marion |  | Indianapolis | 2016-11-16 | CE
CN
|  |  | 1383175 | Marion |  | Indianapolis | 2017-12-13 | CE
CN
|  |  | 1383176 | Marion |  | Indianapolis | 2017-12-13 | CE
CN
|  |  | 1383177 | Hamilton | CPS Acquisitions, LLC | Fishers | 2019-12-11 | PE
ROW
|  |  |  | Marion | CPS Acquisitions, LLC | Fishers | 2019-12-11 | CN
|  |  | 1383178 | Hamilton | CPS Acquisitions, LLC | Fishers | 2018-01-18 | CN
PE
ROW
|  |  | 1383179 | Hamilton |  | Fishers | 2017-10-12 | CN
ROW
|  |  | 1383180 | Hamilton |  | Carmel | 2018-10-11 | CE
CN
|  |  | 1383181 | Montgomery |  | Indiana Department of Transportation | 2014-05-08 | CN
|  |  |  | Tippecanoe |  | Indiana Department of Transportation | 2014-05-08 | CE
CN
|  |  | 1383182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383183 | Various |  | Indiana Department of Transportation | 2015-05-31 | CN
PE
|  |  | 1383184 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383185 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383186 |  |  | Indiana Department of Transportation | 2014-03-05
|  |  | 1383187 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383188 | Elkhart |  | Elkhart County | 2015-04-01 | CE
CN
PE
|  |  | 1383189 | Elkhart |  | Elkhart County | 2014-05-08 | CE
CN
|  |  | 1383190 |  |  | MPO - Evansville | 2013-11-05
|  |  | 1383191 |  |  | MPO - Evansville | 2013-11-05
|  |  | 1383192 |  |  | MPO - Evansville | 2013-11-05
|  |  | 1383193 | Marion |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1383194 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2014-04-02 | CE
CN
|  |  | 1383195 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1383196 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 1383197 | Bartholomew |  | Indiana Department of Transportation | 2015-04-15 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2015-04-15 | CE
CN
|  |  | 1383198 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1383199 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1383200 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1383201 | Rush |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1383202 |  | CGI | Indiana Department of Transportation | 2014-03-05
|  |  | 1383203 |  | Dodd Title Corporation | Indiana Department of Transportation | 2016-05-31
|  |  | 1383204 |  |  | MPO - South Bend / Elkhart | 2013-11-11
|  |  | 1383205 |  |  | MPO - South Bend / Elkhart | 2013-11-11
|  |  | 1383206 |  |  | MPO - South Bend / Elkhart | 2013-11-11
|  |  | 1383207 |  |  | MPO - South Bend / Elkhart | 2013-11-11
|  |  | 1383208 |  |  | MPO - South Bend / Elkhart | 2013-11-11
|  |  | 1383209 |  |  | MPO - South Bend / Elkhart | 2013-11-11
|  |  | 1383210 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383211 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383212 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1383213 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1383214 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1383215 | Vanderburgh |  | Vanderburgh County | -339679.2083 | PE
|  |  | 1383216 | Jennings |  | Indiana Department of Transportation | 2015-05-08 | CE
CN
UT
|  |  | 1383217 |  |  | Westfield | -339679.2083
|  |  | 1383218 |  |  | Indiana Department of Transportation | 2014-02-05
|  |  | 1383219 | Daviess |  | Indiana Department of Transportation | 2014-02-12 | CE
CN
|  |  |  | Gibson |  | Indiana Department of Transportation | 2014-02-12 | CE
CN
|  |  |  | Greene |  | Indiana Department of Transportation | 2014-02-12 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2014-02-12 | CE
CN
|  |  | 1383220 | Daviess |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  |  | Gibson |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  |  | Greene |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1383221 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1383222 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1383223 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1383224 | Monroe |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1383225 | Johnson |  | Franklin | 2016-11-16 | CE
CN
RR
|  |  | 1383226 | Clark |  | Indiana Department of Transportation | 2015-05-31 | CN
|  |  | 1383227 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1383228 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1383229 | Vigo | Bayswater Company, LLC | Terre Haute | 2015-09-24 | PE
RR
|  |  | 1383230 | Vigo | Bayswater Company, LLC | Vigo County | 2014-03-06 | PE
|  |  | 1383231 | Monroe |  | Indiana Department of Transportation | 2014-07-09 | CE
CN
|  |  | 1383232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383234 |  |  | MPO - South Bend / Elkhart | 2013-12-07
|  |  | 1383235 |  |  | MPO - South Bend / Elkhart | 2013-12-07
|  |  | 1383236 | Wabash |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1383237 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2020-02-05 | PE
ROW
|  |  | 1383238 | Elkhart |  | Indiana Department of Transportation | 2019-10-09 | PE
ROW
|  |  | 1383239 | Miami |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1383240 | Vanderburgh |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1383241 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2016-11-30 | CN
|  |  | 1383242 |  |  | Allen County | 2018-05-31
|  |  | 1383245 | Greene |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1383246 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1383247 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2016-05-31 | CN
PE
[5 empty] | Associated Right-of-Way Services, Inc. | Columbus | 2016-05-31
|  |  | 1383248 |  |  | Columbus | -339679.2083
|  |  | 1383249 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 1383250 | Lake | Matt L. Nepote, MAI | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1383251 | Allen |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
RR
|  |  | 1383252 | Marion | ERES International, Inc. | Indianapolis | 2015-07-08 | CE
CN
|  |  | 1383253 | Hamilton | CPS Acquisitions, LLC | Fishers | 2014-10-08 | CE
CN
|  |  | 1383254 | Hamilton | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton County | 2015-09-02 | CE
CN
|  |  | 1383255 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383256 | Hamilton | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton County | 2015-07-08 | CE
CN
|  |  | 1383257 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383258 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383259 |  |  | Indiana Department of Natural Resources | 2014-04-02
|  |  | 1383260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383261 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383262 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383263 | Marion | DCD Consulting LLC | Indianapolis | 2019-11-14 | CN
|  |  | 1383264 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383265 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CN
|  |  | 1383266 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383267 | Marion | DCD Consulting LLC | Indianapolis | 2015-07-16 | PE
|  |  | 1383268 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383269 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383270 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383271 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383272 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383273 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383274 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383275 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383276 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383277 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383278 |  |  | Steuben County | -339679.2083
|  |  | 1383279 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1383280 |  |  | Monroe County | -339679.2083
|  |  | 1383281 |  |  | Lynnville | -339679.2083
|  |  | 1383282 | Marion |  | Indianapolis | 2016-08-05 | OT
|  |  | 1383283 | Various |  | Indiana Department of Natural Resources | 2014-05-31 | CN
|  |  | 1383284 |  |  | Albion | -339679.2083
|  |  | 1383285 | Grant |  | Sweetser | 2015-05-31 | CN
PE
ROW
|  |  | 1383286 |  |  | Hartford City | -339679.2083
|  |  | 1383287 |  |  | Columbus | -339679.2083
|  |  | 1383288 | Gibson |  | Indiana Department of Natural Resources | 2016-05-31 | CN
PE
ROW
|  |  | 1383289 | Porter |  | Indiana Department of Natural Resources | 2015-05-31 | CN
PE
ROW
|  |  | 1383290 | Elkhart |  | Indiana Department of Natural Resources | 2017-05-31 | CN
PE
ROW
|  |  | 1383291 | Pike |  | Pike County | 2020-01-15 | CE
CN
PE
RR
|  |  | 1383292 | Pike |  | Pike County | 2020-01-15 | CE
CN
PE
|  |  | 1383293 | Grant | Level 5 Engineering, LLC | Van Buren | 2016-03-02 | CE
CN
PE
|  |  | 1383294 | Dubois |  | Huntingburg | 2017-09-13 | CE
CN
PE
|  |  | 1383295 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 1383296 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383297 |  |  | Indiana Department of Transportation | 2014-04-02
|  |  | 1383298 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383299 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383300 |  | DCD Consulting LLC | Indiana Department of Transportation | 2014-08-06
|  |  | 1383301 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1383302 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383303 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383304 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383305 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383307 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2014-05-08
|  |  | 1383308 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383309 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1383310 | Franklin | ARCADIS | Batesville | 2015-03-04 | CE
CN
PE
|  |  | 1383311 | Fountain | Linda F. Russell | Veedersburg | 2017-02-08 | CE
CN
PE
ROW
|  |  | 1383312 | Decatur |  | Decatur County | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1383313 | Cass | Chemical Dependency Program of Indiana | Galveston | 2017-01-19 | CE
CN
PE
|  |  | 1383314 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 1383315 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 1383316 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 1383317 | Wayne | Indiana Appraisal Group, Inc. | Wayne County | 2016-12-14 | CE
CN
PE
RR
|  |  | 1383318 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383319 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383320 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 1383321 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383322 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1383323 |  | Appraisal Office of Central Indiana | Wayne County | -339679.2083
|  |  | 1383324 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
RR
|  |  | 1383325 | Hancock |  | Hancock County | 2016-12-14 | CE
CN
|  |  | 1383326 | Grant | CGS Real Estate Services, LLC | Fairmount | 2016-03-02 | CE
CN
PE
|  |  | 1383327 |  |  | Hancock County | -339679.2083
|  |  | 1383328 | St. Joseph |  | Indiana Department of Transportation | 2020-02-19 | PE
|  |  | 1383329 | Daviess |  | Daviess County | 2017-03-01 | CE
CN
PE
ROW
UT
|  |  | 1383330 | Wayne | Fleis & VandenBrink Engineering, Inc. | Milton | 2016-03-01 | PE
|  |  | 1383331 |  |  | Rushville | -339679.2083
|  |  | 1383332 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383333 |  | Boomerang Ventures, LLC | Dunkirk | -339679.2083
|  |  | 1383334 | Hamilton |  | Hamilton County | 2017-04-05 | CE
CN
ROW
|  |  | 1383335 |  |  | Hamilton County | -339679.2083
|  |  | 1383336 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383337 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2015-10-07
|  |  | 1383338 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2014-10-07
|  |  | 1383339 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2014-12-17 | CE
CN
PE
RR
UT
|  |  | 1383340 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2014-12-17 | PE
RR
|  |  | 1383341 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2015-03-04 | CE
CN
PE
UT
|  |  | 1383342 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2015-03-04
|  |  | 1383343 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
PE
|  |  |  | Marion | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
UT
|  |  | 1383344 |  | Fusion by Design, Inc. | Montpelier | -339679.2083
|  |  | 1383345 |  |  | Brown County | -339679.2083
|  |  | 1383346 | Tipton |  | Tipton County | -339679.2083 | PE
|  |  | 1383347 | Franklin | Alfred Benesch & Company | Franklin County | 2018-01-18 | CE
CN
PE
|  |  | 1383348 |  |  | Franklin County | -339679.2083
|  |  | 1383349 |  |  | Franklin County | -339679.2083
|  |  | 1383350 | Marshall | Bayer & Becker, Inc. | Culver | 2016-10-05 | CE
CN
PE
|  |  | 1383351 | Fulton | 2IM Group, LLC | Akron | 2016-11-16 | CE
CN
PE
|  |  | 1383352 | Cass |  | Cass County | 2017-11-15 | CE
CN
PE
ROW
|  |  | 1383353 | Allen |  | Allen County | 2018-03-14 | CE
CN
RR
|  |  | 1383354 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2014-10-08
|  |  | 1383355 | Miami | Atlas Appraisals, LLC | Converse | 2016-03-02 | CE
CN
PE
|  |  | 1383356 | Steuben | ABt SRBI | Angola | 2016-07-15 | CE
CN
PE
|  |  | 1383357 |  | Atlas Appraisals, LLC | Converse | -339679.2083
|  |  | 1383358 |  | ABt SRBI | Angola | -339679.2083
|  |  | 1383359 |  |  | Indiana Department of Natural Resources | 2015-12-09
|  |  | 1383360 |  | H.R. Gray | North Judson | -339679.2083
|  |  | 1383361 |  |  | Indiana Department of Natural Resources | 2015-12-09
|  |  | 1383362 |  |  | Indiana Department of Natural Resources | 2015-12-09
|  |  | 1383363 |  |  | Indiana Department of Transportation | 2014-12-10
|  |  | 1383364 | Porter |  | Porter County | 2020-11-10 | CE
CN
PE
ROW
|  |  | 1383365 |  |  | Noble County | -339679.2083
|  |  | 1383366 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 1383367 |  |  | Indiana Department of Transportation | 2014-12-10
|  |  | 1383368 |  |  | Indiana Department of Natural Resources | 2014-12-10
|  |  | 1383369 | Decatur | Collier Transport Inc. | Greensburg | 2016-03-02 | CE
CN
PE
|  |  | 1383370 | Harrison |  | Harrison County | 2018-04-11 | CE
CN
PE
|  |  | 1383371 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1383372 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1383373 |  |  | Indiana Department of Natural Resources | 2016-12-14
|  |  | 1383374 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 1383375 | Hendricks | Horner and Shifrin, Inc. | Hendricks County | 2016-08-10 | CE
CN
PE
|  |  | 1383383 |  | CTL Engineering of Indiana, Inc. | Indiana University Purdue University Fort Wayne | -339679.2083
|  |  | 1383387 |  |  | South Whitley | -339679.2083
|  |  | 1383388 |  |  | Porter County | -339679.2083
|  |  | 1383389 | Fulton | 2IM Group, LLC | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1383390 | Kosciusko | Home Guide Realty Services | Indiana Department of Transportation | 2015-12-09 | CE
CN
RR
|  |  | 1383391 | Whitley | Durham Engineering, Inc. | Indiana Department of Transportation | 2015-01-14 | CE
CN
RR
|  |  | 1383392 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2015-04-15 | CE
CN
|  |  | 1383393 | Adams | Foresight Land Surveying, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1383394 | White | Fugro Roadware, Inc. | White County | 2017-03-01 | CN
PE
|  |  | 1383395 | St. Joseph | HDR Engineering, Inc. | North Liberty | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1383396 | St. Joseph | HDR Engineering, Inc. | North Liberty | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1383397 |  |  | St. Joseph County | -339679.2083
|  |  | 1383398 | St. Joseph |  | St. Joseph County | 2019-11-14 | CE
CN
PE
ROW
|  |  | 1383399 |  |  | St. Joseph County | -339679.2083
|  |  | 1383400 |  |  | White County | -339679.2083
|  |  | 1383401 |  |  | LaPorte County | -339679.2083
|  |  | 1383402 |  | Fusion by Design, Inc. | Montpelier | -339679.2083
|  |  | 1383403 | Blackford | Fusion by Design, Inc. | Montpelier | 2016-12-14 | CE
CN
PE
RR
|  |  | 1383404 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383405 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1383406 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1383407 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1383408 | Boone |  | Boone County | 2017-02-08 | CE
CN
PE
ROW
|  |  | 1383409 | Whitley |  | South Whitley | 2017-05-10 | CE
CN
PE
|  |  | 1383410 |  | Linda F. Russell | Indiana Department of Transportation | 2014-08-06
|  |  | 1383411 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2014-08-20
|  |  | 1383412 |  |  | Indiana Department of Transportation | 2014-08-20
|  |  | 1383413 |  |  | Grant County | -339679.2083
|  |  | 1383414 | Montgomery | Banning Engineering, P.C. | Crawfordsville | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1383415 | Wabash | M-E Companies, Inc. | Wabash | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1383416 | Clinton | Carters Appraisal Service | Frankfort | 2018-10-11 | CE
CN
PE
ROW
RR
|  |  | 1383417 | Madison | CE Solutions, Inc. | Elwood | 2017-10-12 | CE
CN
PE
ROW
RR
|  |  | 1383423 | Whitley |  | Churubusco | 2017-01-19 | CE
CN
PE
|  |  | 1383424 |  |  | Centerville | -339679.2083
|  |  | 1383425 |  |  | South Whitley | -339679.2083
|  |  | 1383429 |  |  | Hamilton County | -339679.2083
|  |  | 1383430 |  |  | Huntington County | -339679.2083
|  |  | 1383431 |  |  | Tipton County | -339679.2083
|  |  | 1383432 |  |  | Hamilton County | -339679.2083
|  |  | 1383433 | Union |  | Union County | 2017-10-12 | CE
CN
PE
ROW
|  |  | 1383434 | Jay | Boomerang Ventures, LLC | Dunkirk | 2017-02-08 | CN
PE
|  |  | 1383435 | Jay | Hydrogeology, Inc. | Portland | 2016-07-13 | CE
CN
PE
|  |  | 1383436 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1383437 |  |  | Rushville | -339679.2083
|  |  | 1383438 |  |  | Hancock County | -339679.2083
|  |  | 1383439 |  |  | Madison County | -339679.2083
|  |  | 1383440 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 1383441 | Shelby | Jeffrey S. Juday | Shelbyville | 2016-11-16 | CE
CN
PE
|  |  | 1383442 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2017-01-19 | CE
CN
PE
ROW
|  |  | 1383443 |  | Jeffrey S. Juday | Shelbyville | -339679.2083
|  |  | 1383444 | Dearborn |  | Dearborn County | 2017-12-13 | CE
CN
PE
ROW
RR
UT
|  |  | 1383445 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 1383446 | Noble | Debbie L. Morris | Kendallville | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1383447 | Jay |  | Jay County | 2016-05-31 | PE
|  |  | 1383448 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1383449 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1383450 |  | Karen | Indiana Department of Transportation | 2014-08-06
|  |  | 1383451 | Hendricks |  | Hendricks County | 2017-02-08 | CE
CN
|  |  | 1383452 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1383453 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 1383454 | Fayette |  | Fayette County | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1383455 |  |  | Grant County | -339679.2083
|  |  | 1383456 | Grant |  | Grant County | 2017-01-19 | CE
CN
|  |  | 1383457 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
ROW
|  |  | 1383458 |  | Civil Designs, LLP | Glenwood | -339679.2083
|  |  | 1383459 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 1383460 | Grant |  | Indiana Department of Transportation | 2023-01-19 | PE
RR
|  |  | 1383461 | Huntington |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1383462 | Dekalb | Cheri K. Lewis Engineers | Garrett | 2017-03-01 | CE
CN
PE
|  |  | 1383463 | Miami | Holloway Engineering, LLC | Miami County | 2018-12-12 | CE
CN
PE
|  |  | 1383464 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1383465 | Huntington |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1383466 |  | D A Brown Engineering Consultants, Inc. | Huntington | -339679.2083
|  |  | 1383467 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | -339679.2083
|  |  | 1383468 | Huntington |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1383469 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1383470 | Miami |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1383471 | Montgomery | Banning Engineering, P.C. | Crawfordsville | 2016-05-05 | CE
CN
PE
|  |  |  | Various | Banning Engineering, P.C. | Crawfordsville | 2016-05-05 | CN
|  |  | 1383472 |  |  | Starke County | -339679.2083
|  |  | 1383473 | Fulton | InfoTech | Rochester | -339679.2083 | PE
|  |  | 1383474 | Marshall |  | Marshall County | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1383475 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1383476 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1383477 | Fulton | 2IM Group, LLC | Akron | 2017-08-09 | CE
CN
PE
|  |  | 1383478 |  | Fugro Roadware, Inc. | White County | -339679.2083
|  |  | 1383479 | LaPorte |  | LaPorte County | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1383480 |  |  | LaPorte County | -339679.2083
|  |  | 1383481 |  |  | La Porte | -339679.2083
|  |  | 1383482 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1383483 |  | Lonco, Inc. | Indiana Department of Natural Resources | -339679.2083
|  |  | 1383484 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1383485 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1383486 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383487 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383488 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383489 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383490 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1383491 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1383492 | LaGrange |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1383493 | Kosciusko | HE-BFS, LLC | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
RR
|  |  | 1383494 | Kosciusko | Jones & Henry Engineers, Ltd. | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
RR
|  |  | 1383495 | Grant | Dave Helton & Associates, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
RR
|  |  | 1383496 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1383497 | Wabash | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1383498 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1383499 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1383500 | Elkhart |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1383501 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1383502 | Elkhart | McCormick Engineering, LLC | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1383503 | Blackford |  | Indiana Department of Transportation | 2018-12-12 | CE
|  |  |  | Grant |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1383504 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  |  | Wells | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1383505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383506 | Wabash |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1383507 | Grant |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1383508 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1383509 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1383510 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1383511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383512 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1383513 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1383514 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1383515 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1383516 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2015-02-04
|  |  | 1383517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383519 |  |  | Indiana Department of Transportation | 2015-02-04
|  |  | 1383520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383521 |  |  | Indiana Department of Transportation | 2015-02-04
|  |  | 1383522 | Elkhart |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1383523 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383524 |  |  | Indiana Department of Transportation | 2014-08-20
|  |  | 1383525 | Kosciusko |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
PE
|  |  | 1383526 |  |  | Indiana Department of Transportation | 2015-02-18
|  |  | 1383527 | Miami |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1383528 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-06-22
|  |  | 1383529 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-06-22
|  |  | 1383530 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383531 | Jackson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1383532 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383533 | Blackford |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1383534 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383535 | Grant |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1383536 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383537 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1383538 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1383539 |  |  | Indiana Department of Transportation | 2015-04-01
|  |  | 1383540 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1383541 |  |  | Indiana Department of Transportation | 2015-04-01
|  |  | 1383542 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1383543 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383544 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383545 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1383546 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1383547 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1383548 | Shelby |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1383549 | Shelby |  | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1383550 | Howard |  | Howard County | -339679.2083 | PE
|  |  |  | Various |  | Howard County | -339679.2083 | PE
|  |  | 1383551 | Jay |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1383552 | Allen |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1383553 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1383554 | Whitley |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1383555 | Wells |  | Indiana Department of Transportation | 2020-02-05 | PE
ROW
|  |  | 1383556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383557 | Steuben |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1383558 | Adams |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1383559 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1383560 | Wells |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1383561 | Wells |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1383562 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383563 | Starke |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1383564 | Wells |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1383565 |  |  | Indiana Department of Transportation | 2015-02-18
|  |  | 1383566 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383567 |  |  | Indiana Department of Transportation | 2015-02-18
|  |  | 1383568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383569 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383571 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383572 | LaPorte |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
RR
|  |  | 1383573 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1383574 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1383575 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383576 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383577 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383578 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383579 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383580 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1383581 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383582 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383583 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1383584 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383585 | Huntington |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1383586 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1383587 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383588 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383589 |  | Infrastructure Engineering, Inc. | Indiana Department of Transportation | 2015-03-18
|  |  | 1383590 |  | Copperhead Environmental Consulting | Indiana Department of Transportation | -339679.2083
|  |  | 1383591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383592 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383593 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383594 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383595 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383596 |  |  | Indiana Department of Transportation | 2015-03-18
|  |  | 1383597 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1383598 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383599 | Newton |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1383600 | White | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 2023-03-15 | PE
RR
|  |  | 1383601 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383602 | Jasper |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1383603 | Lake | Cornerstone Design | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1383604 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383605 | Noble |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1383606 |  |  | South Bend Transit | 2013-12-23
|  |  | 1383607 | Elkhart |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1383608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383609 |  |  | Hamilton County | -339679.2083
|  |  | 1383610 |  |  | Aurora | -339679.2083
|  |  | 1383611 | Blackford |  | Blackford County | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1383612 | Grant | ERES International, Inc. | Marion | 2016-07-13 | CE
CN
PE
|  |  | 1383613 | Wells |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1383614 | LaPorte |  | Indiana Department of Transportation | 2019-01-23 | CE
CN
PE
|  |  | 1383615 | Lake |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1383616 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383617 | Fulton |  | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1383618 | Marshall |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1383619 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 1383620 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 1383621 | Elkhart |  | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1383622 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383624 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1383625 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2015-10-07
|  |  | 1383626 | Kosciusko |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1383627 | Kosciusko |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1383628 | Posey | GRL Engineers, Inc. | Mount Vernon | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1383629 | Posey | GRL Engineers, Inc. | Mount Vernon | 2018-12-12 | CE
CN
PE
UT
|  |  | 1383630 |  |  | Monroe County | -339679.2083
|  |  | 1383631 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
ROW
|  |  | 1383632 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383633 | Porter |  | Indiana Department of Transportation | 2020-05-07 | PE
ROW
|  |  | 1383634 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383635 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-12-09 | PE
ROW
|  |  | 1383636 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383637 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383638 | Perry |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1383639 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1383640 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383641 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1383642 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1383643 | Knox | Louis Joyner, Architect | Knox County | 2016-09-14 | CE
CN
PE
|  |  | 1383644 | Steuben |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1383645 |  |  | Clark County | -339679.2083
|  |  | 1383646 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383647 | Grant |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1383648 |  |  | Hamilton County | -339679.2083
|  |  | 1383649 |  |  | Hamilton County | -339679.2083
|  |  | 1383650 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
UT
|  |  | 1383651 |  | Louis Joyner, Architect | Knox County | -339679.2083
|  |  | 1383652 |  |  | Spencer County | -339679.2083
|  |  | 1383653 |  |  | Indianapolis | -339679.2083
|  |  | 1383654 |  |  | Indianapolis | -339679.2083
|  |  | 1383655 |  |  | Carmel | -339679.2083
|  |  | 1383656 |  |  | Indianapolis | -339679.2083
|  |  | 1383657 | Crawford |  | Crawford County | 2017-01-19 | CE
CN
PE
|  |  | 1383658 |  | JJR, LLC | Santa Claus | -339679.2083
|  |  | 1383659 | Spencer | JJR, LLC | Santa Claus | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1383660 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1383661 | Spencer | JJR, LLC | Santa Claus | 2021-05-05 | CE
CN
PE
ROW
|  |  | 1383662 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1383663 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1383664 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1383665 |  | Casteel Real Estate | Franklin | -339679.2083
|  |  | 1383668 |  | Associated Right-of-Way Services, Inc. | Bartholomew County | -339679.2083
|  |  | 1383670 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-04-15 | CE
CN
PE
RR
|  |  | 1383671 | Miami |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
UT
|  |  | 1383672 | LaGrange |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1383673 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383674 | Jefferson | Engineering Resources, Inc. | Madison | 2015-11-10 | CE
CN
PE
|  |  | 1383675 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
UT
|  |  | 1383676 | Wabash |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1383677 | Wells |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1383678 | Wells |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1383679 | Kosciusko | Home Guide Realty Services | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1383680 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383681 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383682 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383683 | Hendricks | All About Pavements, Inc. | Brownsburg | 2018-02-07 | CN
RR
|  |  | 1383684 |  | Duesler Realty House | Indiana Department of Transportation | -339679.2083
|  |  | 1383685 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383686 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383687 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383688 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383689 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383690 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383691 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383692 |  | Karen | Indiana Department of Transportation | -339679.2083
|  |  | 1383693 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1383694 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383695 | Lake | Karen | Indiana Department of Transportation | 2020-07-08 | PE
ROW
|  |  | 1383696 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383697 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383698 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1383699 |  |  | Westfield | -339679.2083
|  |  | 1383700 |  |  | Westfield | -339679.2083
|  |  | 1383701 | Dearborn |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
ROW
|  |  | 1383702 |  |  | Sullivan County | -339679.2083
|  |  | 1383703 | Marshall |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1383704 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383706 | LaPorte |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1383707 | Newton |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
ROW
|  |  | 1383708 | St. Joseph | HDR Engineering, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1383709 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
ROW
|  |  | 1383710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383711 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1383712 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1383713 | St. Joseph |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1383714 | Pulaski |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1383715 | Pulaski |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1383716 | White |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
RR
|  |  | 1383717 | Fulton |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1383718 | LaPorte |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1383719 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1383720 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
ROW
|  |  | 1383721 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1383722 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383723 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383724 | Jackson |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1383725 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1383726 | Dearborn |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1383727 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383728 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1383729 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1383730 | Marshall |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1383731 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383732 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1383733 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1383734 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1400001 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
UT
|  |  | 1400002 | Gibson |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1400003 | Vanderburgh |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1400004 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 1400005 | Vanderburgh |  | Indiana Department of Transportation | 2022-02-09 | PE
ROW
RR
|  |  | 1400006 |  |  | Indiana Department of Transportation | 2014-05-08
|  |  | 1400007 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2015-03-04
|  |  | 1400008 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2015-03-04
|  |  | 1400009 |  | Casteel Real Estate | Indiana Department of Transportation | 2015-03-04
|  |  | 1400010 |  | Casteel Real Estate | Indiana Department of Transportation | 2015-03-04
|  |  | 1400011 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1400012 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1400013 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1400014 |  | Martin Riley, Inc. | Indiana Department of Transportation | 2015-03-04
|  |  | 1400015 | Carroll |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1400016 | Henry |  | Indiana Department of Transportation | 2020-07-08 | PE
[6 empty] | Indiana Department of Transportation | 2020-07-08
|  |  | 1400017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400018 | Randolph |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1400019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400020 | Wayne |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1400021 | Wayne |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1400022 | Union |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
ROW
|  |  | 1400023 | Ripley |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1400024 | Switzerland |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1400025 | Jackson |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1400026 | Morgan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
UT
|  |  | 1400027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400028 | Decatur |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1400029 | Jackson |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
UT
|  |  | 1400030 | Henry |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1400031 | Bartholomew |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1400032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400033 | Hancock |  | Indiana Department of Transportation | 2019-01-23 | CE
CN
PE
ROW
|  |  | 1400034 | Boone |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
ROW
UT
|  |  |  | Marion |  | Indiana Department of Transportation | 2021-12-08 | UT
|  |  | 1400035 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1400036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400037 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1400038 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400039 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400040 | Spencer |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
UT
|  |  | 1400041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400043 | Delaware |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
ROW
|  |  | 1400044 | Greene |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
UT
|  |  | 1400045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400046 | Marion |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1400047 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400048 | Randolph | Eel River Abstract | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1400049 |  | Dillabaugh, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400050 |  | Alliance Survey Company | Indiana Department of Transportation | -339679.2083
|  |  | 1400051 | Jay | Hilton Property Management, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1400052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400053 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1400054 |  | Collins Engineers Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 1400055 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400056 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1400057 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1400058 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400059 | Wayne |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400060 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400061 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1400062 |  | Bureau Veritas North America | Indiana Department of Transportation | -339679.2083
|  |  | 1400063 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400064 | Madison |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1400065 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
ROW
|  |  | 1400066 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400069 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1400070 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1400071 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
UT
|  |  | 1400072 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400073 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05 | PE
|  |  | 1400074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400075 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
ROW
UT
|  |  | 1400076 | Marion |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1400077 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1400078 | Decatur |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 1400079 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400080 | Dearborn |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
ROW
|  |  | 1400081 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400082 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400083 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400084 | Marion | CoCal Consulting, LLC | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1400085 | Ripley |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1400086 | Hamilton |  | Indiana Department of Transportation | 2014-05-31 | CE
CN
|  |  | 1400087 | Morgan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1400088 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1400089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400090 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1400091 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1400092 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1400093 | Bartholomew |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1400094 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
RR
|  |  | 1400095 | Monroe |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1400096 | Jackson |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1400097 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1400098 | Brown |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1400099 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1400100 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1400101 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1400102 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1400103 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1400104 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1400105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400106 | Bartholomew |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
UT
|  |  | 1400107 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400109 | Jackson |  | Indiana Department of Transportation | 2019-12-11 | PE
ROW
|  |  | 1400110 | Decatur |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
|  |  | 1400111 | Harrison |  | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1400112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400114 | LaPorte | Leitner and Associates, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
RR
|  |  |  | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
RR
|  |  | 1400115 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1400116 | LaPorte |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1400117 |  | McCormick Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400118 | Marshall |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1400119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400120 | Crawford |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1400121 | Sullivan |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1400122 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400123 | Crawford |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1400124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400125 | Lawrence |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1400126 | Martin |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1400127 | Daviess |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1400128 | Greene |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1400129 | Lawrence |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1400130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400131 | Floyd |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1400132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400133 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400134 | Jennings |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
ROW
UT
|  |  | 1400135 | Jennings |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
ROW
|  |  | 1400136 | Jackson |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1400137 | Jennings |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
RR
|  |  | 1400138 | Washington | Earth Exploration, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1400139 | Scott |  | Indiana Department of Transportation | 2020-04-01 | PE
ROW
|  |  | 1400140 | Miami |  | Indiana Department of Transportation | 2014-08-06 | CE
|  |  |  | Wabash |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400142 | Clark |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
|  |  | 1400143 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400144 | Dearborn |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1400145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400146 | Crawford |  | Indiana Department of Transportation | 2019-10-09 | PE
ROW
|  |  | 1400147 | Gibson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
UT
|  |  | 1400148 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2015-01-14 | CE
CN
RR
|  |  | 1400149 | Switzerland |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
ROW
UT
|  |  | 1400150 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1400151 | Switzerland |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
UT
|  |  | 1400152 | Ohio |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1400153 | Ohio |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1400154 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1400155 | Ohio |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1400156 | Posey |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1400157 | Warrick | Eilts Consulting Services | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1400158 | Spencer |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1400159 | Spencer |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1400160 | Spencer |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1400161 | Spencer |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1400162 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400163 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400164 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1400165 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400166 | Monroe | Absolute Title Services, LLC | Bloomington | 2017-03-01 | CE
CN
|  |  | 1400167 |  |  | Bloomington | -339679.2083
|  |  | 1400168 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400169 |  |  | New Albany | -339679.2083
|  |  | 1400170 |  |  | MPO - Evansville | -339679.2083
|  |  | 1400171 |  |  | MPO - Evansville | -339679.2083
|  |  | 1400172 |  |  | MPO - Evansville | -339679.2083
|  |  | 1400173 | Scott |  | Indiana Department of Transportation | 2019-05-31 | ROW
|  |  | 1400174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400179 | Dubois |  | Indiana Department of Transportation | 2020-02-05 | PE
UT
|  |  | 1400180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400181 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400183 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400187 | Jackson |  | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1400188 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400189 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400191 | Vanderburgh | CGI | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1400192 | Knox |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1400193 | Sullivan |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
|  |  | 1400194 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400195 | Warrick |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1400196 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400197 | Jackson |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1400198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400199 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400200 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400201 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 1400202 | Crawford | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
RR
|  |  | 1400203 | Newton |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1400204 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1400205 | Orange | Consulting Management Inspection Design, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  |  | Washington | Consulting Management Inspection Design, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
PE
|  |  | 1400206 | Gibson | III FFC | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1400207 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1400208 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1400209 | Various |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1400210 | Orange |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1400211 | Various |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1400212 | Benton |  | Otterbein | 2015-02-04 | CE
CN
PE
|  |  | 1400213 | Benton |  | Indiana Department of Transportation | 2020-03-04 | PE
ROW
|  |  | 1400214 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400215 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1400216 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1400217 | Tippecanoe |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1400218 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400219 | Boone |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1400220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400221 | Parke |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1400222 | Clinton |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1400223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400224 | Benton |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1400225 | Benton |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1400226 | Parke |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1400227 | Vermillion |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1400228 | White |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1400229 | Hendricks |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1400230 | Benton |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1400231 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400234 | White |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1400235 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
ROW
|  |  | 1400236 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1400237 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1400238 | Putnam |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
ROW
|  |  | 1400239 | Vigo |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1400240 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1400241 | Warren |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1400242 | Vigo |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1400243 | Vigo |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1400244 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400245 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400246 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | PE
ROW
|  |  | 1400247 | Owen |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1400248 | Benton |  | Indiana Department of Transportation | 2020-03-04 | PE
UT
|  |  | 1400249 | Warren |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1400250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400251 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
RR
|  |  | 1400252 |  | Afram Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1400253 | Warren |  | Indiana Department of Transportation | 2023-03-15 | PE
|  |  | 1400254 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400255 |  | Indiana University | Indiana Department of Transportation | -339679.2083
|  |  | 1400256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400257 | Clinton |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1400258 |  | ETC Institute | Indiana Department of Transportation | -339679.2083
|  |  | 1400259 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400262 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400263 | Clinton | Iteris, Inc. | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
ROW
|  |  | 1400264 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400265 | Clinton |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
ROW
|  |  |  | Howard |  | Indiana Department of Transportation | 2020-02-19 | PE
|  |  | 1400266 | Montgomery |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
ROW
RR
UT
|  |  | 1400267 | Lawrence |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400268 | Lawrence |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400269 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 1400270 | Harrison |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400271 | Hendricks |  | Hendricks County | 2016-03-02 | CN
|  |  | 1400272 | Hendricks |  | Avon | 2018-11-15 | CE
CN
UT
|  |  | 1400273 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400274 | Hendricks |  | Avon | 2018-02-07 | CN
|  |  | 1400275 | Hendricks |  | Avon | 2017-12-13 | CE
CN
|  |  | 1400276 | Hendricks |  | Avon | 2015-03-04 | CE
CN
|  |  | 1400277 | Hendricks |  | Avon | 2015-03-04 | CE
CN
|  |  | 1400278 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400279 | Marion |  | Speedway | 2017-07-12 | CE
CN
|  |  | 1400280 | Marion |  | Lawrence | -339679.2083 | PE
ROW
RR
|  |  | 1400281 | Delaware |  | Delaware County | -339679.2083 | PE
|  |  | 1400282 | Gibson |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400283 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400284 | Jasper |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400285 | St. Joseph |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400286 | Starke |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1400287 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
ROW
|  |  | 1400288 | Daviess |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400289 | Daviess |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400290 | Pike |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400291 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400292 | Dubois |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1400293 | Dubois |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1400294 | Dubois |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
|  |  | 1400295 | Orange |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1400296 | St. Joseph |  | St. Joseph County | 2016-04-06 | CE
CN
ROW
|  |  | 1400297 | Johnson |  | Franklin | 2016-07-13 | CE
CN
RR
|  |  | 1400298 | Johnson |  | Franklin | 2017-12-13 | CE
CN
|  |  | 1400299 |  |  | Franklin | 2014-02-17
|  |  | 1400300 |  |  | Franklin | 2021-05-31
|  |  | 1400301 | Johnson |  | Franklin | 2018-04-11 | CN
|  |  | 1400302 |  |  | Franklin | 2020-05-31
|  |  | 1400303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400305 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1400306 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1400307 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1400308 | Vanderburgh |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1400309 |  | Fusion by Design, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400310 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2014-05-31
|  |  | 1400311 | Brown |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1400325 | Lake |  | Indiana Department of Transportation | 2016-05-31 | ROW
|  |  | 1400326 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21
|  |  | 1400327 | Adams |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400328 | Adams | Bidinfo | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400331 | Miami |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400332 | Miami |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400333 | Miami |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400334 | Miami |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400335 | Miami |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1400336 | Union |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
ROW
|  |  | 1400337 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1400338 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400339 | Boone |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400340 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400341 | Boone |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400342 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400343 | Kosciusko |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400344 | Marion |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400345 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400346 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400347 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400348 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400349 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1400350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400351 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400352 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400353 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400354 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400355 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400356 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400357 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400358 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400359 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400360 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400361 | Elkhart |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400362 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400363 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400364 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400365 | Brown |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
ROW
|  |  | 1400366 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400367 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400368 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400369 | Allen |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400370 | Noble |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400371 | Noble |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400373 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400374 | Whitley |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400375 | Allen |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400376 | Noble |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400377 | Whitley |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400378 |  | Global Management Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400379 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400380 | Dekalb |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400381 | Steuben |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400382 | Steuben |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1400383 | Allen |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400384 | Allen |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400385 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400386 | Henry |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400387 | Henry |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400388 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400389 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400390 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400391 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400392 | Madison |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400393 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400394 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400395 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400396 | Fayette |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400397 | Rush |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400398 | Henry |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400399 | Madison |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400400 | Hancock |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400401 | Delaware |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400402 | Grant |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400404 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400405 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400406 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400407 | Madison |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400408 | Delaware |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400409 | Delaware |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400410 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400411 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400412 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400413 | Hamilton |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400414 |  | CGI | Indiana Department of Transportation | 2014-04-02
|  |  | 1400415 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400416 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400417 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400418 | Grant |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400419 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400420 | LaGrange |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400421 | Steuben |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400422 | Johnson |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1400423 | Steuben |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400424 | Allen |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400425 | Miami |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400426 | Miami |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400427 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400428 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400429 | Adams |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400430 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400431 | Johnson |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1400432 | Johnson |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1400433 | Grant |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400434 | Grant |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400435 | Grant |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400436 | Grant |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400437 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400438 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400439 | Grant |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400441 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400443 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400444 | Huntington |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400445 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400446 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400447 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400448 | Allen |  | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400449 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400450 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-12-09 | CE
CN
|  |  | 1400451 | Johnson |  | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1400452 | Owen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400453 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2015-07-08 | CE
CN
|  |  | 1400454 | Washington |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400455 | Blackford |  | Blackford County | -339679.2083 | PE
|  |  |  | Various |  | Blackford County | -339679.2083 | PE
|  |  | 1400456 | Montgomery |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400458 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400459 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400460 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400461 | Floyd |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400462 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400463 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400465 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400466 |  | Martinez Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1400467 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400468 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400469 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400470 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400471 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400472 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400473 | Floyd |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
|  |  | 1400474 | Bartholomew |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400475 | Bartholomew |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400476 | Bartholomew |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400477 | Bartholomew |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400478 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400479 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400480 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400481 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400482 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400483 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400484 | Boone |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400485 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400486 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400487 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400488 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400489 | Marion |  | Indianapolis | 2016-11-16 | CN
|  |  | 1400490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400492 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400493 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400494 | Marion | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400495 | Marion | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400496 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400497 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400498 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1400499 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1400500 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1400501 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400502 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400503 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400504 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400505 | Marion |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400507 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400510 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400511 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400512 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400515 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400516 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400521 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400522 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400523 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400524 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400525 | Clinton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1400526 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400527 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400529 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400530 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400531 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1400532 |  |  | Michigan City Transit | -339679.2083
|  |  | 1400533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400534 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400536 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1400537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400539 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1400540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400542 | Montgomery |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400543 | Vermillion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400544 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400545 | Hendricks |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400546 | Hendricks |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400547 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400548 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400549 | Vanderburgh |  | Vanderburgh County | 2018-08-08 | CE
CN
UT
|  |  | 1400550 | Floyd |  | Floyd County | 2023-07-12 | PE
ROW
|  |  | 1400551 | Fountain |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400552 | Clinton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1400553 | Clay |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400554 | Tippecanoe |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400555 | Owen |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1400556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400557 | Clinton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1400558 | Clinton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1400559 | Clay |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400560 | Putnam |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400561 | Putnam |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400562 | Putnam |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400563 | Morgan |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400564 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400565 |  |  | Michigan City Transit | -339679.2083
|  |  | 1400566 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2017-01-19 | CN
|  |  | 1400567 | Johnson |  | Franklin | 2016-07-13 | CE
CN
|  |  | 1400568 | Lake |  | Lake County | 2016-12-14 | CE
CN
|  |  | 1400569 | Porter | Leitner and Associates, Inc. | Valparaiso | 2017-03-01 | CE
CN
ROW
|  |  | 1400570 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1400571 | LaPorte |  | LaPorte County | 2015-05-31 | PE
|  |  | 1400572 | Porter |  | MPO - Northwest | 2014-05-05 | PL
|  |  | 1400573 | Porter |  | Chesterton | 2015-05-31 | PE
|  |  | 1400574 | Lake |  | Crown Point | 2014-05-05 | PL
|  |  | 1400575 | Lake |  | East Chicago | 2016-05-31 | PL
|  |  | 1400576 | Lake |  | Gary | 2015-05-31 | PE
|  |  | 1400577 | Lake |  | Highland | 2015-05-31 | PE
|  |  | 1400578 | Porter |  | Porter | 2015-05-31 | PE
|  |  | 1400579 | Lake |  | Winfield | 2015-05-31 | PE
|  |  | 1400580 | Marion |  | Indianapolis | 2015-07-08 | CE
CN
|  |  | 1400581 | Hamilton |  | Fishers | 2018-01-18 | CN
ROW
|  |  | 1400582 | Owen |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2014-10-08 | CE
CN
|  |  | 1400583 | Marion |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1400584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400585 |  |  | East Chicago | 2014-03-14
|  |  | 1400586 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-04-15 | CE
CN
|  |  | 1400587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400588 | Lawrence |  | Bedford | 2015-10-07 | CE
CN
PE
ROW
UT
|  |  | 1400589 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1400590 | Cass |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400591 | Cass |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400592 | Carroll |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1400593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400594 | St. Joseph |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
RR
|  |  | 1400595 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | -339679.2083
|  |  | 1400596 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400597 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
ROW
UT
|  |  | 1400598 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400599 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1400600 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
RR
|  |  | 1400601 | White |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400602 |  |  | MPO - Louisville | 2016-05-31
|  |  | 1400603 |  |  | MPO - Louisville | -339679.2083
|  |  | 1400604 | Various |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400605 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | RR
|  |  | 1400606 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400607 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400608 | Sullivan | Klug Engineering, Inc. | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400609 | Sullivan | Klug Engineering, Inc. | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400610 | Sullivan | Anelena Ackerly | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400611 | Posey |  | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400612 | Posey |  | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400613 | Posey | GRL Engineers, Inc. | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400614 | Dubois |  | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400615 | Floyd |  | Indiana Department of Transportation | 2018-05-31 | PE
RR
|  |  | 1400616 | Floyd |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400617 | Floyd |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400618 | Floyd | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400619 | Harrison |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400620 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400621 | Montgomery |  | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1400622 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400623 | Fayette |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400624 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1400625 | Madison |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400626 | Tipton |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1400627 | Wayne |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400628 | Blackford |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1400629 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400630 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400631 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400632 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1400633 | St. Joseph | Flexible H.R. Solutions, LLC | Mishawaka | 2018-07-11 | CE
CN
|  |  | 1400634 | St. Joseph |  | South Bend | 2019-09-11 | CN
PE
ROW
|  |  | 1400635 | St. Joseph |  | South Bend | 2015-09-02 | CE
CN
PE
|  |  | 1400636 | St. Joseph |  | South Bend | 2015-12-09 | CE
CN
PE
|  |  | 1400637 | St. Joseph |  | South Bend | 2020-04-01 | CE
CN
PE
ROW
RR
|  |  | 1400638 | St. Joseph |  | St. Joseph County | 2021-11-17 | CE
CN
PE
ROW
|  |  | 1400639 | St. Joseph |  | St. Joseph County | 2020-12-09 | CE
CN
PE
ROW
UT
|  |  | 1400640 | St. Joseph |  | St. Joseph County | 2017-07-12 | CE
CN
PE
ROW
|  |  | 1400641 | St. Joseph |  | St. Joseph County | 2017-04-05 | CE
CN
PE
|  |  | 1400642 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2020-05-31
|  |  | 1400643 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1400644 |  |  | Indiana Department of Transportation | 2014-05-31
|  |  | 1400645 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1400646 | Gibson |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1400647 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1400648 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2015-09-02 | CE
CN
ROW
UT
|  |  | 1400649 | Bartholomew |  | MPO - Columbus | -339679.2083 | PL
|  |  | 1400650 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1400651 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1400652 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400653 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400654 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400655 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400656 |  |  | Indiana Department of Transportation | 2014-08-06
|  |  | 1400657 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400658 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400659 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400660 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1400661 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400662 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400663 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400664 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400665 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400666 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1400667 | Jasper |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400668 | Jasper |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1400669 |  |  | Indiana Department of Transportation | 2015-07-08
|  |  | 1400670 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400671 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400672 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400673 |  | Another Test Company | Carmel | 2015-03-06
|  |  | 1400674 | Various |  | Indiana Department of Transportation | 2014-05-21 | CE
CN
|  |  | 1400675 | Dearborn |  | Dearborn County | 2020-03-04 | CE
CN
PE
ROW
UT
|  |  | 1400676 | Dearborn |  | Dearborn County | 2015-05-31 | PE
|  |  | 1400677 | Various |  | Indiana Department of Transportation | 2014-05-28 | CE
CN
|  |  | 1400678 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400679 | Boone | DuSABLE, Inc. | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  |  | Clinton | DuSABLE, Inc. | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400680 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400681 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400682 | Tippecanoe |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400683 | Parke |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1400684 | Parke |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1400685 | Clay |  | Indiana Department of Transportation | 2014-09-10 | CE
CN
|  |  | 1400686 | Fountain |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400687 | Montgomery |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400688 | Putnam |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400689 |  | DCD Consulting LLC | Indiana Department of Transportation | 2014-08-06
|  |  | 1400690 |  |  | Indiana Department of Transportation | 2014-07-23
|  |  | 1400691 | Clay |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1400692 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2014-04-21 | CN
|  |  | 1400693 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400694 | Allen | Global Management Group, Inc. | New Haven | -339679.2083 | PE
ROW
RR
|  |  | 1400695 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400696 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400697 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400698 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400699 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400700 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400701 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400702 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400703 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400704 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400705 | Perry |  | Indiana Department of Transportation | 2014-05-30 | CE
CN
|  |  | 1400706 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400707 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400708 |  | DCD Consulting LLC | Indiana Department of Transportation | 2014-08-06
|  |  | 1400709 | Hendricks |  | Hendricks County | 2017-07-12 | CE
CN
|  |  | 1400710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400711 | Various |  | Indiana Department of Natural Resources | -339679.2083 | PL
|  |  | 1400712 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2019-04-03 | CN
PE
ROW
|  |  | 1400713 | Elkhart | Civil Inspection Services, LLC | Goshen | 2018-02-07 | CE
CN
ROW
RR
|  |  | 1400714 | Elkhart | Civil Inspection Services, LLC | Goshen | 2017-05-31 | PE
RR
|  |  | 1400715 | Elkhart | Civil Inspection Services, LLC | Goshen | 2022-03-09 | PE
ROW
|  |  | 1400716 | Knox |  | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1400717 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400718 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400719 | Franklin |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
ROW
|  |  | 1400720 | Miami | Atlas Appraisals, LLC | Converse | 2017-07-12 | CE
CN
PE
|  |  | 1400721 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400722 | Decatur | Collier Transport Inc. | Greensburg | 2020-07-08 | CE
CN
PE
ROW
UT
|  |  | 1400723 |  |  | Dearborn County | -339679.2083
|  |  | 1400724 |  |  | Clark County | -339679.2083
|  |  | 1400725 | Dearborn |  | Dearborn County | 2020-09-02 | CE
CN
PE
ROW
|  |  | 1400726 |  |  | Harrison County | -339679.2083
|  |  | 1400727 |  |  | Aurora | -339679.2083
|  |  | 1400728 |  |  | Elkhart | -339679.2083
|  |  | 1400729 |  |  | Elkhart | -339679.2083
|  |  | 1400730 |  |  | Elkhart | -339679.2083
|  |  | 1400731 |  |  | Elkhart | -339679.2083
|  |  | 1400732 |  |  | Elkhart | -339679.2083
|  |  | 1400733 |  |  | Elkhart | -339679.2083
|  |  | 1400734 |  |  | Elkhart | -339679.2083
|  |  | 1400735 | Miami | Atlas Appraisals, LLC | Converse | 2017-11-15 | CE
CN
PE
|  |  | 1400736 |  |  | South Bend | -339679.2083
|  |  | 1400737 |  | ABt SRBI | Angola | -339679.2083
|  |  | 1400738 |  |  | South Bend | -339679.2083
|  |  | 1400739 | Steuben |  | Steuben County | 2018-01-18 | CE
CN
PE
ROW
RR
|  |  | 1400740 |  |  | South Bend | -339679.2083
|  |  | 1400741 |  |  | South Bend | -339679.2083
|  |  | 1400742 |  |  | South Bend | -339679.2083
|  |  | 1400743 | Dekalb | American Engineers, Inc. | Butler | 2017-11-15 | CE
CN
PE
|  |  | 1400744 | Hancock |  | Hancock County | 2019-12-11 | CE
CN
|  |  | 1400745 |  |  | Hancock County | -339679.2083
|  |  | 1400746 |  |  | Hancock County | -339679.2083
|  |  | 1400747 |  |  | Hancock County | -339679.2083
|  |  | 1400748 |  | CGS Real Estate Services, LLC | Fairmount | -339679.2083
|  |  | 1400749 |  |  | Hancock County | -339679.2083
|  |  | 1400750 |  | CGS Real Estate Services, LLC | Fairmount | -339679.2083
|  |  | 1400751 | Fayette | Wilcox Environmental Engineering, Inc. | Connersville | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1400752 |  | CGS Real Estate Services, LLC | Fairmount | -339679.2083
|  |  | 1400753 |  |  | Shelbyville | -339679.2083
|  |  | 1400754 |  |  | Henry County | -339679.2083
|  |  | 1400755 |  | Jeffrey S. Juday | Shelbyville | -339679.2083
|  |  | 1400756 | Randolph |  | Randolph County | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1400757 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 1400758 |  |  | Wayne County | -339679.2083
|  |  | 1400759 |  |  | Wayne County | -339679.2083
|  |  | 1400760 | Hamilton |  | Hamilton County | 2019-10-09 | CE
CN
PE
ROW
|  |  | 1400761 |  |  | Hagerstown | -339679.2083
|  |  | 1400762 |  |  | Rush County | -339679.2083
|  |  | 1400763 | Wayne |  | Hagerstown | 2018-10-11 | CE
CN
PE
ROW
RR
|  |  | 1400764 |  |  | Hagerstown | -339679.2083
|  |  | 1400765 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 1400766 | Rush |  | Rush County | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1400767 |  | Civil Designs, LLP | Glenwood | -339679.2083
|  |  | 1400768 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1400769 | Wayne | Indiana Appraisal Group, Inc. | Wayne County | 2018-01-18 | CE
CN
PE
|  |  | 1400770 |  |  | Madison County | -339679.2083
|  |  | 1400771 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 1400772 | Rush | J. Williams Appraisal Group, LLC | Rushville | 2022-02-09 | PE
ROW
|  |  | 1400773 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2017-07-12 | CE
CN
PE
|  |  | 1400774 | LaPorte |  | LaPorte County | 2018-03-14 | CE
CN
PE
|  |  | 1400775 |  |  | LaPorte County | -339679.2083
|  |  | 1400776 | Cass |  | Cass County | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1400777 |  |  | Porter County | -339679.2083
|  |  | 1400778 |  |  | Centerville | -339679.2083
|  |  | 1400779 | Clark |  | Clark County | 2018-01-18 | CE
CN
PE
|  |  | 1400780 | Henry |  | St. Joseph County | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1400781 | White |  | White County | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1400782 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1400783 | Monroe |  | Monroe County | 2021-04-07 | CE
CN
PE
ROW
UT
|  |  | 1400784 | Greene | Eagle Ridge Civil Engineering Services, LLC | Greene County | 2018-12-12 | CE
CN
PE
ROW
UT
|  |  | 1400785 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2018-08-08 | CE
CN
PE
|  |  | 1400786 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2018-07-11 | CE
CN
PE
ROW
RR
|  |  | 1400787 |  |  | Carmel | -339679.2083
|  |  | 1400788 | Hamilton |  | Hamilton County | 2019-10-09 | CE
CN
ROW
|  |  | 1400789 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 1400790 | Boone | E.J. Breneman, LP | Lebanon | 2019-01-16 | CE
CN
PE
ROW
UT
|  |  | 1400791 | Noble |  | Albion | -339679.2083 | PE
|  |  | 1400792 |  | Fink Roberts & Petrie | Kosciusko County | -339679.2083
|  |  | 1400793 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1400794 | Montgomery | Banning Engineering, P.C. | Crawfordsville | 2018-02-07 | CE
CN
PE
ROW
RR
|  |  | 1400795 | Parke | Infrastructure Engineers, Inc. | Rockville | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1400796 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1400797 |  | Hannum, Wagle & Cline Engineering | Orleans | -339679.2083
|  |  | 1400798 |  |  | Perry County | -339679.2083
|  |  | 1400799 | Shelby |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
ROW
|  |  | 1400800 |  |  | Spencer County | -339679.2083
|  |  | 1400801 | Grant |  | Grant County | 2018-03-14 | ROW
|  |  | 1400802 | Vermillion |  | Vermillion County | 2017-08-09 | PE
|  |  |  | Warren |  | Vermillion County | 2017-08-09 | CE
CN
PE
ROW
|  |  | 1400803 |  |  | Vermillion County | -339679.2083
|  |  | 1400804 | Crawford |  | Crawford County | 2020-11-10 | CE
CN
PE
ROW
|  |  | 1400805 | Fountain | McCord, Inc. | Warren County | 2019-09-11 | CE
CN
PE
|  |  |  | Warren | McCord, Inc. | Warren County | 2019-09-11 | PE
|  |  | 1400806 |  | ASC Group, Inc. | Beech Grove | -339679.2083
|  |  | 1400807 |  | CTLGroup | Fortville | -339679.2083
|  |  | 1400808 |  |  | South Whitley | -339679.2083
|  |  | 1400809 | Whitley |  | South Whitley | 2017-05-10 | CE
CN
PE
|  |  | 1400810 | Grant | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2017-07-12 | CE
CN
PE
|  |  | 1400811 | Hamilton | CPS Acquisitions, LLC | Fishers | 2019-01-16 | CE
CN
PE
ROW
UT
|  |  | 1400812 | Knox | Louis Joyner, Architect | Knox County | 2018-08-08 | CE
CN
PE
|  |  | 1400813 |  | Engineering Resources, Inc. | Madison | -339679.2083
|  |  | 1400814 |  |  | Brown County | -339679.2083
|  |  | 1400815 |  | ARCADIS | Batesville | -339679.2083
|  |  | 1400816 | Daviess | AMEC E&I, Inc. | Washington | 2018-07-11 | CE
CN
PE
|  |  | 1400817 |  |  | Harrison County | -339679.2083
|  |  | 1400818 | Randolph | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2019-12-11 | CN
PE
ROW
|  |  | 1400819 | Gibson | HNTB Indiana, Inc. | Oakland City | 2018-11-15 | CE
CN
PE
ROW
RR
|  |  | 1400820 |  |  | Indianapolis | -339679.2083
|  |  | 1400821 |  | Boomerang Ventures, LLC | Dunkirk | -339679.2083
|  |  | 1400822 |  |  | Indianapolis | -339679.2083
|  |  | 1400823 |  |  | Indianapolis | -339679.2083
|  |  | 1400824 |  |  | Crawford County | -339679.2083
|  |  | 1400825 | Crawford |  | Crawford County | 2023-07-12 | CE
CN
PE
ROW
UT
|  |  | 1400826 | Allen |  | Allen County | 2018-03-14 | CE
CN
|  |  | 1400827 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1400828 |  | Hannum, Wagle & Cline Engineering | Orleans | -339679.2083
|  |  | 1400829 | Noble | ERES International, Inc. | Noble County | 2018-01-18 | CE
CN
PE
ROW
|  |  | 1400830 | Perry |  | Perry County | 2018-12-12 | CE
CN
PE
ROW
UT
|  |  | 1400831 |  |  | Noble County | -339679.2083
|  |  | 1400832 | Dekalb | Cheri K. Lewis Engineers | Garrett | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1400833 |  | Mader Design, LLC | Waterloo | -339679.2083
|  |  | 1400834 |  | GRL Engineers, Inc. | Mount Vernon | -339679.2083
|  |  | 1400835 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1400836 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | -339679.2083
|  |  | 1400837 |  |  | Kosciusko County | -339679.2083
|  |  | 1400838 |  |  | Noble County | -339679.2083
|  |  | 1400839 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 1400840 |  |  | Santa Claus | -339679.2083
|  |  | 1400841 | Elkhart |  | Elkhart County | 2017-12-13 | CE
CN
PE
|  |  | 1400842 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1400843 | Lake |  | Lake County | 2018-02-07 | CE
CN
PE
ROW
|  |  | 1400844 | White | Fugro Roadware, Inc. | Monticello | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1400845 |  |  | Lake County | -339679.2083
|  |  | 1400846 |  | Fugro Roadware, Inc. | White County | -339679.2083
|  |  | 1400847 |  |  | St. Joseph County | -339679.2083
|  |  | 1400848 | Cass | Eco Logic, LLC | Cass County | 2018-01-18 | CE
CN
PE
|  |  | 1400849 | Starke | H.R. Gray | North Judson | 2017-07-12 | CE
CN
PE
|  |  | 1400850 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1400851 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1400852 |  |  | South Bend | -339679.2083
|  |  | 1400853 |  |  | South Bend | -339679.2083
|  |  | 1400854 |  |  | Chesterton | -339679.2083
|  |  | 1400855 | Clinton | Carters Appraisal Service | Frankfort | 2018-03-14 | CN
PE
|  |  |  | Various | Carters Appraisal Service | Frankfort | 2018-03-14 | CE
CN
|  |  | 1400856 |  |  | Indiana Department of Natural Resources | -339679.2083
|  |  | 1400857 | Franklin |  | Franklin County | 2019-03-06 | CE
CN
PE
|  |  | 1400858 | Owen | KHAFRA Engineering Consultants, Inc. | Spencer | 2017-08-09 | CE
CN
PE
|  |  | 1400859 |  |  | Franklin County | -339679.2083
|  |  | 1400860 |  | ERES International, Inc. | Marion | -339679.2083
|  |  | 1400861 |  |  | Noble County | -339679.2083
|  |  | 1400862 |  |  | Noble County | -339679.2083
|  |  | 1400863 |  | M-E Companies, Inc. | Wabash | -339679.2083
|  |  | 1400864 | Hamilton |  | Westfield | 2017-08-09 | CN
PE
ROW
UT
|  |  | 1400865 |  |  | Westfield | -339679.2083
|  |  | 1400866 |  |  | Indianapolis | -339679.2083
|  |  | 1400867 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 1400868 | Vermillion | Archaeology and Geomorphology Services | Clinton | 2016-05-05 | CE
CN
PE
|  |  | 1400869 | Fountain |  | Veedersburg | 2015-01-09 | PE
|  |  | 1400870 | Henry | GeoSolutions, Inc. | New Castle | 2018-04-11 | CN
PE
ROW
|  |  | 1400871 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400872 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400873 | Hamilton |  | Hamilton County | 2018-02-07 | CN
|  |  | 1400874 | Hamilton |  | Fishers | 2017-11-15 | CN
ROW
|  |  | 1400875 | Spencer |  | Indiana Department of Transportation | 2014-06-20 | CE
CN
PE
ROW
|  |  | 1400876 | Spencer |  | Indiana Department of Transportation | 2014-06-20 | CE
CN
ROW
UT
|  |  | 1400877 | Spencer |  | Indiana Department of Transportation | 2014-06-20 | CE
CN
ROW
|  |  | 1400878 | Parke |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1400879 |  |  | Jackson County | 2014-12-10
|  |  | 1400880 | Morgan |  | Indiana Department of Transportation | 2014-11-13 | CE
CN
|  |  | 1400881 | Dubois | Danch Harner and Associates, Inc. | Jasper | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1400882 | Johnson |  | Greenwood | 2018-01-18 | CE
CN
|  |  | 1400883 | Johnson |  | Greenwood | 2016-08-10 | CE
CN
|  |  | 1400884 |  | Casteel Real Estate | Franklin | -339679.2083
|  |  | 1400885 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 1400886 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400887 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1400888 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1400889 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400890 | Jennings |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400891 | Jennings | Engineering Resources, Inc. | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400892 | Jennings |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400893 | Jennings |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400894 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400895 | Jennings |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400896 | Jennings |  | Indiana Department of Transportation | 2015-05-08 | CE
CN
|  |  | 1400897 | Jennings |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1400898 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400899 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400900 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400901 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1400902 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1400903 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400904 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | 2015-02-04 | CE
CN
|  |  | 1400905 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400906 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400907 | LaGrange |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400908 | Kosciusko | Home Guide Realty Services | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400909 | Kosciusko | Home Guide Realty Services | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400910 | Allen |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400911 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400912 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1400913 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1400914 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400915 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400916 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400917 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400918 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
UT
|  |  | 1400919 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400920 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400921 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400922 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400923 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400924 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400925 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1400926 | Boone | Martinez Corporation | Whitestown | 2018-01-18 | CE
CN
UT
|  |  | 1400927 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400928 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1400929 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1400930 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400931 | Madison | AAC Environmental Consulting, LLC | Anderson | 2016-04-06 | CE
CN
PE
|  |  | 1400932 | Cass |  | Cass County | -339679.2083 | PE
|  |  |  | Various |  | Cass County | -339679.2083 | PE
|  |  | 1400933 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1400934 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
|  |  | 1400935 |  |  | Indianapolis | -339679.2083
|  |  | 1400936 |  |  | Westfield | -339679.2083
|  |  | 1400937 | Hamilton |  | Carmel | 2017-08-09 | CE
CN
|  |  | 1400938 | Marion | DCD Consulting LLC | Indianapolis | 2016-05-31 | OT
PE
|  |  | 1400939 | Marion |  | Indianapolis | 2017-07-12 | CN
|  |  | 1400940 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CE
CN
|  |  | 1400941 | Marion | DCD Consulting LLC | Indianapolis | 2018-02-07 | CE
CN
UT
|  |  | 1400942 | Marion |  | Indianapolis | 2019-02-06 | CE
CN
|  |  | 1400943 | Marion |  | Indianapolis | 2018-11-15 | CE
CN
|  |  | 1400944 | Marion |  | Indianapolis | 2020-01-15 | CE
CN
|  |  | 1400945 |  |  | Indiana Department of Transportation | 2015-04-01
|  |  | 1400946 |  |  | Indiana Department of Transportation | 2015-04-01
|  |  | 1400947 | Scott |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1400948 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400949 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400950 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400951 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400952 | Jefferson |  | Indiana Department of Transportation | 2015-04-01 | CE
|  |  |  | Switzerland |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1400953 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1400954 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400955 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400956 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400957 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400958 | Clark |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400959 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1400960 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1400961 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400962 | Benton |  | Benton County | -339679.2083 | PE
|  |  | 1400963 | Vigo | Bayswater Company, LLC | Terre Haute | 2016-11-16 | CN
RR
|  |  | 1400964 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400965 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1400966 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1400967 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1400968 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1400969 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2016-01-13 | CN
|  |  | 1400970 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2015-07-08 | CE
CN
|  |  | 1400971 | Various |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
RR
|  |  | 1400972 | Various |  | Indiana Department of Transportation | 2014-08-06 | CE
CN
|  |  | 1400973 | Marion |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1400974 | Marion |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1400975 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1400976 | Henry |  | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400977 | Randolph | Eel River Abstract | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400978 | Jay | Alliance Survey Company | Indiana Department of Transportation | 2014-08-20 | CE
CN
|  |  | 1400979 | Randolph |  | Indiana Department of Transportation | 2014-09-04 | CE
CN
|  |  | 1400980 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1400981 |  |  | Monroe | -339679.2083
|  |  | 1400982 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
UT
|  |  | 1400983 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1400984 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1400992 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1400993 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1400994 | Howard |  | Howard County | 2017-03-01 | CE
CN
PE
|  |  | 1400995 | Elkhart | Civil Inspection Services, LLC | Goshen | 2019-01-16 | CE
CN
PE
RR
|  |  | 1400996 | Various |  | Indiana Counties | -339679.2083 | PL
|  |  | 1400997 | Union |  | Union County | -339679.2083 | PE
|  |  | 1400998 | Hendricks |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  |  | Morgan |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1400999 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401000 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401001 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401002 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401003 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401004 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401005 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401006 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401007 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401008 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401009 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401011 |  |  | Decatur County | -339679.2083
|  |  | 1401012 | Jackson |  | Indiana Department of Transportation | 2015-07-08 | CE
|  |  |  | Marion |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2015-07-08 | CN
|  |  | 1401013 |  |  | Ridgeville | -339679.2083
|  |  | 1401014 |  |  | Lynn | -339679.2083
|  |  | 1401015 | Marion |  | Indianapolis | 2018-12-12 | CE
CN
|  |  | 1401017 | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 1401022 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401023 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401024 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1401025 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1401026 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1401027 | LaPorte |  | LaPorte County | 2021-09-15 | CE
CN
PE
ROW
|  |  | 1401028 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1401029 | Porter |  | Porter County | 2022-03-09 | PE
ROW
|  |  | 1401030 | Lake | Baxter & Woodman, Inc. | Crown Point | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1401031 |  |  | Indiana Department of Transportation | 2015-02-04
|  |  | 1401032 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2017-05-12 | CN
PE
|  |  | 1401033 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2015-02-04
|  |  | 1401034 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2022-03-09 | PE
ROW
|  |  | 1401035 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-02-04
|  |  | 1401036 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | CN
|  |  | 1401037 |  |  | South Bend Transit | -339679.2083
|  |  | 1401038 |  |  | South Bend Transit | -339679.2083
|  |  | 1401039 |  |  | South Bend Transit | -339679.2083
|  |  | 1401040 |  |  | South Bend Transit | -339679.2083
|  |  | 1401041 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 1401042 | LaPorte |  | LaPorte County | 2017-01-19 | CE
CN
PE
|  |  | 1401043 | LaPorte | Farah and Sons, Inc. | Michigan City | 2016-03-02 | CE
CN
|  |  | 1401044 |  |  | Indiana Department of Transportation | 2015-02-04
|  |  | 1401045 | Lake | Courtland Title & Escrow, Inc. | Hobart | 2017-01-19 | CE
CN
PE
|  |  | 1401046 | Lake |  | Merrillville | 2017-03-01 | CE
CN
PE
|  |  | 1401047 | Tippecanoe |  | Tippecanoe County | 2018-10-11 | CN
|  |  | 1401048 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1401049 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1401050 |  |  | Indiana Department of Transportation | 2015-04-01
|  |  | 1401051 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401052 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2015-08-05 | CE
CN
PE
|  |  | 1401053 | Various |  | MPO - Terre Haute | -339679.2083 | PL
|  |  |  | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 1401056 |  |  | Indiana Department of Transportation | 2014-09-10
|  |  | 1401057 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1401066 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1401067 | Marion |  | Indiana Department of Natural Resources | -339679.2083 | OT
|  |  | 1401068 | Grant |  | Indiana Department of Natural Resources | 2016-05-31 | CN
PE
ROW
|  |  | 1401069 | Decatur |  | Indiana Department of Natural Resources | 2016-05-31 | PE
|  |  | 1401070 | Spencer |  | Indiana Department of Natural Resources | 2016-05-31 | CN
PE
ROW
|  |  | 1401071 |  | Mader Design, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1401072 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1401073 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1401074 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1401075 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401076 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1401077 | Various |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1401080 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401081 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401082 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401083 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401084 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1401085 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
RR
|  |  | 1401086 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1401087 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1401088 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1401089 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
|  |  | 1401090 | Allen |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
RR
|  |  | 1401091 | Porter |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1401092 | Porter |  | MPO - Northwest | -339679.2083 | PL
|  |  |  | Various |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1401093 | Various |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1401094 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 1401095 | Various |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1401096 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1401097 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1401098 | Various |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1401099 | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  |  | Various |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1401100 | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  |  | Various |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1401101 | Various |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1401102 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1401103 |  |  | Indiana Department of Transportation | 2016-04-06
|  |  | 1401104 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  |  | Various |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1401105 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  |  | Various |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1401106 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1401107 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2014-12-17
|  |  | 1401108 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2014-12-17
|  |  | 1401109 | Jackson |  | MPO - Cincinnati | -339679.2083 | PL
|  |  |  | Various |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1401110 | Jackson |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1401111 | Henry |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401112 | Blackford |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  |  | Jay |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401113 |  |  | MPO - Cincinnati | -339679.2083
|  |  | 1401114 | Various |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1401115 | Tippecanoe |  | MPO - Lafayette | -339679.2083 | PL
|  |  |  | Various |  | MPO - Lafayette | -339679.2083 | PL
|  |  | 1401116 | Tippecanoe |  | MPO - Lafayette | -339679.2083 | PL
|  |  | 1401117 | Fayette | Civil Designs, LLP | Indiana Department of Transportation | 2015-04-01 | CE
|  |  |  | Rush | Civil Designs, LLP | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401118 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1401119 | Various |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1401120 | Various |  | MPO - Muncie | -339679.2083 | PL
|  |  | 1401121 | Various |  | MPO - Muncie | -339679.2083 | PL
|  |  | 1401122 | Delaware |  | Indiana Department of Natural Resources | 2016-05-31 | CN
PE
|  |  | 1401123 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  |  | Various |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1401124 | Carroll |  | Indiana Department of Natural Resources | 2016-05-31 | PE
|  |  | 1401125 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  |  | Various |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1401126 | Henry |  | Indiana Department of Natural Resources | 2016-05-31 | CN
PE
ROW
|  |  | 1401127 | Miami |  | Indiana Department of Natural Resources | 2017-05-31 | CN
PE
ROW
|  |  | 1401128 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1401129 | St. Joseph |  | St. Joseph County | 2017-12-13 | CN
|  |  | 1401130 | St. Joseph |  | St. Joseph County | 2017-12-13 | CN
|  |  | 1401131 | Various |  | Indiana Department of Natural Resources | 2017-05-31 | OT
|  |  | 1401132 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2015-05-31
|  |  | 1401133 | Various |  | MPO - Muncie | -339679.2083 | PL
|  |  | 1401134 |  | Hambleton LLC | Orland | 2017-05-31
|  |  | 1401135 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401136 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401137 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401138 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401139 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401140 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401141 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401142 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401143 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401144 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401145 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401146 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 1401147 |  |  | Indiana Department of Transportation | 2014-10-08
|  |  | 1401148 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1401149 |  |  | South Bend Transit | -339679.2083
|  |  | 1401150 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1401151 | Madison |  | Pendleton | 2019-02-06 | CN
PE
|  |  | 1401152 | Madison |  | Pendleton | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1401153 | Boone |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1401154 | Floyd |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1401155 | Decatur |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401156 | Decatur |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401157 | Johnson |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1401158 | Decatur |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401159 | Decatur |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401161 | Jackson |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401162 | Jackson |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401163 | Jackson |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401164 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2017-12-13 | CN
|  |  | 1401165 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401166 | Johnson |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401167 | Jackson |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401168 | Spencer |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1401169 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401170 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401171 |  | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | -339679.2083
|  |  | 1401172 | Marion |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  |  | Various |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401173 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401174 | Hamilton |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401175 |  |  | Indiana Department of Transportation | 2016-01-13
|  |  | 1401176 |  |  | Indiana Department of Transportation | 2016-01-13
|  |  | 1401177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401178 | Floyd |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1401179 | Jennings |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
RR
|  |  | 1401180 | Johnson |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1401181 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401182 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401183 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401184 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401185 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401186 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401187 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401188 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401189 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401190 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401191 | St. Joseph |  | St. Joseph County | 2016-02-17 | CE
CN
RR
|  |  | 1401192 | St. Joseph |  | St. Joseph County | 2016-02-17 | CE
CN
RR
|  |  | 1401193 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401194 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401195 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401196 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401202 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401203 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1401204 |  |  | Indiana Department of Transportation | 2016-01-13
|  |  | 1401208 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2015-01-14 | CE
CN
|  |  | 1401209 | Jennings |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  |  | Switzerland |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401210 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1401216 | Perry |  | Perry County | -339679.2083 | PE
|  |  |  | Various |  | Perry County | -339679.2083 | PE
|  |  | 1401217 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-04-15
|  |  | 1401218 |  | Carters Appraisal Service | Indiana Department of Transportation | 2015-05-31
|  |  | 1401219 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401220 | Harrison | Dreibelbiss Title Company, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401221 | Sullivan |  | Sullivan County | -339679.2083 | PE
|  |  | 1401222 | Crawford |  | Crawford County | -339679.2083 | PE
|  |  |  | Various |  | Crawford County | -339679.2083 | PE
|  |  | 1401228 | Posey | I. T. Business Corporation | Indiana Department of Transportation | 2015-11-10 | CE
CN
PE
|  |  | 1401229 | Perry |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
ROW
|  |  | 1401230 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1401231 | Warren |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401232 | Vermillion |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401233 |  |  | Delphi | 2015-02-18
|  |  | 1401234 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1401235 | Adams | Bidinfo | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401236 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  |  | Various |  | MPO - Louisville | -339679.2083 | PL
|  |  | 1401237 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  | 1401238 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  | 1401239 | Clark |  | Indiana Department of Transportation | 2015-05-31 | CN
|  |  | 1401240 |  |  | Indiana Department of Transportation | 2015-06-01
|  |  | 1401243 |  |  | Anderson | -339679.2083
|  |  | 1401244 |  |  | Anderson | -339679.2083
|  |  | 1401245 |  |  | Anderson | -339679.2083
|  |  | 1401246 |  |  | Anderson | -339679.2083
|  |  | 1401247 |  |  | Anderson | -339679.2083
|  |  | 1401248 |  |  | Anderson | -339679.2083
|  |  | 1401249 |  |  | Anderson | -339679.2083
|  |  | 1401250 |  |  | Anderson | -339679.2083
|  |  | 1401251 |  |  | Anderson | -339679.2083
|  |  | 1401252 |  |  | Anderson | -339679.2083
|  |  | 1401255 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401256 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401257 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401258 |  |  | Indiana Department of Transportation | 2015-05-31
|  |  | 1401259 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401260 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401261 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401262 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401263 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401264 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2016-01-13
|  |  | 1401265 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2016-01-13
|  |  | 1401266 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1401267 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1401268 | Howard |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
RR
|  |  | 1401269 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401271 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401272 | Allen |  | Allen County | 2020-03-04 | CE
CN
ROW
|  |  | 1401273 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2022-10-13 | ROW
|  |  | 1401274 | Elkhart |  | Elkhart County | -339679.2083 | CE
CN
|  |  | 1401275 |  |  | Anderson | -339679.2083
|  |  | 1401276 |  |  | Anderson | -339679.2083
|  |  | 1401277 |  |  | Anderson | -339679.2083
|  |  | 1401278 |  |  | Anderson | -339679.2083
|  |  | 1401279 | Tippecanoe |  | Tippecanoe County | 2021-01-13 | CN
ROW
|  |  | 1401280 | Tippecanoe |  | Tippecanoe County | 2024-11-14 | PE
ROW
|  |  | 1401281 | Tippecanoe |  | Tippecanoe County | 2022-10-13 | PE
ROW
|  |  | 1401282 | Tippecanoe |  | Tippecanoe County | 2019-03-06 | CE
CN
PE
ROW
UT
|  |  | 1401283 |  | DuSABLE, Inc. | Lafayette | -339679.2083
|  |  | 1401284 |  |  | Lafayette | 2021-05-31
|  |  | 1401285 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2019-12-11 | CE
CN
PE
ROW
|  |  | 1401286 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2017-02-08 | CE
CN
|  |  | 1401287 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2022-01-12 | PE
|  |  | 1401288 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2019-02-06 | CE
CN
|  |  | 1401289 |  |  | West Lafayette | -339679.2083
|  |  | 1401290 | Tippecanoe |  | West Lafayette | 2019-02-06 | CE
CN
PE
|  |  | 1401291 | Tippecanoe | Manhard Consulting, Ltd. | West Lafayette | 2028-01-12 | PE
|  |  | 1401292 | Henry |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401293 | Henry |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401294 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1401295 | Shelby |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401296 | Shelby |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1401297 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401298 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401299 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401300 | Wayne |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401301 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1401302 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1401303 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1401304 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1401305 | LaPorte | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  |  | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
PE
|  |  | 1401306 | Newton | GG Consulting, Inc. | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401307 | Cass | J. H. Rudolph & Co., Inc. | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401308 | Jasper |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401309 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1401310 | Jasper |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1401311 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1401312 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1401313 |  |  | Terre Haute | -339679.2083
|  |  | 1401314 | Vigo |  | Vigo County | 2021-11-17 | CN
PE
ROW
|  |  | 1401315 | Tippecanoe |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1401316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401317 |  |  | MPO - Indianapolis | 2019-05-31
|  |  | 1401318 |  |  | MPO - Indianapolis | 2020-05-31
|  |  | 1401319 |  |  | Hendricks County | 2018-05-31
|  |  | 1401320 | Vanderburgh |  | Evansville | 2016-05-31 | CN
|  |  | 1401321 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1401322 |  |  | Brazil | 2018-05-31
|  |  | 1401323 |  |  | Brazil | 2018-05-31
|  |  | 1401324 |  |  | Brazil | 2019-05-31
|  |  | 1401325 | Vigo |  | Terre Haute | 2020-03-04 | CN
ROW
|  |  | 1401326 | Ohio |  | Rising Sun | 2015-07-08 | CE
CN
|  |  | 1401327 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401328 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401329 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401330 |  |  | Bargersville | -339679.2083
|  |  | 1401331 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401332 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2015-07-08 | CE
CN
|  |  | 1401338 |  |  | Evansville | 2017-05-31
|  |  | 1401339 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401340 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1401341 | Ripley | ARCADIS | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1401342 |  |  | MPO - Louisville | -339679.2083
|  |  | 1401343 |  |  | Jeffersonville | -339679.2083
|  |  | 1401344 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1401345 |  |  | MPO - Louisville | -339679.2083
|  |  | 1401346 |  |  | MPO - Louisville | -339679.2083
|  |  | 1401347 | Clark |  | Clark County | 2017-03-01 | CE
CN
PE
|  |  | 1401348 | Floyd |  | Floyd County | 2016-05-05 | CN
|  |  | 1401349 | Clark | Data Transfer Solutions, LLC | Jeffersonville | 2017-03-01 | CE
CN
PE
|  |  | 1401350 | Clark |  | Clarksville | 2020-02-05 | CE
CN
PE
ROW
|  |  | 1401351 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1401352 |  |  | MPO - Louisville | -339679.2083
|  |  | 1401353 |  |  | Indiana Department of Transportation | 2014-10-29
|  |  | 1401354 | Scott |  | Indiana Department of Transportation | 2016-03-16 | CE
CN
|  |  | 1401355 | Johnson |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2016-04-06 | CN
|  |  | 1401356 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1401357 |  |  | Monroe | -339679.2083
|  |  | 1401358 |  |  | Bloomington | -339679.2083
|  |  | 1401359 |  |  | Bloomington | -339679.2083
|  |  | 1401360 |  |  | Bloomington | -339679.2083
|  |  | 1401361 |  |  | Bloomington | -339679.2083
|  |  | 1401362 |  |  | Bloomington | -339679.2083
|  |  | 1401363 |  |  | Bloomington | -339679.2083
|  |  | 1401364 |  |  | Bloomington | -339679.2083
|  |  | 1401365 |  |  | Bloomington | -339679.2083
|  |  | 1401366 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1401367 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401368 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401369 | Lawrence | ICA Engineering, Inc. | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1401370 | Lawrence | ICA Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401371 | Perry |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1401372 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1401373 | Various |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1401374 | Crawford |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1401375 | Knox |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1401376 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401377 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401378 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401379 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CN
|  |  | 1401380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401382 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401383 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401384 | Warrick |  | Warrick County | 2020-01-15 | CE
CN
PE
ROW
UT
|  |  | 1401385 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 1401386 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401387 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401388 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1401389 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1401390 |  |  | City of Valparaiso Transit | -339679.2083
|  |  | 1401391 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1401392 | Owen |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401393 | Posey |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401394 | Posey |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401395 | Posey |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401396 | Posey |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401397 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401399 | Daviess |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401400 |  |  | Indiana Department of Transportation | 2015-02-04
|  |  | 1401401 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401402 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401404 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401405 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401406 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401407 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401409 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401418 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401419 | Clay |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401420 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
RR
|  |  | 1401424 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401425 | Jackson |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401426 | Jackson |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401427 | Harrison |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
|  |  | 1401429 |  |  | Muncie | -339679.2083
|  |  | 1401430 |  |  | Indiana Department of Transportation | 2016-01-13
|  |  | 1401431 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401432 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401433 | Grant |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1401434 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401435 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1401436 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1401437 | Delaware |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1401438 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
RR
|  |  | 1401439 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1401440 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401441 | LaPorte |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401442 | LaPorte |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401443 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401444 | Franklin |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1401445 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401446 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401447 | Jackson |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1401448 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401449 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401450 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401451 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401452 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401453 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401454 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401455 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401456 | St. Joseph |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401457 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1401458 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1401459 | Jackson |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1401460 | Switzerland |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401461 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401462 | Johnson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1401463 | Johnson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1401464 | Johnson |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1401465 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401466 | LaGrange |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401467 | Wabash |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401468 | Blackford |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401469 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401470 | Wabash | HE-BFS, LLC | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401471 | Adams |  | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401472 | Adams | Bidinfo | Indiana Department of Transportation | 2016-08-10 | CE
CN
|  |  | 1401473 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401474 | Huntington |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401475 | Elkhart |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401476 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
RR
|  |  | 1401477 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401478 | Adams |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401479 | Huntington |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401480 | Grant |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401481 | Grant |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401482 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401483 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401484 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401485 | Steuben |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401486 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1401487 | Blackford |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401488 | Noble |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401489 | Noble | ERES International, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401491 | Dekalb |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401492 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401493 | Huntington |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401494 | Noble | InspectTech Systems, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401495 | Wabash |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401496 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401497 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401498 | Elkhart |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401499 | Elkhart |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401500 | Elkhart |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401501 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401502 | Miami |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401503 | Miami |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401504 | Miami |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401505 | Miami |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401506 | Huntington |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401507 | Allen |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401508 | Grant |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401509 | Grant |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401510 | Grant |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401511 | Allen |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401512 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401513 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401514 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401515 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401516 | Miami |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401517 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401518 | Whitley |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401519 | Huntington |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401520 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401521 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401522 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401523 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401524 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401525 | Grant |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401526 | Grant |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401527 | Grant |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401528 | Huntington |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401529 | Huntington |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401530 | Huntington |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401531 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401532 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401533 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401534 | Noble |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401535 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401536 | Steuben |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401537 | Steuben |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401538 | Huntington |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401539 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401540 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1401541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401542 | Allen |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401543 | Allen |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401544 | Noble |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401545 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401546 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401547 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401548 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401549 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1401550 | Kosciusko |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401551 | Wabash |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401552 | Jay |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401553 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401554 | Adams |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401555 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401556 | Dekalb |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401557 | Allen |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401558 | Allen |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401559 | Allen |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1401560 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1401561 | Marshall |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401562 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401563 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401564 | Marshall |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401565 | Marshall |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401566 | Marshall |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401567 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401568 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401569 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401570 | St. Joseph | Dummy Consulting Firm Too | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401571 | St. Joseph | Dummy Consulting Firm Too | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401572 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401573 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401574 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401575 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401576 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401577 | Carroll |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401578 | Carroll |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401579 | Cass |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401580 | Cass |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401581 | Cass |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401582 | Cass |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401583 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1401584 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1401585 | Jasper |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401586 | LaPorte |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401588 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1401589 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1401590 | Marshall |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401593 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401594 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401595 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401596 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401597 | Orange |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
|  |  | 1401598 | Orange |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1401599 | Dubois | CMF Engineering, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1401600 | Dubois |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1401601 | Dubois |  | Indiana Department of Transportation | 2019-10-09 | PE
ROW
|  |  | 1401602 | Perry |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
|  |  | 1401603 | Perry |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
|  |  | 1401604 | Franklin |  | Brookville | 2016-05-31 | CN
|  |  | 1401605 | Knox |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1401606 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1401607 | Vanderburgh |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1401608 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1401609 |  |  | Greenwood | -339679.2083
|  |  | 1401610 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2019-11-14 | CE
CN
|  |  | 1401611 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1401612 | Johnson |  | Franklin | 2019-11-14 | CE
CN
|  |  | 1401613 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401614 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401615 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401616 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401617 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401618 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401619 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401620 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401621 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401622 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401623 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401624 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401625 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401626 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401627 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401628 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401629 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401630 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401631 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401632 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401633 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2019-05-31
|  |  | 1401634 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2019-05-31
|  |  | 1401635 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401636 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401637 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401638 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401639 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 1401640 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1401641 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 1401642 | Porter |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1401643 | Carroll | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401644 | Carroll | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1401645 |  |  | Indiana Department of Transportation | 2015-02-04
|  |  | 1401646 | Hendricks | All About Pavements, Inc. | Brownsburg | 2019-02-06 | CE
CN
|  |  | 1401647 | Hendricks | All About Pavements, Inc. | Brownsburg | 2018-07-11 | CE
CN
|  |  | 1401648 | Hendricks |  | Avon | 2018-12-12 | CE
CN
UT
|  |  | 1401649 | Hendricks | Horn and Associates, Inc. | Pittsboro | 2016-09-14 | CE
CN
PE
|  |  | 1401650 |  |  | Westfield | 2020-05-31
|  |  | 1401651 |  |  | MPO - Louisville | 2015-07-02
|  |  | 1401652 |  |  | MPO - Louisville | -339679.2083
|  |  | 1401653 |  |  | Indiana Department of Transportation | 2015-03-04
|  |  | 1401654 |  |  | MPO - Louisville | 2019-05-31
|  |  | 1401655 |  |  | MPO - Louisville | 2018-05-31
|  |  | 1401656 |  |  | MPO - Louisville | 2018-05-31
|  |  | 1401657 | Marion |  | Beech Grove | 2017-03-01 | CE
CN
|  |  | 1401658 | Hancock |  | Mccordsville | 2018-01-18 | CE
CN
|  |  | 1401659 | LaPorte |  | Indiana Department of Transportation | 2015-05-07 | CE
CN
|  |  | 1401660 |  |  | Indiana Department of Transportation | 2016-03-02
|  |  | 1401661 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401662 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401663 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401664 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401665 | Morgan |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1401666 | Putnam |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
|  |  | 1401667 | Hendricks |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
|  |  | 1401668 | Putnam |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401669 | Putnam |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401670 | Putnam |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401671 | Clinton |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1401672 | Vermillion |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1401673 | Vermillion |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
RR
|  |  | 1401674 | Vermillion |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
RR
|  |  | 1401675 | Parke |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1401676 | Warren |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1401677 | Clinton |  | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1401678 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1401679 | Clay |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401680 | Clay |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401681 | Owen |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401682 | Owen |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1401683 | Hendricks |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
|  |  |  | Putnam |  | Indiana Department of Transportation | 2016-09-14 | CE
|  |  | 1401684 | Johnson |  | Bargersville | 2019-07-10 | CE
CN
RR
|  |  | 1401685 | Johnson | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2016-11-16 | CE
CN
PE
|  |  |  | Various | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2016-11-16 | CE
|  |  | 1401686 |  |  | Aurora | 2016-05-31
|  |  | 1401687 | Greene |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
ROW
|  |  | 1401688 |  |  | MPO - Cincinnati | -339679.2083
|  |  | 1401689 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 1401690 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 1401691 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
[6 empty] | Indiana Department of Transportation | -339679.2083
|  |  | 1401692 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1401693 |  |  | MPO - Northwest | -339679.2083
|  |  | 1401694 |  |  | MPO - Northwest | -339679.2083
|  |  | 1401695 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1401699 |  |  | Evansville | -339679.2083
|  |  | 1401700 |  |  | Evansville | 2016-05-31
|  |  | 1401701 | Hamilton |  | Hamilton County | 2020-02-05 | CE
CN
|  |  | 1401702 | Hamilton |  | Hamilton County | 2019-01-16 | CE
CN
|  |  | 1401703 | Hamilton |  | Carmel | 2018-09-12 | CE
CN
|  |  | 1401704 |  | CPS Acquisitions, LLC | Fishers | 2022-05-05
|  |  | 1401705 | Hamilton |  | Fishers | 2018-05-10 | CE
CN
|  |  | 1401706 | Hamilton | CPS Acquisitions, LLC | Fishers | 2018-05-10 | CE
CN
|  |  | 1401707 | Hamilton |  | Westfield | 2017-07-12 | CE
CN
|  |  | 1401708 |  |  | Westfield | -339679.2083
|  |  | 1401709 | Hamilton |  | Westfield | 2018-07-11 | CE
CN
UT
|  |  | 1401710 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1401712 |  |  | MPO - Evansville | 2016-05-31
|  |  | 1401713 | Hamilton | H. Stewart Kline & Associates, Inc. | Noblesville | 2018-07-11 | CE
CN
|  |  | 1401714 | Hamilton |  | Noblesville | 2019-01-16 | CE
CN
|  |  | 1401715 |  |  | MPO - Evansville | 2016-05-31
|  |  | 1401716 | Hamilton |  | Noblesville | 2018-12-12 | CE
CN
UT
|  |  | 1401717 | Marion |  | Indianapolis | 2019-02-06 | CE
CN
|  |  | 1401718 |  | DCD Consulting LLC | Indianapolis | 2022-08-10
|  |  | 1401719 | Marion |  | Indianapolis | 2018-11-15 | CE
CN
RR
|  |  | 1401720 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | CE
CN
PE
|  |  | 1401721 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CE
CN
|  |  | 1401722 | Marion |  | Indianapolis | 2019-02-06 | CE
CN
|  |  | 1401723 |  |  | Indianapolis | -339679.2083
|  |  | 1401724 | Marion |  | Indianapolis | 2018-12-12 | CE
CN
|  |  | 1401725 | Marion | DCD Consulting LLC | Indianapolis | 2019-11-14 | CE
CN
|  |  | 1401726 | Marion | DCD Consulting LLC | Indianapolis | 2019-11-14 | CE
CN
|  |  | 1401727 | Marion |  | Indianapolis | 2019-01-16 | CE
CN
|  |  | 1401728 | Marion |  | Indianapolis | 2019-01-16 | CE
CN
|  |  | 1401729 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CE
CN
|  |  | 1401730 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CE
CN
|  |  | 1401731 |  |  | Evansville | -339679.2083
|  |  | 1401732 | Marion | DCD Consulting LLC | Indianapolis | 2020-03-04 | CE
CN
RR
|  |  | 1401733 | Marion |  | Indianapolis | -339679.2083 | CE
CN
|  |  | 1401734 | Marion |  | Indianapolis | 2019-02-06 | CE
CN
|  |  | 1401735 | Marion |  | Indianapolis | 2018-02-07 | CE
CN
|  |  | 1401736 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1401737 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1401738 | Jackson |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401739 | Clark | Gregg A. Townsend | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  |  | Washington | Gregg A. Townsend | Indiana Department of Transportation | 2016-03-02 | CE
RR
|  |  | 1401740 | Monroe |  | MPO - Bloomington | -339679.2083 | PL
|  |  | 1401741 | Noble |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1401742 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2023-10-12 | PE
|  |  | 1401743 | Noble |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1401744 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1401745 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1401746 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401747 | Elkhart | Civil Inspection Services, LLC | Goshen | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1401748 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1401749 | Elkhart |  | Elkhart County | 2022-11-16 | PE
ROW
|  |  | 1401750 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1401751 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1401752 | Tippecanoe |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
|  |  | 1401753 | Steuben |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1401754 |  |  | South Bend Transit | -339679.2083
|  |  | 1401755 |  |  | South Bend Transit | -339679.2083
|  |  | 1401756 |  |  | South Bend Transit | -339679.2083
|  |  | 1401757 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2015-09-02
|  |  | 1401758 | Marion |  | Indianapolis | 2015-02-04 | CE
CN
|  |  | 1401759 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
PE
|  |  | 1401760 | Grant |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401761 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401762 | Jay |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401763 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401764 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401765 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401766 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401767 | Grant |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401768 | Wabash | HE-BFS, LLC | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401769 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401770 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401771 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401772 | Miami |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401773 | Miami |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401774 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401775 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401776 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401777 | Elkhart |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401778 | Elkhart |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401779 | Noble |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401780 | Dekalb |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401781 | Dekalb |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401782 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1401783 | Dekalb |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401784 | Elkhart |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401785 | Elkhart |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401786 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401787 | Dekalb |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401788 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401789 | Allen |  | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401790 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1401791 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1401792 |  |  | MPO - Muncie | -339679.2083
|  |  | 1401793 |  |  | MPO - Muncie | -339679.2083
|  |  | 1401794 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401795 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401796 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401797 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401798 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401799 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401800 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401801 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401802 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401803 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401804 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401805 |  |  | MPO - Anderson | -339679.2083
|  |  | 1401806 | Marshall |  | Lapaz | 2017-07-12 | CE
CN
PE
|  |  | 1401807 | St. Joseph |  | St. Joseph County | 2017-11-15 | CE
CN
PE
|  |  | 1401808 | St. Joseph |  | South Bend | 2016-11-16 | CE
CN
PE
|  |  | 1401809 | St. Joseph |  | South Bend | 2016-11-16 | CE
CN
PE
|  |  | 1401810 | St. Joseph |  | South Bend | 2021-03-10 | CE
CN
PE
ROW
|  |  | 1401811 | St. Joseph |  | South Bend | 2022-01-12 | PE
ROW
|  |  | 1401812 | Porter |  | Valparaiso | 2015-07-08 | CE
CN
|  |  | 1401813 | Porter |  | Valparaiso | 2019-03-06 | CE
CN
|  |  | 1401814 | Porter |  | Valparaiso | 2017-10-12 | CE
CN
|  |  | 1401815 |  |  | MPO - Muncie | -339679.2083
|  |  | 1401816 | Howard |  | Howard County | 2019-11-14 | CE
CN
PE
|  |  | 1401817 | Howard |  | Howard County | 2020-11-10 | CE
CN
PE
ROW
|  |  | 1401818 | Howard |  | Kokomo | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1401819 |  |  | Kokomo | -339679.2083
|  |  | 1401820 | Howard |  | Kokomo | 2018-03-14 | CE
CN
PE
ROW
RR
|  |  | 1401821 |  |  | Kokomo | -339679.2083
|  |  | 1401822 |  |  | Kokomo | -339679.2083
|  |  | 1401823 |  |  | Indiana Department of Transportation | 2016-01-13
|  |  | 1401824 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401825 | Spencer |  | Santa Claus | 2017-02-08 | CN
PE
RR
|  |  | 1401826 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1401827 | Wells |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
ROW
|  |  | 1401828 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1401829 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1401830 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1401831 | Various |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1401832 | Various |  | MPO - Lafayette | -339679.2083 | PL
|  |  | 1401833 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401834 | Jay |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
ROW
|  |  | 1401835 | Jay |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1401836 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1401837 | Various |  | Indiana Department of Transportation | 2016-02-17 | CE
CN
PE
|  |  | 1401838 | Various |  | Indiana Department of Transportation | 2016-02-17 | CE
CN
PE
|  |  | 1401839 | Jackson |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1401840 | Clark |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1401841 |  | Basin Field Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1401842 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401843 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2015-07-08 | CE
CN
|  |  | 1401844 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401845 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 1401846 | Jackson |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
ROW
|  |  | 1401847 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401848 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401849 | Knox | HOH Engineers, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1401850 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1401851 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401852 | Jefferson |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1401853 | Whitley |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1401854 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1401855 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1401856 | Kosciusko | 2IM Group, LLC | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1401857 | Steuben | Certified Engineering, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1401858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401859 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401860 | Huntington |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
PE
ROW
|  |  | 1401861 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401862 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401863 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1401864 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1401865 | Switzerland |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1401866 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1401867 | Jackson |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
ROW
|  |  | 1401868 | Jackson |  | Indiana Department of Transportation | 2019-12-11 | PE
ROW
|  |  | 1401869 | Jackson |  | Indiana Department of Transportation | 2019-12-11 | PE
ROW
|  |  | 1401870 | Washington |  | Indiana Department of Transportation | 2020-01-15 | PE
ROW
|  |  | 1500001 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500002 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500003 | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1500004 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1500005 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500006 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500007 | Blackford |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1500008 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1500009 | Madison | Enterprise Information Solutions, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500010 | Henry |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
ROW
|  |  | 1500011 | Jackson |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1500012 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1500013 | Jackson |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1500014 | Bartholomew |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
ROW
|  |  | 1500015 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
ROW
|  |  | 1500016 | Scott |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1500017 |  | Earth Exploration, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500018 | Brown |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
ROW
|  |  | 1500019 | Ripley |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
ROW
|  |  | 1500020 | Franklin |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
ROW
|  |  | 1500021 | Jefferson |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1500022 | Brown |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
ROW
|  |  | 1500023 | Dubois |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
UT
|  |  | 1500024 | Daviess | AMEC E&I, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500025 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500026 | Gibson | III FFC | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1500027 | Gibson | III FFC | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1500028 | Gibson | III FFC | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1500029 | Gibson | III FFC | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1500030 | Vanderburgh |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1500031 | Greene |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1500032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500033 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500034 | Henry |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
RR
|  |  | 1500035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500037 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1500038 |  | Alliance Survey Company | Indiana Department of Transportation | -339679.2083
|  |  | 1500039 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500040 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1500041 | Vanderburgh | CGI | Indiana Department of Transportation | 2023-11-15 | PE
|  |  | 1500042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500043 | Steuben |  | Indiana Department of Transportation | 2018-05-31 | CN
PE
|  |  | 1500044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500045 | Marion | DCD Consulting LLC | Indianapolis | 2019-12-11 | CE
CN
|  |  | 1500046 | Marion |  | Indianapolis | 2018-02-07 | CE
CN
|  |  | 1500047 | Sullivan |  | Indiana Department of Transportation | 2020-04-01 | PE
ROW
|  |  | 1500048 | Dubois |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
UT
|  |  | 1500049 | Pike |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1500050 | Greene |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1500051 | Perry |  | Indiana Department of Transportation | 2019-10-09 | PE
ROW
|  |  | 1500052 | Warrick |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1500053 | Gibson |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1500054 | Gibson |  | Indiana Department of Transportation | 2020-01-15 | PE
ROW
|  |  | 1500055 | Perry |  | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1500056 | Perry |  | Indiana Department of Transportation | 2019-10-09 | PE
ROW
|  |  | 1500057 | Perry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500058 | Daviess |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500059 | Orange |  | Indiana Department of Transportation | 2015-03-04 | CE
CN
RR
|  |  | 1500060 |  | ASA Land Surveying | Indiana Department of Transportation | 2022-09-14
|  |  | 1500061 |  | ASA Land Surveying | Indiana Department of Transportation | 2022-09-14
|  |  | 1500062 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2017-05-10 | CE
CN
RR
|  |  | 1500063 | Warrick |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1500064 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
RR
|  |  | 1500065 | Clinton | Iteris, Inc. | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1500066 | Jefferson |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1500067 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1500068 | Jefferson |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1500069 | Jefferson |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1500070 | Switzerland |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1500071 | Martin |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500072 | Greene |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
UT
|  |  | 1500073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500074 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1500075 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500076 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1500077 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1500078 | Newton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
RR
|  |  | 1500079 | Daviess | AMEC E&I, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500080 | Cass |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1500081 | Lake | Cornerstone Design | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
RR
UT
|  |  | 1500082 | Knox |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1500083 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500084 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500085 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500086 | Crawford |  | Indiana Department of Transportation | 2020-10-07 | CE
UT
|  |  |  | Various |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1500087 | Cass |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1500088 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500089 | White | Afram Corporation | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500090 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-04-06 | PE
ROW
|  |  | 1500091 | Lake |  | Indiana Department of Transportation | 2020-01-15 | PE
ROW
|  |  | 1500092 | Dearborn |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1500093 | Carroll |  | Indiana Department of Transportation | 2018-07-11 | PE
|  |  | 1500094 | Switzerland |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1500095 |  | Martinez Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1500096 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500097 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500098 | White |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500099 | Benton |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1500100 | Warren | Manning Real Estate Services | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1500101 | Warren |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1500102 | Warren |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500103 | Owen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
ROW
|  |  | 1500104 | Vermillion |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1500105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500106 | Hendricks |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1500107 | Clinton |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1500108 | Newton |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1500109 | Benton |  | Indiana Department of Transportation | 2023-08-09 | PE
|  |  | 1500110 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
ROW
|  |  | 1500111 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500112 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500113 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500114 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500115 | Hendricks |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1500116 | Warren |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1500117 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
ROW
|  |  | 1500118 | Clay |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1500119 | Benton |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1500120 | Tippecanoe |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1500121 | Tippecanoe |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1500122 | Hendricks |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
ROW
|  |  | 1500123 | Putnam |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
ROW
|  |  | 1500124 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500126 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500127 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500128 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500129 | Various |  | Indiana Department of Transportation | 2017-05-31 | CN
PE
|  |  | 1500130 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1500131 |  |  | Indiana Department of Transportation | 2020-08-30
|  |  | 1500132 | Fountain |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
ROW
UT
|  |  | 1500133 | Parke |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
ROW
|  |  | 1500134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500135 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500136 | Putnam |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1500137 | Montgomery |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500138 | Vermillion |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1500139 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1500140 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500141 | Boone |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
ROW
|  |  | 1500142 | Clinton |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
ROW
|  |  | 1500143 | Hendricks |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
ROW
UT
|  |  | 1500144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500145 | Hendricks |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1500146 | Vigo |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1500147 | Montgomery |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500148 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500149 | Montgomery |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1500150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500151 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500152 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500153 | Jackson |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1500154 | White |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1500155 | Tippecanoe |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
RR
|  |  | 1500156 | Montgomery | Driesenga & Associates, Inc. | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
RR
|  |  | 1500157 |  | CDM Smith, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500158 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500159 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500160 | Boone |  | Indiana Department of Transportation | 2020-04-15 | CE
CN
PE
|  |  | 1500161 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500162 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500163 |  | Clyde L. Hawkins | Indiana Department of Transportation | -339679.2083
|  |  | 1500164 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500165 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500166 | Knox |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500167 | Knox |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500168 | Gibson | Copperhead Environmental Consulting | Indiana Department of Transportation | 2017-05-31 | RR
|  |  | 1500169 | Gibson |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500170 | LaPorte |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1500171 | Porter |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1500172 | Tipton |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1500173 | Madison |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500174 | Randolph |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500175 | Randolph |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500176 | Delaware |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500177 | Wabash |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500178 | Wabash |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500179 | Miami |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500181 | Allen |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500182 | Kosciusko |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500183 | Kosciusko |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500184 | Grant |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1500185 | Wells |  | Indiana Department of Transportation | 2018-05-31 | PE
RR
|  |  | 1500186 | Vigo |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1500187 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500188 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500190 | Various |  | Warren County | -339679.2083 | PE
|  |  |  | Warren |  | Warren County | -339679.2083 | PE
|  |  | 1500191 | Marion |  | Fishers | 2019-12-11 | CN
|  |  | 1500192 | Bartholomew |  | Bartholomew County | -339679.2083 | PE
|  |  | 1500193 |  |  | South Bend Transit | -339679.2083
|  |  | 1500194 |  |  | South Bend Transit | -339679.2083
|  |  | 1500195 |  |  | South Bend Transit | -339679.2083
|  |  | 1500196 |  |  | South Bend Transit | -339679.2083
|  |  | 1500197 |  |  | South Bend Transit | -339679.2083
|  |  | 1500198 |  |  | South Bend Transit | -339679.2083
|  |  | 1500199 |  |  | South Bend Transit | -339679.2083
|  |  | 1500200 | Brown |  | Brown County | -339679.2083 | PE
|  |  |  | Various |  | Brown County | -339679.2083 | PE
|  |  | 1500201 | Clark |  | Clark County | -339679.2083 | PE
|  |  |  | Various |  | Clark County | -339679.2083 | PE
|  |  | 1500202 | Dearborn |  | Dearborn County | -339679.2083 | PE
|  |  | 1500203 | Decatur |  | Decatur County | -339679.2083 | PE
|  |  | 1500204 | Floyd |  | Floyd County | -339679.2083 | PE
|  |  |  | Various |  | Floyd County | -339679.2083 | PE
|  |  | 1500205 | Franklin |  | Franklin County | -339679.2083 | PE
|  |  | 1500206 | Harrison |  | Harrison County | -339679.2083 | PE
|  |  | 1500207 | Jackson |  | Jackson County | -339679.2083 | PE
|  |  | 1500208 | Jefferson |  | Jefferson County | -339679.2083 | PE
|  |  | 1500209 | Johnson |  | Johnson County | -339679.2083 | PE
|  |  | 1500210 | Monroe |  | Monroe County | -339679.2083 | PE
|  |  | 1500211 | Morgan |  | Morgan County | -339679.2083 | PE
|  |  | 1500212 | Ohio |  | Ohio County | -339679.2083 | PE
|  |  | 1500213 | Ripley |  | Ripley County | -339679.2083 | PE
|  |  | 1500214 | Scott |  | Scott County | -339679.2083 | PE
|  |  | 1500215 | Switzerland |  | Switzerland County | -339679.2083 | PE
|  |  | 1500216 | Washington |  | Washington County | -339679.2083 | PE
|  |  | 1500217 | Hamilton | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | RR
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1500218 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500219 | Jennings |  | Jennings County | -339679.2083 | PE
|  |  | 1500220 | Various |  | Indiana Department of Transportation | 2018-05-31 | CN
|  |  | 1500221 | Lake |  | Hammond | 2019-12-11 | CE
CN
ROW
RR
|  |  | 1500222 | Lake | Consolidated Test Company | Hammond | 2020-12-09 | CE
CN
|  |  | 1500223 |  |  | Indiana Department of Natural Resources | 2016-02-03
|  |  | 1500224 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2015-09-02 | CE
CN
|  |  | 1500225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500226 | Bartholomew |  | MPO - Columbus | -339679.2083 | PL
|  |  | 1500227 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 1500228 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500229 | Clay |  | Clay County | -339679.2083 | PE
|  |  | 1500230 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1500231 | Clinton |  | Clinton County | -339679.2083 | PE
|  |  | 1500232 | Fountain |  | Fountain County | -339679.2083 | PE
|  |  | 1500233 |  |  | Indiana Department of Transportation | 2015-07-08
|  |  | 1500234 |  | CGI | Indiana Department of Transportation | 2015-05-07
|  |  | 1500235 |  | CGI | Indiana Department of Transportation | 2015-05-07
|  |  | 1500236 |  |  | Indiana Department of Transportation | 2015-05-07
|  |  | 1500237 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500238 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500239 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500240 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1500241 | Hendricks |  | Hendricks County | -339679.2083 | PE
|  |  | 1500242 | Montgomery |  | Montgomery County | -339679.2083 | PE
|  |  |  | Various |  | Montgomery County | -339679.2083 | PE
|  |  | 1500243 | Owen |  | Owen County | -339679.2083 | PE
|  |  | 1500244 |  |  | Indiana Department of Transportation | 2015-07-08
|  |  | 1500245 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500246 |  |  | Boone County | -339679.2083
|  |  | 1500247 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington | 2015-10-07 | CE
CN
|  |  | 1500248 | Wayne |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1500249 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2016-05-31
|  |  | 1500250 | Parke |  | Parke County | -339679.2083 | PE
|  |  |  | Various |  | Parke County | -339679.2083 | PE
|  |  | 1500251 | Putnam |  | Putnam County | -339679.2083 | PE
|  |  | 1500252 | Tippecanoe |  | Tippecanoe County | -339679.2083 | PE
|  |  | 1500253 | Vermillion |  | Vermillion County | -339679.2083 | PE
|  |  | 1500254 | Vigo |  | Vigo County | -339679.2083 | PE
|  |  | 1500255 | Spencer | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2015-10-07 | CE
CN
PE
|  |  | 1500256 | Wabash | M-E Companies, Inc. | Wabash | 2018-03-14 | CE
CN
PE
ROW
|  |  | 1500257 |  |  | Tipton County | 2015-11-17
|  |  | 1500258 | Dubois |  | Huntingburg | 2017-05-31 | ROW
|  |  | 1500259 | Benton |  | Benton County | -339679.2083 | PE
|  |  | 1500260 | Parke |  | Parke County | -339679.2083 | PE
|  |  | 1500261 | Warren |  | Warren County | -339679.2083 | PE
|  |  | 1500262 | Jennings |  | Indiana Department of Transportation | 2016-05-31 | ROW
|  |  | 1500263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500264 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500265 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500266 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500271 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500272 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500273 | Hamilton |  | Hamilton County | 2016-06-15 | CE
CN
|  |  | 1500274 | Allen |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
PE
RR
UT
|  |  |  | Dekalb |  | Indiana Department of Transportation | 2016-02-03 | CE
RR
|  |  | 1500275 |  |  | Lawrence | -339679.2083
|  |  | 1500276 | Marion | Dyer Environmental Services | Lawrence | 2018-04-11 | CE
CN
PE
|  |  | 1500277 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1500278 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500279 | Delaware |  | Delaware County | -339679.2083 | PE
|  |  | 1500280 | Fayette |  | Fayette County | -339679.2083 | PE
|  |  | 1500281 | Hamilton |  | Hamilton County | -339679.2083 | PE
|  |  | 1500282 | Hancock |  | Hancock County | -339679.2083 | PE
|  |  | 1500283 | Henry |  | Henry County | -339679.2083 | PE
|  |  |  | Various |  | Henry County | -339679.2083 | PE
|  |  | 1500284 | Howard |  | Howard County | -339679.2083 | PE
|  |  | 1500285 | Jay |  | Jay County | -339679.2083 | PE
|  |  | 1500286 | Madison |  | Madison County | -339679.2083 | PE
|  |  | 1500287 | Marion |  | Marion County | -339679.2083 | PE
|  |  | 1500288 | Randolph |  | Randolph County | -339679.2083 | PE
|  |  | 1500289 | Rush |  | Rush County | -339679.2083 | PE
|  |  |  | Various |  | Rush County | -339679.2083 | PE
|  |  | 1500290 | Shelby |  | Shelby County | -339679.2083 | PE
|  |  | 1500291 | Tipton |  | Tipton County | -339679.2083 | PE
|  |  | 1500292 | Union |  | Union County | -339679.2083 | PE
|  |  | 1500293 | Various |  | Wayne County | -339679.2083 | PE
|  |  |  | Wayne |  | Wayne County | -339679.2083 | PE
|  |  | 1500294 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1500295 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1500296 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1500297 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1500298 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500299 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500300 | Vermillion |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1500301 | Montgomery |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1500302 | Montgomery |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1500303 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500304 | Montgomery |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1500305 | Putnam |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500306 | Benton |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500307 | Boone |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500308 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1500309 | Dearborn |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1500310 | Clark |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500311 | Floyd | Commonwealth Heritage Group, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500312 | Jackson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500313 | Scott |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1500314 | Bartholomew |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500315 | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500316 | Jackson |  | Indiana Department of Transportation | 2019-12-11 | PE
ROW
UT
|  |  | 1500317 | Martin | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | 2015-05-31 | PE
|  |  | 1500318 | Jennings |  | North Vernon | 2016-01-13 | CE
CN
|  |  | 1500319 |  |  | Munster | -339679.2083
|  |  | 1500320 | Lake |  | Griffith | 2017-09-13 | CE
CN
PE
|  |  | 1500321 | Lake | Compliance Consulting Service, Inc. | Griffith | 2017-07-12 | CE
CN
PE
|  |  | 1500322 | Lake | Cornerstone Design | Highland | 2017-07-12 | CE
CN
PE
|  |  | 1500323 | Lake | Baxter & Woodman, Inc. | Crown Point | 2018-07-11 | CE
CN
PE
|  |  | 1500324 | LaPorte |  | Michigan City | 2020-01-15 | CE
CN
PE
|  |  | 1500325 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500326 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500327 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500328 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500329 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500330 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500331 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500332 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500333 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500334 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500335 | Warrick |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1500336 | Dearborn |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1500337 | Hendricks |  | Brownsburg | 2018-11-15 | CE
CN
PE
|  |  | 1500338 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1500339 | Madison |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1500340 | Hamilton | Another Test Company | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500341 | Hamilton | Another Test Company | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500342 | Rush |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500343 | Marion |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
PE
|  |  | 1500344 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1500345 | Rush |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1500346 | LaPorte |  | LaPorte County | -339679.2083 | PE
|  |  | 1500347 | Elkhart | Wessler Engineering, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1500348 | Hamilton |  | Fishers | 2016-06-15 | CN
|  |  | 1500349 | Allen |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500350 | LaGrange | Hambleton LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  |  | Steuben | Hambleton LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1500351 | Steuben | Hambleton LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1500352 |  | Casteel Real Estate | Indiana Department of Transportation | 2016-05-31
|  |  | 1500353 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1500354 | Hancock | CTLGroup | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1500355 | Madison |  | Indiana Department of Transportation | 2016-03-16 | CE
CN
|  |  | 1500356 | Marion |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500357 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500358 | Daviess |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  |  | Pike |  | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1500359 |  |  | Indiana Department of Transportation | 2010-10-06
|  |  | 1500360 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1500361 | Kosciusko |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500362 | LaGrange |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1500363 |  |  | Indiana Department of Transportation | 2015-04-20
|  |  | 1500364 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
RR
|  |  | 1500365 | Madison |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
RR
|  |  | 1500366 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500367 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1500368 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500369 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500370 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500371 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500372 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500373 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500374 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1500375 |  |  | Bloomington | 2019-05-01
|  |  | 1500376 | Monroe |  | Bloomington | 2017-04-05 | CE
CN
|  |  | 1500377 |  |  | Bloomington | -339679.2083
|  |  | 1500378 |  |  | Bloomington | -339679.2083
|  |  | 1500379 |  |  | Bloomington | -339679.2083
|  |  | 1500380 | Monroe |  | Bloomington | 2016-04-06 | CN
RR
|  |  | 1500381 | Monroe |  | Bloomington | 2017-04-05 | CE
CN
|  |  | 1500382 | Monroe |  | Bloomington | 2020-01-15 | CN
PE
|  |  | 1500383 | Monroe |  | Bloomington | 2020-01-15 | CN
PE
|  |  | 1500384 | Monroe |  | Bloomington | 2020-01-15 | CN
PE
|  |  | 1500385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500386 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500387 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500388 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500389 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500390 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500391 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500392 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500393 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500394 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500395 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500396 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500397 | Monroe |  | Monroe County | 2016-02-03 | CE
CN
RR
|  |  | 1500398 | Monroe |  | Bloomington | 2021-02-10 | CE
CN
PE
ROW
|  |  | 1500399 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1500400 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500401 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500402 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500403 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500404 | Hendricks |  | Brownsburg | 2017-07-12 | CN
|  |  |  | Various |  | Brownsburg | 2017-07-12 | CE
CN
PE
|  |  | 1500405 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500406 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500407 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500408 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500409 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500410 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500411 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500412 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1500413 | Jasper |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  |  | Newton |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
|  |  | 1500414 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1500415 | LaPorte |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1500416 | Lake |  | Hammond | 2018-07-11 | CE
CN
|  |  | 1500417 | Lake |  | Hobart | 2020-03-04 | CN
PE
|  |  | 1500418 | Porter |  | Portage | 2021-02-10 | CE
CN
PE
|  |  | 1500419 | Porter |  | Porter County | 2024-01-18 | PE
|  |  | 1500420 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500421 | Porter |  | Valparaiso | 2018-04-11 | CE
CN
PE
|  |  | 1500422 | LaPorte |  | La Porte | 2019-05-09 | CE
CN
|  |  | 1500423 | Hendricks |  | Brownsburg | 2017-02-08 | CE
CN
PE
|  |  | 1500424 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500425 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500426 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500427 |  | Advanced Engineering Consultants, Ltd. | Allen County | -339679.2083
|  |  | 1500428 | Hamilton |  | Westfield | 2017-02-08 | CN
PE
ROW
|  |  | 1500429 | Hamilton |  | Westfield | 2018-07-11 | CN
PE
|  |  | 1500430 | Hamilton |  | Westfield | 2016-05-31 | PE
ROW
|  |  | 1500431 | Hamilton |  | Westfield | 2018-12-12 | CN
PE
ROW
|  |  | 1500432 | Marion |  | Indianapolis | 2018-12-12 | CE
CN
PE
|  |  | 1500433 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
RR
|  |  | 1500434 | Marion |  | Indianapolis | 2018-12-12 | CE
CN
PE
|  |  | 1500435 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
PE
|  |  | 1500436 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1500437 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
PE
|  |  | 1500438 | Marion |  | Indianapolis | 2018-12-12 | CE
CN
PE
|  |  | 1500439 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
PE
|  |  | 1500440 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
PE
|  |  | 1500441 | Marion |  | Indianapolis | 2017-02-08 | CE
CN
PE
|  |  | 1500442 | Hancock |  | Hancock County | 2016-12-14 | CE
CN
PE
|  |  | 1500443 | Hancock |  | Hancock County | 2016-12-14 | CE
CN
PE
|  |  | 1500444 | Hamilton |  | Carmel | 2018-05-10 | CE
CN
PE
ROW
|  |  | 1500445 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1500446 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1500447 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1500448 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1500449 |  |  | E Chicago-Gary Public Transportation Corporation | -339679.2083
|  |  | 1500450 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500451 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500452 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500453 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500454 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500455 |  |  | Michigan City Transit | -339679.2083
|  |  | 1500456 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500457 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500458 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500459 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500460 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500461 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500462 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500463 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500464 |  |  | Michigan City Transit | -339679.2083
|  |  | 1500465 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500466 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500467 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500468 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500469 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500470 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500471 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500472 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500473 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500474 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500475 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500476 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500477 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500478 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1500479 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1500480 |  |  | Michigan City Transit | -339679.2083
|  |  | 1500481 | Hamilton |  | Fishers | 2017-08-09 | CE
CN
PE
|  |  | 1500482 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1500483 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1500484 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1500485 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1500486 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500487 | Greene |  | Greene County | -339679.2083 | PE
|  |  |  | Various |  | Greene County | -339679.2083 | PE
|  |  | 1500488 | Dekalb | August Mack Environmental, Inc. | Indiana Department of Transportation | 2015-08-05 | CE
CN
|  |  | 1500489 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500490 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500491 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500492 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500493 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500494 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500495 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500496 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500497 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500498 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500499 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500500 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500501 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500502 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500503 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500504 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500505 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500506 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500507 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1500508 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500510 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1500511 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1500512 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1500513 |  |  | MPO - Evansville | -339679.2083
|  |  | 1500514 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1500515 | Warrick |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1500516 | Perry |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1500517 | Crawford |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1500518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500519 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500520 |  | CPS Acquisitions, LLC | Hamilton County | 2016-03-02
|  |  | 1500521 |  | CPS Acquisitions, LLC | Hamilton County | 2016-03-02
|  |  | 1500522 | Cass |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1500523 | Monroe |  | Monroe County | 2018-08-08 | CE
CN
|  |  | 1500524 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500525 | Marshall |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1500526 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500527 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500528 | Scott |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500529 | Scott |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500530 | Scott |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500531 | Scott |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500532 | Jackson |  | Indiana Department of Transportation | 2019-02-06 | CE
|  |  |  | Scott |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500533 | Jackson |  | Indiana Department of Transportation | 2019-02-06 | CE
|  |  |  | Scott |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500534 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500535 |  |  | Anderson | -339679.2083
|  |  | 1500536 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500539 | Jackson |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500540 | Jackson |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500542 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500543 | Scott |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500544 | Scott |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1500545 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500546 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500547 | Dearborn |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
|  |  | 1500548 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500549 | Carroll |  | Carroll County | -339679.2083 | PE
|  |  | 1500550 | Dearborn |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1500551 | Dearborn |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1500552 | Dearborn |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1500553 | Bartholomew |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500554 | Floyd |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500555 | Jackson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500556 | Brown |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1500557 | Floyd |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500558 | Jackson |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1500559 | Floyd |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500560 | Bartholomew |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500561 | Jackson |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1500562 | Jackson |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1500563 | Jefferson |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1500564 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1500565 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2018-11-15
|  |  | 1500566 | Dearborn |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
RR
|  |  | 1500567 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500568 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500569 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500570 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500571 | Hendricks |  | Brownsburg | 2016-02-03 | CE
CN
|  |  | 1500572 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500573 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500574 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500575 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500576 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500577 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500578 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500579 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1500580 | Morgan |  | Indiana Department of Transportation | 2016-07-13 | CE
CN
RR
|  |  | 1500581 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500582 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1500583 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1500584 |  |  | Indiana Department of Transportation | 2016-04-06
|  |  | 1500585 | St. Joseph | Hanson Professional Services, Inc. | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1500586 |  |  | Montgomery County | 2017-05-31
|  |  | 1500587 | Crawford |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1500588 | Crawford |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500589 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500590 | Lake |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1500591 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500592 | Perry |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500593 | Crawford |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1500594 | Crawford |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1500595 | Gibson |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500596 | Knox |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500597 | Knox |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1500598 | Knox |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500599 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500600 | Sullivan |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500601 | Perry |  | Indiana Department of Transportation | 2018-04-11 | CE
PE
|  |  |  | Spencer |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500602 | Lake |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1500603 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500604 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500605 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500606 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500607 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500608 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500609 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1500610 | Jennings |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500611 | Dearborn |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500612 | Ripley | Craig eonard Historic Preservation Consultant | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500613 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2017-01-19 | CE
CN
PE
|  |  | 1500614 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500615 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500616 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1500617 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1500618 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1500619 | Jasper |  | Indiana Department of Transportation | 2019-01-16 | CE
PE
|  |  |  | White |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1500620 | White |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1500621 | White |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1500622 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1500623 | Vermillion |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1500624 | Benton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1500625 | Warren |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500626 | Warren |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500627 | Hendricks |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500628 | Putnam |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1500629 | Putnam |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1500630 | Boone |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1500631 | White |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1500632 | Putnam |  | Indiana Department of Transportation | 2018-05-31 | CE
CN
PE
|  |  | 1500633 | Putnam |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1500634 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500635 | Morgan |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1500636 | White |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500637 | Clay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500638 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1500639 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500640 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500641 | Montgomery |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500642 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500643 | Tippecanoe |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1500644 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500645 | Clinton |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1500646 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1500647 | Warren |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500648 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500649 | Hendricks |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1500650 | Putnam |  | Indiana Department of Transportation | 2025-12-10 | PE
RR
|  |  | 1500651 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 1500652 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 1500653 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1500654 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
RR
|  |  | 1500655 | Boone |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1500656 | Fountain | Corradino, LLC | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1500657 | Clay |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500658 | Clay |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1500659 | Clay |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1500660 | Clay |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1500661 | Putnam |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 1500662 | Putnam |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1500663 | Putnam |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500664 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1500665 | Hendricks |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1500666 | Boone |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2017-09-13 | CE
|  |  | 1500667 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1500668 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1500669 | Marshall |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1500670 |  | CH2M HILL, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1500671 | Vermillion | H W Lochner, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500672 | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500673 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500674 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1500675 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500676 | White | Independent Appraisers-Consultants, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500678 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500679 | LaPorte |  | Indiana Department of Transportation | 2021-03-10 | CE
|  |  |  | Starke |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1500680 | Marshall |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500681 | Marshall |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500682 | Newton |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1500683 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500684 | Newton |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500685 | Johnson |  | Franklin | 2019-11-14 | CE
CN
PE
ROW
|  |  | 1500686 | Newton |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500687 | Cass |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1500688 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500689 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500690 | Cass |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
RR
|  |  | 1500691 |  |  | Indiana Department of Transportation | 2015-05-22
|  |  | 1500692 | Johnson |  | Franklin | 2018-01-18 | CE
CN
PE
|  |  | 1500693 | Warrick |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500694 | Knox |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1500695 | Sullivan | Anelena Ackerly | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500696 | Crawford |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1500697 | Knox |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500698 | Sullivan |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500699 | Sullivan |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500700 | Sullivan |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500701 | Sullivan | Anelena Ackerly | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1500702 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500703 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1500704 | Knox |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1500705 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500706 | Perry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500707 | Perry |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500708 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500709 | Knox |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500710 | Vanderburgh |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500711 | Spencer |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500712 | Spencer |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  |  | Warrick |  | Indiana Department of Transportation | 2018-04-11 | CE
PE
ROW
|  |  | 1500713 | Greene |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500714 | Warrick |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500715 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 1500716 | Greene |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500717 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500718 | Dubois |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1500719 | Pike |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1500720 | Pike |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500721 | Pike |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500722 | Dubois |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1500723 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500724 | Lake |  | Hammond | 2017-04-05 | CE
CN
|  |  | 1500725 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500726 |  |  | MPO - Northwest | -339679.2083
|  |  | 1500727 |  |  | Indiana Department of Transportation | 2007-11-14
|  |  | 1500728 | Warrick |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500729 | Gibson | Heritage Engineering, LLC | Indiana Department of Transportation | 2018-03-21 | CE
CN
PE
|  |  |  | Knox | Heritage Engineering, LLC | Indiana Department of Transportation | 2018-03-21 | CE
PE
|  |  | 1500730 | Sullivan | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  |  | Vigo | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | 2018-03-14 | PE
|  |  | 1500731 | Dubois |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1500732 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500733 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1500734 | Pike | HNTB Indiana, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500735 | Martin | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500736 | Martin | EcoTec, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500737 | St. Joseph |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500738 |  |  | MPO - Kokomo | 2015-12-14
|  |  | 1500739 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1500740 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1500741 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1500742 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
RR
|  |  | 1500743 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500744 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500745 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500746 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500747 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500748 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500749 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500750 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500751 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500752 | Noble | ERES International, Inc. | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500753 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500754 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500755 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500756 | Miami |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1500757 | Miami |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1500758 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500759 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500760 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500761 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500762 | Kosciusko |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500763 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500764 | Huntington |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500765 | Huntington |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500766 | Wells |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500767 | Huntington |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500768 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500769 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500770 | Grant |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1500771 | Grant |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1500772 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500773 | Grant |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500774 | Steuben |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
RR
|  |  | 1500775 | Steuben |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1500776 | Dekalb |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1500777 | Dekalb |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500778 | Steuben |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500779 | Steuben |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500780 | Dekalb |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1500781 | Allen |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1500782 | Dekalb |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1500783 | Whitley |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500784 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500785 | Marion |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1500786 | Shelby |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1500787 | Allen |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500788 | Allen |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500789 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1500790 | Noble | Debbie L. Morris | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
RR
|  |  | 1500791 | Noble |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500792 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1500793 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1500794 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1500795 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1500796 | Wayne |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500797 | Wayne |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1500798 | Madison |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1500799 | Hamilton | Another Test Company | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500800 | Hamilton | Another Test Company | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500801 | Allen |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500802 | Allen |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500803 | Allen |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500804 | Allen |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500805 | Marion |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1500806 | Wayne |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1500807 | Steuben |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500808 | Steuben |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500809 | Wayne |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1500810 | Marion | Another Test Company | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1500811 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500812 | Whitley |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500813 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1500814 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1500815 | Steuben |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500816 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500817 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500818 | Steuben |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1500819 | Jay | Alliance Survey Company | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1500820 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1500821 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1500822 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1500823 | Steuben |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1500824 | Huntington |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1500825 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500826 | Dekalb |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1500827 | Huntington |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
ROW
|  |  | 1500828 | Steuben |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1500829 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500830 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500831 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500832 | Miami |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500833 | Miami |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500834 | Wabash |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1500835 | Dekalb |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1500836 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1500837 | Allen |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500838 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1500839 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1500840 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1500841 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500842 | Adams | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500843 | Adams |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1500844 | Adams |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500845 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1500846 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1500847 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1500848 | LaGrange |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1500849 | Huntington | M-E Companies, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  |  | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500850 |  | Home Guide Realty Services | Indiana Department of Transportation | -339679.2083
|  |  | 1500851 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500852 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500853 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500854 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500855 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500856 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500857 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500858 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500859 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500860 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500861 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500862 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500863 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1500864 | Shelby |  | Indiana Department of Transportation | 2015-11-10 | CE
CN
|  |  | 1500865 | Perry |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1500866 | Perry |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1500867 | Gibson |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1500868 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1500869 | Greene | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592005 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1592006 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1592007 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1592008 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1592009 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1592010 |  | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592011 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2006-09-13
|  |  | 1592012 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1592013 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1592014 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1592015 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2015-10-07
|  |  | 1592016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592017 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592018 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592019 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592020 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592021 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592022 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592023 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592024 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592025 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592026 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592027 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592028 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592029 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592030 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592031 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592032 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592033 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1592034 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2015-10-07
|  |  | 1592035 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2015-10-07
|  |  | 1592036 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1592037 |  |  | Indiana Department of Transportation | 2015-10-07
|  |  | 1592038 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592039 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592040 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592041 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592042 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592043 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592044 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592045 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592046 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592047 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592048 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592049 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592050 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592051 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592052 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592053 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592054 | Various |  | Indiana Department of Transportation | 2015-05-31 | PL
|  |  | 1592055 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592056 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592057 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592058 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592059 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592060 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592061 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592062 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592063 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592064 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592065 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592066 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592067 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592068 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592069 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592070 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592071 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592072 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592073 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592074 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592075 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592076 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592077 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592078 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592079 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592080 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592081 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592082 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592083 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592084 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592085 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592086 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592087 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592088 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592089 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592090 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592091 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592092 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592093 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592094 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592095 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592096 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592097 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592098 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592099 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592100 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592101 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592102 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592103 |  |  | Indiana Department of Transportation | 2009-02-11
|  |  | 1592104 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592105 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592106 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592107 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592108 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592109 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592110 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592111 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592112 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592113 |  |  | Indiana Department of Transportation | 2008-11-19
|  |  | 1592114 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592115 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592116 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592117 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592118 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592119 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592120 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592121 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592122 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592123 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592124 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592125 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592126 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592127 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592128 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592129 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592130 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592131 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592132 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592133 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592134 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592135 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592136 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592137 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592138 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592139 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592140 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592141 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592142 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592143 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592144 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592145 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592146 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592147 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592148 | Huntington |  | Indiana Department of Transportation | 2015-10-07 | CE
CN
|  |  | 1592149 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592150 | Vanderburgh | CGI | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1592151 | Hendricks |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1592152 | Hamilton |  | Fishers | 2018-12-12 | CN
PE
ROW
|  |  | 1592153 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1592154 | Warrick |  | Warrick County | 2021-02-10 | CE
CN
PE
ROW
UT
|  |  | 1592155 | Starke |  | Starke County | -339679.2083 | PE
|  |  | 1592156 | Vanderburgh |  | Vanderburgh County | 2019-07-10 | CE
CN
PE
RR
|  |  | 1592157 | Cass |  | Cass County | -339679.2083 | PE
|  |  | 1592158 | Fulton |  | Fulton County | -339679.2083 | PE
|  |  | 1592159 | Jasper |  | Jasper County | -339679.2083 | PE
|  |  | 1592160 | Lake |  | Lake County | -339679.2083 | PE
|  |  | 1592161 | Marshall |  | Marshall County | -339679.2083 | PE
|  |  | 1592162 | Newton |  | Newton County | -339679.2083 | PE
|  |  | 1592163 | Porter |  | Porter County | -339679.2083 | PE
|  |  |  | Various |  | Porter County | -339679.2083 | PE
|  |  | 1592164 | Pulaski |  | Pulaski County | -339679.2083 | PE
|  |  | 1592165 | St. Joseph |  | St. Joseph County | -339679.2083 | PE
|  |  | 1592166 | White |  | White County | -339679.2083 | PE
|  |  | 1592167 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592168 | Jackson |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
PE
|  |  | 1592169 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592170 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1592171 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1592172 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592173 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592174 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1592175 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1592176 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592177 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592180 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592181 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592183 |  |  | MPO - Terre Haute | -339679.2083
|  |  | 1592184 |  |  | MPO - Evansville | 2016-05-31
|  |  | 1592185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592186 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2016-09-14
|  |  | 1592187 | Floyd |  | Indiana Department of Transportation | 2020-11-13 | PE
|  |  | 1592188 | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1592189 | Elkhart |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1592190 | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1592191 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 1592192 |  |  | Indiana Department of Transportation | 2003-03-25
|  |  | 1592193 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1592194 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1592195 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1592196 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1592197 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1592198 | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1592199 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1592200 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1592201 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1592202 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1592203 | Porter |  | MPO - Northwest | -339679.2083 | PL
|  |  |  | Various |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1592204 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592205 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592206 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
PL
|  |  | 1592207 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592208 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592209 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592210 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592211 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1592212 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592213 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592214 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592215 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592216 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1592217 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592218 | Clark | Data Transfer Solutions, LLC | MPO - Louisville | -339679.2083 | PL
|  |  | 1592219 | Clark | Data Transfer Solutions, LLC | MPO - Louisville | -339679.2083 | PL
|  |  | 1592220 | Clark | Data Transfer Solutions, LLC | MPO - Louisville | -339679.2083 | PL
|  |  | 1592221 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592223 | Jennings |  | Indiana Department of Transportation | 2022-04-06 | ROW
|  |  | 1592224 | Jennings |  | Indiana Department of Transportation | 2022-04-06 | ROW
|  |  | 1592225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592226 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592227 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592228 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592229 | Clark |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1592230 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592231 |  |  | Indiana Department of Transportation | 2016-01-13
|  |  | 1592232 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1592233 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1592234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592235 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592236 |  |  | Indiana Department of Transportation | 2006-05-24
|  |  | 1592237 |  |  | Indiana Department of Transportation | 2009-03-11
|  |  | 1592238 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 1592239 |  |  | Indiana Department of Transportation | 2008-04-02
|  |  | 1592240 |  |  | Floyd County | 2017-05-31
|  |  | 1592241 |  |  | Floyd County | 2017-05-31
|  |  | 1592242 |  |  | Floyd County | 2017-05-31
|  |  | 1592243 |  |  | Floyd County | 2017-05-31
|  |  | 1592244 |  |  | Floyd County | 2017-05-31
|  |  | 1592245 |  |  | Floyd County | 2017-05-31
|  |  | 1592246 |  |  | Floyd County | 2017-05-31
|  |  | 1592247 | Floyd |  | Floyd County | 2016-05-05 | CE
CN
|  |  | 1592248 |  |  | Floyd County | 2017-05-31
|  |  | 1592249 |  |  | Floyd County | 2017-05-31
|  |  | 1592250 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592251 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592252 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592253 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592254 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592255 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592256 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592257 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1592258 | Greene |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1592259 | Greene |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1592260 | Spencer | Landmark Engineering Group, Inc. | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1592261 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592262 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592264 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592265 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592266 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592267 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592268 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592269 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592270 | Monroe |  | Bloomington | 2016-05-30 | PE
|  |  | 1592271 | Monroe |  | Monroe County | 2016-03-02 | CE
CN
|  |  | 1592272 | Clinton |  | Indiana Department of Transportation | 2016-01-13 | CE
CN
|  |  | 1592273 | Lake | Edwards and Kelcey | Lowell | -339679.2083 | PE
|  |  | 1592274 | Lake |  | Highland | 2019-01-16 | CE
CN
PE
|  |  | 1592275 | Lake |  | Hobart | 2019-08-07 | CE
CN
PE
|  |  | 1592276 |  |  | LaPorte County | -339679.2083
|  |  | 1592277 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592278 | Howard | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1592279 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1592280 |  |  | Clarksville | -339679.2083
|  |  | 1592281 |  | Consolidated Test Company | Indiana Department of Transportation | 2015-08-19
|  |  | 1592282 |  |  | Indiana Department of Transportation | 2016-03-02
|  |  | 1592283 | Howard |  | Kokomo | -339679.2083 | PL
|  |  | 1592284 | Howard |  | Kokomo | -339679.2083 | PL
|  |  | 1592285 | Delaware |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
RR
|  |  | 1592286 | Delaware |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
RR
|  |  | 1592287 | Delaware |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592288 | Delaware |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592289 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1592290 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1592291 | Vanderburgh |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592292 | Monroe |  | Bloomington | -339679.2083 | PL
|  |  | 1592293 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592294 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08
|  |  | 1592295 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08
|  |  | 1592296 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08
|  |  | 1592297 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08
|  |  | 1592298 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-07-08
|  |  | 1592299 | Madison |  | Anderson | 2025-01-15 | PE
|  |  | 1592300 | Madison |  | Anderson | 2019-02-06 | CE
CN
PE
ROW
|  |  | 1592301 |  |  | Indiana Department of Transportation | 2015-08-27
|  |  | 1592302 |  |  | Transit Operators | -339679.2083
|  |  | 1592303 |  |  | Transit Operators | -339679.2083
|  |  | 1592304 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1592305 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592306 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1592307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592308 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592309 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592312 | Jay |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1592313 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592314 | Cass | Eco Logic, LLC | Logansport | 2018-03-14 | PE
|  |  | 1592315 |  | Fidelity National Title Insurance Company, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592316 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1592317 | Elkhart |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
ROW
|  |  | 1592318 | Clark |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
ROW
|  |  | 1592319 | Boone |  | Indiana Department of Transportation | 2016-02-17 | CE
CN
PE
|  |  | 1592320 | Various |  | Indiana Department of Natural Resources | -339679.2083 | OT
|  |  | 1592321 | Marion |  | Indiana Department of Natural Resources | 2016-05-31 | CN
|  |  | 1592322 | Various |  | Indiana Department of Natural Resources | 2016-05-31 | CN
|  |  | 1592323 | Monroe |  | Indiana Department of Natural Resources | 2018-05-31 | CN
PE
ROW
|  |  | 1592324 |  |  | Monroe County | -339679.2083
|  |  | 1592325 |  |  | Monroe County | -339679.2083
|  |  | 1592326 | Wayne |  | Indiana Department of Natural Resources | 2019-05-31 | CN
PE
ROW
|  |  | 1592327 |  |  | Richmond | -339679.2083
|  |  | 1592328 |  |  | Richmond | -339679.2083
|  |  | 1592329 | Elkhart |  | Indiana Department of Natural Resources | 2019-05-31 | CN
PE
ROW
|  |  | 1592330 |  |  | Elkhart County | -339679.2083
|  |  | 1592331 |  |  | Elkhart County | -339679.2083
|  |  | 1592332 | Fountain |  | Veedersburg | 2017-05-31 | CN
PE
|  |  | 1592333 |  |  | Veedersburg | -339679.2083
|  |  | 1592334 |  |  | Veedersburg | -339679.2083
|  |  | 1592335 | LaPorte |  | LaPorte County | 2023-02-15 | PE
|  |  | 1592336 | LaPorte |  | LaPorte County | -339679.2083 | PE
|  |  | 1592337 | LaPorte |  | LaPorte County | -339679.2083 | PE
|  |  | 1592338 | LaPorte |  | LaPorte County | -339679.2083 | PE
|  |  | 1592339 | LaPorte |  | La Porte | -339679.2083 | PE
|  |  | 1592340 |  |  | Michigan City | -339679.2083
|  |  | 1592341 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
UT
|  |  | 1592342 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2016-03-02 | CE
CN
UT
|  |  | 1592343 | Delaware |  | Delaware County | -339679.2083 | PL
|  |  | 1592344 |  | Amereco Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 1592345 | Hamilton | CPS Acquisitions, LLC | Fishers | 2019-07-10 | CE
CN
|  |  | 1592346 | Hamilton | CPS Acquisitions, LLC | Fishers | 2020-12-09 | CE
CN
|  |  | 1592347 | Hamilton | CPS Acquisitions, LLC | Fishers | 2020-12-09 | CE
CN
|  |  | 1592348 |  | CPS Acquisitions, LLC | Fishers | 2022-02-09
|  |  | 1592349 | Hamilton | H. Stewart Kline & Associates, Inc. | Fishers | 2020-02-05 | CE
CN
|  |  | 1592350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592351 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592352 | St. Joseph |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1592353 |  |  | Tippecanoe County | -339679.2083
|  |  | 1592354 | Tippecanoe |  | Tippecanoe County | -339679.2083 | PL
|  |  | 1592355 |  |  | Indiana Department of Transportation | 2016-04-06
|  |  | 1592356 |  |  | Indiana Department of Transportation | 2015-12-01
|  |  | 1592357 |  |  | Huntingburg | 2018-05-31
|  |  | 1592358 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1592359 | Cass |  | Logansport | -339679.2083 | PE
|  |  | 1592360 |  |  | MPO - Muncie | -339679.2083
|  |  | 1592361 |  |  | MPO - Muncie | -339679.2083
|  |  | 1592362 |  |  | MPO - Muncie | -339679.2083
|  |  | 1592363 |  |  | MPO - Muncie | -339679.2083
|  |  | 1592364 |  |  | MPO - Muncie | -339679.2083
|  |  | 1592365 |  |  | Indiana Department of Transportation | 2016-02-03
|  |  | 1592366 | White |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592367 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592368 |  |  | Indiana Department of Transportation | 2016-02-03
|  |  | 1592369 |  |  | Indiana Department of Transportation | 2016-02-03
|  |  | 1592370 |  |  | Indiana Department of Transportation | 2016-02-03
|  |  | 1592371 | Orange |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592372 | Daviess |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  |  | Greene |  | Indiana Department of Transportation | 2019-07-10 | CE
|  |  | 1592373 | Cass | Eco Logic, LLC | Logansport | 2020-01-15 | CE
CN
PE
ROW
|  |  | 1592374 | Morgan |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1592375 | Clinton |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
RR
|  |  | 1592376 | Franklin |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592377 | Franklin |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592378 | Ripley |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592379 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592380 | Ripley |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592381 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592382 |  |  | Indiana Department of Transportation | 2016-04-06
|  |  | 1592383 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1592384 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592385 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05 | PE
|  |  | 1592386 |  |  | Indiana Department of Transportation | 2016-03-02
|  |  | 1592387 |  | CPS Acquisitions, LLC | Fishers | 2022-05-05
|  |  | 1592388 |  |  | Allen County | 2016-05-31
|  |  | 1592389 |  |  | Indiana Department of Transportation | 2016-03-02
|  |  | 1592390 | Lawrence |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592391 |  | ERES International, Inc. | Indiana Department of Transportation | 2016-03-02
|  |  | 1592392 | Dekalb |  | Indiana Department of Transportation | 2016-03-02 | CE
CN
|  |  | 1592393 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2017-02-08
|  |  | 1592394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592396 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592397 | Franklin | ARCADIS | Indiana Department of Transportation | 2017-07-12 | CN
|  |  |  | Ripley | ARCADIS | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592398 | Dearborn | Kaskaskia Engineering Group | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1592399 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1592400 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1592401 |  |  | Indiana Department of Transportation | 2016-09-24
|  |  | 1592402 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2015-05-31
|  |  | 1592403 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2015-05-31
|  |  | 1592404 | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 1592405 | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 1592406 | Warrick | CGI | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1592407 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1592408 | Vigo |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
ROW
UT
|  |  | 1592409 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 1592410 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 1592411 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1592412 |  |  | Indiana Department of Transportation | 2014-12-17
|  |  | 1592413 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592414 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592415 | Hamilton |  | Hamilton County | 2016-12-14 | CE
CN
|  |  | 1592416 | Crawford |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1592417 | Porter | Hy-Tech Response, Inc. | Porter | 2017-03-01 | CE
CN
PE
|  |  | 1592418 | Lake | Jackie S. Dodd, Attorney at Law | Schererville | 2017-04-05 | CE
CN
PE
|  |  | 1592419 | Lake | Edwards and Kelcey | Lowell | 2017-04-05 | CE
CN
PE
|  |  | 1592420 | Lake |  | Merrillville | 2018-11-15 | CE
CN
PE
|  |  | 1592421 | Tipton |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
RR
UT
|  |  | 1592422 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592423 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1592424 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592425 |  |  | Indiana Department of Transportation | 2016-05-05
|  |  | 1592426 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
UT
|  |  | 1592427 |  | Consolidated Test Company | Indiana Department of Transportation | 2016-08-10
|  |  | 1592428 | Allen |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1592429 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1592430 | Jackson |  | Seymour | 2016-04-06 | CE
CN
|  |  | 1592431 | Jackson |  | Seymour | 2016-04-06 | CE
CN
|  |  | 1592432 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2017-05-31
|  |  | 1592433 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  |  | Marion | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1592434 | Delaware |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
PE
|  |  | 1592435 | Delaware |  | Indiana Department of Transportation | 2016-09-14 | CE
CN
|  |  | 1592436 | St. Joseph | HDR Engineering, Inc. | North Liberty | 2021-01-13 | CE
CN
PE
ROW
|  |  | 1592437 |  |  | Indiana Department of Transportation | 2016-05-12
|  |  | 1592438 | Henry |  | Indiana Department of Transportation | 2016-02-03 | CE
CN
|  |  | 1592439 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1592440 | Cass | Eco Logic, LLC | Logansport | 2017-03-01 | CE
CN
PE
|  |  | 1592441 |  |  | Indiana Department of Transportation | 2016-03-02
|  |  | 1592442 |  |  | Anderson | -339679.2083
|  |  | 1592443 | Hancock |  | Fortville | 2018-02-07 | CE
CN
PE
|  |  | 1592444 | Hancock | CTLGroup | Fortville | 2020-07-08 | CE
CN
PE
ROW
RR
|  |  | 1592447 | Hancock | CTLGroup | Fortville | 2022-07-13 | PE
ROW
|  |  | 1592448 | Hancock | CTLGroup | Fortville | 2025-07-09 | PE
ROW
|  |  | 1592449 | Hancock | CTLGroup | Fortville | 2021-11-17 | CE
CN
PE
ROW
|  |  | 1592450 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1592451 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1592452 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1592453 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1592454 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2016-05-31
|  |  | 1592455 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2016-05-31
|  |  | 1592456 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1592457 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1592458 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 1592459 |  |  | Indiana Department of Transportation | 2005-12-14
|  |  | 1592460 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592461 |  | Appraising Indiana, LLC | Indiana Department of Transportation | 2015-06-24
|  |  | 1592462 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1592463 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592464 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592465 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592466 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1592467 | Spencer |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1592468 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1592469 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2019-05-31
|  |  | 1592470 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2019-05-31
|  |  | 1592471 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1592472 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
RR
|  |  | 1592473 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
RR
|  |  | 1592474 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592475 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592476 | Floyd |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1592477 | Knox |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1592478 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1592479 |  |  | Harrison County | 2018-04-11
|  |  | 1592480 | Hamilton |  | Fishers | 2016-04-06 | CN
|  |  | 1592481 | Vanderburgh |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1592482 |  |  | Boone County | 2017-02-08
|  |  | 1592483 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1592484 |  |  | Indiana Department of Transportation | 2016-03-16
|  |  | 1592485 |  | CoCal Consulting, LLC | Greenfield | -339679.2083
|  |  | 1592486 | Various |  | Indiana Department of Transportation | 2017-05-31 | OT
|  |  | 1592487 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1592488 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1592489 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592490 | Allen |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
OT
PE
|  |  | 1592491 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1592492 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592493 | Allen |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592494 | Elkhart |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1592495 | Jay |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1592496 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1592497 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592498 | Allen | D & D Consulting Services, Inc. | Indiana Department of Transportation | 2016-10-05 | CE
CN
PE
|  |  | 1592499 | Whitley |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592500 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592501 | LaGrange | Duesler Realty House | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1592502 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592503 | Adams | Bidinfo | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
RR
|  |  | 1592504 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592505 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592506 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
RR
|  |  | 1592507 | Dekalb |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
RR
|  |  | 1592508 | Allen |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592509 | Whitley |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592510 | Jennings |  | Indiana Department of Transportation | 2017-08-23 | CE
CN
PE
|  |  | 1592511 | Johnson |  | Franklin | 2016-07-13 | CE
CN
|  |  | 1592512 | Jackson |  | Indiana Department of Transportation | 2016-06-15 | CE
CN
|  |  | 1592513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592514 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1592515 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592516 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592517 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592518 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592519 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592520 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592521 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592522 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592523 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592524 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592525 | Marion |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592526 | Marion |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592527 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592528 | Marion |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592529 | Marion |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592530 | Shelby |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592531 | Shelby |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592532 | Wayne |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1592533 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592534 | Shelby |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1592535 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592536 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592537 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592538 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592539 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592540 | Tipton |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592541 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1592542 | Delaware |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1592543 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592544 |  | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | 2022-04-06
|  |  | 1592545 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1592546 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1592547 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1592548 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592549 | Tipton |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592550 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592551 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592552 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592553 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592554 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592555 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 1592556 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 1592557 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592558 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592559 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1592560 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592561 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592562 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592563 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592564 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592565 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1592566 | Delaware |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592567 | Delaware |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592568 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592569 | Delaware |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
RR
|  |  | 1592570 | Delaware |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
RR
|  |  | 1592571 | Delaware |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
RR
|  |  | 1592572 | Delaware |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
RR
|  |  | 1592573 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592574 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592575 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592576 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592577 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592578 | Gibson |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1592579 | Gibson | Harvard Title Searching | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1592580 | Warrick | Eilts Consulting Services | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
RR
|  |  | 1592581 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592582 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592583 | Madison |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1592584 | Martin | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  |  | Orange | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | 2017-04-05 | RR
|  |  | 1592585 | Greene | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
RR
|  |  | 1592586 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1592587 | Lawrence | ICA Engineering, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1592588 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592589 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592590 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592591 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592592 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592593 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592594 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592595 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592596 | Fayette |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1592597 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592598 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592599 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592600 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1592601 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592602 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592603 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592604 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592605 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592606 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592607 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592608 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592609 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592610 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592611 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592612 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1592613 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592614 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592615 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592616 | Knox |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592617 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592618 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592619 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592620 | Parke |  | Indiana Department of Transportation | 2018-06-20 | CE
CN
PE
ROW
|  |  | 1592621 | Daviess |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1592622 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1592623 | Various |  | Indiana Department of Transportation | 2017-01-19 | PE
|  |  | 1592624 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592625 | Various |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592626 | Warrick |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1592627 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1592628 | Knox | CGI | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1592629 | Gibson | HNTB Indiana, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592630 | Orange |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1592631 | Huntington |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1592632 | Huntington |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1592633 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1592634 | Allen |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1592635 | Wabash |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1592636 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1592637 | Huntington |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1592638 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1592639 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592640 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2017-03-01 | CE
CN
|  |  | 1592641 | Grant |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1592642 | Ripley | ARCADIS | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592643 | Brown | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592644 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592645 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1592646 | Dearborn |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1592647 | Johnson | Burrell Appraisal Service, Inc. | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1592648 | Allen |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1592649 | Whitley |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1592650 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592651 |  | ABt SRBI | Indiana Department of Transportation | 2020-09-02
|  |  | 1592652 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592653 |  |  | Whitestown | 2016-04-11
|  |  | 1592654 | Various |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1592655 | Various |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592656 | Various |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1592657 | Boone |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1592658 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592659 | Allen |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1592660 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592661 | Allen |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1592662 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592663 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592664 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592665 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592666 | Miami |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592667 | Noble | Debbie L. Morris | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592668 | Noble | ERES International, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592669 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592670 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1592671 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1592672 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1592673 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592674 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592675 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592676 | Elkhart |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1592677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592678 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1592679 | Miami |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1592680 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1592681 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1592682 | Starke | H.R. Gray | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1592683 | White |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1592684 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1592685 | Clinton | Iteris, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1592686 | Tippecanoe |  | Indiana Department of Transportation | 2019-04-03 | CN
PE
|  |  |  | White |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1592687 | Putnam |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1592688 | Parke |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1592689 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592690 | Boone |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1592691 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592692 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592693 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592694 |  |  | MPO - Northwest | -339679.2083
|  |  | 1592695 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592696 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592697 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592698 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
RR
|  |  | 1592699 | Floyd |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
RR
|  |  | 1592700 | Clark |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592701 | Clark |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592702 | Decatur |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  |  | Franklin |  | Indiana Department of Transportation | 2017-07-12 | CE
|  |  | 1592703 | Dearborn |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1592704 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592705 | Tippecanoe |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1592706 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592707 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
RR
|  |  | 1592708 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
RR
|  |  | 1592709 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
RR
|  |  | 1592710 | Dearborn |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1592711 | Dearborn |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1592712 | Harrison |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592713 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-07-12 | CE
CN
RR
|  |  | 1592714 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-07-12 | CE
CN
RR
|  |  | 1592715 | Porter | Corn Island Archaeology, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592716 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
|  |  | 1592717 | Lake |  | Indiana Department of Transportation | 2017-05-12 | CE
CN
PE
RR
|  |  | 1592718 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
RR
|  |  | 1592719 | Various |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592720 | Clinton |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592721 | Boone |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592722 | Boone |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1592723 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592724 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592725 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 1592726 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592727 | Warrick |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1592728 | Putnam |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1592729 | Putnam |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1592730 | Putnam |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1592731 | Putnam |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1592732 | Putnam |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1592733 | Putnam |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1592734 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1592735 | Porter | Corn Island Archaeology, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592736 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592737 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592738 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592739 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592741 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592742 | Vigo |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1592743 | Vigo |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1592744 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592745 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592746 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2020-03-04 | CE
CN
RR
|  |  | 1592747 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2020-03-04 | CE
CN
RR
|  |  | 1592748 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592749 | Montgomery |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592751 | Hendricks |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592752 | Hendricks |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592753 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592754 | Montgomery |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592755 | Montgomery |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592756 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592757 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592758 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592759 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592760 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1592761 | Montgomery |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592762 | Vermillion |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592763 | Vermillion |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592764 | Boone |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592766 | Montgomery |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1592767 | Montgomery |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1592768 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592769 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592770 | Fountain |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592771 | Fountain |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1592772 | Hendricks |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
RR
|  |  | 1592773 | Hendricks |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
RR
|  |  | 1592774 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592775 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592776 | Dubois |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1592777 | Gibson | I. T. Business Corporation | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1592778 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592779 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592780 | Daviess | CBRE, Inc. | Indiana Department of Transportation | 2020-07-08 | PE
|  |  |  | Greene | CBRE, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1592781 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592782 | Vanderburgh | CGI | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1592783 | Spencer |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1592784 | Fountain |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1592785 | Gibson | Coor Consulting | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
RR
|  |  | 1592786 | Parke |  | Indiana Department of Transportation | 2018-07-11 | CE
|  |  |  | Vermillion |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1592787 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592788 | Montgomery | DLZ Indiana, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1592789 | Greene |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1592790 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592792 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1592793 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1592794 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592795 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592796 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592797 | Dearborn |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1592798 | Jennings |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1592799 | Morgan |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1592800 | Dearborn |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1592801 | Ripley |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1592802 | Warrick |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592803 | Warrick |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592804 | Warrick |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
RR
|  |  | 1592805 | Warrick |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592806 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592807 | Martin |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592808 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592809 | Martin |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592810 | Crawford |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592811 | Posey |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592812 | Greene | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592813 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592814 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592815 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592816 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592817 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592818 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592819 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592820 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592821 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592822 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592823 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592824 |  | MainLine Management, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592825 | Orange |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592826 | Vigo |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1592827 | Montgomery |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
RR
|  |  | 1592828 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592829 | Putnam |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1592830 | Clay | Context, LLC | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1592831 | Fountain |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1592832 | Fountain |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1592833 |  | AECON, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592834 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1592835 | Benton |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592836 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592837 | Benton |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592838 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592839 | Fountain |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1592840 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2020-02-05 | PE
RR
|  |  | 1592841 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1592842 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
RR
|  |  | 1592843 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592844 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1592845 | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1592846 | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1592847 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1592848 | Greene |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592849 | Sullivan |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592850 | Sullivan |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1592851 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
|  |  | 1592852 | Jennings |  | Indiana Department of Transportation | 2017-10-12 | CE
CN
PE
|  |  | 1592853 | Starke |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1592854 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
RR
|  |  | 1592855 |  |  | Indiana Department of Transportation | 2016-04-06
|  |  | 1592856 | Porter | Marine Solutions, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592857 | Porter | Domain Architecture, Inc. | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592858 | Brown |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1592859 | Shelby |  | Shelby County | 2018-04-11 | CE
CN
|  |  | 1592860 | Washington | Earth Source Inc. | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1592861 | Floyd | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2017-05-10 | CN
|  |  |  | Washington | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1592862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592863 |  | J.F. New & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592864 | Adams |  | Adams County | -339679.2083 | PE
|  |  | 1592865 |  | Michael Baker International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592866 | Hamilton | Duneland Group, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
|  |  |  | Madison | Duneland Group, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1592867 | Jay |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592868 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592869 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592870 | St. Joseph |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1592871 | St. Joseph |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1592872 | Allen |  | Allen County | -339679.2083 | PE
|  |  | 1592873 | Lake | Cornerstone Design | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592874 | Steuben | Certified Engineering, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1592875 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592876 | LaGrange |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1592877 | Adams |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1592878 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592879 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592880 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
PE
|  |  | 1592881 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1592882 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2023-02-15 | PE
|  |  | 1592883 | Blackford |  | Blackford County | -339679.2083 | PE
|  |  | 1592884 | Harrison |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1592885 | Harrison |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1592886 | Dekalb |  | Dekalb County | -339679.2083 | PE
|  |  | 1592887 | Elkhart |  | Elkhart County | -339679.2083 | PE
|  |  | 1592888 | Grant |  | Grant County | -339679.2083 | PE
|  |  | 1592889 | Huntington |  | Huntington County | -339679.2083 | PE
|  |  | 1592890 | Spencer | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1592891 | Kosciusko |  | Kosciusko County | -339679.2083 | PE
|  |  |  | Various |  | Kosciusko County | -339679.2083 | PE
|  |  | 1592894 | Franklin | ARCADIS | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1592895 | Scott | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
RR
|  |  | 1592896 | Decatur |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1592897 | Monroe |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1592898 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592899 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592901 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592902 | Daviess |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1592903 | Crawford |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
|  |  | 1592904 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592905 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592906 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592907 | Morgan |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1592908 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
RR
|  |  | 1592909 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592910 | Porter | Corn Island Archaeology, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592911 | Lawrence | Hagerty Engineering, Inc. | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1592912 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592913 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1592914 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1592915 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
RR
UT
|  |  | 1592916 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
RR
|  |  | 1592917 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1592918 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592919 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592920 | Various |  | LaGrange County | -339679.2083 | PE
|  |  | 1592921 | Elkhart |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1592922 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592923 | Miami |  | Miami County | -339679.2083 | PE
|  |  | 1592924 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592925 | Elkhart |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1592926 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592927 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592928 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592929 | Noble |  | Noble County | -339679.2083 | PE
|  |  | 1592930 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592931 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1592932 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592933 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592934 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592935 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592936 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592937 | Hendricks |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1592938 | Steuben |  | Steuben County | -339679.2083 | PE
|  |  | 1592939 | Various |  | Wabash County | -339679.2083 | PE
|  |  |  | Wabash |  | Wabash County | -339679.2083 | PE
|  |  | 1592940 | Wells |  | Wells County | -339679.2083 | PE
|  |  | 1592941 | Warrick |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
RR
|  |  | 1592942 | Greene | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1592943 | Various |  | Whitley County | -339679.2083 | PE
|  |  |  | Whitley |  | Whitley County | -339679.2083 | PE
|  |  | 1592944 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592945 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592946 | Daviess | Houseal Lavigne Associates | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1592947 |  | Indiana University | Indiana Department of Transportation | -339679.2083
|  |  | 1592948 |  | Indiana Infrastructure Partners, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592949 | Vanderburgh |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1592950 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592951 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592952 | Vermillion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1592953 |  | Corradino, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592954 | Putnam |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1592955 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1592956 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592957 |  | Context, LLC | Indiana Department of Transportation | 2020-07-08
|  |  | 1592958 | Vanderburgh |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1592959 |  | Infrastructure Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592960 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592961 |  |  | Indiana Department of Transportation | 2026-07-08
|  |  | 1592962 | Boone |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1592963 |  | Linda F. Russell | Indiana Department of Transportation | -339679.2083
|  |  | 1592964 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592965 |  | Delcan Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1592966 | Lawrence | ICA Engineering, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1592967 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592968 | Tippecanoe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1592969 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1592970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592971 | Clinton |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
ROW
UT
|  |  | 1592972 |  | GRW Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592973 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2019-12-11 | PE
RR
|  |  | 1592974 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592975 |  | BA Martin Architects, PC | Indiana Department of Transportation | -339679.2083
|  |  | 1592976 | Orange |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1592977 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592978 |  | AI Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1592979 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1592980 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1592981 | Crawford |  | Crawford County | -339679.2083 | PE
|  |  | 1592982 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592983 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1592984 | Daviess |  | Daviess County | -339679.2083 | PE
|  |  | 1592985 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592986 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592987 | Dubois |  | Dubois County | -339679.2083 | PE
|  |  |  | Various |  | Dubois County | -339679.2083 | PE
|  |  | 1592988 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1592989 | Allen |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1592990 | Gibson |  | Gibson County | -339679.2083 | PE
|  |  | 1592991 | Knox |  | Knox County | -339679.2083 | PE
|  |  |  | Various |  | Knox County | -339679.2083 | PE
|  |  | 1592992 | Lawrence |  | Lawrence County | -339679.2083 | PE
|  |  | 1592993 | Martin |  | Martin County | -339679.2083 | PE
|  |  |  | Various |  | Martin County | -339679.2083 | PE
|  |  | 1592994 | Orange |  | Orange County | -339679.2083 | PE
|  |  | 1592995 | Clark |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
RR
|  |  | 1592996 | Delaware |  | Muncie | 2019-01-16 | CE
CN
PE
RR
|  |  | 1592997 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1592998 | Delaware | Michael Baker International, Inc. | Yorktown | 2021-01-13 | CE
CN
PE
|  |  | 1592999 | Perry |  | Perry County | -339679.2083 | PE
|  |  | 1593000 | Pike |  | Pike County | -339679.2083 | PE
|  |  | 1593001 | Posey |  | Posey County | -339679.2083 | PE
|  |  |  | Various |  | Posey County | -339679.2083 | PE
|  |  | 1593002 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593003 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
RR
|  |  | 1593004 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
RR
|  |  | 1593005 | Putnam |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1593006 | Putnam |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1593007 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593008 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593009 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593010 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
RR
|  |  | 1593011 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593012 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593013 | Vermillion |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593014 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593015 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1593016 | Spencer |  | Spencer County | -339679.2083 | PE
|  |  | 1593017 | Franklin | Applied Geology and Environmental Science, INC | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1593018 | Sullivan |  | Sullivan County | -339679.2083 | PE
|  |  | 1593019 | Harrison |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1593020 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593021 | Vanderburgh |  | Vanderburgh County | -339679.2083 | PE
|  |  | 1593022 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593023 | Various |  | Warrick County | -339679.2083 | PE
|  |  |  | Warrick |  | Warrick County | -339679.2083 | PE
|  |  | 1593024 | Floyd |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1593025 | Clark |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1593026 | Decatur |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1593027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593029 | Benton | Brockington and Associates, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1593030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593031 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 1593032 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593033 | Decatur |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1593034 | Dearborn |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1593035 |  | Chastain & Associates LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593036 | Clinton |  | Indiana Department of Transportation | 2018-07-18 | CE
CN
PE
|  |  | 1593037 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1593038 | Harrison |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1593039 |  | Lamac Engineering Company | Indiana Department of Transportation | -339679.2083
|  |  | 1593040 | Brown |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1593041 | Harrison |  | Indiana Department of Transportation | 2018-08-08 | PE
|  |  | 1593042 | Jackson |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1593043 |  | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593046 | Jefferson |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1593047 | Clinton |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1593048 | Jefferson |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1593049 | Franklin |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1593050 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593051 | Decatur |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1593052 | Decatur |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1593053 |  | B. L. A., Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593054 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1593055 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1593056 | St. Joseph |  | St. Joseph County | -339679.2083 | PE
|  |  | 1593057 | Knox | Alliance Environmental Group, Inc. | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1593058 | Posey |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1593059 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1593060 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1593061 | Gibson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
RR
UT
|  |  | 1593062 | Crawford |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1593063 | Gibson |  | Indiana Department of Transportation | 2023-02-15 | RR
|  |  | 1593064 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1593065 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1593066 | Warrick |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1593067 | Warrick |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1593068 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1593069 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1593070 | Washington | Consulting Management Inspection Design, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1593071 | Knox |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1593072 | Various |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1593073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593074 | Jasper |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593075 |  | Duneland Group, Inc. | Indiana Department of Natural Resources | -339679.2083
|  |  | 1593076 |  | Earth Exploration, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593077 | Carroll |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593078 | Carroll |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593079 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1593080 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1593081 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1593082 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1593083 | Vigo |  | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
|  |  | 1593084 | Washington |  | Indiana Department of Transportation | 2021-08-11 | CN
PE
|  |  | 1593085 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1593086 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1593087 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1593088 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593089 | Pike |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1593090 | Various |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1593091 | Knox |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1593092 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1593093 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593094 | Various |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1593095 | Pike |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1593096 | Martin |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1593097 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1593098 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1593099 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1593100 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1593101 | Jasper |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1593102 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593103 | Various |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1593104 | Various |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
PE
RR
|  |  | 1593105 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593106 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593107 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1593108 | Marion |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1593109 | Hamilton | Another Test Company | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 1593110 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1593111 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1593112 | Hamilton | Another Test Company | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1593113 | Hamilton | Another Test Company | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1593114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593118 | Morgan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1593119 | Morgan |  | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1593120 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593122 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1593123 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593124 | Bartholomew |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1593125 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593126 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593127 | Jackson |  | Indiana Department of Transportation | 2023-02-15 | PE
|  |  | 1593128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593129 | Martin |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1593130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593131 | Jackson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1593132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593133 | Greene |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1593134 | Marion |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1593135 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593136 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593137 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593138 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593139 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593140 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593141 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593142 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593143 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593144 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593145 | Ripley |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1593146 | Pike |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593148 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593149 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593150 | Knox | Anelena Ackerly | Indiana Department of Transportation | 2020-01-15 | CE
CN
RR
|  |  |  | Sullivan | Anelena Ackerly | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
RR
|  |  | 1593151 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593152 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593153 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593156 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593157 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593158 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593159 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593160 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593161 | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593162 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593163 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593164 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593165 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593166 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593167 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593168 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593169 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593170 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593171 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593172 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593173 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593174 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1593175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593178 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1593179 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1593180 | Marion |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1593181 | Marion |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1593182 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1593183 | Jackson |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1593184 | Shelby |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1593185 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1593186 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1593187 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1593188 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1593189 | Delaware |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  |  | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
|  |  |  | Randolph |  | Indiana Department of Transportation | 2019-01-16 | CE
|  |  | 1593190 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1593191 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2020-02-05 | PE
RR
|  |  | 1593192 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1593193 | Randolph |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1593194 |  | CGS Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593195 | Randolph |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1593196 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  |  | Madison | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1593197 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
RR
|  |  | 1593198 | Delaware | Heritage Appraisal Service | Indiana Department of Transportation | 2017-03-01 | PE
|  |  |  | Randolph | Heritage Appraisal Service | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1593199 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  |  | Madison | Michael Baker International, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
|  |  | 1593200 | Clark |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1593201 | Hamilton |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1593202 | Henry | American Real Estate Appraisers, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1593203 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
PE
|  |  | 1593204 | Madison |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
RR
|  |  | 1593205 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593206 | Switzerland |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1593207 | Union | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1593208 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593209 | Jasper |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1593210 | Howard |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
RR
|  |  | 1593211 | Wayne |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1593212 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593213 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1593214 | Wayne |  | Indiana Department of Transportation | 2021-05-31 | PE
|  |  | 1593215 | Wayne |  | Indiana Department of Transportation | 2021-05-31 | PE
|  |  | 1593216 | Henry |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1593217 | Jay |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1593218 | Tipton |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1593219 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1593220 | Randolph |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1593221 | Rush |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1593222 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 1593223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593224 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593226 | Henry |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1593227 | Marion |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1593228 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593229 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593230 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2024-07-10 | PE
|  |  | 1593231 | Howard | Collins Engineers Incorporated | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1593232 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1593233 | Henry |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1593234 | Wayne |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
|  |  | 1593235 | Fayette |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1593236 | Hamilton |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1593237 | Hamilton |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1593238 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2022-01-12
|  |  | 1593239 | Wayne |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1593240 | Shelby |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1593241 | Union |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1593242 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593243 | Miami |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593244 | Miami |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1593245 |  | Indiana Connect - a Joint Venture | Indiana Department of Transportation | 2022-10-13
|  |  | 1593246 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1593247 | LaPorte |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1593248 | LaPorte |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1593249 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1593250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593253 | Marshall | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1593254 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1593255 | Marshall |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1593256 | Fulton | InfoTech | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1593257 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1593258 | Jasper |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1593259 | Cass |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1593260 | Starke |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
RR
|  |  | 1593261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593262 | Fulton | InfoTech | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1593263 | Marshall | FPBH, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
RR
|  |  | 1593264 | St. Joseph | Dummy Consulting Firm Too | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1593265 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
RR
|  |  | 1593266 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
RR
|  |  | 1593267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1593269 |  | Context, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1593270 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1593271 | Starke |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1593272 | Montgomery | Madison Milton Ferry LLC | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1593273 | Marshall |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1593274 | Parke |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1593275 | Jasper |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1593276 | Clinton |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1593277 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1593278 | Porter |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1593279 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1593280 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1600001 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600002 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600005 | Carroll |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1600006 |  | Global Management Group, Inc. | Indiana State Agencies | 2017-02-08
|  |  | 1600007 | Carroll |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1600008 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600009 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600011 | Fulton |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1600012 | Lake |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1600013 | Carroll |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1600014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600015 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1600016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600018 | Dearborn |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1600019 | Dearborn |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1600020 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2016-08-10
|  |  | 1600021 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2016-08-10
|  |  | 1600022 | St. Joseph |  | Indiana Department of Transportation | 2017-12-13 | CN
|  |  |  | Various |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1600023 | Various |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1600024 | Various |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1600025 | Morgan |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1600026 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600027 | Cass |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  |  | Various |  | Indiana Department of Transportation | 2019-05-09 | PE
|  |  | 1600028 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1600029 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1600030 | St. Joseph |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1600031 | Jasper |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1600032 | Jasper | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
RR
|  |  | 1600033 | Warrick |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
RR
|  |  | 1600034 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1600035 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600036 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600037 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600038 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600039 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600040 | Hamilton | Another Test Company | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600041 | Hamilton | Another Test Company | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600042 | Posey |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1600043 | Dubois |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600044 | Dubois |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600045 | Vanderburgh |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1600046 | Posey |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600047 | Vanderburgh |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
ROW
|  |  | 1600048 | Posey |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600049 | Vanderburgh |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600050 | Perry |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600051 | Perry |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600052 | Perry |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600053 | Gibson |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600054 | Posey |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600055 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1600056 | Lawrence |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600057 | Perry | Landmark Engineering Group, Inc. | Indiana Department of Transportation | 2019-02-06 | CN
|  |  |  | Spencer | Landmark Engineering Group, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
PE
|  |  | 1600058 | Daviess |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1600059 | Crawford |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1600060 | Vanderburgh | CGI | Indiana Department of Transportation | 2023-11-15 | PE
|  |  | 1600061 | Martin |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600062 | Spencer |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1600063 | Gibson | III FFC | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1600064 | Gibson | III FFC | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1600065 | Sullivan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600066 | Knox |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1600067 | Knox |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1600068 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600069 | Various |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
RR
|  |  | 1600070 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1600071 |  | Collier Transport Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1600072 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1600073 |  | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1600074 | St. Joseph |  | South Bend | 2020-03-04 | CE
CN
PE
ROW
|  |  | 1600075 | St. Joseph |  | South Bend | 2017-10-12 | CE
CN
PE
|  |  | 1600076 | St. Joseph |  | South Bend | 2018-10-11 | CE
CN
PE
|  |  | 1600077 | Grant |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
RR
|  |  | 1600078 | Grant |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1600079 | Marion |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
UT
|  |  | 1600080 | Various |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1600081 | Johnson |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1600082 | Johnson |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1600083 | Morgan |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1600084 | Marion |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600085 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600086 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600087 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600088 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600089 | Marion |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600090 | Marion |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1600091 | Various |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1600092 | Dekalb |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
RR
|  |  | 1600093 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600094 | Dekalb |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1600095 | Noble |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
RR
|  |  | 1600096 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600097 | Vanderburgh |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600098 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600099 | Brown |  | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1600100 | Owen | Absolute Title Services, LLC | Indiana Department of Transportation | 2017-09-13 | CE
CN
PE
|  |  | 1600101 | Jennings |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1600102 | Gibson |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600103 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600105 | Gibson |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600106 | Warrick |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600107 | Orange |  | Indiana Department of Transportation | 2019-10-09 | PE
ROW
|  |  | 1600108 | Warrick |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600109 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1600110 | Orange |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1600111 | Scott |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
PE
RR
|  |  | 1600112 | Posey |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1600113 | Various |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1600114 | Various |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
|  |  | 1600115 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600116 | Kosciusko |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600117 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600118 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1600119 | Whitley |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
RR
|  |  | 1600120 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1600121 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600122 | Orange |  | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1600123 | Knox |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600124 | Sullivan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600125 | Various |  | Indiana Department of Transportation | 2016-10-05 | CE
CN
[6 empty] | Indiana Department of Transportation | 2016-10-05
|  |  | 1600126 | Warrick |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600127 | Warrick |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600128 | Warrick |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600129 | Steuben | Hambleton LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600130 | Warrick |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600134 | Noble | Debbie L. Morris | Indiana Department of Transportation | 2020-07-08 | CE
CN
[5 empty] | Debbie L. Morris | Indiana Department of Transportation | 2020-07-08
|  |  | 1600135 | Crawford |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600136 | Perry |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600138 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600139 | Perry |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600140 | Huntington |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
[6 empty] | Indiana Department of Transportation | 2018-12-12
|  |  | 1600141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600142 | Knox |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600143 | Knox |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600145 | Sullivan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600146 | Huntington | ABNA of Illinois | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
RR
|  |  | 1600147 | Sullivan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600148 | Daviess |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600149 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1600150 | Daviess |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600151 | Knox |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600152 | Knox |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600153 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600155 | Vanderburgh |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600156 | Dubois |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1600157 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1600158 | Crawford |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600159 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600161 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600162 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600163 | Dubois |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1600164 | Knox | Bledsoe Riggert Cooper & James, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1600165 | Daviess | AMEC E&I, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1600166 | Warrick |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1600167 | Dubois |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1600168 | Daviess | CBRE, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1600169 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
RR
|  |  | 1600170 | Perry |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1600171 | Perry |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1600172 | Perry | Andrews Engineering, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1600173 |  | Merle Edward Orem | Indiana Department of Transportation | -339679.2083
|  |  | 1600174 | Spencer |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
|  |  | 1600175 | Dekalb | Cheri K. Lewis Engineers | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600176 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  |  | Warrick | CGI | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1600177 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1600178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600179 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1600180 | Dekalb |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
RR
|  |  | 1600181 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1600182 | Noble |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600183 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1600184 |  | Mader Design, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600185 | Jay |  | Indiana Department of Transportation | 2019-02-06 | PE
|  |  |  | Wells |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600186 | Adams |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1600187 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1600188 |  | Infrastructure Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600189 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600190 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600191 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600192 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600193 | Marshall |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600194 | Allen |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1600195 | Grant | Kruse Consulting, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
RR
|  |  | 1600196 | Grant | Atlas Appraisals, LLC | Indiana Department of Transportation | 2018-10-11 | CE
|  |  |  | Miami | Atlas Appraisals, LLC | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1600197 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
RR
|  |  | 1600198 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600199 | Blackford |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1600200 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600201 | Grant | Level 5 Engineering, LLC | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
RR
|  |  |  | Huntington | Level 5 Engineering, LLC | Indiana Department of Transportation | 2018-10-11 | CE
|  |  | 1600202 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600203 | Vigo |  | Indiana Department of Transportation | 2019-05-31 | CN
PE
|  |  | 1600204 | Hendricks |  | Indiana Department of Transportation | 2020-05-31 | CN
PE
|  |  | 1600205 | Grant | Dave Helton & Associates, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
RR
|  |  | 1600206 | Grant |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1600207 | Kosciusko |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1600208 | Kosciusko | LONCO, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600209 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
RR
|  |  | 1600210 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600211 | Kosciusko | Fink Roberts & Petrie | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1600212 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1600213 | Marion |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1600214 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1600215 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1600216 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1600217 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1600218 | Marion |  | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1600219 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1600220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600221 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600222 | Kosciusko |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600223 | Elkhart |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600224 | Huntington |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600225 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1600226 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1600227 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
ROW
|  |  | 1600228 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1600229 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1600230 | Steuben | ABt SRBI | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1600231 | Dekalb |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1600232 | Dekalb |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1600233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600234 | Steuben | ABt SRBI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1600235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600237 | Huntington |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1600238 | Allen |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1600239 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600240 | Allen |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1600241 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1600242 | Miami |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1600243 | Miami |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600244 | Miami |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1600245 |  | ABt SRBI | Indiana Department of Transportation | 2020-09-02
|  |  | 1600246 | Noble |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1600247 | Miami |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1600248 | Huntington |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1600249 | Elkhart |  | Elkhart County | 2017-05-31 | PE
|  |  | 1600250 |  |  | Indiana Department of Transportation | 2016-04-06
|  |  | 1600251 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600252 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600253 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600254 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600255 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600256 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600257 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600258 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600259 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600260 | Huntington |  | Indiana Department of Transportation | 2020-01-24 | CE
CN
PE
|  |  | 1600261 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600262 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600263 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600264 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600265 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600266 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600267 | Huntington |  | Indiana Department of Transportation | 2020-01-24 | CE
CN
PE
|  |  | 1600268 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600269 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600270 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600271 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600272 | Jay | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 2024-03-13 | PE
|  |  | 1600273 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600274 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600275 | Adams |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1600276 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600277 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600278 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600279 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600280 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600281 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600282 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600283 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600284 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600285 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600286 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600287 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1600288 | Grant |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1600289 | Wells |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1600290 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1600291 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1600292 | Dekalb |  | Indiana Department of Transportation | 2020-01-24 | CE
CN
PE
|  |  | 1600293 | Dekalb |  | Indiana Department of Transportation | 2020-01-24 | CE
CN
|  |  | 1600294 | Miami | Blue Sky Engineering, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1600295 | Morgan |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1600296 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600297 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600298 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
RR
|  |  | 1600299 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1600300 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1600301 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1600302 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1600303 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1600304 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2017-02-15 | CE
CN
|  |  | 1600305 | Various |  | Indiana Department of Transportation | 2016-05-05 | CE
CN
|  |  | 1600306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600308 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1600309 |  | Delcan Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1600310 | Floyd |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600312 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600313 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2016-09-14
|  |  | 1600314 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1600315 | Boone | Martinez Corporation | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1600316 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1600317 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1600318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600319 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600321 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600322 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600323 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600324 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600326 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600327 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1600328 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1600329 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1600330 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1600331 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1600332 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1600333 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1600334 | Marion | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
|  |  | 1600335 | Marion | Dyer Environmental Services | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
|  |  | 1600336 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1600337 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1600338 |  |  | Indiana Department of Transportation | 2015-12-09
|  |  | 1600339 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600340 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1600341 | White |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
RR
|  |  | 1600342 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1600343 | Starke |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1600344 | LaPorte |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1600345 | Carroll | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
RR
|  |  | 1600346 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1600347 | Jasper |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1600348 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1600349 | Starke |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1600350 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600351 | Lake |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1600352 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1600353 | St. Joseph |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1600354 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600355 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1600356 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600357 |  | DCD Consulting LLC | Indiana Department of Transportation | 2015-10-07
|  |  | 1600358 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2017-12-13 | PE
|  |  | 1600359 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1600360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600361 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600362 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600363 | White |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1600364 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600365 | Jasper |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1600366 | Jasper |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1600367 |  |  | Clark County | 2012-10-11
|  |  | 1600368 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
RR
|  |  | 1600369 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1600370 | St. Joseph |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1600371 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1600372 |  | Dennison and Company | Indiana Department of Transportation | -339679.2083
|  |  | 1600373 | Lake | Jacobi, Toombs & Lanz, Inc. | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1600374 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600375 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600376 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600377 |  |  | Boone County | -339679.2083
|  |  | 1600378 | Bartholomew |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1600379 | Cass | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1600380 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600381 | Starke |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1600382 | Starke |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
|  |  | 1600383 | Pulaski |  | Indiana Department of Transportation | 2020-04-01 | PE
ROW
|  |  | 1600384 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600386 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600387 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600388 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600389 | Hendricks |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1600390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600391 | St. Joseph |  | Indiana Department of Transportation | 2020-09-02 | PE
|  |  | 1600392 | St. Joseph |  | Indiana Department of Transportation | 2020-09-02 | PE
|  |  | 1600393 | Hendricks |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1600394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600396 | Hendricks |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1600397 | Hendricks |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1600398 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600399 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600400 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600401 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600402 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600403 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600404 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1600405 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2016-07-13 | CE
CN
|  |  | 1600406 | Lake | Cornerstone Design | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1600407 | Allen | Hardlines Design Company | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1600408 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600409 | Crawford |  | Indiana Department of Transportation | 2017-12-13 | CE
CN
|  |  | 1600410 | Whitley |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1600411 | Allen |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1600412 | Grant |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1600413 | Noble |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1600414 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600415 | Elkhart |  | Indiana Department of Transportation | 2020-08-05 | PE
|  |  | 1600416 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600417 |  |  | Gary | -339679.2083
|  |  | 1600418 | Lake |  | Gary | 2019-04-03 | CE
CN
|  |  | 1600419 | Monroe |  | Monroe County | 2018-08-08 | CN
|  |  | 1600420 | Elkhart |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1600421 | Elkhart |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1600422 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600424 | Martin |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1600425 | Noble | Debbie L. Morris | Indiana Department of Transportation | 2019-12-11 | PE
RR
|  |  | 1600426 | Monroe | Absolute Title Services, LLC | Bloomington | 2017-12-13 | CE
CN
|  |  | 1600427 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600429 | Adams |  | Adams County | 2019-09-11 | CN
|  |  | 1600430 | Adams |  | Adams County | 2019-09-11 | CN
|  |  | 1600431 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600432 | Kosciusko |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600436 |  |  | Indiana Department of Transportation | 2017-08-09
|  |  | 1600437 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1600438 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1600439 | Tippecanoe |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600440 | Vigo |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1600441 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1600442 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600443 | Kosciusko | Jones & Henry Engineers, Ltd. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1600444 | Kosciusko |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1600445 | Rush |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600446 | Rush |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1600447 | Shelby |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600448 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600449 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600450 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600451 | LaPorte |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600452 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600453 | Jasper |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600454 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600455 | Porter |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600456 | Morgan |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1600457 | Scott |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1600458 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1600459 | Jackson |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1600460 | Dearborn |  | Indiana Department of Transportation | 2020-05-31 | RR
|  |  | 1600461 | Sullivan |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1600462 | Sullivan |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1600463 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1600464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600465 | Tipton |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
|  |  | 1600466 | Switzerland |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
UT
|  |  | 1600467 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600468 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600469 | Grant |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600470 | Whitley |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1600471 | Allen |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1600472 | Switzerland |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1600473 | Switzerland |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
ROW
|  |  | 1600474 | Switzerland |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600475 | Ohio |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1600476 | Ohio |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1600477 |  |  | Indiana Department of Transportation | 2016-07-13
|  |  | 1600478 |  |  | Indiana Department of Transportation | 2016-07-13
|  |  | 1600479 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1600480 | Porter |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1600481 | Lake |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1600482 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1600483 | Vigo |  | Vigo County | 2019-03-06 | CE
CN
PE
|  |  | 1600484 | Harrison |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600485 | Harrison |  | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1600486 | Harrison |  | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1600487 | Scott |  | Indiana Department of Transportation | 2021-05-31 | PE
|  |  | 1600488 | Jackson |  | Indiana Department of Transportation | 2021-08-11 | CN
PE
|  |  | 1600489 | Decatur |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1600490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600492 | Franklin |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1600493 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600494 | Ripley |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1600495 | Jefferson |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600496 |  |  | Indiana Department of Transportation | 2016-08-10
|  |  | 1600497 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600498 | LaGrange |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1600499 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1600500 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2022-03-09 | PE
RR
|  |  | 1600501 | Wells |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1600502 | Decatur |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1600503 | Bartholomew |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1600504 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1600505 | Brown |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600506 | Ripley |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1600507 | Carroll |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1600508 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600509 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600510 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600511 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600512 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600513 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600514 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600515 | Whitley |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600516 | Miami |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600517 | Elkhart |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1600518 | Elkhart |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1600519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600520 | Elkhart |  | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1600521 | St. Joseph |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1600522 | Marion |  | Indiana Department of Transportation | 2020-05-28 | CE
CN
PE
|  |  | 1600523 | Marion |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1600524 | Boone |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1600525 |  |  | Indiana Department of Transportation | 2018-12-12
|  |  | 1600530 |  |  | Indiana Department of Transportation | 2016-10-05
|  |  | 1600531 |  |  | Indiana Department of Transportation | 2016-10-05
|  |  | 1600532 |  |  | Indiana Department of Transportation | 2016-10-05
|  |  | 1600533 |  |  | Indiana Department of Transportation | 2016-07-13
|  |  | 1600534 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1600536 |  | Collier Transport Inc. | Decatur | -339679.2083
|  |  | 1600537 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600539 | Dearborn |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1600540 | Hamilton | H. Stewart Kline & Associates, Inc. | Fishers | -339679.2083 | PE
ROW
RR
|  |  | 1600541 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1600542 | Elkhart |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  |  | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1600543 | Porter |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1600544 |  |  | Indiana Department of Transportation | 2016-05-31
|  |  | 1600545 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600546 | Whitley |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600547 | Grant |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1600548 | LaGrange |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600549 | Grant |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
PE
|  |  | 1600550 | Wabash |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600551 | Grant |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600552 | Blackford |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600553 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600554 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600555 | Miami |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600556 | Wabash |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600557 | Wabash |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600558 | Miami |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600559 |  |  | Hamilton County | 2018-02-07
|  |  | 1600560 |  |  | Hamilton County | 2018-02-07
|  |  | 1600561 | Miami |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1600562 | Adams |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600563 | Adams |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600564 | Wells |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600565 | Adams | Bidinfo | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1600566 | Wabash |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600567 | Grant |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600569 | Steuben |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600570 | Hancock | CTLGroup | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1600571 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600572 |  |  | MPO - Evansville | -339679.2083
|  |  | 1600573 |  |  | MPO - Evansville | -339679.2083
|  |  | 1600574 |  |  | MPO - Evansville | -339679.2083
|  |  | 1600575 | Huntington |  | Allen County | 2018-04-11 | CE
CN
|  |  | 1600576 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600577 |  |  | Indiana Department of Transportation | 2016-05-05
|  |  | 1600578 |  |  | Indiana Department of Transportation | 2021-03-01
|  |  | 1600579 |  |  | Indiana Department of Transportation | 2021-03-01
|  |  | 1600580 | Lake |  | Gary | 2017-05-12 | CN
|  |  | 1600581 | Lawrence |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1600582 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1600583 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600584 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600585 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600586 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600587 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600588 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600589 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600590 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600591 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600592 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600593 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600594 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600595 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600596 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600597 | Hamilton |  | Hamilton County | 2019-05-09 | CN
RR
|  |  | 1600598 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600599 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600600 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600601 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600602 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600603 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600604 | Various |  | Indiana Department of Transportation | 2016-05-31 | PL
|  |  | 1600605 | Montgomery |  | Crawfordsville | 2019-07-10 | CE
CN
PE
|  |  | 1600606 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600607 |  |  | Indiana Department of Transportation | 2016-08-10
|  |  | 1600608 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1600609 |  |  | MPO - Indianapolis | 2021-05-31
|  |  | 1600610 |  |  | MPO - Anderson | -339679.2083
|  |  | 1600611 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1600612 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1600613 |  |  | Indiana Department of Transportation | 2016-09-14
|  |  | 1600614 | Switzerland |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1600615 | Ohio |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1600616 | Ohio |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1600617 | Switzerland |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1600618 | Switzerland |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1600619 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1600620 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1600621 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600622 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600623 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2021-10-14 | CN
PE
ROW
|  |  | 1600624 | Jay |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
ROW
|  |  | 1600625 | Shelby |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1600626 | Wayne |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600627 | Marion |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1600628 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600629 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600630 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600631 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600632 |  |  | MPO - Northwest | -339679.2083
|  |  | 1600633 | Hancock |  | Hancock County | 2020-12-09 | CE
CN
ROW
|  |  | 1600634 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600635 |  | Indiana Connect - a Joint Venture | Indiana Department of Transportation | 2016-02-17
|  |  | 1600636 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600637 | Franklin |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1600638 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600639 | Delaware |  | MPO - Muncie | -339679.2083 | PL
|  |  | 1600640 | Hamilton |  | Westfield | 2020-01-15 | CN
|  |  | 1600641 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600642 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  |  | Jackson |  | MPO - Louisville | -339679.2083 | PL
|  |  | 1600643 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1600644 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1600645 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600646 | Miami |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
PE
|  |  | 1600647 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600648 |  | CGI | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1600649 |  |  | MPO - Anderson | -339679.2083
|  |  | 1600650 | Hamilton |  | Hamilton County | 2019-05-09 | CE
CN
|  |  | 1600651 | Hamilton |  | Fishers | 2018-02-07 | CE
CN
|  |  | 1600652 | Delaware |  | Muncie | 2017-04-05 | CE
CN
|  |  | 1600653 |  |  | Hagerstown | -339679.2083
|  |  | 1600654 | Monroe |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1600655 | Johnson | Casteel Real Estate | Franklin | 2019-11-14 | CE
CN
|  |  | 1600656 | Cass |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1600657 | Marion | ASC Group, Inc. | Beech Grove | 2020-09-02 | CE
CN
|  |  | 1600658 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1600659 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1600660 | Various |  | Indiana Department of Transportation | 2016-05-31 | PE
|  |  | 1600661 | Bartholomew |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600662 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600663 | Bartholomew |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
UT
|  |  | 1600664 | Jackson |  | Indiana Department of Transportation | 2024-07-10 | PE
|  |  | 1600665 | Harrison |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1600666 | Brown |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1600667 | Brown |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1600668 | Brown |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1600669 | Jefferson |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1600670 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600671 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600672 | Washington |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600673 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600674 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600675 | Clark |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1600676 | Tipton |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
ROW
|  |  | 1600677 | Various |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1600678 | Noble |  | Noble County | 2022-11-16 | PE
ROW
|  |  | 1600679 | Clark |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1600680 | Washington |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1600681 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1600682 | Hamilton |  | Hamilton County | 2019-11-14 | CE
CN
|  |  | 1600683 | Ripley |  | Indiana Department of Transportation | 2024-12-11 | PE
|  |  | 1600684 | Ripley |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1600685 |  | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600686 | Boone |  | Boone County | 2019-10-09 | CE
CN
|  |  | 1600687 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2021-07-14 | CN
|  |  | 1600688 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600689 |  |  | MPO - Columbus | -339679.2083
|  |  | 1600690 | Dubois |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1600691 | Wabash |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1600692 |  |  | North Vernon | 2019-05-31
|  |  | 1600693 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2023-02-15 | PE
|  |  | 1600694 | Porter |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1600695 | Floyd |  | Indiana Department of Transportation | 2020-02-05 | PE
RR
|  |  | 1600696 | Ripley |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600697 | Noble |  | Noble County | 2021-04-07 | CE
CN
PE
ROW
|  |  | 1600698 |  |  | Noble County | -339679.2083
|  |  | 1600699 | Hancock |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
ROW
|  |  | 1600700 | Porter |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1600701 | Porter |  | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1600702 | Jackson |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
ROW
UT
|  |  | 1600703 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600704 | Washington |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1600705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600706 | Dearborn |  | Aurora | 2022-04-06 | PE
ROW
|  |  | 1600707 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600708 | Adams | Bidinfo | Decatur | 2023-02-15 | PE
|  |  | 1600709 | White | Afram Corporation | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1600710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600711 | Washington |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1600712 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600713 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600714 | Clark |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  |  | Jefferson |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1600715 | Morgan |  | Morgan County | 2021-12-08 | CE
CN
PE
ROW
|  |  | 1600716 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1600717 |  | JCI Bridge Group, Inc. | Salem | -339679.2083
|  |  | 1600718 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 1600719 | Dearborn |  | Dearborn County | 2022-09-14 | ROW
|  |  | 1600720 |  |  | Dearborn County | -339679.2083
|  |  | 1600721 | Decatur |  | Decatur County | 2023-01-19 | PE
|  |  | 1600722 |  |  | Noble County | -339679.2083
|  |  | 1600723 |  |  | Churubusco | -339679.2083
|  |  | 1600724 | Pike |  | Pike County | 2022-05-05 | PE
ROW
|  |  | 1600725 | Pike | Home Equity Appraisals | Petersburg | 2022-03-09 | PE
|  |  | 1600726 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600727 | Knox | Louis Joyner, Architect | Vincennes | 2022-01-12 | PE
ROW
|  |  | 1600728 | Knox |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1600729 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1600730 | Martin |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600731 |  |  | Greenwood | -339679.2083
|  |  | 1600732 | Sullivan |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1600733 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1600734 | Knox |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1600735 | Daviess | CBRE, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
RR
|  |  | 1600736 | Dubois |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
UT
|  |  | 1600737 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600738 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600739 | Warrick |  | Warrick County | 2021-07-14 | CE
CN
PE
ROW
UT
|  |  | 1600740 | Orange |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600741 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1600742 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1600743 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2019-11-14 | CE
CN
|  |  | 1600744 | Clark |  | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1600745 |  | Alfred Benesch & Company | Franklin County | -339679.2083
|  |  | 1600746 |  |  | Clark County | -339679.2083
|  |  | 1600747 |  | Atlas Appraisals, LLC | Converse | -339679.2083
|  |  | 1600748 | Ripley | ARCADIS | Batesville | 2021-10-14 | CE
CN
PE
ROW
RR
|  |  | 1600749 |  | Engineering Resources, Inc. | Madison | -339679.2083
|  |  | 1600750 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1600751 |  | D A Brown Engineering Consultants, Inc. | Huntington | -339679.2083
|  |  | 1600752 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | -339679.2083
|  |  | 1600753 | Grant | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2021-03-10 | CE
CN
PE
|  |  | 1600754 | Grant | ERES International, Inc. | Marion | 2020-04-01 | CE
CN
PE
|  |  | 1600755 |  | EnviroScience, Inc. | Martinsville | -339679.2083
|  |  | 1600756 |  |  | Indiana Department of Transportation | 2016-11-16
|  |  | 1600757 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1600758 | Fountain | Linda F. Russell | Veedersburg | 2020-01-15 | CE
CN
PE
|  |  | 1600759 | Greene | Eagle Ridge Civil Engineering Services, LLC | Linton | 2022-05-31 | PE
ROW
|  |  | 1600760 | Blackford |  | Blackford County | 2019-11-14 | CE
CN
PE
|  |  | 1600761 |  | Debbie L. Morris | Kendallville | -339679.2083
|  |  | 1600762 | Steuben |  | Steuben County | 2022-09-14 | PE
ROW
|  |  | 1600763 | Sullivan | Klug Engineering, Inc. | Sullivan | 2020-09-02 | CE
CN
PE
|  |  | 1600764 | Montgomery |  | Montgomery County | -339679.2083 | PE
|  |  | 1600765 |  |  | Warren County | -339679.2083
|  |  | 1600766 |  |  | Tell City | -339679.2083
|  |  | 1600767 |  |  | Harrison County | -339679.2083
|  |  | 1600768 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | -339679.2083
|  |  | 1600769 | Clinton |  | Clinton County | 2022-02-09 | PE
ROW
|  |  | 1600770 |  |  | Columbia City | -339679.2083
|  |  | 1600771 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 1600772 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2017-02-08 | CN
|  |  | 1600773 | Boone |  | Boone County | 2022-10-13 | PE
ROW
|  |  | 1600774 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1600775 |  |  | Kosciusko County | -339679.2083
|  |  | 1600776 |  | American Engineers, Inc. | Butler | -339679.2083
|  |  | 1600777 | Orange | Hannum, Wagle & Cline Engineering | Orleans | 2020-08-05 | CN
PE
|  |  |  | Various | Hannum, Wagle & Cline Engineering | Orleans | 2020-08-05 | CE
CN
|  |  | 1600778 |  | Craig E. Townsend | Holland | -339679.2083
|  |  | 1600779 |  | JCI Bridge Group, Inc. | Salem | -339679.2083
|  |  | 1600780 |  | Alfred Benesch & Company | Franklin County | -339679.2083
|  |  | 1600781 |  | Cheri K. Lewis Engineers | Garrett | -339679.2083
|  |  | 1600782 | Grant | Chicago Title Insurance Company | Gas City | 2021-05-05 | CE
CN
|  |  | 1600783 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2022-07-13 | RR
|  |  | 1600784 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1600785 | Madison | Duneland Group, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
RR
|  |  | 1600786 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1600787 | Wayne | Appraisal Office of Central Indiana | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1600788 | Kosciusko | McLane Realty, Inc. | Winona Lake | 2022-01-12 | PE
ROW
|  |  | 1600789 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1600790 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | -339679.2083
|  |  | 1600791 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 1600792 | Delaware |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1600793 | Jennings |  | Jennings County | 2022-10-13 | PE
ROW
RR
|  |  | 1600794 |  | Hilton Property Management, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1600795 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600796 | Wayne | Bureau Veritas North America | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1600797 | Jennings |  | Jennings County | 2022-04-06 | PE
ROW
|  |  | 1600798 | Marion |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1600799 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | -339679.2083
|  |  | 1600800 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1600801 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1600802 | Decatur | Collier Transport Inc. | Decatur County | 2023-01-19 | PE
|  |  | 1600803 | Wayne |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1600804 |  | Alfred Benesch & Company | Franklin County | -339679.2083
|  |  | 1600805 | Scott |  | Scott County | 2020-01-15 | CE
CN
PE
|  |  | 1600806 |  | Clayton L. Roots | Greencastle | 2020-05-31
|  |  | 1600807 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600808 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05 | CE
CN
PE
RR
UT
|  |  | 1600818 | Marion |  | Beech Grove | 2019-10-09 | CE
CN
|  |  | 1600819 | Hamilton |  | Noblesville | 2017-11-15 | CE
CN
|  |  | 1600820 |  | Carters Appraisal Service | Frankfort | -339679.2083
|  |  | 1600821 | Parke | Infrastructure Engineers, Inc. | Rockville | 2022-09-14 | PE
|  |  | 1600822 | Jasper | Bettina Settles Realty, LLC | De Motte | 2022-04-06 | PE
ROW
|  |  | 1600823 |  |  | MPO - Indianapolis | 2016-07-28
|  |  | 1600824 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1600825 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600826 |  | Holloway Engineering, LLC | Miami County | -339679.2083
|  |  | 1600827 |  | ABt SRBI | Angola | -339679.2083
|  |  | 1600828 | Jay |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1600829 | Bartholomew |  | Indiana Department of Transportation | 2022-08-10 | PE
|  |  | 1600830 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2021-05-31 | PE
|  |  | 1600831 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1600832 | Putnam |  | Putnam County | 2021-03-10 | CE
CN
PE
|  |  | 1600833 |  |  | Putnam County | -339679.2083
|  |  | 1600834 |  |  | Putnam County | -339679.2083
|  |  | 1600835 |  |  | Putnam County | -339679.2083
|  |  | 1600836 | Scott |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1600837 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600838 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600839 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600840 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600841 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600842 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600843 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600844 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600845 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600846 | Randolph |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1600847 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600848 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600849 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600850 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600851 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600852 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1600853 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600854 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2024-11-15
|  |  | 1600855 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600856 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600857 |  | Another Test Company | Indiana Department of Transportation | 2024-11-15
|  |  | 1600858 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600859 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600860 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600861 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600862 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600863 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600864 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600865 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1600866 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  |  | Shelby | Casteel Real Estate | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1600867 | Warren |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1600868 | Clinton |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1600869 | Hendricks |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1600870 | Parke |  | Indiana Department of Transportation | 2022-01-12 | PE
UT
|  |  | 1600871 |  | DCD Consulting LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1600872 | Boone |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1600873 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
UT
|  |  | 1600874 | Clinton |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1600875 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1600876 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600877 | Boone |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1600878 | Johnson |  | Indiana Department of Transportation | 2021-05-31 | PE
|  |  | 1600879 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600880 | Montgomery |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
RR
|  |  | 1600881 |  | CPS Acquisitions, LLC | Fishers | 2022-02-09
|  |  | 1600882 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1600883 | Fountain |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1600884 |  | Another Test Company | Carmel | 2017-05-31
|  |  | 1600885 | Hamilton |  | Carmel | 2019-08-07 | CE
CN
|  |  | 1600886 | Fountain |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1600887 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600888 | Greene |  | Greene County | -339679.2083 | PE
|  |  | 1600889 | Lawrence |  | Lawrence County | 2022-03-09 | PE
RR
|  |  | 1600890 | Spencer | Infrastructure Engineering, Inc. | Rockport | 2021-02-10 | CE
CN
PE
|  |  | 1600891 | Warrick | Accu-Air Surveys, Inc. | Boonville | 2022-03-09 | PE
ROW
|  |  | 1600892 | Knox |  | Knox County | 2022-05-05 | PE
ROW
RR
|  |  | 1600893 | Spencer |  | Spencer County | 2020-08-05 | CE
CN
PE
|  |  | 1600894 | Fountain |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1600895 | Wayne |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1600896 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1600897 | Fayette |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1600898 | Tipton |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1600899 | Marion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1600900 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1600901 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1600902 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1600903 | Marion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1600904 | Marion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1600905 | Marion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1600906 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1600907 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-07-08 | RR
|  |  | 1600908 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-05-31 | PE
|  |  | 1600909 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1600910 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600911 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600912 | Henry |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1600913 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1600914 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-07-08
|  |  | 1600915 |  | Archonsortium, LLC | Indiana Department of Transportation | 2016-12-14
|  |  | 1600916 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1600917 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1600918 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1600919 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1600920 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1600921 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600922 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600923 | Porter |  | Indiana Department of Transportation | 2020-07-08 | RR
|  |  | 1600924 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 1600925 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1600926 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2022-07-13 | PE
ROW
|  |  | 1600927 | White | Fugro Roadware, Inc. | White County | 2021-08-11 | CE
CN
PE
ROW
|  |  | 1600928 | Cass |  | Cass County | 2021-12-08 | PE
ROW
|  |  | 1600929 |  | Edwards and Kelcey | Lake County | -339679.2083
|  |  | 1600930 | Lake |  | Lake County | 2020-10-07 | CE
CN
PE
ROW
|  |  | 1600931 | Marshall |  | Marshall County | 2021-12-08 | CE
CN
PE
ROW
|  |  | 1600932 |  | Archaeological Consultants of the Midwest, Inc. | Lake County | -339679.2083
|  |  | 1600933 |  | Edwards and Kelcey | Lowell | -339679.2083
|  |  | 1600934 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1600935 | Jay |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1600936 | Starke | H.R. Gray | North Judson | 2019-11-14 | CE
CN
PE
|  |  | 1600937 | Fountain |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1600938 | White | Fugro Roadware, Inc. | Monticello | 2021-05-05 | CN
PE
|  |  | 1600939 | Warren |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1600940 |  |  | Starke County | 2022-03-09
|  |  | 1600941 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 1600942 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600943 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1600944 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1600945 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1600946 | Jay | Hydrogeology, Inc. | Portland | -339679.2083 | PE
|  |  | 1600947 |  |  | Hancock County | -339679.2083
|  |  | 1600948 |  |  | Westfield | -339679.2083
|  |  | 1600949 | Hancock |  | Hancock County | 2021-12-08 | CE
CN
|  |  | 1600950 | Wayne |  | Wayne County | 2020-12-09 | CE
CN
PE
ROW
|  |  | 1600951 |  |  | Westfield | -339679.2083
|  |  | 1600952 |  |  | Hancock County | -339679.2083
|  |  | 1600953 |  |  | Henry County | -339679.2083
|  |  | 1600954 |  | Boomerang Ventures, LLC | Dunkirk | -339679.2083
|  |  | 1600955 |  |  | Westfield | -339679.2083
|  |  | 1600956 |  |  | Hamilton County | -339679.2083
|  |  | 1600957 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 1600958 | Henry |  | Henry County | 2021-09-15 | CE
CN
PE
|  |  | 1600959 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 1600960 |  | Cambridge Systematics, Inc. | Wayne County | -339679.2083
|  |  | 1600961 | Rush | J. Williams Appraisal Group, LLC | Rushville | 2022-02-09 | PE
|  |  | 1600962 |  |  | Wayne County | -339679.2083
|  |  | 1600963 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1600964 |  | Jeffrey S. Juday | Shelbyville | -339679.2083
|  |  | 1600965 | Jay | Hydrogeology, Inc. | Portland | 2022-05-05 | PE
ROW
|  |  | 1600966 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 1600967 |  |  | Jay County | -339679.2083
|  |  | 1600968 | Rush |  | Rush County | 2021-12-08 | CE
CN
PE
ROW
|  |  | 1600969 |  |  | Jay County | -339679.2083
|  |  | 1600970 |  |  | Jay County | -339679.2083
|  |  | 1600971 | Tipton | McCullouch Consulting, LLC | Windfall | 2022-04-06 | PE
|  |  | 1600972 | Jay | IXOYE, Limited | Redkey | 2022-01-12 | PE
|  |  | 1600973 |  |  | Jay County | -339679.2083
|  |  | 1600974 | Jay | Boomerang Ventures, LLC | Dunkirk | 2022-04-06 | PE
|  |  | 1600975 |  |  | Tipton County | -339679.2083
|  |  | 1600976 | Henry | GeoSolutions, Inc. | New Castle | 2020-12-09 | CE
CN
PE
|  |  | 1600977 | Dekalb |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1600978 | Elkhart | Finley Engineering Group, Inc. | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1600979 | Warren |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1600980 | Clay |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1600981 | Vermillion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600982 | Vermillion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600983 | Vermillion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600984 | Vermillion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1600985 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600986 | Marion | DCD Consulting LLC | Indianapolis | 2019-11-14 | CE
CN
|  |  | 1600987 | Marion | DCD Consulting LLC | Indianapolis | 2020-03-04 | CE
CN
|  |  | 1600988 | Marion |  | Indianapolis | 2019-11-14 | CE
CN
|  |  | 1600989 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600990 | Marion |  | Indianapolis | 2019-11-14 | CE
CN
|  |  | 1600991 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600992 | Marion | DCD Consulting LLC | Indianapolis | 2020-10-07 | CE
CN
|  |  | 1600993 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600994 | Marion | DCD Consulting LLC | Indianapolis | 2020-11-10 | CE
CN
|  |  | 1600995 | Marion |  | Indianapolis | 2020-07-08 | CE
CN
|  |  | 1600996 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1600997 | Marion |  | Indianapolis | 2020-07-08 | CN
|  |  | 1600998 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
RR
|  |  | 1600999 | Marion |  | Indianapolis | 2019-07-10 | CE
CN
|  |  | 1601000 | Tippecanoe |  | Lafayette | 2018-05-31 | PE
|  |  | 1601001 | Marion | DCD Consulting LLC | Indianapolis | 2020-11-10 | CE
CN
|  |  | 1601002 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 1601003 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1601004 | Miami | Blue Sky Engineering, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1601005 | Hancock | Environmental Monitoring and Technologies, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
RR
|  |  | 1601006 |  | A & Z Engineering, LLC | Indiana Department of Transportation | 2023-12-13
|  |  | 1601007 | Kosciusko | CET, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1601008 | Kosciusko | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1601009 | Vanderburgh | CGI | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1601010 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1601011 | Vanderburgh | CGI | Indiana Department of Transportation | 2025-11-13 | PE
ROW
RR
|  |  | 1601012 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1601013 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1601014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601015 | Huntington |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1601016 | Adams |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1601017 | Scott | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1601018 | Dekalb |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1601019 | Clay |  | Indiana Department of Transportation | 2021-04-07 | CE
|  |  |  | Owen |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1601020 | Wells | Linebach Funkhouser, Inc. | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1601021 | Fountain |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1601022 | Dekalb | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Indiana Department of Transportation | 2020-08-05 | PE
|  |  | 1601023 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1601024 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1601025 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601026 |  |  | Evansville | -339679.2083
|  |  | 1601027 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1601028 | Tippecanoe |  | Tippecanoe County | 2022-11-16 | PE
ROW
|  |  | 1601029 | Carroll |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1601030 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 1601031 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1601032 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601033 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601034 | Perry |  | Indiana Department of Transportation | 2026-07-08 | PE
|  |  | 1601035 | Perry |  | Indiana Department of Transportation | 2026-07-08 | PE
|  |  | 1601036 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
UT
|  |  | 1601037 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601038 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
UT
|  |  | 1601039 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601040 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
UT
|  |  | 1601041 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601042 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601043 | Crawford |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601044 | Greene |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1601045 | Hendricks |  | Brownsburg | 2019-10-09 | CE
CN
|  |  | 1601046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601047 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1601048 |  |  | Brownsburg | -339679.2083
|  |  | 1601049 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1601050 | Martin | EcoTec, Inc. | Indiana Department of Transportation | 2024-01-18 | PE
|  |  | 1601051 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2021-08-11 | CN
PE
|  |  | 1601052 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1601053 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | 2022-03-09
|  |  | 1601054 |  | JJR, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1601055 |  | CMF Engineering, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1601056 | Hendricks |  | Brownsburg | 2020-11-10 | CE
CN
|  |  | 1601057 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1601058 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601059 |  | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1601060 | Gibson | III FFC | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601061 | Hendricks |  | Brownsburg | 2019-12-11 | CE
CN
|  |  | 1601062 | Posey | Beacon Surveying and Engineering | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1601063 | Crawford | Engineering Technologies, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1601064 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1601065 | Dubois |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
RR
|  |  | 1601066 |  | CGI | Indiana Department of Transportation | 2023-01-19
|  |  | 1601067 | Newton |  | Indiana Department of Transportation | 2018-05-18 | CE
CN
PE
RR
|  |  | 1601068 | Pulaski |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1601069 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1601070 | Fulton |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1601071 | Jackson |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1601072 | Hendricks | AFRAM Group, Incorporated | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  |  | Marion | AFRAM Group, Incorporated | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1601073 | Tippecanoe | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
UT
|  |  | 1601074 |  | GRW Engineers, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1601075 |  | Franklin Property Matters, LLC. | Indiana Department of Transportation | 2022-11-16
|  |  | 1601076 | Vigo | Indiana Infrastructure Partners, LLC | Indiana Department of Transportation | 2020-05-07 | CE
CN
RR
|  |  | 1601077 | Boone |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1601078 | Fountain |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1601079 | Warren |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1601080 | Montgomery |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1601081 | Owen |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1601082 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
RR
UT
|  |  | 1601083 | Benton |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1601084 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601085 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601086 | Huntington |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1601087 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601088 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1601089 | LaPorte |  | Indiana Department of Transportation | 2024-07-10 | PE
|  |  | 1601090 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601091 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1601092 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1601093 | Hendricks |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1601094 | Putnam |  | Indiana Department of Transportation | 2026-07-08 | PE
|  |  | 1601095 | Fountain |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1601096 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601097 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601098 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601099 |  |  | Indiana Department of Transportation | 2016-09-14
|  |  | 1601100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601101 | Dekalb | KZF Design, Inc. | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1601102 | Steuben | Certified Engineering, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1601103 | Whitley |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1601104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601105 | Warren | Chastain & Associates LLC | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1601106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601108 | Hendricks | Indiana University | Indiana Department of Transportation | 2021-03-10 | CE
|  |  |  | Putnam | Indiana University | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1601109 |  | CDM Smith, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601110 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1601111 | Jackson |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1601112 |  |  | MPO - Muncie | -339679.2083
|  |  | 1601113 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2022-11-16
|  |  | 1601114 | Floyd |  | New Albany | 2017-03-01 | CN
|  |  | 1601115 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1601116 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1601117 | Lake |  | Indiana Department of Transportation | 2016-11-21 | CE
CN
|  |  | 1601118 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601119 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601120 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601121 | Hendricks |  | Avon | 2019-01-16 | CE
CN
|  |  | 1601122 | Porter |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1601123 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1601124 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601125 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2017-02-08
|  |  | 1601126 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2017-02-08
|  |  | 1601127 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601128 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601129 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601130 | Monroe |  | MPO - Bloomington | -339679.2083 | PL
|  |  | 1601131 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1601132 | Marion |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1601133 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601134 | Various |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
PE
|  |  | 1601135 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601136 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601137 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1601138 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1601139 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1601140 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1601141 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601142 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1601143 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1601144 | Floyd |  | Floyd County | 2018-02-07 | CN
RR
|  |  | 1601145 |  | Consolidated Test Company | Hammond | 2022-07-13
|  |  | 1601146 | Lake | Browning Day Mullins Dierdorf Architects | East Chicago | 2022-07-13 | PE
|  |  | 1601147 |  | American Commercial Title & Escrow | Burns Harbor | 2022-04-06
|  |  | 1601148 | Lake | Gibson County Abstract & Title Co., Inc. | New Chicago | -339679.2083 | PE
|  |  | 1601149 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | -339679.2083 | PE
|  |  | 1601150 | LaPorte |  | La Porte | -339679.2083 | PE
|  |  | 1601151 | Lake | Baxter & Woodman, Inc. | Crown Point | -339679.2083 | PE
|  |  | 1601152 |  |  | Portage | -339679.2083
|  |  | 1601153 |  |  | Floyd County | -339679.2083
|  |  | 1601154 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1601155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601156 |  |  | Lake County | -339679.2083
|  |  | 1601157 | Lake | Baxter & Woodman, Inc. | Crown Point | 2020-03-04 | CE
CN
PE
ROW
|  |  | 1601158 | Lake | Baxter & Woodman, Inc. | Crown Point | 2021-03-10 | CE
CN
PE
|  |  | 1601159 | Porter | Leitner and Associates, Inc. | Valparaiso | 2019-04-03 | CE
CN
PE
|  |  | 1601160 | Porter | Leitner and Associates, Inc. | Valparaiso | -339679.2083 | PE
|  |  | 1601161 | Porter | Domain Architecture, Inc. | Kouts | 2018-07-11 | CE
CN
PE
|  |  | 1601162 | Porter | Domain Architecture, Inc. | Kouts | 2019-01-16 | CN
PE
|  |  | 1601163 | Lake | Consolidated Test Company | Hammond | 2020-08-05 | CE
CN
PE
ROW
|  |  | 1601164 | Lake | Consolidated Test Company | Hammond | 2018-01-18 | CE
CN
PE
|  |  | 1601165 |  |  | Gary | -339679.2083
|  |  | 1601166 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1601167 | Tippecanoe |  | Tippecanoe County | -339679.2083 | PL
|  |  | 1601168 | Howard |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1601169 | Vigo |  | Vigo County | -339679.2083 | PL
|  |  | 1601170 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601172 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601173 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601176 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601177 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Natural Resources | 2020-04-01
|  |  | 1601178 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Natural Resources | 2021-04-07 | RR
|  |  | 1601179 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601180 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601181 | Various |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1601182 | Floyd |  | Floyd County | 2018-02-07 | CN
RR
|  |  | 1601183 | Various |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
PE
RR
|  |  | 1601184 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601185 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601186 |  |  | Indiana Department of Transportation | 2017-05-10
|  |  | 1601187 |  |  | Indiana Department of Transportation | 2017-04-12
|  |  | 1601188 |  |  | Indiana Department of Transportation | 2017-04-12
|  |  | 1601189 | Tippecanoe |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1601190 |  |  | Indiana Department of Transportation | 2017-08-09
|  |  | 1601191 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2016-08-31 | CE
CN
|  |  |  | Jackson | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2016-08-31 | CE
|  |  | 1601192 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2017-02-08
|  |  | 1601193 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601194 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601195 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601196 | Johnson |  | Johnson County | -339679.2083 | RR
|  |  | 1601197 | Johnson |  | Johnson County | 2021-07-14 | CE
CN
|  |  | 1601198 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1601199 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1601200 |  | Finley Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601201 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2017-03-01
|  |  | 1601202 |  |  | Indiana Department of Transportation | 2017-04-05
|  |  | 1601203 |  |  | Indiana Department of Transportation | 2017-04-05
|  |  | 1601204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601205 | Harrison |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  |  | Various |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1601206 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1601207 | Various |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1601208 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1601209 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1601210 | Floyd |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1601211 |  |  | Lake County | -339679.2083
|  |  | 1601212 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601213 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601214 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2017-02-08 | CE
CN
|  |  | 1601215 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1601216 | Allen |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1601217 | Allen |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
PE
|  |  | 1601218 | Owen |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1601219 | Knox |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
|  |  | 1601220 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1601221 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1601222 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1601223 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1601224 |  | DCD Consulting LLC | Marion | -339679.2083
|  |  | 1601225 | Clark |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601226 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1601227 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1601228 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1601229 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1601230 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1601231 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601232 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601233 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1601234 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2016-11-16 | CE
CN
|  |  | 1601235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601236 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601237 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601238 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601239 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601240 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601241 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601242 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1601243 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601244 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601245 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601246 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601247 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601248 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601249 | Hamilton |  | Hamilton County | 2019-05-09 | CE
CN
|  |  | 1601250 |  |  | Bloomington | -339679.2083
|  |  | 1601251 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601252 |  | DCD Consulting LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1601253 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601254 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601255 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601256 | Tippecanoe |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
|  |  | 1601257 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2017-05-31
|  |  | 1601258 |  | ARCADIS | Batesville | 2017-05-31
|  |  | 1601259 |  | Feutz Contractors, Inc. | Middletown | 2017-05-31
|  |  | 1601260 |  | Alfred Benesch & Company | Brookville | 2017-05-31
|  |  | 1601261 |  |  | Rush County | 2017-05-31
|  |  | 1601262 |  |  | Randolph County | 2017-05-31
|  |  | 1601263 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2017-05-31
|  |  | 1601264 |  |  | Brown County | 2017-05-31
|  |  | 1601265 |  | Fidelity National Title Insurance Company, Inc. | Milan | 2017-05-31
|  |  | 1601266 |  |  | Shelby County | 2017-05-31
|  |  | 1601267 |  |  | Henry County | 2017-05-31
|  |  | 1601268 |  | Hydrogeology, Inc. | Portland | 2017-05-31
|  |  | 1601269 |  |  | Jennings County | 2017-05-31
|  |  | 1601270 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2017-05-31
|  |  | 1601271 |  | David Matthews Associates (Former) | Kempton | 2017-05-31
|  |  | 1601272 |  |  | Tipton County | 2017-05-31
|  |  | 1601273 |  | 2IM Group, LLC | Akron | 2017-05-31
|  |  | 1601274 |  | Wilcox Environmental Engineering, Inc. | Connersville | 2017-05-31
|  |  | 1601275 |  | JCI Bridge Group, Inc. | Salem | 2017-05-31
|  |  | 1601276 |  |  | Charlestown | 2017-05-31
|  |  | 1601277 |  |  | Washington County | 2017-05-31
|  |  | 1601278 |  | Collier Transport Inc. | Greensburg | 2017-05-31
|  |  | 1601279 |  |  | Fayette County | 2017-05-31
|  |  | 1601280 |  | Indiana Search Technologies | Rising Sun | 2017-05-31
|  |  | 1601281 |  | Construction Consultants & Inspection Services, LLC | Hanover | 2017-05-31
|  |  | 1601282 |  |  | North Vernon | 2017-05-31
|  |  | 1601283 |  | Land Construction Corp | Tipton | 2017-05-31
|  |  | 1601284 |  |  | Harrison County | 2017-05-31
|  |  | 1601285 |  | Apex Consulting & Surveying, Inc. | Winchester | 2017-05-31
|  |  | 1601286 |  | Apex Consulting & Surveying, Inc. | Winchester | 2017-05-31
|  |  | 1601287 |  | Boomerang Ventures, LLC | Dunkirk | 2017-05-31
|  |  | 1601288 |  | Active Environmental Services, Inc. | Bourbon | -339679.2083
|  |  | 1601289 |  | Civil Designs, LLP | Glenwood | 2017-05-31
|  |  | 1601290 |  | Advanced Engineering Consultants, Ltd. | Bremen | -339679.2083
|  |  | 1601291 |  |  | Jackson County | 2017-05-31
|  |  | 1601292 |  |  | Clarksville | 2017-05-31
|  |  | 1601293 |  | Casteel Real Estate | Franklin | 2017-05-31
|  |  | 1601294 |  |  | Jackson County | 2017-05-31
|  |  | 1601295 |  |  | Decatur County | 2017-05-31
|  |  | 1601296 |  | Quantum Spatial, Inc. | Auburn | 2017-05-31
|  |  | 1601297 |  |  | Scott County | 2017-05-31
|  |  | 1601298 |  | AES Services, Inc. | Avilla | 2017-05-31
|  |  | 1601299 |  |  | Morgantown | 2017-05-31
|  |  | 1601300 |  | American Engineers, Inc. | Butler | 2017-05-31
|  |  | 1601301 |  |  | Trafalgar | 2017-05-31
|  |  | 1601302 |  |  | Jefferson County | 2017-05-31
|  |  | 1601303 |  |  | Aurora | 2017-05-31
|  |  | 1601304 |  |  | Jefferson County | 2017-05-31
|  |  | 1601305 |  | Cheri K. Lewis Engineers | Garrett | 2017-05-31
|  |  | 1601306 |  | Mader Design, LLC | Waterloo | 2017-05-31
|  |  | 1601307 |  | Clyde L. Hawkins | Greendale | 2017-05-31
|  |  | 1601308 |  | Mader Design, LLC | Waterloo | 2017-05-31
|  |  | 1601309 |  | Bartlett & Associates, Inc. | Cromwell | 2017-05-31
|  |  | 1601310 |  | American Structurepoint, Inc. | Camden | -339679.2083
|  |  | 1601311 |  | Debbie L. Morris | Kendallville | 2017-05-31
|  |  | 1601312 |  |  | Carroll County | 2017-05-31
|  |  | 1601313 |  | Debbie L. Morris | Kendallville | 2017-05-31
|  |  | 1601314 |  | InspectTech Systems, Inc. | Rome City | 2017-05-31
|  |  | 1601315 |  |  | Scottsburg | 2017-05-31
|  |  | 1601316 |  |  | Cass County | -339679.2083
|  |  | 1601317 |  | Garcia LE & Associates, L.L.C. | Nashville | 2017-05-31
|  |  | 1601318 |  |  | Noble County | 2017-05-31
|  |  | 1601319 |  | Civil & Environmental Consultants, Inc. | Georgetown | 2017-05-31
|  |  | 1601320 |  |  | Noble County | 2017-05-31
|  |  | 1601321 |  |  | Noble County | 2017-05-31
|  |  | 1601322 |  | Data Transfer Solutions, LLC | Jeffersonville | 2017-05-31
|  |  | 1601323 |  |  | Cass County | -339679.2083
|  |  | 1601324 |  |  | Union County | 2017-05-31
|  |  | 1601325 |  | IXOYE, Limited | Redkey | 2017-05-31
|  |  | 1601326 |  | J. Williams Appraisal Group, LLC | Rushville | 2017-05-31
|  |  | 1601327 |  | Jean Stewart, LLC | Sharpsville | 2017-05-31
|  |  | 1601328 |  | Jeffrey S. Juday | Shelbyville | 2017-05-31
|  |  | 1601329 |  | Associated Right-of-Way Services, Inc. | Columbus | 2017-05-31
|  |  | 1601330 |  | Absolute Title Services, LLC | Bloomington | 2017-05-31
|  |  | 1601331 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2017-05-31
|  |  | 1601332 |  |  | Dearborn County | 2017-05-31
|  |  | 1601333 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2017-05-31
|  |  | 1601334 |  |  | Clark County | 2017-05-31
|  |  | 1601335 |  |  | Cass County | -339679.2083
|  |  | 1601336 |  |  | Adams County | 2017-05-31
|  |  | 1601337 |  |  | Adams County | 2017-05-31
|  |  | 1601338 |  | Continental Mapping Consultants, LLC | Hartford City | 2017-05-31
|  |  | 1601339 |  | Fusion by Design, Inc. | Montpelier | 2017-05-31
|  |  | 1601340 |  | Jeffrey S. Juday | Shelbyville | 2017-05-31
|  |  | 1601341 |  | Jeffrey S. Juday | Shelbyville | 2017-05-31
|  |  | 1601342 |  | HLRD | North Salem | -339679.2083
|  |  | 1601343 |  | Horn and Associates, Inc. | Pittsboro | -339679.2083
|  |  | 1601344 |  |  | Dublin | 2017-05-31
|  |  | 1601345 |  |  | Tippecanoe County | -339679.2083
|  |  | 1601346 |  | GAI Consultants, Inc. | Mooresville | 2017-05-31
|  |  | 1601347 |  | ABNA of Illinois | Andrews | 2017-05-31
|  |  | 1601348 |  | DuSABLE, Inc. | Lafayette | -339679.2083
|  |  | 1601349 |  |  | Clarks Hill | -339679.2083
|  |  | 1601350 |  |  | Ellettsville | 2017-05-31
|  |  | 1601351 |  | MHM Associates, Inc. | Warren County | -339679.2083
|  |  | 1601352 |  | McAlister Excavating Co., Inc. | Williams Creek | 2017-05-31
|  |  | 1601353 |  | Commonwealth Engineers, Inc. | Greenwood | 2017-05-31
|  |  | 1601354 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2017-05-31
|  |  | 1601355 |  | Hey and Associates, Inc. | Pendleton | 2017-05-31
|  |  | 1601356 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2017-05-31
|  |  | 1601357 |  | IHS Global Insight | Princes Lakes | 2017-05-31
|  |  | 1601358 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2017-05-31
|  |  | 1601359 |  | Dynasty Group, Inc. | Lawrenceburg | 2017-05-31
|  |  | 1601360 |  |  | Hamilton County | 2017-05-31
|  |  | 1601361 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2017-05-31
|  |  | 1601362 |  |  | Johnson County | 2017-05-31
|  |  | 1601363 |  |  | Hamilton County | 2017-05-31
|  |  | 1601364 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2017-05-31
|  |  | 1601365 |  | ASA Engineering Consultants, Inc. | Battle Ground | -339679.2083
|  |  | 1601366 |  | Facility Management and Engineering, Inc. | Meridian Hills | -339679.2083
|  |  | 1601367 |  |  | Floyd County | 2017-05-31
|  |  | 1601368 |  | DLZ Indiana, LLC | Jamestown | -339679.2083
|  |  | 1601369 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 1601370 |  | ACME | Arcadia | 2017-05-31
|  |  | 1601371 |  |  | Floyd County | 2017-05-31
|  |  | 1601372 |  | Burrell Appraisal Service, Inc. | Edinburgh | 2017-05-31
|  |  | 1601373 |  |  | Huntington County | 2017-05-31
|  |  | 1601374 |  |  | New Albany | 2017-05-31
|  |  | 1601375 |  |  | Huntington County | 2017-05-31
|  |  | 1601376 |  |  | Huntington County | 2017-05-31
|  |  | 1601377 |  | MainLine Management, Inc. | Waynetown | -339679.2083
|  |  | 1601378 |  | ASA Land Surveying | Bedford | 2017-05-31
|  |  | 1601379 |  | DKA Associates, Inc. | Ingalls | 2017-05-31
|  |  | 1601380 |  |  | Hagerstown | 2017-05-31
|  |  | 1601381 | Lake |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1601382 |  | ASA Land Surveying | Bedford | 2017-05-31
|  |  | 1601383 |  | AV Consulting Engineers, Inc. | Bicknell | 2017-05-31
|  |  | 1601384 |  |  | Bartholomew County | 2017-05-31
|  |  | 1601385 |  | Accu-Air Surveys, Inc. | Boonville | 2017-05-31
|  |  | 1601386 |  |  | Bartholomew County | 2017-05-31
|  |  | 1601387 |  | Americas Engineers, Inc. | Cannelburg | 2017-05-31
|  |  | 1601388 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1601389 |  | Andrews Engineering, Inc. | Cannelton | 2017-05-31
|  |  | 1601390 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1601391 |  |  | Morgan County | 2017-05-31
|  |  | 1601392 |  | CGI | Evansville | 2017-05-31
|  |  | 1601393 |  |  | Huntingburg | 2017-05-31
|  |  | 1601394 |  |  | Monroe County | 2017-05-31
|  |  | 1601395 |  | Dan Moore Real Estate Services, Inc. | Jasonville | 2017-05-31
|  |  | 1601396 |  | Danch Harner and Associates, Inc. | Jasper | 2017-05-31
|  |  | 1601397 |  |  | LaGrange County | 2017-05-31
|  |  | 1601398 |  |  | Monroe County | 2017-05-31
|  |  | 1601399 |  |  | LaGrange County | 2017-05-31
|  |  | 1601400 |  |  | Greendale | 2017-05-31
|  |  | 1601401 |  |  | LaGrange County | 2017-05-31
|  |  | 1601402 |  |  | Monroe County | 2017-05-31
|  |  | 1601403 |  | EcoTec, Inc. | Loogootee | 2017-05-31
|  |  | 1601404 |  |  | Franklin County | 2017-05-31
|  |  | 1601405 |  | Eagle Ridge Civil Engineering Services, LLC | Linton | 2017-05-31
|  |  | 1601406 |  | GRL Engineers, Inc. | Mount Vernon | 2017-05-31
|  |  | 1601407 |  |  | Franklin County | 2017-05-31
|  |  | 1601408 |  | Home Equity Appraisals | Petersburg | 2017-05-31
|  |  | 1601409 |  | Appraisal Service | Chalmers | -339679.2083
|  |  | 1601410 |  | III FFC | Princeton | 2017-05-31
|  |  | 1601411 |  | Infrastructure Engineering, Inc. | Rockport | 2017-05-31
|  |  | 1601412 |  | Klug Engineering, Inc. | Sullivan | 2017-05-31
|  |  | 1601413 |  |  | LaGrange County | 2017-05-31
|  |  | 1601414 |  | Bayer & Becker, Inc. | Culver | -339679.2083
|  |  | 1601415 |  |  | Tell City | 2017-05-31
|  |  | 1601416 |  |  | New Whiteland | 2017-05-31
|  |  | 1601417 |  |  | LaGrange County | 2017-05-31
|  |  | 1601418 |  | Louis Joyner, Architect | Vincennes | 2017-05-31
|  |  | 1601419 |  | Martin Riley, Inc. | Whiteland | 2017-05-31
|  |  | 1601420 |  | AMEC E&I, Inc. | Washington | 2017-05-31
|  |  | 1601421 |  |  | Crawford County | 2017-05-31
|  |  | 1601422 |  | Indiana Search Technologies | Rising Sun | 2017-05-31
|  |  | 1601423 |  | Blood Hound, Inc. (former) | Delphi | -339679.2083
|  |  | 1601424 |  | Merle Edward Orem | Wolcottville | 2017-05-31
|  |  | 1601425 |  | Alt & Witzig Engineering, Inc. | Bunker Hill | -339679.2083
|  |  | 1601426 |  | Atlas Appraisals, LLC | Converse | 2017-05-31
|  |  | 1601427 |  |  | Miami County | 2017-05-31
|  |  | 1601428 |  |  | Miami County | 2017-05-31
|  |  | 1601429 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601430 |  | ABt SRBI | Angola | 2017-05-31
|  |  | 1601431 |  | ABt SRBI | Angola | 2017-05-31
|  |  | 1601432 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2017-05-31
|  |  | 1601433 |  | Hambleton LLC | Orland | 2017-05-31
|  |  | 1601434 |  |  | Steuben County | 2017-05-31
|  |  | 1601435 |  |  | Steuben County | 2017-05-31
|  |  | 1601436 |  |  | Steuben County | 2017-05-31
|  |  | 1601437 |  |  | Steuben County | 2017-05-31
|  |  | 1601438 |  |  | Steuben County | 2017-05-31
|  |  | 1601439 |  |  | Steuben County | 2017-05-31
|  |  | 1601440 |  |  | Steuben County | 2017-05-31
|  |  | 1601441 |  | Dorochoff Consulting, LLC | La Fontaine | 2017-05-31
|  |  | 1601442 |  | Dorochoff Consulting, LLC | La Fontaine | 2017-05-31
|  |  | 1601443 |  | Duke Energy Corporation | Lagro | 2017-05-31
|  |  | 1601444 | Warrick |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1601445 |  | HE-BFS, LLC | North Manchester | 2017-05-31
|  |  | 1601446 |  | HE-BFS, LLC | North Manchester | 2017-05-31
|  |  | 1601447 |  | M-E Companies, Inc. | Wabash | 2017-05-31
|  |  | 1601448 |  | Accidental Discoveries, LLC | Bluffton | 2017-05-31
|  |  | 1601449 |  | Martinez Corporation | Whitestown | -339679.2083
|  |  | 1601450 |  | Hardlines Design Company | Ossian | 2017-05-31
|  |  | 1601451 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1601452 |  | Archonsortium, LLC | Cloverdale | -339679.2083
|  |  | 1601453 |  | Enginuity Management & Consulting Corporation | Markle | 2017-05-31
|  |  | 1601454 |  | Enginuity Management & Consulting Corporation | Markle | 2017-05-31
|  |  | 1601455 |  | Frost Engineering & Consulting Company | Montgomery County | -339679.2083
|  |  | 1601456 |  |  | Wells County | 2017-05-31
|  |  | 1601457 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 1601458 |  |  | Boone County | -339679.2083
|  |  | 1601459 |  |  | Wells County | 2017-05-31
|  |  | 1601460 |  |  | Parke County | -339679.2083
|  |  | 1601461 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | -339679.2083
|  |  | 1601462 |  |  | Wells County | 2017-05-31
|  |  | 1601463 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1601464 |  |  | Vermillion County | -339679.2083
|  |  | 1601465 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 1601466 |  | Manhard Consulting, Ltd. | West Lafayette | -339679.2083
|  |  | 1601467 |  | McCord, Inc. | Williamsport | -339679.2083
|  |  | 1601468 |  | AECON, Inc. | Attica | -339679.2083
|  |  | 1601469 |  | Ark Engineering Services, Inc. | Coatesville | -339679.2083
|  |  | 1601470 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 1601471 |  |  | Allen County | 2017-05-31
|  |  | 1601472 |  | Bella Villa Realtors, LLC | Danville | -339679.2083
|  |  | 1601473 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2017-05-31
|  |  | 1601474 |  | D & D Consulting Services, Inc. | Huntertown | 2017-05-31
|  |  | 1601475 |  |  | Leo-Cedarville | 2017-05-31
|  |  | 1601476 |  | Global Management Group, Inc. | New Haven | 2017-05-31
|  |  | 1601477 |  | Carters Appraisal Service | Frankfort | -339679.2083
|  |  | 1601478 |  | Global Management Group, Inc. | New Haven | 2017-05-31
|  |  | 1601479 |  | Bella Villa Realtors, LLC | Hendricks County | -339679.2083
|  |  | 1601480 |  | Frontline Construction Inspection, Inc. | Montezuma | -339679.2083
|  |  | 1601481 |  |  | Putnam County | -339679.2083
|  |  | 1601482 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 1601483 |  |  | Shadeland | -339679.2083
|  |  | 1601484 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601485 |  |  | Avon | -339679.2083
|  |  | 1601486 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601487 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 1601488 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601489 |  |  | Vigo County | -339679.2083
|  |  | 1601490 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601491 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601492 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601493 |  | C Blair Enterprises, Inc. | Elkhart | 2017-05-31
|  |  | 1601494 |  |  | Elkhart County | 2017-05-31
|  |  | 1601495 |  | Civil Inspection Services, LLC | Goshen | 2017-05-31
|  |  | 1601496 |  | Midwest Archaeological Research Services, Inc. | Zionsville | -339679.2083
|  |  | 1601497 |  | Farren Real Estate Services | Middlebury | 2017-05-31
|  |  | 1601498 |  |  | Benton County | -339679.2083
|  |  | 1601499 |  |  | Benton County | -339679.2083
|  |  | 1601500 |  | Farren Real Estate Services | Middlebury | 2017-05-31
|  |  | 1601501 |  |  | Benton County | -339679.2083
|  |  | 1601502 |  | Finley Engineering Group, Inc. | Millersburg | 2017-05-31
|  |  | 1601503 |  | Driesenga & Associates, Inc. | Ladoga | -339679.2083
|  |  | 1601504 |  | Gandhi and Associates, Inc. | Nappanee | 2017-05-31
|  |  | 1601505 |  |  | Oxford | -339679.2083
|  |  | 1601506 |  | Gandhi and Associates, Inc. | Nappanee | 2017-05-31
|  |  | 1601507 |  | All About Pavements, Inc. | Brownsburg | -339679.2083
|  |  | 1601508 |  | Advanced Appraisals, LLC | Clay County | -339679.2083
|  |  | 1601509 |  | Wessler Engineering, Inc. | Wakarusa | 2017-05-31
|  |  | 1601510 |  | Iteris, Inc. | Rossville | -339679.2083
|  |  | 1601511 |  |  | Owen County | -339679.2083
|  |  | 1601512 |  | Wessler Engineering, Inc. | Wakarusa | 2017-05-31
|  |  | 1601513 |  |  | Owen County | -339679.2083
|  |  | 1601514 |  | Evans, Mechwart, Hambleton & Tilton, Inc. | Medaryville | -339679.2083
|  |  | 1601515 |  | Chicago Title Insurance Company | Gas City | 2017-05-31
|  |  | 1601516 |  |  | Grant County | 2017-05-31
|  |  | 1601517 |  | Dave Helton & Associates, Inc. | Jonesboro | 2017-05-31
|  |  | 1601518 |  | Dave Helton & Associates, Inc. | Jonesboro | 2017-05-31
|  |  | 1601519 |  |  | Daviess County | 2017-05-31
|  |  | 1601520 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2017-05-31
|  |  | 1601521 |  | Level 5 Engineering, LLC | Van Buren | 2017-05-31
|  |  | 1601522 |  | Level 5 Engineering, LLC | Van Buren | 2017-05-31
|  |  | 1601523 |  |  | Kosciusko County | 2017-05-31
|  |  | 1601524 |  |  | Kosciusko County | 2017-05-31
|  |  | 1601525 |  |  | Kosciusko County | 2017-05-31
|  |  | 1601526 |  |  | Leesburg | 2017-05-31
|  |  | 1601527 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2017-05-31
|  |  | 1601528 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2017-05-31
|  |  | 1601529 |  | Mackie Consultants, LLC | Warsaw | 2017-05-31
|  |  | 1601530 |  | Mackie Consultants, LLC | Warsaw | 2017-05-31
|  |  | 1601531 |  | Mackie Consultants, LLC | Warsaw | 2017-05-31
|  |  | 1601532 |  | Mackie Consultants, LLC | Warsaw | 2017-05-31
|  |  | 1601533 |  | McLane Realty, Inc. | Winona Lake | 2017-05-31
|  |  | 1601534 |  | McLane Realty, Inc. | Winona Lake | 2017-05-31
|  |  | 1601535 |  | Booker Real Estate Services | Dune Acres | 2017-05-31
|  |  | 1601536 |  | Brenner Design Incorporated | Dyer | -339679.2083
|  |  | 1601537 |  | CTLGroup | Fortville | 2017-05-31
|  |  | 1601538 |  | Burgess & Niple, Inc. | Eaton | 2017-05-31
|  |  | 1601539 |  |  | Daleville | 2017-05-31
|  |  | 1601540 |  |  | Clermont | 2017-05-31
|  |  | 1601541 |  | Appraising Indiana, LLC | Cicero | 2017-05-31
|  |  | 1601542 |  | American Resources Group, Ltd. | Cambridge City | 2017-05-31
|  |  | 1601543 |  | CoCal Consulting, LLC | Greenfield | -339679.2083
|  |  | 1601544 |  | Another Test Company | Carmel | 2017-05-31
|  |  | 1601545 |  |  | Alexandria | 2017-05-31
|  |  | 1601546 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1601547 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 1601548 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 1601549 |  | ASC Group, Inc. | Beech Grove | -339679.2083
|  |  | 1601550 |  | Collins Engineers Incorporated | Greentown | 2017-05-31
|  |  | 1601551 |  | J.F. New & Associates, Inc. | Russiaville | 2017-05-31
|  |  | 1601552 |  | ATSI Engineering Services | Beverly Shores | -339679.2083
|  |  | 1601553 |  | AAC Environmental Consulting, LLC | Anderson | 2017-05-31
|  |  | 1601554 |  | KERAMIDA Environmental, Inc. | Speedway | 2017-05-31
|  |  | 1601555 |  | Innis Consulting Group, LLC | Rocky Ripple | 2017-05-31
|  |  | 1601556 |  | American Commercial Title & Escrow | Burns Harbor | -339679.2083
|  |  | 1601557 |  |  | Chesterton | -339679.2083
|  |  | 1601558 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 1601559 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 1601560 |  |  | Dubois County | 2017-05-31
|  |  | 1601561 |  |  | Gibson County | 2017-05-31
|  |  | 1601562 |  |  | Greene County | 2017-05-31
|  |  | 1601563 |  |  | Knox County | 2017-05-31
|  |  | 1601564 |  |  | Lawrence County | 2017-05-31
|  |  | 1601565 |  |  | Lawrence County | 2017-05-31
|  |  | 1601566 |  |  | Martin County | 2017-05-31
|  |  | 1601567 |  |  | Martin County | 2017-05-31
|  |  | 1601568 |  |  | Martin County | 2017-05-31
|  |  | 1601569 |  |  | Martin County | 2017-05-31
|  |  | 1601570 |  |  | Martin County | 2017-05-31
|  |  | 1601571 |  | Dodd Title Corporation | Kokomo | 2017-05-31
|  |  | 1601572 |  |  | Orange County | 2017-05-31
|  |  | 1601573 |  | Dodd Title Corporation | Kokomo | 2017-05-31
|  |  | 1601574 |  |  | Perry County | 2017-05-31
|  |  | 1601575 |  |  | Pike County | 2017-05-31
|  |  | 1601576 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 1601577 |  |  | Posey County | 2017-05-31
|  |  | 1601578 |  |  | Posey County | 2017-05-31
|  |  | 1601579 |  |  | Spencer County | 2017-05-31
|  |  | 1601580 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 1601581 |  | Appraisal Office of Central Indiana | Centerville | 2017-05-31
|  |  | 1601582 |  | Appraisal Office of Central Indiana | Centerville | 2017-05-31
|  |  | 1601583 |  |  | Centerville | -339679.2083
|  |  | 1601584 |  | Indiana Appraisal Group, Inc. | Richmond | 2017-05-31
|  |  | 1601585 |  | Indiana Appraisal Group, Inc. | Richmond | 2017-05-31
|  |  | 1601586 |  |  | Richmond | -339679.2083
|  |  | 1601587 |  |  | Sullivan County | 2017-05-31
|  |  | 1601588 |  | Anelena Ackerly | Carlisle | 2017-05-31
|  |  | 1601589 |  | Beacon Surveying and Engineering | Cynthiana | 2017-05-31
|  |  | 1601590 |  |  | Newton County | -339679.2083
|  |  | 1601591 |  | Dyer Environmental Services | Lawrence | 2017-05-31
|  |  | 1601592 |  | Hafer PSC | Onward | -339679.2083
|  |  | 1601593 |  | Beals-Moore & Associates, Inc. | Dale | 2017-05-31
|  |  | 1601594 |  | Jill D Reed and Associates, Inc. | Sheridan | 2017-05-31
|  |  | 1601595 |  |  | Darmstadt | 2017-05-31
|  |  | 1601596 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1601597 |  |  | Delaware County | 2017-05-31
|  |  | 1601598 |  |  | Delaware County | 2017-05-31
|  |  | 1601599 |  |  | Delaware County | 2017-05-31
|  |  | 1601600 |  | CMF Engineering, Inc. | Ferdinand | 2017-05-31
|  |  | 1601601 |  | CSR Engineering, Inc. | Fort Branch | 2017-05-31
|  |  | 1601602 |  |  | Madison County | 2017-05-31
|  |  | 1601603 |  | Frost Engineering & Consulting Company | Montgomery | 2017-05-31
|  |  | 1601604 |  | Global Land Surveying, LLC | New Harmony | 2017-05-31
|  |  | 1601605 |  |  | Newburgh | 2017-05-31
|  |  | 1601606 |  | JJR, LLC | Santa Claus | 2017-05-31
|  |  | 1601607 |  | JJR, LLC | Santa Claus | 2017-05-31
|  |  | 1601608 |  |  | Tennyson | 2017-05-31
|  |  | 1601609 |  |  | Vanderburgh County | 2017-05-31
|  |  | 1601610 |  |  | Vanderburgh County | 2017-05-31
|  |  | 1601611 |  |  | Warrick County | 2017-05-31
|  |  | 1601612 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1601613 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1601614 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1601615 |  | Corn Island Archaeology, LLC | Hebron | -339679.2083
|  |  | 1601616 |  | Corn Island Archaeology, LLC | Hebron | -339679.2083
|  |  | 1601617 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1601618 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 1601619 |  | J. H. Rudolph & Co., Inc. | Royal Center | 2017-05-31
|  |  | 1601620 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 1601621 |  |  | White County | 2017-05-31
|  |  | 1601622 |  |  | Hamlet | -339679.2083
|  |  | 1601623 |  | Marino Engineering Associates Inc | Wheatfield | -339679.2083
|  |  | 1601624 |  |  | Wheatfield | -339679.2083
|  |  | 1601625 |  | MCCARTIN - ASSOCIATES | Walton | -339679.2083
|  |  | 1601626 |  | Donohue & Associates, Inc. | La Crosse | -339679.2083
|  |  | 1601627 |  | Deig Bros. Lumber & Construction Co., Inc. | Kewanna | -339679.2083
|  |  | 1601628 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1601629 |  |  | Wayne County | 2017-05-31
|  |  | 1601630 |  |  | Wayne County | 2017-05-31
|  |  | 1601631 |  |  | Wayne County | 2017-05-31
|  |  | 1601632 |  |  | Fulton County | -339679.2083
|  |  | 1601633 |  |  | Fulton County | -339679.2083
|  |  | 1601634 |  |  | Knox | -339679.2083
|  |  | 1601635 |  |  | Knox | -339679.2083
|  |  | 1601636 |  |  | Knox | -339679.2083
|  |  | 1601637 |  | Hy-Tech Response, Inc. | Porter | -339679.2083
|  |  | 1601638 |  | M.A.T. Consulting, Inc. | Walkerton | -339679.2083
|  |  | 1601639 |  |  | Flora | -339679.2083
|  |  | 1601640 |  | Capstone, Inc. | Francesville | -339679.2083
|  |  | 1601641 |  | Capstone, Inc. | Francesville | -339679.2083
|  |  | 1601642 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1601643 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1601644 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 1601645 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1601646 |  |  | Westfield | 2017-05-31
|  |  | 1601647 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1601648 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1601649 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2017-05-31
|  |  | 1601650 |  | Edwards and Kelcey | Lowell | -339679.2083
|  |  | 1601651 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2017-05-31
|  |  | 1601652 |  | Edwards and Kelcey | Lowell | -339679.2083
|  |  | 1601653 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2017-05-31
|  |  | 1601654 |  | Edwards and Kelcey | Lowell | -339679.2083
|  |  | 1601655 |  | CGS Real Estate Services, LLC | Fairmount | 2017-05-31
|  |  | 1601656 |  | Dummy Consulting Firm Too | Lakeville | -339679.2083
|  |  | 1601657 |  | Dummy Consulting Firm Too | Lakeville | -339679.2083
|  |  | 1601658 |  |  | Hancock County | 2017-05-31
|  |  | 1601659 |  |  | Hancock County | 2017-05-31
|  |  | 1601660 |  |  | Lake County | -339679.2083
|  |  | 1601661 |  |  | Howard County | 2017-05-31
|  |  | 1601662 |  | Huff & Huff, Inc. | Portage | -339679.2083
|  |  | 1601663 |  |  | South Bend | -339679.2083
|  |  | 1601664 |  | Jacobi, Toombs & Lanz, Inc. | Schneider | -339679.2083
|  |  | 1601665 |  |  | St. Joseph County | -339679.2083
|  |  | 1601666 |  |  | Porter County | -339679.2083
|  |  | 1601667 |  |  | Porter County | -339679.2083
|  |  | 1601668 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1601669 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1601670 |  | HDR Engineering, Inc. | North Liberty | -339679.2083
|  |  | 1601671 |  |  | Munster | -339679.2083
|  |  | 1601672 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 1601673 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1601674 |  |  | Winfield | -339679.2083
|  |  | 1601675 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 1601676 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1601677 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1601678 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1601679 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1601680 |  |  | Jasper County | -339679.2083
|  |  | 1601681 | Vigo |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1601682 |  |  | Jasper County | -339679.2083
|  |  | 1601683 |  |  | Marshall County | -339679.2083
|  |  | 1601684 |  |  | Marshall County | -339679.2083
|  |  | 1601685 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1601686 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1601687 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 1601688 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 1601689 |  |  | Pulaski County | -339679.2083
|  |  | 1601690 |  |  | Pulaski County | -339679.2083
|  |  | 1601691 |  |  | Pulaski County | -339679.2083
|  |  | 1601692 |  |  | Pulaski County | -339679.2083
|  |  | 1601693 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1601694 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1601695 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1601696 |  | CRI Construction Inc. | Flora | -339679.2083
|  |  | 1601697 |  |  | Flora | -339679.2083
|  |  | 1601698 | Vanderburgh |  | Vanderburgh County | 2017-05-31 | PE
|  |  | 1601699 |  | Dodd Title Corporation | Indiana Department of Transportation | 2017-05-31
|  |  | 1601700 | Vanderburgh | CGI | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1601701 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1601702 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1601703 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601704 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1601705 | Various |  | Indiana Department of Transportation | 2016-12-14 | CE
CN
PE
|  |  | 1601706 |  |  | Indiana Department of Transportation | 2017-07-12
|  |  | 1601707 |  |  | Indiana Department of Transportation | 2017-10-12
|  |  | 1601708 |  |  | Indiana Department of Transportation | 2017-12-13
|  |  | 1601709 |  |  | Indiana Department of Transportation | 2017-12-13
|  |  | 1601710 | Various |  | Indiana Department of Transportation | 2017-01-19 | CE
CN
PE
|  |  | 1601711 | LaPorte |  | Indiana Department of Transportation | 2019-01-23 | CE
CN
|  |  | 1601712 |  | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601713 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601714 | Hamilton | CPS Acquisitions, LLC | Fishers | 2017-02-15 | CN
|  |  | 1601715 |  | EnviroScience, Inc. | Martinsville | 2017-05-31
|  |  | 1601716 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1601717 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601718 | Vanderburgh | CGI | Indiana Department of Transportation | 2018-03-14 | CE
CN
RR
|  |  | 1601719 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601720 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601721 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601722 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1601723 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601724 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601725 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1601726 | Lake | McDonough Associates, Inc. | Winfield | 2019-04-03 | CN
|  |  | 1601727 | Lake | McDonough Associates, Inc. | Winfield | 2019-04-03 | CN
|  |  | 1601728 | Lake | McDonough Associates, Inc. | Winfield | 2019-04-03 | CN
|  |  | 1601729 |  |  | Brookston | 2018-05-31
|  |  | 1601730 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601731 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601732 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1601733 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1601734 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1601735 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601736 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1601737 | Vanderburgh |  | Indiana Department of Transportation | 2017-05-31 | CN
OT
|  |  | 1601738 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601739 |  |  | Indiana Department of Transportation | 2018-03-07
|  |  | 1601740 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601741 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601742 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601743 |  |  | Indiana Department of Transportation | 2017-02-08
|  |  | 1601744 |  | ARCADIS | Batesville | 2017-05-31
|  |  | 1601745 | Bartholomew |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1601746 | LaPorte |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1601747 | Various |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1601748 | Warrick |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1601749 | Various |  | Indiana Department of Natural Resources | -339679.2083 | OT
|  |  | 1601750 | Greene |  | Indiana Department of Natural Resources | 2017-05-31 | CN
|  |  | 1601751 | Various |  | Indiana Department of Natural Resources | 2017-05-31 | OT
|  |  | 1601752 | Wayne |  | Indiana Department of Natural Resources | 2018-05-31 | PE
|  |  | 1601753 | Randolph |  | Indiana Department of Natural Resources | 2018-05-31 | PE
|  |  | 1601754 | Fulton |  | Indiana Department of Natural Resources | 2018-05-31 | CN
PE
ROW
|  |  | 1601755 | Howard |  | Indiana Department of Natural Resources | 2018-05-31 | CN
PE
ROW
|  |  | 1601756 | Miami |  | Indiana Department of Natural Resources | 2019-05-31 | PE
|  |  | 1601757 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601758 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1601759 | Lake |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601760 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601761 | LaPorte |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601762 | LaPorte |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601763 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601764 | Porter |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601765 | Marshall |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1601766 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601767 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601768 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601769 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601770 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601771 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1601772 |  | Bertsch-Frank & Associates, LLC | Dayton | -339679.2083
|  |  | 1601774 | Shelby |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1601775 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1601776 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2019-05-09 | PE
RR
|  |  | 1601777 |  |  | Lawrenceburg | 2017-05-31
|  |  | 1601778 |  |  | Indiana Department of Transportation | 2017-09-13
|  |  | 1601779 |  |  | Indiana Department of Transportation | 2018-01-18
|  |  | 1601780 |  |  | Indiana Department of Transportation | 2018-01-18
|  |  | 1601781 |  |  | Indiana Department of Transportation | 2018-01-18
|  |  | 1601782 |  | DCD Consulting LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1601783 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1601784 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601785 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1601786 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601787 |  |  | Hamilton County | 2018-05-31
|  |  | 1601788 | Elkhart |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
RR
|  |  |  | Noble |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
RR
|  |  | 1601789 | Various |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1601790 | Warrick |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1601791 |  |  | East Chicago | 2017-02-08
|  |  | 1601792 | Scott |  | Indiana Department of Transportation | 2020-01-15 | ROW
|  |  | 1601793 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
ROW
UT
|  |  | 1601794 | Noble | InspectTech Systems, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1601795 | LaGrange | Merle Edward Orem | Indiana Department of Transportation | 2019-03-06 | CE
|  |  |  | Noble | Merle Edward Orem | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1601796 | Dearborn |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
|  |  | 1601797 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601798 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601799 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601800 | Marion |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1601801 | Jefferson |  | Indiana Department of Transportation | 2018-12-12 | ROW
|  |  | 1601802 | Clay |  | Indiana Department of Transportation | 2017-04-05 | CE
CN
PE
ROW
|  |  | 1601803 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1601804 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1601805 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1601806 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1601807 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1601808 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601809 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 1601810 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601811 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601812 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1601813 | Hamilton |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1601814 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601815 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1601816 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1601817 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1601818 | LaPorte |  | La Porte | 2017-05-10 | CE
CN
|  |  | 1601819 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601820 | Marion |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
ROW
|  |  | 1601821 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1601822 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1601823 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1601824 | Vanderburgh |  | Evansville | 2019-07-10 | CN
|  |  |  | Various |  | Evansville | 2019-07-10 | CN
PE
|  |  | 1601825 |  |  | Indiana Department of Transportation | 2017-05-10
|  |  | 1601826 | Hamilton | H. Stewart Kline & Associates, Inc. | Fishers | 2020-02-05 | CE
CN
|  |  | 1601827 | Hamilton | CPS Acquisitions, LLC | Fishers | 2019-07-10 | CE
CN
|  |  | 1601828 | Hamilton | CPS Acquisitions, LLC | Fishers | 2020-12-09 | CE
CN
|  |  | 1601829 | Hamilton | H. Stewart Kline & Associates, Inc. | Fishers | 2018-09-12 | CE
CN
|  |  | 1601830 |  | CPS Acquisitions, LLC | Fishers | 2022-02-09
|  |  | 1601831 | Hamilton | H. Stewart Kline & Associates, Inc. | Fishers | 2018-09-12 | CE
CN
|  |  | 1601832 | Hamilton |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1601833 | Madison |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1601834 | Marion |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1601835 | Marion |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1601836 |  |  | Indiana Department of Transportation | 2017-08-09
|  |  | 1601837 | Starke |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1601838 | Marion |  | Indiana Department of Transportation | 2017-03-01 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2017-03-01 | CE
CN
PE
|  |  | 1601839 |  |  | Indianapolis | -339679.2083
|  |  | 1601840 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1601841 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1601842 |  |  | Indianapolis | -339679.2083
|  |  | 1601843 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | PE
|  |  | 1601844 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | PE
|  |  | 1601845 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | PE
|  |  | 1601846 | Lake | Dummy Consulting Firm | Lake Station | -339679.2083 | PE
|  |  | 1601847 |  |  | La Porte | -339679.2083
|  |  | 1601848 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601849 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
RR
|  |  | 1601850 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1601851 | Monroe | Absolute Title Services, LLC | Bloomington | 2019-01-16 | CE
CN
PE
|  |  | 1601852 | Warrick |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601853 | Warrick |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601854 | Spencer |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601855 | Spencer |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601856 | Spencer |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601857 | Spencer |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601858 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-04-05
|  |  | 1601859 | Pike |  | Indiana Department of Transportation | 2017-05-31 | PE
|  |  | 1601860 |  | AAC Environmental Consulting, LLC | Anderson | 2017-02-04
|  |  | 1601861 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1601862 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2017-07-12 | CE
CN
RR
|  |  | 1601863 | Hamilton | CPS Acquisitions, LLC | Fishers | 2018-05-10 | CE
CN
|  |  | 1601864 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601865 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601866 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1601867 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2022-02-09 | PE
ROW
|  |  | 1601868 | LaPorte |  | LaPorte County | 2019-05-09 | CN
PE
ROW
|  |  | 1601869 | LaPorte | Farah and Sons, Inc. | Michigan City | 2021-04-07 | CE
CN
PE
|  |  | 1601870 | LaPorte |  | La Porte | -339679.2083 | PE
|  |  | 1601871 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1601872 | Clark |  | Indiana Department of Transportation | 2017-07-12 | CE
CN
|  |  | 1601873 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601874 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601875 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601876 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601877 |  |  | Indiana Department of Transportation | 2017-04-05
|  |  | 1601878 |  |  | Indiana Department of Transportation | 2017-04-05
|  |  | 1601879 | Gibson |  | Indiana Department of Transportation | 2019-05-31 | CE
CN
ROW
|  |  | 1601881 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601882 | Putnam | Clayton L. Roots | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601883 | Clay |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1601884 | Tippecanoe |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
RR
|  |  | 1601885 |  |  | Indiana Department of Transportation | 2018-01-18
|  |  | 1601886 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1601887 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601889 | Allen |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
UT
|  |  | 1601890 | Allen |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1601891 |  |  | Merrillville | -339679.2083
|  |  | 1601892 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601893 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1601894 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601895 |  |  | MPO - Northwest | -339679.2083
|  |  | 1601896 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | 2017-04-05 | CE
CN
|  |  | 1601897 |  |  | Hobart | -339679.2083
|  |  | 1601898 |  |  | Hobart | -339679.2083
|  |  | 1601899 | Lake | Chicago Testing Laboratory, Inc. | Gary | -339679.2083 | PE
|  |  | 1601900 |  |  | Gary | -339679.2083
|  |  | 1601901 |  |  | Gary | -339679.2083
|  |  | 1601902 |  |  | Lake County | -339679.2083
|  |  | 1601903 |  |  | Lake County | -339679.2083
|  |  | 1601904 |  |  | Lake County | -339679.2083
|  |  | 1601905 |  |  | Lake County | -339679.2083
|  |  | 1601906 | Porter | Leitner and Associates, Inc. | Valparaiso | -339679.2083 | PE
|  |  | 1601907 |  |  | Valparaiso | -339679.2083
|  |  | 1601908 |  |  | Valparaiso | -339679.2083
|  |  | 1601909 |  |  | Valparaiso | -339679.2083
|  |  | 1601910 |  |  | Valparaiso | -339679.2083
|  |  | 1601911 |  |  | Valparaiso | -339679.2083
|  |  | 1601912 |  |  | Valparaiso | -339679.2083
|  |  | 1601913 |  |  | Valparaiso | -339679.2083
|  |  | 1601914 |  |  | Valparaiso | -339679.2083
|  |  | 1601915 |  |  | Valparaiso | -339679.2083
|  |  | 1601916 |  |  | MPO - Cincinnati | -339679.2083
|  |  | 1601917 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1601918 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2015-05-31
|  |  | 1601919 | Rush |  | Rushville | 2019-12-11 | CE
CN
PE
|  |  | 1601920 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1601921 | Rush |  | Rushville | 2019-12-11 | CE
CN
PE
|  |  | 1601922 | LaPorte | Donohue & Associates, Inc. | La Crosse | 2019-03-06 | CE
CN
PE
|  |  | 1601923 | Porter | Huff & Huff, Inc. | Portage | 2018-07-11 | CN
|  |  | 1601924 |  |  | MPO - Evansville | -339679.2083
|  |  | 1601925 |  |  | MPO - Evansville | -339679.2083
|  |  | 1601926 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1601927 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1601928 | Adams |  | Indiana Department of Transportation | 2018-07-11 | CE
|  |  |  | Hendricks |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
ROW
|  |  | 1601929 | Lawrence |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
ROW
|  |  | 1601930 | Clay |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
ROW
|  |  | 1601931 | Allen | Global Management Group, Inc. | New Haven | 2021-10-14 | CE
CN
|  |  | 1601932 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601933 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2017-12-13 | CE
CN
ROW
|  |  | 1601934 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1601943 | Jackson |  | Seymour | 2019-11-14 | CE
CN
RR
|  |  | 1601944 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1601945 | Wayne |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1601946 | Wayne |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601947 | Wayne |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601948 | Wayne |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601949 | Wayne |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601950 | Randolph |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601951 | Randolph |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601952 | Henry |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601953 | Henry |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1601954 | Henry |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1601955 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601956 | Hancock |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601957 | Hancock |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601958 | Hancock |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601959 | Henry |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601960 | Henry |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1601961 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1601962 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601963 | Henry | American Real Estate Appraisers, Inc. | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1601964 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1601965 | Marion |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1601966 |  | Environmental Monitoring and Technologies, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601967 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1601968 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1601969 | Kosciusko | LONCO, Inc. | Indiana Department of Transportation | 2021-08-11 | CE
CN
PE
|  |  | 1601970 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1601971 | Floyd |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1601972 | Harrison |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1601973 | Shelby |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1601974 | Shelby |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1601975 | Harrison |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1601976 | Wabash |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1601977 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1601978 | Shelby |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1601979 | Jackson |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1601980 | Shelby |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1601981 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1601982 |  | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | 2022-04-06
|  |  | 1601983 | LaGrange |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1601984 | Noble |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1601985 |  |  | Indiana Department of Transportation | 2019-11-14
|  |  | 1601986 | Jackson |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1601987 | Franklin |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1601988 | Grant |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1601989 | Jackson |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  |  | Washington |  | Indiana Department of Transportation | 2019-09-11 | CE
|  |  | 1601990 | Posey |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1601991 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1601992 | Tippecanoe |  | Indiana Department of Transportation | 2019-11-20 | CE
CN
PE
|  |  | 1601993 | Vigo |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1601994 | Clinton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1601995 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1601996 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1601997 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2019-11-20
|  |  | 1601998 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1601999 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-11-20 | CE
CN
|  |  | 1602000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602001 | Morgan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1602002 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602003 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602004 | Putnam |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602005 | Putnam |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602006 | Putnam |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1602007 | Morgan |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1602008 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1602009 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602010 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1602011 | Fountain |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1602012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602014 | Clinton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602015 | Parke |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1602016 | Parke |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1602017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602018 | Clay |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602019 | Parke |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1602020 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1602021 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602022 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602023 | Warren |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1602024 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1602025 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602026 | Hendricks |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1602027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602029 |  |  | Indiana Department of Transportation | 2019-11-14
|  |  | 1602030 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1602031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602032 | Hendricks |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602033 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602034 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602035 | Hendricks |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1602036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602037 | Vigo |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602038 | Clinton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602039 | Vigo |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602040 | Vigo |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602041 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602042 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-11-20 | CE
CN
|  |  | 1602043 | Parke |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1602044 | Vigo |  | Indiana Department of Transportation | 2020-03-04 | RR
|  |  | 1602045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602047 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602048 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1602049 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602051 | Clinton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602052 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602053 | Parke |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1602054 | Hendricks |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1602055 | Hendricks |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1602056 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1602057 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-11-20 | RR
|  |  | 1602058 | Warren |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
RR
|  |  | 1602059 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
RR
|  |  | 1602060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602063 | Fountain | Linda F. Russell | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1602064 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602065 | Hendricks |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1602066 | Fountain |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1602067 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1602068 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602069 |  |  | Indiana Department of Transportation | 2019-11-20
|  |  | 1602070 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602071 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602072 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602073 | Fountain |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1602074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602075 | Putnam |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602076 | Putnam |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602077 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1602078 |  |  | Indiana Department of Transportation | 2019-11-14
|  |  | 1602079 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602080 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602081 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602082 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1602083 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1602084 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602085 | Clinton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602086 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1602087 | Montgomery |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602088 |  |  | Westfield | -339679.2083
|  |  | 1602089 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602090 |  | FHG Consulting, Inc. | Indiana Department of Transportation | 2019-11-14
|  |  | 1602091 | Boone |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1602092 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602093 | Putnam |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1602094 |  |  | Indiana Department of Transportation | 2019-11-20
|  |  | 1602095 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1602096 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602097 | Harrison |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602098 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1602099 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1602100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602101 |  |  | Indiana Department of Transportation | 2019-11-14
|  |  | 1602102 | Jefferson |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602103 | Lawrence |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1602104 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602105 | Brown | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602106 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1602107 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1602108 | Starke |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602109 |  |  | Indiana Department of Transportation | 2017-04-05
|  |  | 1602110 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2021-09-15 | PE
|  |  | 1602111 | Marshall |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1602112 | Starke |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
RR
|  |  | 1602113 | Marshall | ACMS Group, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
RR
|  |  | 1602114 | Crawford |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1602115 | Greene |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1602116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602117 | Perry |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1602118 | Perry |  | Indiana Department of Transportation | 2025-11-13 | PE
|  |  | 1602119 | Perry |  | Indiana Department of Transportation | 2025-11-13 | PE
|  |  | 1602120 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-03-04
|  |  | 1602121 |  | A & Z Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602122 | St. Joseph |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1602123 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1602124 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1602125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602126 |  | Franco Consulting Engineers, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602128 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602129 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602130 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602131 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602132 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1602133 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602134 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602135 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602136 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602137 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602138 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602139 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602140 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1602141 | Various |  | Indiana Department of Transportation | 2020-11-10 | PE
ROW
|  |  | 1602142 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1602143 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1602144 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602145 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1602146 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
RR
|  |  | 1602147 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-12-11
|  |  | 1602148 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602149 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602150 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602151 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602152 | Wayne |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1602153 | Wayne |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1602154 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1602155 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1602156 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602157 | Boone |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602158 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1602159 | Dubois |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1602160 | Various |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1602161 | Various |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1602162 | Various |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602163 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1602164 | Lawrence |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602165 | Jennings |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1602166 | Various |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1602167 | Johnson |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
RR
|  |  | 1602168 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
RR
|  |  | 1602169 |  | Casteel Real Estate | Indiana Department of Transportation | 2019-12-11
|  |  | 1602170 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1602171 | Jackson |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  |  | Lawrence |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602172 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1602173 | Decatur | March Environmental Services, LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602174 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1602175 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1602176 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1602177 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1602178 | Marion | ASC Group, Inc. | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602179 | Marion | ASC Group, Inc. | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602180 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1602181 | Marion |  | Indiana Department of Transportation | 2017-08-09 | CE
CN
|  |  | 1602182 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602183 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1602184 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602185 | Jennings |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
RR
|  |  | 1602186 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602187 | Dearborn |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  |  | Ohio |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602188 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602190 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602191 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602192 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602193 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602194 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602195 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602196 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602197 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602198 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602199 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602200 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
RR
|  |  | 1602201 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
RR
|  |  | 1602202 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1602203 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1602204 | Delaware |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1602205 | Delaware |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1602206 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602207 | Marion |  | Indiana Department of Transportation | 2018-09-12 | PE
|  |  | 1602208 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1602209 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1602210 | Delaware |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1602211 | Delaware |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1602212 | Marion |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1602213 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1602214 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1602215 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1602216 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1602217 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1602218 | Randolph |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1602219 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1602220 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1602221 | Hamilton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1602222 | Henry | Dillabaugh, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1602223 | Marion |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1602224 | Marion |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1602225 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1602226 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1602227 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1602228 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1602229 | Hamilton | CPS Acquisitions, LLC | Fishers | 2019-07-10 | CE
CN
|  |  | 1602230 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1602231 | Hamilton | CPS Acquisitions, LLC | Fishers | 2020-12-09 | CE
CN
|  |  | 1602232 | Wayne |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1602233 | Wayne |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1602234 | Wayne |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1602235 | Wayne |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1602236 | Wayne |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1602237 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1602238 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1602239 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602240 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602241 | Shelby |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1602242 | Shelby |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1602243 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1602244 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1602245 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1602246 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1602247 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1602248 | Vanderburgh |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1602249 | Daviess |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1602250 | Daviess |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1602251 | Martin |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1602252 | Pike |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602253 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1602254 | Dubois |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1602255 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1602256 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1602257 | Greene |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1602258 | Vanderburgh | CGI | Indiana Department of Transportation | 2023-11-15 | PE
|  |  | 1602259 | Jefferson |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1602260 | Decatur |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
UT
|  |  | 1602261 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1602262 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1602263 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1602264 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1602265 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1602266 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1602267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602268 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602271 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1602272 | Allen | EDP Consultants | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
ROW
|  |  | 1602273 |  |  | Indiana Department of Transportation | 2017-07-12
|  |  | 1602274 |  |  | Indiana Department of Transportation | 2017-07-12
|  |  | 1602275 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2017-07-12
|  |  | 1602276 | Washington |  | Indiana Department of Transportation | 2022-01-12 | PE
UT
|  |  | 1602277 | Jackson |  | Indiana Department of Transportation | 2021-08-11 | CN
PE
UT
|  |  | 1602278 | Decatur |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1602279 | Ripley | ARCADIS | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1602280 |  |  | Hendricks County | -339679.2083
|  |  | 1602281 | Dearborn |  | Indiana Department of Transportation | 2022-10-13 | PE
|  |  | 1602282 | Ripley |  | Indiana Department of Transportation | 2022-10-13 | PE
|  |  | 1602283 | Franklin |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1602284 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1700001 | Switzerland |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700002 |  |  | Indiana Department of Transportation | 2017-07-12
|  |  | 1700003 | Sullivan |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700004 | Scott |  | Indiana Department of Transportation | 2022-01-12 | PE
UT
|  |  | 1700005 | Jefferson |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1700006 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700007 | Crawford |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1700008 |  | H.R. Gray | Indiana Department of Transportation | 2022-05-05
|  |  | 1700009 | Washington |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1700010 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-08-10
|  |  | 1700011 |  | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2022-02-09
|  |  | 1700012 | Bartholomew |  | Indiana Department of Transportation | 2022-03-09 | PE
UT
|  |  | 1700013 | Crawford |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1700014 | Lawrence |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1700015 | Crawford |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700016 | Orange |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700017 | Posey |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1700018 |  | Dummy Consulting Firm Too | Indiana Department of Transportation | 2021-07-14
|  |  | 1700019 | Martin | ASA Land Surveying | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1700020 | St. Joseph |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1700021 | LaPorte |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1700022 | Lake |  | Indiana Department of Transportation | 2023-02-15 | PE
|  |  | 1700023 | Knox |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1700024 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700025 | Lake | Applied Pavement Technology, Inc. | Indiana Department of Transportation | 2025-07-09 | PE
|  |  | 1700026 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700028 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1700029 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1700030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700031 | Grant | CGS Real Estate Services, LLC | Indiana Department of Transportation | 2022-01-12 | RR
|  |  | 1700032 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1700033 |  | IXOYE, Limited | Indiana Department of Transportation | -339679.2083
|  |  | 1700034 | Fulton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700035 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1700036 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1700037 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1700038 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1700039 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1700040 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-09-14
|  |  | 1700041 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1700042 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1700043 | Lawrence |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1700044 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700045 | Jackson |  | Indiana Department of Transportation | 2022-01-12 | PE
UT
|  |  | 1700046 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700047 | Lawrence |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700048 | Jackson |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700049 | Jefferson |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1700050 | Decatur |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1700051 | Greene |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700052 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1700053 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1700054 | Ripley | ARCADIS | Indiana Department of Transportation | 2022-01-12 | RR
|  |  | 1700055 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2020-02-05
|  |  | 1700056 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1700057 | Harrison |  | Indiana Department of Transportation | 2023-10-12 | PE
|  |  | 1700058 | Jefferson |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1700059 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700060 | Harrison |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1700061 | Harrison |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700062 |  |  | Hendricks County | 2017-05-31
|  |  | 1700063 | Pike |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700064 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 1700065 | Washington |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1700066 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700067 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700068 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700069 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700070 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700071 | Johnson |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700072 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700073 | Marshall |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1700074 | Porter |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700075 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700076 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700077 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700078 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1700079 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1700080 | Fulton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700081 | Fulton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700082 | Starke |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700083 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700085 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1700086 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700087 | Lake |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700088 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1700089 | Miami |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700090 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1700091 |  | Archonsortium, LLC | Indiana Department of Transportation | 2022-04-06
|  |  | 1700092 | LaGrange |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1700093 | Huntington |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1700094 | Lake |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700095 | Clinton |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700096 |  | E.J. Breneman, LP | Indiana Department of Transportation | -339679.2083
|  |  | 1700097 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1700098 | Vermillion |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1700099 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1700100 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1700101 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1700102 | Carroll | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700103 | White |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700104 | Benton | CDM Smith, Inc. | Indiana Department of Transportation | 2022-01-12 | RR
|  |  | 1700105 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1700106 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 1700107 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 1700108 | Johnson | Burrell Appraisal Service, Inc. | Indiana Department of Transportation | 2024-09-11 | PE
|  |  | 1700109 |  | Indiana Search Technologies | Indiana Department of Transportation | -339679.2083
|  |  | 1700110 |  | Indiana Search Technologies | Indiana Department of Transportation | -339679.2083
|  |  | 1700111 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1700112 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1700113 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1700114 | Warren | Chastain & Associates LLC | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700115 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  |  | Noble | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1700116 | Hendricks |  | Indiana Department of Transportation | 2022-04-06 | RR
|  |  | 1700117 | Benton |  | Indiana Department of Transportation | 2022-02-09 | PE
RR
|  |  | 1700118 | Jackson |  | Indiana Department of Transportation | 2022-02-09 | PE
UT
|  |  | 1700119 | Putnam | AI Engineers, Inc. | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1700120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700121 | Putnam | Clayton L. Roots | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700122 | Switzerland |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1700123 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700124 | Newton |  | Indiana Department of Transportation | 2020-09-02 | PE
|  |  | 1700125 | Ohio |  | Indiana Department of Transportation | 2024-10-09 | PE
|  |  | 1700126 | Floyd |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1700127 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700128 | Harrison |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1700129 | Elkhart |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700130 | Huntington | HE-BFS, LLC | Indiana Department of Transportation | 2020-01-15 | CE
CN
RR
|  |  |  | Wabash | HE-BFS, LLC | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
RR
|  |  | 1700131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700132 |  | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1700133 |  | EDP Consultants | Indiana Department of Transportation | -339679.2083
|  |  | 1700134 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1700135 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1700136 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1700137 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
RR
|  |  | 1700138 |  | Clyde L. Hawkins | Indiana Department of Transportation | -339679.2083
|  |  | 1700139 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
ROW
RR
|  |  | 1700140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700141 | Greene |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700142 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1700143 | Clark |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
RR
|  |  | 1700144 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1700145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700146 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1700147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700148 | Sullivan |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700149 | Knox |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700150 | Pike |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1700151 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1700152 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1700153 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1700154 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1700155 | Martin |  | Indiana Department of Transportation | 2022-05-05 | PE
|  |  | 1700156 | Knox |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700157 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1700158 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1700159 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1700160 | Pike |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700161 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1700162 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1700163 |  |  | Indiana Department of Transportation | 2024-04-10
|  |  | 1700164 |  |  | Indiana Department of Transportation | 2024-04-10
|  |  | 1700165 | Gibson |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700166 | Pike |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700167 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1700168 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700169 | Sullivan |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1700170 | Warrick |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1700171 | Jackson |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1700172 | Crawford |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1700173 | Washington | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700174 | Greene |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700175 | Greene |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700177 | Spencer |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1700178 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1700179 | LaGrange | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700180 | Spencer |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1700181 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1700182 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-05-05 | CE
CN
UT
|  |  | 1700183 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1700184 |  | Iteris, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1700185 | Ripley |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1700186 |  | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2022-02-09
|  |  | 1700187 | Morgan |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700188 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1700189 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1700190 |  | ETC Institute | Indiana Department of Transportation | 2022-09-14
|  |  | 1700191 | Clay |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1700192 | Putnam |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700193 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 1700194 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 1700195 |  | Alfred Benesch & Company | Indiana Department of Transportation | 2025-08-06
|  |  | 1700196 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 1700197 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1700198 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2023-09-13
|  |  | 1700199 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1700200 | Jackson |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1700201 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1700202 | Ripley |  | Indiana Department of Transportation | 2022-10-13 | PE
|  |  | 1700203 | Jennings |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700204 |  |  | Indiana Department of Transportation | 2027-01-13
|  |  | 1700205 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1700206 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1700207 | Floyd |  | Indiana Department of Transportation | 2024-03-13 | PE
|  |  | 1700208 | Ripley |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1700209 | Floyd | Commonwealth Heritage Group, Inc. | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1700210 |  | Louis Joyner, Architect | Indiana Department of Transportation | -339679.2083
|  |  | 1700211 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1700212 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700213 | Various |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1700214 | Bartholomew |  | MPO - Columbus | -339679.2083 | PL
|  |  | 1700215 | Benton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700216 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1700217 | Grant |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1700218 | Huntington |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1700219 | Cass | Chemical Dependency Program of Indiana | Indiana Department of Transportation | 2023-01-19 | RR
|  |  | 1700220 | Various |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1700221 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1700222 | Wells |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1700223 | Adams | Bidinfo | Indiana Department of Transportation | 2019-11-14 | CE
CN
PE
|  |  | 1700224 | Allen |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1700225 | Huntington |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700226 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700227 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1700228 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1700229 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1700230 | Miami |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700231 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700232 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700233 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700234 | Various |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1700235 | Various |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1700236 | Various |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1700237 | Various |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1700238 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700239 | Various |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700240 | Various |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
ROW
|  |  | 1700241 | Various |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1700242 | Various |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700243 | Spencer |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1700244 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700245 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700246 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1700247 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700248 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700249 | Dekalb |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700250 | LaGrange | Duesler Realty House | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700251 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700252 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2020-01-15 | PE
RR
|  |  | 1700253 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1700254 | Miami | Holloway Engineering, LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700255 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700256 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700257 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700258 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700259 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700260 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700261 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700262 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 1700263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700264 |  |  | Indiana Department of Transportation | 2018-01-18
|  |  | 1700265 | Scott |  | Indiana Department of Transportation | 2017-05-10 | CE
CN
|  |  | 1700266 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700267 |  | B. L. A., Inc. | Corydon | -339679.2083
|  |  | 1700268 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1700269 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700270 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2024-07-10 | CE
CN
PE
|  |  | 1700271 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700272 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700273 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700274 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700275 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700276 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700277 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700278 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700279 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700280 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700281 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700282 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700283 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700284 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700285 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700286 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700287 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700288 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700289 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700290 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700291 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700292 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1700293 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-02-05
|  |  | 1700294 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-02-05
|  |  | 1700295 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-03-04
|  |  | 1700296 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-09-15 | PE
|  |  | 1700297 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-09-15 | PE
|  |  | 1700298 | Porter |  | Indiana Department of Transportation | 2023-10-12 | PE
|  |  | 1700299 | Porter |  | Indiana Department of Transportation | 2023-10-12 | PE
|  |  | 1700300 | LaPorte |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1700301 | LaPorte |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1700302 | St. Joseph |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1700303 | Marshall |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1700304 | Marshall |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1700305 | Newton |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1700306 | Newton |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1700307 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700308 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700309 | Elkhart |  | Elkhart County | 2021-12-08 | CN
PE
ROW
|  |  | 1700310 | Elkhart |  | Elkhart County | 2023-01-19 | PE
ROW
|  |  | 1700311 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700312 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700313 | Various |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1700314 | Various |  | Indiana Department of Transportation | 2020-01-15 | RR
|  |  | 1700315 | Various |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1700316 | Various |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1700317 | Various |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1700318 | Various |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1700319 | Various |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1700320 | Various |  | Indiana Department of Transportation | 2020-04-15 | CE
CN
PE
ROW
|  |  | 1700321 | Various |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1700322 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1700323 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1700324 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1700325 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1700326 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1700327 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1700328 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1700329 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700330 | Fulton |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1700331 | Marshall |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1700332 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-05-07
|  |  | 1700333 | White |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1700334 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1700335 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1700336 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1700337 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700338 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700339 |  |  | MPO - Fort Wayne | -339679.2083
|  |  | 1700340 |  |  | MPO - Muncie | -339679.2083
|  |  | 1700341 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1700342 |  |  | MPO - Evansville | -339679.2083
|  |  | 1700343 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2020-02-05
|  |  | 1700344 |  |  | MPO - Louisville | -339679.2083
|  |  | 1700345 |  |  | MPO - Cincinnati | -339679.2083
|  |  | 1700346 |  |  | Vigo County | -339679.2083
|  |  | 1700347 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1700348 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700349 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700350 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700351 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1700352 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1700353 |  |  | Indiana Department of Transportation | 2017-12-13
|  |  | 1700354 | Porter |  | Indiana Department of Transportation | 2020-05-07 | PE
RR
|  |  | 1700355 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1700356 | Newton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1700357 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1700358 |  | Consolidated Test Company | Indiana Department of Transportation | 2020-03-04
|  |  | 1700359 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1700360 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
RR
|  |  | 1700361 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700362 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700363 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700364 | Marshall | Active Environmental Services, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1700365 | Marshall | Active Environmental Services, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1700366 | Lake |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700367 | St. Joseph |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1700368 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-03-04
|  |  | 1700369 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-03-04
|  |  | 1700370 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1700371 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2020-02-05
|  |  | 1700372 | Newton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1700373 | Marshall |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1700374 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1700375 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1700376 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1700377 |  | Consolidated Test Company | Indiana Department of Transportation | 2020-02-05
|  |  | 1700378 | Jasper |  | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 1700379 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-03-04
|  |  | 1700380 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2020-04-01
|  |  | 1700381 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700382 | Jasper |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1700383 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1700384 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700385 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1700386 |  |  | Indiana Department of Transportation | 2018-04-04
|  |  | 1700387 | Various |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1700388 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700389 | Marshall |  | Marshall County | 2018-02-07 | CN
|  |  | 1700390 | Crawford |  | Indiana Department of Transportation | 2018-02-07 | CN
|  |  |  | Lawrence |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1700391 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1700392 |  |  | Indiana Department of Transportation | 2015-01-14
|  |  | 1700393 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700394 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
|  |  | 1700395 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1700396 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700397 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700399 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700400 | Vanderburgh |  | Evansville | 2020-02-05 | CE
CN
PE
ROW
|  |  | 1700401 | Tippecanoe |  | Lafayette | 2018-02-07 | CE
CN
PE
|  |  | 1700402 | Madison |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
ROW
|  |  | 1700403 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1700404 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1700405 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2021-01-13 | CE
CN
PE
|  |  | 1700406 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1700407 |  |  | Tippecanoe County | -339679.2083
|  |  | 1700408 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700409 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700410 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700411 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700412 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700413 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700414 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700415 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700416 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700417 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700418 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700419 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700420 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700421 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700422 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700423 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700424 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700425 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700426 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700427 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700428 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700429 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700430 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700431 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1700432 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1700433 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1700434 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1700435 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2017-01-19
|  |  | 1700436 | Vigo |  | Vigo County | 2021-05-31 | PE
|  |  | 1700437 | Vigo |  | Vigo County | 2026-08-05 | PE
|  |  | 1700438 | Vigo |  | Vigo County | 2021-10-14 | PE
|  |  | 1700439 | Vigo |  | Vigo County | 2026-08-05 | PE
|  |  | 1700440 | Vigo |  | Vigo County | 2026-08-05 | PE
|  |  | 1700441 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1700442 |  |  | Chesterton | -339679.2083
|  |  | 1700443 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700444 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1700445 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1700446 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2017-01-19
|  |  | 1700447 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2017-01-19
|  |  | 1700448 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1700450 |  | ASA Land Surveying | Indiana Department of Transportation | 2018-09-12
|  |  | 1700451 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700452 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700453 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700454 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700455 |  |  | MPO - Anderson | -339679.2083
|  |  | 1700456 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700457 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700458 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700459 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700460 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700461 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700462 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700463 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2015-05-31
|  |  | 1700464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700465 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700466 |  |  | Indiana Department of Transportation | 2017-10-12
|  |  | 1700467 |  |  | Indiana Department of Transportation | 2017-09-13
|  |  | 1700468 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700469 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700470 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700471 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700472 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700473 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700474 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700475 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700476 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700477 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700478 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700479 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700480 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700481 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1700482 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700483 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1700484 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700485 | Wabash |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1700486 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700487 |  |  | Vanderburgh County | -339679.2083
|  |  | 1700488 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1700489 |  |  | Indiana Department of Transportation | 2018-02-07
|  |  | 1700490 |  |  | Indiana Department of Transportation | 2018-02-07
|  |  | 1700491 |  |  | Indiana Department of Transportation | 2018-02-07
|  |  | 1700492 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1700493 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1700494 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700495 | Spencer |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1700496 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1700497 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2016-12-14
|  |  | 1700498 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1700499 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1700500 | Porter |  | Porter County | -339679.2083 | PE
|  |  | 1700501 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1700502 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700503 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1700504 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700506 | Sullivan |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700507 | Greene |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700508 | Greene |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700509 | Greene |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700510 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700511 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700512 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700513 | Posey |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700514 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700515 | Posey |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700516 | Daviess |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700517 | Vanderburgh |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700518 | Sullivan |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700520 | Sullivan |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700521 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1700522 | Vanderburgh |  | Indiana Department of Transportation | 2018-05-31 | RR
|  |  | 1700523 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1700524 | Marshall |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1700525 | Marion |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1700526 | Grant |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1700527 | Allen |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1700528 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700529 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700530 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700531 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700532 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700533 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700534 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700535 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700536 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700537 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700538 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700539 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700540 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700541 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700542 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700543 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700544 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700545 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700546 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700547 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700548 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700549 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700550 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700551 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700552 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700553 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700554 | Madison | Duneland Group, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
ROW
|  |  | 1700555 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1700556 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700557 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700558 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700559 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700560 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700561 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700562 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700563 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700564 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700565 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700566 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700567 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700568 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700569 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700570 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700571 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700572 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700573 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700574 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700575 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700576 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700579 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700580 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700581 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700582 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700583 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700584 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700585 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700586 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700587 | Vanderburgh | CGI | Indiana Department of Transportation | 2020-05-31 | RR
|  |  | 1700588 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700589 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700590 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700591 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700592 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700593 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700594 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700595 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700596 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700597 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700598 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700599 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700600 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700601 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700602 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700603 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700604 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700605 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700606 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700607 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700608 | Various |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1700609 | Various |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1700610 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1700611 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1700612 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700613 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700614 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1700615 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700616 | St. Joseph |  | Indiana Department of Transportation | 2017-09-13 | CE
CN
|  |  | 1700617 |  |  | Kokomo | -339679.2083
|  |  | 1700618 | Kosciusko |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  |  | Monroe |  | Indiana Department of Transportation | 2018-02-07 | CN
|  |  |  | Various |  | Indiana Department of Transportation | 2018-02-07 | CE
CN
|  |  | 1700619 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700620 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700621 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700622 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700623 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700624 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700625 |  |  | Indiana Department of Transportation | 2017-05-23
|  |  | 1700626 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700627 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700628 |  |  | Indiana Department of Transportation | 2017-05-31
|  |  | 1700629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700630 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700631 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700632 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700633 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700634 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700635 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700636 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700637 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700638 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700639 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700640 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700641 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700642 |  |  | MPO - Northwest | -339679.2083
|  |  | 1700643 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700644 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700645 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700646 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700647 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700648 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700649 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700650 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700651 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1700652 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1700653 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700654 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700655 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1700656 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700657 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700658 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700659 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700660 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700661 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700662 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700663 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700664 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700665 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700666 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700667 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700668 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700669 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700670 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700671 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700672 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700673 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700674 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700675 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1700676 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1700677 |  |  | Hamilton County | 2018-05-31
|  |  | 1700678 | Delaware |  | Yorktown | 2022-02-09 | PE
ROW
|  |  | 1700679 |  |  | Delaware County | -339679.2083
|  |  | 1700680 | Delaware |  | Delaware County | 2022-02-09 | PE
ROW
|  |  | 1700681 | Delaware |  | Delaware County | 2020-02-05 | CE
CN
|  |  | 1700682 |  |  | Delaware County | 2023-07-12
|  |  | 1700683 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1700684 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1700685 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1700686 | Clay |  | Indiana Department of Transportation | 2017-11-15 | CE
CN
|  |  | 1700687 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700688 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700689 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700690 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700691 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700692 |  |  | MPO - Cincinnati | -339679.2083
|  |  | 1700693 |  |  | Lawrenceburg | -339679.2083
|  |  | 1700694 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1700695 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1700696 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1700697 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1700698 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1700699 | Putnam |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700700 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700701 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700702 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700703 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700704 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700705 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700706 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700707 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1700708 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1700709 | St. Joseph |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1700710 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700711 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1700712 | Hamilton |  | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1700713 |  |  | Columbus | -339679.2083
|  |  | 1700714 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1700715 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1700716 |  |  | LaPorte Transporte | -339679.2083
|  |  | 1700717 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1700718 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1700719 |  |  | Columbus | -339679.2083
|  |  | 1700720 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700721 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700722 | Hamilton | CPS Acquisitions, LLC | Fishers | 2021-11-17 | CN
PE
ROW
|  |  | 1700723 |  | CPS Acquisitions, LLC | Fishers | 2022-02-09
|  |  | 1700724 | Clark |  | Clarksville | 2023-02-15 | ROW
|  |  | 1700725 | Clark |  | Clarksville | 2022-12-07 | PE
ROW
|  |  | 1700726 | Marion | KERAMIDA Environmental, Inc. | Speedway | 2018-12-12 | CE
CN
|  |  | 1700727 |  |  | New Albany | -339679.2083
|  |  | 1700728 | Hamilton |  | Westfield | 2020-07-08 | CE
CN
UT
|  |  | 1700729 | Hamilton |  | Westfield | 2021-08-11 | CE
CN
|  |  | 1700730 | Floyd |  | New Albany | 2022-03-09 | PE
|  |  | 1700731 | Hamilton |  | Hamilton County | 2021-08-11 | CE
CN
|  |  | 1700732 | Bartholomew |  | Bartholomew County | 2026-07-08 | PE
|  |  | 1700733 | Monroe |  | Monroe County | 2021-04-07 | CE
CN
|  |  | 1700734 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700735 | Monroe | Absolute Title Services, LLC | Bloomington | 2022-11-16 | ROW
|  |  | 1700736 | Monroe |  | Bloomington | 2020-04-01 | CN
PE
|  |  | 1700737 | Hancock |  | Hancock County | 2020-12-09 | CE
CN
|  |  | 1700738 | Hamilton | H. Stewart Kline & Associates, Inc. | Noblesville | 2021-11-17 | CN
|  |  | 1700739 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1700740 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1700741 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1700742 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1700743 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1700744 |  |  | Terre Haute | -339679.2083
|  |  | 1700745 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700746 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700747 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700748 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700749 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1700750 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1700751 | Delaware |  | Muncie | 2022-12-07 | PE
|  |  | 1700752 |  |  | Muncie | -339679.2083
|  |  | 1700753 |  |  | Muncie | -339679.2083
|  |  | 1700754 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2018-03-14 | CE
CN
|  |  | 1700755 | Allen |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1700756 |  |  | La Porte | -339679.2083
|  |  | 1700757 |  |  | La Porte | -339679.2083
|  |  | 1700758 | LaPorte |  | La Porte | 2019-05-09 | CE
CN
|  |  | 1700759 |  |  | La Porte | -339679.2083
|  |  | 1700760 |  |  | La Porte | 2022-03-09
|  |  | 1700761 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700762 |  |  | Columbus | -339679.2083
|  |  | 1700763 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700764 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700766 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700767 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700768 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700769 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700770 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700771 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700772 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700773 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700774 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700775 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700776 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700777 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700778 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700779 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700780 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700781 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700782 |  |  | MPO - Lafayette | -339679.2083
|  |  | 1700783 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700784 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700785 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700786 |  |  | MPO - Bloomington | -339679.2083
|  |  | 1700787 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1700788 | Floyd |  | Floyd County | 2022-07-13 | PE
|  |  | 1700789 | Johnson |  | Greenwood | 2020-10-07 | CE
CN
|  |  | 1700790 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1700791 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700792 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700793 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700794 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1700795 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1700796 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700797 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1700798 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1700799 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1700800 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2019-12-11
|  |  | 1700801 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1700802 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1700803 |  | CTLGroup | Indiana Department of Transportation | 2022-07-13
|  |  | 1700804 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1700805 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1700806 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1700807 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700808 |  | Fleis & VandenBrink Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1700809 | Henry | Dillabaugh, Inc. | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1700810 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1700811 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1700812 | Blackford | Boomerang Ventures, LLC | Indiana Department of Transportation | 2020-02-05 | RR
|  |  | 1700813 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1700814 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1700815 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1700816 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1700817 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700818 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700819 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
RR
|  |  | 1700820 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
RR
|  |  | 1700821 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
RR
|  |  | 1700822 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
RR
|  |  | 1700823 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700824 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700825 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1700826 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700827 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700828 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700829 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700830 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700831 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700832 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700833 | Marion |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1700834 | Marion |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1700835 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700836 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700837 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700838 | Marion |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700839 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700840 | Blackford |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700841 | Randolph |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700842 | Union |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700843 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1700844 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700845 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700846 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700847 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700848 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700849 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700850 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700851 | Delaware | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700852 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700853 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1700854 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1700855 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1700856 | Shelby |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700857 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700858 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700859 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700860 | Jay |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700861 | Henry |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700862 | Franklin |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700863 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700864 | Shelby |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700865 | Shelby |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700866 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1700867 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700868 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700869 | Rush |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700870 | Henry |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700871 | Hamilton | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1700872 | Hancock |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700873 | Hancock |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700874 | Jay |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700875 | Wayne |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1700876 | Marion |  | Indiana Department of Transportation | 2023-07-12 | CE
CN
PE
|  |  | 1700877 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1700878 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700879 | Marion |  | Indiana Department of Transportation | 2020-05-28 | CE
CN
PE
|  |  | 1700880 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700881 | Marion |  | Indiana Department of Transportation | 2020-05-28 | CE
CN
PE
|  |  | 1700882 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700883 | Marion |  | Indiana Department of Transportation | 2020-05-28 | CE
CN
PE
|  |  | 1700884 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700885 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1700886 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700887 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1700888 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700889 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1700890 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700891 | Wayne |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1700892 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700893 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700894 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1700895 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1700896 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1700897 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1700898 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700899 | Randolph |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1700900 | Randolph | Indiana Connect - a Joint Venture | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1700901 | Marion | DCD Consulting LLC | Indianapolis | 2020-10-07 | CE
CN
|  |  | 1700902 | Marion | DCD Consulting LLC | Indianapolis | 2020-10-07 | CE
CN
|  |  | 1700903 | Marion | DCD Consulting LLC | Indianapolis | 2021-11-17 | CE
CN
|  |  | 1700904 | Wayne |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1700905 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1700906 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1700907 | Marion | DCD Consulting LLC | Indianapolis | 2019-05-31 | CN
|  |  | 1700908 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700909 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700910 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700911 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700912 | Warrick |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700913 | Warrick |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700914 | Warrick |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700915 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1700916 | Warrick |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700917 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1700918 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700919 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700920 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700921 | Jay |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1700922 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700923 | Wayne |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1700924 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700925 | Marion | DCD Consulting LLC | Indianapolis | 2021-11-17 | CE
CN
|  |  | 1700926 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700927 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700928 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1700929 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1700930 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700931 |  | DCD Consulting LLC | Indianapolis | 2022-07-13
|  |  | 1700932 | Vanderburgh |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1700933 | Marion | DCD Consulting LLC | Indianapolis | 2020-10-07 | CE
CN
|  |  | 1700934 | Hamilton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700935 | Hamilton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1700936 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1700937 | Vanderburgh |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1700938 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
RR
|  |  | 1700939 | Howard |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1700940 | Posey |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1700941 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1700942 | Wayne |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1700943 | Hamilton |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1700944 | Greene |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1700945 | Tipton |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1700946 | Greene |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1700947 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 1700948 | Pike |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1700949 | Marion |  | Indiana Department of Transportation | 2020-08-13 | PE
|  |  | 1700950 | Delaware |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1700951 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700952 | Fayette |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1700953 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1700954 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700955 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1700956 | Gibson |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1700957 | Shelby |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700958 | Randolph |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700959 | Wayne |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1700960 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700961 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700962 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700963 | Greene |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1700964 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
RR
|  |  | 1700965 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
RR
|  |  | 1700966 | Henry |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1700967 | Hancock |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700968 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700969 | Knox |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1700970 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1700971 | Henry |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700972 | Henry |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1700973 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700974 | Monroe |  | Bloomington | 2019-12-11 | CE
CN
|  |  | 1700975 | Warrick |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1700976 | Monroe | Absolute Title Services, LLC | Bloomington | 2022-01-12 | CE
CN
|  |  | 1700977 | Vanderburgh |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1700978 | Dubois |  | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1700979 | Johnson | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-07-10 | CE
CN
|  |  | 1700980 | Knox |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1700981 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700982 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1700983 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1700984 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1700985 | Howard |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1700986 | Hancock |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1700987 | Jay |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1700988 | Hancock |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1700989 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1700990 | Hancock |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1700991 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1700992 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1700993 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700994 | Delaware | GS-IN P.C. | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700995 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1700996 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
RR
|  |  | 1700997 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700998 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1700999 | Madison |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701000 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1701001 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701002 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701005 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701006 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701007 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701008 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701009 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1701010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701012 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701015 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701018 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701019 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701020 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701021 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701022 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701023 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701024 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701025 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701026 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701027 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1701028 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701029 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701030 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1701031 |  |  | MPO - Kokomo | -339679.2083
|  |  | 1701032 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701033 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701034 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701036 |  |  | Indian Heights | -339679.2083
|  |  | 1701037 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701038 | Wayne |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 1701039 | Martin |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701040 | Wayne |  | Indiana Department of Transportation | 2021-05-31 | PE
RR
|  |  | 1701041 | Martin |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701042 | Martin |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701043 | Hancock | Great Lakes Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701044 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1701045 |  |  | MPO - Northwest | -339679.2083
|  |  | 1701046 |  |  | MPO - Northwest | -339679.2083
|  |  | 1701047 |  |  | MPO - Northwest | -339679.2083
|  |  | 1701048 | Orange |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701049 | Henry |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1701050 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1701051 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701052 | Henry |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1701053 | Martin |  | Indiana Department of Transportation | 2022-02-09 | PE
UT
|  |  | 1701054 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1701055 | Perry |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1701056 | Pulaski |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1701057 | Lake | Matt L. Nepote, MAI | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701058 | Warrick |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701059 | St. Joseph |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1701060 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1701061 | Bartholomew |  | Columbus | -339679.2083 | PE
|  |  | 1701062 | Bartholomew |  | Columbus | -339679.2083 | PE
|  |  | 1701063 | Bartholomew |  | Columbus | 2018-05-30 | CE
CN
PE
|  |  | 1701064 | Jasper |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1701065 | Starke |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701066 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701067 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2020-12-09 | PE
RR
|  |  | 1701068 | Fayette | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1701069 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1701070 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701071 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701072 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701073 | Starke |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1701074 | Starke |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1701075 | Jasper |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701076 | Wayne |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701077 | Jay |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701078 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701079 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1701080 | Cass |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701081 | Lake |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701082 | St. Joseph |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1701083 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1701084 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701085 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701086 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1701087 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1701088 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1701089 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1701090 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1701091 | Clark |  | Indiana Department of Transportation | 2023-09-13 | PE
|  |  | 1701092 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1701093 | Floyd |  | Indiana Department of Transportation | 2023-09-13 | PE
|  |  | 1701094 | Clark |  | Indiana Department of Transportation | 2023-09-13 | PE
|  |  | 1701095 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1701096 | Shelby |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1701097 | LaPorte |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701098 |  | DCD Consulting LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1701099 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1701100 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-11-10 | PE
|  |  | 1701101 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2019-05-09
|  |  | 1701102 | Lake |  | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1701103 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1701104 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701105 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1701106 | Cass |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701107 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701108 | Lake |  | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1701109 | Lake |  | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1701110 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701111 | Carroll |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701112 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701113 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701114 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
RR
|  |  | 1701115 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701116 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701117 | Starke |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
RR
|  |  | 1701118 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701119 | Fulton |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701120 | St. Joseph |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701121 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
RR
|  |  | 1701122 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1701123 | Newton |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701124 | Carroll |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701125 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701126 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701127 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701128 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1701129 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1701130 | Jasper |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701131 | Jasper |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701132 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701133 | Cass |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1701134 | Lake |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701135 | White |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701136 | Fulton |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701137 | Pulaski |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1701138 | Cass |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1701139 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1701140 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-11-10
|  |  | 1701141 | Porter |  | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1701142 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1701143 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1701144 | Pulaski |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1701145 | Johnson |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1701146 | Clinton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701147 | White |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1701148 | Jasper |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1701149 | Porter |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1701150 | Johnson |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1701151 | Carroll |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1701152 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1701153 | Jasper |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701155 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1701156 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1701157 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1701158 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1701159 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1701160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701161 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1701162 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1701163 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1701164 | Carroll |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1701165 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1701166 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1701167 |  | Consolidated Test Company | Indiana Department of Transportation | 2020-02-05
|  |  | 1701168 | Bartholomew |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1701169 | Jackson |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1701170 | Brown |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1701171 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701172 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701173 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1701174 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701175 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701176 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701177 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701178 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701179 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701180 | Bartholomew |  | Indiana Department of Transportation | 2019-02-06 | CE
|  |  |  | Jackson |  | Indiana Department of Transportation | 2019-02-06 | CN
|  |  | 1701181 | Rush |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1701182 | Decatur |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1701183 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701184 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701185 | Shelby |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701186 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701187 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701188 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701189 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701190 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701191 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701192 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701193 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701194 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701195 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701196 |  |  | MPO - Indianapolis | -339679.2083
|  |  | 1701197 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1701198 | Shelby |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701199 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701200 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701201 | Greene |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
PE
|  |  | 1701202 | Posey |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1701203 | Floyd |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1701204 | Allen |  | Indiana Department of Transportation | 2018-07-11 | CE
CN
PE
|  |  | 1701205 |  | ASA Land Surveying | Indiana Department of Transportation | 2022-03-09
|  |  | 1701206 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1701207 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1701208 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
RR
|  |  | 1701209 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701210 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701211 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701212 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701213 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1701214 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1701215 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1701216 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701217 | Grant |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701218 | Allen |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701219 | Allen |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701220 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701221 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701222 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701223 |  | CMF Engineering, Inc. | Indiana Department of Transportation | 2019-11-14
|  |  | 1701224 |  | CMF Engineering, Inc. | Indiana Department of Transportation | 2019-11-14
|  |  | 1701225 | Allen |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701226 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701227 | Steuben |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1701228 | Martin |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1701229 | Steuben |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1701230 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701231 | Gibson | HNTB Indiana, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
|  |  |  | Pike | HNTB Indiana, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
RR
|  |  | 1701232 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701233 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701234 | Huntington |  | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1701235 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701236 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701237 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701238 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701239 | Pike |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1701240 | Steuben |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701241 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701242 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701243 | Franklin |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701244 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701245 | Dekalb |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
RR
|  |  | 1701246 | Harrison |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1701247 | Dekalb |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
PE
|  |  | 1701248 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701249 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701250 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701251 | Jackson | Earth Exploration, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1701252 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1701253 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701254 | Allen |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701255 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1701256 | Allen |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701257 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701258 | Dekalb |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701259 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1701260 | Dekalb |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701261 | Adams | Bidinfo | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1701262 | Adams | Bidinfo | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1701263 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701264 | Huntington |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1701265 | Allen | D & D Consulting Services, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701266 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701267 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1701268 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701269 | Dekalb |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701270 | Dekalb |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701271 | Grant |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1701272 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701273 | Franklin |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701274 | Wabash |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1701275 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701276 | Miami |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1701277 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701278 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701279 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1701280 | Miami |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1701281 | Miami |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1701282 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1701283 | Grant |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1701284 | Blackford |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1701285 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701286 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701287 | Kosciusko |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701288 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 1701289 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 1701290 | Jasper |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1701291 | Whitley |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701292 | Miami |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1701293 | Jasper |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1701294 | Noble |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701295 | Grant | Dave Helton & Associates, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1701296 | Adams |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1701297 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701298 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701299 | Whitley |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701300 | Adams |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1701301 | Adams | Bidinfo | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1701302 | Huntington |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1701303 | Wells |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701304 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701305 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701306 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701307 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701308 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1701309 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701310 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 1701311 | Allen |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1701312 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701313 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701314 | Allen |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701315 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701316 | Grant |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1701317 | St. Joseph |  | Indiana Department of Transportation | 2021-11-17 | PE
|  |  | 1701318 | Grant |  | Indiana Department of Transportation | 2018-09-12 | CE
CN
|  |  | 1701319 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701320 | Allen |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701321 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701322 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701323 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2024-07-01 | PE
|  |  | 1701324 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701325 | Bartholomew |  | Columbus | 2022-12-07 | PE
|  |  | 1701326 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701327 |  |  | Columbus | 2019-05-31
|  |  | 1701328 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701329 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701330 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1701331 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2021-11-17 | PE
|  |  | 1701332 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701333 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1701334 | Porter |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1701335 | Porter |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1701336 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1701337 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1701338 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1701339 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1701340 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1701341 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701342 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1701343 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2020-03-04 | PE
RR
|  |  | 1701344 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1701345 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13 | CE
CN
|  |  | 1701346 | Wabash |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1701347 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1701348 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701349 | Miami |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1701350 | Elkhart |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  | 1701351 | Wabash |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1701352 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701353 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701354 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701355 | Wells |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1701356 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1701357 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701358 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701359 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701360 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701361 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1701362 | Allen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1701363 | Floyd |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1701364 | Johnson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  |  | Shelby |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1701365 | Jackson |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
PE
|  |  | 1701366 |  | ABt SRBI | Indiana Department of Transportation | 2020-09-02
|  |  | 1701367 | Johnson |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701368 | Johnson |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701369 | Huntington |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1701370 | Noble |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701371 | Noble |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701372 | Elkhart | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1701373 | Grant |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1701374 | Grant |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1701375 | Allen |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1701376 | Allen |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1701377 |  |  | Kokomo | -339679.2083
|  |  | 1701378 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1701379 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1701380 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2019-10-09 | CE
CN
PE
|  |  | 1701381 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1701382 | Noble | Bartlett & Associates, Inc. | Indiana Department of Transportation | 2022-03-09 | PE
RR
|  |  | 1701383 | Kosciusko |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1701384 | Miami |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1701385 | Kosciusko |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701386 | Kosciusko |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701387 | Dekalb |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701388 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1701389 | Kosciusko |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701390 | Kosciusko |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701391 | Grant |  | Indiana Department of Transportation | 2021-10-14 | CN
PE
|  |  | 1701392 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1701393 | Dekalb |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1701394 | Adams |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1701395 | Grant |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1701396 | Kosciusko |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701397 | Kosciusko |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701398 | Grant |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1701399 | Fountain |  | Indiana Department of Transportation | 2019-10-09 | PE
|  |  | 1701400 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1701401 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1701402 | Huntington |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1701403 | Boone | Lamac Engineering Company | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1701404 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1701405 | Clay |  | Indiana Department of Transportation | 2020-04-01 | RR
|  |  | 1701406 | Allen |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1701407 | Vermillion |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1701408 | Allen |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1701409 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1701410 | Knox |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1701411 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2020-02-05
|  |  | 1701412 | Putnam |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1701413 | Parke |  | Indiana Department of Transportation | 2019-01-16 | CE
PE
|  |  |  | Vermillion |  | Indiana Department of Transportation | 2019-01-16 | CN
|  |  | 1701414 | Tippecanoe |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
RR
|  |  | 1701415 | Starke |  | Indiana Department of Transportation | 2022-02-09 | RR
|  |  | 1701416 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1701417 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1701418 | Tippecanoe |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
RR
|  |  | 1701419 | Tippecanoe |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1701420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701421 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701422 | Lake |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1701423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701424 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1701425 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1701426 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701427 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701428 | Jackson |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701429 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701430 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1701431 | Jackson |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701432 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701433 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1701434 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701435 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701436 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701437 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701438 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701439 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701440 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1701441 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1701442 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-11-17 | PE
|  |  | 1701443 | Porter | American Commercial Title & Escrow | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701444 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701445 | Porter |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1701446 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701447 | Spencer | Appraisers, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1701448 | Porter |  | Indiana Department of Transportation | 2021-11-17 | PE
|  |  | 1701449 | Clark |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701450 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1701451 | Fulton | InfoTech | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701452 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1701453 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701454 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701455 | Jefferson |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1701456 | Vanderburgh |  | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1701457 | Jefferson |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1701458 | Putnam |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1701459 | Dearborn |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1701460 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701461 |  |  | Allen County | -339679.2083
|  |  | 1701462 |  |  | Allen County | -339679.2083
|  |  | 1701463 |  |  | Allen County | -339679.2083
|  |  | 1701464 |  |  | Allen County | -339679.2083
|  |  | 1701465 | Dearborn |  | Indiana Department of Transportation | 2021-09-15 | CE
CN
PE
|  |  | 1701466 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1701467 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1701468 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1701469 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1701470 | Vigo |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1701471 | Vigo |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1701472 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2021-11-17 | PE
|  |  | 1701473 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1701474 | Starke |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701475 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701476 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701477 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701478 | Jasper |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701479 | Starke |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701480 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701481 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701482 | Porter |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701483 | Harrison |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1701484 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1701485 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1701486 |  | M-E Companies, Inc. | Indiana Department of Transportation | 2018-05-10
|  |  | 1701487 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1701488 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701489 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1701490 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1701491 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701492 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701493 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701494 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701495 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701496 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701497 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701498 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701499 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701500 | Switzerland |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701501 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701502 | Jennings |  | Indiana Department of Transportation | 2022-02-09 | PE
UT
|  |  | 1701503 | Washington |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701504 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 1701505 | Newton |  | Indiana Department of Transportation | 2022-02-09 | PE
RR
|  |  | 1701506 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701507 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1701508 | Jasper |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701509 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1701510 | Newton |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701511 | Jackson |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1701512 | Newton |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701513 | St. Joseph | Integrated Environmental Solutions, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701514 | Jasper |  | Indiana Department of Transportation | 2019-03-06 | CE
|  |  |  | Newton |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
PE
|  |  | 1701515 | Ohio |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701516 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1701517 | Harrison |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
PE
|  |  | 1701518 | Harrison |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1701519 | Porter | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1701520 | Lake |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1701521 | Porter | Land Title Service Company, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1701522 | LaPorte |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1701523 | Lake | Edwards and Kelcey | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701524 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1701525 | LaPorte | Dennison and Company | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1701526 | St. Joseph |  | Indiana Department of Transportation | 2019-08-07 | PE
|  |  | 1701527 | LaPorte |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1701528 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701529 | Hancock | Great Lakes Engineering, Inc. | New Palestine | 2020-10-07 | CE
CN
|  |  | 1701530 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2020-12-09
|  |  | 1701531 | White |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
RR
|  |  | 1701532 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1701533 | Newton |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
RR
|  |  | 1701534 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2021-02-10
|  |  | 1701535 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1701536 | Cass |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1701537 | Marshall |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1701538 | St. Joseph |  | Indiana Department of Transportation | 2021-11-17 | PE
|  |  | 1701539 |  | Dodd Title Corporation | Indiana Department of Transportation | 2016-02-17
|  |  | 1701540 |  | Dodd Title Corporation | Indiana Department of Transportation | 2016-02-17
|  |  | 1701541 | Jasper |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1701542 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1701543 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1701544 | White |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701545 | Fountain |  | Indiana Department of Transportation | 2019-12-11 | CN
PE
|  |  |  | Warren |  | Indiana Department of Transportation | 2019-12-11 | CE
|  |  | 1701546 | Clinton |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1701547 | Fountain | AECON, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
|  |  |  | Warren | AECON, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1701548 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1701549 | Tippecanoe |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701550 | White |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701551 | Hendricks |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701552 | Vermillion |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
PE
|  |  | 1701553 | Clay |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701554 | Montgomery |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701555 | Montgomery |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701556 | Boone |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
|  |  | 1701557 | Montgomery |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1701558 | Montgomery |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1701559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701560 | Warren |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1701561 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1701562 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1701563 | Vermillion |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  |  | Vigo |  | Indiana Department of Transportation | 2021-05-05 | CE
RR
|  |  | 1701564 | Benton |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1701565 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1701566 |  | All About Pavements, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1701567 | Benton | CDM Smith, Inc. | Indiana Department of Transportation | 2022-01-12 | PE
RR
|  |  | 1701568 | Various |  | Indiana Department of Transportation | 2020-05-31 | PE
|  |  | 1701569 | Vigo |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701570 | Putnam |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701571 | Benton |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1701572 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1701573 |  |  | South Bend Transit | -339679.2083
|  |  | 1701574 |  |  | South Bend Transit | -339679.2083
|  |  | 1701575 |  |  | South Bend Transit | -339679.2083
|  |  | 1701576 | Huntington |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1701577 | Dubois | CMF Engineering, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1701578 | Dubois | Aarcher, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1701579 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701580 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 1701581 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1701582 | Montgomery |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701583 | Clinton |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701584 | Boone |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701585 | Franklin |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1701586 | Hendricks | All About Pavements, Inc. | Brownsburg | 2021-10-14 | CE
CN
|  |  | 1701587 | Clay |  | Indiana Department of Transportation | 2021-12-08 | CN
PE
|  |  | 1701588 | Hendricks | Kieser Consulting, LLC | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1701589 | Vermillion |  | Indiana Department of Transportation | 2024-07-10 | PE
|  |  | 1701590 |  | All About Pavements, Inc. | Brownsburg | 2022-07-13
|  |  | 1701591 |  | Madison Milton Ferry LLC | Indiana Department of Transportation | 2022-04-06
|  |  | 1701592 | White |  | Indiana Department of Transportation | 2022-05-31 | PE
|  |  | 1701593 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1701594 | Montgomery |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701595 | Owen |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1701596 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1701597 | Montgomery |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1701598 | Various |  | Indiana Department of Transportation | 2022-01-12 | PE
|  |  | 1701599 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701600 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701601 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701602 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701603 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701604 |  | Infrastructure Engineering, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1701605 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701606 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701607 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1701608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701609 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1701610 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1701611 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1701612 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1701613 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1701614 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1701615 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1702038 |  | III FFC | Indiana Department of Transportation | 2016-12-14
|  |  | 1702039 |  | III FFC | Indiana Department of Transportation | 2016-12-14
|  |  | 1702040 |  | CGI | Indiana Department of Transportation | 2016-12-14
|  |  | 1702041 |  | Home Equity Appraisals | Indiana Department of Transportation | -339679.2083
|  |  | 1702042 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1702043 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1702044 | Henry |  | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1702045 | Crawford |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1702046 | Henry |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1702047 | Pike |  | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1702048 | Henry |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1702049 | Henry |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1702050 | Owen |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
PE
|  |  | 1702051 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1702052 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1702053 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1702054 | Crawford |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1702055 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1702056 | Knox |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702057 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1702058 | Posey |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1702059 | Daviess |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1702060 | Perry |  | Indiana Department of Transportation | 2020-04-01 | PE
|  |  | 1702061 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1702062 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702063 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702064 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1702065 | Wayne |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1702066 | Vanderburgh | CGI | Indiana Department of Transportation | 2023-11-15 | PE
|  |  | 1702067 | Dubois |  | Indiana Department of Transportation | 2021-09-15 | CN
PE
|  |  | 1702068 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1702069 | Daviess |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1702070 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1702071 | Warrick |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1702072 | Warrick |  | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1702073 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702074 |  |  | Indiana Department of Natural Resources | 2018-03-14
|  |  | 1702075 |  |  | Indiana Department of Natural Resources | 2018-03-14
|  |  | 1702076 |  |  | Indiana Department of Natural Resources | 2018-03-14
|  |  | 1702077 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702078 | Tippecanoe |  | Indiana Department of Transportation | 2019-11-20 | CE
CN
|  |  | 1702079 | Tippecanoe |  | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1702080 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1702081 | Fulton |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1702082 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1702083 | Howard |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1702084 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1702085 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1702086 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702087 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702088 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702089 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702090 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1702091 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702092 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702093 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1702094 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702095 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702096 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702097 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702098 | Johnson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702099 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702100 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2022-02-09 | PE
ROW
UT
|  |  | 1702101 | Various |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1702102 | Various |  | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1702103 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1702104 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1702105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702106 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702107 | Bartholomew | Associated Right-of-Way Services, Inc. | Columbus | 2020-05-07 | CE
CN
ROW
|  |  | 1702108 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702109 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702110 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702111 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702112 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1702113 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702114 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702115 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702116 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702118 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702119 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  |  | Monroe |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1702120 | Hendricks |  | Avon | 2017-12-13 | CE
CN
|  |  | 1702121 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1702122 | Scott |  | Indiana Department of Transportation | 2019-05-31 | RR
|  |  | 1702123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702124 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702125 | Various |  | Indiana Department of Transportation | 2018-05-10 | CE
CN
PE
|  |  | 1702126 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702127 | Hamilton | Another Test Company | Carmel | 2020-05-07 | CE
CN
|  |  | 1702128 | Hamilton | Another Test Company | Carmel | 2020-05-07 | CE
CN
|  |  | 1702129 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 1702130 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1702131 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-05-31
|  |  | 1702132 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702133 | Hendricks | AFRAM Group, Incorporated | Avon | 2020-07-08 | CE
CN
|  |  | 1702134 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702135 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702136 | Vigo | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | 2019-01-16 | CE
CN
PE
|  |  | 1702137 | Tippecanoe |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1702138 | Benton |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1702139 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702140 |  |  | Harrison County | 2018-04-11
|  |  | 1702141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702142 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702143 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1702144 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1702145 | Porter |  | Valparaiso | 2017-10-12 | CN
|  |  | 1702146 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1702147 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
UT
|  |  | 1702148 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702149 | Hamilton |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1702150 |  | Leitner and Associates, Inc. | Valparaiso | 2024-03-13
|  |  | 1702151 |  | Leitner and Associates, Inc. | Valparaiso | 2022-09-14
|  |  | 1702152 | St. Joseph |  | St. Joseph County | 2020-12-09 | CN
|  |  | 1702153 | St. Joseph |  | St. Joseph County | 2020-12-09 | CN
|  |  | 1702154 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1702155 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
PE
|  |  | 1702156 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702157 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1702158 | Lake |  | Gary | 2020-11-10 | CE
CN
PE
|  |  | 1702159 | Lake |  | Lake County | -339679.2083 | PE
|  |  | 1702160 |  | Another Test Company | Indiana Department of Transportation | 2016-02-17
|  |  | 1702161 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702162 |  | Advantage Appraisal Services | Indiana Department of Transportation | 2017-01-19
|  |  | 1702163 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702164 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702165 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702166 |  |  | Porter | 2010-11-10
|  |  | 1702167 |  |  | Porter | 2010-11-10
|  |  | 1702168 | Marshall |  | Plymouth | 2018-02-07 | CN
|  |  | 1702169 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1702170 |  | Landmark Archaeological & Environmental Services, Inc. | Indiana Department of Transportation | 2018-05-10
|  |  | 1702171 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1702172 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702173 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702175 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702176 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702178 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702181 | Morgan |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1702182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702183 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702187 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702188 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702191 | Harrison | B. L. A., Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1702192 | Jennings | Loftus Engineering, Inc. | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1702193 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 1702194 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 1702195 |  |  | Indiana Department of Transportation | 2010-07-09
|  |  | 1702196 |  |  | Indiana Department of Transportation | 2010-07-09
|  |  | 1702197 | Madison |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
PE
|  |  | 1702198 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1702199 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702200 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1702201 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2016-02-17
|  |  | 1702202 |  |  | Indiana Department of Transportation | 2016-02-17
|  |  | 1702203 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1702204 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1702205 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702206 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702207 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1702208 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1702209 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1702210 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2018-09-12 | CE
CN
PE
|  |  | 1702211 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702212 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 1702213 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 1702214 | Marion | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 1702215 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702216 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2020-01-15 | CE
CN
ROW
|  |  | 1702217 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702218 | Crawford |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
PE
|  |  | 1702219 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702221 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702222 | Various |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702223 | Martin | EcoTec, Inc. | Indiana Department of Transportation | 2024-02-14 | PE
|  |  | 1702224 | Johnson |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1702225 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1702226 | Various |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1702227 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702228 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1702229 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702230 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702231 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702232 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702233 |  | Dummy Consulting Firm | Lake Station | 2018-05-31
|  |  | 1702234 |  |  | Benton County | 2018-05-31
|  |  | 1702235 |  |  | Boone County | -339679.2083
|  |  | 1702236 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702237 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702238 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702239 |  | AECON, Inc. | Attica | -339679.2083
|  |  | 1702240 |  |  | Clinton | -339679.2083
|  |  | 1702241 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702242 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702243 |  | BA Martin Architects, PC | Covington | -339679.2083
|  |  | 1702244 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 1702245 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 1702246 |  |  | Lafayette | -339679.2083
|  |  | 1702247 |  | E.J. Breneman, LP | Lebanon | 2018-05-31
|  |  | 1702248 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 1702249 |  |  | West Lafayette | -339679.2083
|  |  | 1702250 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702251 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702252 | Various |  | Indiana Department of Transportation | 2018-05-31 | PE
|  |  | 1702253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702254 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1702255 | Floyd |  | Indiana Department of Transportation | 2020-11-13 | CE
CN
PE
RR
|  |  | 1702256 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702257 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1702258 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1702259 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1702260 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1702261 |  | Martinez Corporation | Indiana Department of Transportation | 2017-01-19
|  |  | 1702262 | LaPorte | Douglass Environmental Services, Inc. | La Porte | -339679.2083 | PE
|  |  | 1702263 |  |  | Clay County | 2018-05-31
|  |  | 1702264 |  |  | Clinton County | -339679.2083
|  |  | 1702265 |  |  | Fountain County | -339679.2083
|  |  | 1702266 |  |  | Hendricks County | 2018-05-31
|  |  | 1702267 |  | DLZ Indiana, LLC | Jamestown | -339679.2083
|  |  | 1702268 |  |  | Montgomery County | -339679.2083
|  |  | 1702269 |  |  | Owen County | -339679.2083
|  |  | 1702270 |  |  | Parke County | 2018-05-31
|  |  | 1702271 |  |  | Putnam County | -339679.2083
|  |  | 1702272 | Various |  | Indiana Department of Natural Resources | -339679.2083 | PE
|  |  | 1702273 | Various |  | Indiana Department of Natural Resources | 2018-05-31 | CN
|  |  | 1702274 | Various |  | Indiana Department of Natural Resources | 2018-05-31 | CN
|  |  | 1702275 | Miami |  | Indiana Department of Natural Resources | 2020-05-31 | CN
PE
ROW
|  |  | 1702276 | LaPorte |  | Indiana Department of Natural Resources | 2019-05-31 | CN
PE
ROW
|  |  | 1702277 | Grant |  | Indiana Department of Natural Resources | 2019-05-31 | CN
PE
ROW
|  |  | 1702278 | Shelby |  | Indiana Department of Natural Resources | 2019-05-31 | CN
PE
ROW
|  |  | 1702279 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1702280 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1702281 | LaPorte |  | La Porte | 2018-05-10 | CE
CN
|  |  | 1702282 |  |  | La Porte | -339679.2083
|  |  | 1702283 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702284 |  |  | Indiana Department of Transportation | 2018-03-14
|  |  | 1702285 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702286 | Marion |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1702287 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1702288 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1702289 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702290 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 1702291 |  | III FFC | Indiana Department of Transportation | -339679.2083
|  |  | 1702292 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2018-01-18 | CE
CN
PE
|  |  | 1702293 |  | AV Consulting Engineers, Inc. | Bicknell | 2018-05-31
|  |  | 1702294 |  |  | Boonville | 2018-05-31
|  |  | 1702295 |  | CGI | Evansville | 2018-05-31
|  |  | 1702296 |  |  | Huntingburg | 2018-05-31
|  |  | 1702297 |  |  | Jasper | 2018-05-31
|  |  | 1702298 |  |  | Linton | -339679.2083
|  |  | 1702299 |  | EcoTec, Inc. | Loogootee | 2018-05-31
|  |  | 1702300 |  |  | Mitchell | 2018-05-31
|  |  | 1702301 | Perry |  | Indiana Department of Transportation | 2019-08-21 | CE
CN
PE
|  |  | 1702302 |  | GRL Engineers, Inc. | Mount Vernon | 2018-05-31
|  |  | 1702303 |  | HNTB Indiana, Inc. | Oakland City | 2018-05-31
|  |  | 1702304 |  | III FFC | Princeton | 2018-05-31
|  |  | 1702305 |  | Infrastructure Engineering, Inc. | Rockport | 2018-05-31
|  |  | 1702306 |  |  | Sullivan | 2018-05-31
|  |  | 1702307 |  |  | Tell City | 2018-05-31
|  |  | 1702308 |  | Louis Joyner, Architect | Vincennes | 2018-05-31
|  |  | 1702309 |  |  | Washington | 2018-05-31
|  |  | 1702310 |  |  | Daviess County | 2018-05-31
|  |  | 1702311 |  |  | Dubois County | 2018-05-31
|  |  | 1702312 |  |  | Gibson County | 2018-05-31
|  |  | 1702313 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702314 |  |  | Greene County | 2018-05-31
|  |  | 1702315 |  |  | Knox County | 2018-05-31
|  |  | 1702316 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1702317 |  |  | Lawrence County | 2018-05-31
|  |  | 1702318 |  |  | Lawrence County | 2018-05-31
|  |  | 1702319 |  |  | Martin County | 2018-05-31
|  |  | 1702320 |  |  | Orange County | 2018-05-31
|  |  | 1702321 |  |  | Perry County | 2018-05-31
|  |  | 1702322 |  |  | Pike County | 2018-05-31
|  |  | 1702323 |  |  | Posey County | 2018-05-31
|  |  | 1702324 | Vermillion |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1702325 | Dubois |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1702326 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702327 |  |  | Spencer County | 2018-05-31
|  |  | 1702328 |  |  | Sullivan County | 2018-05-31
|  |  | 1702329 |  | Alliance Environmental Group, Inc. | Bruceville | 2018-05-31
|  |  | 1702330 |  | Alliance Environmental Group, Inc. | Bruceville | -339679.2083
|  |  | 1702331 |  | Americas Engineers, Inc. | Cannelburg | -339679.2083
|  |  | 1702332 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702333 |  |  | Tippecanoe County | -339679.2083
|  |  | 1702334 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702335 |  | Appraisers, Inc. | Chrisney | 2018-05-31
|  |  | 1702336 |  | Appraisers, Inc. | Chrisney | -339679.2083
|  |  | 1702337 |  | Beals-Moore & Associates, Inc. | Dale | 2018-05-31
|  |  | 1702338 |  |  | Darmstadt | 2018-05-31
|  |  | 1702339 |  | Bonar Group, LLC | Dugger | 2018-05-31
|  |  | 1702340 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | -339679.2083
|  |  | 1702341 |  | CBRE, Inc. | Elnora | 2018-05-31
|  |  | 1702342 |  | CHA, Inc. | Farmersburg | 2018-05-31
|  |  | 1702343 |  | CMF Engineering, Inc. | Ferdinand | 2018-05-31
|  |  | 1702344 |  | CSR Engineering, Inc. | Fort Branch | -339679.2083
|  |  | 1702345 |  |  | French Lick | 2018-05-31
|  |  | 1702346 |  | CivCon Services, Inc. | Gentryville | 2018-05-31
|  |  | 1702347 |  | Clark Dietz, Inc. | Grandview | 2018-05-31
|  |  | 1702348 |  | Coor Consulting | Haubstadt | 2018-05-31
|  |  | 1702349 |  | D L Savage Engineering, Inc. | Hymera | -339679.2083
|  |  | 1702350 |  | Dan Moore Real Estate Services, Inc. | Jasonville | 2018-05-31
|  |  | 1702351 |  | Eilts Consulting Services | Lynnville | 2018-05-31
|  |  | 1702352 |  | Elizabeth Niemann & Associates, Inc. | Lyons | 2018-05-31
|  |  | 1702353 |  | Fanning Howey Associates | Merom | 2018-05-31
|  |  | 1702354 |  | Fosse & Associates Architects, Inc. | Monroe City | 2018-05-31
|  |  | 1702355 |  | Frost Engineering & Consulting Company | Montgomery | 2018-05-31
|  |  | 1702356 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1702357 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1702358 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2018-02-07
|  |  | 1702359 |  | Global Land Surveying, LLC | New Harmony | -339679.2083
|  |  | 1702360 |  |  | Newburgh | 2018-05-31
|  |  | 1702361 |  |  | Newburgh | 2018-05-31
|  |  | 1702362 |  |  | Odon | 2018-05-31
|  |  | 1702363 |  | Hagerty Engineering, Inc. | Oolitic | 2018-05-31
|  |  | 1702364 |  | Hannum, Wagle & Cline Engineering | Orleans | 2018-05-31
|  |  | 1702365 |  |  | Indiana Department of Transportation | 2019-01-23
|  |  | 1702366 |  | Harvard Title Searching | Owensville | 2018-05-31
|  |  | 1702367 |  |  | Indiana Department of Transportation | 2018-02-07
|  |  | 1702368 |  | Hazeltine & Associates, Inc. | Paoli | 2018-05-31
|  |  | 1702369 |  | Heritage Engineering, LLC | Patoka | 2018-05-31
|  |  | 1702370 |  |  | Sandborn | 2018-05-31
|  |  | 1702371 |  | JJR, LLC | Santa Claus | 2018-05-31
|  |  | 1702372 |  | Jeffrey P. French & Associates Land Surveying | Shelburn | 2018-05-31
|  |  | 1702373 |  | Landmark Engineering Group, Inc. | Troy | 2018-05-31
|  |  | 1702374 |  | Metropolitan Title of Indiana, LLC | Worthington | 2018-05-31
|  |  | 1702375 |  | CGI | Vanderburgh County | -339679.2083
|  |  | 1702376 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2018-05-31
|  |  | 1702377 |  | Dummy Consulting Firm Too | Lakeville | -339679.2083
|  |  | 1702378 | Orange |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1702379 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702380 |  |  | Vanderburgh County | -339679.2083
|  |  | 1702381 |  |  | Warrick County | 2018-05-31
|  |  | 1702382 |  |  | Advance | -339679.2083
|  |  | 1702383 |  |  | Amo | -339679.2083
|  |  | 1702384 |  |  | Avon | 2018-05-31
|  |  | 1702385 |  |  | Bainbridge | -339679.2083
|  |  | 1702386 |  |  | Battle Ground | 2018-05-31
|  |  | 1702387 |  |  | Bloomingdale | 2018-05-31
|  |  | 1702388 |  |  | Boswell | 2018-05-31
|  |  | 1702389 |  |  | Brownsburg | -339679.2083
|  |  | 1702390 |  |  | Carbon | -339679.2083
|  |  | 1702391 |  |  | Clayton | 2018-05-31
|  |  | 1702392 | Hancock |  | Hancock County | 2019-03-06 | CE
CN
|  |  | 1702393 | Various |  | Indiana Department of Transportation | 2018-05-31 | CN
|  |  | 1702394 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702395 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702396 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702397 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1702398 |  |  | Bartholomew County | -339679.2083
|  |  | 1702399 |  |  | Aurora | -339679.2083
|  |  | 1702400 |  | AEROCON Photogrammetric Services, Inc. | Austin | -339679.2083
|  |  | 1702401 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 1702402 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 1702403 |  | Dynasty Group, Inc. | Lawrenceburg | -339679.2083
|  |  | 1702404 |  |  | New Albany | -339679.2083
|  |  | 1702405 |  | Associated Right-of-Way Services, Inc. | Columbus | -339679.2083
|  |  | 1702406 |  | Casteel Real Estate | Franklin | -339679.2083
|  |  | 1702407 |  | Casteel Real Estate | Franklin | -339679.2083
|  |  | 1702408 |  | Engineering Resources, Inc. | Madison | -339679.2083
|  |  | 1702409 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1702410 |  | Commonwealth Engineers, Inc. | Greenwood | -339679.2083
|  |  | 1702411 |  | CDM Smith, Inc. | Fowler | 2018-05-31
|  |  | 1702412 |  | Commonwealth Engineers, Inc. | Greenwood | -339679.2083
|  |  | 1702413 |  | EnviroScience, Inc. | Martinsville | -339679.2083
|  |  | 1702414 |  |  | North Vernon | -339679.2083
|  |  | 1702415 |  |  | North Vernon | -339679.2083
|  |  | 1702416 |  | Indiana Search Technologies | Rising Sun | -339679.2083
|  |  | 1702417 |  | JCI Bridge Group, Inc. | Salem | -339679.2083
|  |  | 1702418 |  |  | Scottsburg | -339679.2083
|  |  | 1702419 | Clark | Cornerstone Civil Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Scott | Cornerstone Civil Group, LLC | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1702420 |  | Jacobs Pannicke Architects, Inc. | Sellersburg | -339679.2083
|  |  | 1702421 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1702422 |  |  | Dearborn County | -339679.2083
|  |  | 1702423 |  |  | Decatur County | -339679.2083
|  |  | 1702424 |  |  | Floyd County | -339679.2083
|  |  | 1702425 |  |  | Jennings County | -339679.2083
|  |  | 1702426 |  |  | Johnson County | -339679.2083
|  |  | 1702427 |  |  | St. Joseph County | -339679.2083
|  |  | 1702428 |  | 40th Parallel Surveying, LLC | Albany | 2018-05-31
|  |  | 1702429 |  |  | Howard County | 2018-05-31
|  |  | 1702430 |  |  | Madison County | -339679.2083
|  |  | 1702431 |  | J. H. Rudolph & Co., Inc. | Royal Center | -339679.2083
|  |  | 1702432 | Vanderburgh |  | Vanderburgh County | 2019-05-31 | CN
|  |  | 1702433 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2018-05-31
|  |  | 1702434 |  | ACME | Arcadia | -339679.2083
|  |  | 1702435 |  | ASC Group, Inc. | Beech Grove | 2018-05-31
|  |  | 1702436 |  | Another Test Company | Carmel | 2018-05-31
|  |  | 1702437 |  |  | Carthage | 2018-05-31
|  |  | 1702438 |  | Appraisals Unlimited of Indiana, LLC | Chesterfield | 2018-05-31
|  |  | 1702439 |  |  | Jennings County | -339679.2083
|  |  | 1702440 |  |  | Monroe County | -339679.2083
|  |  | 1702441 |  |  | Monroe County | -339679.2083
|  |  | 1702442 |  |  | Morgan County | -339679.2083
|  |  | 1702443 |  |  | Ohio County | -339679.2083
|  |  | 1702444 |  |  | Ripley County | -339679.2083
|  |  | 1702445 |  |  | Scott County | -339679.2083
|  |  | 1702446 |  |  | Switzerland County | -339679.2083
|  |  | 1702447 |  |  | Switzerland County | -339679.2083
|  |  | 1702448 |  |  | Switzerland County | -339679.2083
|  |  | 1702449 |  |  | Switzerland County | -339679.2083
|  |  | 1702450 |  | Appraising Indiana, LLC | Cicero | 2018-05-31
|  |  | 1702451 |  | Wilcox Environmental Engineering, Inc. | Connersville | 2018-05-31
|  |  | 1702452 |  |  | Cumberland | 2018-05-31
|  |  | 1702453 |  |  | Delaware County | 2018-05-31
|  |  | 1702454 |  |  | Delaware County | 2018-05-31
|  |  | 1702455 |  | Burgess & Niple, Inc. | Eaton | 2018-05-31
|  |  | 1702456 |  | CE Solutions, Inc. | Elwood | 2018-05-31
|  |  | 1702457 |  |  | Fayette County | 2018-05-31
|  |  | 1702458 |  | CTLGroup | Fortville | 2018-05-31
|  |  | 1702459 |  |  | Knightsville | 2018-05-31
|  |  | 1702460 |  | Alfred Benesch & Company | Brookville | -339679.2083
|  |  | 1702461 |  | American Surveying & Engineering, P.C. | Campbellsburg | -339679.2083
|  |  | 1702462 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702463 |  | Central Diving Contractors | Frankton | 2018-05-31
|  |  | 1702464 |  | CoCal Consulting, LLC | Greenfield | 2018-05-31
|  |  | 1702465 |  | Collins Engineers Incorporated | Greentown | 2018-05-31
|  |  | 1702466 |  |  | Hagerstown | 2018-05-31
|  |  | 1702467 |  |  | Hamilton County | 2018-05-31
|  |  | 1702468 |  |  | Hancock County | 2018-05-31
|  |  | 1702469 |  |  | Henry County | 2018-05-31
|  |  | 1702470 |  | Martin Riley, Inc. | Whiteland | -339679.2083
|  |  | 1702471 |  | March Environmental Services, LLC | Westport | -339679.2083
|  |  | 1702472 |  | Lonco, Inc. | Versailles | -339679.2083
|  |  | 1702473 |  | Loftus Engineering, Inc. | Vernon | -339679.2083
|  |  | 1702474 |  | B. L. A., Inc. | Corydon | -339679.2083
|  |  | 1702475 |  | B. L. A., Inc. | Corydon | -339679.2083
|  |  | 1702476 |  | Basin Field Services, Inc. | Crothersville | -339679.2083
|  |  | 1702479 |  |  | Dillsboro | -339679.2083
|  |  | 1702480 |  | C & E Clark, LLC | Elizabethtown | -339679.2083
|  |  | 1702481 |  |  | Ellettsville | -339679.2083
|  |  | 1702482 |  |  | Ellettsville | -339679.2083
|  |  | 1702483 |  | Civil & Environmental Consultants, Inc. | Georgetown | -339679.2083
|  |  | 1702484 |  | DKA Associates, Inc. | Ingalls | 2018-05-31
|  |  | 1702485 |  | David Matthews Associates (Former) | Kempton | 2018-05-31
|  |  | 1702486 |  | Dillabaugh, Inc. | Knightstown | -339679.2083
|  |  | 1702487 |  | Dodd Title Corporation | Kokomo | -339679.2083
|  |  | 1702488 |  | Duneland Group, Inc. | Lapel | 2018-05-31
|  |  | 1702489 | Whitley |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1702490 |  | Conveyance Group, Inc. | Hartsville | -339679.2083
|  |  | 1702491 |  | Craig eonard Historic Preservation Consultant | Holton | -339679.2083
|  |  | 1702492 |  | Crawford, Murphy & Tilly, Inc. | Hope | -339679.2083
|  |  | 1702493 |  |  | Lanesville | -339679.2083
|  |  | 1702494 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | -339679.2083
|  |  | 1702495 |  | Environmental Management Associatese | Mauckport | -339679.2083
|  |  | 1702496 |  | Fidelity National Title Insurance Company, Inc. | Milan | -339679.2083
|  |  | 1702497 |  |  | Moores Hill | -339679.2083
|  |  | 1702498 |  | KW Garner Consulting | St Paul | -339679.2083
|  |  | 1702499 |  | IHS Global Insight | Princes Lakes | -339679.2083
|  |  | 1702500 |  | Hardcore Concrete Sawing Inc. | Osgood | -339679.2083
|  |  | 1702501 |  |  | New Whiteland | -339679.2083
|  |  | 1702502 |  | Garcia LE & Associates, L.L.C. | Nashville | -339679.2083
|  |  | 1702503 |  | Garcia LE & Associates, L.L.C. | Nashville | -339679.2083
|  |  | 1702504 |  |  | Morgantown | -339679.2083
|  |  | 1702505 |  | GAI Consultants, Inc. | Mooresville | -339679.2083
|  |  | 1702506 |  | ARCADIS | Batesville | -339679.2083
|  |  | 1702507 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702508 |  |  | Knox | -339679.2083
|  |  | 1702509 |  |  | Knox | -339679.2083
|  |  | 1702510 |  |  | Knox | -339679.2083
|  |  | 1702511 |  |  | Vigo County | -339679.2083
|  |  | 1702512 |  |  | Vermillion County | -339679.2083
|  |  | 1702513 | Clark |  | Indiana Department of Transportation | 2019-09-11 | CN
|  |  | 1702514 |  |  | Noble County | 2018-05-31
|  |  | 1702515 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702516 |  | Dyer Environmental Services | Lawrence | 2018-05-31
|  |  | 1702517 |  | Eel River Abstract | Lynn | 2018-05-31
|  |  | 1702518 |  |  | Marion County | 2018-05-31
|  |  | 1702519 |  | Enterprise Information Solutions, Inc. | Markleville | 2018-05-31
|  |  | 1702520 |  | Enterprise Information Solutions, Inc. | Markleville | 2018-05-31
|  |  | 1702521 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2018-05-31
|  |  | 1702522 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 1702523 |  | Great Lakes Engineering, Inc. | New Palestine | 2018-05-31
|  |  | 1702524 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2018-05-31
|  |  | 1702525 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702526 |  | H.R. Gray | North Judson | -339679.2083
|  |  | 1702527 |  | Duesler Realty House | Lagrange | 2018-05-31
|  |  | 1702528 |  | Heritage Appraisal Service | Parker City | 2018-05-31
|  |  | 1702529 |  | Duesler Realty House | Lagrange | 2018-05-31
|  |  | 1702530 |  | Hey and Associates, Inc. | Pendleton | 2018-05-31
|  |  | 1702531 |  |  | Redkey | 2018-05-31
|  |  | 1702532 |  | Indiana Appraisal Group, Inc. | Richmond | 2018-05-31
|  |  | 1702533 |  | J. Williams Appraisal Group, LLC | Rushville | 2018-05-31
|  |  | 1702534 |  | J.F. New & Associates, Inc. | Russiaville | 2018-05-31
|  |  | 1702535 |  | James Pichler Appraisals | Selma | 2018-05-31
|  |  | 1702536 |  |  | Shelby County | 2018-05-31
|  |  | 1702537 |  | Jill D Reed and Associates, Inc. | Sheridan | 2018-05-31
|  |  | 1702538 |  | John G. Brinkworth, Inc. | Shirley | 2018-05-31
|  |  | 1702539 |  | KCI Technologies, Inc. | Southport | 2018-05-31
|  |  | 1702540 |  | KERAMIDA Environmental, Inc. | Speedway | 2018-05-31
|  |  | 1702541 |  | Kovachevich & Co., Inc. | Summitville | 2018-05-31
|  |  | 1702542 |  | Land Construction Corp | Tipton | -339679.2083
|  |  | 1702543 |  |  | Tipton County | -339679.2083
|  |  | 1702544 |  |  | Union County | -339679.2083
|  |  | 1702545 |  |  | Wayne County | 2018-05-31
|  |  | 1702546 |  |  | Westfield | 2018-05-31
|  |  | 1702547 |  | Apex Consulting & Surveying, Inc. | Winchester | 2018-05-31
|  |  | 1702548 |  | McCullouch Consulting, LLC | Windfall | 2018-05-31
|  |  | 1702549 |  |  | Monon | -339679.2083
|  |  | 1702550 |  | ACMS Group, Inc. | Argos | -339679.2083
|  |  | 1702551 |  | Amereco Incorporated | Burlington | -339679.2083
|  |  | 1702552 |  |  | Carroll County | -339679.2083
|  |  | 1702553 |  | Applied Pavement Technology, Inc. | Cedar Lake | -339679.2083
|  |  | 1702554 |  | Wessler Engineering, Inc. | Wakarusa | 2018-05-31
|  |  | 1702555 |  |  | Newton County | -339679.2083
|  |  | 1702556 |  |  | Lake County | -339679.2083
|  |  | 1702557 |  |  | Rush County | -339679.2083
|  |  | 1702558 |  | Appraisal Service | Chalmers | -339679.2083
|  |  | 1702559 |  | Brenner Design Incorporated | Dyer | -339679.2083
|  |  | 1702560 |  | Chemical Dependency Program of Indiana | Galveston | -339679.2083
|  |  | 1702561 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702562 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1702563 |  |  | LaPorte County | -339679.2083
|  |  | 1702564 |  |  | Merrillville | -339679.2083
|  |  | 1702565 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 1702566 |  |  | Munster | -339679.2083
|  |  | 1702567 |  | Gensic Engineering, Inc. | New Carlisle | -339679.2083
|  |  | 1702568 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | -339679.2083
|  |  | 1702569 |  | HDR Engineering, Inc. | North Liberty | -339679.2083
|  |  | 1702570 |  | Land Title Service Company, LLC | Town Of Pines | -339679.2083
|  |  | 1702571 |  | Huff & Huff, Inc. | Portage | -339679.2083
|  |  | 1702572 |  | Hy-Tech Response, Inc. | Porter | -339679.2083
|  |  | 1702573 |  |  | Pulaski County | -339679.2083
|  |  | 1702574 |  | InfoTech | Rochester | -339679.2083
|  |  | 1702575 |  | Jacobi, Toombs & Lanz, Inc. | Schneider | -339679.2083
|  |  | 1702576 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1702577 |  | Context, LLC | Harmony | -339679.2083
|  |  | 1702578 |  | Karen | St. John | -339679.2083
|  |  | 1702579 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702581 |  |  | South Bend | -339679.2083
|  |  | 1702582 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | -339679.2083
|  |  | 1702583 |  | Marine Solutions, Inc. | Westville | -339679.2083
|  |  | 1702584 |  | Capstone, Inc. | Francesville | -339679.2083
|  |  | 1702585 |  | Matt L. Nepote, MAI | Whiting | -339679.2083
|  |  | 1702586 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 1702587 |  |  | Winfield | -339679.2083
|  |  | 1702588 |  | Meridian Title Corporation | Wolcott | -339679.2083
|  |  | 1702589 |  | Engineered Management Systems, Inc. | Macy | 2018-05-31
|  |  | 1702590 |  |  | White County | -339679.2083
|  |  | 1702591 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 1702592 |  |  | Hamlet | -339679.2083
|  |  | 1702593 |  | Corn Island Archaeology, LLC | Hebron | -339679.2083
|  |  | 1702594 |  | Domain Architecture, Inc. | Kouts | -339679.2083
|  |  | 1702595 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702596 |  | Atlas Appraisals, LLC | Converse | 2018-05-31
|  |  | 1702597 |  | Bartlett & Associates, Inc. | Cromwell | 2018-05-31
|  |  | 1702598 |  | Bartlett & Associates, Inc. | Cromwell | 2018-05-31
|  |  | 1702599 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-03-10
|  |  | 1702600 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1702601 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1702602 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1702603 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1702604 |  | American Commercial Title & Escrow | Indiana Department of Transportation | -339679.2083
|  |  | 1702605 |  | Eco Logic, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1702606 | Harrison |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1702607 |  | Entran, PLC | Marshall | 2018-05-31
|  |  | 1702608 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2018-05-31
|  |  | 1702609 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2018-05-31
|  |  | 1702610 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-11-10
|  |  | 1702611 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1702612 | St. Joseph |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1702613 |  | Cornerstone Design | Indiana Department of Transportation | -339679.2083
|  |  | 1702614 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1702615 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1702616 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1702617 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1702618 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1702619 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702620 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702621 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702622 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702623 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702624 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702625 |  | Booker Real Estate Services | Dune Acres | -339679.2083
|  |  | 1702626 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702627 | Monroe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1702628 |  | Booker Real Estate Services | Dune Acres | -339679.2083
|  |  | 1702629 | Washington |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1702630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702631 | Harrison |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1702632 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702633 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702634 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702635 | Harrison |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1702636 |  | Edwards and Kelcey | Indiana Department of Transportation | -339679.2083
|  |  | 1702637 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702638 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702639 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702640 | Harrison |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1702641 |  |  | Whitley County | 2018-05-31
|  |  | 1702642 |  |  | Whitley County | 2018-05-31
|  |  | 1702643 |  |  | Dekalb County | 2018-05-31
|  |  | 1702644 |  | Infrastructure Engineering, Inc. | Rockport | 2018-05-31
|  |  | 1702645 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1702646 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1702647 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1702648 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702649 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1702650 | Bartholomew |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1702651 | Boone | Martinez Corporation | Indiana Department of Transportation | 2018-07-11 | CE
CN
|  |  | 1702652 |  |  | Marshall County | -339679.2083
|  |  | 1702653 |  |  | Marshall County | -339679.2083
|  |  | 1702654 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1702655 |  | Hambleton LLC | Orland | 2018-05-31
|  |  | 1702656 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1702657 |  | Hambleton LLC | Orland | 2018-05-31
|  |  | 1702658 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1702659 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1702660 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2021-05-31
|  |  | 1702661 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1702662 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702663 |  |  | Kosciusko County | 2018-05-31
|  |  | 1702664 |  | Industrial Waste Management Consulting Group, LLC | Roann | 2018-05-31
|  |  | 1702665 |  |  | Tell City | 2018-05-31
|  |  | 1702666 |  | Kevin K. Parsons & Associates, Inc. | Staunton | 2018-05-31
|  |  | 1702667 |  | Global Management Group, Inc. | New Haven | 2018-05-31
|  |  | 1702668 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1702669 |  |  | Brown County | 2016-12-14
|  |  | 1702670 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1702671 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1702672 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1702673 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702674 |  |  | Columbia City | 2018-05-31
|  |  | 1702675 |  | Archonsortium, LLC | Cloverdale | -339679.2083
|  |  | 1702676 |  | Bella Villa Realtors, LLC | Danville | -339679.2083
|  |  | 1702677 |  | Bertsch-Frank & Associates, LLC | Dayton | 2018-05-31
|  |  | 1702678 |  | Corradino, LLC | Hillsboro | 2018-05-31
|  |  | 1702679 |  | Digital Appraisals, LLC | Kirklin | -339679.2083
|  |  | 1702680 |  |  | Monrovia | -339679.2083
|  |  | 1702681 |  | Frontline Construction Inspection, Inc. | Montezuma | -339679.2083
|  |  | 1702682 |  | GRW Engineers, Inc. | Mulberry | -339679.2083
|  |  | 1702683 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1702684 |  |  | New Richmond | -339679.2083
|  |  | 1702685 |  | HLRD | North Salem | -339679.2083
|  |  | 1702686 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | -339679.2083
|  |  | 1702687 |  | Horn and Associates, Inc. | Pittsboro | -339679.2083
|  |  | 1702688 | Marion |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702689 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 1702690 |  | Indiana University | Roachdale | -339679.2083
|  |  | 1702691 |  | Integra Realty Resources | Rosedale | -339679.2083
|  |  | 1702692 |  | Iteris, Inc. | Rossville | -339679.2083
|  |  | 1702693 |  | J.A. Barker Engineering, Inc. | Russellville | -339679.2083
|  |  | 1702694 |  |  | South Bend Transit | -339679.2083
|  |  | 1702695 |  |  | South Bend Transit | -339679.2083
|  |  | 1702696 |  |  | South Bend Transit | -339679.2083
|  |  | 1702697 |  |  | South Bend Transit | -339679.2083
|  |  | 1702698 |  | Midwest Archaeological Research Services, Inc. | Zionsville | -339679.2083
|  |  | 1702699 |  | McCord, Inc. | Williamsport | 2018-05-31
|  |  | 1702700 |  | Jacobs Engineering Group, Inc. | Seelyville | -339679.2083
|  |  | 1702701 |  |  | Shadeland | -339679.2083
|  |  | 1702702 |  | Lamac Engineering Company | Thorntown | 2018-05-31
|  |  | 1702703 |  | Linda F. Russell | Veedersburg | -339679.2083
|  |  | 1702704 |  | Marbach & Brady Land Surveying, Inc. | West Terre Haute | 2018-05-31
|  |  | 1702705 |  | Madison Milton Ferry LLC | Waveland | -339679.2083
|  |  | 1702706 |  | Martinez Corporation | Whitestown | -339679.2083
|  |  | 1702707 |  | McKee Enterprises, Inc. | Wingate | -339679.2083
|  |  | 1702708 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2019-05-09 | PE
|  |  | 1702709 |  | LONCO, Inc. | Syracuse | 2018-05-31
|  |  | 1702710 |  | LONCO, Inc. | Syracuse | 2018-05-31
|  |  | 1702711 |  |  | Jasper County | -339679.2083
|  |  | 1702712 |  |  | Jasper County | -339679.2083
|  |  | 1702713 |  |  | Jasper County | -339679.2083
|  |  | 1702714 |  |  | Jasper County | -339679.2083
|  |  | 1702715 |  | American Engineers, Inc. | Butler | 2018-05-31
|  |  | 1702716 |  |  | Steuben County | 2018-05-31
|  |  | 1702717 |  |  | Steuben County | 2018-05-31
|  |  | 1702718 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  |  | Various | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2019-03-06 | PE
|  |  | 1702719 |  | Debbie L. Morris | Kendallville | 2018-05-31
|  |  | 1702720 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702721 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1702722 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1702723 |  | Blood Hound, Inc. (former) | Delphi | -339679.2083
|  |  | 1702724 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2019-07-10
|  |  | 1702725 |  | Independent Appraisers-Consultants, Inc. | Remington | -339679.2083
|  |  | 1702726 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 1702727 |  | ERES International, Inc. | Marion | 2018-05-31
|  |  | 1702728 |  |  | Allen County | 2018-05-31
|  |  | 1702729 | Noble |  | Noble County | 2022-11-16 | PE
ROW
|  |  | 1702730 |  |  | Noble County | -339679.2083
|  |  | 1702731 | Noble | Debbie L. Morris | Kendallville | 2022-12-07 | PE
ROW
RR
|  |  | 1702732 |  | HRV Conformance Verification Associates, Inc. | Ogden Dunes | -339679.2083
|  |  | 1702733 |  | HRV Conformance Verification Associates, Inc. | Ogden Dunes | -339679.2083
|  |  | 1702734 |  |  | Indiana Department of Transportation | 2018-12-12
|  |  | 1702735 | Wells |  | Wells County | 2022-11-16 | PE
|  |  | 1702736 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1702737 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1702738 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1702739 | Various |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1702740 |  |  | South Bend Transit | -339679.2083
|  |  | 1702741 |  | CRI Construction Inc. | Flora | -339679.2083
|  |  | 1702742 |  | CRI Construction Inc. | Flora | -339679.2083
|  |  | 1702743 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2018-05-10 | CE
CN
|  |  | 1702744 |  | Accidental Discoveries, LLC | Bluffton | 2018-05-31
|  |  | 1702745 |  | AES Services, Inc. | Avilla | -339679.2083
|  |  | 1702746 |  | AES Services, Inc. | Avilla | 2018-05-31
|  |  | 1702747 |  |  | Elkhart County | 2018-05-31
|  |  | 1702748 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1702749 |  |  | Indiana Department of Transportation | 2018-03-21
|  |  | 1702750 |  |  | Indiana Department of Transportation | 2018-03-21
|  |  | 1702751 |  |  | Indiana Department of Transportation | 2018-03-21
|  |  | 1702752 |  |  | Indiana Department of Transportation | 2018-12-12
|  |  | 1702753 | Rush | J. Williams Appraisal Group, LLC | Rush County | 2022-09-14 | PE
|  |  | 1702754 | Hancock |  | Hancock County | 2022-12-07 | PE
ROW
|  |  | 1702755 | Hancock |  | Hancock County | 2022-12-07 | PE
ROW
|  |  | 1702756 | Hancock |  | Hancock County | 2022-03-09 | PE
ROW
|  |  | 1702757 | Hancock |  | Hancock County | 2021-12-08 | CE
CN
|  |  | 1702758 | Henry |  | Henry County | 2021-09-15 | PE
|  |  |  | Various |  | Henry County | 2021-09-15 | CE
CN
|  |  | 1702759 | Fayette | Wilcox Environmental Engineering, Inc. | Connersville | 2021-02-10 | CE
CN
PE
|  |  | 1702760 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2020-11-10 | CE
CN
PE
|  |  | 1702761 | Fayette |  | Fayette County | 2022-02-09 | PE
ROW
|  |  | 1702762 | Jay | Hydrogeology, Inc. | Portland | 2022-05-05 | PE
ROW
|  |  | 1702763 |  |  | Rushville | -339679.2083
|  |  | 1702764 |  |  | Rushville | -339679.2083
|  |  | 1702765 | Hamilton |  | Westfield | 2022-07-13 | PE
|  |  | 1702766 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 1702767 |  |  | Hamilton County | -339679.2083
|  |  | 1702768 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 1702769 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 2022-01-12 | PE
|  |  | 1702770 |  | Cambridge Systematics, Inc. | Wayne County | -339679.2083
|  |  | 1702771 |  |  | Wayne County | -339679.2083
|  |  | 1702772 | Fayette |  | Rush County | 2021-11-17 | CE
CN
PE
ROW
|  |  | 1702773 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1702774 | Rush | Civil Designs, LLP | Glenwood | 2022-11-16 | PE
ROW
|  |  | 1702775 | Shelby | Jeffrey S. Juday | Shelbyville | 2022-11-16 | PE
|  |  | 1702776 |  | IXOYE, Limited | Redkey | -339679.2083
|  |  | 1702777 |  | Evans, Mechwart, Hambleton & Tilton, Inc. | Medaryville | -339679.2083
|  |  | 1702778 |  | Evans, Mechwart, Hambleton & Tilton, Inc. | Medaryville | -339679.2083
|  |  | 1702779 |  | Evans, Mechwart, Hambleton & Tilton, Inc. | Medaryville | -339679.2083
|  |  | 1702780 |  | American Structurepoint, Inc. | Camden | -339679.2083
|  |  | 1702781 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702782 |  | Civil Inspection Services, LLC | Goshen | 2018-05-31
|  |  | 1702783 |  | Civil Inspection Services, LLC | Goshen | 2018-05-31
|  |  | 1702784 |  | Civil Inspection Services, LLC | Goshen | 2018-05-31
|  |  | 1702785 |  | Jackie S. Dodd, Attorney at Law | Schererville | -339679.2083
|  |  | 1702786 |  | 2IM Group, LLC | Akron | -339679.2083
|  |  | 1702787 | Clark |  | Clark County | 2020-02-05 | CE
CN
UT
|  |  | 1702788 | Clark |  | Clark County | 2020-02-05 | CE
CN
|  |  | 1702789 |  | Afram Corporation | Brookston | -339679.2083
|  |  | 1702790 |  | ATSI Engineering Services | Beverly Shores | -339679.2083
|  |  | 1702791 |  | ATSI Engineering Services | Beverly Shores | -339679.2083
|  |  | 1702792 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2017-03-01
|  |  | 1702793 |  |  | Chesterton | -339679.2083
|  |  | 1702794 |  |  | Chesterton | -339679.2083
|  |  | 1702795 |  | Compliance Consulting Service, Inc. | Griffith | -339679.2083
|  |  | 1702796 |  | Marino Engineering Associates Inc | Wheatfield | -339679.2083
|  |  | 1702797 |  | Marino Engineering Associates Inc | Wheatfield | -339679.2083
|  |  | 1702798 |  | MCCARTIN - ASSOCIATES | Walton | -339679.2083
|  |  | 1702799 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1702800 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1702801 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1702802 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington | 2022-01-12 | PE
ROW
|  |  | 1702803 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1702804 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1702805 |  |  | Boone County | -339679.2083
|  |  | 1702806 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1702807 |  |  | Boone County | -339679.2083
|  |  | 1702808 |  | M-E Companies, Inc. | Wabash | -339679.2083
|  |  | 1702809 |  |  | Fulton | -339679.2083
|  |  | 1702810 | Adams |  | Allen County | 2023-01-19 | PE
|  |  | 1702811 |  | American Commercial Title & Escrow | Burns Harbor | -339679.2083
|  |  | 1702812 |  | American Commercial Title & Escrow | Burns Harbor | -339679.2083
|  |  | 1702813 |  | American Commercial Title & Escrow | Burns Harbor | -339679.2083
|  |  | 1702814 | Huntington |  | Huntington County | 2022-11-16 | PE
|  |  | 1702815 |  |  | Fulton County | -339679.2083
|  |  | 1702816 |  |  | Fulton County | -339679.2083
|  |  | 1702817 |  |  | Fulton County | -339679.2083
|  |  | 1702818 |  |  | Cass County | -339679.2083
|  |  | 1702819 |  |  | Cass County | -339679.2083
|  |  | 1702820 | Randolph | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1702821 |  |  | Porter County | 2022-12-07
|  |  | 1702822 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 1702823 | Pulaski | McCormick Engineering, LLC | Winamac | 2023-01-19 | PE
|  |  | 1702824 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 1702825 |  | McCormick Engineering, LLC | Winamac | -339679.2083
|  |  | 1702826 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1702827 |  |  | Porter County | 2022-02-09
|  |  | 1702828 |  |  | Porter County | 2022-03-09
|  |  | 1702829 | LaPorte |  | LaPorte County | 2022-01-12 | PE
ROW
|  |  | 1702830 | Lake |  | Lake County | 2022-10-13 | PE
|  |  | 1702831 | Lake |  | Lake County | 2022-01-12 | PE
ROW
|  |  | 1702832 | St. Joseph |  | St. Joseph County | 2022-10-13 | PE
|  |  | 1702833 |  |  | LaPorte County | 2022-10-13
|  |  | 1702834 | Starke | H.R. Gray | North Judson | 2021-12-08 | PE
|  |  | 1702835 | White | Fugro Roadware, Inc. | White County | 2022-10-13 | PE
|  |  | 1702836 |  |  | Marshall County | -339679.2083
|  |  | 1702837 | Marshall | Howard J. Barth & Associates, Inc. | Plymouth | 2022-01-12 | PE
|  |  | 1702838 | Marshall |  | Marshall County | 2022-10-13 | PE
ROW
|  |  | 1702839 | Marshall |  | Marshall County | 2022-10-13 | PE
ROW
|  |  | 1702840 | Fulton |  | Fulton County | 2022-10-13 | PE
|  |  | 1702841 | Fulton |  | Fulton County | 2022-10-13 | PE
|  |  | 1702842 |  | Active Environmental Services, Inc. | Bourbon | -339679.2083
|  |  | 1702843 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1702844 | LaGrange | Duesler Realty House | Lagrange | 2022-12-07 | PE
|  |  | 1702845 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1702846 |  |  | Owen County | -339679.2083
|  |  | 1702847 |  |  | Kosciusko County | -339679.2083
|  |  | 1702848 | Elkhart | Wessler Engineering, Inc. | Elkhart County | 2022-12-07 | PE
ROW
|  |  | 1702849 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2022-12-07 | PE
ROW
|  |  | 1702850 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2022-02-09 | PE
ROW
|  |  | 1702851 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1702852 |  |  | Upland | 2018-05-31
|  |  | 1702853 |  | Farren Real Estate Services | Middlebury | 2018-05-31
|  |  | 1702854 | Montgomery | Banning Engineering, P.C. | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1702855 | Blackford | Fusion by Design, Inc. | Montpelier | 2021-04-07 | CE
CN
PE
|  |  | 1702856 | Grant | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2021-03-10 | CE
CN
PE
|  |  | 1702857 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702858 | Blackford | Continental Mapping Consultants, LLC | Hartford City | 2021-08-11 | CE
CN
PE
|  |  | 1702859 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702860 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1702861 |  | Holloway Engineering, LLC | Miami County | -339679.2083
|  |  | 1702862 | Elkhart | Gandhi and Associates, Inc. | Nappanee | 2022-12-07 | PE
ROW
|  |  | 1702863 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | -339679.2083
|  |  | 1702864 |  |  | Upland | 2023-01-19
|  |  | 1702865 |  | M.A.T. Consulting, Inc. | Walkerton | -339679.2083
|  |  | 1702866 | Kosciusko | Mackie Consultants, LLC | Kosciusko County | 2022-11-16 | PE
|  |  | 1702867 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1702868 | Delaware | Michael Baker International, Inc. | Yorktown | 2021-01-13 | CE
CN
|  |  | 1702869 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1702870 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1702871 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702872 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1702873 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702874 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702875 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702876 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702877 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702878 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702879 |  | HE-BFS, LLC | North Manchester | 2018-05-31
|  |  | 1702880 |  | HE-BFS, LLC | North Manchester | 2018-05-31
|  |  | 1702881 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702882 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1702883 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1702884 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702885 |  | Howard J. Barth & Associates, Inc. | Plymouth | -339679.2083
|  |  | 1702886 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1702887 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702889 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702891 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702892 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702893 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702894 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702895 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702897 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702898 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1702899 |  | EFI Global, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1702900 |  | Baxter & Woodman, Inc. | Crown Point | -339679.2083
|  |  | 1702901 |  | EFI Global, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1702902 |  | Kinzelman Kline Gossman | Indiana Department of Transportation | 2022-10-13
|  |  | 1702903 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1702904 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1702905 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1702906 |  | Dave Helton & Associates, Inc. | Jonesboro | 2018-05-31
|  |  | 1702907 |  | AECOM Technical Services, Inc. | Ashley | 2018-05-31
|  |  | 1702908 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702909 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702910 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702911 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702912 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702913 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702914 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1702915 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702916 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702917 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702918 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1702919 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2021-10-14 | CN
UT
[5 empty] | CoCal Consulting, LLC | Indiana Department of Transportation | 2021-10-14
|  |  | 1702920 | Henry |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1702921 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702922 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1702923 |  | Duneland Group, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1702924 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2018-05-31
|  |  | 1702925 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 1702926 |  | M-E Companies, Inc. | Wabash | 2018-05-31
|  |  | 1702927 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702928 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702929 |  | Dodd Title Corporation | Indiana Department of Transportation | 2022-11-16
|  |  | 1702930 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1702931 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1702932 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702933 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1702934 |  | Duneland Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702935 |  | CTLGroup | Indiana Department of Transportation | 2022-07-13
|  |  | 1702936 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1702937 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 1702938 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702939 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702940 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1702941 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1702942 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702943 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2022-03-09
|  |  | 1702944 |  | Central Diving Contractors | Indiana Department of Transportation | -339679.2083
|  |  | 1702945 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702946 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1702947 |  |  | Indiana Department of Transportation | 2018-04-11
|  |  | 1702948 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 1702949 |  | Chicago Testing Laboratory, Inc. | Gary | -339679.2083
|  |  | 1702950 | Dekalb |  | Dekalb County | 2024-01-18 | PE
ROW
|  |  | 1702951 |  | ERES International, Inc. | Grant County | -339679.2083
|  |  | 1702952 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 1702953 |  |  | Johnson County | -339679.2083
|  |  | 1702954 | Johnson |  | Johnson County | 2021-09-15 | CE
CN
|  |  | 1702955 |  |  | Monroe County | -339679.2083
|  |  | 1702956 |  |  | Monroe County | -339679.2083
|  |  | 1702957 |  | Absolute Title Services, LLC | Monroe County | 2022-11-16
|  |  | 1702958 | Lawrence |  | Monroe County | 2021-01-13 | UT
|  |  |  | Monroe |  | Monroe County | 2021-01-13 | CE
CN
UT
|  |  | 1702959 | Dearborn |  | Dearborn County | 2022-11-16 | PE
|  |  | 1702960 | Harrison |  | Harrison County | 2022-07-13 | ROW
|  |  | 1702961 | Morgan | EnviroScience, Inc. | Martinsville | 2022-01-12 | PE
ROW
|  |  | 1702962 | Morgan | EnviroScience, Inc. | Martinsville | 2022-08-10 | PE
ROW
|  |  | 1702963 | Jennings |  | North Vernon | 2022-05-31 | PE
|  |  | 1702964 | Washington | JCI Bridge Group, Inc. | Salem | 2022-11-16 | PE
ROW
|  |  | 1702965 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1702966 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 1702967 | Morgan |  | Morgan County | 2022-10-13 | PE
|  |  | 1702968 |  | Accu-Air Surveys, Inc. | Clark County | -339679.2083
|  |  | 1702969 | Franklin | Alfred Benesch & Company | Brookville | 2021-11-17 | CE
CN
PE
ROW
|  |  | 1702970 | Vigo |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
UT
|  |  | 1702971 |  |  | Pike County | 2018-05-31
|  |  | 1702972 |  | AMEC E&I, Inc. | Washington | 2018-05-31
|  |  | 1702973 |  |  | Kentland | -339679.2083
|  |  | 1702974 |  | John A. Doyle Associates, Inc. | Shipshewana | 2018-05-31
|  |  | 1702975 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702976 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1702977 |  |  | Huntington County | 2018-05-31
|  |  | 1702978 |  |  | Huntington County | 2018-05-31
|  |  | 1702979 |  |  | Huntington County | 2018-05-31
|  |  | 1702980 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702981 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1702982 | Delaware |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1702983 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702984 |  | Hey and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702985 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1702986 | Pulaski |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1702987 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702988 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1702989 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1702990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1702991 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1702992 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702993 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1702994 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1702995 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1702996 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1702997 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 1702998 |  |  | Richland | 2018-05-31
|  |  | 1702999 |  | Eco Logic, LLC | Indiana Department of Transportation | 2023-04-12
|  |  | 1703000 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1703001 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1703002 |  | Donohue & Associates, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1703003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1703004 |  | Brenner Design Incorporated | Indiana Department of Transportation | 2023-03-15
|  |  | 1703005 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1703006 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1703007 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1703008 |  | Land Consultants, Inc. | Topeka | 2018-05-31
|  |  | 1703009 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1703010 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 1703011 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1703012 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1703013 | Franklin |  | Franklin County | 2023-08-09 | PE
|  |  | 1703014 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2021-03-10 | CE
CN
|  |  | 1703015 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2022-11-16 | PE
|  |  | 1703016 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1703017 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 1703018 | Jackson |  | Jackson County | 2023-10-12 | PE
|  |  | 1703019 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1703020 | Jackson |  | Jackson County | 2023-02-15 | PE
|  |  | 1703021 |  |  | Johnson County | -339679.2083
|  |  | 1703022 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1703023 |  |  | Miami County | 2018-05-31
|  |  | 1703024 |  |  | Miami County | 2018-05-31
|  |  | 1703025 |  |  | Miami County | 2018-05-31
|  |  | 1703026 |  |  | Miami County | 2018-05-31
|  |  | 1703027 |  |  | Miami County | 2018-05-31
|  |  | 1703028 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1703029 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1703030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1703031 |  |  | Indiana Department of Transportation | 2021-07-14
|  |  | 1703032 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1703033 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1703034 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1703035 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1703036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1703037 | Cass |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1703038 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1703039 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1703040 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1703041 |  | Integrated Environmental Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1703042 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1703043 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1703044 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 1703045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1703046 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800001 |  | Knies Constr/Calcar Paving J/V | Lapaz | -339679.2083
|  |  | 1800002 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800003 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800005 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800006 | Harrison | B. L. A., Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1800007 |  |  | Hendricks County | -339679.2083
|  |  | 1800008 | Bartholomew |  | Bartholomew County | 2024-07-01 | PE
|  |  | 1800009 | Jay | Hydrogeology, Inc. | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1800010 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2018-05-31
|  |  | 1800011 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2018-05-31
|  |  | 1800012 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2018-05-31
|  |  | 1800013 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800014 |  | Bartlett & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800015 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1800016 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1800017 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800018 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1800019 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1800020 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 1800021 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 1800022 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800023 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800024 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1800025 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1800026 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1800027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800028 |  | ERES International, Inc. | Ligonier | 2018-05-31
|  |  | 1800029 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2024-04-10
|  |  | 1800030 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2024-04-10
|  |  | 1800031 |  | Advanced Engineering Consultants, Ltd. | Bremen | -339679.2083
|  |  | 1800032 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 1800033 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2024-04-10
|  |  | 1800034 | Allen |  | Indiana Department of Transportation | 2022-08-10 | PE
|  |  | 1800035 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1800036 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1800037 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1800038 |  | Fugro Roadware, Inc. | Monticello | -339679.2083
|  |  | 1800039 | Elkhart |  | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1800040 | Noble | ERES International, Inc. | Indiana Department of Transportation | 2024-02-14 | PE
|  |  | 1800041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800044 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800045 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 1800046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800047 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800048 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800049 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800050 |  | EDP Consultants | Indiana Department of Transportation | 2022-11-16
|  |  | 1800051 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800052 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800053 |  | Mader Design, LLC | Indiana Department of Transportation | 2022-11-16
|  |  | 1800054 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800055 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 1800056 | Miami | Blue Sky Engineering, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1800057 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2023-04-12
|  |  | 1800058 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1800059 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1800060 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800061 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800062 |  | Advantage Appraisal Services | Indiana Department of Transportation | 2022-07-13
|  |  | 1800063 | Carroll | American Structurepoint, Inc. | Indiana Department of Transportation | 2023-01-19 | RR
|  |  | 1800064 |  | J. H. Rudolph & Co., Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1800065 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800066 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800067 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-12-07
|  |  | 1800068 |  | Landstory, Inc. | Grabill | 2018-05-31
|  |  | 1800069 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800070 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800071 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800072 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1800073 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800074 |  | Archonsortium, LLC | Indiana Department of Transportation | 2022-10-13
|  |  | 1800075 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1800076 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800077 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800078 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800079 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800080 |  |  | Roanoke | 2018-05-31
|  |  | 1800081 |  | Casteel Real Estate | Indiana Department of Transportation | 2024-05-31
|  |  | 1800082 |  | Casteel Real Estate | Indiana Department of Transportation | 2022-07-13
|  |  | 1800083 |  | Casteel Real Estate | Indiana Department of Transportation | 2024-05-31
|  |  | 1800084 |  |  | Berne | 2018-05-31
|  |  | 1800085 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800086 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2024-08-14
|  |  | 1800087 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800088 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2024-04-10
|  |  | 1800089 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1800090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800091 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800092 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2023-09-13
|  |  | 1800093 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1800094 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1800095 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1800096 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1800097 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800098 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800099 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1800100 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1800101 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800102 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2023-01-19
|  |  | 1800103 |  | Chicago Title Insurance Company | Gas City | 2018-05-31
|  |  | 1800104 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1800105 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2023-01-19
|  |  | 1800106 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800107 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800109 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800111 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800112 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800113 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800114 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800115 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800116 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800117 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 1800118 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800119 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1800120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800121 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800122 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800123 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800124 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800125 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800126 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800128 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800129 |  | Action Title and Escrow, LLC | Indiana Department of Transportation | 2022-10-13
|  |  | 1800130 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1800131 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800132 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800133 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1800134 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800135 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1800136 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800138 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800139 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800140 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1800141 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800142 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800143 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1800144 |  | Cultural Resource Analysts, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 1800145 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800146 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1800147 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1800148 | Wabash |  | Indiana Department of Transportation | 2024-01-18 | RR
|  |  | 1800149 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800151 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800152 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800153 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800154 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800155 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800156 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1800157 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1800158 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800159 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800160 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Indiana Department of Transportation | 2023-04-12
|  |  | 1800161 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2023-09-13
|  |  | 1800162 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1800163 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800164 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800165 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800166 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800167 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800168 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1800169 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800170 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1800171 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800172 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1800173 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1800174 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800175 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800176 |  | Eilts Consulting Services | Indiana Department of Transportation | 2023-02-15
|  |  | 1800177 |  | III FFC | Indiana Department of Transportation | 2022-12-07
|  |  | 1800178 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1800179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800180 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800181 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800182 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800183 |  | AV Consulting Engineers, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1800184 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1800185 | Ripley |  | Indiana Department of Transportation | 2022-07-13 | RR
|  |  | 1800186 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800187 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800188 |  | Lamac Engineering Company | Indiana Department of Transportation | 2022-12-07
|  |  | 1800189 | Owen |  | Indiana Department of Transportation | 2025-09-10 | PE
|  |  | 1800190 |  | Clayton L. Roots | Indiana Department of Transportation | 2022-07-13
|  |  | 1800191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800192 |  | Linda F. Russell | Indiana Department of Transportation | 2022-12-07
|  |  | 1800193 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1800194 |  | Hazeltine & Associates, Inc. | Paoli | 2018-05-31
|  |  | 1800195 | Boone | DLZ Indiana, LLC | Indiana Department of Transportation | 2022-12-07 | RR
|  |  | 1800196 |  | Hazeltine & Associates, Inc. | Paoli | 2018-05-31
|  |  | 1800197 |  | Hazeltine & Associates, Inc. | Paoli | -339679.2083
|  |  | 1800198 | Monroe |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1800199 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1800200 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800201 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800202 | Franklin | ARCADIS | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1800203 |  | AFRAM Group, Incorporated | Indiana Department of Transportation | 2024-04-10
|  |  | 1800204 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800205 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800206 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800207 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800208 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1800209 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1800210 | Scott |  | Indiana Department of Transportation | 2023-02-15 | PE
|  |  | 1800211 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2023-08-09
|  |  | 1800212 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800213 | Clay |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1800214 | Hendricks |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1800215 | Tippecanoe |  | Indiana Department of Transportation | 2023-04-12 | PE
|  |  | 1800216 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800217 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1800218 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800219 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800220 | Gibson |  | Indiana Department of Transportation | 2022-11-16 | PE
|  |  | 1800221 | Johnson |  | Indiana Department of Transportation | 2020-12-09 | PE
|  |  | 1800222 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800223 | Gibson |  | Indiana Department of Transportation | 2023-02-15 | PE
|  |  | 1800224 | Knox |  | Indiana Department of Transportation | 2023-03-15 | PE
|  |  | 1800225 | Dearborn |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1800226 | Sullivan | Anelena Ackerly | Indiana Department of Transportation | 2023-03-15 | PE
|  |  | 1800227 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800228 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800229 |  | AMEC E&I, Inc. | Washington | 2018-05-31
|  |  | 1800230 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800231 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800233 |  | Bayer & Becker, Inc. | Culver | -339679.2083
|  |  | 1800234 |  | Bayer & Becker, Inc. | Culver | -339679.2083
|  |  | 1800235 |  | EcoTec, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800236 | Clinton | Carters Appraisal Service | Frankfort | 2020-03-04 | CE
CN
RR
|  |  | 1800237 | Boone | E.J. Breneman, LP | Lebanon | 2022-03-09 | PE
ROW
|  |  | 1800238 | Putnam | Clayton L. Roots | Greencastle | 2022-07-13 | PE
ROW
|  |  | 1800239 | Vermillion | Archaeology and Geomorphology Services | Clinton | 2022-07-13 | PE
|  |  | 1800240 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800241 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1800242 | Madison |  | Alexandria | 2024-07-10 | PE
ROW
|  |  | 1800243 | Madison |  | Alexandria | 2023-07-12 | PE
ROW
|  |  | 1800244 | Madison |  | Alexandria | 2023-07-12 | PE
ROW
RR
|  |  | 1800245 | Putnam |  | Putnam County | 2021-12-08 | CE
CN
PE
ROW
RR
|  |  | 1800246 | Boone |  | Boone County | 2021-01-13 | CE
CN
PE
ROW
|  |  | 1800247 | Clinton |  | Clinton County | 2022-07-13 | PE
ROW
|  |  | 1800248 |  | Banning Engineering, P.C. | Montgomery County | -339679.2083
|  |  | 1800249 |  |  | Crawfordsville | -339679.2083
|  |  | 1800250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800251 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1800252 |  | Quantum Spatial, Inc. | Auburn | 2018-05-31
|  |  | 1800253 |  | Quantum Spatial, Inc. | Auburn | 2018-05-31
|  |  | 1800254 |  | Quantum Spatial, Inc. | Auburn | 2018-05-31
|  |  | 1800255 | Decatur | Collier Transport Inc. | Indiana Department of Transportation | 2024-01-18 | PE
|  |  | 1800256 |  | Collier Transport Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1800257 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1800258 |  | Casteel Real Estate | Indiana Department of Transportation | 2023-05-31
|  |  | 1800259 |  | Casteel Real Estate | Indiana Department of Transportation | 2023-05-31
|  |  | 1800260 |  | Hanson Professional Services, Inc. | Osceola | -339679.2083
|  |  | 1800261 |  | Casteel Real Estate | Indiana Department of Transportation | 2024-05-31
|  |  | 1800262 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 1800263 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800264 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800265 |  | Earth Exploration, Inc. | Indiana Department of Transportation | 2022-08-10
|  |  | 1800266 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800268 |  | MCIS LLC | Wanatah | -339679.2083
|  |  | 1800269 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800270 |  | MCIS LLC | Wanatah | -339679.2083
|  |  | 1800271 |  | Digital Appraisals, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 1800272 |  | Casteel Real Estate | Indiana Department of Transportation | 2022-07-13
|  |  | 1800273 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800274 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1800275 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1800276 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800277 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800278 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800279 | Ripley | ARCADIS | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800280 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1800281 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800282 |  |  | Starke County | -339679.2083
|  |  | 1800283 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800284 |  |  | Starke County | -339679.2083
|  |  | 1800285 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800286 |  |  | Starke County | -339679.2083
|  |  | 1800287 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800288 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800289 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800291 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800292 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800293 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800294 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800295 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1800296 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1800297 |  | Eco Logic, LLC | Logansport | -339679.2083
|  |  | 1800298 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800299 |  |  | Newton County | -339679.2083
|  |  | 1800300 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800301 |  |  | Leesburg | 2018-05-31
|  |  | 1800302 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1800303 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1800304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800305 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800306 |  | Danch Harner and Associates, Inc. | Jasper | -339679.2083
|  |  | 1800307 | Pike | Meca Engineering Corporation of America Incorporated | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800308 | Warrick |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800309 | Gibson |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800310 | Martin | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800311 | Posey |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800312 |  |  | Leo-Cedarville | 2018-05-31
|  |  | 1800313 | Knox |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800315 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800316 |  |  | Churubusco | 2018-05-31
|  |  | 1800317 |  | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800318 |  |  | Indiana Department of Transportation | 2024-04-10
|  |  | 1800319 | Randolph |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800320 | Union |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800321 | Madison |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800322 | Randolph |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800323 | Hancock |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800324 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
UT
|  |  | 1800325 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1800326 | Blackford |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800327 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1800328 | Grant |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800329 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1800330 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1800331 |  | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01
|  |  | 1800332 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800333 | Tipton |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800334 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 1800335 | Rush |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800336 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800337 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800338 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800339 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800340 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1800341 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800342 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800343 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800344 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800345 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800346 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800347 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800348 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800349 | Dearborn | Clyde L. Hawkins | Indiana Department of Transportation | 2024-08-14 | PE
RR
|  |  | 1800350 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800351 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800352 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800353 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800354 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800355 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800356 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800357 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800358 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800359 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800360 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1800361 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800362 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800363 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800364 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800365 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1800366 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800367 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800368 |  | ERES International, Inc. | Ligonier | 2018-05-31
|  |  | 1800369 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800371 | Monroe |  | Indiana Department of Transportation | 2023-08-09 | PE
|  |  | 1800372 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800373 |  | Hanson Professional Services, Inc. | Osceola | -339679.2083
|  |  | 1800374 |  | MCIS LLC | Wanatah | -339679.2083
|  |  | 1800375 | Clark |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1800376 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800377 | Hamilton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1800378 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800379 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800380 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800381 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800382 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800383 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800384 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800385 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800386 |  | Advanced Engineering Services Inc. | Bristol | 2018-05-31
|  |  | 1800387 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800388 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800389 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800390 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800391 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800392 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800393 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800394 | Marion | Another Test Company | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800395 |  | Franco Consulting Engineers, LLC | Monroeville | 2018-05-31
|  |  | 1800396 | Spencer |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800397 | Fountain |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1800398 | Vermillion |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1800399 | Tippecanoe |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800400 | Tippecanoe |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800401 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800402 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800403 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2022-07-13 | CE
CN
PE
|  |  | 1800404 | Putnam |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800405 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1800406 | Putnam |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800407 | Vigo |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800408 | Vigo |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800409 | Hendricks |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1800410 | Hendricks |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1800411 | Montgomery |  | Indiana Department of Transportation | 2021-11-17 | CE
CN
PE
|  |  | 1800412 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2022-07-13 | CE
CN
PE
|  |  | 1800413 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800414 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800415 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2020-05-07
|  |  | 1800416 | Clinton |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800417 | Vermillion |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800418 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
RR
|  |  | 1800419 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800420 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800421 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
RR
|  |  | 1800422 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800423 | Putnam |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800424 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800425 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
RR
|  |  | 1800426 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800427 |  | Mackie Consultants, LLC | Warsaw | 2018-05-31
|  |  | 1800428 |  | Mackie Consultants, LLC | Warsaw | 2018-05-31
|  |  | 1800429 |  | Mackie Consultants, LLC | Warsaw | 2018-05-31
|  |  | 1800430 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
RR
|  |  | 1800431 | Tippecanoe |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800432 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800433 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800434 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1800435 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2020-05-07
|  |  | 1800436 | Fountain |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
PE
|  |  | 1800437 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800438 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800439 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800440 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800441 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800442 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800443 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800444 | Montgomery |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800445 | Tippecanoe |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
RR
|  |  | 1800446 |  | Martinez Corporation | Indiana Department of Transportation | 2020-05-07
|  |  | 1800447 | White |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800448 | Warren |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1800449 | Clinton |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800450 | Montgomery |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800451 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800452 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800453 | Benton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800454 | Benton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800455 | Tippecanoe |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800456 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800457 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800458 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2020-05-07 | PE
RR
|  |  | 1800459 | Owen |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800460 | Owen |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800461 | Vermillion |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800462 | Clay |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800463 | Benton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800464 | Warren |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1800465 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1800466 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800467 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800468 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800469 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800470 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800471 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800472 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800473 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800474 | Marion |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
PE
|  |  | 1800475 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800476 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800477 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800478 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800479 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800480 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800481 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800482 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800483 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800484 | Marion |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
PE
|  |  | 1800485 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800486 | Various |  | Other | -339679.2083 | PL
|  |  | 1800487 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800488 |  | DCD Consulting LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1800489 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1800490 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 1800491 | Delaware |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800492 | Delaware |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800493 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800494 | Henry |  | Indiana Department of Transportation | 2025-12-10 | PE
RR
|  |  | 1800495 | Henry |  | Indiana Department of Transportation | 2025-12-10 | PE
RR
|  |  | 1800496 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800497 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800498 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800499 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1800500 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1800501 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1800502 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1800503 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800504 | Clay |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800505 | Shelby |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800506 | Montgomery |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800507 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800508 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800509 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1800510 | Morgan |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1800511 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800512 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800513 | Benton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800514 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800515 | Fountain |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800516 | Fountain |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800519 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800520 | Montgomery |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800521 |  | Continental Mapping Consultants, LLC | Hartford City | 2018-05-31
|  |  | 1800522 | Benton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800523 | Vermillion |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800524 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800525 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800526 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800527 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800528 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800529 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800530 | Vigo |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800531 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800532 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1800533 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-12-07
|  |  | 1800534 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800535 | Grant |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800536 | Adams |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800537 |  | ABt SRBI | Indiana Department of Transportation | 2020-08-05
|  |  | 1800538 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
RR
|  |  | 1800539 | Wells |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800540 | Marion |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1800541 | Fulton |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800542 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1800543 |  | ABt SRBI | Indiana Department of Transportation | 2020-08-05
|  |  | 1800544 | Adams |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800545 | Dekalb |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
RR
|  |  | 1800546 | Whitley | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800547 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
PE
|  |  | 1800548 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800549 | Elkhart | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2020-08-05 | PE
|  |  | 1800550 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1800551 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1800552 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2023-04-12
|  |  | 1800553 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1800554 |  | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800555 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1800556 | Morgan | Franklin Property Matters, LLC. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1800557 |  | Infrastructure Engineers, Inc. | Indiana Department of Transportation | 2021-03-10
|  |  | 1800558 | Fountain | AECON, Inc. | Indiana Department of Transportation | 2021-03-10 | PE
|  |  | 1800559 | Warren | McCord, Inc. | Indiana Department of Transportation | 2021-03-10 | PE
|  |  | 1800560 | Hendricks | Franklin Property Matters, LLC. | Indiana Department of Transportation | 2020-08-05 | PE
|  |  | 1800561 | Hendricks |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1800562 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1800563 |  | Infrastructure Engineers, Inc. | Indiana Department of Transportation | 2021-03-10
|  |  | 1800564 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2021-04-07 | PE
|  |  | 1800565 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1800566 | Fountain | H&H Associates, LLC | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1800567 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-03-09
|  |  | 1800568 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2021-05-31
|  |  | 1800569 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2021-01-13
|  |  | 1800570 |  | Martinez Corporation | Indiana Department of Transportation | 2020-09-02
|  |  | 1800571 |  | Alt & Witzig Engineering, Inc. | Bunker Hill | 2018-05-31
|  |  | 1800572 | Jasper | DuSABLE, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  |  | White | DuSABLE, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800573 | Jasper |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800574 | Steuben |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1800575 | Steuben |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1800576 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800577 | Grant | ERES International, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800578 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800579 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
RR
|  |  | 1800580 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
RR
|  |  | 1800581 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800582 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800583 | Grant |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1800584 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800585 | Huntington | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800586 | Huntington |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800587 | Allen |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800588 | Steuben |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1800589 | Steuben |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1800590 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800591 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800592 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800593 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 1800594 | Huntington |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800595 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
RR
|  |  | 1800596 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800597 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800598 | Dekalb | August Mack Environmental, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
RR
|  |  | 1800599 | Wabash | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800600 | Steuben | ABt SRBI | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1800601 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1800602 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
RR
|  |  | 1800603 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800604 | Allen |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1800605 | Allen |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800606 | Miami |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800607 | Miami |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800608 | Elkhart |  | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1800609 | Adams |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1800610 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1800611 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1800612 | Elkhart |  | Indiana Department of Transportation | 2020-08-05 | PE
|  |  | 1800613 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1800614 | Wells |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1800615 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1800616 | Elkhart |  | Indiana Department of Transportation | 2020-10-07 | PE
|  |  | 1800617 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2021-05-05 | PE
|  |  | 1800618 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800619 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1800620 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1800621 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800622 |  | Consolidated Test Company | Indiana Department of Transportation | 2024-07-10
|  |  | 1800623 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-03-04
|  |  | 1800624 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-03-04
|  |  | 1800625 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800626 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800627 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 1800628 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1800629 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800630 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800631 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 1800632 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800633 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800634 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-03-04
|  |  | 1800635 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800636 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800637 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800638 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800639 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1800640 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
RR
|  |  | 1800641 | Henry |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1800642 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1800643 |  |  | LaGrange County | 2018-05-31
|  |  | 1800644 |  |  | LaGrange County | 2018-05-31
|  |  | 1800645 |  |  | LaGrange County | 2018-05-31
|  |  | 1800646 | Clark |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1800647 |  |  | LaGrange County | 2018-05-31
|  |  | 1800648 | Putnam |  | Indiana Department of Transportation | 2022-07-13 | PE
|  |  | 1800649 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1800650 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800651 | Hendricks |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800652 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800653 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800654 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1800655 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1800656 |  | Archonsortium, LLC | Indiana Department of Transportation | 2023-02-15
|  |  | 1800657 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1800658 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800659 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1800660 | Morgan |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1800661 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1800662 | Hendricks |  | Indiana Department of Transportation | 2022-08-10 | PE
|  |  | 1800663 | Putnam |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1800664 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2023-02-15
|  |  | 1800665 | Putnam |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1800666 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-11-10
|  |  | 1800667 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800668 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 2020-11-10
|  |  | 1800669 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800670 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1800671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800672 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800673 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800674 | Hendricks |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1800675 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800676 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800677 | Wells | Hrezo Engineering, Inc. | Indiana Department of Transportation | 2021-12-08 | RR
|  |  | 1800678 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1800679 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800680 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
RR
|  |  | 1800681 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800682 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800683 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800684 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800685 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2024-02-14
|  |  | 1800686 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800687 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-09-15
|  |  | 1800688 |  | MCIS LLC | Indiana Department of Transportation | 2020-12-09
|  |  | 1800689 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | 2024-02-14
|  |  | 1800690 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1800691 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1800692 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800693 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800694 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800695 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800696 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-11-10
|  |  | 1800697 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800698 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
RR
|  |  | 1800699 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800700 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800701 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800702 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800703 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800704 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1800705 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1800706 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1800707 |  | Certified Engineering, Inc. | Fremont | 2018-05-31
|  |  | 1800708 |  | C Blair Enterprises, Inc. | Elkhart | 2018-05-31
|  |  | 1800709 |  | C Blair Enterprises, Inc. | Elkhart | 2018-05-31
|  |  | 1800710 |  | C Blair Enterprises, Inc. | Elkhart | 2018-05-31
|  |  | 1800711 |  | C Blair Enterprises, Inc. | Elkhart | 2018-05-31
|  |  | 1800712 |  |  | Monroe County | -339679.2083
|  |  | 1800713 |  | A & H Surveying, Inc. | Altona | 2018-05-31
|  |  | 1800714 |  |  | Switzerland County | -339679.2083
|  |  | 1800715 | Marion | DCD Consulting LLC | Indianapolis | 2022-11-16 | PE
|  |  | 1800716 |  | B. L. A., Inc. | Corydon | -339679.2083
|  |  | 1800717 |  | MHM Associates, Inc. | Warren | 2018-05-31
|  |  | 1800718 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1800719 | Jennings |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800720 | Hendricks |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1800721 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1800722 | Marion |  | Indiana Department of Transportation | 2018-12-12 | CN
|  |  | 1800723 | Marion |  | Indiana Department of Transportation | 2019-09-11 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1800724 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 1800725 | Morgan |  | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1800726 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1800727 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1800728 | Warrick |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800729 | Marion |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1800730 | Monroe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800731 | Sullivan |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800732 | Gibson |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800733 | Monroe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800734 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1800735 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1800736 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800737 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1800738 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1800739 | Shelby |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
PE
|  |  | 1800740 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1800741 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1800742 | Jay | IXOYE, Limited | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1800743 | Randolph | CKW Land Surveying, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800744 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2022-02-09 | RR
|  |  | 1800745 | Hancock |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  |  | Madison |  | Indiana Department of Transportation | 2020-12-09 | CE
|  |  | 1800746 | Washington |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800747 | Fayette | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | 2020-04-01 | CE
CN
RR
|  |  |  | Franklin | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1800748 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1800749 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800750 | Henry | Dillabaugh, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  |  | Rush | Dillabaugh, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800751 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1800752 | Tipton | Land Construction Corp | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1800753 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1800754 | Hamilton | ACME | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800755 | Tipton | Land Construction Corp | Indiana Department of Transportation | 2021-05-05 | CE
CN
RR
|  |  | 1800756 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1800757 | Hancock |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800758 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2021-10-14 | CN
RR
|  |  | 1800759 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800760 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1800761 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800762 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800763 | Rush | Civil Designs, LLP | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800764 | Marion |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1800765 | Howard |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800766 | Randolph |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800767 | Randolph |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800768 | Henry | Bowman, Barrett & Associates, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800769 | Henry |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800770 | Henry | Kinzelman Kline Gossman | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800771 | Marion |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800772 | Shelby |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800773 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1800774 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2019-05-31
|  |  | 1800775 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800776 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800777 | White |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800778 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1800779 | Madison | Hey and Associates, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800780 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800781 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800782 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1800783 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1800784 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1800785 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1800786 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 1800787 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800788 | Marshall |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800789 | Marshall |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800790 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1800791 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800792 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800793 | White | Fugro Roadware, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800794 | Carroll |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800795 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1800796 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800797 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800798 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800799 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800800 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800801 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 1800802 |  | Cornerstone Design | Indiana Department of Transportation | 2021-02-10
|  |  | 1800803 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800804 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800805 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1800806 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2020-11-10
|  |  | 1800807 | Floyd |  | Indiana Department of Transportation | 2023-09-13 | PE
|  |  | 1800808 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800809 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1800810 | Monroe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800811 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800812 | Floyd |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800813 | Carroll |  | Indiana Department of Transportation | 2021-02-10 | CN
|  |  |  | White |  | Indiana Department of Transportation | 2021-02-10 | CE
|  |  | 1800814 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-03-10
|  |  | 1800815 |  | American Commercial Title & Escrow | Indiana Department of Transportation | -339679.2083
|  |  | 1800816 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800817 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800818 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800819 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800820 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800821 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800822 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800823 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800824 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800825 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800826 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800827 | Cass | Eco Logic, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
RR
|  |  | 1800828 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800829 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800830 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800831 | Marshall |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800832 | Lake |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800833 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 1800834 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 1800835 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800836 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800837 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800838 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1800839 | Marshall |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800840 | Marshall |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800841 |  | Edwards and Kelcey | Indiana Department of Transportation | 2022-04-06
|  |  | 1800842 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800843 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800844 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800845 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800846 | Jasper |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800847 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-12-09
|  |  | 1800848 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2020-12-09
|  |  | 1800849 | Fulton | InfoTech | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1800850 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800851 | Starke |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800852 | Starke |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800853 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 1800854 |  | Integrated Environmental Solutions, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800855 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800856 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1800857 | Jasper |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800858 |  | MCIS LLC | Indiana Department of Transportation | 2020-12-09
|  |  | 1800859 | Jasper |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800860 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 1800861 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1800862 | Jasper |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1800863 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1800864 | Marion |  | Indiana Department of Transportation | 2022-05-31 | CN
|  |  | 1800865 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1800866 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1800867 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1800868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800869 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2022-09-14
|  |  | 1800870 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1800871 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2020-11-10
|  |  | 1800872 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1800873 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800874 | St. Joseph |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1800875 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1800876 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
PE
|  |  | 1800877 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1800878 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1800879 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1800880 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1800881 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1800882 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1800883 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1800884 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1800885 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1800886 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1800887 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1800888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800889 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800890 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800891 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800892 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800893 | Harrison |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
PE
|  |  | 1800894 | Ohio |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
PE
|  |  | 1800895 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800896 | Franklin |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1800897 | Gibson |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800898 | Gibson |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800899 |  | Alfred Benesch & Company | Franklin County | -339679.2083
|  |  | 1800900 |  |  | Floyd County | 2023-07-12
|  |  | 1800901 | Daviess |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800902 |  | ABt SRBI | Angola | 2018-05-31
|  |  | 1800903 |  | ABt SRBI | Angola | 2018-05-31
|  |  | 1800904 |  | Dorochoff Consulting, LLC | La Fontaine | 2018-05-31
|  |  | 1800905 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 1800906 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800907 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1800908 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800909 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1800910 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1800911 | Knox |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800912 | Pike |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800913 | Pike |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800914 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800915 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1800916 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800917 | Crawford |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800918 | Knox |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800919 | Warrick |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800920 | Posey |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800921 | Sullivan |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1800922 | Spencer |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1800923 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 1800924 | St. Joseph | HDR Engineering, Inc. | Indiana Department of Transportation | 2020-08-05 | RR
|  |  | 1800925 |  | HDR Engineering, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 1800926 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1800927 | Jasper |  | Indiana Department of Transportation | 2020-05-07 | PE
|  |  | 1800928 | Marshall | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800929 | Cass | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2021-03-10 | CE
CN
RR
|  |  | 1800930 | Owen |  | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1800931 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800932 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-12-08
|  |  | 1800933 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1800934 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800935 | Posey |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1800936 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1800937 | Posey |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1800938 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1800939 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1800940 | Various |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1800941 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800942 | Various |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
PE
|  |  | 1800943 | Allen |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1800944 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  | 1800945 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1800946 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1800947 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1800948 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1800949 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1800950 | Various |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 1800951 | Crawford |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800952 | Warrick |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800953 | Warrick |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
PE
|  |  | 1800954 | Daviess | Houseal Lavigne Associates | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1800955 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-08-10
|  |  | 1800956 |  | EFI Global, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1800957 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1800958 | Spencer |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1800959 | Spencer | JJR, LLC | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1800960 | Crawford | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1800961 | Crawford | Aarcher, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  |  | Dubois | Aarcher, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1800962 | Orange | Hannum, Wagle & Cline Engineering | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1800963 | Crawford | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
|  |  |  | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1800964 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 1800965 |  | Frost Engineering & Consulting Company | Indiana Department of Transportation | 2022-12-07
|  |  | 1800966 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1800967 | Lawrence |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1800968 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800969 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1800970 |  | Aarcher, Inc. | Indiana Department of Transportation | 2022-09-14
|  |  | 1800971 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1800972 |  | ARCADIS | Indiana Department of Transportation | 2020-10-07
|  |  | 1800973 |  | CGI | Vanderburgh County | -339679.2083
|  |  | 1800974 | Daviess |  | Daviess County | 2021-03-10 | CE
CN
PE
ROW
UT
|  |  | 1800975 |  |  | Warrick County | -339679.2083
|  |  | 1800976 | Knox | Louis Joyner, Architect | Vincennes | 2022-09-14 | PE
ROW
|  |  | 1800977 | Lawrence |  | Lawrence County | 2020-09-02 | CE
CN
PE
|  |  | 1800978 | Sullivan | Klug Engineering, Inc. | Sullivan | 2021-09-15 | CE
CN
PE
|  |  | 1800979 | Crawford |  | Crawford County | 2020-11-10 | CE
CN
PE
|  |  | 1800980 |  | Eagle Ridge Civil Engineering Services, LLC | Linton | -339679.2083
|  |  | 1800981 |  | Home Equity Appraisals | Pike County | -339679.2083
|  |  | 1800982 |  | DuSABLE, Inc. | Tippecanoe County | -339679.2083
|  |  | 1800983 |  |  | Vermillion County | -339679.2083
|  |  | 1800984 | Daviess | AMEC E&I, Inc. | Washington | 2023-02-15 | PE
ROW
|  |  | 1800985 |  | Infrastructure Engineering, Inc. | Rockport | -339679.2083
|  |  | 1800986 | Knox |  | Knox County | 2022-02-09 | PE
ROW
|  |  | 1800987 |  | HLRD | North Salem | -339679.2083
|  |  | 1800988 | Perry |  | Tell City | 2022-04-06 | PE
|  |  | 1800989 | Johnson |  | Johnson County | -339679.2083 | RR
|  |  | 1800990 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 1800991 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 1800992 |  | ARCADIS | Indiana Department of Transportation | 2020-09-02
|  |  | 1800993 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 1800994 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800995 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1800996 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800997 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1800998 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1800999 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1801000 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1801001 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1801002 | Morgan |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
ROW
|  |  | 1801003 |  | DCD Consulting LLC | Indianapolis | 2021-05-31
|  |  | 1801004 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801005 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801006 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801007 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801008 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801009 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801010 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801011 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801012 | Franklin |  | Indiana Department of Transportation | 2023-10-12 | PE
|  |  | 1801013 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1801014 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1801015 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1801016 | Owen |  | Indiana Department of Transportation | 2022-08-10 | RR
|  |  | 1801017 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1801018 | Morgan |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1801019 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1801020 | Morgan |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
ROW
|  |  | 1801021 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801022 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801023 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801024 | Morgan |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
ROW
|  |  | 1801025 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1801026 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801027 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801028 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1801029 | Morgan |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801030 | Franklin |  | Indiana Department of Transportation | 2023-10-12 | PE
|  |  | 1801031 | Morgan |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801032 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801033 |  | CGI | Indiana Department of Transportation | 2016-12-14
|  |  | 1801034 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1801035 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1801036 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801037 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801038 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801039 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801040 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1801041 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1801042 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1801043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801045 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801046 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801047 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801048 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801049 |  |  | Indiana Department of Transportation | 2018-12-12
|  |  | 1801050 |  |  | Indiana Department of Transportation | 2018-12-12
|  |  | 1801051 | Morgan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1801052 | Morgan |  | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1801053 |  | Gandhi and Associates, Inc. | Nappanee | 2018-05-31
|  |  | 1801054 |  | Gandhi and Associates, Inc. | Nappanee | 2018-05-31
|  |  | 1801055 |  | Gandhi and Associates, Inc. | Nappanee | 2018-05-31
|  |  | 1801056 |  | Gandhi and Associates, Inc. | Nappanee | 2018-05-31
|  |  | 1801057 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801058 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801059 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801060 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801061 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801062 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1801063 |  |  | Grant County | 2018-05-31
|  |  | 1801064 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1801065 |  | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2020-11-10
|  |  | 1801066 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 1801067 |  | Alfred Benesch & Company | Indiana Department of Transportation | 2020-07-08
|  |  | 1801068 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801069 |  | Alfred Benesch & Company | Indiana Department of Transportation | 2021-04-07
|  |  | 1801070 |  | GSG Consultants, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1801071 |  | CGS Real Estate Services, LLC | Indiana Department of Transportation | 2022-01-12
|  |  | 1801072 | Delaware |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1801073 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801074 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
RR
|  |  | 1801075 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
PE
RR
|  |  | 1801076 | Randolph |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1801077 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801078 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801079 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801080 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801081 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801082 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801083 | Howard |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801084 | Howard |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801085 | Howard |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801086 | Howard |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801087 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801088 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1801089 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1801090 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801091 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1801092 | Fulton |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1801093 | LaPorte |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1801094 | Lake | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2019-11-14 | PE
|  |  | 1801095 | St. Joseph |  | Indiana Department of Transportation | 2020-07-08 | PE
|  |  | 1801096 | Porter |  | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1801097 | Jasper |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1801098 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801099 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 1801100 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1801101 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1801102 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1801103 |  | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801104 | Wells |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1801105 | Noble |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1801106 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2022-09-14
|  |  | 1801107 | Wabash |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801108 | Wabash |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801109 | Kosciusko |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1801110 | Allen |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1801111 | Miami |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1801112 | Grant |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801113 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801114 | Grant |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801115 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801116 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1801117 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801118 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801119 | Wabash |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801120 | Marshall | Bayer & Becker, Inc. | Culver | 2021-07-14 | CE
CN
PE
ROW
|  |  | 1801121 | Grant |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1801122 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1801123 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1801124 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1801125 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-12-11 | CE
CN
|  |  | 1801126 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801127 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-12-11 | PE
|  |  | 1801128 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801129 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801130 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801131 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801132 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801133 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801134 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801135 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801136 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1801137 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801138 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801139 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801140 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801141 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801142 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801143 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801144 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801145 | Wabash |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801146 | Wabash |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801147 | Elkhart |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801148 | Elkhart | Civil Inspection Services, LLC | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1801149 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1801150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801151 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2020-03-04
|  |  | 1801152 | Kosciusko |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801153 | Grant |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801154 | Elkhart |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801155 | Jackson |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1801156 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1801157 | Jackson |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1801158 | Elkhart |  | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801159 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1801160 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1801161 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1801162 |  | Fusion by Design, Inc. | Montpelier | 2018-05-31
|  |  | 1801163 | Jackson |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801164 |  |  | Pierceton | 2018-05-31
|  |  | 1801165 | Grant | Dave Helton & Associates, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1801166 | Wabash | HE-BFS, LLC | Indiana Department of Transportation | 2020-02-05 | PE
|  |  | 1801167 | Adams |  | Indiana Department of Transportation | 2020-03-04 | PE
|  |  | 1801168 | Harrison |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1801169 | Jackson |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801170 | Bartholomew |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1801171 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1801172 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1801173 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801174 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1801175 | Washington |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1801176 | Scott |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1801177 | Scott |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1801178 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801180 | Cass |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
RR
|  |  | 1801181 | Adams | Bidinfo | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1801182 | Cass |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1801183 | Cass |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
PE
|  |  | 1801184 | Marshall |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1801185 | Marshall |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
PE
|  |  | 1801186 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1801187 | Grant |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
PE
|  |  | 1801188 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801189 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801190 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1801191 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801192 | Huntington |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1801193 | Huntington |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
PE
|  |  | 1801194 | Allen |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1801195 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1801196 | Dekalb |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801197 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1801198 | Allen |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1801199 | Jasper |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1801200 | Decatur |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1801201 | Decatur |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
PE
|  |  | 1801202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801204 | Allen |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1801205 | Allen |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1801206 | Allen |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1801207 | Allen |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1801208 | Allen |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
PE
|  |  | 1801209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801211 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801212 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1801213 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1801214 |  |  | Andrews | 2018-05-31
|  |  | 1801215 |  | Consolidated Test Company | Indiana Department of Transportation | 2020-03-04
|  |  | 1801216 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1801217 |  | Enginuity Management & Consulting Corporation | Markle | 2018-05-31
|  |  | 1801218 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 1801219 | LaPorte |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2021-01-13 | PE
|  |  | 1801220 |  | Merle Edward Orem | Wolcottville | 2018-05-31
|  |  | 1801221 |  | Kruse Consulting, Inc. | Swayzee | 2018-05-31
|  |  | 1801222 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1801223 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1801224 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801225 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1801226 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801227 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801228 | Various |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801229 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1801230 | Various |  | Indiana Department of Transportation | 2021-05-31 | CN
|  |  | 1801231 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1801232 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801233 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801234 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1801235 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2018-05-31
|  |  | 1801236 | Dekalb |  | Indiana Department of Transportation | 2018-04-11 | CE
CN
|  |  | 1801237 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801238 | Marshall | Bayer & Becker, Inc. | Culver | 2021-01-13 | CE
CN
PE
|  |  | 1801239 | Marshall | Bayer & Becker, Inc. | Culver | 2021-01-13 | CE
CN
PE
|  |  | 1801240 | St. Joseph |  | South Bend | 2021-12-08 | CN
PE
|  |  | 1801241 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2024-07-10
|  |  | 1801242 |  |  | Adams County | 2018-05-31
|  |  | 1801243 |  |  | Adams County | 2018-05-31
|  |  | 1801244 |  |  | Adams County | 2018-05-31
|  |  | 1801245 | Monroe |  | MPO - Bloomington | -339679.2083 | PL
|  |  | 1801246 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801247 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801248 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801249 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801250 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801251 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801252 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801253 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801254 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801255 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801256 | Various |  | Indiana Department of Transportation | 2019-05-31 | PE
|  |  | 1801257 |  |  | Indiana Department of Transportation | 2018-10-11
|  |  | 1801258 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801259 |  |  | Indiana Department of Transportation | 2018-10-11
|  |  | 1801260 |  |  | Indiana Department of Transportation | 2018-10-11
|  |  | 1801261 | Vigo | Bayswater Company, LLC | Terre Haute | -339679.2083 | RR
|  |  | 1801262 | Grant | ERES International, Inc. | Marion | -339679.2083 | RR
|  |  | 1801263 | Grant | ERES International, Inc. | Marion | -339679.2083 | RR
|  |  | 1801264 |  | Dorochoff Consulting, LLC | Indiana Department of Transportation | 2020-05-31
|  |  | 1801265 | Elkhart | Civil Inspection Services, LLC | Goshen | -339679.2083 | RR
|  |  | 1801266 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801267 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1801268 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  | 1801269 | Fulton | 2IM Group, LLC | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801270 | Huntington |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  |  | Various |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801271 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801272 | Marion | DCD Consulting LLC | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1801273 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801274 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801275 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801276 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801277 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801278 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801279 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801280 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801281 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801282 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801283 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801284 |  | D L Savage Engineering, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1801285 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801286 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801287 | Clark | Jacobs Pannicke Architects, Inc. | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1801288 | Bartholomew |  | Bartholomew County | -339679.2083 | RR
|  |  | 1801289 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801290 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1801291 | Bartholomew |  | MPO - Columbus | -339679.2083 | PL
|  |  | 1801292 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2018-05-31
|  |  | 1801293 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2017-01-19
|  |  | 1801294 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801295 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 1801296 | Various |  | Indiana Department of Transportation | 2018-10-15 | CN
|  |  | 1801297 |  |  | Indiana Department of Transportation | 2019-04-15
|  |  | 1801298 |  |  | Indiana Department of Transportation | 2019-11-20
|  |  | 1801299 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2019-11-20 | CE
CN
|  |  | 1801300 | Vermillion |  | Indiana Department of Transportation | 2020-04-01 | RR
|  |  | 1801301 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801302 | Vermillion |  | Indiana Department of Transportation | 2020-04-01 | RR
|  |  | 1801303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801305 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801307 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801308 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801309 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1801310 | Various |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1801311 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 1801312 | Various |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801313 | Jennings |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1801314 | Various |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801315 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801316 |  | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | 2021-03-10
|  |  | 1801317 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1801318 | Johnson |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1801319 | Lawrence |  | Indiana Department of Transportation | 2020-10-07 | CN
|  |  |  | Ripley |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1801320 | Various |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1801321 | Howard |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 1801322 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801323 | Tippecanoe |  | MPO - Lafayette | -339679.2083 | PL
|  |  | 1801324 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  | 1801325 | Delaware |  | MPO - Muncie | -339679.2083 | PL
|  |  | 1801326 |  | Collins Engineers Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 1801327 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801328 |  |  | Indiana State Agencies | 2020-03-04
|  |  | 1801329 |  | Burgess & Niple, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801331 |  | Dodd Title Corporation | Indiana Department of Transportation | 2022-09-14
|  |  | 1801332 |  |  | MPO - Evansville | -339679.2083
|  |  | 1801333 |  |  | MPO - Evansville | -339679.2083
|  |  | 1801334 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2019-12-11
|  |  | 1801335 |  |  | MPO - Evansville | -339679.2083
|  |  | 1801336 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801337 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801338 | Tippecanoe |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1801339 |  |  | MPO - Evansville | -339679.2083
|  |  | 1801340 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1801341 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1801342 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801343 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801344 | Tippecanoe |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1801345 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1801346 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1801347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801348 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801349 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1801350 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801351 | Fountain | Linda F. Russell | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1801352 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1801353 | Tippecanoe |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1801354 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801355 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1801356 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1801357 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1801358 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1801359 | Porter |  | MPO - Northwest | -339679.2083 | PL
|  |  | 1801360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801361 |  |  | Terre Haute | -339679.2083
|  |  | 1801362 | Elkhart |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  |  | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 1801363 |  |  | Indiana Department of Transportation | 2018-05-10
|  |  | 1801364 | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 1801365 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1801366 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 1801367 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1801368 |  |  | Indiana State Agencies | -339679.2083
|  |  | 1801369 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1801370 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1801371 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801372 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801373 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2021-01-13 | CE
CN
PE
|  |  | 1801374 | Bartholomew |  | Indiana Department of Transportation | 2021-02-10 | PE
|  |  | 1801375 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1801376 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801377 | Lawrence |  | Indiana Department of Transportation | 2021-08-11 | CN
PE
|  |  | 1801378 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801379 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801380 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801381 |  |  | Indiana Department of Transportation | 2018-05-18
|  |  | 1801382 |  |  | Vigo County | 2019-05-31
|  |  | 1801383 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801384 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1801385 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1801386 |  |  | Monroe County | -339679.2083
|  |  | 1801387 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801388 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801389 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2021-05-05 | CE
CN
ROW
|  |  | 1801390 |  |  | Bloomington Public Transportation Corp | -339679.2083
|  |  | 1801391 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801392 | Various |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1801393 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801394 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 1801395 | Monroe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801396 | Monroe |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801397 | Dubois |  | Indiana Department of Transportation | 2021-04-07 | PE
|  |  |  | Various |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
|  |  | 1801398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801399 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1801400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801401 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1801402 | Various |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
RR
|  |  | 1801403 | Various |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801404 | Various |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
PE
|  |  | 1801405 | Various |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
RR
|  |  | 1801406 | Various |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801407 | Various |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1801408 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 1801409 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1801410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801411 | Various |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1801412 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1801413 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1801414 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1801415 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1801416 | Dearborn | Kaskaskia Engineering Group | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  |  | Franklin | Kaskaskia Engineering Group | Indiana Department of Transportation | 2020-04-01 | CE
|  |  | 1801417 |  | Linda F. Russell | Indiana Department of Transportation | 2023-02-15
|  |  | 1801418 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1801419 |  |  | Morgan County | -339679.2083
|  |  | 1801420 |  | CPS Acquisitions, LLC | Fishers | 2022-12-07
|  |  | 1801421 |  |  | Hamilton County | 2022-12-07
|  |  | 1801422 | Marion | ASC Group, Inc. | Beech Grove | 2021-10-14 | CE
CN
|  |  | 1801423 |  | CoCal Consulting, LLC | Greenfield | 2022-10-13
|  |  | 1801424 |  | CoCal Consulting, LLC | Greenfield | 2023-11-15
|  |  | 1801425 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 1801426 | Allen | EDP Consultants | Leo-Cedarville | 2023-10-12 | PE
|  |  | 1801427 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1801428 | Hendricks |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1801429 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1801430 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1801431 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801432 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801433 |  |  | Westfield | 2022-07-13
|  |  | 1801434 | Hamilton |  | Westfield | 2021-07-14 | CN
|  |  | 1801435 | Hamilton | Another Test Company | Carmel | 2018-09-12 | CE
CN
|  |  | 1801436 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801437 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2022-09-14
|  |  | 1801438 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2022-09-14
|  |  | 1801439 |  | DCD Consulting LLC | Indianapolis | 2022-10-13
|  |  | 1801440 | Marion | DCD Consulting LLC | Indianapolis | 2021-10-14 | CE
CN
|  |  | 1801441 |  | DCD Consulting LLC | Indianapolis | 2022-09-14
|  |  | 1801442 | Marion | DCD Consulting LLC | Indianapolis | 2021-10-14 | CE
CN
|  |  | 1801443 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1801444 |  | DCD Consulting LLC | Indianapolis | 2022-08-10
|  |  | 1801445 | Marion | DCD Consulting LLC | Indianapolis | 2021-10-14 | CE
CN
|  |  | 1801446 |  | DCD Consulting LLC | Indianapolis | 2022-10-13
|  |  | 1801447 |  | DCD Consulting LLC | Indianapolis | 2022-07-13
|  |  | 1801448 |  | DCD Consulting LLC | Indianapolis | 2022-07-13
|  |  | 1801449 | Johnson | Casteel Real Estate | Franklin | 2021-11-17 | CE
CN
|  |  | 1801450 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1801451 | Johnson | Casteel Real Estate | Franklin | 2020-07-08 | CE
CN
|  |  | 1801452 |  |  | Johnson County | 2022-02-09
|  |  | 1801453 | Various |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1801454 |  |  | Johnson County | 2022-03-09
|  |  | 1801455 |  | Commonwealth Engineers, Inc. | Johnson County | 2022-07-13
|  |  | 1801456 |  |  | Indiana Department of Natural Resources | 2019-03-06
|  |  | 1801457 |  |  | Indiana Department of Natural Resources | 2019-03-06
|  |  | 1801458 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801459 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801460 |  |  | Indiana Department of Natural Resources | 2019-03-06
|  |  | 1801461 | Various |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1801462 |  |  | Plainfield | -339679.2083
|  |  | 1801463 |  | AFRAM Group, Incorporated | Avon | 2022-11-16
|  |  | 1801464 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801465 |  | Iteris, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801466 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1801467 |  | ABt SRBI | Indiana Department of Transportation | 2018-07-11
|  |  | 1801468 |  | ABt SRBI | Indiana Department of Transportation | 2018-07-11
|  |  | 1801469 |  | Farren Real Estate Services | Indiana Department of Transportation | 2018-07-11
|  |  | 1801470 |  | Finley Engineering Group, Inc. | Indiana Department of Transportation | 2018-07-11
|  |  | 1801471 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2018-07-11
|  |  | 1801472 |  | Jones & Henry Engineers, Ltd. | Indiana Department of Transportation | 2018-07-11
|  |  | 1801473 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2018-07-11
|  |  | 1801474 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | 2018-07-11
|  |  | 1801475 |  | Debbie L. Morris | Indiana Department of Transportation | 2018-07-11
|  |  | 1801476 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1801477 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1801478 |  |  | Indiana Department of Transportation | 2018-07-11
|  |  | 1801479 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | 2018-07-11
|  |  | 1801480 | Grant |  | Indiana Department of Transportation | 2018-08-08 | CE
CN
|  |  | 1801481 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801482 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801483 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801484 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1801485 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1801486 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1801487 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1801488 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1801489 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1801490 | Floyd |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801491 | LaPorte |  | Indiana Department of Transportation | 2018-03-14 | CN
|  |  | 1801492 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1801493 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1801494 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2019-05-09
|  |  | 1801495 |  |  | Indiana Department of Transportation | 2018-09-12
|  |  | 1801496 |  |  | Kokomo Transit | -339679.2083
|  |  | 1801497 |  |  | Kokomo Transit | -339679.2083
|  |  | 1801498 |  |  | MPO - Muncie | -339679.2083
|  |  | 1801499 |  |  | MPO - Muncie | -339679.2083
|  |  | 1801500 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2021-04-07
|  |  | 1801501 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2021-04-07
|  |  | 1801502 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2019-12-11
|  |  | 1801503 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2019-12-11
|  |  | 1801504 | St. Joseph |  | Indiana Department of Transportation | 2021-04-07 | PE
|  |  | 1801505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801506 |  | Engineering Resources, Inc. | Madison | 2022-11-16
|  |  | 1801507 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801508 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801510 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801511 |  |  | MPO - Louisville | -339679.2083
|  |  | 1801512 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801513 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801514 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801515 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1801516 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801518 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801519 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801520 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801521 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801522 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801523 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801524 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1801525 | Monroe |  | Indiana Department of Transportation | 2019-11-14 | CE
CN
|  |  | 1801526 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801527 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801528 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801529 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801530 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801531 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801532 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801533 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801534 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801535 |  | ASC Group, Inc. | Indiana Department of Transportation | 2018-09-12
|  |  | 1801536 |  | DCD Consulting LLC | Indiana Department of Transportation | 2018-08-08
|  |  | 1801537 |  | DCD Consulting LLC | Indiana Department of Transportation | 2018-09-12
|  |  | 1801538 |  | DCD Consulting LLC | Indiana Department of Transportation | 2018-08-08
|  |  | 1801539 |  |  | Indiana Department of Transportation | 2018-09-12
|  |  | 1801540 | Greene |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1801541 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 1801542 |  |  | Indiana Department of Transportation | 2018-11-15
|  |  | 1801543 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801544 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801545 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801546 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801547 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801548 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801549 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1801550 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801551 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801552 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801553 |  | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 2018-08-08
|  |  | 1801554 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2018-08-08
|  |  | 1801555 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801556 | Hamilton | CPS Acquisitions, LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  |  | Marion | CPS Acquisitions, LLC | Indiana Department of Transportation | 2019-04-17 | CE
|  |  | 1801557 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801558 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801559 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801560 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801561 |  | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2017-01-19
|  |  | 1801562 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801563 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801564 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801565 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801566 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801567 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801568 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801569 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801570 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801571 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801572 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801574 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801575 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801576 | Marion | Another Test Company | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1801577 | Boone |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1801578 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1801579 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1801580 | Floyd |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  | 1801581 | Floyd |  | Floyd County | 2022-02-09 | PE
|  |  | 1801582 | Floyd |  | Floyd County | 2022-02-09 | PE
|  |  | 1801583 | Floyd |  | New Albany | 2019-03-06 | CN
|  |  | 1801584 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801585 |  | All About Pavements, Inc. | Brownsburg | -339679.2083
|  |  | 1801586 | Switzerland |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1801587 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801588 | Harrison |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  | 1801589 | Floyd |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  | 1801590 | Floyd |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  |  | Harrison |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  | 1801591 | Floyd |  | Indiana Department of Transportation | 2017-08-09 | CN
|  |  | 1801592 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2021-09-15 | CE
CN
|  |  | 1801593 |  |  | Crawford County | 2019-05-31
|  |  | 1801594 |  |  | Crawford County | -339679.2083
|  |  | 1801595 | Clark |  | Clarksville | 2020-05-07 | CN
|  |  | 1801596 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2017-08-09 | CN
|  |  | 1801597 | Clark |  | Clarksville | 2022-07-13 | PE
|  |  | 1801598 |  |  | Indiana Department of Transportation | 2018-05-31
|  |  | 1801599 | Clark |  | Clarksville | 2019-01-16 | CN
|  |  | 1801600 | Floyd |  | New Albany | 2019-03-06 | CE
CN
|  |  | 1801601 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2019-11-14 | CE
CN
|  |  | 1801602 | Gibson |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801603 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801604 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801605 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801606 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801607 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801609 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801611 | Elkhart | C Blair Enterprises, Inc. | Elkhart | 2023-10-12 | PE
|  |  | 1801612 |  |  | Elkhart County | -339679.2083
|  |  | 1801613 |  | Civil Inspection Services, LLC | Goshen | -339679.2083
|  |  | 1801614 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801615 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  | 1801616 | Adams |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801617 | Adams |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801618 | Adams |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801619 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801620 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  | 1801621 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801622 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  | 1801623 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  | 1801624 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
PL
|  |  | 1801625 |  |  | MPO - Louisville | 2019-05-01
|  |  | 1801626 | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 2019-07-10 | RR
|  |  | 1801627 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2019-07-10
|  |  | 1801628 | Fountain | Delcan Corporation | Indiana Department of Transportation | 2019-05-09 | CE
CN
PE
|  |  |  | Various | Delcan Corporation | Indiana Department of Transportation | 2019-05-09 | CE
|  |  | 1801629 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1801630 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801631 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801632 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801633 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801634 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801635 |  |  | Indiana Department of Transportation | 2018-08-08
|  |  | 1801636 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801637 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801638 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801639 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801640 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801641 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801642 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801643 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801644 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801645 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801646 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801647 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801648 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801649 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801650 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801651 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801652 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801653 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1801654 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801655 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801656 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801657 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801658 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801659 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801660 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801661 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801662 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801663 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801664 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1801665 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1801666 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2019-08-07 | CE
CN
|  |  | 1801667 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801668 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801669 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801670 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801671 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801672 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801673 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801674 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801675 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801676 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801677 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801678 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801679 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1801680 | Various |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1801681 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 1801682 | Various |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1801683 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1801684 | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1801685 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1801686 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1801687 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801688 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801689 |  | ERES International, Inc. | Indiana Department of Transportation | 2019-04-03
|  |  | 1801690 |  | GMG INC. | Indiana Department of Transportation | 2019-04-03
|  |  | 1801691 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801692 |  | Loftus Engineering, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1801693 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CN
|  |  | 1801694 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CN
|  |  | 1801695 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13 | CE
CN
RR
UT
|  |  | 1801696 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801697 | Johnson | DCD Consulting LLC | Indiana Department of Transportation | 2020-11-18 | CE
CN
PE
UT
|  |  |  | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-11-18 | CN
|  |  | 1801698 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801699 | Starke |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801700 | Lake |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801701 | Lake |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801702 | Marshall |  | Indiana Department of Transportation | 2019-05-31 | CN
|  |  | 1801703 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-03-01
|  |  | 1801704 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-03-01
|  |  | 1801705 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-03-01
|  |  | 1801706 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801707 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801708 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801709 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801710 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801711 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1801712 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801713 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CE
CN
|  |  | 1801714 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801715 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1801716 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801717 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801718 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801719 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801720 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1801721 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1801722 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2017-03-01
|  |  | 1801723 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-03-01
|  |  | 1801724 |  | Another Test Company | Indiana Department of Transportation | 2017-03-01
|  |  | 1801725 |  | CGI | Evansville | 2024-12-11
|  |  | 1801726 |  | CGI | Evansville | 2022-12-07
|  |  | 1801727 | Vanderburgh | CGI | Evansville | 2022-01-12 | ROW
|  |  | 1801728 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801729 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801730 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801731 | Hamilton |  | Westfield | 2022-12-07 | PE
|  |  | 1801732 |  |  | Indiana Department of Transportation | 2018-09-12
|  |  | 1801733 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801734 |  |  | Indiana Department of Transportation | 2017-08-09
|  |  | 1801735 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801736 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801737 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1801738 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2021-05-05 | CE
CN
PE
|  |  | 1801739 | LaGrange |  | Indiana Department of Transportation | 2018-10-11 | CE
CN
|  |  | 1801740 |  | CPS Acquisitions, LLC | Fishers | 2019-12-11
|  |  | 1801741 | Marion | DCD Consulting LLC | Indianapolis | 2019-09-11 | CE
CN
|  |  | 1801742 |  | Another Test Company | Indiana Department of Transportation | 2017-03-01
|  |  | 1801743 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801744 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1801745 |  | Dyer Environmental Services | Indiana Department of Transportation | 2017-01-19
|  |  | 1801746 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-01-19
|  |  | 1801747 |  | DCD Consulting LLC | Indiana Department of Transportation | 2017-01-19
|  |  | 1801748 |  | D & D Consulting Services, Inc. | Huntertown | 2022-10-13
|  |  | 1801749 | Allen | D & D Consulting Services, Inc. | Huntertown | 2022-10-13 | PE
|  |  | 1801750 | Marion |  | Indiana Department of Natural Resources | -339679.2083 | PE
|  |  | 1801751 | Marion |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 1801752 | Various |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 1801753 | Dekalb |  | Indiana Department of Natural Resources | 2020-05-31 | CN
PE
|  |  | 1801754 | Henry |  | Indiana Department of Natural Resources | 2020-05-31 | PE
|  |  | 1801755 | Dearborn |  | Indiana Department of Natural Resources | 2020-05-31 | CN
PE
|  |  | 1801756 | Vigo |  | Indiana Department of Natural Resources | 2020-05-31 | PE
|  |  | 1801757 | Porter |  | Indiana Department of Natural Resources | 2020-05-31 | PE
|  |  | 1801758 | Jay |  | Indiana Department of Natural Resources | 2020-05-31 | PE
|  |  | 1801759 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1801760 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1801761 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1801762 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1801763 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801764 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801765 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801766 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801767 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801768 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1801769 |  |  | Indiana Department of Transportation | 2025-02-05
|  |  | 1801770 |  |  | Indiana Department of Transportation | 2025-02-05
|  |  | 1801771 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801772 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801773 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801774 | Randolph | Langworthy, Strader, LeBlanc & Associates, Inc. | Indiana Department of Transportation | 2019-12-11 | CE
CN
RR
|  |  | 1801775 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1801776 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1801777 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1801778 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2016-12-14
|  |  | 1801779 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801780 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801781 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801782 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801783 |  |  | Wells County | -339679.2083
|  |  | 1801784 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1801785 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801786 | Jefferson |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1801787 | Harrison |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1801788 |  | Lonco, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1801789 | Jefferson |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1801790 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801791 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801792 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801793 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801794 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801795 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801796 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801797 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801798 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801799 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1801800 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1801801 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801802 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1801803 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1801804 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1801805 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 1801806 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1801807 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1801808 |  | CET, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801809 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801810 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801811 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801812 |  | DCD Consulting LLC | Indiana Department of Transportation | 2018-10-11
|  |  | 1801813 |  | Consolidated Test Company | Indiana Department of Transportation | 2019-12-11
|  |  | 1801814 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2018-09-12
|  |  | 1801815 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801816 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801817 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801818 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801819 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2019-04-03
|  |  | 1801820 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801821 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801822 | Marion | DCD Consulting LLC | Indianapolis | 2019-11-14 | CN
|  |  | 1801823 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1801824 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
PE
|  |  | 1801825 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1801826 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1801827 | Vanderburgh | CGI | Evansville | 2019-05-31 | PE
|  |  | 1801828 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1801829 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1801830 | Vigo |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1801831 | LaPorte |  | LaPorte County | 2025-01-15 | PE
|  |  | 1801832 | Various |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
PE
|  |  | 1801833 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801834 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801835 | Various |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801836 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2018-11-15 | CE
CN
|  |  | 1801837 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801838 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801839 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801841 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801842 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801843 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801844 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801845 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801846 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801847 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801848 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801849 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1801850 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801851 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | 2018-12-12 | CE
CN
|  |  | 1801852 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801854 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801855 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801856 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801857 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801859 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801861 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801863 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801864 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801865 |  |  | Hamilton County | 2022-12-07
|  |  | 1801866 |  |  | Hamilton County | 2022-12-07
|  |  | 1801867 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801868 |  | MCIS LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1801869 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801870 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801871 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801872 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801873 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1801874 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801875 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1801876 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801877 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801878 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801879 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801880 | Marion |  | Indiana Department of Transportation | 2019-01-16 | CE
CN
|  |  | 1801881 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1801882 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1801883 |  |  | Indiana Department of Transportation | 2018-10-11
|  |  | 1801884 |  |  | Gary | -339679.2083
|  |  | 1801885 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1801886 |  | Carters Appraisal Service | Frankfort | -339679.2083
|  |  | 1801887 |  | Huff & Huff, Inc. | Portage | -339679.2083
|  |  | 1801888 |  |  | Hendricks County | -339679.2083
|  |  | 1801889 |  |  | Clarksville | -339679.2083
|  |  | 1801890 |  | Global Management Group, Inc. | Allen County | -339679.2083
|  |  | 1801891 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 1801892 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801893 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801894 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801895 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801896 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801897 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801898 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801899 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801901 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801902 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801903 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801904 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801905 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801906 |  | Courtland Title & Escrow, Inc. | Hobart | 2022-08-10
|  |  | 1801907 |  | Consolidated Test Company | Hammond | 2023-07-12
|  |  | 1801908 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801909 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | -339679.2083
|  |  | 1801910 |  |  | St. Joseph County | -339679.2083
|  |  | 1801911 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2023-07-12
|  |  | 1801912 |  | Douglass Environmental Services, Inc. | La Porte | 2023-04-12
|  |  | 1801913 |  |  | Elkhart County | 2023-05-10
|  |  | 1801914 |  |  | Tippecanoe County | -339679.2083
|  |  | 1801915 |  | M-E Companies, Inc. | Wabash | 2023-03-15
|  |  | 1801916 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | -339679.2083
|  |  | 1801917 |  |  | Wells County | -339679.2083
|  |  | 1801918 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801919 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801921 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801922 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801923 |  |  | Montgomery County | -339679.2083
|  |  | 1801924 |  |  | Vanderburgh County | 2023-05-10
|  |  | 1801925 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1801926 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1801927 | Jay |  | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801928 |  |  | Elkhart County | 2023-01-19
|  |  | 1801929 | Various |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1801930 |  |  | Albion | -339679.2083
|  |  | 1801931 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 1801932 |  | Bayswater Company, LLC | Terre Haute | 2023-04-12
|  |  | 1801933 |  | C Blair Enterprises, Inc. | Elkhart | 2023-04-12
|  |  | 1801934 |  |  | Floyd County | -339679.2083
|  |  | 1801935 |  |  | Kosciusko County | 2022-05-05
|  |  | 1801936 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1801937 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801938 |  |  | Indiana Department of Transportation | 2018-11-15
|  |  | 1801939 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2020-07-08
|  |  | 1801940 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1801941 | Spencer |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1801942 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1801943 | Various |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1801944 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801945 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801946 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801947 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801948 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1801949 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801950 | Bartholomew |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1801951 | Various |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1801952 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1801953 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1801954 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2019-02-06 | CE
CN
|  |  | 1801955 |  |  | Michigan City Transit | -339679.2083
|  |  | 1801956 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1801957 |  | AAC Environmental Consulting, LLC | Adams County | -339679.2083
|  |  | 1801958 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 1801959 | Various |  | Indiana Department of Transportation | 2019-10-09 | CE
CN
|  |  | 1801960 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1801961 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1801962 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1801963 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1801964 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1801965 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801966 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801967 |  | Associated Right-of-Way Services, Inc. | Columbus | -339679.2083
|  |  | 1801968 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1801969 | Vanderburgh | CGI | Evansville | 2021-02-10 | CE
CN
PE
|  |  | 1801970 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1801971 | Various |  | Indiana Department of Transportation | 2019-03-06 | CE
CN
|  |  | 1801972 | Various |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1801973 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801974 |  |  | Indiana Department of Transportation | 2018-12-12
|  |  | 1801975 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801976 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801977 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801978 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1801979 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1801980 |  |  | Indiana Department of Transportation | 2018-11-15
|  |  | 1801981 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1801982 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801983 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1801984 |  |  | South Bend Transit | -339679.2083
|  |  | 1801985 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801986 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801987 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801988 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801989 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1801990 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801991 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801992 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801993 |  |  | Indiana Department of Natural Resources | 2019-02-06
|  |  | 1801994 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801995 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801996 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801997 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801998 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1801999 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802000 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802001 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802002 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1802003 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1802004 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1802005 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1802006 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1802007 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802008 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802009 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802010 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802011 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802012 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802013 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802014 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802015 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802016 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802017 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802018 |  |  | Indiana Department of Transportation | 2019-01-23
|  |  | 1802019 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802020 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802021 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802022 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802023 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802024 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802025 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1802026 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802027 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802028 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802029 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802030 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802031 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802032 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802033 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802034 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1802035 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802036 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802037 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802038 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802039 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802040 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802042 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802043 |  |  | Indiana Department of Transportation | 2021-01-13
|  |  | 1802044 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1802045 |  |  | Indiana Department of Transportation | 2021-01-13
|  |  | 1802046 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1802047 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1802048 |  |  | Vanderburgh County | 2021-12-08
|  |  | 1802049 | Warrick |  | Warrick County | 2024-07-10 | PE
|  |  | 1802050 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-08-11 | CN
PE
|  |  | 1802051 | Marshall | ACMS Group, Inc. | Indiana Department of Transportation | 2023-01-19 | PE
|  |  | 1802052 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1802053 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1802054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802055 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1802056 | Wayne |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1802057 | Delaware |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1802058 | Randolph |  | Indiana Department of Transportation | 2022-04-20 | PE
|  |  | 1802059 | Delaware |  | Indiana Department of Transportation | 2022-09-14 | PE
|  |  | 1802060 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1802061 | Various |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1802062 | Various |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1802063 | Various |  | Indiana Department of Transportation | 2021-11-17 | CE
CN
PE
|  |  | 1802064 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1802065 |  | EHI Consultants, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1802066 | Hancock |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1802067 | Hamilton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1802068 | Hamilton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1802069 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802070 | Various |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1802071 | Various |  | Indiana Department of Transportation | 2022-04-06 | PE
UT
|  |  | 1802072 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802074 |  |  | Vanderburgh County | 2023-07-12
|  |  | 1802075 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13 | CE
CN
RR
UT
|  |  | 1802076 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802077 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802078 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802079 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802081 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802082 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2019-07-10
|  |  | 1802083 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1802084 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2019-07-10
|  |  | 1802085 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1802086 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2025-02-12
|  |  | 1802087 |  | CGI | Indiana Department of Transportation | 2026-02-11
|  |  | 1802088 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802089 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1802090 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1802091 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1802092 | Bartholomew |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
RR
|  |  | 1802093 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 1802094 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802095 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802096 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802097 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802098 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802099 | Hamilton | CPS Acquisitions, LLC | Fishers | 2019-01-16 | CN
|  |  | 1802100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802101 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802102 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802103 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802104 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802105 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1802106 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1802107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802108 | Marion | DCD Consulting LLC | Indianapolis | 2021-09-15 | CN
|  |  | 1802109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802110 |  |  | Indiana Department of Transportation | 2019-01-16
|  |  | 1802111 |  | KERAMIDA Environmental, Inc. | Speedway | 2019-05-31
|  |  | 1802112 |  | ASA Land Surveying | Bedford | 2019-05-31
|  |  | 1802113 |  | J. H. Rudolph & Co., Inc. | Royal Center | 2019-05-31
|  |  | 1802114 |  |  | Rush County | 2019-05-31
|  |  | 1802115 |  | Duesler Realty House | Lagrange | 2019-05-31
|  |  | 1802116 |  | DCD Consulting LLC | Indianapolis | 2019-05-31
|  |  | 1802117 |  | H&H Associates, LLC | Newton County | 2020-05-31
|  |  | 1802118 |  | American Resources Group, Ltd. | Cambridge City | 2019-05-31
|  |  | 1802119 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2019-05-31
|  |  | 1802120 |  | Carters Appraisal Service | Frankfort | 2019-05-31
|  |  | 1802121 |  | Haas & Associates, L.L.C. | Oldenburg | 2019-05-31
|  |  | 1802122 |  | Lorenz Williams Clinton | Vevay | 2019-05-31
|  |  | 1802123 |  |  | Perry County | 2019-05-31
|  |  | 1802124 |  | McDonough Associates, Inc. | Winfield | 2019-05-31
|  |  | 1802125 |  | American Engineers, Inc. | Butler | 2019-05-31
|  |  | 1802126 |  | J. H. Rudolph & Co., Inc. | Royal Center | 2019-05-31
|  |  | 1802127 |  | Apex Engineering, Inc. | Cayuga | 2019-05-31
|  |  | 1802128 |  | ASC Group, Inc. | Beech Grove | 2019-05-31
|  |  | 1802129 |  | Feutz Contractors, Inc. | Middletown | 2019-05-31
|  |  | 1802130 |  | J.F. New & Associates, Inc. | Russiaville | 2019-05-31
|  |  | 1802131 |  |  | Dekalb County | 2019-05-31
|  |  | 1802132 |  |  | Chesterton | 2019-05-31
|  |  | 1802133 |  | AAC Environmental Consulting, LLC | Anderson | 2019-05-31
|  |  | 1802134 |  |  | Knox County | 2019-05-31
|  |  | 1802135 |  | Feutz Contractors, Inc. | Middletown | 2019-05-31
|  |  | 1802136 |  |  | Monroe County | -339679.2083
|  |  | 1802137 |  | Duke Energy Corporation | Lagro | 2019-05-31
|  |  | 1802138 |  | Booker Real Estate Services | Dune Acres | 2019-05-31
|  |  | 1802139 |  | Farren Real Estate Services | Middlebury | 2019-05-31
|  |  | 1802140 |  | Farren Real Estate Services | Middlebury | 2019-05-31
|  |  | 1802141 |  | Booker Real Estate Services | Dune Acres | 2019-05-31
|  |  | 1802142 |  | Eco-Tech Consultants, Inc. | Long Beach | 2019-05-31
|  |  | 1802143 |  | Independent Appraisers-Consultants, Inc. | Remington | 2019-05-31
|  |  | 1802144 |  |  | Tippecanoe County | 2019-05-31
|  |  | 1802145 |  |  | Starke County | 2019-05-31
|  |  | 1802146 |  |  | Starke County | 2019-05-31
|  |  | 1802147 |  |  | Chesterton | 2019-05-31
|  |  | 1802148 |  |  | Chesterton | 2019-05-31
|  |  | 1802149 |  |  | Chesterton | 2019-05-31
|  |  | 1802150 |  |  | Monon | 2019-05-31
|  |  | 1802151 |  | H.R. Gray | North Judson | 2019-05-31
|  |  | 1802152 |  |  | Chesterton | 2019-05-31
|  |  | 1802153 |  |  | Chesterton | 2019-05-31
|  |  | 1802154 |  |  | Wells County | 2019-05-31
|  |  | 1802155 |  |  | Cumberland | 2019-05-31
|  |  | 1802156 |  |  | Cumberland | 2019-05-31
|  |  | 1802157 |  | Lonco, Inc. | Versailles | 2019-05-31
|  |  | 1802158 |  | Martinez Corporation | Whitestown | 2019-05-31
|  |  | 1802159 |  | Burgess & Niple, Inc. | Eaton | 2019-05-31
|  |  | 1802160 |  | Engineering Technologies, Inc. | Marengo | 2019-05-31
|  |  | 1802161 |  | I. T. Business Corporation | Poseyville | 2019-05-31
|  |  | 1802162 |  | Duesler Realty House | Lagrange | 2019-05-31
|  |  | 1802163 |  | Lang, Feeney & Associates, Inc. | Ulen | 2019-05-31
|  |  | 1802164 |  | Booker Real Estate Services | Dune Acres | 2019-05-31
|  |  | 1802165 |  | Global Land Surveying, LLC | New Harmony | 2019-05-31
|  |  | 1802166 |  | Andrews Engineering, Inc. | Cannelton | 2019-05-31
|  |  | 1802167 |  |  | Boone County | 2019-05-31
|  |  | 1802168 |  | Bonar Group, LLC | Dugger | 2019-05-31
|  |  | 1802169 |  | Lorenz Williams Clinton | Vevay | 2019-05-31
|  |  | 1802170 |  | Holloway Engineering, LLC | Peru | 2020-05-31
|  |  | 1802171 |  | American Structurepoint, Inc. | Camden | 2019-05-31
|  |  | 1802172 |  |  | Darmstadt | 2019-05-31
|  |  | 1802173 |  | American Structurepoint, Inc. | Camden | 2019-05-31
|  |  | 1802174 |  |  | Albion | 2019-05-31
|  |  | 1802175 |  | Burrell Appraisal Service, Inc. | Edinburgh | -339679.2083
|  |  | 1802176 |  | Innis Consulting Group, LLC | Rocky Ripple | 2019-05-31
|  |  | 1802177 |  | Mader Design, LLC | Waterloo | -339679.2083
|  |  | 1802178 |  |  | Boone County | 2019-05-31
|  |  | 1802179 |  | Integra Realty Resources | Rosedale | -339679.2083
|  |  | 1802180 |  | Integra Realty Resources | Rosedale | -339679.2083
|  |  | 1802181 |  |  | Whitley County | 2019-05-31
|  |  | 1802182 |  | Environmental Solutions & Innovations, Inc. | Mecca | -339679.2083
|  |  | 1802183 |  | Duneland Group, Inc. | Lapel | 2019-05-31
|  |  | 1802184 |  | Home Equity Appraisals | Petersburg | 2019-05-31
|  |  | 1802185 |  |  | Whitley County | 2019-05-31
|  |  | 1802186 |  | ATSI Engineering Services | Beverly Shores | 2019-05-31
|  |  | 1802187 |  | CTL Engineering of Indiana, Inc. | Allen County | 2020-05-31
|  |  | 1802188 |  | Commonwealth Heritage Group, Inc. | Greenville | -339679.2083
|  |  | 1802189 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2019-05-31
|  |  | 1802190 |  | Commonwealth Heritage Group, Inc. | Adams County | -339679.2083
|  |  | 1802191 |  | Commonwealth Heritage Group, Inc. | Greenville | -339679.2083
|  |  | 1802192 |  | John Milner Associates, Architects, Archeologists, Planners, | Shoals | 2020-05-31
|  |  | 1802193 |  | John Milner Associates, Architects, Archeologists, Planners, | Shoals | 2019-05-31
|  |  | 1802194 |  |  | Ohio County | 2019-05-31
|  |  | 1802195 |  | Hardlines Design Company | Ossian | 2019-05-31
|  |  | 1802196 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2019-05-31
|  |  | 1802197 |  |  | Ohio County | 2019-05-31
|  |  | 1802198 |  | Compass Rose Consulting, LLC | Griffin | 2019-05-31
|  |  | 1802199 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2019-05-31
|  |  | 1802200 |  | Anelena Ackerly | Carlisle | 2019-05-31
|  |  | 1802201 |  |  | Vanderburgh County | 2019-05-31
|  |  | 1802202 |  | Anelena Ackerly | Carlisle | 2019-05-31
|  |  | 1802203 |  |  | Jefferson County | -339679.2083
|  |  | 1802204 |  | Delcan Corporation | Kingman | 2020-05-31
|  |  | 1802205 |  |  | Switzerland County | 2019-05-31
|  |  | 1802206 |  | Keeler-Webb Associates | St. Paul | 2019-05-31
|  |  | 1802207 |  | Delcan Corporation | Kingman | 2020-05-31
|  |  | 1802208 |  | McDonough Associates, Inc. | Winfield | 2019-05-31
|  |  | 1802209 |  | McDonough Associates, Inc. | Winfield | 2019-05-31
|  |  | 1802210 |  | McDonough Associates, Inc. | Winfield | 2019-05-31
|  |  | 1802211 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802212 |  | Atlas Appraisals, LLC | Converse | 2019-05-31
|  |  | 1802213 |  |  | Randolph County | 2019-05-31
|  |  | 1802214 |  |  | Shadeland | -339679.2083
|  |  | 1802215 |  |  | Crawford County | 2019-05-31
|  |  | 1802216 |  |  | Spiceland | 2019-05-31
|  |  | 1802217 |  | CivCon Services, Inc. | Gentryville | 2019-05-31
|  |  | 1802218 |  | David Matthews Associates (Former) | Kempton | 2019-05-31
|  |  | 1802219 |  |  | Switzerland County | 2019-05-31
|  |  | 1802220 |  |  | Wells County | 2019-05-31
|  |  | 1802221 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2019-05-31
|  |  | 1802222 |  |  | Wells County | 2019-05-31
|  |  | 1802223 |  |  | Moores Hill | 2019-05-31
|  |  | 1802224 |  |  | Jay County | 2019-05-31
|  |  | 1802225 |  | Heritage Engineering, LLC | Patoka | 2019-05-31
|  |  | 1802226 |  |  | Scott County | -339679.2083
|  |  | 1802227 |  | Larry J. Allison | Uniondale | 2020-05-31
|  |  | 1802228 |  | Heritage Engineering, LLC | Patoka | 2019-05-31
|  |  | 1802229 |  |  | Dearborn County | 2019-05-31
|  |  | 1802230 |  | American Surveying & Engineering, P.C. | Campbellsburg | 2019-05-31
|  |  | 1802231 |  | CHA, Inc. | Farmersburg | 2019-05-31
|  |  | 1802232 |  |  | Warren County | 2019-05-31
|  |  | 1802233 |  | CHA, Inc. | Farmersburg | 2019-05-31
|  |  | 1802234 |  | I. T. Business Corporation | Poseyville | 2019-05-31
|  |  | 1802235 |  | H W Lochner, Inc. | Newport | -339679.2083
|  |  | 1802236 |  | Home Equity Appraisals | Petersburg | 2019-05-31
|  |  | 1802237 |  |  | Franklin County | 2019-05-31
|  |  | 1802238 |  | HNTB Indiana, Inc. | Oakland City | 2019-05-31
|  |  | 1802239 |  |  | Aurora | 2020-05-31
|  |  | 1802241 |  |  | Whitley County | 2019-05-31
|  |  | 1802242 |  | HOH Engineers, Inc. | Oaktown | 2019-05-31
|  |  | 1802243 |  | Mader Design, LLC | Waterloo | 2019-05-31
|  |  | 1802244 |  | Clark Dietz, Inc. | Grandview | 2019-05-31
|  |  | 1802245 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2019-05-31
|  |  | 1802246 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2019-05-31
|  |  | 1802247 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2019-05-31
|  |  | 1802248 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2019-05-31
|  |  | 1802249 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2019-05-31
|  |  | 1802250 |  |  | Shadeland | 2019-05-31
|  |  | 1802251 |  | CGS Real Estate Services, LLC | Fairmount | 2019-05-31
|  |  | 1802252 |  | Corradino, LLC | Hillsboro | 2019-05-31
|  |  | 1802253 |  |  | Dillsboro | 2019-05-31
|  |  | 1802254 |  | D L Savage Engineering, Inc. | Hymera | 2020-05-31
|  |  | 1802255 |  |  | Berne | 2019-05-31
|  |  | 1802256 |  | D L Savage Engineering, Inc. | Hymera | 2020-05-31
|  |  | 1802257 |  | Associated Right-of-Way Services, Inc. | Columbus | 2019-05-31
|  |  | 1802258 |  | Fanning Howey Associates | Merom | 2019-05-31
|  |  | 1802259 |  |  | Berne | 2019-05-31
|  |  | 1802260 |  |  | Berne | 2019-05-31
|  |  | 1802261 |  |  | Berne | 2019-05-31
|  |  | 1802262 |  |  | Berne | 2019-05-31
|  |  | 1802263 |  |  | Berne | 2019-05-31
|  |  | 1802264 |  |  | Berne | 2019-05-31
|  |  | 1802265 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 1802266 |  |  | Berne | 2019-05-31
|  |  | 1802267 |  |  | Berne | -339679.2083
|  |  | 1802268 |  |  | Berne | 2019-05-31
|  |  | 1802269 |  |  | Berne | 2019-05-31
|  |  | 1802270 |  |  | Berne | 2019-05-31
|  |  | 1802271 |  |  | Berne | 2019-05-31
|  |  | 1802272 |  | EFI Global, Inc. | Lewisville | 2019-05-31
|  |  | 1802273 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802274 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802275 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802276 |  | HLRD | North Salem | -339679.2083
|  |  | 1802277 |  |  | Knox | 2019-05-31
|  |  | 1802278 |  | Approved Appraisals of Indiana, LLC | Clay City | -339679.2083
|  |  | 1802279 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802280 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802281 |  |  | Knox | 2019-05-31
|  |  | 1802282 |  | Carters Appraisal Service | Frankfort | 2019-05-31
|  |  | 1802283 |  | Land Consultants, Inc. | Topeka | -339679.2083
|  |  | 1802284 |  | Civil & Environmental Consultants, Inc. | Georgetown | 2019-05-31
|  |  | 1802285 |  |  | Randolph County | 2019-05-31
|  |  | 1802286 |  | Foresight Land Surveying, Inc. | Monroe | 2019-05-31
|  |  | 1802287 |  |  | Lake County | 2019-05-31
|  |  | 1802288 |  | Linda F. Russell | Veedersburg | 2019-05-31
|  |  | 1802289 |  | Linda F. Russell | Veedersburg | 2019-05-31
|  |  | 1802290 |  |  | Alexandria | 2019-05-31
|  |  | 1802291 |  | Andy Easley Engineering, Inc. | Carbon | -339679.2083
|  |  | 1802292 |  | Bayer & Becker, Inc. | Culver | 2019-05-31
|  |  | 1802293 |  | Bayer & Becker, Inc. | Culver | 2019-05-31
|  |  | 1802294 |  | Marine Solutions, Inc. | Westville | 2019-05-31
|  |  | 1802295 |  | Chicago Title Insurance Company | Gas City | -339679.2083
|  |  | 1802296 |  | MainLine Management, Inc. | Waynetown | 2019-05-31
|  |  | 1802297 |  | Douglass Environmental Services, Inc. | LaPorte County | 2019-05-31
|  |  | 1802298 |  |  | Fountain County | 2019-05-31
|  |  | 1802299 |  | Mark Keutzer, Appraiser | Wheatland | 2019-05-31
|  |  | 1802300 |  | Bayer & Becker, Inc. | Culver | 2019-05-31
|  |  | 1802301 |  |  | Alexandria | 2019-05-31
|  |  | 1802302 |  | Bayer & Becker, Inc. | Culver | 2019-05-31
|  |  | 1802303 |  | Mader Design, LLC | Waterloo | 2019-05-31
|  |  | 1802304 |  | Bayer & Becker, Inc. | Culver | 2019-05-31
|  |  | 1802305 |  | Duesler Realty House | Lagrange | 2019-05-31
|  |  | 1802306 |  | Burrell Appraisal Service, Inc. | Edinburgh | -339679.2083
|  |  | 1802307 |  | AECOM Technical Services, Inc. | Ashley | 2019-05-31
|  |  | 1802308 |  | D & D Consulting Services, Inc. | Huntertown | 2019-05-31
|  |  | 1802309 |  | Holloway Engineering, LLC | Peru | -339679.2083
|  |  | 1802310 |  |  | Ashley | 2019-05-31
|  |  | 1802312 |  | AECOM Technical Services, Inc. | Ashley | 2019-05-31
|  |  | 1802313 |  | Houseal Lavigne Associates | Plainville | 2019-05-31
|  |  | 1802314 |  | CGS Real Estate Services, LLC | Fairmount | 2019-05-31
|  |  | 1802315 |  |  | Warren County | 2019-05-31
|  |  | 1802316 |  |  | Tell City | 2019-05-31
|  |  | 1802317 |  |  | Porter County | 2019-05-31
|  |  | 1802318 |  | CGS Real Estate Services, LLC | Fairmount | 2019-05-31
|  |  | 1802319 |  | Houseal Lavigne Associates | Plainville | 2019-05-31
|  |  | 1802320 |  |  | Warren County | 2019-05-31
|  |  | 1802321 |  | Lonco, Inc. | Versailles | 2019-05-31
|  |  | 1802322 |  |  | Franklin County | 2019-05-31
|  |  | 1802323 |  |  | Warren County | 2019-05-31
|  |  | 1802324 |  |  | Porter County | 2019-05-31
|  |  | 1802325 |  | Dillterra LLC | Knightsville | -339679.2083
|  |  | 1802326 |  | Horn and Associates, Inc. | Pittsboro | -339679.2083
|  |  | 1802327 |  |  | Clinton County | 2019-05-31
|  |  | 1802328 |  | Indiana Acquisition of Indiana, LLC | Richland | 2019-05-31
|  |  | 1802329 |  | Ark Engineering Services, Inc. | Coatesville | -339679.2083
|  |  | 1802330 |  | Appraisal Service | Chalmers | 2019-05-31
|  |  | 1802331 |  | Bayer & Becker, Inc. | Culver | 2019-05-31
|  |  | 1802332 |  | Eco-Tech Consultants, Inc. | Long Beach | 2019-05-31
|  |  | 1802333 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2019-05-31
|  |  | 1802334 |  | 40th Parallel Surveying, LLC | Albany | 2019-05-31
|  |  | 1802335 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2019-05-31
|  |  | 1802336 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2019-05-31
|  |  | 1802337 |  | Eco-Tech Consultants, Inc. | Long Beach | 2019-05-31
|  |  | 1802338 |  | Appraisers, Inc. | Chrisney | 2019-05-31
|  |  | 1802339 |  | Robert Neal Sanders | Shamrock | 2019-05-31
|  |  | 1802340 |  | Beacon Surveying and Engineering | Cynthiana | 2019-05-31
|  |  | 1802341 |  |  | Clinton County | 2019-05-31
|  |  | 1802342 |  | Commonwealth Engineers, Inc. | Greenwood | 2019-05-31
|  |  | 1802343 |  | Clyde L. Hawkins | Greendale | 2019-05-31
|  |  | 1802344 |  |  | Albion | 2019-05-31
|  |  | 1802345 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802346 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802347 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802348 |  |  | Vanderburgh County | 2019-05-31
|  |  | 1802349 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802350 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802351 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802352 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2019-05-31
|  |  | 1802353 |  |  | Clermont | 2019-05-31
|  |  | 1802354 |  | Afram Corporation | Brookston | 2019-05-31
|  |  | 1802355 |  | CPS Acquisitions, LLC | Fishers | 2019-05-31
|  |  | 1802356 |  | D & D Consulting Services, Inc. | Huntertown | 2019-05-31
|  |  | 1802357 |  | Driesenga & Associates, Inc. | Ladoga | -339679.2083
|  |  | 1802358 |  |  | Wabash County | -339679.2083
|  |  | 1802359 |  |  | Sandborn | 2019-05-31
|  |  | 1802360 |  | Domain Architecture, Inc. | Kouts | 2020-05-31
|  |  | 1802361 |  | Kinzelman Kline Gossman | Straughn | 2019-05-31
|  |  | 1802362 |  | Corradino, LLC | Hillsboro | 2019-05-31
|  |  | 1802363 |  |  | Aurora | 2020-05-31
|  |  | 1802364 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1802365 |  |  | Fountain County | 2019-05-31
|  |  | 1802366 |  | Kevin K. Parsons & Associates, Inc. | Staunton | -339679.2083
|  |  | 1802367 |  | Jeffrey P. French & Associates Land Surveying | Shelburn | 2019-05-31
|  |  | 1802368 |  |  | Blackford County | 2019-05-31
|  |  | 1802369 |  |  | Porter County | 2019-05-31
|  |  | 1802370 |  |  | Porter County | 2019-05-31
|  |  | 1802371 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-05-31
|  |  | 1802372 |  |  | Franklin County | 2019-05-31
|  |  | 1802373 |  | Martin Riley, Inc. | Whiteland | 2019-05-31
|  |  | 1802374 |  | Bidinfo | Decatur | 2019-05-31
|  |  | 1802375 |  | Bidinfo | Decatur | 2019-05-31
|  |  | 1802376 |  | Edwards and Kelcey | Lowell | 2020-05-31
|  |  | 1802377 |  | MainLine Management, Inc. | Waynetown | 2019-05-31
|  |  | 1802378 |  | Beam, Longest and Neff, LLC | Dana | -339679.2083
|  |  | 1802379 |  | CKW Land Surveying, Inc. | Farmland | 2019-05-31
|  |  | 1802380 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1802381 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1802382 |  |  | Michiana Shores | 2019-05-31
|  |  | 1802383 |  |  | Saratoga | 2019-05-31
|  |  | 1802384 |  | Douglass Environmental Services, Inc. | LaPorte County | 2019-05-31
|  |  | 1802385 |  | M.A.T. Consulting, Inc. | Walkerton | 2019-05-31
|  |  | 1802386 |  | Jeffrey S. Juday | Shelbyville | 2019-05-31
|  |  | 1802387 |  | Boomerang Ventures, LLC | Dunkirk | 2019-05-31
|  |  | 1802388 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1802389 |  |  | Daleville | 2019-05-31
|  |  | 1802390 |  | AI Engineers, Inc. | Bainbridge | -339679.2083
|  |  | 1802391 |  | CE Solutions, Inc. | Elwood | 2019-05-31
|  |  | 1802392 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1802393 |  | AI Engineers, Inc. | Bainbridge | -339679.2083
|  |  | 1802394 |  | Jacobs Engineering Group, Inc. | Seelyville | -339679.2083
|  |  | 1802395 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1802396 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 1802397 |  | Jacobs Engineering Group, Inc. | Seelyville | -339679.2083
|  |  | 1802398 |  | Jacobs Engineering Group, Inc. | Seelyville | -339679.2083
|  |  | 1802399 |  | CGS Real Estate Services, LLC | Fairmount | 2019-05-31
|  |  | 1802400 |  | Appraisal Office of Central Indiana | Centerville | 2019-05-31
|  |  | 1802402 |  | Indiana University | Roachdale | -339679.2083
|  |  | 1802404 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-05-31
|  |  | 1802405 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-05-31
|  |  | 1802406 |  | Dynasty Group, Inc. | Lawrenceburg | 2019-05-31
|  |  | 1802407 |  |  | Bartholomew County | 2019-05-31
|  |  | 1802408 |  | CGS Real Estate Services, LLC | Fairmount | 2019-05-31
|  |  | 1802409 |  | Digital Appraisals, LLC | Kirklin | 2019-05-31
|  |  | 1802410 |  | CE Solutions, Inc. | Elwood | 2019-05-31
|  |  | 1802411 |  | CE Solutions, Inc. | Elwood | 2019-05-31
|  |  | 1802413 |  | Beam, Longest and Neff, LLC | Dana | -339679.2083
|  |  | 1802414 |  | Chastain & Associates LLC | Pine Village | 2019-05-31
|  |  | 1802415 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2019-05-31
|  |  | 1802416 |  | Digital Appraisals, LLC | Kirklin | 2019-05-31
|  |  | 1802418 |  |  | Michigantown | 2019-05-31
|  |  | 1802420 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-05-31
|  |  | 1802421 |  | Foresight Land Surveying, Inc. | Monroe | 2019-05-31
|  |  | 1802422 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2019-05-31
|  |  | 1802423 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-05-31
|  |  | 1802424 |  |  | French Lick | 2019-05-31
|  |  | 1802425 |  | Applied Research Associates, Inc. | Center Point | -339679.2083
|  |  | 1802426 |  |  | Knox | 2019-05-31
|  |  | 1802427 |  |  | Randolph County | 2019-05-31
|  |  | 1802428 |  | MCCARTIN - ASSOCIATES | Walton | 2019-05-31
|  |  | 1802429 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802430 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802431 |  | Eel River Abstract | Lynn | 2019-05-31
|  |  | 1802432 |  | AMEC E&I, Inc. | Washington | 2019-05-31
|  |  | 1802433 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2019-05-31
|  |  | 1802434 |  | Lamac Engineering Company | Thorntown | 2019-05-31
|  |  | 1802435 |  | Associated Right-of-Way Services, Inc. | Columbus | 2019-05-31
|  |  | 1802436 |  | Associated Right-of-Way Services, Inc. | Columbus | 2019-05-31
|  |  | 1802437 |  | EnviroScience, Inc. | Martinsville | 2019-05-31
|  |  | 1802438 |  |  | Newburgh | 2020-05-31
|  |  | 1802439 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1802440 |  | Central Diving Contractors | Frankton | 2019-05-31
|  |  | 1802441 |  |  | Hagerstown | 2019-05-31
|  |  | 1802442 |  |  | Hagerstown | 2019-05-31
|  |  | 1802443 |  | BradsKo Engineering and Surveying Inc. | Dupont | 2019-05-31
|  |  | 1802444 |  |  | Clarksville | 2019-05-31
|  |  | 1802445 |  | BradsKo Engineering and Surveying Inc. | Dupont | 2019-05-31
|  |  | 1802446 |  | Jill D Reed and Associates, Inc. | Sheridan | 2019-05-31
|  |  | 1802447 |  | Jill D Reed and Associates, Inc. | Sheridan | 2019-05-31
|  |  | 1802448 |  | EnviroScience, Inc. | Martinsville | 2019-05-31
|  |  | 1802450 |  | Jill D Reed and Associates, Inc. | Sheridan | 2019-05-31
|  |  | 1802451 |  | Associated Right-of-Way Services, Inc. | Columbus | 2019-05-31
|  |  | 1802452 |  | Associated Right-of-Way Services, Inc. | Columbus | 2019-05-31
|  |  | 1802453 |  | Jill D Reed and Associates, Inc. | Sheridan | 2019-05-31
|  |  | 1802454 |  | Associated Right-of-Way Services, Inc. | Columbus | 2019-05-31
|  |  | 1802455 |  | Jean Stewart, LLC | Sharpsville | 2019-05-31
|  |  | 1802456 |  |  | Decatur County | 2019-05-31
|  |  | 1802458 |  |  | Decatur County | 2019-05-31
|  |  | 1802459 |  |  | Decatur County | 2019-05-31
|  |  | 1802460 |  | Alliance Survey Company | Bryant | 2019-05-31
|  |  | 1802461 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802462 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802463 |  |  | New Richmond | 2019-05-31
|  |  | 1802464 |  | CDM Smith, Inc. | Fowler | -339679.2083
|  |  | 1802465 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802466 |  |  | Decatur County | 2019-05-31
|  |  | 1802467 |  | Michael Baker International, Inc. | Yorktown | 2019-05-31
|  |  | 1802468 |  | ERES International, Inc. | Ligonier | 2020-05-31
|  |  | 1802469 |  | AV Consulting Engineers, Inc. | Bicknell | 2019-05-31
|  |  | 1802470 |  | Accu-Air Surveys, Inc. | Boonville | 2019-05-31
|  |  | 1802471 |  | Michael Baker International, Inc. | Yorktown | 2019-05-31
|  |  | 1802472 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802473 |  | Jeffrey S. Juday | Shelbyville | 2019-05-31
|  |  | 1802474 |  | Coor Consulting | Haubstadt | 2019-05-31
|  |  | 1802475 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802476 |  |  | Knox | 2019-05-31
|  |  | 1802477 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802478 |  | Certified Engineering, Inc. | Fremont | 2019-05-31
|  |  | 1802479 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 1802480 |  | Edwards and Kelcey | Lowell | 2019-05-31
|  |  | 1802481 |  | Commonwealth Engineers, Inc. | Greenwood | -339679.2083
|  |  | 1802482 |  | CDM Smith, Inc. | Fowler | -339679.2083
|  |  | 1802483 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802484 |  | CDM Smith, Inc. | Fowler | -339679.2083
|  |  | 1802485 |  | CDM Smith, Inc. | Fowler | -339679.2083
|  |  | 1802486 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802487 |  |  | Clarks Hill | 2019-05-31
|  |  | 1802488 |  | Coor Consulting | Haubstadt | 2019-05-31
|  |  | 1802489 |  | ACMS Group, Inc. | Argos | 2019-05-31
|  |  | 1802490 |  | Capstone, Inc. | Francesville | 2020-05-31
|  |  | 1802491 |  | GS-IN P.C. | Muncie | 2019-05-31
|  |  | 1802492 |  | Leitner and Associates, Inc. | Valparaiso | 2019-05-31
|  |  | 1802493 |  | Matt L. Nepote, MAI | Whiting | 2019-05-31
|  |  | 1802494 |  | Coor Consulting | Haubstadt | 2019-05-31
|  |  | 1802495 |  | Heritage Appraisal Service | Parker City | 2019-05-31
|  |  | 1802496 |  | Jeffrey S. Juday | Shelbyville | 2019-05-31
|  |  | 1802497 |  | BA Martin Architects, PC | Covington | 2019-05-31
|  |  | 1802498 |  | Michael Baker International, Inc. | Yorktown | 2019-05-31
|  |  | 1802499 |  | Kovachevich & Co., Inc. | Summitville | 2019-05-31
|  |  | 1802500 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2019-05-31
|  |  | 1802502 |  |  | Advance | 2019-05-31
|  |  | 1802505 |  | B. L. A., Inc. | Corydon | 2019-05-31
|  |  | 1802507 |  | Certified Engineering, Inc. | Fremont | 2019-05-31
|  |  | 1802515 |  | Martin Riley, Inc. | Whiteland | 2019-05-31
|  |  | 1802522 |  | Martin Riley, Inc. | Whiteland | 2019-05-31
|  |  | 1802524 |  | Meca Engineering Corporation of America Incorporated | Winslow | 2019-05-31
|  |  | 1802525 |  | Abonmarche Consultants of Indiana L.L.C. | Bloomfield | 2019-05-31
|  |  | 1802526 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2019-05-31
|  |  | 1802531 |  | Accu-Air Surveys, Inc. | Boonville | 2019-05-31
|  |  | 1802532 |  |  | Jefferson County | 2019-05-31
|  |  | 1802533 |  | Action Title and Escrow, LLC | Boswell | 2019-05-31
|  |  | 1802538 |  | Martin Riley, Inc. | Whiteland | 2019-05-31
|  |  | 1802539 |  |  | Jefferson County | 2019-05-31
|  |  | 1802541 |  |  | Jefferson County | 2019-05-31
|  |  | 1802542 |  | Hazeltine & Associates, Inc. | Paoli | 2019-05-31
|  |  | 1802545 |  | ABNA of Illinois | Andrews | 2019-05-31
|  |  | 1802546 |  | Hazeltine & Associates, Inc. | Paoli | 2019-05-31
|  |  | 1802549 |  | ABNA of Illinois | Andrews | 2019-05-31
|  |  | 1802550 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1802551 |  |  | Kentland | 2019-05-31
|  |  | 1802552 |  | Farren Real Estate Services | Middlebury | 2019-05-31
|  |  | 1802555 |  |  | Michigantown | 2019-05-31
|  |  | 1802560 |  | Accu-Air Surveys, Inc. | Boonville | 2019-05-31
|  |  | 1802569 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2019-05-31
|  |  | 1802570 |  | Entran, PLC | Marshall | -339679.2083
|  |  | 1802571 |  | Action Title and Escrow, LLC | Boswell | 2019-05-31
|  |  | 1802572 |  | Construction Consultants & Inspection Services, LLC | Hanover | 2019-05-31
|  |  | 1802573 |  | Heritage Land Services | Patriot | 2019-05-31
|  |  | 1802574 |  |  | Lanesville | 2019-05-31
|  |  | 1802575 |  | Arrow Consulting Services, Inc. | Colfax | 2019-05-31
|  |  | 1802576 |  | Martin Riley, Inc. | Whiteland | 2019-05-31
|  |  | 1802577 |  |  | Lizton | -339679.2083
|  |  | 1802578 |  | McKee Enterprises, Inc. | Wingate | 2019-05-31
|  |  | 1802579 |  |  | Darmstadt | 2019-05-31
|  |  | 1802580 |  | AMEC E&I, Inc. | Washington | 2019-05-31
|  |  | 1802581 |  | Matt L. Nepote, MAI | Whiting | 2019-05-31
|  |  | 1802582 |  | Matt L. Nepote, MAI | Whiting | 2019-05-31
|  |  | 1802583 |  |  | Daleville | 2019-05-31
|  |  | 1802584 |  | Matt L. Nepote, MAI | Whiting | 2019-05-31
|  |  | 1802585 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802586 |  |  | Daleville | 2019-05-31
|  |  | 1802587 |  |  | Daleville | 2019-05-31
|  |  | 1802588 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1802589 |  | Hazeltine & Associates, Inc. | Paoli | 2019-05-31
|  |  | 1802590 |  |  | Odon | 2019-05-31
|  |  | 1802591 |  |  | Odon | 2019-05-31
|  |  | 1802592 |  | Indiana Connect - a Joint Venture | Ridgeville | 2019-05-31
|  |  | 1802593 |  | Metropolitan Title of Indiana, LLC | Worthington | 2019-05-31
|  |  | 1802594 |  | AECOM USA, Inc. | Atlanta | 2019-05-31
|  |  | 1802595 |  | JJR, LLC | Santa Claus | 2019-05-31
|  |  | 1802596 |  | Hilton Property Management, LLC | Pennville | 2019-05-31
|  |  | 1802597 |  | Appraising Indiana, LLC | Cicero | 2019-05-31
|  |  | 1802598 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802599 |  | ACME | Arcadia | 2019-05-31
|  |  | 1802600 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | 2019-05-31
|  |  | 1802601 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1802602 |  | GAI Consultants, Inc. | Mooresville | 2019-05-31
|  |  | 1802603 |  |  | Morristown | 2019-05-31
|  |  | 1802604 |  | Jacobi, Toombs & Lanz, Inc. | Schneider | 2020-05-31
|  |  | 1802605 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2019-05-31
|  |  | 1802606 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802607 |  |  | Michiana Shores | 2019-05-31
|  |  | 1802608 |  | Martin Riley, Inc. | Whiteland | 2019-05-31
|  |  | 1802609 |  | GAI Consultants, Inc. | Mooresville | 2019-05-31
|  |  | 1802610 |  |  | Michiana Shores | 2019-05-31
|  |  | 1802611 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802612 |  | Casteel Real Estate | Franklin | 2019-05-31
|  |  | 1802613 |  |  | Michiana Shores | 2019-05-31
|  |  | 1802614 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802615 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2019-05-31
|  |  | 1802616 |  |  | Cumberland | 2019-05-31
|  |  | 1802617 |  |  | Cumberland | 2019-05-31
|  |  | 1802618 |  | Hannum, Wagle & Cline Engineering | Orleans | -339679.2083
|  |  | 1802619 |  |  | Michiana Shores | 2019-05-31
|  |  | 1802620 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2019-05-31
|  |  | 1802621 |  | Hannum, Wagle & Cline Engineering | Orleans | 2019-05-31
|  |  | 1802622 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802623 |  | Landstory, Inc. | Grabill | 2019-05-31
|  |  | 1802624 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1802625 |  | CGI | Evansville | 2019-05-31
|  |  | 1802626 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802627 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802628 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802629 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802630 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802631 |  | Kieser Consulting, LLC | Stilesville | -339679.2083
|  |  | 1802632 |  |  | Clermont | 2019-05-31
|  |  | 1802633 |  |  | Clermont | 2019-05-31
|  |  | 1802634 |  | J.A. Barker Engineering, Inc. | Russellville | -339679.2083
|  |  | 1802635 |  | J.A. Barker Engineering, Inc. | Russellville | -339679.2083
|  |  | 1802636 |  | John A. Doyle Associates, Inc. | Shipshewana | 2020-05-31
|  |  | 1802637 |  |  | Hagerstown | 2019-05-31
|  |  | 1802638 |  | JAY Real Estate Services, Inc. | Salamonia | 2019-05-31
|  |  | 1802639 |  | John A. Doyle Associates, Inc. | Shipshewana | 2019-05-31
|  |  | 1802640 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802641 |  |  | Hagerstown | 2019-05-31
|  |  | 1802642 |  | Enterprise Information Solutions, Inc. | Markleville | 2019-05-31
|  |  | 1802643 |  | JJR, LLC | Santa Claus | 2019-05-31
|  |  | 1802644 |  | Great Lakes Engineering, Inc. | New Palestine | 2019-05-31
|  |  | 1802645 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802646 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 1802647 |  |  | Hagerstown | 2019-05-31
|  |  | 1802648 |  |  | Hagerstown | 2019-05-31
|  |  | 1802649 |  | Hydrogeology, Inc. | Portland | 2019-05-31
|  |  | 1802650 |  |  | Fillmore | -339679.2083
|  |  | 1802651 |  | Accu-Air Surveys, Inc. | Boonville | 2019-05-31
|  |  | 1802652 |  | Burns & McDonnell Engineering Company, Inc. | Edgewood | 2019-05-31
|  |  | 1802653 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802654 |  |  | Leesburg | -339679.2083
|  |  | 1802655 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802656 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802657 |  | LFR, Inc. | Switz City | 2019-05-31
|  |  | 1802658 |  | Marine Solutions, Inc. | Westville | 2019-05-31
|  |  | 1802659 |  |  | Carthage | 2019-05-31
|  |  | 1802660 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802661 |  |  | Jennings County | 2019-05-31
|  |  | 1802662 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802663 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802664 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802665 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802666 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802667 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802668 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802669 |  | LFR, Inc. | Switz City | 2019-05-31
|  |  | 1802670 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802671 |  | Basin Field Services, Inc. | Crothersville | 2019-05-31
|  |  | 1802672 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2019-05-31
|  |  | 1802673 |  | LFR, Inc. | Switz City | 2019-05-31
|  |  | 1802674 |  | Accu-Air Surveys, Inc. | Boonville | 2019-05-31
|  |  | 1802675 |  |  | Newburgh | 2019-05-31
|  |  | 1802676 |  |  | Daleville | 2019-05-31
|  |  | 1802677 |  |  | South Whitley | 2020-05-31
|  |  | 1802678 |  | CityWise Real Estate Services, LLC | Geneva | 2020-05-31
|  |  | 1802679 |  |  | West Baden Springs | 2019-05-31
|  |  | 1802680 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802681 |  | McLane Realty, Inc. | Larwill | 2019-05-31
|  |  | 1802682 |  | CivCon Services, Inc. | Gentryville | 2019-05-31
|  |  | 1802683 |  | Land Title Service Company, LLC | Town Of Pines | 2019-05-31
|  |  | 1802684 |  | Advantage Appraisal Services | Brook | 2020-05-31
|  |  | 1802685 |  | Michael Baker International, Inc. | Yorktown | 2019-05-31
|  |  | 1802686 |  | ICA Engineering, Inc. | Mitchell | 2019-05-31
|  |  | 1802687 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802688 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802689 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802690 |  | CGI | Evansville | 2019-05-31
|  |  | 1802691 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802692 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802693 |  |  | Newburgh | 2019-05-31
|  |  | 1802694 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802695 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802696 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802697 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802698 |  | Commonwealth Engineers, Inc. | Greenwood | 2019-05-31
|  |  | 1802699 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1802700 |  | Enterprise Information Solutions, Inc. | Markleville | 2019-05-31
|  |  | 1802701 |  | Enterprise Information Solutions, Inc. | Markleville | 2019-05-31
|  |  | 1802702 |  | Enterprise Information Solutions, Inc. | Markleville | 2019-05-31
|  |  | 1802703 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802704 |  | Douglass Environmental Services, Inc. | La Porte | 2020-05-31
|  |  | 1802705 |  | GRW Engineers, Inc. | Mulberry | 2019-05-31
|  |  | 1802706 |  |  | Sellersburg | 2019-05-31
|  |  | 1802707 |  | AMEC E&I, Inc. | Washington | 2019-05-31
|  |  | 1802708 |  | Jacobs Pannicke Architects, Inc. | Sellersburg | 2019-05-31
|  |  | 1802709 |  |  | Darmstadt | 2019-05-31
|  |  | 1802710 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2019-05-31
|  |  | 1802711 |  | AMEC E&I, Inc. | Washington | 2019-05-31
|  |  | 1802712 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2019-05-31
|  |  | 1802713 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2019-05-31
|  |  | 1802714 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2019-05-31
|  |  | 1802715 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2019-05-31
|  |  | 1802716 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2019-05-31
|  |  | 1802717 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802718 |  | Civil Engineering Consultants | Goodland | 2019-05-31
|  |  | 1802719 |  | CDM Smith, Inc. | Fowler | 2019-05-31
|  |  | 1802720 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802721 |  |  | Sellersburg | 2019-05-31
|  |  | 1802722 |  | Garcia LE & Associates, L.L.C. | Nashville | -339679.2083
|  |  | 1802723 |  | Abonmarche Consultants of Indiana L.L.C. | Bloomfield | 2019-05-31
|  |  | 1802724 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802725 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802726 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802727 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802728 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802729 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802730 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802731 |  | American Commercial Title & Escrow | Burns Harbor | 2019-05-31
|  |  | 1802732 |  | Durham Engineering, Inc. | Larwill | 2020-05-31
|  |  | 1802733 |  | Boomerang Ventures, LLC | Dunkirk | 2019-05-31
|  |  | 1802734 |  | Garcia LE & Associates, L.L.C. | Nashville | -339679.2083
|  |  | 1802735 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802736 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 1802737 |  |  | South Whitley | 2020-05-31
|  |  | 1802738 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802739 |  | Land Consultants, Inc. | Topeka | -339679.2083
|  |  | 1802740 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802741 |  | Land Consultants, Inc. | Topeka | -339679.2083
|  |  | 1802742 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802743 |  |  | Churubusco | 2019-05-31
|  |  | 1802744 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802745 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802746 |  | C & E Clark, LLC | Elizabethtown | 2019-05-31
|  |  | 1802747 |  | C & E Clark, LLC | Elizabethtown | 2019-05-31
|  |  | 1802748 |  | C & E Clark, LLC | Elizabethtown | 2019-05-31
|  |  | 1802749 |  | C & E Clark, LLC | Elizabethtown | 2019-05-31
|  |  | 1802750 |  | Brenner Design Incorporated | Dyer | 2019-05-31
|  |  | 1802751 |  | AECOM USA, Inc. | Atlanta | 2019-05-31
|  |  | 1802752 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802753 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802754 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802755 |  | ERES International, Inc. | Marion | 2019-05-31
|  |  | 1802756 |  | Dummy Consulting Firm Too | Lakeville | 2019-05-31
|  |  | 1802757 |  |  | Jennings County | 2019-05-31
|  |  | 1802758 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802759 |  | McLane Realty, Inc. | Winona Lake | 2019-05-31
|  |  | 1802760 |  |  | Jennings County | 2019-05-31
|  |  | 1802761 |  |  | Jennings County | 2019-05-31
|  |  | 1802762 |  |  | Jennings County | -339679.2083
|  |  | 1802763 |  |  | Jennings County | 2019-05-31
|  |  | 1802764 |  | ASA Land Surveying | Bedford | 2019-05-31
|  |  | 1802765 |  |  | Monon | 2019-05-31
|  |  | 1802766 |  |  | Knox | 2019-05-31
|  |  | 1802767 |  | Linda F. Russell | Veedersburg | 2019-05-31
|  |  | 1802768 |  | Kevin K. Parsons & Associates, Inc. | Staunton | -339679.2083
|  |  | 1802769 |  | Approved Appraisals of Indiana, LLC | Clay City | -339679.2083
|  |  | 1802770 |  | CE Solutions, Inc. | Elwood | 2019-05-31
|  |  | 1802771 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2019-05-31
|  |  | 1802772 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2019-05-31
|  |  | 1802773 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802774 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2019-05-31
|  |  | 1802775 |  | ATSI Engineering Services | Beverly Shores | 2019-05-31
|  |  | 1802776 |  | ATSI Engineering Services | Beverly Shores | 2019-05-31
|  |  | 1802777 |  | Hazeltine & Associates, Inc. | Paoli | 2019-05-31
|  |  | 1802778 |  | GAI Consultants, Inc. | Mooresville | 2019-05-31
|  |  | 1802779 |  | ACME | Arcadia | 2019-05-31
|  |  | 1802780 |  | Hazeltine & Associates, Inc. | Paoli | 2019-05-31
|  |  | 1802781 |  | Douglass Environmental Services, Inc. | La Porte | 2020-05-31
|  |  | 1802782 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1802783 |  |  | Indiana Department of Transportation | 2019-08-07
|  |  | 1802784 | Kosciusko | Mackie Consultants, LLC | Warsaw | 2020-04-15 | CE
CN
PE
RR
|  |  | 1802785 |  | Farah and Sons, Inc. | Michigan City | 2023-07-12
|  |  | 1802786 | Vanderburgh | CGI | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  |  | Warrick | CGI | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1802787 | Various |  | Indiana Department of Transportation | 2020-04-01 | PE
RR
|  |  | 1802788 | Various |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
PE
RR
|  |  | 1802789 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802790 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802791 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1802792 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1802793 | Vanderburgh | CGI | Evansville | 2020-10-07 | CE
CN
|  |  | 1802794 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1802795 | Vanderburgh | CGI | Evansville | 2021-10-14 | CN
|  |  | 1802796 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1802797 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1802798 | Vanderburgh | CGI | Evansville | 2020-10-07 | CE
CN
|  |  | 1802799 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802800 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802801 |  |  | Indiana Department of Transportation | 2016-12-14
|  |  | 1802802 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802803 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802804 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1802805 | Clark |  | Clark County | 2023-01-19 | PE
|  |  | 1802806 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802807 | Tippecanoe |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1802808 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802809 | Tippecanoe |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1802810 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802811 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802812 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802813 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802814 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802815 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802816 |  |  | Metropolitian Evansville Transit System | -339679.2083
|  |  | 1802817 |  |  | Hamilton County | 2019-05-09
|  |  | 1802818 |  |  | Indiana Department of Transportation | 2019-04-03
|  |  | 1802819 | Hendricks |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1802820 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1802821 |  |  | Indiana Department of Transportation | 2017-01-19
|  |  | 1802822 | Johnson |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1802823 | Dubois |  | Dubois County | -339679.2083 | RR
|  |  | 1802824 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1802825 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1802826 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802827 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1802828 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802829 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802830 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802831 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802832 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802833 | Boone |  | Boone County | 2023-07-12 | PE
|  |  | 1802834 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802835 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802836 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802837 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802838 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802839 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802841 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802842 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802843 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802844 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802845 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802846 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1802847 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802848 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802849 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802850 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802851 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802852 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802853 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802854 |  | Hey and Associates, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1802855 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802856 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802857 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802859 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802861 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802862 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802863 |  |  | Terre Haute | -339679.2083
|  |  | 1802864 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1802865 |  |  | Lebanon | -339679.2083
|  |  | 1802866 |  |  | Montgomery County | -339679.2083
|  |  | 1802867 | LaPorte | Farah and Sons, Inc. | Michigan City | -339679.2083 | PE
|  |  | 1802868 | Morgan | EnviroScience, Inc. | Martinsville | 2024-01-18 | PE
|  |  | 1802869 | Morgan | EnviroScience, Inc. | Martinsville | 2024-01-18 | PE
|  |  | 1802870 |  |  | Washington County | -339679.2083
|  |  | 1802871 |  |  | Johnson County | -339679.2083
|  |  | 1802872 | Jennings |  | Jennings County | 2023-10-12 | PE
|  |  | 1802873 | Jennings |  | Jennings County | 2023-10-12 | PE
|  |  | 1802874 | Jennings |  | Jennings County | 2023-10-12 | PE
|  |  | 1802875 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2023-09-13 | PE
|  |  | 1802876 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2023-09-13 | PE
|  |  | 1802877 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2023-09-13 | PE
|  |  | 1802878 | Jennings |  | Jennings County | 2023-08-09 | PE
|  |  | 1802879 | Scott |  | Scott County | 2023-11-15 | PE
|  |  | 1802880 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1802881 | Morgan |  | Morgan County | 2023-07-12 | PE
|  |  | 1802882 |  | ARCADIS | Batesville | -339679.2083
|  |  | 1802883 |  |  | Bartholomew County | -339679.2083
|  |  | 1802884 |  |  | Johnson County | -339679.2083
|  |  | 1802885 | Dearborn |  | Dearborn County | 2023-11-15 | PE
|  |  | 1802886 | Jefferson | Engineering Resources, Inc. | Madison | 2023-07-14 | ROW
|  |  | 1802887 |  |  | Johnson County | -339679.2083
|  |  | 1802888 |  |  | Monroe County | -339679.2083
|  |  | 1802889 |  |  | Monroe County | -339679.2083
|  |  | 1802890 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1802891 |  |  | Hendricks County | -339679.2083
|  |  | 1802892 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1802893 |  | Banning Engineering, P.C. | Crawfordsville | -339679.2083
|  |  | 1802894 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1802895 | Clinton |  | Clinton County | 2023-07-12 | PE
|  |  | 1802896 |  |  | Noble County | -339679.2083
|  |  | 1802897 |  |  | Martin County | -339679.2083
|  |  | 1802898 | Sullivan | Klug Engineering, Inc. | Sullivan | 2023-09-13 | PE
RR
|  |  | 1802899 | Pike |  | Pike County | 2023-11-15 | PE
|  |  | 1802900 | Pike |  | Pike County | 2023-11-15 | PE
|  |  | 1802901 | Perry |  | Tell City | 2022-04-06 | PE
|  |  | 1802902 |  |  | Rockport | -339679.2083
|  |  | 1802903 | Perry |  | Perry County | 2024-01-18 | PE
|  |  | 1802904 | Lawrence |  | Lawrence County | 2022-09-14 | PE
|  |  | 1802905 | Tippecanoe |  | Tippecanoe County | 2023-11-15 | PE
|  |  | 1802906 | Warrick |  | Warrick County | 2024-02-14 | PE
|  |  | 1802907 | Tippecanoe |  | Tippecanoe County | 2023-11-15 | PE
|  |  | 1802908 |  | CGI | Vanderburgh County | -339679.2083
|  |  | 1802909 | Daviess |  | Daviess County | 2021-03-10 | CE
CN
|  |  | 1802910 |  |  | Vigo County | -339679.2083
|  |  | 1802911 | Fulton |  | Fulton County | 2024-01-18 | PE
|  |  | 1802912 | Allen |  | Allen County | 2024-02-14 | PE
|  |  | 1802913 | Marshall | Bayer & Becker, Inc. | Culver | 2023-10-12 | PE
|  |  | 1802914 | Starke | H.R. Gray | North Judson | 2021-03-10 | CE
CN
PE
|  |  | 1802915 | Vermillion | Archaeology and Geomorphology Services | Clinton | 2020-12-09 | CE
CN
PE
|  |  | 1802916 | Grant | ERES International, Inc. | Grant County | 2021-05-05 | CE
CN
|  |  | 1802917 | Kosciusko |  | Kosciusko County | 2023-12-13 | PE
|  |  | 1802918 | Steuben |  | Steuben County | 2024-01-18 | PE
|  |  | 1802919 |  |  | Starke County | -339679.2083
|  |  | 1802920 | Lake | Edwards and Kelcey | Lowell | 2023-10-12 | PE
|  |  | 1802921 |  |  | Starke County | -339679.2083
|  |  | 1802922 |  | Bettina Settles Realty, LLC | De Motte | -339679.2083
|  |  | 1802923 | Fulton | InfoTech | Rochester | 2023-07-12 | PE
|  |  | 1802924 | Lake | Edwards and Kelcey | Lowell | 2023-10-12 | PE
|  |  | 1802925 | Jay | Boomerang Ventures, LLC | Dunkirk | 2023-09-13 | PE
|  |  | 1802926 |  | Jeffrey S. Juday | Shelbyville | -339679.2083
|  |  | 1802927 | Rush |  | Rush County | 2023-12-13 | PE
|  |  | 1802928 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1802929 | Rush |  | Rush County | 2023-12-13 | PE
|  |  | 1802930 | Wayne |  | Wayne County | 2023-11-15 | PE
|  |  | 1802931 | Hamilton | CPS Acquisitions, LLC | Fishers | 2023-09-13 | PE
|  |  | 1802932 |  |  | Porter County | 2023-10-12
|  |  | 1802933 |  |  | New Castle | -339679.2083
|  |  | 1802934 | Wayne |  | Wayne County | 2023-10-12 | PE
|  |  | 1802935 | White |  | White County | 2023-10-12 | PE
|  |  | 1802936 | Wayne |  | Wayne County | 2023-11-15 | PE
|  |  | 1802937 | Fayette | Wilcox Environmental Engineering, Inc. | Connersville | 2021-02-10 | CE
CN
PE
|  |  | 1802938 |  |  | Hamilton County | 2023-09-13
|  |  | 1802939 |  | Great Lakes Engineering, Inc. | Hancock County | -339679.2083
|  |  | 1802940 | Hancock |  | Hancock County | 2023-12-13 | PE
ROW
|  |  | 1802941 |  |  | Porter County | 2023-10-12
|  |  | 1802942 |  |  | LaPorte County | -339679.2083
|  |  | 1802943 |  |  | Westfield | -339679.2083
|  |  | 1802944 | Randolph | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2023-07-12 | PE
RR
|  |  | 1802945 |  |  | Westfield | -339679.2083
|  |  | 1802946 |  |  | Wells County | -339679.2083
|  |  | 1802947 |  | M-E Companies, Inc. | Wabash | -339679.2083
|  |  | 1802948 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802949 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802950 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802951 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802952 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802953 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802954 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802955 | Wells |  | Wells County | 2023-12-13 | PE
|  |  | 1802956 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802957 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802958 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07 | CE
CN
[5 empty] | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1802959 | Miami | Holloway Engineering, LLC | Miami County | 2021-03-10 | CE
CN
|  |  | 1802960 |  | Continental Mapping Consultants, LLC | Hartford City | -339679.2083
|  |  | 1802961 |  |  | Wells County | -339679.2083
|  |  | 1802962 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802963 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1802964 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2020-01-15 | PE
|  |  | 1802965 | Allen | Franco Consulting Engineers, LLC | Indiana Department of Transportation | 2020-03-04 | RR
|  |  | 1802966 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1802967 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
[6 empty] | Indiana Department of Transportation | 2020-10-07
|  |  | 1802968 | Huntington | MHM Associates, Inc. | Indiana Department of Transportation | 2020-02-05 | RR
|  |  | 1802969 |  | MHM Associates, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1802970 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1802971 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802972 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1802973 | Lake | Chicago Testing Laboratory, Inc. | Gary | 2023-12-13 | PE
|  |  | 1802974 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1802975 |  | Chicago Testing Laboratory, Inc. | Gary | 2022-03-09
|  |  | 1802976 |  |  | Jackson County | 2023-12-13
|  |  | 1802977 | Monroe |  | Monroe County | 2023-07-12 | ROW
|  |  | 1802978 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1802979 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802980 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802981 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1802982 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1802983 |  |  | Seymour | -339679.2083
|  |  | 1802984 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1802985 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1802986 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1802987 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1802988 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1802989 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1802990 |  | Fidelity National Title Insurance Company, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 1802991 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 1802992 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 1802993 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1802994 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1802995 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1802996 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1802997 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1802998 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1802999 |  | Burrell Appraisal Service, Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 1803000 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900001 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1900002 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1900003 |  |  | Indiana Department of Transportation | 2026-09-02
|  |  | 1900004 | Tipton | Land Construction Corp | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1900005 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900006 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900007 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1900008 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1900009 |  | Consolidated Test Company | Indiana Department of Transportation | 2024-07-10
|  |  | 1900010 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1900011 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900012 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2023-08-09
|  |  | 1900013 |  |  | Indiana Department of Transportation | 2019-11-14
|  |  | 1900014 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900015 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900016 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900017 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900018 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900019 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900020 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900021 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1900022 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900023 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1900024 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1900025 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1900026 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900028 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900029 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900030 | Gibson | III FFC | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1900031 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900032 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1900033 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900034 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900035 |  | Hardlines Design Company | Indiana Department of Transportation | 2023-10-12
|  |  | 1900036 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900037 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900038 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900039 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900040 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900041 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900042 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900044 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900045 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900046 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900047 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2024-09-11
|  |  | 1900048 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900049 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900050 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900051 |  | HE-BFS, LLC | Indiana Department of Transportation | 2024-11-14
|  |  | 1900052 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900053 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900054 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900055 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2023-09-13
|  |  | 1900056 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900057 |  | MCIS LLC | Indiana Department of Transportation | 2023-10-12
|  |  | 1900058 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900059 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900061 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1900062 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 1900063 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900064 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1900065 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900066 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900067 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900068 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900069 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900070 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 1900071 |  | M-E Companies, Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1900072 |  | M-E Companies, Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1900073 |  | LONCO, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 1900074 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900075 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900076 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900077 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2024-01-18
|  |  | 1900078 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2024-01-18
|  |  | 1900079 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900080 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900081 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900082 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900083 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900084 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900085 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900086 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900087 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900088 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900089 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1900090 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1900091 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900092 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900093 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900094 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900095 |  | Farren Real Estate Services | Indiana Department of Transportation | 2023-12-13
|  |  | 1900096 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1900097 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1900098 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900099 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900100 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900101 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900102 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900103 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900104 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900105 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900107 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2023-08-09
|  |  | 1900108 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900111 |  | Land Construction Corp | Indiana Department of Transportation | -339679.2083
|  |  | 1900112 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1900113 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900114 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900115 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900116 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1900117 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900118 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900119 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900120 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900121 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900122 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900123 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900124 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900126 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900127 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900128 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900129 |  | HOH Engineers, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 1900130 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900131 |  | HOH Engineers, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 1900132 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900133 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900134 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900135 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900136 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900137 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900138 | Noble |  | Indiana Department of Transportation | 2023-08-09 | PE
|  |  | 1900139 |  | Farren Real Estate Services | Indiana Department of Transportation | -339679.2083
|  |  | 1900140 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900141 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 1900142 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 1900143 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900144 | Various |  | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 1900145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900146 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900147 | Delaware |  | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1900148 |  | GS-IN P.C. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900149 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1900150 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900151 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1900152 | Madison |  | Indiana Department of Transportation | 2024-01-18 | PE
|  |  | 1900153 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900154 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900155 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900156 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900157 | Marion | Dyer Environmental Services | Indiana Department of Transportation | 2023-07-12 | PE
|  |  | 1900158 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1900159 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900160 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900161 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900162 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 1900163 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900164 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1900165 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900166 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900167 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900168 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900169 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900171 |  | DKA Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900172 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | -339679.2083
|  |  | 1900173 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900174 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900175 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900176 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900177 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900178 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900180 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900181 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900182 |  | Eco Logic, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900183 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900186 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2023-12-13
|  |  | 1900187 |  | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | -339679.2083
|  |  | 1900188 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900189 |  |  | Indiana Department of Transportation | 2024-11-15
|  |  | 1900190 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900191 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1900192 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900193 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900194 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900195 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900196 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900197 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900198 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900199 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1900200 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900201 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900202 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900203 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900205 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900206 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900207 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900208 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900209 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900210 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900211 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900212 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1900213 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900214 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900215 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900216 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900217 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900218 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900219 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900220 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900221 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900222 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900223 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900225 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900226 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900227 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900228 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900229 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900230 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2024-01-18
|  |  | 1900231 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900232 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900233 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900234 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900236 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900237 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900238 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900239 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900240 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900241 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900242 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900243 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1900244 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1900245 |  | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | -339679.2083
|  |  | 1900246 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900247 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900248 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900249 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900250 |  | Enterprise Information Solutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900251 |  | Central Diving Contractors | Indiana Department of Transportation | 2023-07-12
|  |  | 1900252 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900253 |  | Land Construction Corp | Indiana Department of Transportation | 2023-09-13
|  |  | 1900254 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900255 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900256 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900257 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900258 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1900259 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1900260 |  | CGI | Indiana Department of Transportation | 2024-07-10
|  |  | 1900261 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900262 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900263 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 1900264 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 1900265 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900266 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1900267 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1900268 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 1900269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900270 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900271 |  | Harvard Title Searching | Indiana Department of Transportation | 2023-12-13
|  |  | 1900272 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2023-10-12
|  |  | 1900273 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900274 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1900275 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900276 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900277 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900278 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900279 |  |  | Indiana Department of Transportation | 2017-03-01
|  |  | 1900280 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900281 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900282 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900283 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900284 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900285 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900286 |  | HLRD | Indiana Department of Transportation | 2023-12-13
|  |  | 1900287 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900288 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1900289 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900291 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900292 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 1900293 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900294 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900295 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900296 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900297 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900298 |  | GMG INC. | Indiana Department of Transportation | -339679.2083
|  |  | 1900299 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900300 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900301 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900302 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900303 |  | Clayton L. Roots | Indiana Department of Transportation | 2023-07-12
|  |  | 1900304 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900305 |  | Clayton L. Roots | Indiana Department of Transportation | 2023-07-12
|  |  | 1900306 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900308 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 1900309 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900310 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1900311 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900312 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | 2023-11-15
|  |  | 1900313 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900314 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900315 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900316 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900317 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 1900318 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 1900319 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900321 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900322 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900323 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900324 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900325 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900326 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900327 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900329 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900330 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1900331 |  | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2024-09-11
|  |  | 1900332 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900333 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900334 |  | Lorenz Williams Clinton | Indiana Department of Transportation | 2023-09-13
|  |  | 1900335 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900336 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900337 |  | Lorenz Williams Clinton | Indiana Department of Transportation | 2023-09-13
|  |  | 1900338 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900339 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-12-13
|  |  | 1900340 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1900341 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1900342 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900343 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1900344 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900345 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900346 |  | Harvard Title Searching | Indiana Department of Transportation | -339679.2083
|  |  | 1900347 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900348 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900349 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900350 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900351 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900352 |  | Manning Real Estate Services | Indiana Department of Transportation | 2023-12-13
|  |  | 1900353 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 1900354 |  | Chastain & Associates LLC | Indiana Department of Transportation | 2023-10-12
|  |  | 1900355 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900356 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2023-07-12
|  |  | 1900357 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1900358 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1900359 |  | HLRD | Indiana Department of Transportation | 2023-12-13
|  |  | 1900360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900361 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2023-07-12
|  |  | 1900362 |  |  | Terre Haute | -339679.2083
|  |  | 1900363 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 1900364 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900365 | Bartholomew |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900366 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900367 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900368 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900369 | Clark | Jacobs Pannicke Architects, Inc. | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900370 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 1900371 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900372 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900373 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2025-04-09
|  |  | 1900374 | Clark |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900375 | Clark |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900376 | Clark |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900377 | Johnson |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900378 |  | Martin Riley, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900379 |  | Casteel Real Estate | Indiana Department of Transportation | 2024-05-31
|  |  | 1900380 |  | Casteel Real Estate | Indiana Department of Transportation | 2024-05-31
|  |  | 1900381 | Scott |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900382 | Scott | AEROCON Photogrammetric Services, Inc. | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900383 | Jackson | Basin Field Services, Inc. | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900384 | Jackson |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900385 | Bartholomew |  | Louisville and Indiana Railroad Company | -339679.2083 | RR
|  |  | 1900386 |  |  | Columbus | -339679.2083
|  |  | 1900387 | Bartholomew |  | Bartholomew County | -339679.2083 | RR
|  |  | 1900388 | Bartholomew |  | Bartholomew County | -339679.2083 | RR
|  |  | 1900389 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900390 | Madison | AAC Environmental Consulting, LLC | Anderson | 2022-01-12 | PE
|  |  | 1900391 | Elkhart | Civil Inspection Services, LLC | Goshen | -339679.2083 | RR
|  |  | 1900392 |  | H W Lochner, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900393 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900394 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900396 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1900397 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900398 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900399 |  | Absolute Title Services, LLC | Bloomington | 2022-10-13
|  |  | 1900400 |  | Absolute Title Services, LLC | Bloomington | 2024-05-31
|  |  | 1900401 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 1900402 |  | Absolute Title Services, LLC | Bloomington | 2022-03-09
|  |  | 1900403 | Monroe | Absolute Title Services, LLC | Bloomington | 2022-10-13 | PE
|  |  | 1900404 |  | Absolute Title Services, LLC | Bloomington | 2022-04-06
|  |  | 1900405 |  |  | Monroe | 2023-07-12
|  |  | 1900406 |  |  | Monroe County | 2022-11-16
|  |  | 1900407 |  | H&H Associates, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900408 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Railroad | -339679.2083 | RR
|  |  | 1900409 | Monroe |  | Indiana Railroad | -339679.2083 | RR
|  |  | 1900410 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 1900411 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900412 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900413 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1900414 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900415 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1900416 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1900417 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1900418 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1900419 | Johnson | Commonwealth Engineers, Inc. | Greenwood | 2019-11-14 | CE
CN
|  |  | 1900420 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900421 |  |  | Seymour | -339679.2083
|  |  | 1900422 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900423 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900424 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900425 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1900426 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1900427 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 1900428 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900429 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900430 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900431 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900432 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1900433 |  | Land Construction Corp | Indiana Department of Transportation | 2023-09-13
|  |  | 1900434 |  | Land Construction Corp | Indiana Department of Transportation | 2023-09-13
|  |  | 1900435 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1900436 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-04-01
|  |  | 1900437 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1900438 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1900439 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900440 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1900441 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900442 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900443 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1900444 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900445 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1900446 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2023-07-12
|  |  | 1900447 |  |  | South Bend | 2024-03-13
|  |  | 1900448 | St. Joseph |  | St. Joseph County | 2023-07-12 | PE
|  |  | 1900449 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2023-10-12
|  |  | 1900450 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1900451 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 1900452 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 1900453 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 1900454 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1900455 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1900456 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1900457 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1900458 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1900459 | Various |  | Indiana Department of Transportation | 2020-12-16 | CE
CN
|  |  | 1900460 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1900461 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1900462 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1900463 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900464 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900465 | Elkhart |  | Elkhart County | 2024-03-13 | PE
|  |  | 1900466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900467 | Monroe |  | Monroe County | 2021-05-05 | CE
CN
ROW
UT
|  |  | 1900468 | Various |  | Indiana Department of Transportation | 2020-01-15 | CE
CN
|  |  | 1900469 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900470 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1900471 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900472 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900473 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-01-15
|  |  | 1900474 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900475 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900476 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900477 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2020-03-04 | CE
CN
PE
|  |  | 1900478 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900479 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900481 |  |  | Lafayette CityBus | -339679.2083
|  |  | 1900482 | Tippecanoe | DuSABLE, Inc. | Lafayette | 2025-08-06 | PE
|  |  | 1900483 | Tippecanoe | Bertsch-Frank & Associates, LLC | Dayton | 2025-05-31 | PE
|  |  | 1900484 |  |  | Union City | -339679.2083
|  |  | 1900485 |  | Cornerstone Design | Indiana Department of Transportation | -339679.2083
|  |  | 1900486 | Elkhart |  | Elkhart County | -339679.2083 | PE
|  |  | 1900487 |  | Archaeological Consultants of Ossian | Indiana Department of Transportation | 2020-03-04
|  |  | 1900488 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900489 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900490 |  | FPBH, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900491 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900492 |  | Jeffrey S. Juday | Indiana Department of Transportation | -339679.2083
|  |  | 1900493 |  |  | Monroe County | 2023-10-12
|  |  | 1900494 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1900495 | Morgan |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1900496 | Morgan |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1900497 | Morgan |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1900498 | Morgan |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1900499 |  |  | Indiana Department of Transportation | 2019-08-07
|  |  | 1900500 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900501 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900502 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900503 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900504 |  | DCD Consulting LLC | Indiana Department of Transportation | 2018-09-12
|  |  | 1900505 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1900506 |  |  | St. Joseph County | -339679.2083
|  |  | 1900507 | Kosciusko | Mackie Consultants, LLC | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900508 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 1900509 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2019-05-09
|  |  | 1900510 | Grant |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900511 | Noble | ERES International, Inc. | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900512 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900513 | Dekalb |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900514 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900515 | Whitley |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900516 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900517 | Shelby |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900518 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 1900519 |  | AMEC E&I, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900520 | Vigo |  | Indiana Department of Transportation | 2019-08-21 | CE
CN
|  |  | 1900521 | Clay | Bayswater Company, LLC | Indiana Department of Transportation | 2019-08-21 | CE
CN
|  |  | 1900522 | Putnam |  | Indiana Department of Transportation | 2019-08-21 | CE
CN
|  |  | 1900523 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900524 |  |  | Indiana Department of Transportation | 2017-09-13
|  |  | 1900525 | Fountain | Linda F. Russell | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900526 | Morgan | Franklin Property Matters, LLC. | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900527 | Putnam | Clayton L. Roots | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1900528 | Clay | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  |  | Vigo | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1900529 | Vigo |  | Indiana Department of Transportation | 2019-08-07 | CE
CN
|  |  | 1900530 |  | ASC Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900531 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900532 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1900533 | Various |  | Indiana Department of Transportation | 2019-08-21 | CE
CN
|  |  | 1900534 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900535 | Various |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
RR
|  |  | 1900536 | Various |  | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900537 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 1900538 | Various | CGI | Indiana Department of Transportation | 2019-05-09 | CE
CN
|  |  | 1900539 |  | CGI | Indiana Department of Transportation | 2019-12-11
|  |  | 1900540 | Vanderburgh |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900542 |  |  | Indiana Department of Transportation | 2019-05-15
|  |  | 1900543 | Various |  | Indiana Department of Transportation | 2019-05-15 | CE
CN
|  |  | 1900544 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900545 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900546 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1900547 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1900548 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1900549 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1900550 |  |  | Muncie Indiana Transit System | -339679.2083
|  |  | 1900551 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1900552 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900553 |  |  | MPO - Evansville | -339679.2083
|  |  | 1900554 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1900555 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900556 |  | Fidelity National Title Insurance Company, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900557 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1900558 |  | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | 2019-05-09
|  |  | 1900559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900560 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900561 | Crawford |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1900562 | Warrick |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900563 | Warrick | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2021-08-11 | CN
RR
|  |  | 1900564 |  | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | 2022-03-09
|  |  | 1900565 | Spencer |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900566 |  | Anelena Ackerly | Indiana Department of Transportation | 2022-03-09
|  |  | 1900567 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900568 | Dubois |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
RR
|  |  | 1900569 | Various |  | Indiana Department of Transportation | 2020-05-31 | CN
|  |  | 1900570 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900571 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 2019-04-03 | CE
CN
|  |  | 1900572 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1900573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900574 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1900575 |  | Earth Exploration, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900576 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900577 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900578 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900579 |  |  | Indiana Department of Transportation | 2020-11-13
|  |  | 1900580 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900581 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900582 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900583 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900584 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900585 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900586 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900587 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900588 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900589 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900590 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900591 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900592 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900593 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900594 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900595 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900596 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900597 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900598 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900599 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900600 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-27
|  |  | 1900601 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900602 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900603 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900604 | Marion |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900605 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900606 | Boone |  | Indiana Department of Transportation | 2019-04-17 | CE
CN
|  |  | 1900607 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1900608 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900609 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900611 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900612 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900613 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900614 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1900615 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1900616 |  |  | ColumBUS Transit | -339679.2083
|  |  | 1900617 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1900618 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1900619 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 1900620 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 1900621 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2021-12-08 | RR
|  |  | 1900622 | Kosciusko |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900623 | Dekalb | Quantum Spatial, Inc. | Indiana Department of Transportation | 2021-07-14 | CE
CN
RR
|  |  | 1900624 |  | Bidinfo | Indiana Department of Transportation | 2021-12-08
|  |  | 1900625 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1900626 | Brown |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900627 | Franklin |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1900628 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900630 | Scott |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1900631 | Scott |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1900632 | Harrison |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1900633 | Jackson |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1900634 | Johnson | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1900635 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900636 | Clark |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1900637 | Jackson |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900638 | Jackson |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900639 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1900640 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1900641 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1900642 | Shelby |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1900643 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900644 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1900645 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1900646 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2020-11-10 | CE
CN
RR
|  |  | 1900647 |  | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 2022-04-06
|  |  | 1900648 |  | Linda F. Russell | Indiana Department of Transportation | 2022-02-09
|  |  | 1900649 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900650 | Putnam |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900651 | Marion | GAI Consultants, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1900652 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900653 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900654 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900655 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900656 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900657 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900658 | Shelby |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1900659 | Shelby |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1900660 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900661 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900662 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900663 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900664 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
RR
|  |  | 1900665 | Tippecanoe |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1900666 | Tippecanoe | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900667 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900668 | Floyd |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1900669 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900670 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900671 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900672 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900673 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1900674 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1900675 | Jasper |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1900676 | Jasper |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1900677 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-04-06
|  |  | 1900678 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-04-06
|  |  | 1900679 | Putnam | Archonsortium, LLC | Indiana Department of Transportation | 2021-12-08 | RR
|  |  | 1900680 |  | Archonsortium, LLC | Indiana Department of Transportation | 2021-12-08
|  |  | 1900681 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1900682 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900683 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1900684 |  | Alliance Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1900685 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1900686 | Bartholomew |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1900687 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1900688 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1900689 |  | Casteel Real Estate | Indiana Department of Transportation | 2022-03-09
|  |  | 1900690 | Franklin |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1900691 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900692 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900693 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900694 | Dearborn |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900695 | Morgan |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1900696 |  | Casteel Real Estate | Indiana Department of Transportation | 2022-02-09
|  |  | 1900697 | Jennings |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900698 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900699 | Dearborn | Kaskaskia Engineering Group | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900700 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900701 | Decatur |  | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1900702 |  | Casteel Real Estate | Indiana Department of Transportation | 2022-02-09
|  |  | 1900703 | Franklin |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900704 | Owen | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900705 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900706 | Franklin | ARCADIS | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900707 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1900708 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1900709 | Jennings |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900710 | Monroe |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900711 | Monroe |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900712 | Ripley | ARCADIS | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900713 | Jackson |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1900714 | Jennings |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900715 | Jackson |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900716 | Jackson |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1900717 | Monroe |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900718 | Monroe |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900719 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900720 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900721 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1900722 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1900723 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900724 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900725 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900726 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1900727 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900728 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900729 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900730 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900731 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900732 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900733 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900734 | Vigo |  | Indiana Department of Transportation | 2022-03-09 | RR
|  |  | 1900735 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900736 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1900737 | Benton |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900738 | Benton |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1900739 | Elkhart | Civil Inspection Services, LLC | Goshen | 2024-07-10 | PE
|  |  | 1900740 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900741 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900742 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900743 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900744 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1900745 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1900746 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1900747 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1900748 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1900749 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1900750 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1900751 | Hendricks |  | Indiana Department of Transportation | 2022-02-09 | RR
|  |  | 1900752 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900753 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1900754 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900755 | Vigo |  | Indiana Department of Transportation | 2022-03-09 | RR
|  |  | 1900756 | Montgomery |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1900757 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1900758 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1900759 | Vermillion |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1900760 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2020-10-07 | CE
CN
RR
|  |  | 1900761 | Parke |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1900762 | Morgan |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900763 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900764 | Clay |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1900765 | Vermillion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1900766 | Hendricks |  | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1900767 | Clay |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900768 | Clay |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900769 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1900770 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900771 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900772 | Vanderburgh |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1900773 |  | GS-IN P.C. | Muncie | 2023-07-12
|  |  | 1900774 | Delaware | GS-IN P.C. | Muncie | 2023-08-09 | PE
|  |  | 1900775 | Vanderburgh | CGI | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1900776 | Vanderburgh | CGI | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1900777 | Posey |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1900778 |  |  | Kokomo | 2023-07-12
|  |  | 1900779 | Posey |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1900780 | Howard | Dodd Title Corporation | Kokomo | 2022-01-12 | PE
|  |  | 1900781 |  |  | Kokomo | -339679.2083
|  |  | 1900782 |  | CGI | Indiana Department of Transportation | 2023-01-19
|  |  | 1900783 | Sullivan |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1900784 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1900785 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1900786 | Warrick |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1900787 | Knox |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900788 | Perry |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900789 | Posey |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900790 | Dubois |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900791 | Dubois |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900792 | Perry |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900793 | Crawford |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900794 | Vanderburgh | CGI | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900795 | Vanderburgh | CGI | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900796 | Vanderburgh |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900797 | Vanderburgh |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900798 | Vanderburgh |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900799 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900800 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900801 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1900802 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900803 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900804 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900805 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900806 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900807 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900808 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900809 | Orange | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1900810 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1900811 |  | Edwards and Kelcey | Indiana Department of Transportation | 2021-02-10
|  |  | 1900812 | Marshall |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1900813 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 1900814 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
RR
|  |  | 1900815 | Cass |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1900816 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 1900817 | Pulaski |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 1900818 | Carroll |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1900819 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1900820 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1900821 |  | C Blair Enterprises, Inc. | Elkhart | 2023-04-12
|  |  | 1900822 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  | 1900823 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 1900824 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2020-11-10
|  |  | 1900825 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2020-11-10
|  |  | 1900826 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1900827 | Huntington |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1900828 | Dekalb |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1900829 | Dekalb |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1900830 |  | Chicago Testing Laboratory, Inc. | Gary | 2024-04-10
|  |  | 1900831 |  | Douglass Environmental Services, Inc. | La Porte | 2023-02-15
|  |  | 1900832 |  | Courtland Title & Escrow, Inc. | Hobart | 2022-08-10
|  |  | 1900833 |  | Consolidated Test Company | Hammond | 2023-07-12
|  |  | 1900834 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2023-07-12
|  |  | 1900835 |  | Douglass Environmental Services, Inc. | La Porte | 2023-04-12
|  |  | 1900836 |  |  | Elkhart County | 2023-05-10
|  |  | 1900837 |  | M-E Companies, Inc. | Wabash | 2023-03-15
|  |  | 1900838 |  |  | Wells County | 2023-03-15
|  |  | 1900839 |  |  | Vanderburgh County | 2023-05-10
|  |  | 1900840 |  |  | Terre Haute | -339679.2083
|  |  | 1900841 |  |  | Kosciusko County | 2022-05-05
|  |  | 1900842 |  | Bayswater Company, LLC | Terre Haute | 2023-04-12
|  |  | 1900843 |  |  | Ellettsville | 2020-05-31
|  |  | 1900844 |  |  | Ellettsville | 2020-05-31
|  |  | 1900845 |  |  | Ellettsville | 2020-05-31
|  |  | 1900846 |  |  | Ellettsville | 2020-05-31
|  |  | 1900847 |  |  | Ellettsville | 2020-05-31
|  |  | 1900848 |  |  | Ellettsville | 2020-05-31
|  |  | 1900849 |  | Wilcox Environmental Engineering, Inc. | Connersville | 2020-05-31
|  |  | 1900850 |  |  | Monroe County | 2020-05-31
|  |  | 1900851 |  | Dorochoff Consulting, LLC | La Fontaine | 2020-05-31
|  |  | 1900852 |  | Huff & Huff, Inc. | Portage | -339679.2083
|  |  | 1900853 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2020-05-31
|  |  | 1900854 |  | CMF Engineering, Inc. | Ferdinand | 2020-05-31
|  |  | 1900855 |  | CMF Engineering, Inc. | Ferdinand | 2020-05-31
|  |  | 1900856 |  |  | Union County | 2020-05-31
|  |  | 1900857 |  | AAC Environmental Consulting, LLC | Anderson | 2020-05-31
|  |  | 1900858 |  | Indiana Appraisal Group, Inc. | Richmond | 2020-05-31
|  |  | 1900859 |  |  | New Albany | 2020-05-31
|  |  | 1900860 |  |  | Gibson County | 2020-05-31
|  |  | 1900861 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1900862 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1900863 |  | Gregg A. Townsend | Borden | 2020-05-31
|  |  | 1900864 |  |  | Henry County | -339679.2083
|  |  | 1900865 |  |  | Noble County | 2020-05-31
|  |  | 1900866 |  | Hardcore Concrete Sawing Inc. | Osgood | 2020-05-31
|  |  | 1900867 |  |  | Fulton County | 2020-05-31
|  |  | 1900868 |  |  | Fulton County | 2020-05-31
|  |  | 1900869 |  |  | Fulton County | 2020-05-31
|  |  | 1900870 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 1900871 |  |  | Tipton County | 2020-05-31
|  |  | 1900872 |  |  | Tipton County | 2020-05-31
|  |  | 1900873 |  |  | Tipton County | 2020-05-31
|  |  | 1900874 |  | Wilcox Environmental Engineering, Inc. | Connersville | 2020-05-31
|  |  | 1900875 |  |  | Jackson County | 2020-05-31
|  |  | 1900876 |  | Gensic Engineering, Inc. | New Carlisle | 2020-05-31
|  |  | 1900877 |  | Gensic Engineering, Inc. | New Carlisle | 2020-05-31
|  |  | 1900878 |  | Gensic Engineering, Inc. | New Carlisle | 2020-05-31
|  |  | 1900879 |  | Indiana Search Technologies | Rising Sun | 2020-05-31
|  |  | 1900880 |  | Gensic Engineering, Inc. | New Carlisle | 2020-05-31
|  |  | 1900881 |  | Gensic Engineering, Inc. | New Carlisle | 2020-05-31
|  |  | 1900882 |  | Wilcox Environmental Engineering, Inc. | Connersville | 2020-05-31
|  |  | 1900883 |  |  | Hancock County | 2020-05-31
|  |  | 1900884 |  |  | Clay County | -339679.2083
|  |  | 1900885 |  |  | Pulaski County | 2020-05-31
|  |  | 1900886 |  | Indiana Search Technologies | Rising Sun | 2020-05-31
|  |  | 1900887 |  |  | Whitley County | 2020-05-31
|  |  | 1900888 |  |  | Whitley County | 2020-05-31
|  |  | 1900889 |  |  | Whitley County | 2020-05-31
|  |  | 1900890 |  |  | Whitley County | 2020-05-31
|  |  | 1900891 |  |  | Whitley County | 2020-05-31
|  |  | 1900892 |  |  | Hancock County | 2020-05-31
|  |  | 1900893 |  |  | Putnam County | -339679.2083
|  |  | 1900894 |  |  | Clay County | -339679.2083
|  |  | 1900895 |  |  | Dubois County | 2020-05-31
|  |  | 1900896 |  |  | Boone County | 2020-05-31
|  |  | 1900897 |  |  | South Bend | 2020-05-31
|  |  | 1900898 |  |  | Boone County | 2020-05-31
|  |  | 1900899 |  |  | Decatur County | 2020-05-31
|  |  | 1900900 |  | Clark Dietz, Inc. | Grandview | 2020-05-31
|  |  | 1900901 |  | ARCADIS | Batesville | 2020-05-31
|  |  | 1900902 |  |  | Batesville | 2020-05-31
|  |  | 1900903 |  | ASC Group, Inc. | Beech Grove | 2020-05-31
|  |  | 1900904 |  |  | Warrick County | 2020-05-31
|  |  | 1900905 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2020-05-31
|  |  | 1900906 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2020-05-31
|  |  | 1900907 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2020-05-31
|  |  | 1900908 |  |  | Switzerland County | 2020-05-31
|  |  | 1900909 |  |  | Switzerland County | 2020-05-31
|  |  | 1900910 |  |  | Fayette County | 2020-05-31
|  |  | 1900911 |  |  | Knox County | 2020-05-31
|  |  | 1900912 |  |  | Howard County | 2020-05-31
|  |  | 1900913 |  |  | Howard County | 2020-05-31
|  |  | 1900914 |  |  | Howard County | 2020-05-31
|  |  | 1900915 |  |  | Howard County | 2020-05-31
|  |  | 1900916 |  |  | Dubois County | 2020-05-31
|  |  | 1900917 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1900918 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1900919 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1900920 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1900921 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1900922 |  |  | Perry County | 2020-05-31
|  |  | 1900923 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1900924 |  |  | Ripley County | 2020-05-31
|  |  | 1900925 |  |  | Ripley County | 2020-05-31
|  |  | 1900926 |  |  | Ripley County | 2020-05-31
|  |  | 1900927 |  |  | Marshall County | 2020-05-31
|  |  | 1900928 |  |  | Marshall County | 2020-05-31
|  |  | 1900929 |  |  | Marshall County | 2020-05-31
|  |  | 1900930 |  |  | Marshall County | 2020-05-31
|  |  | 1900931 |  |  | Marshall County | 2020-05-31
|  |  | 1900932 |  | Atlas Appraisals, LLC | Converse | 2020-05-31
|  |  | 1900933 |  |  | Dubois County | 2020-05-31
|  |  | 1900934 |  | Indiana Appraisal Group, Inc. | Richmond | 2020-05-31
|  |  | 1900935 |  | AECON, Inc. | Attica | 2020-05-31
|  |  | 1900936 |  | AECON, Inc. | Attica | 2020-05-31
|  |  | 1900937 |  | AECON, Inc. | Attica | 2020-05-31
|  |  | 1900938 |  |  | Washington County | 2020-05-31
|  |  | 1900939 |  |  | Wayne County | -339679.2083
|  |  | 1900940 |  |  | White County | 2020-05-31
|  |  | 1900941 |  | McCord, Inc. | Williamsport | 2020-05-31
|  |  | 1900942 |  | McCord, Inc. | Williamsport | 2020-05-31
|  |  | 1900943 |  |  | Clark County | 2020-05-31
|  |  | 1900944 |  | Apex Consulting & Surveying, Inc. | Winchester | 2020-05-31
|  |  | 1900945 |  | Apex Consulting & Surveying, Inc. | Winchester | 2020-05-31
|  |  | 1900946 |  | Apex Consulting & Surveying, Inc. | Winchester | 2020-05-31
|  |  | 1900947 |  | Apex Consulting & Surveying, Inc. | Winchester | 2020-05-31
|  |  | 1900948 |  |  | Dubois County | 2020-05-31
|  |  | 1900949 |  |  | Martin County | 2020-05-31
|  |  | 1900950 |  |  | Benton County | 2020-05-31
|  |  | 1900951 |  | Greenman-Pedersen, Inc. | New Pekin | 2020-05-31
|  |  | 1900952 |  | Greenman-Pedersen, Inc. | New Pekin | 2020-05-31
|  |  | 1900953 |  | Baxter & Woodman, Inc. | Crown Point | 2020-05-31
|  |  | 1900954 |  | Baxter & Woodman, Inc. | Crown Point | 2020-05-31
|  |  | 1900955 |  | Baxter & Woodman, Inc. | Crown Point | 2020-05-31
|  |  | 1900956 |  | Baxter & Woodman, Inc. | Crown Point | 2020-05-31
|  |  | 1900957 |  |  | Middletown | 2020-05-31
|  |  | 1900958 |  |  | Miami County | 2020-05-31
|  |  | 1900959 |  |  | Miami County | 2020-05-31
|  |  | 1900960 |  |  | Miami County | 2020-05-31
|  |  | 1900961 |  |  | Miami County | 2020-05-31
|  |  | 1900962 |  |  | Miami County | 2020-05-31
|  |  | 1900963 |  |  | Putnam County | -339679.2083
|  |  | 1900964 |  |  | Jackson County | 2020-05-31
|  |  | 1900965 |  | CoCal Consulting, LLC | Greenfield | 2020-05-31
|  |  | 1900966 |  | CoCal Consulting, LLC | Greenfield | 2020-05-31
|  |  | 1900967 |  | CoCal Consulting, LLC | Greenfield | 2020-05-31
|  |  | 1900968 |  | ABt SRBI | Angola | 2020-05-31
|  |  | 1900969 |  | Hy-Tech Response, Inc. | Porter | 2020-05-31
|  |  | 1900970 |  | Alliance Environmental Group, Inc. | Bruceville | 2020-05-31
|  |  | 1900971 |  | Danch Harner and Associates, Inc. | Jasper | 2020-05-31
|  |  | 1900972 |  |  | Fayette County | 2020-05-31
|  |  | 1900973 |  |  | Fayette County | 2020-05-31
|  |  | 1900974 |  |  | Morgan County | 2020-05-31
|  |  | 1900975 |  |  | Fayette County | 2020-05-31
|  |  | 1900976 |  | J. Williams Appraisal Group, LLC | Rushville | 2020-05-31
|  |  | 1900977 |  | J. Williams Appraisal Group, LLC | Rushville | 2020-05-31
|  |  | 1900978 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1900979 |  | Chicago Title Insurance Company | Gas City | 2020-05-31
|  |  | 1900980 |  |  | Monroe County | 2020-05-31
|  |  | 1900981 |  | Louis Joyner, Architect | Vincennes | 2020-05-31
|  |  | 1900982 |  |  | Monroe County | 2020-05-31
|  |  | 1900983 |  | AES Services, Inc. | Avilla | 2020-05-31
|  |  | 1900984 |  |  | Monroe County | 2020-05-31
|  |  | 1900985 |  | Klug Engineering, Inc. | Sullivan | 2020-05-31
|  |  | 1900986 |  | Klug Engineering, Inc. | Sullivan | 2020-05-31
|  |  | 1900987 |  | Klug Engineering, Inc. | Sullivan | 2020-05-31
|  |  | 1900988 |  |  | Pike County | 2020-05-31
|  |  | 1900989 |  |  | Pike County | 2020-05-31
|  |  | 1900990 |  |  | Pike County | 2020-05-31
|  |  | 1900991 |  |  | Pike County | 2020-05-31
|  |  | 1900992 |  | Hardcore Concrete Sawing Inc. | Osgood | 2020-05-31
|  |  | 1900993 |  | Independent Land Surveying, Inc. | Rensselaer | 2020-05-31
|  |  | 1900994 |  | Independent Land Surveying, Inc. | Rensselaer | 2020-05-31
|  |  | 1900995 |  | Independent Land Surveying, Inc. | Rensselaer | 2020-05-31
|  |  | 1900996 |  | Independent Land Surveying, Inc. | Rensselaer | 2020-05-31
|  |  | 1900997 |  | Independent Land Surveying, Inc. | Rensselaer | 2020-05-31
|  |  | 1900998 |  | J. Williams Appraisal Group, LLC | Rushville | 2020-05-31
|  |  | 1900999 |  |  | Merrillville | 2020-05-31
|  |  | 1901000 |  |  | Merrillville | 2020-05-31
|  |  | 1901001 |  | KERAMIDA Environmental, Inc. | Speedway | 2020-05-31
|  |  | 1901002 |  |  | Jennings County | 2020-05-31
|  |  | 1901003 |  |  | Highland | 2020-05-31
|  |  | 1901004 |  | J. Williams Appraisal Group, LLC | Rushville | 2020-05-31
|  |  | 1901005 |  |  | Jay County | 2020-05-31
|  |  | 1901006 |  | Louis Joyner, Architect | Vincennes | 2020-05-31
|  |  | 1901007 |  | ABt SRBI | Angola | 2020-05-31
|  |  | 1901009 |  | J. Williams Appraisal Group, LLC | Rushville | 2020-05-31
|  |  | 1901010 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2020-05-31
|  |  | 1901011 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2020-05-31
|  |  | 1901012 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2020-05-31
|  |  | 1901013 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2020-05-31
|  |  | 1901014 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2020-05-31
|  |  | 1901015 |  |  | Clark County | 2020-05-31
|  |  | 1901016 |  | HE-BFS, LLC | North Manchester | 2020-05-31
|  |  | 1901017 |  |  | Vanderburgh County | 2020-05-31
|  |  | 1901018 |  |  | Wells County | 2020-05-31
|  |  | 1901019 |  |  | Wells County | 2020-05-31
|  |  | 1901020 |  | ABt SRBI | Angola | 2020-05-31
|  |  | 1901021 |  | Beals-Moore & Associates, Inc. | Dale | 2020-05-31
|  |  | 1901022 |  | Beals-Moore & Associates, Inc. | Dale | 2020-05-31
|  |  | 1901023 |  | Beals-Moore & Associates, Inc. | Dale | 2020-05-31
|  |  | 1901024 |  | Beals-Moore & Associates, Inc. | Dale | 2020-05-31
|  |  | 1901025 |  | J. Williams Appraisal Group, LLC | Rushville | 2020-05-31
|  |  | 1901026 |  |  | Spencer County | 2020-05-31
|  |  | 1901027 |  |  | Posey County | 2020-05-31
|  |  | 1901028 |  |  | Wells County | 2020-05-31
|  |  | 1901029 |  |  | Wells County | 2020-05-31
|  |  | 1901030 |  |  | Wells County | 2020-05-31
|  |  | 1901031 |  |  | Posey County | 2020-05-31
|  |  | 1901032 |  |  | Posey County | 2020-05-31
|  |  | 1901033 |  | Global Management Group, Inc. | New Haven | 2020-05-31
|  |  | 1901034 |  |  | Vermillion County | -339679.2083
|  |  | 1901035 |  |  | Daviess County | 2020-05-31
|  |  | 1901036 |  |  | Daviess County | 2020-05-31
|  |  | 1901037 |  | Louis Joyner, Architect | Vincennes | 2020-05-31
|  |  | 1901038 |  | Manhard Consulting, Ltd. | West Lafayette | 2020-05-31
|  |  | 1901039 |  | Louis Joyner, Architect | Vincennes | 2020-05-31
|  |  | 1901040 |  | Active Environmental Services, Inc. | Bourbon | 2020-05-31
|  |  | 1901041 |  | Active Environmental Services, Inc. | Bourbon | 2020-05-31
|  |  | 1901042 |  | Active Environmental Services, Inc. | Bourbon | 2020-05-31
|  |  | 1901043 |  | Active Environmental Services, Inc. | Bourbon | 2020-05-31
|  |  | 1901044 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2020-05-31
|  |  | 1901045 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2020-05-31
|  |  | 1901046 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2020-05-31
|  |  | 1901047 |  |  | Hendricks County | -339679.2083
|  |  | 1901048 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2020-05-31
|  |  | 1901049 |  |  | Charlestown | 2020-05-31
|  |  | 1901050 |  | Hy-Tech Response, Inc. | Porter | -339679.2083
|  |  | 1901051 |  | Archonsortium, LLC | Cloverdale | -339679.2083
|  |  | 1901052 |  | Archonsortium, LLC | Cloverdale | -339679.2083
|  |  | 1901053 |  | DCD Consulting LLC | Indianapolis | 2020-05-31
|  |  | 1901054 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1901055 |  |  | Adams County | 2020-05-31
|  |  | 1901056 |  | Accidental Discoveries, LLC | Bluffton | 2020-05-31
|  |  | 1901057 |  | Crane Environmental Services, LLC | Homecroft | 2020-05-31
|  |  | 1901058 |  |  | Bartholomew County | 2020-05-31
|  |  | 1901059 |  |  | Carroll County | 2020-05-31
|  |  | 1901060 |  | Craig eonard Historic Preservation Consultant | Holton | 2020-05-31
|  |  | 1901061 |  |  | Carroll County | 2020-05-31
|  |  | 1901062 |  |  | Carroll County | 2020-05-31
|  |  | 1901063 |  | MCCARTIN - ASSOCIATES | Walton | 2020-05-31
|  |  | 1901064 |  | Anelena Ackerly | Carlisle | 2020-05-31
|  |  | 1901065 |  | Anelena Ackerly | Carlisle | 2020-05-31
|  |  | 1901066 |  | Aerial Services, Inc. | Brooklyn | 2020-05-31
|  |  | 1901067 |  | HDR Engineering, Inc. | North Liberty | 2020-05-31
|  |  | 1901068 |  | ICx Transportation Group | Pottawattamie Park | 2020-05-31
|  |  | 1901069 |  |  | Crawford County | 2020-05-31
|  |  | 1901070 |  |  | Morgan County | 2020-05-31
|  |  | 1901071 |  | Kristine Fallon Associates, Inc. | Sunman | 2020-05-31
|  |  | 1901072 |  | Corn Island Archaeology, LLC | Hebron | 2020-05-31
|  |  | 1901073 |  | General Energy Corp. | New Amsterdam | 2020-05-31
|  |  | 1901074 |  |  | Steuben County | 2020-05-31
|  |  | 1901075 |  |  | Steuben County | 2020-05-31
|  |  | 1901076 |  |  | Steuben County | 2020-05-31
|  |  | 1901077 |  |  | Steuben County | 2020-05-31
|  |  | 1901078 |  |  | New Harmony | 2020-05-31
|  |  | 1901079 |  |  | Scottsburg | 2020-05-31
|  |  | 1901080 |  |  | Scottsburg | 2020-05-31
|  |  | 1901081 |  |  | Scottsburg | 2020-05-31
|  |  | 1901082 |  |  | Scottsburg | 2020-05-31
|  |  | 1901083 |  |  | Scottsburg | 2020-05-31
|  |  | 1901084 |  |  | Vanderburgh County | 2020-05-31
|  |  | 1901085 |  | Afram Corporation | Brookston | 2020-05-31
|  |  | 1901086 |  |  | Cass County | 2020-05-31
|  |  | 1901087 |  | Hanson Professional Services, Inc. | Osceola | 2020-05-31
|  |  | 1901088 |  |  | Jasper County | 2020-05-31
|  |  | 1901089 |  |  | Jasper County | 2020-05-31
|  |  | 1901090 |  |  | Jasper County | 2020-05-31
|  |  | 1901091 |  |  | Jasper County | 2020-05-31
|  |  | 1901092 |  |  | Jasper County | 2020-05-31
|  |  | 1901093 |  |  | Scottsburg | 2020-05-31
|  |  | 1901094 |  | Spire Real Estate Valuation & Advisory, Inc. | Morocco | 2020-05-31
|  |  | 1901095 |  |  | Scottsburg | 2020-05-31
|  |  | 1901096 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901097 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901098 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1901099 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901100 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901101 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1901102 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901103 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901104 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901105 |  | Farah and Sons, Inc. | Michigan City | 2020-05-31
|  |  | 1901106 |  | Brenner Design Incorporated | Dyer | 2020-05-31
|  |  | 1901107 |  | Quantum Spatial, Inc. | Auburn | 2020-05-31
|  |  | 1901108 |  | Quantum Spatial, Inc. | Auburn | -339679.2083
|  |  | 1901109 |  | Quantum Spatial, Inc. | Auburn | -339679.2083
|  |  | 1901110 |  |  | Morgantown | 2020-05-31
|  |  | 1901111 |  |  | Scottsburg | 2020-05-31
|  |  | 1901112 |  | Burgess & Niple, Inc. | Eaton | 2020-05-31
|  |  | 1901113 |  |  | Upland | 2020-05-31
|  |  | 1901114 |  |  | Sullivan County | 2020-05-31
|  |  | 1901115 |  |  | Sullivan County | 2020-05-31
|  |  | 1901116 |  | Burgess & Niple, Inc. | Eaton | 2020-05-31
|  |  | 1901117 |  | Brenner Design Incorporated | Dyer | 2020-05-31
|  |  | 1901118 |  |  | Charlestown | 2020-05-31
|  |  | 1901119 |  |  | Brown County | 2020-05-31
|  |  | 1901120 |  |  | Brown County | 2020-05-31
|  |  | 1901121 |  | Home Equity Appraisals | Petersburg | 2020-05-31
|  |  | 1901122 |  |  | Charlestown | 2020-05-31
|  |  | 1901123 |  | Burgess & Niple, Inc. | Eaton | 2020-05-31
|  |  | 1901124 |  | CTL Engineering of Indiana, Inc. | Allen County | 2020-05-31
|  |  | 1901125 |  | Burgess & Niple, Inc. | Eaton | 2020-05-31
|  |  | 1901126 |  | Alt & Witzig Engineering, Inc. | Bunker Hill | 2020-05-31
|  |  | 1901127 |  |  | Kosciusko County | 2020-05-31
|  |  | 1901128 |  |  | Westfield | 2020-05-31
|  |  | 1901129 |  |  | Hamilton County | 2020-05-31
|  |  | 1901130 |  |  | Orange County | 2020-05-31
|  |  | 1901131 |  |  | Orange County | 2020-05-31
|  |  | 1901132 |  | FAA National, Inc. | Medora | 2020-05-31
|  |  | 1901133 |  |  | Hamilton County | 2020-05-31
|  |  | 1901134 |  |  | Kosciusko County | 2020-05-31
|  |  | 1901135 |  | McAlister Excavating Co., Inc. | Williams Creek | 2020-05-31
|  |  | 1901136 |  | CTLGroup | Fortville | 2020-05-31
|  |  | 1901137 |  | CTLGroup | Fortville | 2020-05-31
|  |  | 1901138 |  | EDP Consultants | Leo-Cedarville | 2020-05-31
|  |  | 1901139 |  | EDP Consultants | Leo-Cedarville | 2020-05-31
|  |  | 1901140 |  | EDP Consultants | Leo-Cedarville | 2020-05-31
|  |  | 1901141 |  |  | Elizabeth | 2020-05-31
|  |  | 1901142 |  |  | Hancock County | 2020-05-31
|  |  | 1901143 |  | EDP Consultants | Leo-Cedarville | 2020-05-31
|  |  | 1901144 |  |  | Hancock County | 2020-05-31
|  |  | 1901145 |  | III FFC | Princeton | 2020-05-31
|  |  | 1901146 |  | Archonsortium, LLC | Cloverdale | -339679.2083
|  |  | 1901147 |  | Manhard Consulting, Ltd. | West Lafayette | 2020-05-31
|  |  | 1901148 |  | John G. Brinkworth, Inc. | Shirley | 2020-05-31
|  |  | 1901149 |  | Gandhi and Associates, Inc. | Nappanee | 2020-05-31
|  |  | 1901150 |  |  | Hancock County | 2020-05-31
|  |  | 1901151 |  |  | Westfield | 2020-05-31
|  |  | 1901152 |  | Engineering Resources, Inc. | Madison | 2020-05-31
|  |  | 1901153 |  | Crane Environmental Services, LLC | Homecroft | 2020-05-31
|  |  | 1901154 |  | Gandhi and Associates, Inc. | Nappanee | 2020-05-31
|  |  | 1901155 |  |  | Vermillion County | -339679.2083
|  |  | 1901156 |  | Engineering Resources, Inc. | Madison | 2020-05-31
|  |  | 1901157 |  | III FFC | Princeton | 2020-05-31
|  |  | 1901158 |  |  | Bloomingdale | -339679.2083
|  |  | 1901159 |  | Farren Real Estate Services | Middlebury | 2020-05-31
|  |  | 1901160 |  | Farren Real Estate Services | Middlebury | 2020-05-31
|  |  | 1901161 |  |  | Franklin County | 2020-05-31
|  |  | 1901162 |  | Engineering Resources, Inc. | Madison | 2020-05-31
|  |  | 1901163 |  |  | Vermillion County | -339679.2083
|  |  | 1901164 |  |  | Tell City | 2020-05-31
|  |  | 1901165 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1901166 |  |  | Sandborn | 2020-05-31
|  |  | 1901167 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2020-05-31
|  |  | 1901168 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1901169 |  |  | Charlestown | 2020-05-31
|  |  | 1901170 |  |  | Francisco | 2020-05-31
|  |  | 1901171 |  | Bureau Veritas North America | East Germantown | 2020-05-31
|  |  | 1901172 |  | Engineering Resources, Inc. | Madison | 2020-05-31
|  |  | 1901173 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2020-05-31
|  |  | 1901174 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2020-05-31
|  |  | 1901175 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2020-05-31
|  |  | 1901176 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1901177 |  |  | Francisco | 2020-05-31
|  |  | 1901178 |  |  | Decatur County | 2020-05-31
|  |  | 1901179 |  | Fosse & Associates Architects, Inc. | Monroe City | 2020-05-31
|  |  | 1901180 |  |  | Cumberland | 2020-05-31
|  |  | 1901181 |  | Dyer Environmental Services | Lawrence | 2020-05-31
|  |  | 1901182 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2020-05-31
|  |  | 1901183 |  | Dyer Environmental Services | Lawrence | 2020-05-31
|  |  | 1901184 |  | Dyer Environmental Services | Lawrence | 2020-05-31
|  |  | 1901185 |  | Dyer Environmental Services | Lawrence | 2020-05-31
|  |  | 1901186 |  | Fosse & Associates Architects, Inc. | Monroe City | 2020-05-31
|  |  | 1901187 |  | Craig eonard Historic Preservation Consultant | Holton | 2020-05-31
|  |  | 1901188 |  | GeoSolutions, Inc. | New Castle | 2020-05-31
|  |  | 1901189 |  | Eco Logic, LLC | Logansport | 2020-05-31
|  |  | 1901190 |  | Eco Logic, LLC | Logansport | 2020-05-31
|  |  | 1901191 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1901192 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901193 |  |  | Huntington County | 2020-05-31
|  |  | 1901194 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901195 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901196 |  | HE-BFS, LLC | North Manchester | 2020-05-31
|  |  | 1901197 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1901198 |  | Craig eonard Historic Preservation Consultant | Holton | 2020-05-31
|  |  | 1901199 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901200 |  |  | Porter County | -339679.2083
|  |  | 1901201 |  | HDR Engineering, Inc. | North Liberty | 2020-05-31
|  |  | 1901202 |  | Associated Appraisal Group, Inc. | Columbia City | 2020-05-31
|  |  | 1901203 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901204 |  | Craig eonard Historic Preservation Consultant | Holton | 2020-05-31
|  |  | 1901205 |  | HDR Engineering, Inc. | North Liberty | 2020-05-31
|  |  | 1901206 |  |  | Hamlet | 2020-05-31
|  |  | 1901207 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901208 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901209 |  | Cheri K. Lewis Engineers | Garrett | 2020-05-31
|  |  | 1901210 |  | Courtland Title & Escrow, Inc. | Hobart | 2020-05-31
|  |  | 1901211 |  |  | Brownstown | 2020-05-31
|  |  | 1901212 |  |  | New Whiteland | 2020-05-31
|  |  | 1901213 |  |  | Brownstown | 2020-05-31
|  |  | 1901214 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901215 |  |  | Brownstown | 2020-05-31
|  |  | 1901216 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901217 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901218 |  |  | New Whiteland | 2020-05-31
|  |  | 1901219 |  |  | New Whiteland | 2020-05-31
|  |  | 1901220 |  |  | New Whiteland | 2020-05-31
|  |  | 1901221 |  |  | Porter County | 2020-05-31
|  |  | 1901222 |  | Casteel Real Estate | Franklin | 2020-05-31
|  |  | 1901223 |  |  | Bloomingdale | -339679.2083
|  |  | 1901224 |  |  | Huntington County | 2020-05-31
|  |  | 1901225 |  | Gandhi and Associates, Inc. | Nappanee | 2020-05-31
|  |  | 1901226 |  | Casteel Real Estate | Franklin | 2020-05-31
|  |  | 1901227 |  |  | Jennings County | 2020-05-31
|  |  | 1901228 |  |  | Sullivan County | 2020-05-31
|  |  | 1901229 |  |  | Cumberland | -339679.2083
|  |  | 1901230 |  |  | Huntingburg | 2020-05-31
|  |  | 1901231 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901232 |  | Construction Consultants & Inspection Services, LLC | Hanover | 2020-05-31
|  |  | 1901233 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901234 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901235 |  |  | Jennings County | 2020-05-31
|  |  | 1901236 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901237 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901238 |  | GeoSolutions, Inc. | New Castle | 2020-05-31
|  |  | 1901239 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901240 |  | Associated Appraisal Group, Inc. | Columbia City | 2020-05-31
|  |  | 1901241 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901242 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901243 |  | Mackie Consultants, LLC | Warsaw | 2020-05-31
|  |  | 1901244 |  | Wessler Engineering, Inc. | Wakarusa | 2020-05-31
|  |  | 1901245 |  | GeoSolutions, Inc. | New Castle | 2020-05-31
|  |  | 1901246 |  | Hey and Associates, Inc. | Pendleton | 2020-05-31
|  |  | 1901247 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2020-05-31
|  |  | 1901248 |  |  | New Albany | 2020-05-31
|  |  | 1901249 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2020-05-31
|  |  | 1901250 |  | Associated Appraisal Group, Inc. | Columbia City | 2020-05-31
|  |  | 1901251 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2020-05-31
|  |  | 1901252 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901253 |  | Associated Appraisal Group, Inc. | Columbia City | 2020-05-31
|  |  | 1901254 |  | Ark Engineering Services, Inc. | Coatesville | -339679.2083
|  |  | 1901255 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 1901256 |  |  | Munster | 2020-05-31
|  |  | 1901257 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901258 |  | Dennison and Company | Kingsford Heights | 2020-05-31
|  |  | 1901259 |  |  | Upland | 2020-05-31
|  |  | 1901260 |  |  | Jennings County | 2020-05-31
|  |  | 1901261 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901262 |  |  | North Vernon | 2020-05-31
|  |  | 1901263 |  |  | Munster | 2020-05-31
|  |  | 1901264 |  |  | North Vernon | 2020-05-31
|  |  | 1901265 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1901266 |  | Compliance Consulting Service, Inc. | Griffith | 2020-05-31
|  |  | 1901267 |  | Compliance Consulting Service, Inc. | Griffith | 2020-05-31
|  |  | 1901268 |  |  | Owen County | -339679.2083
|  |  | 1901269 |  | Chicago Testing Laboratory, Inc. | Gary | 2020-05-31
|  |  | 1901270 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1901271 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | 2020-05-31
|  |  | 1901272 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | 2020-05-31
|  |  | 1901273 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | 2020-05-31
|  |  | 1901274 |  |  | North Vernon | 2020-05-31
|  |  | 1901275 |  | Chicago Testing Laboratory, Inc. | Gary | 2020-05-31
|  |  | 1901276 |  | Chicago Testing Laboratory, Inc. | Gary | 2020-05-31
|  |  | 1901277 |  | Chicago Testing Laboratory, Inc. | Gary | 2020-05-31
|  |  | 1901278 |  | Chicago Testing Laboratory, Inc. | Gary | 2020-05-31
|  |  | 1901279 |  |  | North Vernon | 2020-05-31
|  |  | 1901280 |  | Chicago Testing Laboratory, Inc. | Gary | 2020-05-31
|  |  | 1901281 |  | Andrews Engineering, Inc. | Cannelton | 2020-05-31
|  |  | 1901282 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1901283 |  | Edwards and Kelcey | Lowell | 2020-05-31
|  |  | 1901284 |  |  | North Vernon | 2020-05-31
|  |  | 1901285 |  | Bettina Settles Realty, LLC | De Motte | 2020-05-31
|  |  | 1901286 |  | Bettina Settles Realty, LLC | De Motte | 2020-05-31
|  |  | 1901287 |  | Casteel Real Estate | Franklin | 2020-05-31
|  |  | 1901288 |  | Leitner and Associates, Inc. | Valparaiso | 2020-05-31
|  |  | 1901289 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901290 |  | Chicago Title Insurance Company | Gas City | 2020-05-31
|  |  | 1901291 |  | Iteris, Inc. | Rossville | 2020-05-31
|  |  | 1901292 |  | Iteris, Inc. | Rossville | 2020-05-31
|  |  | 1901293 |  | Jeffrey S. Juday | Shelbyville | 2020-05-31
|  |  | 1901294 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 1901295 |  | Edwards and Kelcey | Lowell | 2020-05-31
|  |  | 1901296 |  |  | Albion | 2020-05-31
|  |  | 1901297 |  |  | Albion | 2020-05-31
|  |  | 1901298 |  |  | Clinton County | 2020-05-31
|  |  | 1901299 |  |  | Albion | 2020-05-31
|  |  | 1901300 |  | HE-BFS, LLC | North Manchester | 2020-05-31
|  |  | 1901301 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901302 |  | McLane Realty, Inc. | Winona Lake | 2020-05-31
|  |  | 1901303 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901304 | Howard | Dodd Title Corporation | Kokomo | 2022-02-09 | PE
ROW
|  |  | 1901305 | Noble |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901306 | Noble |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901307 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901308 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 1901309 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2019-07-10 | CE
CN
PE
|  |  | 1901310 | Grant | CGS Real Estate Services, LLC | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1901311 | Randolph |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1901312 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1901313 | Wabash |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901314 |  |  | Kokomo Transit | -339679.2083
|  |  | 1901315 |  |  | Kokomo Transit | -339679.2083
|  |  | 1901316 |  |  | Kokomo | -339679.2083
|  |  | 1901317 |  |  | Kokomo Transit | -339679.2083
|  |  | 1901318 | Wabash |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901319 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2020-09-02
|  |  | 1901320 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2020-09-02
|  |  | 1901321 | Miami |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901322 | Allen |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901323 | Wabash |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901324 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901325 | Wabash |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901326 | Huntington |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901327 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901328 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901329 | Wells |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901330 | Wells |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901331 | Wells |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901332 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1901333 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901334 |  |  | Indiana Department of Transportation | 2019-08-07
|  |  | 1901335 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-05-31 | CE
CN
PE
|  |  | 1901336 | Henry | American Real Estate Appraisers, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 1901337 | Henry | GeoSolutions, Inc. | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1901338 | Hancock | CTLGroup | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1901339 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901340 | Wells |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901341 | Wells |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901342 |  |  | South Bend Transit | -339679.2083
|  |  | 1901343 | Adams | Bidinfo | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901344 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901345 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901346 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901347 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901348 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901349 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901350 | Huntington |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901351 | Huntington |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901352 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1901353 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1901354 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1901355 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1901356 | Allen |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1901357 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901358 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1901359 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1901360 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901361 |  | Brenner Design Incorporated | Indiana Department of Transportation | 2022-02-09
|  |  | 1901362 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901363 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901364 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901365 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1901366 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901367 | Howard | Dodd Title Corporation | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901368 | Tipton |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 1901369 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901370 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1901371 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901372 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901373 | Various |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1901374 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901375 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901376 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901377 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1901378 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1901379 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1901380 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 1901381 | Morgan | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13 | CE
CN
|  |  | 1901382 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 1901383 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901384 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-03-09
|  |  | 1901385 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901386 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901387 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901388 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-03-09
|  |  | 1901389 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2021-11-17
|  |  | 1901390 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1901391 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-03-09
|  |  | 1901392 | Johnson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901393 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1901394 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1901395 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901396 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-04-06
|  |  | 1901397 | Johnson |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
UT
|  |  | 1901398 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1901399 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901400 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-03-09
|  |  | 1901401 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 1901402 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 1901403 | Marshall |  | Indiana Department of Transportation | 2022-02-09 | RR
|  |  | 1901404 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901405 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-09-15
|  |  | 1901406 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1901407 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901408 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-09-15
|  |  | 1901409 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2021-09-15
|  |  | 1901410 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2022-03-09
|  |  | 1901411 |  | Brenner Design Incorporated | Indiana Department of Transportation | 2022-02-09
|  |  | 1901412 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901413 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901414 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1901415 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1901416 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1901417 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901418 |  |  | Boone County | -339679.2083
|  |  | 1901419 | Jasper |  | Indiana Department of Transportation | 2022-01-12 | CN
RR
|  |  | 1901420 | Jasper |  | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 1901421 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901422 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901423 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901424 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901425 | Starke |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901426 | Starke |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901427 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901428 | Starke |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901429 | Starke |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901430 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1901431 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 1901432 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901433 |  |  | Indiana Department of Transportation | 2019-07-10
|  |  | 1901434 | Various |  | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1901435 | Hancock | CTLGroup | Fortville | 2022-07-13 | PE
ROW
|  |  | 1901436 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901437 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901438 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901439 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901440 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901441 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901442 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901443 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901444 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901445 |  | Manhard Consulting, Ltd. | Tippecanoe County | -339679.2083
|  |  | 1901446 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901447 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901448 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1901449 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901450 | Shelby | Jeffrey S. Juday | Indiana Department of Transportation | 2019-07-10 | CE
CN
|  |  | 1901451 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901452 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901453 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901454 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901455 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901456 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901457 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901458 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901459 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901460 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901461 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901462 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 1901463 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901464 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 1901465 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901466 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901467 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1901468 |  | MCIS LLC | Indiana Department of Transportation | 2021-11-17
|  |  | 1901469 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901470 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901471 | Newton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1901472 | Newton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1901473 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901474 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901475 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901476 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901477 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901478 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901479 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-03-09
|  |  | 1901480 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-01-13
|  |  | 1901481 |  | DCD Consulting LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 1901482 | Kosciusko |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901483 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1901484 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1901485 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901486 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901487 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901488 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901489 | Jay |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1901490 | Grant |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1901491 | Grant |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1901492 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901493 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901494 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901495 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901496 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 1901497 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901498 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901499 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901500 | Marion |  | Indiana Department of Transportation | 2021-10-14 | CE
CN
|  |  | 1901501 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901503 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901504 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901505 |  | Hydrogeology, Inc. | Indiana Department of Transportation | 2022-01-12
|  |  | 1901506 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2022-01-12
|  |  | 1901507 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901508 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2022-03-09
|  |  | 1901509 |  | EHI Consultants, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 1901510 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1901511 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2023-10-12
|  |  | 1901512 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1901513 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901514 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1901515 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1901516 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 1901517 | Carroll |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901518 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901519 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901520 |  | Another Test Company | Indiana Department of Transportation | 2023-07-12
|  |  | 1901521 | Hamilton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1901522 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901523 | Howard |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901524 | Marion |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1901525 | Marion |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1901526 | Tipton |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901527 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901529 | Marion |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 1901530 | Marion |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1901531 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901532 | Hamilton | Another Test Company | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1901533 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901534 |  | CGI | Evansville | -339679.2083
|  |  | 1901535 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901536 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1901537 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1901538 | Shelby |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901539 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2022-03-09
|  |  | 1901540 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 1901541 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 1901542 | Jay | IXOYE, Limited | Indiana Department of Transportation | 2022-03-09 | RR
|  |  | 1901543 | Shelby |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1901544 | Tipton |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901545 |  | 40th Parallel Surveying, LLC | Indiana Department of Transportation | 2020-02-05
|  |  | 1901546 | Howard |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1901547 |  | DCD Consulting LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1901548 |  | DCD Consulting LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1901549 |  | DCD Consulting LLC | Indiana Department of Transportation | 2022-02-09
|  |  | 1901550 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901551 | Delaware |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1901552 | Hamilton |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901553 | Hamilton |  | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1901554 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901555 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
|  |  | 1901556 | Marion |  | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  | 1901557 | Marion |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901558 | Marion |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1901559 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901560 | Boone |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1901561 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901562 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901563 |  | Amereco Incorporated | Indiana Department of Transportation | -339679.2083
|  |  | 1901564 | Various |  | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1901565 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1901566 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901567 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901569 |  | Delcan Corporation | Kingman | 2020-05-31
|  |  | 1901570 |  | Delcan Corporation | Kingman | 2020-05-31
|  |  | 1901571 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901572 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901574 |  |  | Howard County | -339679.2083
|  |  | 1901575 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901576 | Various |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1901577 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901578 | Various |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1901579 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901581 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 1901582 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901583 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901584 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901585 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901586 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901587 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901588 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901589 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901590 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901591 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901592 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1901593 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2019-02-06
|  |  | 1901594 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2019-02-06
|  |  | 1901595 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1901596 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901597 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901598 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901599 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901600 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901601 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901602 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901603 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901604 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901605 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901606 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901607 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901608 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901609 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901610 |  |  | Vincennes | -339679.2083
|  |  | 1901611 |  |  | Crawfordsville | -339679.2083
|  |  | 1901612 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901613 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901614 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901615 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901616 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901617 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901618 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901619 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901620 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901621 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1901622 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1901623 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901624 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901625 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901626 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901627 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901628 |  |  | MPO - Northwest | -339679.2083
|  |  | 1901629 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901630 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1901631 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901632 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1901633 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901634 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901635 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901636 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901637 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901638 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901639 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901640 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901641 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901642 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901643 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2024-03-13
|  |  | 1901644 |  |  | Indiana Department of Transportation | 2019-08-07
|  |  | 1901645 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1901646 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1901647 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901648 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901649 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901650 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 1901651 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901652 | Morgan |  | Indiana Department of Transportation | 2019-11-20 | CE
CN
|  |  | 1901653 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1901654 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1901655 | Hendricks | AFRAM Group, Incorporated | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  |  | Marion | AFRAM Group, Incorporated | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901656 |  | Farren Real Estate Services | Indiana Department of Transportation | 2019-02-06
|  |  | 1901657 | Hendricks | AFRAM Group, Incorporated | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  |  | Marion | AFRAM Group, Incorporated | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1901658 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1901659 | Hamilton |  | Hamilton County | 2020-02-05 | CE
CN
|  |  | 1901660 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901661 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 1901662 |  |  | Terre Haute Transit Utility | -339679.2083
|  |  | 1901663 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2019-12-11
|  |  | 1901664 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901665 |  |  | West Lafayette | -339679.2083
|  |  | 1901666 |  | Manhard Consulting, Ltd. | West Lafayette | -339679.2083
|  |  | 1901667 |  | CPS Acquisitions, LLC | Fishers | 2023-11-15
|  |  | 1901668 |  | CPS Acquisitions, LLC | Fishers | 2023-10-12
|  |  | 1901669 |  | CPS Acquisitions, LLC | Fishers | 2023-10-12
|  |  | 1901670 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901671 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901672 |  | ASC Group, Inc. | Beech Grove | 2023-10-12
|  |  | 1901673 | Johnson | Casteel Real Estate | Franklin | 2021-11-17 | CE
CN
|  |  | 1901674 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1901675 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901676 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901677 | Various |  | Indiana Department of Transportation | 2019-09-11 | CE
CN
|  |  | 1901678 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901679 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901680 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901681 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901682 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1901683 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901684 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901685 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901686 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901687 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901688 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901689 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901690 |  |  | Knox County | 2022-02-09
|  |  | 1901691 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901692 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901693 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901694 |  |  | Hamilton County | 2023-11-15
|  |  | 1901695 |  |  | Hamilton County | 2023-08-09
|  |  | 1901696 |  |  | Hamilton County | 2023-08-09
|  |  | 1901697 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2020-04-01
|  |  | 1901698 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1901699 |  | CTL Engineering of Indiana, Inc. | Allen County | 2022-10-13
|  |  | 1901700 |  |  | Marion County | -339679.2083
|  |  | 1901701 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1901702 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901703 |  | CTL Engineering of Indiana, Inc. | Allen County | 2027-11-10
|  |  | 1901704 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901705 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2025-10-08 | PE
|  |  | 1901706 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1901707 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901708 | Johnson |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1901709 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901710 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  |  | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 1901711 |  | D & D Consulting Services, Inc. | Huntertown | 2025-10-08
|  |  | 1901712 |  | EDP Consultants | Leo-Cedarville | 2026-11-05
|  |  | 1901713 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901714 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1901715 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901716 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901717 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901718 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901719 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901720 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901721 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901722 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901723 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901724 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901725 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901726 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901727 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901728 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901729 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901730 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901731 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901732 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901733 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901734 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901735 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901736 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901737 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901738 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901739 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901740 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901741 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901742 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901743 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901744 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901745 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1901746 | Gibson |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1901747 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901748 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1901749 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901751 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1901752 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901753 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901754 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901755 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901756 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901757 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901758 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901759 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1901760 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901761 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901762 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901763 |  | AFRAM Group, Incorporated | Avon | 2023-10-12
|  |  | 1901764 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901765 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1901766 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901767 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901768 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901769 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901770 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901771 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901772 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901773 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901774 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901775 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901776 |  | CoCal Consulting, LLC | Greenfield | 2023-11-15
|  |  | 1901777 | Hamilton |  | Westfield | 2021-12-08 | CE
CN
|  |  | 1901778 | Vigo | Bayswater Company, LLC | Terre Haute | 2024-08-14 | PE
|  |  | 1901779 |  | Bayswater Company, LLC | Terre Haute | 2025-05-31
|  |  | 1901780 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901781 |  |  | Vigo County | 2026-08-05
|  |  | 1901782 |  | Bayswater Company, LLC | Terre Haute | 2025-05-31
|  |  | 1901783 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901784 |  | Consolidated Test Company | Hammond | 2022-08-10
|  |  | 1901785 |  | Bayswater Company, LLC | Terre Haute | 2025-08-06
|  |  | 1901786 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1901787 |  |  | Indiana Department of Transportation | 2019-12-11
|  |  | 1901788 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1901789 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901790 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 2023-08-09 | PE
|  |  | 1901791 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1901792 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901793 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901794 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901795 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901796 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 1901797 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901798 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901799 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901800 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901801 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901802 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1901803 | Marion |  | Indiana Department of Transportation | 2020-04-01 | CE
CN
|  |  | 1901804 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901805 |  | Dodd Title Corporation | Howard County | -339679.2083
|  |  | 1901806 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901807 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 1901808 |  | Fusion by Design, Inc. | Indiana Department of Transportation | 2020-05-07
|  |  | 1901809 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1901810 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901811 |  | Martinez Corporation | Indiana Department of Transportation | 2020-05-07
|  |  | 1901812 | Allen | Global Management Group, Inc. | New Haven | 2021-02-10 | CE
CN
RR
|  |  | 1901813 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901814 | Boone | Martinez Corporation | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1901815 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901816 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1901817 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901818 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901819 | Allen | Global Management Group, Inc. | New Haven | 2021-10-14 | CE
CN
|  |  | 1901820 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901821 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901822 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901823 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901824 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1901825 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901826 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901827 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901828 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901829 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901830 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901831 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2020-05-31
|  |  | 1901832 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1901833 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901834 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-13
|  |  | 1901835 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901836 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1901837 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 1901838 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901839 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901841 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901842 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1901843 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1901844 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 1901845 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 1901846 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1901847 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901848 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901849 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901850 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901851 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901852 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901853 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901854 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901855 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901856 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901857 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901858 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901859 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901860 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901861 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901862 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901863 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901864 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901865 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901866 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901867 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 1901868 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901869 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901870 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901871 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901872 | Marion |  | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901873 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901874 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901875 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901876 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901877 | Hendricks | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
PE
RR
|  |  | 1901878 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1901879 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1901880 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1901881 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901882 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901883 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1901884 | Allen | CTL Engineering of Indiana, Inc. | Allen County | 2021-10-14 | CE
CN
|  |  | 1901885 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901886 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901887 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1901888 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2023-01-19
|  |  | 1901889 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901890 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 1901891 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1901892 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901893 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 1901894 |  | Another Test Company | Carmel | 2023-07-12
|  |  | 1901895 |  | Another Test Company | Carmel | 2023-07-12
|  |  | 1901896 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901897 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901898 |  | Karen | Indiana Department of Transportation | 2020-05-07
|  |  | 1901899 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901900 |  | Consolidated Test Company | Hammond | 2024-02-14
|  |  | 1901901 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901902 |  | Consolidated Test Company | Hammond | 2024-02-14
|  |  | 1901903 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901904 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 1901905 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901906 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901907 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901908 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901909 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901910 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1901911 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1901912 |  | EDP Consultants | Leo-Cedarville | 2023-10-12
|  |  | 1901913 |  | EDP Consultants | Leo-Cedarville | 2023-10-12
|  |  | 1901914 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901915 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901916 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2020-02-05
|  |  | 1901917 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901918 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901919 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901920 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901921 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901922 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901923 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901924 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901925 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901926 |  |  | Indiana Department of Transportation | 2020-03-04
|  |  | 1901927 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901928 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901929 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901930 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901931 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901932 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901933 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901934 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1901935 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901936 |  |  | Indiana Department of Transportation | 2020-05-05
|  |  | 1901937 | Randolph |  | Randolph County | -339679.2083 | PE
|  |  |  | Various |  | Randolph County | -339679.2083 | PE
|  |  | 1901938 |  |  | MPO - Evansville | -339679.2083
|  |  | 1901939 |  |  | MPO - Evansville | -339679.2083
|  |  | 1901940 |  | CGI | Indiana Department of Transportation | 2023-01-19
|  |  | 1901941 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901942 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1901943 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1901944 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901945 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1901946 |  | DCD Consulting LLC | Indianapolis | 2024-05-31
|  |  | 1901947 |  | McDonough Associates, Inc. | Winfield | 2022-07-13
|  |  | 1901948 | Lake | Baxter & Woodman, Inc. | Crown Point | 2023-02-15 | PE
|  |  | 1901949 | Lake |  | Merrillville | 2022-02-09 | ROW
|  |  | 1901950 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901951 |  |  | Merrillville | 2023-12-11
|  |  | 1901952 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901953 |  | DCD Consulting LLC | Indianapolis | 2023-07-12
|  |  | 1901954 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901955 |  | DCD Consulting LLC | Indianapolis | 2023-09-13
|  |  | 1901956 |  | DCD Consulting LLC | Indianapolis | 2023-07-12
|  |  | 1901957 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901958 |  | DCD Consulting LLC | Indianapolis | 2023-10-12
|  |  | 1901959 |  | DCD Consulting LLC | Indianapolis | 2022-08-10
|  |  | 1901960 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901961 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1901962 |  | CGI | Indiana Department of Transportation | 2019-03-06
|  |  | 1901963 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1901964 |  |  | Indiana Department of Transportation | 2019-11-14
|  |  | 1901965 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-03-18 | CE
CN
|  |  | 1901966 | Scott |  | Indiana Department of Transportation | 2021-11-17 | CN
PE
|  |  | 1901967 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1901968 | Franklin |  | Indiana Department of Transportation | 2022-04-06 | CN
|  |  | 1901969 | Dearborn |  | Indiana Department of Transportation | 2021-11-17 | CN
RR
|  |  | 1901970 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1901971 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1901972 | Various |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1901973 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1901974 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1901975 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1901976 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1901977 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 1901978 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 1901979 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2019-03-06
|  |  | 1901980 |  | AFRAM Group, Incorporated | Indiana Department of Transportation | 2022-01-12
|  |  | 1901981 |  | Alliance Environmental Group, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 1901982 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901983 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1901984 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901985 |  | CTLGroup | Fortville | 2022-07-13
|  |  | 1901986 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901987 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1901988 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1901989 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901990 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1901991 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1901992 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1901993 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1901994 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1901995 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1901996 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1901997 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1901998 | Bartholomew |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
RR
|  |  | 1901999 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902000 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2029-07-20
|  |  | 1902001 |  |  | Porter County | 2029-07-20
|  |  | 1902002 | LaPorte | Douglass Environmental Services, Inc. | La Porte | 2023-01-19 | PE
|  |  | 1902003 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1902004 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 1902005 |  | Douglass Environmental Services, Inc. | La Porte | 2022-11-16
|  |  | 1902006 |  | Douglass Environmental Services, Inc. | La Porte | 2022-11-16
|  |  | 1902007 |  | Douglass Environmental Services, Inc. | La Porte | 2023-11-15
|  |  | 1902008 |  | Douglass Environmental Services, Inc. | La Porte | 2023-11-15
|  |  | 1902009 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2022-09-14
|  |  | 1902010 | Hamilton | H. Stewart Kline & Associates, Inc. | Noblesville | 2021-11-17 | CN
|  |  | 1902011 | Clark | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2020-05-07 | CE
CN
RR
|  |  | 1902012 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1902013 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1902014 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1902015 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1902016 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 1902017 | Hamilton |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1902018 | Various |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1902019 |  | Clyde L. Hawkins | Indiana Department of Transportation | 2023-01-19
|  |  | 1902020 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 1902021 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1902022 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1902023 | Jefferson |  | Indiana Department of Transportation | 2022-10-13 | PE
|  |  | 1902024 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1902025 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 1902026 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1902027 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902029 | LaPorte |  | LaPorte County | -339679.2083 | PE
|  |  |  | Various |  | LaPorte County | -339679.2083 | PE
|  |  | 1902030 | Fayette |  | Fayette County | -339679.2083 | PE
|  |  | 1902031 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1902032 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902033 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1902034 |  | Huff & Huff, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1902035 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902036 | Various |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 1902037 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1902038 | Various |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1902039 | Various |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
PE
|  |  | 1902040 | Various |  | Indiana Department of Transportation | 2022-02-09 | PE
|  |  | 1902041 | Elkhart |  | Indiana Department of Transportation | 2021-12-08 | PE
|  |  | 1902042 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1902043 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1902044 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 1902045 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902046 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902047 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902048 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1902049 |  | Iteris, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 1902050 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902051 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902053 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902055 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902056 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1902057 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902058 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902059 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1902060 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1902061 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1902062 |  | Clayton L. Roots | Indiana Department of Transportation | 2022-07-13
|  |  | 1902063 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1902064 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902065 | Decatur |  | Decatur County | -339679.2083 | PE
|  |  | 1902066 | Rush |  | Rush County | -339679.2083 | PE
|  |  | 1902067 | Carroll |  | Carroll County | -339679.2083 | PE
|  |  | 1902068 | Miami |  | Miami County | -339679.2083 | PE
|  |  | 1902069 | Greene |  | Greene County | -339679.2083 | PE
|  |  | 1902070 | Henry |  | Henry County | -339679.2083 | PE
|  |  | 1902071 |  |  | Vigo County | -339679.2083
|  |  | 1902072 | Hamilton |  | Hamilton County | -339679.2083 | PE
|  |  | 1902073 | Knox |  | Knox County | -339679.2083 | PE
|  |  | 1902074 | Warrick |  | Warrick County | -339679.2083 | PE
|  |  | 1902075 | Boone |  | Boone County | -339679.2083 | PE
|  |  | 1902076 | Huntington |  | Huntington County | -339679.2083 | PE
|  |  | 1902077 | Scott |  | Scott County | -339679.2083 | PE
|  |  | 1902078 | Brown |  | Brown County | -339679.2083 | PE
|  |  | 1902079 | Grant |  | Grant County | -339679.2083 | PE
|  |  | 1902080 | Shelby |  | Shelby County | -339679.2083 | PE
|  |  | 1902081 | Steuben |  | Steuben County | -339679.2083 | PE
|  |  | 1902082 | Wells |  | Wells County | -339679.2083 | PE
|  |  | 1902083 |  |  | LaGrange County | -339679.2083
|  |  | 1902084 | Jay |  | Jay County | -339679.2083 | PE
|  |  | 1902085 | Martin |  | Martin County | -339679.2083 | PE
|  |  | 1902086 |  |  | South Bend | 2020-02-19
|  |  | 1902087 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1902088 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1902089 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1902090 |  |  | Marion County | -339679.2083
|  |  | 1902091 |  |  | Marion County | -339679.2083
|  |  | 1902092 |  |  | Marion | -339679.2083
|  |  | 1902093 |  |  | Monroe County | -339679.2083
|  |  | 1902094 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902095 |  |  | Marion County | -339679.2083
|  |  | 1902096 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902097 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2019-05-09
|  |  | 1902098 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902099 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902100 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902101 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902102 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902103 | Knox | Louis Joyner, Architect | Vincennes | 2020-05-31 | CN
|  |  | 1902104 | Various |  | Indiana Department of Natural Resources | -339679.2083 | PE
|  |  | 1902105 | Various |  | Indiana Department of Natural Resources | 2020-05-31 | CN
|  |  | 1902106 | Jackson |  | Indiana Department of Natural Resources | 2020-05-31 | CN
|  |  | 1902107 | Clay |  | Indiana Department of Natural Resources | 2021-05-31 | CN
PE
|  |  | 1902108 | Spencer |  | Indiana Department of Natural Resources | 2020-05-31 | CN
PE
|  |  | 1902109 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902110 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902113 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902114 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902115 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902116 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902117 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902118 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902119 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902120 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902121 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1902122 | Dubois | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1902123 | Crawford |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1902124 | Porter | Huff & Huff, Inc. | Portage | 2022-02-09 | PE
|  |  | 1902125 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902126 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1902127 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 1902128 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 1902129 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902131 | Various |  | Indiana Department of Natural Resources | -339679.2083 | PE
|  |  | 1902132 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 1902133 |  | CSR Engineering, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1902134 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902135 |  | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 1902136 |  | Marine Solutions, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1902137 |  | H.R. Gray | Indiana Department of Transportation | 2022-11-16
|  |  | 1902138 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-02-05 | CN
|  |  |  | Henry | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-02-05 | CE
CN
|  |  |  | Marion | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-02-05 | CE
|  |  | 1902139 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2020-02-19 | CE
CN
PE
|  |  | 1902140 |  |  | Indiana Department of Transportation | 2019-02-06
|  |  | 1902141 | Marion | DCD Consulting LLC | Indianapolis | 2020-03-04 | CE
CN
|  |  | 1902142 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 1902143 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 1902144 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 1902145 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902146 | Crawford |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1902147 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1902148 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1902149 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1902150 | Johnson |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 1902151 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1902152 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1902153 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1902154 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902155 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902156 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902157 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902158 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1902159 |  |  | Seymour | -339679.2083
|  |  | 1902160 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 1902161 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1902162 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1902163 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 1902164 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1902165 | Madison |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1902166 | Shelby |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 1902167 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2020-12-09 | CE
CN
|  |  | 1902168 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902169 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902170 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902171 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 1902172 | Hamilton |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 1902173 | Hamilton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1902174 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902175 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1902176 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902177 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902178 | St. Joseph |  | South Bend | 2022-03-09 | PE
RR
|  |  | 1902179 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1902180 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 1902181 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2020-03-04 | CE
CN
|  |  | 1902182 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 1902183 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 1902184 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1902185 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1902186 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1902187 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1902188 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 1902189 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1902190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902191 | Morgan |  | Indiana Department of Transportation | 2020-01-29 | CE
CN
|  |  | 1902192 | Wayne |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 1902193 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902194 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902195 |  |  | Seymour | 2020-02-05
|  |  | 1902196 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902197 | LaPorte |  | LaPorte County | 2022-02-09 | PE
|  |  | 1902198 |  | Alliance Environmental Group, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 1902199 |  |  | Rush County | 2020-05-31
|  |  | 1902200 |  | IHS Global Insight | Princes Lakes | 2020-05-31
|  |  | 1902201 |  | Dummy Consulting Firm | Lake Station | 2020-05-31
|  |  | 1902202 |  | Cheri K. Lewis Engineers | Garrett | 2020-05-31
|  |  | 1902203 |  | Blood Hound, Inc. (former) | Delphi | 2020-05-31
|  |  | 1902204 |  |  | Warrick County | 2020-05-31
|  |  | 1902205 |  |  | Montgomery County | 2020-05-31
|  |  | 1902206 |  |  | Monroe County | 2020-05-31
|  |  | 1902207 |  | Appraisal Office of Central Indiana | Centerville | 2020-05-31
|  |  | 1902208 |  |  | LaPorte County | 2020-05-31
|  |  | 1902209 |  | Lonco, Inc. | Versailles | 2020-05-31
|  |  | 1902210 |  | EcoTec, Inc. | Loogootee | 2020-05-31
|  |  | 1902211 |  | EcoTec, Inc. | Loogootee | 2020-05-31
|  |  | 1902212 |  | Absolute Title Services, LLC | Bloomington | 2020-05-31
|  |  | 1902213 |  |  | Monroe County | 2020-05-31
|  |  | 1902214 |  |  | Perry County | 2020-05-31
|  |  | 1902215 |  |  | Monroe County | 2020-05-31
|  |  | 1902216 |  | Booker Real Estate Services | Dune Acres | 2020-05-31
|  |  | 1902217 |  |  | Lawrence County | 2020-05-31
|  |  | 1902218 |  |  | Lawrence County | 2020-05-31
|  |  | 1902219 |  |  | St. Joseph County | 2020-05-31
|  |  | 1902220 |  |  | Wabash County | 2020-05-31
|  |  | 1902221 |  |  | Boone County | 2020-05-31
|  |  | 1902222 |  |  | Aurora | 2020-05-31
|  |  | 1902223 |  | Enginuity Management & Consulting Corporation | Markle | 2020-05-31
|  |  | 1902224 |  | Enginuity Management & Consulting Corporation | Markle | 2020-05-31
|  |  | 1902225 |  | Enginuity Management & Consulting Corporation | Markle | 2020-05-31
|  |  | 1902226 |  | Enginuity Management & Consulting Corporation | Markle | 2020-05-31
|  |  | 1902227 |  | Farren Real Estate Services | Middlebury | 2020-05-31
|  |  | 1902228 |  | Enginuity Management & Consulting Corporation | Markle | 2020-05-31
|  |  | 1902229 |  |  | Knox County | 2020-05-31
|  |  | 1902230 |  |  | Newton County | 2020-05-31
|  |  | 1902231 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2021-05-31
|  |  | 1902232 |  |  | Greene County | 2020-05-31
|  |  | 1902233 |  |  | Greene County | 2020-05-31
|  |  | 1902234 |  |  | Greene County | 2020-05-31
|  |  | 1902235 |  |  | Greene County | 2020-05-31
|  |  | 1902236 |  |  | Greene County | 2020-05-31
|  |  | 1902237 |  | Booker Real Estate Services | Dune Acres | 2020-05-31
|  |  | 1902238 |  | Land Construction Corp | Tipton | -339679.2083
|  |  | 1902239 |  |  | Randolph County | 2020-05-31
|  |  | 1902240 |  |  | Greene County | 2020-05-31
|  |  | 1902241 |  |  | Martin County | 2020-05-31
|  |  | 1902242 |  | Commonwealth Engineers, Inc. | Greenwood | 2020-05-31
|  |  | 1902243 |  | American Engineers, Inc. | Butler | 2020-05-31
|  |  | 1902244 |  |  | Shadeland | 2020-05-31
|  |  | 1902245 |  |  | Shadeland | 2020-05-31
|  |  | 1902246 |  |  | Shadeland | 2020-05-31
|  |  | 1902247 |  |  | Madison County | 2020-05-31
|  |  | 1902248 |  | ATSI Engineering Services | Beverly Shores | 2020-05-31
|  |  | 1902249 |  | MCIS LLC | Wanatah | 2020-05-31
|  |  | 1902250 |  |  | Chesterton | 2020-05-31
|  |  | 1902251 |  |  | Chesterton | 2020-05-31
|  |  | 1902252 |  | Associated Right-of-Way Services, Inc. | Columbus | 2020-05-31
|  |  | 1902253 |  | Home Equity Appraisals | Petersburg | 2020-05-31
|  |  | 1902254 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2020-05-31
|  |  | 1902255 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2020-05-31
|  |  | 1902256 |  |  | Dekalb County | -339679.2083
|  |  | 1902257 |  |  | Berne | 2020-05-31
|  |  | 1902258 |  |  | Randolph County | 2020-05-31
|  |  | 1902259 |  | Independent Appraisers-Consultants, Inc. | Remington | 2020-05-31
|  |  | 1902260 |  |  | LaGrange County | 2021-05-31
|  |  | 1902261 |  |  | Huntington County | 2020-05-31
|  |  | 1902262 |  | Harvard Title Searching | Owensville | 2020-05-31
|  |  | 1902263 |  |  | Berne | 2020-05-31
|  |  | 1902264 |  |  | LaGrange County | 2020-05-31
|  |  | 1902265 |  |  | Dearborn County | 2020-05-31
|  |  | 1902266 |  |  | Benton County | 2020-05-31
|  |  | 1902267 |  | Jacobs Pannicke Architects, Inc. | Sellersburg | 2020-05-31
|  |  | 1902268 |  |  | Switzerland County | 2020-05-31
|  |  | 1902269 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1902270 |  | Innis Consulting Group, LLC | Rocky Ripple | 2020-05-31
|  |  | 1902271 |  | ETC Institute | Linden | 2020-05-31
|  |  | 1902272 |  |  | Vanderburgh County | 2020-05-31
|  |  | 1902273 |  |  | Warren County | 2020-05-31
|  |  | 1902274 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Palmyra | 2020-05-31
|  |  | 1902275 |  |  | Benton County | 2020-05-31
|  |  | 1902276 |  | MCIS LLC | Wanatah | 2020-05-31
|  |  | 1902277 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Palmyra | 2020-05-31
|  |  | 1902278 |  | Indiana University | Roachdale | -339679.2083
|  |  | 1902279 |  |  | Franklin County | 2020-05-31
|  |  | 1902280 |  | Eagle Ridge Civil Engineering Services, LLC | Linton | 2020-05-31
|  |  | 1902281 |  | McDonough Associates, Inc. | Winfield | 2020-05-31
|  |  | 1902282 |  |  | Allen County | 2020-05-31
|  |  | 1902283 |  | Griffin Real Estate Services, Inc. | New Ross | -339679.2083
|  |  | 1902284 |  | E.J. Breneman, LP | Boone County | 2020-05-31
|  |  | 1902285 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902286 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902287 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902288 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902289 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902290 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902291 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902292 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902293 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902294 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902295 |  | D & D Consulting Services, Inc. | Huntertown | 2020-05-31
|  |  | 1902296 |  | A & A Consultants, Inc. | Amo | -339679.2083
|  |  | 1902297 |  | Harvard Title Searching | Owensville | 2020-05-31
|  |  | 1902298 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902299 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902300 |  | Collier Transport Inc. | Greensburg | 2020-05-31
|  |  | 1902301 |  | Americas Engineers, Inc. | Cannelburg | 2020-05-31
|  |  | 1902302 |  | GAI Consultants, Inc. | Mooresville | 2020-05-31
|  |  | 1902303 |  |  | Monon | 2020-05-31
|  |  | 1902304 |  |  | Vanderburgh County | 2020-05-31
|  |  | 1902305 |  |  | Vanderburgh County | 2020-05-31
|  |  | 1902306 |  |  | Daleville | 2020-05-31
|  |  | 1902307 |  | Chicago Title Insurance Company | Gas City | 2020-05-31
|  |  | 1902308 |  | Fidelity National Title Insurance Company, Inc. | Milan | 2020-05-31
|  |  | 1902309 |  | Chicago Title Insurance Company | Gas City | 2020-05-31
|  |  | 1902310 |  | Louis Joyner, Architect | Vincennes | 2020-05-31
|  |  | 1902311 |  | Horner and Shifrin, Inc. | Plainfield | -339679.2083
|  |  | 1902312 |  | JJR, LLC | Santa Claus | 2020-05-31
|  |  | 1902313 |  |  | LaGrange County | 2020-05-31
|  |  | 1902314 |  | Associated Right-of-Way Services, Inc. | Columbus | 2020-05-31
|  |  | 1902315 |  |  | Pike County | 2020-05-31
|  |  | 1902316 |  | Dynasty Group, Inc. | Lawrenceburg | 2020-05-31
|  |  | 1902317 |  | Dynasty Group, Inc. | Lawrenceburg | 2020-05-31
|  |  | 1902318 |  | Dynasty Group, Inc. | Lawrenceburg | 2020-05-31
|  |  | 1902319 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902320 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902321 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902322 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902323 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902324 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902325 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2020-05-31
|  |  | 1902326 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902327 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2020-05-31
|  |  | 1902328 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2020-05-31
|  |  | 1902329 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2020-05-31
|  |  | 1902330 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2020-05-31
|  |  | 1902331 |  |  | Franklin County | 2020-05-31
|  |  | 1902332 |  | Karen | St. John | 2020-05-31
|  |  | 1902333 |  | Durham Engineering, Inc. | Larwill | 2020-05-31
|  |  | 1902334 |  |  | Lawrence County | 2020-05-31
|  |  | 1902335 |  |  | Lawrence County | 2020-05-31
|  |  | 1902336 |  | Bowman, Barrett & Associates, Inc. | Dunreith | 2020-05-31
|  |  | 1902337 |  | Archaeological Consultants of Ossian | Clayton | -339679.2083
|  |  | 1902338 |  |  | Jefferson County | 2020-05-31
|  |  | 1902339 |  | American Commercial Title & Escrow | Burns Harbor | 2020-05-31
|  |  | 1902340 |  | B. L. A., Inc. | Corydon | 2020-05-31
|  |  | 1902341 |  | AV Consulting Engineers, Inc. | Bicknell | 2020-05-31
|  |  | 1902342 |  | Context, LLC | Harmony | -339679.2083
|  |  | 1902343 |  | Context, LLC | Harmony | -339679.2083
|  |  | 1902344 |  | Fidelity National Title Insurance Company, Inc. | Milan | 2020-05-31
|  |  | 1902345 |  |  | Huntington County | 2020-05-31
|  |  | 1902346 |  |  | Crawford County | 2020-05-31
|  |  | 1902347 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2020-05-31
|  |  | 1902348 |  |  | Wayne County | 2020-05-31
|  |  | 1902349 |  | Collier Transport Inc. | Greensburg | 2020-05-31
|  |  | 1902350 |  | Fugro Roadware, Inc. | Monticello | 2020-05-31
|  |  | 1902351 |  |  | Monon | 2020-05-31
|  |  | 1902352 |  | AV Consulting Engineers, Inc. | Bicknell | 2020-05-31
|  |  | 1902353 |  | Collier Transport Inc. | Greensburg | 2020-05-31
|  |  | 1902354 |  | MCCARTIN - ASSOCIATES | Walton | 2020-05-31
|  |  | 1902355 |  | Collier Transport Inc. | Greensburg | 2020-05-31
|  |  | 1902356 |  |  | Delaware County | 2020-05-31
|  |  | 1902357 |  | Hardcore Concrete Sawing Inc. | Osgood | 2020-05-31
|  |  | 1902358 |  | J.F. New & Associates, Inc. | Russiaville | 2020-05-31
|  |  | 1902359 |  | March Environmental Services, LLC | Westport | 2020-05-31
|  |  | 1902360 |  |  | Martin County | 2020-05-31
|  |  | 1902361 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 1902362 |  |  | Hamilton County | 2020-05-31
|  |  | 1902363 |  |  | Wayne County | 2020-05-31
|  |  | 1902364 |  | David Matthews Associates (Former) | Kempton | 2020-05-31
|  |  | 1902365 |  |  | South Bend | 2020-05-31
|  |  | 1902366 |  |  | Wayne County | 2020-05-31
|  |  | 1902367 |  | Matt L. Nepote, MAI | Whiting | 2020-05-31
|  |  | 1902368 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2020-05-31
|  |  | 1902369 |  |  | Roanoke | 2020-05-31
|  |  | 1902370 |  |  | Lanesville | 2020-05-31
|  |  | 1902371 |  | McCormick Engineering, LLC | Winamac | 2020-05-31
|  |  | 1902372 |  |  | Kentland | 2020-05-31
|  |  | 1902373 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2020-05-31
|  |  | 1902374 |  | Lamac Engineering Company | Thorntown | 2020-05-31
|  |  | 1902375 |  | Hazeltine & Associates, Inc. | Paoli | 2020-05-31
|  |  | 1902376 |  | LONCO, Inc. | Syracuse | 2021-05-31
|  |  | 1902377 |  | CDM Smith, Inc. | Fowler | 2020-05-31
|  |  | 1902378 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2020-05-31
|  |  | 1902379 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2020-05-31
|  |  | 1902380 |  | I. T. Business Corporation | Poseyville | 2020-05-31
|  |  | 1902381 |  | EDP Consultants | Leo-Cedarville | 2020-05-31
|  |  | 1902382 |  | American Engineers, Inc. | Butler | 2020-05-31
|  |  | 1902383 |  | I. T. Business Corporation | Poseyville | 2020-05-31
|  |  | 1902384 |  | CBRE, Inc. | Elnora | 2020-05-31
|  |  | 1902385 |  | HRV Conformance Verification Associates, Inc. | Ogden Dunes | 2020-05-31
|  |  | 1902386 |  | DuSABLE, Inc. | Lafayette | 2020-05-31
|  |  | 1902387 |  |  | Elkhart County | 2020-05-31
|  |  | 1902388 |  | Bertsch-Frank & Associates, LLC | Dayton | 2020-05-31
|  |  | 1902389 |  | Bertsch-Frank & Associates, LLC | Dayton | 2020-05-31
|  |  | 1902390 |  | Bertsch-Frank & Associates, LLC | Dayton | 2020-05-31
|  |  | 1902391 |  | Heritage Engineering, LLC | Patoka | 2020-05-31
|  |  | 1902392 |  | E.J. Breneman, LP | Lebanon | 2020-05-31
|  |  | 1902393 |  | DuSABLE, Inc. | Lafayette | 2020-05-31
|  |  | 1902394 |  |  | Lake County | 2020-05-31
|  |  | 1902395 |  | Hardlines Design Company | Ossian | 2020-05-31
|  |  | 1902396 |  | M-E Companies, Inc. | Wabash | 2020-05-31
|  |  | 1902397 |  | H.R. Gray | North Judson | 2020-05-31
|  |  | 1902398 |  | Fidelity National Title Insurance Company, Inc. | Milan | 2020-05-31
|  |  | 1902399 |  |  | Spiceland | 2020-05-31
|  |  | 1902400 |  | Eco Logic, LLC | Logansport | 2020-05-31
|  |  | 1902401 |  | Dummy Consulting Firm Too | Lakeville | 2020-05-31
|  |  | 1902402 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 1902403 |  | Certified Engineering, Inc. | Fremont | 2020-05-31
|  |  | 1902404 |  | Certified Engineering, Inc. | Fremont | 2020-05-31
|  |  | 1902405 |  |  | Benton County | 2020-05-31
|  |  | 1902406 |  |  | Benton County | 2020-05-31
|  |  | 1902407 |  |  | Benton County | 2020-05-31
|  |  | 1902408 |  |  | Knox | 2020-05-31
|  |  | 1902409 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902410 |  | Hazeltine & Associates, Inc. | Paoli | 2020-05-31
|  |  | 1902411 |  |  | Knox | 2020-05-31
|  |  | 1902412 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Mount Summit | 2020-05-31
|  |  | 1902413 |  |  | Pike County | 2020-05-31
|  |  | 1902414 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 1902415 |  | Capstone, Inc. | Francesville | 2020-05-31
|  |  | 1902416 |  | Hazeltine & Associates, Inc. | Paoli | 2020-05-31
|  |  | 1902417 |  |  | Scott County | 2020-05-31
|  |  | 1902418 |  | Bonar Group, LLC | Dugger | 2020-05-31
|  |  | 1902419 |  | Bayer & Becker, Inc. | Culver | 2020-05-31
|  |  | 1902420 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2020-05-31
|  |  | 1902421 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 1902422 |  | Martinez Corporation | Whitestown | 2020-05-31
|  |  | 1902423 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1902424 |  | Hazeltine & Associates, Inc. | Paoli | 2020-05-31
|  |  | 1902425 |  |  | Pike County | 2020-05-31
|  |  | 1902426 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902427 |  | Appraisers, Inc. | Chrisney | 2020-05-31
|  |  | 1902428 |  | GRL Engineers, Inc. | Mount Vernon | 2020-05-31
|  |  | 1902429 |  | Appraisers, Inc. | Chrisney | 2020-05-31
|  |  | 1902430 |  | Karen | St. John | 2020-05-31
|  |  | 1902431 |  | Bayer & Becker, Inc. | Culver | 2020-05-31
|  |  | 1902432 |  | Bayer & Becker, Inc. | Culver | 2020-05-31
|  |  | 1902433 |  | American Resources Group, Ltd. | Cambridge City | 2020-05-31
|  |  | 1902434 |  | CityWise Real Estate Services, LLC | Geneva | 2021-05-31
|  |  | 1902435 |  |  | Bartholomew County | 2020-05-31
|  |  | 1902436 |  | Duesler Realty House | Lagrange | 2020-05-31
|  |  | 1902437 |  |  | Clarksville | 2020-05-31
|  |  | 1902438 |  | AECOM Technical Services, Inc. | Ashley | 2020-05-31
|  |  | 1902439 |  | Debbie L. Morris | Kendallville | 2020-05-31
|  |  | 1902440 |  |  | Johnson County | 2020-05-31
|  |  | 1902441 |  | D & D Consulting Services, Inc. | Huntertown | 2020-05-31
|  |  | 1902442 |  |  | Lanesville | 2020-05-31
|  |  | 1902443 |  |  | Porter County | 2020-05-31
|  |  | 1902444 |  |  | Fillmore | -339679.2083
|  |  | 1902445 |  | CKW Land Surveying, Inc. | Farmland | 2020-05-31
|  |  | 1902446 |  | Andy Easley Engineering, Inc. | Carbon | -339679.2083
|  |  | 1902447 |  |  | Lanesville | 2020-05-31
|  |  | 1902448 |  | Dillterra LLC | Knightsville | -339679.2083
|  |  | 1902449 |  | Debbie L. Morris | Kendallville | 2020-05-31
|  |  | 1902450 |  | Global Land Surveying, LLC | New Harmony | 2020-05-31
|  |  | 1902451 |  | Banning Engineering, P.C. | Crawfordsville | 2020-05-31
|  |  | 1902452 |  |  | Parke County | -339679.2083
|  |  | 1902453 |  | Advanced Engineering Services Inc. | Bristol | 2021-05-31
|  |  | 1902454 |  | Knies Constr/Calcar Paving J/V | Lapaz | 2020-05-31
|  |  | 1902455 |  | Debbie L. Morris | Kendallville | 2020-05-31
|  |  | 1902456 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2020-05-31
|  |  | 1902457 |  |  | Martin County | 2020-05-31
|  |  | 1902458 |  | Foresight Land Surveying, Inc. | Monroe | 2020-05-31
|  |  | 1902459 |  | Corradino, LLC | Hillsboro | 2020-05-31
|  |  | 1902460 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2020-05-31
|  |  | 1902461 |  |  | Johnson County | 2020-05-31
|  |  | 1902462 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | -339679.2083
|  |  | 1902463 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2020-05-31
|  |  | 1902464 |  |  | Tell City | 2020-05-31
|  |  | 1902465 |  | Appraisers, Inc. | Chrisney | 2020-05-31
|  |  | 1902466 |  | Quantum Spatial, Inc. | Auburn | 2020-05-31
|  |  | 1902467 |  | Burns & McDonnell Engineering Company, Inc. | Edgewood | 2020-05-31
|  |  | 1902468 |  | McCullouch Consulting, LLC | Windfall | 2020-05-31
|  |  | 1902469 |  | CHA, Inc. | Farmersburg | 2020-05-31
|  |  | 1902470 |  | Quantum Spatial, Inc. | Auburn | 2020-05-31
|  |  | 1902471 |  | CHA, Inc. | Farmersburg | 2020-05-31
|  |  | 1902472 |  | CHA, Inc. | Farmersburg | 2020-05-31
|  |  | 1902473 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2020-05-31
|  |  | 1902474 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2020-05-31
|  |  | 1902475 |  |  | Hagerstown | 2020-05-31
|  |  | 1902476 |  |  | Clarks Hill | -339679.2083
|  |  | 1902477 |  |  | Blackford County | 2020-05-31
|  |  | 1902478 |  | Indiana Connect - a Joint Venture | Ridgeville | 2020-05-31
|  |  | 1902479 |  |  | Daleville | 2020-05-31
|  |  | 1902480 |  |  | Daleville | 2020-05-31
|  |  | 1902481 |  |  | Daleville | 2020-05-31
|  |  | 1902482 |  |  | Jefferson County | 2020-05-31
|  |  | 1902483 |  |  | Jefferson County | 2020-05-31
|  |  | 1902484 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2020-05-31
|  |  | 1902485 |  | C & E Clark, LLC | Elizabethtown | 2020-05-31
|  |  | 1902486 |  | Kevin K. Parsons & Associates, Inc. | Staunton | -339679.2083
|  |  | 1902487 |  |  | Porter County | 2020-05-31
|  |  | 1902488 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2020-05-31
|  |  | 1902489 |  | C & E Clark, LLC | Elizabethtown | 2020-05-31
|  |  | 1902490 |  | C & E Clark, LLC | Elizabethtown | 2020-05-31
|  |  | 1902491 |  | C & E Clark, LLC | Elizabethtown | 2020-05-31
|  |  | 1902492 |  | Edwards and Kelcey | Lowell | 2020-05-31
|  |  | 1902493 |  | Clyde L. Hawkins | Greendale | 2020-05-31
|  |  | 1902494 |  | Civil & Environmental Consultants, Inc. | Georgetown | 2020-05-31
|  |  | 1902495 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Palmyra | -339679.2083
|  |  | 1902496 |  |  | Roanoke | 2020-05-31
|  |  | 1902497 |  |  | Roanoke | 2020-05-31
|  |  | 1902498 |  |  | Roanoke | 2020-05-31
|  |  | 1902499 |  |  | Benton County | -339679.2083
|  |  | 1902500 |  | C & E Clark, LLC | Elizabethtown | 2020-05-31
|  |  | 1902501 |  | Accidental Discoveries, LLC | Bluffton | -339679.2083
|  |  | 1902502 |  | M-E Companies, Inc. | Wabash | 2020-05-31
|  |  | 1902503 |  | CivCon Services, Inc. | Gentryville | 2020-05-31
|  |  | 1902504 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902505 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902506 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902507 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902508 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2019-05-31
|  |  | 1902509 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902510 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902511 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2020-05-31
|  |  | 1902512 |  | Integra Realty Resources | Rosedale | -339679.2083
|  |  | 1902513 |  |  | Benton County | 2020-05-31
|  |  | 1902514 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2020-05-31
|  |  | 1902515 |  |  | Benton County | 2020-05-31
|  |  | 1902516 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2020-05-31
|  |  | 1902517 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 1902518 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 1902519 |  | EDP Consultants | Leo-Cedarville | 2020-05-31
|  |  | 1902520 |  | JRM Environmental, Inc. | Saratoga | 2020-05-31
|  |  | 1902521 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2020-05-31
|  |  | 1902522 |  | Burgess & Niple, Inc. | Eaton | 2020-05-31
|  |  | 1902523 |  | Durkin & Villalta Partners Engineering | Laurel | 2020-05-31
|  |  | 1902524 |  | CivCon Services, Inc. | Gentryville | 2020-05-31
|  |  | 1902525 |  | Apex Consulting & Surveying, Inc. | Winchester | 2020-05-31
|  |  | 1902526 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2020-05-31
|  |  | 1902527 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2020-05-31
|  |  | 1902528 |  | CivCon Services, Inc. | Gentryville | 2020-05-31
|  |  | 1902529 |  | CivCon Services, Inc. | Gentryville | 2020-05-31
|  |  | 1902530 |  | Land Construction Corp | Tipton | 2020-05-31
|  |  | 1902531 |  | CivCon Services, Inc. | Gentryville | 2020-05-31
|  |  | 1902532 |  | Indiana University | Roachdale | -339679.2083
|  |  | 1902533 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | 2020-05-31
|  |  | 1902534 |  | CivCon Services, Inc. | Gentryville | 2020-05-31
|  |  | 1902535 |  | Knies Constr/Calcar Paving J/V | Lapaz | 2020-05-31
|  |  | 1902536 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2020-05-31
|  |  | 1902537 |  | CHA, Inc. | Farmersburg | 2020-05-31
|  |  | 1902538 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2020-05-31
|  |  | 1902539 |  | John A. Doyle Associates, Inc. | Shipshewana | 2020-05-31
|  |  | 1902540 |  | 40th Parallel Surveying, LLC | Albany | 2020-05-31
|  |  | 1902541 |  | ETC Institute | Linden | 2020-05-31
|  |  | 1902542 |  | CGI | Evansville | 2020-05-31
|  |  | 1902543 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2020-05-31
|  |  | 1902544 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2020-05-31
|  |  | 1902545 |  |  | Grant County | 2020-05-31
|  |  | 1902546 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2020-05-31
|  |  | 1902547 |  |  | Warren County | 2020-05-31
|  |  | 1902548 |  | Level 5 Engineering, LLC | Van Buren | 2020-05-31
|  |  | 1902549 |  | ABNA of Illinois | Andrews | 2020-05-31
|  |  | 1902550 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2020-05-31
|  |  | 1902551 |  |  | Hagerstown | 2020-05-31
|  |  | 1902552 |  | GS-IN P.C. | Muncie | 2020-05-31
|  |  | 1902553 |  | Alfred Benesch & Company | Brookville | 2020-05-31
|  |  | 1902554 |  | Finley Engineering Group, Inc. | Millersburg | 2020-05-31
|  |  | 1902555 |  | InspectTech Systems, Inc. | Rome City | 2020-05-31
|  |  | 1902556 |  | E.J. Breneman, LP | Lebanon | 2020-05-31
|  |  | 1902557 |  | 40th Parallel Surveying, LLC | Albany | 2020-05-31
|  |  | 1902558 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2020-05-31
|  |  | 1902559 |  |  | Steuben County | 2020-05-31
|  |  | 1902560 |  | Michael Baker International, Inc. | Yorktown | 2020-05-31
|  |  | 1902561 |  | Jacobs Pannicke Architects, Inc. | Sellersburg | 2020-05-31
|  |  | 1902562 |  | Another Test Company | Carmel | 2020-05-31
|  |  | 1902563 |  | CH2M HILL, Inc. | Fairview Park | -339679.2083
|  |  | 1902564 |  | 40th Parallel Surveying, LLC | Albany | 2020-05-31
|  |  | 1902565 |  | Michael Baker International, Inc. | Yorktown | 2020-05-31
|  |  | 1902566 |  | 40th Parallel Surveying, LLC | Albany | 2020-05-31
|  |  | 1902567 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2020-05-31
|  |  | 1902568 |  | Land Construction Corp | Tipton | 2020-05-31
|  |  | 1902569 |  | Arrow Consulting Services, Inc. | Colfax | 2020-05-31
|  |  | 1902570 |  | E.J. Breneman, LP | Lebanon | 2020-05-31
|  |  | 1902571 |  | CEI Appraisal Group, Inc. | English | 2020-05-31
|  |  | 1902572 |  | Accu-Air Surveys, Inc. | Boonville | 2020-05-31
|  |  | 1902573 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2020-05-31
|  |  | 1902574 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2020-05-31
|  |  | 1902575 |  | KZF Design, Inc. | St. Joe | 2020-05-31
|  |  | 1902576 |  | Eel River Abstract | Lynn | 2020-05-31
|  |  | 1902577 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | 2020-05-31
|  |  | 1902578 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2020-05-31
|  |  | 1902579 |  |  | Lanesville | 2020-05-31
|  |  | 1902580 |  | Burrell Appraisal Service, Inc. | Edinburgh | 2020-05-31
|  |  | 1902581 |  | Michael Baker International, Inc. | Yorktown | 2020-05-31
|  |  | 1902582 |  | Michael Baker International, Inc. | Yorktown | 2020-05-31
|  |  | 1902583 |  | AFRAM Group, Incorporated | Avon | -339679.2083
|  |  | 1902584 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902585 |  | Dodd Title Corporation | Kokomo | 2020-05-31
|  |  | 1902586 |  | III FFC | Princeton | 2020-05-31
|  |  | 1902587 |  |  | Roanoke | 2020-05-31
|  |  | 1902588 |  | Landstory, Inc. | Grabill | 2020-05-31
|  |  | 1902589 |  | Landstory, Inc. | Grabill | 2020-05-31
|  |  | 1902590 |  | Landstory, Inc. | Grabill | 2020-05-31
|  |  | 1902591 |  | Douglass Environmental Services, Inc. | La Porte | 2020-05-31
|  |  | 1902592 |  | Land Consultants, Inc. | Topeka | 2020-05-31
|  |  | 1902593 |  | Land Consultants, Inc. | Topeka | 2020-05-31
|  |  | 1902594 |  | Land Consultants, Inc. | Topeka | 2020-05-31
|  |  | 1902595 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902596 |  | JCI Bridge Group, Inc. | Salem | 2020-05-31
|  |  | 1902597 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2020-05-31
|  |  | 1902598 |  | Accu-Air Surveys, Inc. | Boonville | 2020-05-31
|  |  | 1902599 |  | JCI Bridge Group, Inc. | Salem | 2020-05-31
|  |  | 1902600 |  |  | Lanesville | 2020-05-31
|  |  | 1902601 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2020-05-31
|  |  | 1902602 |  | Abonmarche Consultants of Indiana L.L.C. | Bloomfield | 2020-05-31
|  |  | 1902603 |  | Indiana 15 Regional Planning Commission | Reynolds | 2020-05-31
|  |  | 1902604 |  | Hagerty Engineering, Inc. | Oolitic | 2020-05-31
|  |  | 1902605 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2020-05-31
|  |  | 1902606 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902607 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902608 |  | Andrews Engineering, Inc. | Cannelton | 2020-05-31
|  |  | 1902609 |  | Bynum Fanyo & Associates, Inc. | Elberfeld | 2020-05-31
|  |  | 1902610 |  | Bayswater Company, LLC | Vigo County | -339679.2083
|  |  | 1902611 |  | M-E Companies, Inc. | Wabash | 2020-05-31
|  |  | 1902612 |  | C Blair Enterprises, Inc. | Elkhart | 2020-05-31
|  |  | 1902613 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902614 |  |  | Starke County | 2020-05-31
|  |  | 1902615 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902616 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902617 |  | Klug Engineering, Inc. | Sullivan | 2020-05-31
|  |  | 1902618 |  | Douglass Environmental Services, Inc. | La Porte | 2020-05-31
|  |  | 1902619 |  | Douglass Environmental Services, Inc. | La Porte | 2020-05-31
|  |  | 1902620 |  | Commonwealth Engineers, Inc. | Greenwood | 2020-05-31
|  |  | 1902621 |  | Commonwealth Engineers, Inc. | Greenwood | 2020-05-31
|  |  | 1902622 |  | Klug Engineering, Inc. | Sullivan | 2020-05-31
|  |  | 1902623 |  |  | Huntingburg | 2020-05-31
|  |  | 1902624 |  | Duneland Group, Inc. | Lapel | 2020-05-31
|  |  | 1902625 |  |  | Huntingburg | 2020-05-31
|  |  | 1902626 |  |  | Alexandria | 2020-05-31
|  |  | 1902627 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902628 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 1902629 |  |  | Munster | 2020-05-31
|  |  | 1902630 |  |  | West Baden Springs | 2020-05-31
|  |  | 1902631 |  |  | Munster | 2020-05-31
|  |  | 1902632 | Various |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 1902633 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1902634 |  |  | Indiana Department of Transportation | 2020-01-15
|  |  | 1902635 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 1902636 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-07-08 | CE
CN
UT
|  |  | 1902637 |  | CGI | Indiana Department of Transportation | 2019-03-06
|  |  | 1902638 |  | DCD Consulting LLC | Indianapolis | 2022-07-13
|  |  | 1902639 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902640 | Montgomery |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1902641 | Montgomery |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1902642 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1902643 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902644 |  |  | Indiana Department of Transportation | 2019-10-29
|  |  | 1902645 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1902646 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2024-01-18
|  |  | 1902647 |  |  | Shelby County | 2020-05-31
|  |  | 1902648 |  |  | Shelby County | 2020-05-31
|  |  | 1902649 |  |  | Shelby County | 2020-05-31
|  |  | 1902650 |  |  | Shelby County | 2020-05-31
|  |  | 1902651 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 1902652 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 1902653 | Scott |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 1902654 |  |  | Indiana Department of Transportation | 2020-02-19
|  |  | 1902655 | Hendricks |  | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 1902656 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902657 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902658 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902659 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902660 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902661 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902662 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1902663 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1902664 | Various |  | Indiana Department of Transportation | 2022-12-07 | PE
|  |  | 1902665 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2019-05-09
|  |  | 1902666 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902667 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902668 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902669 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902670 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1902671 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902672 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902673 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902674 |  | DKA Associates, Inc. | Indiana Department of Transportation | 2020-04-01
|  |  | 1902675 |  |  | Lake County | 2023-12-13
|  |  | 1902676 |  |  | Lake County | 2023-12-13
|  |  | 1902677 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902678 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 1902679 | Various | DuSABLE, Inc. | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1902680 | Various | CH2M HILL, Inc. | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 1902681 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2019-05-09
|  |  | 1902682 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902683 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902684 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902685 |  | Leitner and Associates, Inc. | Valparaiso | -339679.2083
|  |  | 1902686 | Porter | Leitner and Associates, Inc. | Valparaiso | 2024-12-11 | PE
|  |  | 1902687 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1902688 |  | Farah and Sons, Inc. | Michigan City | -339679.2083
|  |  | 1902689 |  | Farah and Sons, Inc. | Michigan City | 2026-07-08
|  |  | 1902690 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902691 |  | Farah and Sons, Inc. | Michigan City | 2023-07-12
|  |  | 1902692 |  | Farah and Sons, Inc. | Michigan City | 2026-07-08
|  |  | 1902693 | Various |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
RR
|  |  | 1902694 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902695 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 1902696 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2021-08-11 | CN
|  |  | 1902697 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 1902698 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902699 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1902700 |  | Consolidated Test Company | Hammond | 2022-11-16
|  |  | 1902701 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 1902702 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902703 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902704 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902705 |  |  | Indiana Department of Natural Resources | 2025-05-31
|  |  | 1902706 |  | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1902707 |  | Courtland Title & Escrow, Inc. | Hobart | 2022-11-16
|  |  | 1902708 |  | Courtland Title & Escrow, Inc. | Hobart | -339679.2083
|  |  | 1902709 | Vanderburgh | CGI | Indiana Department of Transportation | 2023-05-10 | PE
|  |  | 1902710 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 1902711 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 1902712 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902713 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1902714 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1902715 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 1902716 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 1902717 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902718 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902719 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902720 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902721 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 1902722 | Marion | ASC Group, Inc. | Beech Grove | 2020-09-02 | CN
|  |  | 1902723 | Marion | ASC Group, Inc. | Beech Grove | 2020-09-02 | CN
|  |  | 1902724 | Marion | ASC Group, Inc. | Beech Grove | 2020-09-02 | CN
|  |  | 1902725 | Marion | ASC Group, Inc. | Beech Grove | 2020-09-02 | CN
|  |  | 1902726 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902727 | Madison |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 1902728 |  | DCD Consulting LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 1902729 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 1902730 |  |  | Indiana Department of Transportation | 2020-04-01
|  |  | 1902731 | Hamilton |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 1902732 | Johnson |  | Indiana Department of Transportation | 2020-05-07 | CE
CN
|  |  | 1902733 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 1902734 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1902735 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902736 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902737 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 1902738 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902739 |  | CGI | Indiana Department of Transportation | 2022-04-06
|  |  | 1902740 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1902741 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 1902742 | Clay | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | 2022-03-09 | PE
|  |  | 1902743 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902744 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902745 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902746 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902747 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902748 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902749 | Allen |  | Allen County | 2024-12-11 | PE
|  |  | 1902750 | Noble | Debbie L. Morris | Kendallville | 2024-12-11 | PE
|  |  | 1902751 | Vermillion |  | Vermillion County | 2024-12-11 | PE
|  |  | 1902752 | Montgomery | Banning Engineering, P.C. | Crawfordsville | 2024-12-11 | PE
|  |  | 1902753 |  | Horner and Shifrin, Inc. | Hendricks County | 2023-12-13
|  |  | 1902754 |  | DuSABLE, Inc. | Tippecanoe County | 2023-12-13
|  |  | 1902755 |  |  | Clark County | -339679.2083
|  |  | 1902756 |  |  | Lebanon | -339679.2083
|  |  | 1902757 | Huntington | D A Brown Engineering Consultants, Inc. | Huntington County | 2024-12-11 | PE
|  |  | 1902758 |  | Chastain & Associates LLC | Warren County | -339679.2083
|  |  | 1902759 |  |  | Madison | -339679.2083
|  |  | 1902760 | Johnson | Burrell Appraisal Service, Inc. | Edinburgh | 2024-09-11 | PE
|  |  | 1902761 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 1902762 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2024-12-11 | PE
|  |  | 1902763 | Johnson | Casteel Real Estate | Franklin | 2021-11-17 | CN
|  |  | 1902764 | Jackson | Janssen & Spaans Engineering, Inc. | Seymour | 2024-12-11 | PE
|  |  | 1902765 | Jackson |  | Jackson County | -339679.2083 | PE
|  |  | 1902766 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 1902767 | Johnson |  | Johnson County | 2024-10-09 | PE
|  |  | 1902768 | Clark |  | Clark County | 2024-12-11 | PE
|  |  | 1902769 | Washington | JCI Bridge Group, Inc. | Salem | 2024-12-11 | PE
|  |  | 1902770 | Jackson |  | Jackson County | -339679.2083 | PE
|  |  | 1902771 |  |  | Johnson County | 2023-10-12
|  |  | 1902772 | Monroe |  | Monroe County | 2024-12-11 | PE
|  |  | 1902773 | Dearborn |  | Dearborn County | 2024-10-09 | PE
|  |  | 1902774 | Franklin | ARCADIS | Batesville | 2024-12-11 | PE
|  |  | 1902775 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 1902776 | Rush | J. Williams Appraisal Group, LLC | Rushville | 2024-11-14 | PE
|  |  | 1902777 |  | Christopher B. Burke Engineering, Ltd. | Gaston | -339679.2083
|  |  | 1902778 |  |  | Huntingburg | -339679.2083
|  |  | 1902779 | Rush | J. Williams Appraisal Group, LLC | Rushville | 2024-11-14 | PE
|  |  | 1902780 | Howard |  | Howard County | 2024-12-11 | PE
|  |  | 1902781 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 1902782 |  |  | Gibson County | -339679.2083
|  |  | 1902783 | Hancock |  | Hancock County | 2024-12-11 | PE
|  |  | 1902784 | Gibson |  | Gibson County | 2024-12-11 | PE
|  |  | 1902785 | Martin |  | Martin County | 2024-12-11 | PE
|  |  | 1902786 | Hamilton | CPS Acquisitions, LLC | Fishers | 2023-09-13 | PE
|  |  | 1902787 | Posey | GRL Engineers, Inc. | Mount Vernon | 2024-12-11 | PE
|  |  | 1902788 |  |  | Spencer County | -339679.2083
|  |  | 1902789 |  |  | Santa Claus | -339679.2083
|  |  | 1902790 |  | H.R. Gray | North Judson | 2024-12-11
|  |  | 1902791 | Lawrence |  | Lawrence County | 2022-09-14 | PE
|  |  | 1902792 | Lawrence | ASA Land Surveying | Bedford | 2024-12-11 | PE
|  |  | 1902793 | Hancock |  | Hancock County | 2023-12-13 | PE
|  |  | 1902794 |  |  | Vanderburgh County | 2023-12-13
|  |  | 1902795 | Warrick |  | Warrick County | 2024-12-11 | PE
|  |  | 1902796 | Hancock |  | Hancock County | 2023-12-13 | PE
|  |  | 1902797 |  |  | Hancock County | -339679.2083
|  |  | 1902798 |  |  | Hamilton County | -339679.2083
|  |  | 1902799 | Wayne |  | Wayne County | 2024-12-11 | PE
|  |  | 1902800 |  |  | Hamilton County | 2025-02-12
|  |  | 1902801 | Hamilton |  | Westfield | 2024-07-10 | PE
|  |  | 1902802 | Wayne |  | Wayne County | 2024-07-10 | PE
|  |  | 1902803 |  | AAC Environmental Consulting, LLC | Madison County | 2024-12-11
|  |  | 1902804 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 1902805 | Union |  | Union County | 2024-12-11 | PE
|  |  | 1902806 | Wayne |  | Wayne County | 2024-12-11 | PE
|  |  | 1902807 | White |  | White County | 2024-12-11 | PE
|  |  | 1902808 | Jasper |  | Jasper County | 2024-12-11 | PE
|  |  | 1902809 |  |  | Marshall County | 2023-12-13
|  |  | 1902810 |  |  | Porter County | 2024-12-11
|  |  | 1902811 |  |  | Porter County | 2024-09-11
|  |  | 1902812 |  | Huff & Huff, Inc. | Porter County | 2024-12-11
|  |  | 1902813 |  |  | Porter County | 2024-12-11
|  |  | 1902814 | Starke |  | Starke County | 2024-12-11 | PE
|  |  | 1902815 | LaPorte |  | LaPorte County | 2024-12-11 | PE
|  |  | 1902816 |  | Independent Land Surveying, Inc. | Rensselaer | -339679.2083
|  |  | 1902817 |  |  | St. Joseph County | 2023-12-13
|  |  | 1902818 | LaPorte |  | LaPorte County | 2024-12-11 | PE
|  |  | 1902819 | Lake |  | Lake County | 2024-12-11 | PE
|  |  | 1902820 | Marshall | Howard J. Barth & Associates, Inc. | Marshall County | 2024-12-11 | PE
|  |  | 1902821 | Fulton |  | Fulton County | 2024-12-11 | PE
|  |  | 1902822 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 1902823 | Allen |  | Allen County | 2024-11-14 | PE
|  |  | 1902824 |  |  | Allen County | 2023-12-13
|  |  | 1902825 | Allen |  | Allen County | 2024-11-14 | PE
|  |  | 1902826 |  |  | Allen County | 2023-12-13
|  |  | 1902827 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902828 |  |  | Allen County | -339679.2083
|  |  | 1902829 | Elkhart |  | Elkhart County | 2024-12-11 | PE
|  |  | 1902830 |  | Chicago Testing Laboratory, Inc. | Gary | 2023-02-15
|  |  | 1902831 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902832 |  |  | Chesterton | 2023-07-12
|  |  | 1902833 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1902834 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2024-12-11 | PE
|  |  | 1902835 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 1902836 | Allen | CTL Engineering of Indiana, Inc. | Fort Wayne | 2024-11-14 | PE
|  |  | 1902837 | Allen | D & D Consulting Services, Inc. | Huntertown | 2024-10-09 | PE
|  |  | 1902838 | Kosciusko | Fink Roberts & Petrie | Kosciusko County | 2024-12-11 | PE
|  |  | 1902839 |  |  | Noble County | 2023-12-13
|  |  | 1902840 | Noble |  | Noble County | 2025-12-10 | PE
|  |  | 1902841 |  |  | Noble County | 2024-12-11
|  |  | 1902842 | Noble |  | Noble County | 2024-12-11 | PE
|  |  | 1902843 |  |  | Wells County | 2023-12-13
|  |  | 1902844 | Wells |  | Wells County | 2024-12-11 | PE
|  |  | 1902845 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1902846 |  |  | Wells County | 2023-12-13
|  |  | 1902847 | Grant | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2024-12-11 | PE
|  |  | 1902848 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 1902849 |  |  | Wabash County | 2023-12-13
|  |  | 1902850 | Wabash | HE-BFS, LLC | Wabash County | 2024-12-11 | PE
|  |  | 1902851 | Various |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 1902852 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902853 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902854 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2020-11-10 | CE
CN
|  |  | 1902855 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902856 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 1902857 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902858 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902859 |  |  | Tippecanoe County | -339679.2083
|  |  | 1902860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902861 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1902862 | Marion |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 1902863 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 1902864 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 1902865 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902866 |  | CoCal Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1902867 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902868 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 1902869 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 1902870 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902871 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902872 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902873 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902874 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902875 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902876 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902877 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902878 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902879 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902880 | Madison | Hey and Associates, Inc. | Pendleton | -339679.2083 | PE
|  |  | 1902881 | Clinton |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1902882 | Boone |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 1902883 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 1902884 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 1902885 |  | Collier Transport Inc. | Indiana Department of Transportation | 2023-04-12
|  |  | 1902886 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1902887 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 1902888 |  |  | Indiana Department of Transportation | 2021-01-13
|  |  | 1902889 |  |  | Indiana Department of Transportation | 2021-07-14
|  |  | 1902890 |  |  | Indiana Department of Transportation | 2021-07-14
|  |  | 1902891 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 1902892 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1902893 |  | Farren Real Estate Services | Indiana Department of Transportation | 2023-01-19
|  |  | 1902894 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 1902895 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1902896 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 1902897 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000014 | Bartholomew |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 2000015 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 2000016 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 2000017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000018 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2000019 | Various |  | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 2000020 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2000021 |  | Bettina Settles Realty, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2000022 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2024-08-14
|  |  | 2000023 | Lake | Applied Pavement Technology, Inc. | Cedar Lake | 2021-02-10 | CE
CN
|  |  | 2000024 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2000025 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2000026 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2000027 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2025-09-10
|  |  | 2000028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000029 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000030 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000031 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2000032 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2000033 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2000034 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2000035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000036 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2000037 | Various |  | Indiana Department of Transportation | 2020-07-08 | CE
CN
|  |  | 2000038 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000039 |  | Matt L. Nepote, MAI | Indiana Department of Transportation | 2022-12-07
|  |  | 2000040 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2022-07-13
|  |  | 2000041 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000042 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2022-07-13
|  |  | 2000043 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000044 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000045 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000046 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000047 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2000048 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2000049 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000051 |  |  | Indiana Department of Transportation | 2022-07-12
|  |  | 2000052 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000053 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2000054 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000055 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2000056 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000057 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000058 |  |  | Indiana Department of Transportation | 2022-07-12
|  |  | 2000059 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000060 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000061 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000062 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-10-13
|  |  | 2000063 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000064 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000065 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2000066 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000067 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000068 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000069 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000070 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000071 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000072 |  | Burgess & Niple, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000073 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000074 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000075 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000076 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000077 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000078 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000079 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2000080 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2000081 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000082 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000083 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000084 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000085 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 2000086 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000087 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2000088 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000089 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000090 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2000091 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000092 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2000093 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000094 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-10-13
|  |  | 2000095 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-10-13
|  |  | 2000096 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-10-13
|  |  | 2000097 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2000098 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000099 |  |  | NICTD (Northern Indiana Commuter Trans District) South Shore | -339679.2083
|  |  | 2000100 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000101 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000102 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000103 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000104 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000105 | Montgomery |  | Indiana Department of Transportation | 2022-07-13 | RR
|  |  | 2000106 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000107 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000108 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000109 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000110 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000111 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000112 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2022-08-10
|  |  | 2000113 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000114 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000115 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000116 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000117 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000118 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000119 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000120 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000121 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000122 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000123 | Clay |  | Indiana Department of Transportation | 2022-07-13 | RR
|  |  | 2000124 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000125 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000126 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000127 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000128 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2000129 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2000130 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000131 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000132 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 2000133 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000134 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000135 |  | Bettina Settles Realty, LLC | Indiana Department of Transportation | 2022-09-14
|  |  | 2000136 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000137 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000138 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000139 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000140 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000141 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000142 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2000143 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000144 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2000145 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2000146 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2025-04-09
|  |  | 2000147 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000148 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000149 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2000150 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000151 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000152 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000153 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2000154 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000155 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000156 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000158 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 2000159 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2000160 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2000161 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000162 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000163 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000164 |  | BradsKo Engineering and Surveying Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2000165 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000166 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000167 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000168 |  | IXOYE, Limited | Indiana Department of Transportation | -339679.2083
|  |  | 2000169 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000170 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 2000171 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 2000172 |  | ASC Group, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2000173 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000174 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000175 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000176 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000177 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000178 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000179 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000180 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000181 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2000182 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000183 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000184 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2000185 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000186 | Vanderburgh | CGI | Indiana Department of Transportation | 2023-05-10 | PE
|  |  | 2000187 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 2000188 |  |  | New Albany | 2024-10-09
|  |  | 2000189 |  | ASC Group, Inc. | Indiana Department of Transportation | 2026-04-08
|  |  | 2000190 |  |  | Indiana Department of Transportation | 2021-09-15
|  |  | 2000191 |  | Another Test Company | Indiana Department of Transportation | 2022-02-09
|  |  | 2000192 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000193 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000194 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000195 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000196 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000198 | Whitley |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 2000199 |  |  | Indiana Department of Transportation | 2021-09-15
|  |  | 2000200 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000201 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000202 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2000203 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000204 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000205 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000206 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000207 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000208 |  | ASC Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000209 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000211 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000212 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000213 |  | Edwards and Kelcey | Indiana Department of Transportation | 2023-09-13
|  |  | 2000214 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000215 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000216 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000217 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 2000218 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2000219 |  | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000221 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000223 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000224 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000225 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000226 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 2000227 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000228 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000229 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000230 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000231 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2025-04-09
|  |  | 2000232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000233 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2000234 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000235 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000237 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000238 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000239 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000240 | Jefferson |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 2000241 | Owen |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000242 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2000243 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000244 | Blackford |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000245 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2000246 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000247 | Johnson |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 2000248 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000249 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000251 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000254 | Noble |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000255 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000256 | Wabash |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000257 | Wabash |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000258 | Huntington |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000259 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000260 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-12-08 | CN
RR
|  |  | 2000261 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000262 | Adams |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000263 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000264 | Adams | Bidinfo | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000265 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000266 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2000267 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000268 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000269 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000270 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000271 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000272 | Allen |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000273 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000274 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000275 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000276 |  |  | Indiana Department of Transportation | 2025-04-09
|  |  | 2000277 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000278 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000279 | Allen |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000280 | Allen |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000281 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000282 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000283 | Allen |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000284 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2000285 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000286 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000287 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000288 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2000289 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 2000290 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000291 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000292 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000293 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000294 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000295 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000296 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000297 |  |  | Indiana Department of Natural Resources | 2023-11-15
|  |  | 2000298 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000299 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000300 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000301 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000302 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000303 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000304 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000305 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000306 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000307 |  | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000308 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000309 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000310 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000311 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000312 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000313 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000314 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000315 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000316 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000317 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000318 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000319 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000320 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000321 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000322 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000323 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000324 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000325 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000326 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000327 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000328 | Allen |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2000329 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000330 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000331 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000332 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000333 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000334 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000335 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000336 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000337 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000338 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000339 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000340 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000341 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000342 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000343 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000344 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 2000345 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000346 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000347 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000348 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000349 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000350 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000351 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000352 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000353 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000354 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000355 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000356 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000357 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2000358 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000359 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000360 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000361 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000362 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000363 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000364 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000365 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000366 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2000367 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000368 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000369 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2000370 |  | Lonco, Inc. | Indiana Department of Transportation | 2022-09-14
|  |  | 2000371 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000372 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000373 |  | ARCADIS | Indiana Department of Transportation | 2023-01-19
|  |  | 2000374 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000375 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000376 |  | Dodd Title Corporation | Indiana Department of Transportation | 2022-07-13
|  |  | 2000377 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2022-07-13 | RR
|  |  | 2000378 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 2000379 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000380 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000381 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000382 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000383 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000384 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000385 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000386 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2000387 |  | Lamac Engineering Company | Indiana Department of Transportation | 2023-07-12
|  |  | 2000388 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000389 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000390 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000391 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000392 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000393 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000394 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000395 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000396 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000397 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000398 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000399 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000400 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000401 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000402 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000403 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000404 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000405 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000406 |  | Dodd Title Corporation | Indiana Department of Transportation | 2022-07-13
|  |  | 2000407 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2024-03-13
|  |  | 2000408 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000409 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000410 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000411 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000412 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000413 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000414 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000415 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000416 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000417 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000418 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000419 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000420 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2000421 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000422 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000423 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2000424 |  | Another Test Company | Indiana Department of Transportation | 2022-07-13
|  |  | 2000425 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000426 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2000427 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000428 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000429 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000430 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000431 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000432 |  | Dodd Title Corporation | Indiana Department of Transportation | 2022-07-13
|  |  | 2000433 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000434 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000435 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000436 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000437 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000438 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000439 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000441 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000442 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000443 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000444 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000445 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000446 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 2000447 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000448 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000449 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000450 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000451 |  | Heritage Land Services | Indiana Department of Transportation | 2022-12-07
|  |  | 2000452 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2000453 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000454 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000455 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000456 | Warrick |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000457 | Spencer |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000458 | Spencer |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000459 | Johnson |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 2000460 | Johnson |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 2000461 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000462 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000463 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000464 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2024-02-14
|  |  | 2000465 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000466 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000467 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000468 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000469 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000470 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000471 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000472 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000473 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000474 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2000475 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2000476 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2000477 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 2000478 | Hancock |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 2000479 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000480 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000481 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000482 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000483 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000484 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000485 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000486 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000487 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000488 |  | Appraisal Specialists, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000489 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000490 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000491 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000492 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2000493 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000494 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000495 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000496 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000497 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2000498 |  |  | Indiana Department of Transportation | 2029-05-31
|  |  | 2000499 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2022-09-14
|  |  | 2000500 |  |  | Indiana Department of Transportation | 2030-05-31
|  |  | 2000501 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2022-09-14
|  |  | 2000502 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000503 |  | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 2000504 | Spencer |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000506 | Spencer |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000507 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2000508 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000509 |  | Land Construction Corp | Indiana Department of Transportation | 2023-09-13
|  |  | 2000510 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000511 | Spencer |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000512 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000513 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000514 |  | CGI | Indiana Department of Transportation | 2021-04-07
|  |  | 2000515 | Spencer |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2000516 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000517 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000518 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000519 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000520 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000521 |  | Eco Logic, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2000522 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000523 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000524 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000525 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000526 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2022-09-14
|  |  | 2000527 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000528 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000529 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-10-13
|  |  | 2000530 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000531 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000532 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2022-11-16
|  |  | 2000533 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000534 |  | Consolidated Test Company | Indiana Department of Transportation | 2022-11-16
|  |  | 2000535 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000536 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000537 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000538 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000539 | Vermillion |  | Indiana Department of Transportation | 2023-12-13 | RR
|  |  | 2000540 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000541 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000542 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000543 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000544 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000545 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000546 |  | Bidinfo | Indiana Department of Transportation | 2022-11-16
|  |  | 2000547 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000548 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000549 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000550 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000551 |  | Duke Energy Corporation | Indiana Department of Transportation | 2023-08-09
|  |  | 2000552 |  | Duke Energy Corporation | Indiana Department of Transportation | 2023-08-09
|  |  | 2000553 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000554 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000555 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000556 |  | Bidinfo | Indiana Department of Transportation | 2023-11-15
|  |  | 2000557 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000558 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000559 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000560 |  | Eel River Abstract | Indiana Department of Transportation | 2022-08-10
|  |  | 2000561 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2000562 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000563 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000564 |  | Maten (Bob) Gabor Gerdenich II | Indiana Department of Transportation | 2022-07-13
|  |  | 2000565 |  | Maten (Bob) Gabor Gerdenich II | Indiana Department of Transportation | 2022-07-13
|  |  | 2000566 |  | Maten (Bob) Gabor Gerdenich II | Indiana Department of Transportation | 2022-07-13
|  |  | 2000567 |  | Another Test Company | Indiana Department of Transportation | 2022-12-07
|  |  | 2000568 |  | Duneland Group, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2000569 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 2000570 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000571 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000572 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000573 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000574 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000575 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000576 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000577 |  | Land Construction Corp | Indiana Department of Transportation | 2022-10-13
|  |  | 2000578 |  | KERAMIDA Environmental, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2000579 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 2000580 |  | Coates Field Service, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000581 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000582 |  | James Pichler Appraisals | Indiana Department of Transportation | 2022-03-09
|  |  | 2000583 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000584 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2022-07-13
|  |  | 2000585 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000586 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000587 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000588 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000589 |  | CKW Land Surveying, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000590 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000591 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000592 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000593 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2022-09-14
|  |  | 2000594 |  | GS-IN P.C. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000595 |  | McCullouch Consulting, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 2000596 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2022-09-14
|  |  | 2000597 |  | CTLGroup | Indiana Department of Transportation | 2023-07-12
|  |  | 2000598 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000599 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000600 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000601 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000602 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000603 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000604 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000605 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000606 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 2000607 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000608 |  | Meridian Title Corporation | Indiana Department of Transportation | 2023-09-13
|  |  | 2000609 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2023-08-09
|  |  | 2000610 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000611 |  | ACMS Group, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000612 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000613 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2023-12-13
|  |  | 2000614 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000615 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000616 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000617 | Clinton | Carters Appraisal Service | Indiana Department of Transportation | 2020-05-07 | CE
CN
UT
|  |  | 2000618 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000619 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000620 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000621 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000622 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000623 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000624 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000625 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000626 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000627 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000628 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000629 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000630 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000631 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000632 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000633 | Warren |  | Indiana Department of Transportation | 2023-12-13 | RR
|  |  | 2000634 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000635 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000636 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000637 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000638 |  | CGI | Indiana Department of Transportation | 2023-01-19
|  |  | 2000639 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000640 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000641 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000642 |  | CGI | Indiana Department of Transportation | 2022-10-13
|  |  | 2000643 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2000644 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000645 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000646 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000647 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000648 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000649 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000650 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000651 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000652 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000653 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000654 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000655 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000656 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000657 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000658 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000659 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000660 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000661 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000662 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000663 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000664 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000665 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000666 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000667 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000668 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000669 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000670 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000671 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000672 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000673 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000674 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000675 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000676 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000677 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000678 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000679 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000680 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000681 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000682 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000683 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000684 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 2000685 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000686 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000687 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000688 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000689 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000690 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000691 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000692 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000693 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000694 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000695 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000696 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000697 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000698 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000699 |  | ASA Land Surveying | Indiana Department of Transportation | 2022-12-07
|  |  | 2000700 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 2000701 |  | CGI | Indiana Department of Transportation | 2022-07-13
|  |  | 2000702 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000703 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000704 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000705 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000706 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000707 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000708 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000709 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000710 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000711 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000712 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000713 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2023-11-15
|  |  | 2000714 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000715 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000716 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2023-11-15
|  |  | 2000717 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000718 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000719 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000720 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000721 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000722 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000723 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000724 |  | Bledsoe Riggert Cooper & James, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 2000725 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000726 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000727 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000728 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000729 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000730 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000731 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000732 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000733 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2000734 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000735 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000736 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000737 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000738 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000739 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000740 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000741 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000742 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000743 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000744 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000745 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 2000746 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000747 |  | McCormick Engineering, LLC | Indiana Department of Transportation | 2023-10-12
|  |  | 2000748 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000749 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000750 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000751 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000752 |  |  | Railroads | -339679.2083
|  |  | 2000753 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000754 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000755 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000756 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000757 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000758 |  | Consolidated Test Company | Indiana Department of Transportation | 2023-08-09
|  |  | 2000759 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000760 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000761 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000762 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000763 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000764 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000765 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000766 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000767 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000768 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000769 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000770 |  | Consolidated Test Company | Indiana Department of Transportation | 2023-08-09
|  |  | 2000771 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000772 |  | Consolidated Test Company | Indiana Department of Transportation | 2023-08-09
|  |  | 2000773 |  | GRL Engineers, Inc. | Mount Vernon | -339679.2083
|  |  | 2000774 |  | GRL Engineers, Inc. | Mount Vernon | -339679.2083
|  |  | 2000775 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000776 |  | GRL Engineers, Inc. | Mount Vernon | -339679.2083
|  |  | 2000777 |  | Consolidated Test Company | Indiana Department of Transportation | 2023-08-09
|  |  | 2000778 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000779 |  | GRL Engineers, Inc. | Mount Vernon | -339679.2083
|  |  | 2000780 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 2000781 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 2000782 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000783 | Kosciusko |  | Norfolk Southern Railway Co | -339679.2083 | RR
|  |  | 2000784 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000785 | LaPorte | Farah and Sons, Inc. | Chicago Southshore and S. Bend Railroad | -339679.2083 | RR
|  |  | 2000786 |  |  | Monroe County | -339679.2083
|  |  | 2000787 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000788 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000789 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000790 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000791 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000792 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000793 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000794 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2000795 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000796 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000797 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000798 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000799 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000800 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000801 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000802 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000803 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000804 |  |  | Railroads | -339679.2083
|  |  | 2000805 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000806 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000807 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000808 |  |  | Railroads | -339679.2083
|  |  | 2000809 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000810 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 2023-11-15
|  |  | 2000811 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000812 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000813 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000814 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000815 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000816 |  | Jill D Reed and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000817 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000818 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000819 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000820 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2023-12-13
|  |  | 2000821 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000822 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000823 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000824 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000825 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000826 |  | Fusion by Design, Inc. | Montpelier | -339679.2083
|  |  | 2000827 |  | Fusion by Design, Inc. | Montpelier | -339679.2083
|  |  | 2000828 |  | Kovachevich & Co., Inc. | Summitville | -339679.2083
|  |  | 2000829 |  |  | Kosciusko County | -339679.2083
|  |  | 2000830 |  |  | Mccordsville | -339679.2083
|  |  | 2000831 |  | Engineering Technologies, Inc. | Marengo | -339679.2083
|  |  | 2000832 |  |  | Brownsburg | -339679.2083
|  |  | 2000833 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 2000834 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 2000835 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 2000836 |  | Cornerstone Design | Highland | -339679.2083
|  |  | 2000837 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000838 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000839 |  | HLRD | Indiana Department of Transportation | 2022-12-07
|  |  | 2000840 |  |  | St. Joseph County | -339679.2083
|  |  | 2000841 |  |  | St. Joseph County | -339679.2083
|  |  | 2000842 |  |  | St. Joseph County | -339679.2083
|  |  | 2000843 |  |  | St. Joseph County | -339679.2083
|  |  | 2000844 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000845 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000846 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000847 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000848 |  | MBP Appraisals, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2000849 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000850 | Vigo |  | Indiana Department of Transportation | 2023-02-15 | RR
|  |  | 2000851 |  | Clayton L. Roots | Indiana Department of Transportation | 2022-10-13
|  |  | 2000852 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000853 |  | Alliance Environmental Group, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000854 |  | Copperhead Environmental Consulting | Indiana Department of Transportation | 2023-11-15
|  |  | 2000855 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000856 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000857 |  | Jeffrey P. French & Associates Land Surveying | Indiana Department of Transportation | 2023-09-13
|  |  | 2000858 |  | EcoTec, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000859 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000860 |  | KTA-TATOR, INC. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000861 |  | Bruce S. Grimes | Indiana Department of Transportation | 2023-07-12
|  |  | 2000862 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000863 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2000864 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000865 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000866 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000867 |  | ETC Institute | Indiana Department of Transportation | 2022-09-14
|  |  | 2000868 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2000869 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000870 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2000871 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000872 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000873 | Hendricks | All About Pavements, Inc. | Indiana Department of Transportation | 2023-10-12 | RR
|  |  | 2000874 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000875 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000876 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 2000877 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2000878 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000879 |  | Hatch Mott MacDonald | Indiana Department of Transportation | 2022-07-13
|  |  | 2000880 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000881 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2000882 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000883 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000884 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000885 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000886 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000887 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000888 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000889 |  | CGI | Indiana Department of Transportation | 2022-11-16
|  |  | 2000890 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000891 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2000892 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000893 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000894 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000895 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2022-11-16
|  |  | 2000896 |  | Engineering Technologies, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000897 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000898 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000899 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000900 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2000901 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000902 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2000903 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000904 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000905 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000906 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2000907 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2000908 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000909 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000910 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000911 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000912 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000913 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000914 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000915 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2022-08-10
|  |  | 2000916 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 2022-08-10
|  |  | 2000917 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000918 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2000919 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2000920 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000921 |  | ABt SRBI | Indiana Department of Transportation | 2023-08-09
|  |  | 2000922 |  | ABt SRBI | Indiana Department of Transportation | 2023-08-09
|  |  | 2000923 |  | CEI Appraisal Group, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2000924 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2024-01-18
|  |  | 2000925 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-09-13
|  |  | 2000926 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-09-13
|  |  | 2000927 |  | ERES International, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 2000928 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000929 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000930 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000931 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000932 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000933 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000934 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000935 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 2000936 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 2000937 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000938 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000939 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 2000940 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2000941 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2000942 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2000943 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2000944 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 2000945 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2000946 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000947 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000948 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000949 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000950 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000951 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000952 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000953 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2000954 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000955 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000956 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000957 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000958 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2023-08-09
|  |  | 2000959 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000960 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000961 |  | ERES International, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 2000962 |  | ERES International, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 2000963 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2000964 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000965 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000966 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000967 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000968 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000969 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000970 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2000971 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2000972 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2000973 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2022-08-10
|  |  | 2000974 |  | August Mack Environmental, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2000975 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2000976 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2000977 |  | ASC Group, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 2000978 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2000979 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2022-08-10
|  |  | 2000980 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2000981 |  | John A. Doyle Associates, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 2000982 |  | Debbie L. Morris | Indiana Department of Transportation | 2022-07-13
|  |  | 2000983 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 2000984 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000985 |  | ERES International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2000986 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | -339679.2083
|  |  | 2000987 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2000988 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000989 | Madison |  | MPO - Anderson | -339679.2083 | PL
|  |  | 2000990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000991 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000992 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000993 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000994 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2000995 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2000996 | Marshall |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 2000997 | Union |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 2000998 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2000999 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001000 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001014 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001022 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2001025 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2001030 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2001034 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2001035 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001036 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2001037 | Newton |  | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 2001038 | Jasper |  | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 2001039 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2001040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001041 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001042 |  |  | Indiana Department of Transportation | 2021-09-15
|  |  | 2001043 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2001044 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2001045 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2001046 |  | MCCARTIN - ASSOCIATES | Indiana Department of Transportation | 2022-02-09
|  |  | 2001047 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2001048 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2001049 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001050 | Monroe |  | MPO - Bloomington | -339679.2083 | PL
|  |  | 2001051 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2023-10-12
|  |  | 2001052 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2001053 |  | CGI | Indiana Department of Transportation | 2023-07-12
|  |  | 2001054 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2001055 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2001056 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2001057 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2001058 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 2001059 | Bartholomew |  | MPO - Columbus | -339679.2083 | PL
|  |  | 2001060 | Vanderburgh |  | MPO - Evansville | -339679.2083 | PL
|  |  | 2001061 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001062 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2001063 | Allen |  | MPO - Fort Wayne | -339679.2083 | PL
|  |  | 2001064 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001065 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001066 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-04-07
|  |  | 2001067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001068 | Marion |  | MPO - Indianapolis | -339679.2083 | PL
|  |  | 2001069 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2001070 | Tippecanoe |  | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 2001071 | Vermillion |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001072 | Montgomery |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001073 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
RR
|  |  | 2001074 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 2021-09-15 | CN
|  |  | 2001075 | Clinton |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001076 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001077 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001078 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001079 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001080 | Boone |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001081 | Putnam |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001082 | Putnam |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001083 | Howard |  | MPO - Kokomo | -339679.2083 | PL
|  |  | 2001084 | Tippecanoe |  | MPO - Lafayette | -339679.2083 | PL
|  |  | 2001085 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2001086 | Putnam |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001087 | Montgomery |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001088 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  | 2001089 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001090 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001091 | Delaware |  | MPO - Muncie | -339679.2083 | PL
|  |  | 2001092 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2001093 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2001094 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001095 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2001096 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001097 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001098 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2001099 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2001100 | LaPorte |  | MPO - Northwest | -339679.2083 | PL
|  |  | 2001101 | Elkhart |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  |  | St. Joseph |  | MPO - South Bend / Elkhart | -339679.2083 | PL
|  |  | 2001102 | Vigo |  | MPO - Terre Haute | -339679.2083 | PL
|  |  | 2001103 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2001104 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 2001105 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 2001106 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001107 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 2001108 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 2001109 |  |  | Indiana Department of Transportation | 2020-08-13
|  |  | 2001110 | Vigo |  | Indiana Department of Transportation | 2021-08-11 | CE
CN
|  |  | 2001111 |  |  | New Albany | -339679.2083
|  |  | 2001112 |  | AV Consulting Engineers, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 2001113 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2001114 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001115 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001116 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001117 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001118 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001119 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001120 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001121 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001122 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2001123 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001124 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001125 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001126 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001127 | Madison | Hey and Associates, Inc. | Pendleton | 2022-11-16 | PE
|  |  | 2001128 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2022-08-10
|  |  | 2001129 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 2001130 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001131 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001132 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2020-12-09
|  |  | 2001133 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001134 |  | ASC Group, Inc. | Indiana Department of Transportation | 2022-02-09
|  |  | 2001135 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 2001136 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 2001137 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 2001138 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 2001139 |  | JJR, LLC | Santa Claus | 2021-05-05
|  |  | 2001141 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 2001142 |  | Casteel Real Estate | Indiana Department of Transportation | 2019-05-09
|  |  | 2001143 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 2001144 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001145 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 2001146 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2001147 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001148 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001149 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001150 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001151 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 2001152 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 2001153 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 2001154 | Harrison | Dreibelbiss Title Company, Inc. | Indiana Department of Transportation | 2025-07-09 | PE
|  |  | 2001155 |  |  | Harrison County | 2022-07-13
|  |  | 2001156 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001157 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001158 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001159 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2001160 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-09-02 | CE
CN
|  |  | 2001161 |  | GS-IN P.C. | Indiana Department of Transportation | 2022-07-13
|  |  | 2001162 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2001163 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001164 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001165 |  | ERES International, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2001166 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | 2023-10-12
|  |  | 2001167 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2001168 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2001169 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2001170 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001171 |  | Clayton L. Roots | Indiana Department of Natural Resources | 2022-07-13
|  |  | 2001172 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2001173 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2001174 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2001175 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2001176 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2001177 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2001178 |  | III FFC | Indiana Department of Transportation | 2022-02-09
|  |  | 2001179 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2001180 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2001181 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2001182 |  |  | Whitley County | 2021-05-31
|  |  | 2001183 |  |  | Knox County | 2021-05-31
|  |  | 2001184 |  |  | Whitley County | 2021-05-31
|  |  | 2001185 |  | Meca Engineering Corporation of America Incorporated | Winslow | 2021-05-31
|  |  | 2001186 |  |  | Putnam County | -339679.2083
|  |  | 2001187 |  | AES Services, Inc. | Avilla | 2021-05-31
|  |  | 2001188 |  |  | New Whiteland | 2021-05-31
|  |  | 2001189 |  | Marine Solutions, Inc. | Westville | 2021-05-31
|  |  | 2001190 |  |  | Brown County | -339679.2083
|  |  | 2001191 |  | Indiana Appraisal Group, Inc. | Richmond | -339679.2083
|  |  | 2001192 |  |  | Clay County | -339679.2083
|  |  | 2001193 |  |  | Shelby County | -339679.2083
|  |  | 2001194 |  |  | Gibson County | 2021-05-31
|  |  | 2001195 |  |  | Vermillion County | -339679.2083
|  |  | 2001196 |  | Dorochoff Consulting, LLC | La Fontaine | 2021-05-31
|  |  | 2001197 |  |  | Hamilton County | -339679.2083
|  |  | 2001198 |  |  | Decatur County | -339679.2083
|  |  | 2001199 |  |  | Ripley County | 2021-05-31
|  |  | 2001200 |  |  | Miami County | 2021-05-31
|  |  | 2001201 |  |  | Chesterton | 2021-05-31
|  |  | 2001202 |  |  | Westfield | -339679.2083
|  |  | 2001203 |  |  | Miami County | 2021-05-31
|  |  | 2001204 |  | Engineering Resources, Inc. | Madison | 2021-05-31
|  |  | 2001205 |  |  | Ellettsville | 2021-05-31
|  |  | 2001206 |  |  | Hamlet | 2021-05-31
|  |  | 2001207 |  |  | Orange County | 2020-05-31
|  |  | 2001208 |  | AMEC E&I, Inc. | Washington | 2021-05-31
|  |  | 2001209 |  |  | Perry County | 2021-05-31
|  |  | 2001210 |  |  | Owen County | -339679.2083
|  |  | 2001211 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2021-05-31
|  |  | 2001212 |  | Danch Harner and Associates, Inc. | Jasper | 2021-05-31
|  |  | 2001213 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2021-05-31
|  |  | 2001214 |  | Wilcox Environmental Engineering, Inc. | Connersville | -339679.2083
|  |  | 2001215 |  |  | Warrick County | 2021-05-31
|  |  | 2001216 |  | AECOM Technical Services, Inc. | Ashley | 2021-05-31
|  |  | 2001217 |  |  | Hancock County | -339679.2083
|  |  | 2001218 |  | Brenner Design Incorporated | Dyer | 2021-05-31
|  |  | 2001219 |  | EDP Consultants | Leo-Cedarville | 2021-05-31
|  |  | 2001220 |  |  | Shelby County | 2021-05-31
|  |  | 2001221 |  |  | Marshall County | 2021-05-31
|  |  | 2001222 |  | Consolidated Test Company | Hammond | 2021-05-31
|  |  | 2001223 |  |  | Franklin County | -339679.2083
|  |  | 2001224 |  | Chicago Title Insurance Company | Gas City | 2021-05-31
|  |  | 2001225 |  |  | Jackson County | 2021-05-31
|  |  | 2001226 |  | Cheri K. Lewis Engineers | Garrett | 2021-05-31
|  |  | 2001227 |  | ASC Group, Inc. | Beech Grove | 2021-05-31
|  |  | 2001228 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2001229 |  |  | Sullivan County | 2021-05-31
|  |  | 2001230 |  |  | Carroll County | 2021-05-31
|  |  | 2001231 |  | Dave Helton & Associates, Inc. | Jonesboro | 2021-05-31
|  |  | 2001232 |  |  | Noble County | 2021-05-31
|  |  | 2001233 |  | Dave Helton & Associates, Inc. | Jonesboro | 2021-05-31
|  |  | 2001234 |  |  | Noble County | 2021-05-31
|  |  | 2001235 |  |  | Howard County | -339679.2083
|  |  | 2001236 |  |  | Daviess County | 2021-05-31
|  |  | 2001237 |  | Carters Appraisal Service | Frankfort | 2021-05-31
|  |  | 2001238 |  | Lonco, Inc. | Versailles | 2021-05-31
|  |  | 2001239 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2001240 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2001241 |  |  | Alfordsville | 2021-05-31
|  |  | 2001242 |  |  | Martin County | 2021-05-31
|  |  | 2001243 |  |  | Boone County | 2021-05-31
|  |  | 2001244 |  |  | Starke County | 2021-05-31
|  |  | 2001245 |  |  | Starke County | 2021-05-31
|  |  | 2001246 |  |  | Fountain County | 2021-05-31
|  |  | 2001247 |  | Gensic Engineering, Inc. | New Carlisle | 2021-05-31
|  |  | 2001248 |  |  | Monroe County | 2021-05-31
|  |  | 2001249 |  | Domain Architecture, Inc. | Kouts | 2021-05-31
|  |  | 2001250 |  |  | Vanderburgh County | 2021-05-31
|  |  | 2001251 |  |  | Hancock County | 2021-05-31
|  |  | 2001252 |  |  | Hancock County | 2021-05-31
|  |  | 2001253 |  | AAC Environmental Consulting, LLC | Anderson | 2021-05-31
|  |  | 2001254 |  |  | Fayette County | 2021-05-31
|  |  | 2001255 |  |  | Martin County | 2021-05-31
|  |  | 2001256 |  |  | Martin County | 2021-05-31
|  |  | 2001257 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2021-05-31
|  |  | 2001258 |  | Martin Riley, Inc. | Whiteland | 2021-05-31
|  |  | 2001259 |  | Accu-Air Surveys, Inc. | Boonville | 2021-05-31
|  |  | 2001260 |  | Haas & Associates, L.L.C. | Oldenburg | 2021-05-31
|  |  | 2001261 |  |  | Washington County | 2021-05-31
|  |  | 2001262 |  |  | Posey County | 2021-05-31
|  |  | 2001263 |  |  | Posey County | 2021-05-31
|  |  | 2001264 |  | III FFC | Princeton | 2021-05-31
|  |  | 2001265 |  |  | Wells County | 2021-05-31
|  |  | 2001266 |  | Context, LLC | Harmony | -339679.2083
|  |  | 2001267 |  |  | Jay County | 2021-05-31
|  |  | 2001268 |  | Baxter & Woodman, Inc. | Crown Point | 2021-05-31
|  |  | 2001269 |  | Baxter & Woodman, Inc. | Crown Point | 2021-05-31
|  |  | 2001270 |  |  | Hancock County | 2021-05-31
|  |  | 2001271 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2001272 |  | Hagerty Engineering, Inc. | Oolitic | 2021-05-31
|  |  | 2001273 |  | Land Construction Corp | Tipton | 2021-05-31
|  |  | 2001274 |  | KERAMIDA Environmental, Inc. | Speedway | 2021-05-31
|  |  | 2001275 |  | Huff & Huff, Inc. | Portage | 2021-05-31
|  |  | 2001276 |  |  | Fulton County | 2021-05-31
|  |  | 2001277 |  |  | Jasper County | 2021-05-31
|  |  | 2001278 |  |  | Fulton County | 2021-05-31
|  |  | 2001279 |  |  | Hancock County | 2021-05-31
|  |  | 2001280 |  |  | Alfordsville | -339679.2083
|  |  | 2001281 |  |  | Boone County | 2021-05-31
|  |  | 2001282 |  |  | Wells County | 2021-05-31
|  |  | 2001283 |  | Gensic Engineering, Inc. | New Carlisle | 2021-05-31
|  |  | 2001284 |  |  | Fountain County | 2021-05-31
|  |  | 2001285 |  |  | South Bend | 2021-05-31
|  |  | 2001286 |  | Carters Appraisal Service | Frankfort | 2021-05-31
|  |  | 2001287 |  | Indiana Search Technologies | Rising Sun | 2021-05-31
|  |  | 2001288 |  |  | Clarksville | -339679.2083
|  |  | 2001289 |  |  | Pulaski County | 2020-05-31
|  |  | 2001290 |  |  | St. Joseph County | 2021-05-31
|  |  | 2001291 |  |  | Franklin County | -339679.2083
|  |  | 2001292 |  | Central Diving Contractors | Frankton | 2021-05-31
|  |  | 2001293 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2021-05-31
|  |  | 2001294 |  |  | Warren County | 2021-05-31
|  |  | 2001295 |  |  | Spencer County | -339679.2083
|  |  | 2001296 |  | Hydrogeology, Inc. | Portland | 2021-05-31
|  |  | 2001297 |  | CSR Engineering, Inc. | Fort Branch | 2021-05-31
|  |  | 2001298 |  | ACMS Group, Inc. | Argos | 2021-05-31
|  |  | 2001299 |  | Hatch Mott MacDonald | Oxford | 2021-05-31
|  |  | 2001300 |  | Hannum, Wagle & Cline Engineering | Orleans | 2021-05-31
|  |  | 2001301 |  |  | Floyd County | 2021-05-31
|  |  | 2001302 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2021-05-31
|  |  | 2001303 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2021-05-31
|  |  | 2001304 |  |  | Clinton County | 2021-05-31
|  |  | 2001305 |  | BA Martin Architects, PC | Covington | -339679.2083
|  |  | 2001306 |  | D L Savage Engineering, Inc. | Hymera | 2021-05-31
|  |  | 2001307 |  | Farah and Sons, Inc. | Michigan City | 2021-05-31
|  |  | 2001308 |  | Spire Real Estate Valuation & Advisory, Inc. | Morocco | 2021-05-31
|  |  | 2001309 |  |  | Hamilton County | -339679.2083
|  |  | 2001310 |  |  | Hendricks County | -339679.2083
|  |  | 2001311 |  | J.A. Barker Engineering, Inc. | Russellville | -339679.2083
|  |  | 2001312 |  | ABt SRBI | Angola | 2021-05-31
|  |  | 2001313 |  | ABt SRBI | Angola | 2021-05-31
|  |  | 2001314 |  | Casteel Real Estate | Franklin | 2021-05-31
|  |  | 2001315 |  | Greenman-Pedersen, Inc. | New Pekin | 2021-05-31
|  |  | 2001316 |  | ARCADIS | Batesville | -339679.2083
|  |  | 2001317 |  | Eco-Tech Consultants, Inc. | Long Beach | 2021-05-31
|  |  | 2001318 |  |  | Pike County | 2021-05-31
|  |  | 2001319 |  | 2IM Group, LLC | Akron | 2021-05-31
|  |  | 2001320 |  | Civil Inspection Services, LLC | Goshen | 2021-05-31
|  |  | 2001321 |  | ARCADIS | Batesville | -339679.2083
|  |  | 2001322 |  |  | Pike County | 2021-05-31
|  |  | 2001323 |  | ABt SRBI | Angola | 2021-05-31
|  |  | 2001324 |  |  | Grant County | 2021-05-31
|  |  | 2001325 |  |  | Pike County | 2021-05-31
|  |  | 2001326 |  | Cornerstone Design | Highland | 2021-05-31
|  |  | 2001327 |  |  | Miami County | 2021-05-31
|  |  | 2001328 |  |  | Cass County | 2021-05-31
|  |  | 2001329 |  |  | Cumberland | 2021-05-31
|  |  | 2001330 |  |  | Cumberland | 2021-05-31
|  |  | 2001331 |  | Civil Engineering Consultants | Goodland | 2021-05-31
|  |  | 2001332 |  | Data Transfer Solutions, LLC | Jeffersonville | 2021-05-31
|  |  | 2001333 |  | MCCARTIN - ASSOCIATES | Walton | 2021-05-31
|  |  | 2001334 |  | Afram Corporation | Brookston | 2021-05-31
|  |  | 2001335 |  |  | Pike County | 2021-05-31
|  |  | 2001336 |  |  | Pike County | 2021-05-31
|  |  | 2001337 |  | Great Lakes Engineering, Inc. | New Palestine | 2021-05-31
|  |  | 2001338 |  | Hy-Tech Response, Inc. | Porter | 2021-05-31
|  |  | 2001339 |  |  | Ohio County | 2021-05-31
|  |  | 2001340 |  |  | Dubois County | 2021-05-31
|  |  | 2001341 |  |  | Dubois County | 2021-05-31
|  |  | 2001342 |  |  | Dubois County | 2021-05-31
|  |  | 2001343 |  |  | Moores Hill | 2021-05-31
|  |  | 2001344 |  | Boomerang Ventures, LLC | Dunkirk | 2021-05-31
|  |  | 2001345 |  |  | Bartholomew County | -339679.2083
|  |  | 2001346 |  | Casteel Real Estate | Franklin | -339679.2083
|  |  | 2001347 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 2001348 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2021-05-31
|  |  | 2001349 |  |  | Franklin County | -339679.2083
|  |  | 2001350 |  |  | Pike County | 2021-05-31
|  |  | 2001351 |  | Alliance Environmental Group, Inc. | Bruceville | 2021-05-31
|  |  | 2001352 |  |  | Dubois County | 2021-05-31
|  |  | 2001353 |  | Farren Real Estate Services | Middlebury | 2021-05-31
|  |  | 2001354 |  | Global Land Surveying, LLC | New Harmony | 2021-05-31
|  |  | 2001355 |  | Farren Real Estate Services | Middlebury | 2021-05-31
|  |  | 2001356 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Mount Summit | 2021-05-31
|  |  | 2001357 |  | Bureau Veritas North America | East Germantown | 2021-05-31
|  |  | 2001358 |  | HE-BFS, LLC | North Manchester | 2021-05-31
|  |  | 2001359 |  | Bowman, Barrett & Associates, Inc. | Dunreith | 2021-05-31
|  |  | 2001360 |  | Jeffrey S. Juday | Shelbyville | 2021-05-31
|  |  | 2001361 |  | Farren Real Estate Services | Middlebury | 2021-05-31
|  |  | 2001362 |  | HE-BFS, LLC | North Manchester | 2021-05-31
|  |  | 2001363 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2021-05-31
|  |  | 2001364 |  | Active Environmental Services, Inc. | Bourbon | 2021-05-31
|  |  | 2001365 |  | Active Environmental Services, Inc. | Bourbon | 2021-05-31
|  |  | 2001366 |  | Active Environmental Services, Inc. | Bourbon | 2021-05-31
|  |  | 2001367 |  |  | Munster | 2021-05-31
|  |  | 2001368 |  |  | Fountain County | 2021-05-31
|  |  | 2001369 |  | C Blair Enterprises, Inc. | Elkhart | 2021-05-31
|  |  | 2001370 |  |  | Munster | 2021-05-31
|  |  | 2001371 |  |  | Allen County | 2021-05-31
|  |  | 2001372 |  |  | Monroe County | 2021-05-31
|  |  | 2001373 |  |  | Fountain County | 2021-05-31
|  |  | 2001374 |  | CPS Acquisitions, LLC | Fishers | 2021-05-31
|  |  | 2001375 |  | Dillabaugh, Inc. | Knightstown | 2021-05-31
|  |  | 2001376 |  | H.R. Gray | North Judson | 2021-05-31
|  |  | 2001377 |  | Edwards and Kelcey | Lowell | 2021-05-31
|  |  | 2001378 |  | Digital Appraisals, LLC | Kirklin | 2021-05-31
|  |  | 2001379 |  | CRI Construction Inc. | Flora | 2021-05-31
|  |  | 2001380 |  | AECON, Inc. | Attica | 2021-05-31
|  |  | 2001381 |  | IXOYE, Limited | Redkey | 2021-05-31
|  |  | 2001382 |  | Louis Joyner, Architect | Vincennes | 2021-05-31
|  |  | 2001383 |  |  | Vanderburgh County | 2021-05-31
|  |  | 2001384 |  | GRW Engineers, Inc. | Mulberry | 2021-05-31
|  |  | 2001385 |  | Corn Island Archaeology, LLC | Hebron | 2021-05-31
|  |  | 2001386 |  |  | Henry County | 2021-05-31
|  |  | 2001387 |  |  | Vanderburgh County | 2021-05-31
|  |  | 2001388 |  |  | Elkhart County | 2021-05-31
|  |  | 2001389 |  | Louis Joyner, Architect | Vincennes | 2021-05-31
|  |  | 2001390 |  | Bettina Settles Realty, LLC | De Motte | 2021-05-31
|  |  | 2001391 |  | ABNA of Illinois | Andrews | 2021-05-31
|  |  | 2001392 |  | Archaeology and Geomorphology Services | Clinton | -339679.2083
|  |  | 2001393 |  |  | Huntington County | 2021-05-31
|  |  | 2001394 |  |  | Cass County | 2021-05-31
|  |  | 2001395 |  | Bidinfo | Decatur | 2021-05-31
|  |  | 2001396 |  | Linda F. Russell | Veedersburg | -339679.2083
|  |  | 2001397 |  | Land Title Service Company, LLC | Town Of Pines | 2021-05-31
|  |  | 2001398 |  | Cheri K. Lewis Engineers | Garrett | 2021-05-31
|  |  | 2001399 |  | Associated Appraisal Group, Inc. | Columbia City | 2021-05-31
|  |  | 2001400 |  | Jeffrey P. French & Associates Land Surveying | Shelburn | 2021-05-31
|  |  | 2001401 |  |  | Grant County | 2021-05-31
|  |  | 2001402 |  |  | Miami County | 2021-05-31
|  |  | 2001403 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 2001404 |  | Gandhi and Associates, Inc. | Nappanee | 2021-05-31
|  |  | 2001405 |  |  | White County | 2021-05-31
|  |  | 2001406 |  | ASA Land Surveying | Bedford | 2020-05-31
|  |  | 2001407 |  | Gandhi and Associates, Inc. | Nappanee | 2021-05-31
|  |  | 2001408 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2021-05-31
|  |  | 2001409 |  |  | Clark County | -339679.2083
|  |  | 2001410 |  | Gandhi and Associates, Inc. | Nappanee | 2021-05-31
|  |  | 2001411 |  | Courtland Title & Escrow, Inc. | Hobart | 2021-05-31
|  |  | 2001412 |  | ERES International, Inc. | Marion | 2021-05-31
|  |  | 2001413 |  |  | Clermont | 2021-05-31
|  |  | 2001414 |  | J. Williams Appraisal Group, LLC | Rushville | 2021-05-31
|  |  | 2001415 |  | J. Williams Appraisal Group, LLC | Rushville | 2021-05-31
|  |  | 2001416 |  | J. Williams Appraisal Group, LLC | Rushville | 2021-05-31
|  |  | 2001417 |  | CE Solutions, Inc. | Elwood | 2021-05-31
|  |  | 2001418 |  | Holloway Engineering, LLC | Peru | 2021-05-31
|  |  | 2001419 |  | MainLine Management, Inc. | Waynetown | 2021-05-31
|  |  | 2001420 |  | GS-IN P.C. | Muncie | 2021-05-31
|  |  | 2001421 |  | Midwest Archaeological Research Services, Inc. | Zionsville | -339679.2083
|  |  | 2001422 |  |  | Spencer County | 2021-05-31
|  |  | 2001423 |  | Midwest Archaeological Research Services, Inc. | Zionsville | 2021-05-31
|  |  | 2001424 |  | McLane Realty, Inc. | Winona Lake | 2021-05-31
|  |  | 2001425 |  |  | French Lick | 2021-05-31
|  |  | 2001426 |  |  | Spencer County | 2021-05-31
|  |  | 2001427 |  |  | New Whiteland | 2021-05-31
|  |  | 2001428 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2021-05-31
|  |  | 2001429 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2021-05-31
|  |  | 2001430 |  | Dennison and Company | Kingsford Heights | 2021-05-31
|  |  | 2001431 |  | Digital Appraisals, LLC | Kirklin | -339679.2083
|  |  | 2001432 |  | Home Equity Appraisals | Petersburg | 2021-05-31
|  |  | 2001433 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2021-05-31
|  |  | 2001434 |  | John Milner Associates, Architects, Archeologists, Planners, | Shoals | 2021-05-31
|  |  | 2001435 |  | Absolute Title Services, LLC | Bloomington | -339679.2083
|  |  | 2001436 |  |  | Dillsboro | 2021-05-31
|  |  | 2001437 |  |  | Newburgh | 2021-05-31
|  |  | 2001438 |  |  | Clarks Hill | 2021-05-31
|  |  | 2001439 |  | Heritage Land Services | Patriot | 2021-05-31
|  |  | 2001440 |  | Collins Engineers Incorporated | Greentown | 2021-05-31
|  |  | 2001441 |  | 40th Parallel Surveying, LLC | Albany | 2021-05-31
|  |  | 2001442 |  | Apex Consulting & Surveying, Inc. | Winchester | 2021-05-31
|  |  | 2001443 |  | HE-BFS, LLC | North Manchester | 2021-05-31
|  |  | 2001444 |  |  | Newburgh | 2021-05-31
|  |  | 2001445 |  | Leitner and Associates, Inc. | Valparaiso | 2021-05-31
|  |  | 2001446 |  | HE-BFS, LLC | North Manchester | 2021-05-31
|  |  | 2001447 |  |  | Jennings County | 2021-05-31
|  |  | 2001448 |  | EFI Global, Inc. | Lewisville | 2021-05-31
|  |  | 2001449 |  | Jeffrey S. Juday | Shelbyville | 2021-05-31
|  |  | 2001450 |  | Basin Field Services, Inc. | Crothersville | -339679.2083
|  |  | 2001451 |  | Jeffrey P. French & Associates Land Surveying | Shelburn | 2021-05-31
|  |  | 2001452 |  |  | New Albany | 2021-05-31
|  |  | 2001453 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | 2021-05-31
|  |  | 2001454 |  |  | South Whitley | 2021-05-31
|  |  | 2001455 |  | KPFF, Inc. | Springport | 2021-05-31
|  |  | 2001456 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2021-05-31
|  |  | 2001457 |  |  | Vigo County | -339679.2083
|  |  | 2001458 |  |  | Jennings County | 2021-05-31
|  |  | 2001459 |  |  | Jennings County | 2021-05-31
|  |  | 2001460 |  | CMF Engineering, Inc. | Ferdinand | 2021-05-31
|  |  | 2001461 |  | Appraisal Service | Chalmers | 2021-05-31
|  |  | 2001462 |  | Hannum, Wagle & Cline Engineering | Orleans | 2021-05-31
|  |  | 2001463 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2021-05-31
|  |  | 2001464 |  | Dan Moore Real Estate Services, Inc. | Jasonville | 2021-05-31
|  |  | 2001465 |  | Mackie Consultants, LLC | Warsaw | 2021-05-31
|  |  | 2001466 |  | Hanson Professional Services, Inc. | Osceola | 2021-05-31
|  |  | 2001467 |  |  | Huntingburg | 2021-05-31
|  |  | 2001468 |  |  | Huntingburg | 2021-05-31
|  |  | 2001469 |  |  | Churubusco | 2021-05-31
|  |  | 2001470 |  |  | South Whitley | 2021-05-31
|  |  | 2001471 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2021-05-31
|  |  | 2001472 |  | Landmark Archaeological & Environmental Services, Inc. | Trail Creek | 2021-05-31
|  |  | 2001473 |  | Archaeological Consultants of the Midwest, Inc. | Clear Lake | 2021-05-31
|  |  | 2001474 |  |  | Porter County | 2021-05-31
|  |  | 2001475 |  |  | Trafalgar | 2021-05-31
|  |  | 2001476 |  |  | Porter County | 2021-05-31
|  |  | 2001477 |  | Dyer Environmental Services | Lawrence | 2021-05-31
|  |  | 2001478 |  | Dyer Environmental Services | Lawrence | 2021-05-31
|  |  | 2001479 |  | Douglass Environmental Services, Inc. | La Porte | 2021-05-31
|  |  | 2001480 |  | Douglass Environmental Services, Inc. | La Porte | 2021-05-31
|  |  | 2001481 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2021-05-31
|  |  | 2001482 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2021-05-31
|  |  | 2001483 |  | Hey and Associates, Inc. | Pendleton | 2021-05-31
|  |  | 2001484 |  | Dyer Environmental Services | Lawrence | 2021-05-31
|  |  | 2001485 |  | Dummy Consulting Firm | Lake Station | 2021-05-31
|  |  | 2001486 |  | Hey and Associates, Inc. | Pendleton | 2021-05-31
|  |  | 2001487 |  |  | Clermont | 2021-05-31
|  |  | 2001488 |  | Chicago Title Insurance Company | Gas City | 2021-05-31
|  |  | 2001489 |  | Chicago Title Insurance Company | Gas City | 2021-05-31
|  |  | 2001490 |  | ERES International, Inc. | Marion | 2021-05-31
|  |  | 2001491 |  |  | Jennings County | 2021-05-31
|  |  | 2001492 |  |  | Jennings County | 2021-05-31
|  |  | 2001493 |  |  | West Baden Springs | 2021-05-31
|  |  | 2001494 |  | Collier Transport Inc. | Indiana Department of Transportation | 2022-04-06
|  |  | 2001495 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2020-10-07
|  |  | 2001496 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 2001497 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 2001498 |  |  | Indiana Department of Transportation | 2020-02-05
|  |  | 2001499 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001500 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001501 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001502 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001503 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001504 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001505 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2001506 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001507 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001508 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-04-07
|  |  | 2001509 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001510 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 2001511 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 2001512 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001513 | Various |  | Indiana University Purdue University Fort Wayne | -339679.2083 | PL
|  |  | 2001514 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001515 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001516 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001517 | Various |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2001518 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001519 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2001520 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2001521 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001522 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2022-03-09
|  |  | 2001523 | Allen |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 2001524 | Allen |  | Indiana Department of Transportation | 2020-08-05 | CE
CN
|  |  | 2001525 | Jay | IXOYE, Limited | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2001526 |  |  | Indiana Department of Transportation | 2021-01-13
|  |  | 2001527 |  |  | Indiana Department of Transportation | 2021-01-13
|  |  | 2001528 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001529 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001530 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001531 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001532 |  | ETC Institute | Indiana Department of Transportation | -339679.2083
|  |  | 2001533 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2001534 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2001535 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2001536 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2001537 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2001538 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001539 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 2001540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001541 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2001542 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2020-07-08
|  |  | 2001543 |  | DLZ Indiana, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2001544 |  |  | Indiana University Purdue University Fort Wayne | -339679.2083
|  |  | 2001545 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001546 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 2001547 |  |  | Indiana Department of Transportation | 2019-05-09
|  |  | 2001548 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001549 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001550 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001551 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001552 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001553 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001554 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001555 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001556 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001557 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001558 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001559 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001560 |  | KCI Technologies, Inc. | Southport | 2021-05-31
|  |  | 2001561 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2001562 |  |  | Indiana Department of Transportation | 2020-05-31
|  |  | 2001563 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001564 | Delaware | Michael Baker International, Inc. | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  |  | Madison | Michael Baker International, Inc. | Indiana Department of Transportation | 2021-01-13 | CN
|  |  | 2001565 |  | GS-IN P.C. | Indiana Department of Transportation | 2022-07-13
|  |  | 2001566 | Various |  | Indiana Department of Transportation | 2020-05-31 | CN
|  |  | 2001567 |  | Michael Baker International, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2001568 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001569 |  |  | ColumBUS Transit | -339679.2083
|  |  | 2001570 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001571 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001572 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2021-12-08
|  |  | 2001573 | Various |  | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 2001574 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001575 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001576 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001577 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001578 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001579 |  | Clayton L. Roots | Indiana Department of Transportation | 2022-04-06
|  |  | 2001580 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2019-03-06
|  |  | 2001581 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2001582 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001583 | Allen | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 2001584 |  |  | Indiana Department of Transportation | 2021-01-13
|  |  | 2001585 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2001586 |  |  | Wayne County | 2024-12-11
|  |  | 2001587 | Whitley |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 2001588 | Whitley |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 2001589 | Huntington | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 2001590 | Wabash |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 2001591 | Brown |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 2001592 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2001593 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001594 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001595 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001596 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001597 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001598 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001599 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001600 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001601 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001602 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2001603 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001604 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001605 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001606 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2001607 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001608 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2001609 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2001610 |  | Casteel Real Estate | Indiana Department of Transportation | 2022-07-13
|  |  | 2001611 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 2001612 |  | Bettina Settles Realty, LLC | Indiana Department of Transportation | 2023-11-15
|  |  | 2001613 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001614 |  | Advantage Appraisal Services | Indiana Department of Transportation | 2023-11-15
|  |  | 2001615 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2001616 | Boone |  | Indiana Department of Transportation | 2020-10-07 | CE
CN
|  |  | 2001617 |  | Independent Land Surveying, Inc. | Indiana Department of Transportation | 2023-11-15
|  |  | 2001618 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 2001619 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2023-01-19
|  |  | 2001620 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 2001621 |  | Houseal Lavigne Associates | Indiana Department of Transportation | 2023-01-19
|  |  | 2001622 | Morgan |  | Indiana Department of Transportation | 2020-11-18 | CE
CN
|  |  | 2001623 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2001624 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2001625 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2001626 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001627 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001628 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001629 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001631 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001632 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001633 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 2019-10-09
|  |  | 2001634 |  | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 2001635 | Various |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 2001636 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001637 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001638 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001639 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001640 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 2001641 |  | E.J. Breneman, LP | Lebanon | -339679.2083
|  |  | 2001642 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2001643 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 2001644 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2001645 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001646 |  | CGI | Indiana Department of Transportation | 2019-03-06
|  |  | 2001647 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2019-03-06
|  |  | 2001648 |  | ASA Land Surveying | Indiana Department of Transportation | 2019-03-06
|  |  | 2001649 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2001650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001651 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001652 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001653 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001654 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 2001655 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2001656 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2001657 |  | Carters Appraisal Service | Indiana Department of Transportation | 2024-02-14
|  |  | 2001658 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2001659 |  | Carters Appraisal Service | Indiana Department of Transportation | -339679.2083
|  |  | 2001660 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2001661 |  |  | Indiana Department of Transportation | 2020-10-07
|  |  | 2001662 |  | C Blair Enterprises, Inc. | Elkhart | 2023-04-12
|  |  | 2001663 |  | AFRAM Group, Incorporated | Avon | 2023-10-12
|  |  | 2001664 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 2001665 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2022-04-06
|  |  | 2001666 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001667 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001668 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001669 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001670 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001671 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001672 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001673 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001674 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001675 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2022-04-06
|  |  | 2001676 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001677 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001678 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001679 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2022-04-06
|  |  | 2001680 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001681 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001682 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 2001683 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001684 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001685 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001686 | Various |  | Indiana Department of Natural Resources | -339679.2083 | PL
|  |  | 2001687 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001688 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001689 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001690 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001691 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001692 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001693 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001694 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001695 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001696 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001697 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001698 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001699 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001700 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001701 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001702 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001703 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001704 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001705 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001706 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001707 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001708 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001709 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001711 | Marion |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 2001712 | Various |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 2001713 | Marion |  | Indiana Department of Natural Resources | -339679.2083 | CN
|  |  | 2001714 | Allen |  | Indiana Department of Natural Resources | 2021-05-31 | PE
|  |  | 2001715 | Tipton |  | Indiana Department of Natural Resources | -339679.2083 | PE
|  |  | 2001716 |  | Beacon Surveying and Engineering | Indiana Department of Transportation | 2022-03-09
|  |  | 2001717 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2001718 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2022-01-12 | CN
|  |  | 2001719 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2001720 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2001721 |  |  | Monroe County | 2023-07-12
|  |  | 2001722 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001723 |  |  | Elkhart County | 2023-05-10
|  |  | 2001724 |  |  | Elkhart County | 2023-05-10
|  |  | 2001725 |  | Flexible H.R. Solutions, LLC | Mishawaka | -339679.2083
|  |  | 2001726 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2001727 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2001728 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 2001729 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001730 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2001731 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2001732 |  |  | Fort Wayne Public Transportation Corporation (Citilink) | -339679.2083
|  |  | 2001733 |  |  | Indiana Department of Transportation | 2025-03-12
|  |  | 2001734 |  |  | Indiana Department of Transportation | 2025-03-12
|  |  | 2001735 |  |  | South Bend Transit | -339679.2083
|  |  | 2001736 |  |  | South Bend Transit | -339679.2083
|  |  | 2001737 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2001738 |  |  | South Bend Transit | -339679.2083
|  |  | 2001739 |  |  | South Bend Transit | -339679.2083
|  |  | 2001740 |  |  | South Bend Transit | -339679.2083
|  |  | 2001741 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2001742 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001743 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001744 |  | ASC Group, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001745 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2001746 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001747 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2001748 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 2001749 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001750 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001751 |  |  | Indiana Department of Transportation | 2019-05-31
|  |  | 2001752 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001753 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2021-05-05
|  |  | 2001754 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | -339679.2083
|  |  | 2001755 |  |  | Indiana Department of Transportation | 2024-01-18
|  |  | 2001756 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2001757 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001758 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001759 |  | Consolidated Test Company | Indiana Department of Transportation | 2023-10-12
|  |  | 2001760 |  | Jacobi, Toombs & Lanz, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2001761 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001762 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2001763 |  |  | City of Anderson Transit System | -339679.2083
|  |  | 2001764 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001765 |  |  | Indiana Department of Transportation | 2020-11-10
|  |  | 2001766 | Vanderburgh | CGI | Indiana Department of Transportation | 2021-04-07 | CE
CN
|  |  | 2001767 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001768 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001769 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001770 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2001771 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001772 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001773 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2001774 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2001775 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2001776 |  | H W Lochner, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001777 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001778 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-12-13
|  |  | 2001779 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2001780 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-12-13
|  |  | 2001781 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001782 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2001783 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2001784 |  | Franco Consulting Engineers, LLC | Monroeville | 2022-03-09
|  |  | 2001785 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001786 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001787 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2025-02-12
|  |  | 2001788 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001789 |  | Franco Consulting Engineers, LLC | Monroeville | 2022-03-09
|  |  | 2001790 |  | Franco Consulting Engineers, LLC | Monroeville | 2022-03-09
|  |  | 2001791 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001792 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001793 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001794 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2001795 |  |  | Indiana Department of Transportation | 2010-12-08
|  |  | 2001796 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001797 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2021-03-10
|  |  | 2001798 |  | Home Equity Appraisals | Indiana Department of Transportation | 2022-04-06
|  |  | 2001799 |  | Eco Logic, LLC | Indiana Department of Transportation | 2019-10-09
|  |  | 2001800 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 2001801 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 2001802 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2001803 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001804 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001805 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001806 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001807 | Marshall | Bayer & Becker, Inc. | Culver | 2024-03-22 | PE
|  |  | 2001808 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2001809 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2019-10-09
|  |  | 2001810 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2019-10-09
|  |  | 2001811 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2001812 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2001813 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2001814 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2001815 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2001816 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2001817 | Dearborn |  | Dearborn County | 2025-07-09 | PE
|  |  | 2001818 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2011-05-31
|  |  | 2001819 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2001820 | Fountain | Corradino, LLC | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 2001821 |  | Advanced Engineering Services Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001822 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2024-11-14
|  |  | 2001823 |  | H&H Associates, LLC | Indiana Department of Transportation | 2024-10-09
|  |  | 2001824 |  | Chastain & Associates LLC | Indiana Department of Transportation | 2024-10-09
|  |  | 2001825 |  | H W Lochner, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2001826 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001827 |  | Beam, Longest and Neff, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001828 |  | Afram Corporation | Indiana Department of Transportation | 2024-07-10
|  |  | 2001829 |  | Afram Corporation | Indiana Department of Transportation | 2024-07-10
|  |  | 2001830 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2001831 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001832 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001833 |  | DLZ Indiana, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001834 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001835 |  | Apex Engineering, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001836 |  | Indiana Infrastructure Partners, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001837 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001838 |  | Hitchcock Design Group | Indiana Department of Transportation | 2024-07-10
|  |  | 2001839 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2001840 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001841 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001842 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001843 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001844 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001845 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001846 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2001847 |  | M-E Companies, Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 2001848 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001849 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001850 |  | Holloway Engineering, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2001851 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001852 |  | Foresight Land Surveying, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001853 |  | InspectTech Systems, Inc. | Indiana Department of Transportation | 2024-11-14
|  |  | 2001854 |  | LONCO, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2001855 |  | American Resources Group, Ltd. | Indiana Department of Transportation | 2024-09-11
|  |  | 2001856 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001857 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2024-10-09
|  |  | 2001858 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2001859 |  | Majestic Real Estate, Inc. US Land Acquisitions | Indiana Department of Transportation | 2024-09-11
|  |  | 2001860 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001861 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001862 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001863 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001864 |  | Civil Designs, LLP | Indiana Department of Transportation | 2024-09-11
|  |  | 2001865 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001866 |  | Collins Engineers Incorporated | Indiana Department of Transportation | 2024-09-11
|  |  | 2001867 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2024-09-11
|  |  | 2001868 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001869 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2024-07-10
|  |  | 2001870 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001871 |  | DCD Consulting LLC | Indiana Department of Transportation | 2024-09-11
|  |  | 2001872 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001873 |  | Another Test Company | Indiana Department of Transportation | 2024-07-10
|  |  | 2001874 |  | DCD Consulting LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001875 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001876 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | 2024-10-09
|  |  | 2001877 |  | Glaus, Pyle, Schomer, Burns & Dehaven, P.C. | Indiana Department of Transportation | 2024-10-09
|  |  | 2001878 |  | CE Solutions, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001879 |  | DCD Consulting LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001880 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2001881 |  | Digital Appraisals, LLC | Indiana Department of Transportation | 2025-01-15
|  |  | 2001882 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001883 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001884 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2001885 |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001886 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 2001887 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001888 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001889 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001891 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001892 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001893 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001894 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001895 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2001896 |  | Alfred Benesch & Company | Indiana Department of Transportation | -339679.2083
|  |  | 2001897 |  | Fidelity National Title Insurance Company, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2001898 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001899 |  | B. L. A., Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 2001900 |  | Garcia LE & Associates, L.L.C. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001901 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2001902 |  | ARCADIS | Indiana Department of Transportation | 2024-10-09
|  |  | 2001903 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001904 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2001905 |  | ARCADIS | Indiana Department of Transportation | 2024-08-14
|  |  | 2001906 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2024-08-14
|  |  | 2001907 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001908 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2001909 |  | B. L. A., Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 2001910 |  | Heritage Land Services | Indiana Department of Transportation | 2025-07-09
|  |  | 2001911 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2001912 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001913 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2001914 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001915 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001916 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2001917 |  | CGI | Indiana Department of Transportation | 2023-11-15
|  |  | 2001918 |  | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001919 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001920 |  | Harvard Title Searching | Indiana Department of Transportation | 2024-07-10
|  |  | 2001921 |  | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001922 |  | Harvard Title Searching | Indiana Department of Transportation | 2024-07-10
|  |  | 2001923 |  | Hydrogeology, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2001924 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2001925 |  | Dyer Environmental Services | Indiana Department of Transportation | 2024-07-10
|  |  | 2001926 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001927 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001928 |  | Dodd Title Corporation | Indiana Department of Transportation | 2024-07-10
|  |  | 2001929 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001930 |  | Dodd Title Corporation | Indiana Department of Transportation | 2024-09-11
|  |  | 2001931 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001932 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001933 |  | Eilts Consulting Services | Indiana Department of Transportation | -339679.2083
|  |  | 2001934 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001935 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001936 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001937 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2001938 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001939 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001940 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001941 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2001942 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001943 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001944 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001945 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001946 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001947 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001948 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001949 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001950 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001951 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001952 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001953 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001954 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001955 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001956 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001957 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001958 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001959 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001960 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001961 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001962 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 2024-09-11
|  |  | 2001963 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001964 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001965 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001966 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2024-12-11
|  |  | 2001967 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001968 | Various |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 2001969 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001970 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2001971 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001972 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001973 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001974 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001975 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001976 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 2024-12-11
|  |  | 2001977 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001978 |  | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | 2024-07-10
|  |  | 2001979 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001980 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001981 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001982 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2001983 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2001984 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001985 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001986 |  | Collier Transport Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001987 |  | Collier Transport Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2001988 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001989 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001990 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001991 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001992 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001993 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001994 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001995 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2001996 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001997 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2001998 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2001999 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002000 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002004 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2002005 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2024-12-11
|  |  | 2002007 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002008 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002009 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002010 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002011 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2002014 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2002015 |  |  | Indiana Department of Transportation | 2025-03-12
|  |  | 2002016 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002017 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002018 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002019 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002020 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002021 |  | Bidinfo | Indiana Department of Transportation | 2024-12-11
|  |  | 2002022 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002023 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002024 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002026 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002027 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002028 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002029 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002030 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002031 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002032 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002033 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2002034 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002035 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2024-08-14
|  |  | 2002036 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002037 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002038 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002039 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002040 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002041 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002042 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002043 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002044 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002045 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002046 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002047 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002048 |  | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2024-12-11
|  |  | 2002049 |  | Gregg A. Townsend | Indiana Department of Transportation | 2024-12-11
|  |  | 2002050 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002051 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002052 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002053 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002054 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002055 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002056 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002057 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002058 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002059 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002060 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002061 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002062 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002063 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002064 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002065 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002066 |  |  | Indiana Department of Transportation | 2025-03-12
|  |  | 2002067 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002068 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002069 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002070 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002071 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002072 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002073 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002074 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002075 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002076 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2002077 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002078 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002079 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2002080 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2002081 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002082 |  | H&H Associates, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2002083 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002084 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002085 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002086 |  | Blood Hound, Inc. (former) | Indiana Department of Transportation | 2024-09-11
|  |  | 2002087 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002088 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002089 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002090 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002091 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002092 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002093 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002094 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002095 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002096 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002097 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002098 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002099 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002100 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002101 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002102 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002103 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002104 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002105 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002106 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2002107 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002108 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002109 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002110 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2002111 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2002112 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002113 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002114 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2002115 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2002116 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2002117 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2002118 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002119 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002120 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002121 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002122 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2024-07-10
|  |  | 2002123 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2024-07-10
|  |  | 2002124 |  | DKA Associates, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002125 |  | DKA Associates, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002126 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002127 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002128 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002129 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002130 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002131 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002132 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002133 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002134 |  | CGI | Indiana Department of Transportation | 2024-07-10
|  |  | 2002135 |  | CGI | Indiana Department of Transportation | 2024-07-10
|  |  | 2002136 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002137 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2024-11-14
|  |  | 2002138 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2024-11-14
|  |  | 2002139 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002140 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002141 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002142 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002143 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002144 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002145 |  | Collier Transport Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002146 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2024-07-10
|  |  | 2002147 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2024-07-10
|  |  | 2002148 |  | Dummy Consulting Firm | Indiana Department of Transportation | 2024-07-10
|  |  | 2002149 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002150 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002151 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002152 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002153 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002154 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002155 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002156 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002157 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002158 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002159 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002160 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002161 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002162 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002163 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002164 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002165 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002166 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002167 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002168 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002169 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002170 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002171 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002172 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002173 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002174 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002175 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002176 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002177 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002178 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002179 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002180 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002181 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002182 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002183 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002184 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002185 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002186 |  | DLZ Indiana, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2002187 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002188 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002189 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002190 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002191 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002192 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002193 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002194 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002195 |  | Indiana University | Indiana Department of Transportation | 2024-07-10
|  |  | 2002196 |  | Driesenga & Associates, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002197 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002198 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002199 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002200 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002201 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002202 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002203 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002204 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002205 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002206 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002207 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002208 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002209 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002210 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2002211 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002212 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2002213 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002214 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002215 |  | D & D Consulting Services, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2002216 |  | D & D Consulting Services, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2002217 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002218 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002219 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002220 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002221 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2002222 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002223 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2002224 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002225 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002226 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002227 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002228 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002229 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2002230 |  |  | Indiana Department of Transportation | 2025-01-15
|  |  | 2002231 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002232 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002233 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002234 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002235 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002237 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002238 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002239 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002240 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002241 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002242 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002243 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 2024-09-11
|  |  | 2002244 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002245 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002246 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002247 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002248 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002249 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002250 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002251 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002252 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002253 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002254 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002255 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002256 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002257 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002258 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002259 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002260 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 2002261 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002262 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002263 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002264 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002265 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002266 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002267 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002268 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002269 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002270 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002271 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002272 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002273 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002274 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002275 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002276 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002277 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002278 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002279 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002280 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002281 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002282 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002283 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002284 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002285 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002286 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002287 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002288 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002289 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002290 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002291 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002292 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002293 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002294 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002295 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002296 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002297 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002298 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2024-11-14
|  |  | 2002299 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002300 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002301 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002302 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002303 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002304 |  | Knight E/A, Inc. | Indiana Department of Transportation | 2024-10-09
|  |  | 2002305 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002306 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002307 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002308 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002309 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002310 |  |  | NIRPC Various subgrantees through Lake and Porter Counties | -339679.2083
|  |  | 2002311 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 2002312 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2024-08-14
|  |  | 2002313 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002314 |  | Eco Logic, LLC | Indiana Department of Transportation | 2024-09-11
|  |  | 2002315 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 2002316 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 2024-07-10
|  |  | 2002317 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2024-10-09
|  |  | 2002318 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002319 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002320 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2002321 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002322 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2002323 |  | Archonsortium, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 2002324 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2002325 | Marion |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 2002326 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2002327 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2002328 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002329 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002330 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002331 |  |  | Indiana Department of Transportation | 2023-08-09
|  |  | 2002332 |  | Another Test Company | Indiana Department of Transportation | 2023-08-09
|  |  | 2002333 |  | DCD Consulting LLC | Indiana Department of Transportation | 2023-08-09
|  |  | 2002334 |  | Martinez Corporation | Indiana Department of Transportation | 2023-08-09
|  |  | 2002335 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2024-08-14
|  |  | 2002336 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2002337 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002338 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2002339 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002340 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002341 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002342 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002343 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2002344 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002345 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002346 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002347 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002348 | Dubois |  | Indiana Department of Transportation | 2021-03-10 | CE
CN
|  |  | 2002349 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002350 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002351 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002352 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002353 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002354 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002355 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002356 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002357 |  |  | Indiana Department of Transportation | 2024-08-14
|  |  | 2002358 |  |  | Indiana Department of Transportation | 2024-10-09
|  |  | 2002359 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002360 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002361 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002362 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2024-07-10
|  |  | 2002363 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002364 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2002365 |  | DCD Consulting LLC | Indiana Department of Transportation | 2024-10-09
|  |  | 2002366 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002367 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002368 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002369 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002370 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002371 |  |  | Indiana Department of Transportation | 2025-02-05
|  |  | 2002372 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002373 |  | CGI | Indiana Department of Transportation | 2020-07-08
|  |  | 2002374 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2002375 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2002376 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2002377 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 2022-04-06
|  |  | 2002378 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002379 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002380 |  |  | Indiana Department of Transportation | 2020-12-09
|  |  | 2002381 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2020-05-07
|  |  | 2002382 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 2020-05-07
|  |  | 2002383 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002384 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002385 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002386 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002387 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2002388 |  | III FFC | Indiana Department of Transportation | 2020-07-08
|  |  | 2002389 | Adams |  | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 2002390 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2002391 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2002392 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002393 | Various |  | Indiana Department of Transportation | 2022-04-06 | PE
|  |  | 2002394 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2002395 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002396 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2002397 |  | J. H. Rudolph & Co., Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002398 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2002399 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2002400 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2002401 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 2002402 |  | Another Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 2002403 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002404 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2021-02-10
|  |  | 2002405 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2002406 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002407 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2002408 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2002409 |  |  | Indiana Department of Transportation | 2024-04-10
|  |  | 2002410 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2002411 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002412 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2002413 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002414 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002415 | Various |  | Indiana Department of Transportation | 2022-09-14 | RR
|  |  | 2002416 | Huntington |  | Indiana Department of Transportation | 2021-07-14 | CE
CN
|  |  | 2002417 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | 2021-12-08 | RR
|  |  | 2002418 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002419 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 2002420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002421 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002422 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002423 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002424 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002425 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002426 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002427 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002428 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002429 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002430 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002431 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002432 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002433 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002434 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002435 |  |  | Hendricks County | -339679.2083
|  |  | 2002436 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002437 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002438 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002439 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002440 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2002441 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002442 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002443 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002444 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002445 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002446 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002447 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002448 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002449 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002450 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002451 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002452 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002453 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002454 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002455 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002456 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002457 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002458 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002459 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002460 |  |  | Hancock County | -339679.2083
|  |  | 2002461 |  |  | Johnson County | -339679.2083
|  |  | 2002462 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002463 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002464 |  |  | Marion County | -339679.2083
|  |  | 2002465 |  |  | Morgan County | -339679.2083
|  |  | 2002466 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002467 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002468 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002469 |  |  | Indiana Department of Natural Resources | 2021-02-10
|  |  | 2002470 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002471 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002472 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002473 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002474 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002475 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2021-02-10
|  |  | 2002476 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002477 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002478 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002479 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002480 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 2002481 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002482 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002483 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002484 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002485 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002486 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002487 |  | CGI | Indiana Department of Transportation | 2021-02-10
|  |  | 2002488 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002489 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 2002490 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002491 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002492 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002493 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2002494 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002495 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002496 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002497 |  |  | Indianapolis Public Transportation Corporation (IndyGo) | -339679.2083
|  |  | 2002498 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 2002499 |  |  | Indiana Department of Transportation | 2019-09-11
|  |  | 2002500 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2019-02-06
|  |  | 2002501 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 2002502 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002503 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002504 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2002505 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002506 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002507 | Various |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 2002508 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2002509 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002510 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2002511 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2002512 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002513 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002514 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002515 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002516 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2002517 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2002518 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2002519 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2002520 |  |  | New Harmony | -339679.2083
|  |  | 2002521 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002522 |  |  | Indiana Department of Transportation | 2021-04-07
|  |  | 2002523 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002524 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002525 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2002526 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2011-05-31
|  |  | 2002527 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002528 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002529 | Various |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2002530 |  | Another Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 2002531 | Various |  | Indiana Department of Transportation | 2021-10-14 | CN
|  |  | 2002532 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2002533 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 2021-03-10
|  |  | 2002534 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2002535 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002536 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002537 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2002538 |  |  | Vanderburgh County | 2025-07-09
|  |  | 2002539 |  |  | Warrick County | 2026-07-08
|  |  | 2002540 |  |  | Indiana Department of Transportation | 2021-07-14
|  |  | 2002541 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002542 |  |  | Indiana Department of Transportation | 2024-12-11
|  |  | 2002543 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2002544 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002545 |  | Douglass Environmental Services, Inc. | La Porte | 2023-04-12
|  |  | 2002546 |  |  | Indiana Department of Transportation | 2021-09-15
|  |  | 2002547 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2002548 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2002549 |  |  | MPO - Lafayette | -339679.2083
|  |  | 2002550 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2002551 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2002552 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002553 |  | DCD Consulting LLC | Indianapolis | 2023-12-13
|  |  | 2002554 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2002555 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2002556 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2002557 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2002558 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2025-02-12
|  |  | 2002559 |  | Kaskaskia Engineering Group | Indiana Department of Transportation | 2025-02-12
|  |  | 2002560 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2002561 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002562 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2002563 | Tipton | Dodd Title Corporation | Kokomo | 2022-10-13 | PE
|  |  | 2002564 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002565 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002566 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002567 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002568 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002569 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002570 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002571 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002572 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2002573 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002574 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002575 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2002576 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2002577 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2002578 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002579 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002581 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002582 |  | Cornerstone Design | Highland | 2023-03-15
|  |  | 2002583 |  | GRL Engineers, Inc. | Mount Vernon | 2024-12-11
|  |  | 2002584 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2002585 | Starke |  | Indiana Department of Transportation | 2021-05-05 | CE
CN
|  |  | 2002586 |  | Consolidated Test Company | Hammond | 2023-03-15
|  |  | 2002587 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002588 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002589 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2002590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002591 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002592 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2002593 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002594 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2002595 |  | Horn and Associates, Inc. | Indiana Department of Transportation | 2022-04-06
|  |  | 2002596 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2002597 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2002598 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2002599 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2002600 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2002601 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2002602 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
[6 empty] | Indiana Department of Transportation | 2021-10-14
|  |  | 2002603 |  | Jeffrey S. Juday | Indiana Department of Transportation | 2020-08-05
|  |  | 2002604 | Gibson |  | Indiana Department of Transportation | 2021-02-10 | CE
CN
|  |  | 2002605 | Pike | Home Equity Appraisals | Indiana Department of Transportation | 2021-01-13 | CE
CN
|  |  | 2002606 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2002607 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002608 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002609 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002610 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 2002611 |  |  | Indiana Department of Transportation | 2021-09-15
|  |  | 2002612 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 2002613 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2002614 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2002615 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2002616 |  |  | Albion | 2021-05-31
|  |  | 2002617 |  |  | Albion | 2021-05-31
|  |  | 2002618 |  |  | Alexandria | 2021-05-31
|  |  | 2002619 |  |  | Allen County | 2021-05-31
|  |  | 2002620 |  | A & A Consultants, Inc. | Amo | -339679.2083
|  |  | 2002621 |  | ABNA of Illinois | Andrews | 2021-05-31
|  |  | 2002622 |  | ACMS Group, Inc. | Argos | 2021-05-31
|  |  | 2002623 |  | Quantum Spatial, Inc. | Auburn | 2021-05-31
|  |  | 2002624 |  | Quantum Spatial, Inc. | Auburn | 2021-05-31
|  |  | 2002625 |  | Quantum Spatial, Inc. | Auburn | 2021-05-31
|  |  | 2002626 |  | Quantum Spatial, Inc. | Auburn | 2021-05-31
|  |  | 2002627 |  | AES Services, Inc. | Avilla | 2021-05-31
|  |  | 2002628 |  | AI Engineers, Inc. | Bainbridge | -339679.2083
|  |  | 2002629 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2021-05-31
|  |  | 2002630 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2021-05-31
|  |  | 2002631 |  |  | Bartholomew County | 2021-05-31
|  |  | 2002632 |  | ARCADIS | Batesville | 2021-05-31
|  |  | 2002633 |  | ASA Land Surveying | Bedford | 2021-05-31
|  |  | 2002634 |  |  | Benton County | 2021-05-31
|  |  | 2002635 |  |  | Benton County | 2021-05-31
|  |  | 2002636 |  |  | Benton County | 2021-05-31
|  |  | 2002637 |  |  | Benton County | 2021-05-31
|  |  | 2002638 |  |  | Benton County | 2021-05-31
|  |  | 2002639 |  |  | Benton County | 2021-05-31
|  |  | 2002640 |  |  | Benton County | 2021-05-31
|  |  | 2002641 |  |  | Berne | 2021-05-31
|  |  | 2002642 |  | ATSI Engineering Services | Beverly Shores | 2021-05-31
|  |  | 2002643 |  | Abonmarche Consultants of Indiana L.L.C. | Bloomfield | 2021-05-31
|  |  | 2002644 |  | Absolute Title Services, LLC | Bloomington | 2021-05-31
|  |  | 2002645 |  | Accidental Discoveries, LLC | Bluffton | 2021-05-31
|  |  | 2002646 |  |  | Boone County | 2021-05-31
|  |  | 2002647 |  | Active Environmental Services, Inc. | Bourbon | 2021-05-31
|  |  | 2002648 |  | Active Environmental Services, Inc. | Bourbon | 2021-05-31
|  |  | 2002649 |  | Active Environmental Services, Inc. | Bourbon | 2021-05-31
|  |  | 2002650 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2021-05-31
|  |  | 2002651 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2021-05-31
|  |  | 2002652 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2021-05-31
|  |  | 2002653 |  | Afram Corporation | Brookston | 2021-05-31
|  |  | 2002654 |  | Alfred Benesch & Company | Brookville | 2021-05-31
|  |  | 2002655 |  | Alliance Survey Company | Bryant | 2021-05-31
|  |  | 2002656 |  | American Engineers, Inc. | Butler | 2021-05-31
|  |  | 2002657 |  | American Resources Group, Ltd. | Cambridge City | 2021-05-31
|  |  | 2002658 |  | Andrews Engineering, Inc. | Cannelton | 2021-05-31
|  |  | 2002659 |  | Andy Easley Engineering, Inc. | Carbon | -339679.2083
|  |  | 2002660 |  | Another Test Company | Carmel | 2021-05-31
|  |  | 2002661 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2021-05-31
|  |  | 2002662 |  | Appraisal Office of Central Indiana | Centerville | 2021-05-31
|  |  | 2002663 |  | Appraisal Service | Chalmers | 2021-05-31
|  |  | 2002664 |  |  | Charlestown | 2021-05-31
|  |  | 2002665 |  |  | Charlestown | 2021-05-31
|  |  | 2002666 |  |  | Chesterton | 2021-05-31
|  |  | 2002667 |  |  | Churubusco | 2021-05-31
|  |  | 2002668 |  |  | Clark County | 2021-05-31
|  |  | 2002669 |  |  | Clark County | 2021-05-31
|  |  | 2002670 |  | Ark Engineering Services, Inc. | Coatesville | -339679.2083
|  |  | 2002671 |  | Arrow Consulting Services, Inc. | Colfax | 2021-05-31
|  |  | 2002672 |  | Associated Right-of-Way Services, Inc. | Columbus | 2021-05-31
|  |  | 2002673 |  | Associated Right-of-Way Services, Inc. | Columbus | 2021-05-31
|  |  | 2002674 |  | B. L. A., Inc. | Corydon | 2021-05-31
|  |  | 2002675 |  | BCA Consultants, Inc. | Crandall | 2021-05-31
|  |  | 2002676 |  | Banning Engineering, P.C. | Crawfordsville | 2021-05-31
|  |  | 2002677 |  | Banning Engineering, P.C. | Crawfordsville | 2021-05-31
|  |  | 2002678 |  | Baxter & Woodman, Inc. | Crown Point | 2021-05-31
|  |  | 2002679 |  | Bayer & Becker, Inc. | Culver | 2021-05-31
|  |  | 2002680 |  | Bayer & Becker, Inc. | Culver | 2021-05-31
|  |  | 2002681 |  | Beacon Surveying and Engineering | Cynthiana | 2021-05-31
|  |  | 2002682 |  |  | Daleville | 2021-05-31
|  |  | 2002683 |  |  | Daleville | 2021-05-31
|  |  | 2002684 |  |  | Dearborn County | 2021-05-31
|  |  | 2002685 |  |  | Dekalb County | 2021-05-31
|  |  | 2002686 |  |  | Delaware County | 2021-05-31
|  |  | 2002687 |  |  | Delaware County | 2021-05-31
|  |  | 2002688 |  | Blood Hound, Inc. (former) | Delphi | 2021-05-31
|  |  | 2002689 |  | Blood Hound, Inc. (former) | Delphi | 2021-05-31
|  |  | 2002690 |  | Blood Hound, Inc. (former) | Delphi | 2021-05-31
|  |  | 2002691 |  |  | Dillsboro | 2021-05-31
|  |  | 2002692 |  | Booker Real Estate Services | Dune Acres | 2021-05-31
|  |  | 2002693 |  | Booker Real Estate Services | Dune Acres | 2021-05-31
|  |  | 2002694 |  | Boomerang Ventures, LLC | Dunkirk | 2021-05-31
|  |  | 2002695 |  | Brenner Design Incorporated | Dyer | 2021-05-31
|  |  | 2002696 |  | Browning Day Mullins Dierdorf Architects | East Chicago | 2021-05-31
|  |  | 2002697 |  | Burrell Appraisal Service, Inc. | Edinburgh | 2021-05-31
|  |  | 2002698 |  | C Blair Enterprises, Inc. | Elkhart | 2021-05-31
|  |  | 2002699 |  |  | Elkhart County | 2021-05-31
|  |  | 2002700 |  |  | Elkhart County | 2021-05-31
|  |  | 2002701 |  | CGI | Evansville | 2021-05-31
|  |  | 2002702 |  | CHA, Inc. | Farmersburg | 2021-05-31
|  |  | 2002703 |  | CHA, Inc. | Farmersburg | 2021-05-31
|  |  | 2002704 |  |  | Fillmore | -339679.2083
|  |  | 2002705 |  |  | Fountain County | 2021-05-31
|  |  | 2002706 |  |  | Fountain County | 2021-05-31
|  |  | 2002707 |  | Casteel Real Estate | Franklin | 2021-05-31
|  |  | 2002708 |  | Certified Engineering, Inc. | Fremont | 2021-05-31
|  |  | 2002709 |  | Certified Engineering, Inc. | Fremont | 2021-05-31
|  |  | 2002710 |  |  | Fulton County | 2021-05-31
|  |  | 2002711 |  | Chicago Testing Laboratory, Inc. | Gary | 2021-05-31
|  |  | 2002712 |  | Christopher B. Burke Engineering, Ltd. | Gaston | 2021-05-31
|  |  | 2002713 |  | Civil Engineering Consultants | Goodland | 2021-05-31
|  |  | 2002714 |  | Civil Engineering Consultants | Goodland | 2021-05-31
|  |  | 2002715 |  | Civil Inspection Services, LLC | Goshen | 2021-05-31
|  |  | 2002716 |  |  | Grant County | 2021-05-31
|  |  | 2002717 |  |  | Grant County | 2021-05-31
|  |  | 2002718 |  | Clayton L. Roots | Greencastle | -339679.2083
|  |  | 2002719 |  | Clyde L. Hawkins | Greendale | 2021-05-31
|  |  | 2002720 |  |  | Greene County | 2021-05-31
|  |  | 2002721 |  |  | Greene County | 2021-05-31
|  |  | 2002722 |  |  | Greene County | 2021-05-31
|  |  | 2002723 |  | Collier Transport Inc. | Greensburg | 2021-05-31
|  |  | 2002724 |  | Commonwealth Engineers, Inc. | Greenwood | 2021-05-31
|  |  | 2002725 |  | Compliance Consulting Service, Inc. | Griffith | 2021-05-31
|  |  | 2002726 |  |  | Hagerstown | 2021-05-31
|  |  | 2002727 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2021-05-31
|  |  | 2002728 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2021-05-31
|  |  | 2002729 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Hamilton | 2021-05-31
|  |  | 2002730 |  |  | Hamilton County | 2021-05-31
|  |  | 2002731 |  | Consolidated Test Company | Hammond | 2021-05-31
|  |  | 2002732 |  | Construction Consultants & Inspection Services, LLC | Hanover | 2021-05-31
|  |  | 2002733 |  | Context, LLC | Harmony | -339679.2083
|  |  | 2002734 |  |  | Harrison County | 2021-05-31
|  |  | 2002735 |  | Corn Island Archaeology, LLC | Hebron | 2021-05-31
|  |  | 2002736 |  | Corn Island Archaeology, LLC | Hebron | 2021-05-31
|  |  | 2002737 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2021-05-31
|  |  | 2002738 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2021-05-31
|  |  | 2002739 |  | CrossRoad Engineers, PC | Hudson | 2021-05-31
|  |  | 2002740 |  | CrossRoad Engineers, PC | Hudson | 2021-05-31
|  |  | 2002741 |  | D & D Consulting Services, Inc. | Huntertown | 2021-05-31
|  |  | 2002742 |  |  | Huntingburg | 2021-05-31
|  |  | 2002743 |  |  | Huntingburg | 2021-05-31
|  |  | 2002744 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2021-05-31
|  |  | 2002745 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2021-05-31
|  |  | 2002746 |  |  | Huntington County | 2021-05-31
|  |  | 2002747 |  | Danch Harner and Associates, Inc. | Jasper | 2021-05-31
|  |  | 2002748 |  |  | Jefferson County | 2021-05-31
|  |  | 2002749 |  | Data Transfer Solutions, LLC | Jeffersonville | 2021-05-31
|  |  | 2002750 |  |  | Johnson County | 2022-05-31
|  |  | 2002751 |  | Dave Helton & Associates, Inc. | Jonesboro | 2021-05-31
|  |  | 2002752 |  | David Matthews Associates (Former) | Kempton | 2021-05-31
|  |  | 2002753 |  | Debbie L. Morris | Kendallville | 2021-05-31
|  |  | 2002754 |  |  | Kentland | 2021-05-31
|  |  | 2002755 |  | Dennison and Company | Kingsford Heights | 2021-05-31
|  |  | 2002756 |  | Digital Appraisals, LLC | Kirklin | 2021-05-31
|  |  | 2002757 |  | Dillabaugh, Inc. | Knightstown | 2021-05-31
|  |  | 2002758 |  | Dillterra LLC | Knightsville | -339679.2083
|  |  | 2002759 |  |  | Knox | 2021-05-31
|  |  | 2002760 |  |  | Knox | 2021-05-31
|  |  | 2002761 |  |  | Knox County | 2021-05-31
|  |  | 2002762 |  | Dodd Title Corporation | Kokomo | 2021-05-31
|  |  | 2002763 |  |  | Kosciusko County | 2021-05-31
|  |  | 2002764 |  | Domain Architecture, Inc. | Kouts | 2021-05-31
|  |  | 2002765 |  | Driesenga & Associates, Inc. | Ladoga | -339679.2083
|  |  | 2002766 |  | Duesler Realty House | Lagrange | 2021-05-31
|  |  | 2002767 |  |  | LaGrange County | 2021-05-31
|  |  | 2002768 |  |  | LaGrange County | 2021-05-31
|  |  | 2002769 |  |  | LaGrange County | 2021-05-31
|  |  | 2002770 |  |  | Lake County | 2021-05-31
|  |  | 2002771 |  | Dummy Consulting Firm Too | Lakeville | 2021-05-31
|  |  | 2002772 |  | Duneland Group, Inc. | Lapel | 2021-05-31
|  |  | 2002773 |  | Duneland Group, Inc. | Lapel | 2021-05-31
|  |  | 2002774 |  |  | LaPorte County | 2021-05-31
|  |  | 2002775 |  |  | Lawrence County | 2021-05-31
|  |  | 2002776 |  |  | Lawrence County | 2021-05-31
|  |  | 2002777 |  | Dynasty Group, Inc. | Lawrenceburg | 2021-05-31
|  |  | 2002778 |  | E. L. Robinson Engineering of Ohio Co. | Leavenworth | 2021-05-31
|  |  | 2002779 |  | E.J. Breneman, LP | Lebanon | 2021-05-31
|  |  | 2002780 |  | E.J. Breneman, LP | Lebanon | 2021-05-31
|  |  | 2002781 |  | ERES International, Inc. | Ligonier | 2021-05-31
|  |  | 2002782 |  | Eagle Ridge Civil Engineering Services, LLC | Linton | 2021-05-31
|  |  | 2002783 |  | Eco Logic, LLC | Logansport | 2021-05-31
|  |  | 2002784 |  | Eel River Abstract | Lynn | 2021-05-31
|  |  | 2002785 |  | Engineering Resources, Inc. | Madison | 2021-05-31
|  |  | 2002786 |  |  | Madison County | 2021-05-31
|  |  | 2002787 |  |  | Madison County | 2021-05-31
|  |  | 2002788 |  | Enginuity Management & Consulting Corporation | Markle | 2021-05-31
|  |  | 2002789 |  | Enginuity Management & Consulting Corporation | Markle | 2021-05-31
|  |  | 2002790 |  | Enginuity Management & Consulting Corporation | Markle | 2021-05-31
|  |  | 2002791 |  |  | Marshall County | 2021-05-31
|  |  | 2002792 |  | EnviroScience, Inc. | Martinsville | 2021-05-31
|  |  | 2002793 |  | Environmental Management Associatese | Mauckport | 2021-05-31
|  |  | 2002794 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2021-05-31
|  |  | 2002795 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2021-05-31
|  |  | 2002796 |  | Environmental Monitoring and Technologies, Inc. | Mccordsville | 2021-05-31
|  |  | 2002797 |  | FAA National, Inc. | Medora | 2021-05-31
|  |  | 2002798 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2021-05-31
|  |  | 2002799 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2021-05-31
|  |  | 2002800 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2021-05-31
|  |  | 2002801 |  | Facility Management and Engineering, Inc. | Meridian Hills | 2021-05-31
|  |  | 2002802 |  | Fanning Howey Associates | Merom | 2021-05-31
|  |  | 2002803 |  |  | Merrillville | 2021-05-31
|  |  | 2002804 |  | Farah and Sons, Inc. | Michigan City | 2021-05-31
|  |  | 2002805 |  |  | Michigantown | 2021-05-31
|  |  | 2002806 |  | Farren Real Estate Services | Middlebury | 2021-05-31
|  |  | 2002807 |  | Feutz Contractors, Inc. | Middletown | 2021-05-31
|  |  | 2002808 |  | Fink Roberts & Petrie | Milford (Kosciusko Co) | 2021-05-31
|  |  | 2002809 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2021-05-31
|  |  | 2002810 |  | ICA Engineering, Inc. | Mitchell | 2021-05-31
|  |  | 2002811 |  | Foresight Land Surveying, Inc. | Monroe | 2021-05-31
|  |  | 2002812 |  | Fosse & Associates Architects, Inc. | Monroe City | 2021-05-31
|  |  | 2002813 |  |  | Monroe County | 2021-05-31
|  |  | 2002814 |  |  | Montgomery County | 2021-05-31
|  |  | 2002815 |  | Fugro Roadware, Inc. | Monticello | 2021-05-31
|  |  | 2002816 |  | Fusion by Design, Inc. | Montpelier | 2021-05-31
|  |  | 2002817 |  | GAI Consultants, Inc. | Mooresville | 2021-05-31
|  |  | 2002818 |  | GAI Consultants, Inc. | Mooresville | 2021-05-31
|  |  | 2002819 |  |  | Morgan County | 2021-05-31
|  |  | 2002820 |  | Spire Real Estate Valuation & Advisory, Inc. | Morocco | 2021-05-31
|  |  | 2002821 |  | GS-IN P.C. | Muncie | 2021-05-31
|  |  | 2002822 |  | GS-IN P.C. | Muncie | 2021-05-31
|  |  | 2002823 |  |  | Munster | 2021-05-31
|  |  | 2002824 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | 2022-05-31
|  |  | 2002825 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | 2022-05-31
|  |  | 2002826 |  | Global Land Surveying, LLC | New Harmony | 2021-05-31
|  |  | 2002827 |  | Global Management Group, Inc. | New Haven | 2021-05-31
|  |  | 2002828 |  | Great Lakes Engineering, Inc. | New Palestine | 2021-05-31
|  |  | 2002829 |  | Bruce S. Grimes | Newberry | 2021-05-31
|  |  | 2002830 |  |  | Newton County | 2021-05-31
|  |  | 2002831 |  |  | Newton County | 2021-05-31
|  |  | 2002832 |  |  | Noble County | 2021-05-31
|  |  | 2002833 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2021-05-31
|  |  | 2002834 |  | HDR Engineering, Inc. | North Liberty | 2021-05-31
|  |  | 2002835 |  | HDR Engineering, Inc. | North Liberty | 2021-05-31
|  |  | 2002836 |  | HDR Engineering, Inc. | North Liberty | 2021-05-31
|  |  | 2002837 |  | HRV Conformance Verification Associates, Inc. | Ogden Dunes | 2021-05-31
|  |  | 2002838 |  | Hambleton LLC | Orland | 2021-05-31
|  |  | 2002839 |  | Hambleton LLC | Orland | 2021-05-31
|  |  | 2002840 |  | Hannum, Wagle & Cline Engineering | Orleans | 2021-05-31
|  |  | 2002841 |  | Hardcore Concrete Sawing Inc. | Osgood | 2021-05-31
|  |  | 2002842 |  | Hardlines Design Company | Ossian | 2021-05-31
|  |  | 2002843 |  |  | Owen County | -339679.2083
|  |  | 2002844 |  | Harvard Title Searching | Owensville | 2021-05-31
|  |  | 2002845 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Palmyra | 2021-05-31
|  |  | 2002846 |  |  | Parke County | -339679.2083
|  |  | 2002847 |  | Heritage Appraisal Service | Parker City | 2021-05-31
|  |  | 2002848 |  | Heritage Engineering, LLC | Patoka | 2021-05-31
|  |  | 2002849 |  | Hey and Associates, Inc. | Pendleton | 2021-05-31
|  |  | 2002850 |  | Home Equity Appraisals | Petersburg | 2021-05-31
|  |  | 2002851 |  |  | Pike County | 2021-05-31
|  |  | 2002852 |  |  | Pike County | 2021-05-31
|  |  | 2002853 |  |  | Pike County | 2021-05-31
|  |  | 2002854 |  | Huff & Huff, Inc. | Portage | 2021-05-31
|  |  | 2002855 |  |  | Porter County | 2021-05-31
|  |  | 2002856 |  | Hydrogeology, Inc. | Portland | 2021-05-31
|  |  | 2002857 |  | I. T. Business Corporation | Poseyville | 2021-05-31
|  |  | 2002858 |  | IHS Global Insight | Princes Lakes | 2021-05-31
|  |  | 2002859 |  |  | Pulaski County | 2021-05-31
|  |  | 2002860 |  |  | Randolph County | 2021-05-31
|  |  | 2002861 |  |  | Randolph County | 2021-05-31
|  |  | 2002862 |  |  | Randolph County | 2021-05-31
|  |  | 2002863 |  | Independent Land Surveying, Inc. | Rensselaer | 2021-05-31
|  |  | 2002864 |  | Indiana 15 Regional Planning Commission | Reynolds | 2021-05-31
|  |  | 2002865 |  | Indiana Appraisal Group, Inc. | Richmond | 2021-05-31
|  |  | 2002866 |  | Indiana Search Technologies | Rising Sun | 2021-05-31
|  |  | 2002867 |  | Indiana University | Roachdale | -339679.2083
|  |  | 2002868 |  | Infrastructure Engineers, Inc. | Rockville | -339679.2083
|  |  | 2002869 |  | Innis Consulting Group, LLC | Rocky Ripple | 2021-05-31
|  |  | 2002870 |  | InspectTech Systems, Inc. | Rome City | 2021-05-31
|  |  | 2002871 |  | J. Williams Appraisal Group, LLC | Rushville | 2021-05-31
|  |  | 2002872 |  | JCI Bridge Group, Inc. | Salem | 2021-05-31
|  |  | 2002873 |  | JRM Environmental, Inc. | Saratoga | 2021-05-31
|  |  | 2002874 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2021-05-31
|  |  | 2002875 |  |  | Scott County | 2021-05-31
|  |  | 2002876 |  |  | Scott County | 2021-05-31
|  |  | 2002877 |  |  | Scott County | 2021-05-31
|  |  | 2002878 |  |  | Scott County | 2021-05-31
|  |  | 2002879 |  |  | Scott County | 2021-05-31
|  |  | 2002880 |  |  | Scott County | 2021-05-31
|  |  | 2002881 |  |  | Scottsburg | 2021-05-31
|  |  | 2002882 |  | Jacobs Pannicke Architects, Inc. | Sellersburg | 2021-05-31
|  |  | 2002883 |  |  | Shadeland | 2021-05-31
|  |  | 2002884 |  |  | Shadeland | 2021-05-31
|  |  | 2002885 |  |  | Shadeland | 2021-05-31
|  |  | 2002886 |  | Jean Stewart, LLC | Sharpsville | 2021-05-31
|  |  | 2002887 |  | John A. Doyle Associates, Inc. | Shipshewana | 2021-05-31
|  |  | 2002888 |  | John G. Brinkworth, Inc. | Shirley | 2021-05-31
|  |  | 2002889 |  | K & S Engineers, Inc. | Somerville | 2021-05-31
|  |  | 2002890 |  |  | South Bend | 2021-05-31
|  |  | 2002891 |  |  | Spencer County | 2021-05-31
|  |  | 2002892 |  | Karen | St. John | 2021-05-31
|  |  | 2002893 |  |  | Starke County | 2021-05-31
|  |  | 2002894 |  |  | Starke County | 2021-05-31
|  |  | 2002895 |  |  | Steuben County | 2021-05-31
|  |  | 2002896 |  |  | Steuben County | 2021-05-31
|  |  | 2002897 |  | L'Acquis Consulting Enterprises Indianapolis, LLC | Sweetser | 2021-05-31
|  |  | 2002898 |  | LFR, Inc. | Switz City | 2021-05-31
|  |  | 2002899 |  |  | Switzerland County | 2021-05-31
|  |  | 2002900 |  | LONCO, Inc. | Syracuse | 2021-05-31
|  |  | 2002901 |  |  | Tell City | 2021-05-31
|  |  | 2002902 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 2002903 |  | Bayswater Company, LLC | Terre Haute | -339679.2083
|  |  | 2002904 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002905 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002906 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002907 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002908 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002909 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002910 |  |  | Tippecanoe County | 2021-05-31
|  |  | 2002911 |  | Land Consultants, Inc. | Topeka | 2021-05-31
|  |  | 2002912 |  | Landmark Engineering Group, Inc. | Troy | 2021-05-31
|  |  | 2002913 |  | Landmark Engineering Group, Inc. | Troy | 2021-05-31
|  |  | 2002914 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | 2021-05-31
|  |  | 2002915 |  |  | Union County | 2021-05-31
|  |  | 2002916 |  | Larry J. Allison | Uniondale | 2021-05-31
|  |  | 2002917 |  | Leitner and Associates, Inc. | Valparaiso | 2021-05-31
|  |  | 2002918 |  | Level 5 Engineering, LLC | Van Buren | 2021-05-31
|  |  | 2002919 |  |  | Vanderburgh County | 2021-05-31
|  |  | 2002920 |  |  | Vanderburgh County | 2021-05-31
|  |  | 2002921 |  | Linda F. Russell | Veedersburg | 2021-05-31
|  |  | 2002922 |  | Lonco, Inc. | Versailles | 2021-05-31
|  |  | 2002923 |  | M-E Companies, Inc. | Wabash | 2021-05-31
|  |  | 2002924 |  |  | Wabash County | 2021-05-31
|  |  | 2002925 |  | Wessler Engineering, Inc. | Wakarusa | 2021-05-31
|  |  | 2002926 |  | MCCARTIN - ASSOCIATES | Walton | 2021-05-31
|  |  | 2002927 |  | MCIS LLC | Wanatah | 2021-05-31
|  |  | 2002928 |  |  | Warrick County | 2021-05-31
|  |  | 2002929 |  |  | Wayne County | 2021-05-31
|  |  | 2002930 |  |  | Wayne County | 2021-05-31
|  |  | 2002931 |  |  | Wayne County | 2021-05-31
|  |  | 2002932 |  |  | Wells County | 2021-05-31
|  |  | 2002933 |  |  | Wells County | 2021-05-31
|  |  | 2002934 |  | Manhard Consulting, Ltd. | West Lafayette | 2021-05-31
|  |  | 2002935 |  | Martinez Corporation | Whitestown | 2021-05-31
|  |  | 2002936 |  | Apex Consulting & Surveying, Inc. | Winchester | 2021-05-31
|  |  | 2002937 |  | Apex Consulting & Surveying, Inc. | Winchester | 2021-05-31
|  |  | 2002938 |  | McCullouch Consulting, LLC | Windfall | 2021-05-31
|  |  | 2002939 |  | McDonough Associates, Inc. | Winfield | 2021-05-31
|  |  | 2002940 |  | Metropolitan Abstracting Consultants, LLC | Woodburn | 2021-05-31
|  |  | 2002941 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2002942 |  | CPS Acquisitions, LLC | Indiana Department of Transportation | 2019-03-06
|  |  | 2002943 |  |  | Indiana Department of Transportation | 2019-03-06
|  |  | 2002944 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2002945 |  | Browning Day Mullins Dierdorf Architects | East Chicago | -339679.2083
|  |  | 2002946 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2002947 |  | Wood Environment & Infrastructure Solutions, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 2002948 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002949 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2002950 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2002951 |  | Absolute Title Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2002952 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2002953 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2002954 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2002955 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2002956 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2002957 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002958 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2002959 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2002960 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2002961 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2002962 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2002963 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002964 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2002965 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2002966 |  | Dyer Environmental Services | Indiana Department of Transportation | 2023-11-15
|  |  | 2002967 |  |  | Noble County | 2026-03-11
|  |  | 2002968 |  |  | Odon | -339679.2083
|  |  | 2002969 |  |  | Posey County | -339679.2083
|  |  | 2002970 |  |  | Perry County | -339679.2083
|  |  | 2002971 |  |  | Tell City | 2025-07-09
|  |  | 2002972 |  | ASA Land Surveying | Bedford | 2025-07-09
|  |  | 2002973 |  | ASA Land Surveying | Lawrence County | 2025-07-09
|  |  | 2002974 |  | Klug Engineering, Inc. | Sullivan | 2025-07-09
|  |  | 2002975 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 2002976 |  |  | Milford (Kosciusko Co) | -339679.2083
|  |  | 2002977 |  | JCI Bridge Group, Inc. | Salem | 2026-03-11
|  |  | 2002978 |  |  | Monroe County | 2026-03-11
|  |  | 2002979 |  | Haas & Associates, L.L.C. | Oldenburg | -339679.2083
|  |  | 2002980 |  |  | Jefferson County | 2026-03-11
|  |  | 2002981 |  | Engineering Resources, Inc. | Madison | 2026-03-11
|  |  | 2002982 |  | B. L. A., Inc. | Harrison County | 2026-03-11
|  |  | 2002983 |  |  | Bartholomew County | -339679.2083
|  |  | 2002984 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 2002985 |  |  | Clark County | -339679.2083
|  |  | 2002986 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 2002987 |  | Janssen & Spaans Engineering, Inc. | Seymour | -339679.2083
|  |  | 2002988 |  |  | Morgan County | 2026-03-11
|  |  | 2002989 |  | Collier Transport Inc. | Greensburg | -339679.2083
|  |  | 2002990 |  |  | Harrison County | 2026-03-11
|  |  | 2002991 |  |  | Johnson County | 2026-03-11
|  |  | 2002992 |  |  | Jennings County | 2026-03-11
|  |  | 2002993 |  |  | Johnson County | 2026-03-11
|  |  | 2002994 |  |  | Morgan County | -339679.2083
|  |  | 2002995 |  |  | Morgan County | 2026-03-11
|  |  | 2002996 |  |  | Morgan County | 2025-09-10
|  |  | 2002997 |  |  | Morgan County | 2025-09-10
|  |  | 2002998 |  |  | Morgan County | 2026-03-11
|  |  | 2002999 |  |  | Clinton County | 2026-01-14
|  |  | 2003000 |  |  | Lebanon | -339679.2083
|  |  | 2003006 |  |  | Columbia City | -339679.2083
|  |  | 2003013 |  | Mackie Consultants, LLC | Kosciusko County | 2023-08-09
|  |  | 2003014 |  |  | Hendricks County | -339679.2083
|  |  | 2003016 | Montgomery |  | Montgomery County | 2025-11-13 | PE
|  |  | 2003017 |  | DuSABLE, Inc. | Tippecanoe County | -339679.2083
|  |  | 2003018 |  | DuSABLE, Inc. | Tippecanoe County | -339679.2083
|  |  | 2003019 |  | DuSABLE, Inc. | Tippecanoe County | 2025-11-13
|  |  | 2003020 |  |  | Boone County | 2025-08-06
|  |  | 2003021 |  | CPS Acquisitions, LLC | Fishers | -339679.2083
|  |  | 2003022 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 2003023 |  | GS-IN P.C. | Delaware County | 2025-07-09
|  |  | 2003024 |  |  | Fayette County | -339679.2083
|  |  | 2003025 |  | Eco Logic, LLC | Logansport | 2026-03-11
|  |  | 2003026 |  |  | Cass County | -339679.2083
|  |  | 2003027 |  |  | Hamilton County | -339679.2083
|  |  | 2003028 |  | McCormick Engineering, LLC | Pulaski County | -339679.2083
|  |  | 2003029 |  | H.R. Gray | North Judson | 2026-03-11
|  |  | 2003030 |  |  | Hamilton County | -339679.2083
|  |  | 2003031 |  | CPS Acquisitions, LLC | Hamilton County | 2025-07-09
|  |  | 2003032 |  |  | White County | 2026-03-11
|  |  | 2003033 |  |  | White County | 2026-03-11
|  |  | 2003034 |  |  | Hancock County | 2025-12-10
|  |  | 2003035 |  |  | Hamlet | -339679.2083
|  |  | 2003036 |  |  | LaPorte County | 2025-07-09
|  |  | 2003037 |  | Howard J. Barth & Associates, Inc. | Marshall County | -339679.2083
|  |  | 2003038 |  |  | Starke County | -339679.2083
|  |  | 2003039 |  |  | Starke County | -339679.2083
|  |  | 2003040 |  |  | Starke County | 2026-03-11
|  |  | 2003041 |  |  | Porter County | 2026-03-11
|  |  | 2003042 |  |  | Porter County | 2026-03-11
|  |  | 2003043 |  |  | Hancock County | 2025-12-10
|  |  | 2003044 |  |  | Hancock County | 2025-12-10
|  |  | 2003045 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 2003046 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 2003047 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003048 |  |  | Muncie | -339679.2083
|  |  | 2003049 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003050 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003051 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003052 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003053 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2025-07-09
|  |  | 2003054 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003055 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2003056 |  |  | Randolph County | -339679.2083
|  |  | 2003057 |  |  | Randolph County | -339679.2083
|  |  | 2003058 |  |  | Shelby County | -339679.2083
|  |  | 2003059 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 2003060 |  | Jeffrey S. Juday | Shelbyville | -339679.2083
|  |  | 2003061 |  | Apex Consulting & Surveying, Inc. | Winchester | -339679.2083
|  |  | 2003062 |  |  | Union County | -339679.2083
|  |  | 2003063 |  | Indiana Appraisal Group, Inc. | Wayne County | -339679.2083
|  |  | 2003064 |  |  | Whitley County | 2026-02-11
|  |  | 2003065 |  |  | Wabash County | 2025-10-08
|  |  | 2003066 |  | Fusion by Design, Inc. | Montpelier | -339679.2083
|  |  | 2003067 |  | Farren Real Estate Services | Middlebury | -339679.2083
|  |  | 2003068 |  |  | Noble County | -339679.2083
|  |  | 2003069 |  | ABt SRBI | Angola | 2026-08-05
|  |  | 2003070 |  |  | Indiana Department of Transportation | 2020-12-30
|  |  | 2003071 |  |  | Elkhart County | 2026-01-14
|  |  | 2003072 |  |  | Wells County | 2026-02-11
|  |  | 2003073 |  |  | Allen County | 2026-01-14
|  |  | 2003074 |  |  | Allen County | -339679.2083
|  |  | 2003075 |  |  | Allen County | -339679.2083
|  |  | 2003076 |  |  | Wells County | -339679.2083
|  |  | 2003077 |  | Accidental Discoveries, LLC | Wells County | 2026-02-11
|  |  | 2003078 |  | McLane Realty, Inc. | Winona Lake | -339679.2083
|  |  | 2003079 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 2003080 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2003081 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2003082 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2003083 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2003084 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2003085 |  | Dodd Title Corporation | Indiana Department of Transportation | 2026-04-08
|  |  | 2003086 |  | KERAMIDA Environmental, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2003087 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2003088 |  | Another Test Company | Indiana Department of Transportation | 2025-07-09
|  |  | 2003089 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 2003090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2003091 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 2024-07-10
|  |  | 2003092 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2003093 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2003094 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2003095 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2024-05-31
|  |  | 2003096 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2003097 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2003098 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2003099 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2003100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100001 | Dearborn |  | MPO - Cincinnati | -339679.2083 | PL
|  |  | 2100002 | Clark |  | MPO - Louisville | -339679.2083 | PL
|  |  | 2100003 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2100004 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100005 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100006 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2100007 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2100008 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2100009 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100010 |  | D & D Consulting Services, Inc. | Indiana Department of Transportation | 2024-08-14
|  |  | 2100011 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100012 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | 2025-11-13
|  |  | 2100013 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100014 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100015 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100016 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100017 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100018 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2100019 |  |  | Indiana Department of Transportation | 2024-03-13
|  |  | 2100020 |  | Civil Inspection Services, LLC | Goshen | 2025-07-09
|  |  | 2100021 |  | Civil Inspection Services, LLC | Goshen | 2027-07-14
|  |  | 2100022 |  |  | South Bend | 2027-03-10
|  |  | 2100023 |  |  | Mishawaka | -339679.2083
|  |  | 2100024 |  |  | St. Joseph County | 2026-03-11
|  |  | 2100025 |  |  | South Bend | 2025-03-12
|  |  | 2100026 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100027 |  |  | Elkhart County | 2025-07-09
|  |  | 2100028 |  |  | Elkhart County | 2026-07-08
|  |  | 2100029 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100030 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2100031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100032 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2100033 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100034 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100036 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100037 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100038 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100039 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2100040 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100041 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2100042 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100044 |  | CGI | Indiana Department of Transportation | 2026-03-11
|  |  | 2100045 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100046 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100047 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100048 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2026-04-08
|  |  | 2100049 | Tippecanoe |  | Indiana Department of Transportation | 2021-11-17 | CN
|  |  | 2100050 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2026-04-08
|  |  | 2100051 |  | CGI | Indiana Department of Transportation | 2026-03-11
|  |  | 2100052 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100053 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100054 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100055 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2023-01-19
|  |  | 2100056 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100057 |  |  | Indiana Department of Transportation | 2035-05-31
|  |  | 2100058 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100059 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100060 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2100061 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100062 |  |  | Clinton County | -339679.2083
|  |  | 2100063 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2100064 |  |  | Bartholomew County | 2019-05-09
|  |  | 2100065 |  |  | Elkhart County | 2023-05-10
|  |  | 2100066 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2022-01-12
|  |  | 2100067 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100068 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2100069 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2100070 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2100071 |  | Casteel Real Estate | Franklin | 2022-12-07
|  |  | 2100072 |  |  | Indiana Department of Transportation | 2019-10-09
|  |  | 2100073 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100074 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2100075 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2100076 |  |  | Indiana Department of Transportation | 2021-05-05
|  |  | 2100077 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2100078 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2100079 |  |  | Dubois County | -339679.2083
|  |  | 2100080 |  |  | Clark County | -339679.2083
|  |  | 2100081 |  |  | Floyd County | -339679.2083
|  |  | 2100082 |  |  | Gibson County | -339679.2083
|  |  | 2100083 |  |  | Kosciusko County | -339679.2083
|  |  | 2100084 |  |  | Monroe | -339679.2083
|  |  | 2100085 |  |  | Whitley County | -339679.2083
|  |  | 2100086 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2100087 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100088 | Delaware | GS-IN P.C. | Delaware County | 2024-07-10 | PE
|  |  | 2100089 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2100090 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2100091 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2100092 |  | DKA Associates, Inc. | Ingalls | 2023-07-12
|  |  | 2100093 |  |  | Kokomo | -339679.2083
|  |  | 2100094 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2100095 |  |  | Hamilton County | 2023-09-13
|  |  | 2100096 |  |  | Hamilton County | 2023-09-13
|  |  | 2100097 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2100098 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2100099 |  | Another Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 2100100 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2022-04-06
|  |  | 2100101 |  |  | Fulton County | -339679.2083
|  |  | 2100102 |  |  | Montgomery County | -339679.2083
|  |  | 2100103 |  |  | Wayne County | -339679.2083
|  |  | 2100104 |  |  | Posey County | -339679.2083
|  |  | 2100105 |  |  | Adams County | -339679.2083
|  |  | 2100106 |  |  | Allen County | -339679.2083
|  |  | 2100107 |  |  | Bartholomew County | -339679.2083
|  |  | 2100108 |  |  | Orange County | -339679.2083
|  |  | 2100109 |  |  | Porter County | -339679.2083
|  |  | 2100110 |  |  | Switzerland County | -339679.2083
|  |  | 2100111 |  |  | Wabash County | -339679.2083
|  |  | 2100112 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2100113 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100114 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100115 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2100116 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2100117 | Hancock |  | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2100118 | Hancock | CoCal Consulting, LLC | Indiana Department of Transportation | 2021-10-14 | CN
UT
|  |  | 2100119 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2100120 |  |  | Washington County | -339679.2083
|  |  | 2100121 |  |  | Indianapolis | 2023-12-13
|  |  | 2100122 |  |  | Indianapolis | 2023-12-13
|  |  | 2100123 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2100124 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2100125 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2100126 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2100127 |  | EnviroScience, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100128 |  |  | Harrison County | -339679.2083
|  |  | 2100129 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100130 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2022-02-09
|  |  | 2100131 |  | Huff & Huff, Inc. | Portage | 2023-01-19
|  |  | 2100132 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2100133 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2100134 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2100135 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2100136 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2100137 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2022-04-06
|  |  | 2100138 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 2100139 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2100140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100141 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100142 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2100143 |  |  | Delaware County | -339679.2083
|  |  | 2100144 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2100145 |  | McKee Enterprises, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2100146 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2029-10-11
|  |  | 2100147 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2100148 |  | Archonsortium, LLC | Indiana Department of Transportation | 2021-08-11
|  |  | 2100149 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 2100150 |  | Horner and Shifrin, Inc. | Hendricks County | 2023-12-13
|  |  | 2100151 |  | GS-IN P.C. | Muncie | 2023-07-12
|  |  | 2100152 |  |  | Allen County | 2029-10-11
|  |  | 2100153 |  |  | Jasper County | -339679.2083
|  |  | 2100154 |  |  | Spencer County | -339679.2083
|  |  | 2100155 |  |  | Newton County | -339679.2083
|  |  | 2100156 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100157 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100158 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100159 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100160 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100161 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2100162 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100163 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100164 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100165 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100166 |  | EHI Consultants, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100167 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100168 |  | III FFC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100169 |  | Infrastructure Engineering, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100170 |  | Greenman-Pedersen, Inc. | Indiana Department of Transportation | 2025-12-10
|  |  | 2100171 |  | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 2025-07-09
|  |  | 2100172 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100173 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100174 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100175 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100176 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100177 |  |  | Indiana Department of Transportation | 2023-11-08
|  |  | 2100178 |  | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 2023-03-15
|  |  | 2100179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100180 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100181 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100182 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100183 |  |  | Indiana Department of Transportation | 2026-04-08
|  |  | 2100184 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100185 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100186 |  | Archonsortium, LLC | Indiana Department of Transportation | 2025-12-10
|  |  | 2100187 |  | Hatch Mott MacDonald | Indiana Department of Transportation | 2025-11-13
|  |  | 2100188 |  | H W Lochner, Inc. | Indiana Department of Transportation | 2025-11-13
|  |  | 2100189 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100190 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100191 |  | Ark Engineering Services, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100192 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 2025-12-10
|  |  | 2100193 |  | Corradino, LLC | Indiana Department of Transportation | 2025-11-13
|  |  | 2100194 |  | Delcan Corporation | Indiana Department of Transportation | 2025-11-13
|  |  | 2100195 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100196 |  | Farren Real Estate Services | Indiana Department of Transportation | 2025-10-08
|  |  | 2100197 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100198 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100199 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2025-09-10
|  |  | 2100200 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100201 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100202 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100203 |  | LONCO, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100204 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100205 |  | Cambridge Systematics, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100206 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100207 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100208 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100209 |  | J.F. New & Associates, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100210 |  | J.F. New & Associates, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100211 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100212 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100213 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100214 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100215 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100216 |  | Maurer Surveying, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100217 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100218 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100219 |  | Landmark Engineering Group, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100220 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100221 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 2025-10-08
|  |  | 2100222 |  | ATSI Engineering Services | Indiana Department of Transportation | 2025-07-09
|  |  | 2100223 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100224 |  | Meridian Title Corporation | Indiana Department of Transportation | 2025-07-09
|  |  | 2100225 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100226 |  | McCormick Engineering, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100227 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100228 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100229 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100230 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100231 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100232 |  | M.A.T. Consulting, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100233 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100234 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100235 |  | Appraisal Service | Indiana Department of Transportation | 2025-07-09
|  |  | 2100236 |  | Consolidated Test Company | Indiana Department of Transportation | 2025-10-08
|  |  | 2100237 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100238 |  | Cornerstone Design | Indiana Department of Transportation | 2026-01-14
|  |  | 2100239 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100240 |  | McCormick Engineering, LLC | Indiana Department of Transportation | 2026-01-14
|  |  | 2100241 |  | Domain Architecture, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100242 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100243 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2026-02-11
|  |  | 2100244 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100245 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100246 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100247 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100248 |  | Heartland Recycling LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100249 |  | Crawford, Murphy & Tilly, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100250 |  | Haworth-Meyer-Boleyn Professional Engineers, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100251 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100252 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100253 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100254 |  | B. L. A., Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100255 |  | Kristine Fallon Associates, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100256 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-12-10
|  |  | 2100257 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100258 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2026-01-14
|  |  | 2100259 |  | JJR, LLC | Indiana Department of Transportation | 2025-07-09
|  |  | 2100260 |  | CGI | Indiana Department of Transportation | 2025-11-13
|  |  | 2100261 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100262 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100263 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100264 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 2025-11-13
|  |  | 2100265 |  | Fanning Howey Associates | Indiana Department of Transportation | 2025-09-10
|  |  | 2100266 |  | Bonar Group, LLC | Indiana Department of Transportation | 2025-09-10
|  |  | 2100267 |  | HLRD | Indiana Department of Transportation | 2025-10-08
|  |  | 2100268 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100269 |  | AI Engineers, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100270 |  | AI Engineers, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100271 |  | AI Engineers, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100272 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100273 |  | ERES International, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100274 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100275 |  | Hilton Property Management, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100276 |  | Hydrogeology, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100277 |  | Maten (Bob) Gabor Gerdenich II | Indiana Department of Transportation | 2025-07-09
|  |  | 2100278 |  | Durkin & Villalta Partners Engineering | Indiana Department of Transportation | 2025-07-09
|  |  | 2100279 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100280 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100281 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100282 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100283 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100284 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100285 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2025-11-13
|  |  | 2100286 |  | ASA Land Surveying | Indiana Department of Transportation | 2025-09-10
|  |  | 2100287 |  |  | Indiana Department of Transportation | 2021-10-15
|  |  | 2100288 |  |  | Fountain County | -339679.2083
|  |  | 2100289 |  |  | Lawrence County | -339679.2083
|  |  | 2100290 |  |  | Indiana Department of Transportation | 2021-10-14
|  |  | 2100291 |  |  | Elkhart County | -339679.2083
|  |  | 2100292 |  |  | Lake County | -339679.2083
|  |  | 2100293 |  |  | Adams County | 2022-05-31
|  |  | 2100294 |  |  | Adams County | 2022-05-31
|  |  | 2100295 |  |  | Advance | 2022-05-31
|  |  | 2100296 |  | 2IM Group, LLC | Akron | 2022-05-31
|  |  | 2100297 |  | 40th Parallel Surveying, LLC | Albany | -339679.2083
|  |  | 2100298 |  |  | Allen County | 2022-05-31
|  |  | 2100299 |  | A & F Engineering Co (former, no longer valid) | Alton | 2022-05-31
|  |  | 2100300 |  | AAC Environmental Consulting, LLC | Anderson | -339679.2083
|  |  | 2100301 |  | ABt SRBI | Angola | 2022-05-31
|  |  | 2100302 |  | ACME | Arcadia | -339679.2083
|  |  | 2100303 |  | AECOM USA, Inc. | Atlanta | -339679.2083
|  |  | 2100304 |  | AECON, Inc. | Attica | -339679.2083
|  |  | 2100305 |  | Quantum Spatial, Inc. | Auburn | 2022-05-31
|  |  | 2100306 |  |  | Aurora | 2022-05-31
|  |  | 2100307 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2022-05-31
|  |  | 2100308 |  | AEROCON Photogrammetric Services, Inc. | Austin | 2022-05-31
|  |  | 2100309 |  |  | Bartholomew County | 2022-05-31
|  |  | 2100310 |  | ARCADIS | Batesville | 2022-05-31
|  |  | 2100311 |  | ARCADIS | Batesville | 2022-05-31
|  |  | 2100312 |  | ASA Engineering Consultants, Inc. | Battle Ground | 2022-05-31
|  |  | 2100313 |  | AV Consulting Engineers, Inc. | Bicknell | 2022-05-31
|  |  | 2100314 |  |  | Boone County | 2022-05-31
|  |  | 2100315 |  |  | Boone County | -339679.2083
|  |  | 2100316 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2100317 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2100318 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2100319 |  | Advanced Appraisals, LLC | Brazil | -339679.2083
|  |  | 2100320 |  | Advanced Engineering Services Inc. | Bristol | 2022-05-31
|  |  | 2100321 |  | Amereco Incorporated | Burlington | 2022-05-31
|  |  | 2100322 |  | American Commercial Title & Escrow | Burns Harbor | 2022-05-31
|  |  | 2100323 |  | Anelena Ackerly | Carlisle | 2022-05-31
|  |  | 2100324 |  |  | Carroll County | 2022-05-31
|  |  | 2100325 |  |  | Cass County | 2022-05-31
|  |  | 2100326 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2022-05-31
|  |  | 2100327 |  | Applied Research Associates, Inc. | Center Point | -339679.2083
|  |  | 2100328 |  | Appraisals Unlimited of Indiana, LLC | Chesterfield | -339679.2083
|  |  | 2100329 |  |  | Clarks Hill | 2022-05-31
|  |  | 2100330 |  |  | Clay County | -339679.2083
|  |  | 2100331 |  |  | Clifford | 2022-05-31
|  |  | 2100332 |  |  | Clinton County | 2022-05-31
|  |  | 2100333 |  | Associated Appraisal Group, Inc. | Columbia City | 2022-05-31
|  |  | 2100334 |  | Associated Right-of-Way Services, Inc. | Columbus | 2022-05-31
|  |  | 2100335 |  | Atlas Appraisals, LLC | Converse | 2022-05-31
|  |  | 2100336 |  | Robert C. Bommer | Country Club Heights | -339679.2083
|  |  | 2100337 |  | BA Martin Architects, PC | Covington | -339679.2083
|  |  | 2100338 |  |  | Crawford County | 2022-05-31
|  |  | 2100339 |  | Basin Field Services, Inc. | Crothersville | 2022-05-31
|  |  | 2100340 |  | Baxter & Woodman, Inc. | Crown Point | 2022-05-31
|  |  | 2100341 |  | Beals-Moore & Associates, Inc. | Dale | 2022-05-31
|  |  | 2100342 |  | Beam, Longest and Neff, LLC | Dana | -339679.2083
|  |  | 2100343 |  | Bella Villa Realtors, LLC | Danville | -339679.2083
|  |  | 2100344 |  |  | Darmstadt | 2022-05-31
|  |  | 2100345 |  |  | Daviess County | 2022-05-31
|  |  | 2100346 |  | Bertsch-Frank & Associates, LLC | Dayton | 2022-05-31
|  |  | 2100347 |  | Bertsch-Frank & Associates, LLC | Dayton | 2022-05-31
|  |  | 2100348 |  | Bettina Settles Realty, LLC | De Motte | 2022-05-31
|  |  | 2100349 |  |  | Decatur County | 2022-05-31
|  |  | 2100350 |  |  | Delaware County | -339679.2083
|  |  | 2100351 |  |  | Delaware County | -339679.2083
|  |  | 2100352 |  |  | Delaware County | -339679.2083
|  |  | 2100353 |  | Blood Hound, Inc. (former) | Delphi | 2022-05-31
|  |  | 2100354 |  |  | Dublin | -339679.2083
|  |  | 2100355 |  |  | Dubois County | 2022-05-31
|  |  | 2100356 |  | Brenner Design Incorporated | Dyer | 2022-05-31
|  |  | 2100357 |  | Browning Day Mullins Dierdorf Architects | East Chicago | 2022-05-31
|  |  | 2100358 |  | Burgess & Niple, Inc. | Eaton | -339679.2083
|  |  | 2100359 |  | Burns & McDonnell Engineering Company, Inc. | Edgewood | -339679.2083
|  |  | 2100360 |  | C & E Clark, LLC | Elizabethtown | 2022-05-31
|  |  | 2100361 |  | C Blair Enterprises, Inc. | Elkhart | 2022-05-31
|  |  | 2100362 |  |  | Elkhart County | 2022-05-31
|  |  | 2100363 |  | CE Solutions, Inc. | Elwood | -339679.2083
|  |  | 2100364 |  |  | Fairland | -339679.2083
|  |  | 2100365 |  |  | Fayette County | -339679.2083
|  |  | 2100366 |  | CMF Engineering, Inc. | Ferdinand | 2022-05-31
|  |  | 2100367 |  | CRI Construction Inc. | Flora | 2022-05-31
|  |  | 2100368 |  |  | Floyd County | 2022-05-31
|  |  | 2100369 |  | Casteel Real Estate | Franklin | 2022-05-31
|  |  | 2100370 |  |  | Franklin County | 2022-05-31
|  |  | 2100371 |  |  | Fulton County | 2022-05-31
|  |  | 2100372 |  | Chicago Title Insurance Company | Gas City | 2022-05-31
|  |  | 2100373 |  | Christopher B. Burke Engineering, Ltd. | Gaston | -339679.2083
|  |  | 2100374 |  | Civil & Environmental Consultants, Inc. | Georgetown | 2022-05-31
|  |  | 2100375 |  |  | Gibson County | 2022-05-31
|  |  | 2100376 |  | Civil Inspection Services, LLC | Goshen | 2022-05-31
|  |  | 2100377 |  | Clark Dietz, Inc. | Grandview | 2022-05-31
|  |  | 2100378 |  |  | Grant County | 2022-05-31
|  |  | 2100379 |  | Cole and Associates, Inc. | Greensboro | -339679.2083
|  |  | 2100380 |  | Collier Transport Inc. | Greensburg | 2022-05-31
|  |  | 2100381 |  | Commonwealth Engineers, Inc. | Greenwood | 2022-05-31
|  |  | 2100382 |  | Commonwealth Engineers, Inc. | Greenwood | 2022-05-31
|  |  | 2100383 |  |  | Greenwood | 2022-05-31
|  |  | 2100384 |  | Commonwealth Engineers, Inc. | Greenwood | 2022-05-31
|  |  | 2100385 |  | Compliance Consulting Service, Inc. | Griffith | 2022-05-31
|  |  | 2100386 |  |  | Hamilton County | -339679.2083
|  |  | 2100387 |  |  | Hancock County | -339679.2083
|  |  | 2100388 |  |  | Harrison County | 2022-05-31
|  |  | 2100389 |  | Coor Consulting | Haubstadt | 2022-05-31
|  |  | 2100390 |  |  | Hendricks County | -339679.2083
|  |  | 2100391 |  |  | Henry County | -339679.2083
|  |  | 2100392 |  | Cornerstone Design | Highland | 2022-05-31
|  |  | 2100393 |  |  | Howard County | -339679.2083
|  |  | 2100394 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2022-05-31
|  |  | 2100395 |  |  | Huntington County | 2022-05-31
|  |  | 2100396 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 2100397 |  | DKA Associates, Inc. | Ingalls | -339679.2083
|  |  | 2100398 |  |  | Jackson County | 2022-05-31
|  |  | 2100399 |  | Dan Moore Real Estate Services, Inc. | Jasonville | 2022-05-31
|  |  | 2100400 |  |  | Jasper County | 2022-05-31
|  |  | 2100401 |  | Data Transfer Solutions, LLC | Jeffersonville | 2022-05-31
|  |  | 2100402 |  |  | Jennings County | 2022-05-31
|  |  | 2100403 |  |  | Jennings County | 2022-05-31
|  |  | 2100404 |  |  | Jennings County | 2022-05-31
|  |  | 2100405 |  |  | Jennings County | 2022-05-31
|  |  | 2100406 |  |  | Jennings County | 2022-05-31
|  |  | 2100407 |  |  | Kentland | 2022-05-31
|  |  | 2100408 |  |  | Knox County | 2022-05-31
|  |  | 2100409 |  | Dodd Title Corporation | Kokomo | -339679.2083
|  |  | 2100410 |  | DuSABLE, Inc. | Lafayette | 2022-05-31
|  |  | 2100411 |  |  | Lanesville | 2022-05-31
|  |  | 2100412 |  | Duneland Group, Inc. | Lapel | -339679.2083
|  |  | 2100413 |  | Dyer Environmental Services | Lawrence | -339679.2083
|  |  | 2100414 |  |  | Lizton | -339679.2083
|  |  | 2100415 |  | Eco Logic, LLC | Logansport | 2022-05-31
|  |  | 2100416 |  | Eco-Tech Consultants, Inc. | Long Beach | 2022-05-31
|  |  | 2100417 |  | Edwards and Kelcey | Lowell | 2022-05-31
|  |  | 2100418 |  |  | Marshall County | 2022-05-31
|  |  | 2100419 |  |  | Martin County | 2022-05-31
|  |  | 2100420 |  | EnviroScience, Inc. | Martinsville | 2022-05-31
|  |  | 2100421 |  | Farah and Sons, Inc. | Michigan City | 2022-05-31
|  |  | 2100422 |  | Farren Real Estate Services | Middlebury | 2022-05-31
|  |  | 2100423 |  | Finley Engineering Group, Inc. | Millersburg | 2022-05-31
|  |  | 2100424 |  | First Group Engineering, Inc. | Milltown | 2022-05-31
|  |  | 2100425 |  | ICA Engineering, Inc. | Mitchell | 2022-05-31
|  |  | 2100426 |  | Foresight Land Surveying, Inc. | Monroe | 2022-05-31
|  |  | 2100427 |  |  | Monroe County | 2022-05-31
|  |  | 2100428 |  | Fugro Roadware, Inc. | Monticello | 2022-05-31
|  |  | 2100429 |  | Fugro Roadware, Inc. | Monticello | 2022-05-31
|  |  | 2100430 |  | Fusion by Design, Inc. | Montpelier | 2022-05-31
|  |  | 2100431 |  |  | Morgan County | 2022-05-31
|  |  | 2100432 |  | GRL Engineers, Inc. | Mount Vernon | 2022-05-31
|  |  | 2100433 |  | GS-IN P.C. | Muncie | -339679.2083
|  |  | 2100434 |  |  | Munster | 2022-05-31
|  |  | 2100435 |  | Gandhi and Associates, Inc. | Nappanee | 2022-05-31
|  |  | 2100436 |  | Gandhi and Associates, Inc. | Nappanee | 2022-05-31
|  |  | 2100437 |  | Gandhi and Associates, Inc. | Nappanee | 2022-05-31
|  |  | 2100438 |  | Garcia LE & Associates, L.L.C. | Nashville | 2022-05-31
|  |  | 2100439 |  | Garcia LE & Associates, L.L.C. | Nashville | 2021-05-31
|  |  | 2100440 |  |  | New Albany | 2022-05-31
|  |  | 2100441 |  | Gensic Engineering, Inc. | New Carlisle | 2022-05-31
|  |  | 2100442 |  | GeoSolutions, Inc. | New Castle | -339679.2083
|  |  | 2100443 |  | Global Land Surveying, LLC | New Harmony | 2022-05-31
|  |  | 2100444 |  |  | New Richmond | 2022-05-31
|  |  | 2100445 |  |  | New Whiteland | 2022-05-31
|  |  | 2100446 |  |  | Noble County | 2022-05-31
|  |  | 2100447 |  | H. Stewart Kline & Associates, Inc. | Noblesville | -339679.2083
|  |  | 2100448 |  | HE-BFS, LLC | North Manchester | 2022-05-31
|  |  | 2100449 |  | HE-BFS, LLC | North Manchester | 2022-05-31
|  |  | 2100450 |  |  | Odon | 2022-05-31
|  |  | 2100451 |  |  | Ohio County | 2022-05-31
|  |  | 2100452 |  |  | Orange County | 2022-05-31
|  |  | 2100453 |  | Hannum, Wagle & Cline Engineering | Orleans | 2022-05-31
|  |  | 2100454 |  | Hanson Professional Services, Inc. | Osceola | 2022-05-31
|  |  | 2100455 |  | Hardlines Design Company | Ossian | 2022-05-31
|  |  | 2100456 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | 2022-05-31
|  |  | 2100457 |  | Harris Miller Miller and Hanson, Inc. | Otterbein | 2022-05-31
|  |  | 2100458 |  |  | Owen County | -339679.2083
|  |  | 2100459 |  | Heritage Land Services | Patriot | 2022-05-31
|  |  | 2100460 |  | Hey and Associates, Inc. | Pendleton | -339679.2083
|  |  | 2100461 |  |  | Perry County | 2022-05-31
|  |  | 2100462 |  | Home Equity Appraisals | Petersburg | 2022-05-31
|  |  | 2100463 |  |  | Pike County | 2022-05-31
|  |  | 2100464 |  |  | Pike County | 2022-05-31
|  |  | 2100465 |  | Huff & Huff, Inc. | Portage | 2022-05-31
|  |  | 2100466 |  | Hy-Tech Response, Inc. | Porter | 2022-05-31
|  |  | 2100467 |  |  | Porter County | 2022-05-31
|  |  | 2100468 |  |  | Posey County | 2022-05-31
|  |  | 2100469 |  | III FFC | Princeton | 2022-05-31
|  |  | 2100470 |  |  | Putnam County | -339679.2083
|  |  | 2100471 |  |  | Randolph County | -339679.2083
|  |  | 2100472 |  | IXOYE, Limited | Redkey | -339679.2083
|  |  | 2100473 |  | Indiana Appraisal Group, Inc. | Richmond | 2022-05-31
|  |  | 2100474 |  | Indiana Infrastructure Partners, LLC | Riley | -339679.2083
|  |  | 2100475 |  |  | Ripley County | 2022-05-31
|  |  | 2100476 |  | Indiana Search Technologies | Rising Sun | 2022-05-31
|  |  | 2100477 |  |  | Roanoke | 2022-05-31
|  |  | 2100478 |  |  | Roanoke | 2022-05-31
|  |  | 2100479 |  | Iteris, Inc. | Rossville | 2022-05-31
|  |  | 2100480 |  | J. Williams Appraisal Group, LLC | Rushville | -339679.2083
|  |  | 2100481 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2022-05-31
|  |  | 2100482 |  |  | Scottsburg | 2022-05-31
|  |  | 2100483 |  | James Pichler Appraisals | Selma | 2022-05-31
|  |  | 2100484 |  | James Pichler Appraisals | Selma | 2022-05-31
|  |  | 2100485 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2022-05-31
|  |  | 2100486 |  | Robert Neal Sanders | Shamrock | -339679.2083
|  |  | 2100487 |  | Jeffrey P. French & Associates Land Surveying | Shelburn | 2022-05-31
|  |  | 2100488 |  | Jeffrey P. French & Associates Land Surveying | Shelburn | 2022-05-31
|  |  | 2100489 |  |  | Shelby County | -339679.2083
|  |  | 2100490 |  | Jill D Reed and Associates, Inc. | Sheridan | -339679.2083
|  |  | 2100491 |  | John A. Doyle Associates, Inc. | Shipshewana | 2022-05-31
|  |  | 2100492 |  |  | Silver Lake | 2022-05-31
|  |  | 2100493 |  |  | Silver Lake | 2022-05-31
|  |  | 2100494 |  |  | Silver Lake | 2022-05-31
|  |  | 2100495 |  |  | South Bend | 2022-05-31
|  |  | 2100496 |  |  | South Whitley | 2022-05-31
|  |  | 2100497 |  |  | South Whitley | 2022-05-31
|  |  | 2100498 |  |  | South Whitley | 2022-05-31
|  |  | 2100499 |  |  | South Whitley | 2022-05-31
|  |  | 2100500 |  | KCI Technologies, Inc. | Southport | -339679.2083
|  |  | 2100501 |  | KERAMIDA Environmental, Inc. | Speedway | -339679.2083
|  |  | 2100502 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2022-05-31
|  |  | 2100503 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2022-05-31
|  |  | 2100504 |  | KHAFRA Engineering Consultants, Inc. | Spencer | 2022-05-31
|  |  | 2100505 |  |  | Spiceland | -339679.2083
|  |  | 2100506 |  |  | Spiceland | -339679.2083
|  |  | 2100507 |  | KZF Design, Inc. | St. Joe | 2022-05-31
|  |  | 2100508 |  |  | St. Joseph County | 2022-05-31
|  |  | 2100509 |  |  | Sullivan County | 2022-05-31
|  |  | 2100510 |  | Kovachevich & Co., Inc. | Summitville | -339679.2083
|  |  | 2100511 |  |  | Switzerland County | 2022-05-31
|  |  | 2100512 |  | LONCO, Inc. | Syracuse | 2022-05-31
|  |  | 2100513 |  | Lamac Engineering Company | Thorntown | 2022-05-31
|  |  | 2100514 |  |  | Tippecanoe County | 2022-05-31
|  |  | 2100515 |  | Land Construction Corp | Tipton | -339679.2083
|  |  | 2100516 |  |  | Tipton County | -339679.2083
|  |  | 2100517 |  | Land Title Service Company, LLC | Town Of Pines | 2022-05-31
|  |  | 2100518 |  | Land Title Service Company, LLC | Town Of Pines | 2022-05-31
|  |  | 2100519 |  | Landmark Engineering Group, Inc. | Troy | 2022-05-31
|  |  | 2100520 |  | Landmark Engineering Group, Inc. | Troy | 2022-05-31
|  |  | 2100521 |  | Langworthy, Strader, LeBlanc & Associates, Inc. | Union City | -339679.2083
|  |  | 2100522 |  |  | Union County | -339679.2083
|  |  | 2100523 |  | Leitner and Associates, Inc. | Valparaiso | 2022-05-31
|  |  | 2100524 |  | Level 5 Engineering, LLC | Van Buren | 2022-05-31
|  |  | 2100525 |  |  | Vanderburgh County | 2022-05-31
|  |  | 2100526 |  |  | Vermillion County | -339679.2083
|  |  | 2100527 |  | Lonco, Inc. | Versailles | 2022-05-31
|  |  | 2100528 |  | Lonco, Inc. | Versailles | 2022-05-31
|  |  | 2100529 |  |  | Vigo County | -339679.2083
|  |  | 2100530 |  | Louis Joyner, Architect | Vincennes | 2022-05-31
|  |  | 2100531 |  |  | Wabash County | 2022-05-31
|  |  | 2100532 |  |  | Warren County | -339679.2083
|  |  | 2100533 |  |  | Warrick County | 2022-05-31
|  |  | 2100534 |  |  | Washington County | 2022-05-31
|  |  | 2100535 |  | Mader Design, LLC | Waterloo | 2022-05-31
|  |  | 2100536 |  |  | Waveland | 2022-05-31
|  |  | 2100537 |  |  | Wells County | 2022-05-31
|  |  | 2100538 |  |  | Westfield | -339679.2083
|  |  | 2100539 |  | Marine Solutions, Inc. | Westville | 2022-05-31
|  |  | 2100540 |  |  | White County | 2022-05-31
|  |  | 2100541 |  | Martin Riley, Inc. | Whiteland | 2022-05-31
|  |  | 2100542 |  | Matt L. Nepote, MAI | Whiting | 2022-05-31
|  |  | 2100543 |  |  | Whitley County | 2022-05-31
|  |  | 2100544 |  | McCormick Engineering, LLC | Winamac | 2022-05-31
|  |  | 2100545 |  | Apex Consulting & Surveying, Inc. | Winchester | -339679.2083
|  |  | 2100546 |  | Apex Consulting & Surveying, Inc. | Winchester | -339679.2083
|  |  | 2100547 |  | McDonough Associates, Inc. | Winfield | 2022-05-31
|  |  | 2100548 |  | Meca Engineering Corporation of America Incorporated | Winslow | 2022-05-31
|  |  | 2100549 |  | Midwest Archaeological Research Services, Inc. | Zionsville | 2022-05-31
|  |  | 2100550 |  |  | Johnson County | 2026-03-11
|  |  | 2100551 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100552 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100553 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2100554 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2100555 |  | InspectTech Systems, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100556 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100557 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100558 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100559 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 2025-10-08
|  |  | 2100560 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100561 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100562 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100563 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100564 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100565 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100566 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100567 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100568 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100569 |  | ASA Land Surveying | Indiana Department of Transportation | 2025-08-06
|  |  | 2100570 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100571 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100572 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100573 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100574 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100575 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100576 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100577 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2100578 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100579 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100580 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100581 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100582 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100583 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100584 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2100585 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100586 |  | Consolidated Test Company | Indiana Department of Transportation | 2025-10-08
|  |  | 2100587 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100588 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100589 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100590 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100591 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100592 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100593 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100594 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100595 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100596 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100597 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100598 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100599 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100600 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100601 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100602 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100603 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100604 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100605 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100606 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100607 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2025-08-06
|  |  | 2100608 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2025-08-06
|  |  | 2100609 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100610 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100611 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100612 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100613 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100614 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100615 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100616 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100617 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100618 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100619 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100620 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100621 |  | Consolidated Test Company | Indiana Department of Transportation | 2025-07-09
|  |  | 2100622 |  | Global Management Group, Inc. | New Haven | 2029-10-11
|  |  | 2100623 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2100624 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2100625 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2100626 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2100627 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100628 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100629 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100630 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100631 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100632 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100633 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100634 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100635 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100636 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100637 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100638 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100639 |  | Eco Logic, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100640 |  | Eco Logic, LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100641 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100642 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100643 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100644 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100645 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100646 |  | Consolidated Test Company | Indiana Department of Transportation | 2025-07-09
|  |  | 2100647 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2025-08-06
|  |  | 2100648 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100649 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100650 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2025-08-06
|  |  | 2100651 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2025-08-06
|  |  | 2100652 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100653 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100654 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100655 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100656 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100657 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100658 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100659 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100660 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100661 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100662 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100663 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100664 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100665 |  | Cornerstone Design | Indiana Department of Transportation | 2025-10-08
|  |  | 2100666 |  | Cornerstone Design | Indiana Department of Transportation | 2026-01-14
|  |  | 2100667 |  | Consolidated Test Company | Indiana Department of Transportation | 2025-10-08
|  |  | 2100668 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100669 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100670 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100671 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100672 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100673 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100674 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100675 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100676 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100677 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100678 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100679 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100680 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100681 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100682 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 2025-07-09
|  |  | 2100683 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 2025-08-06
|  |  | 2100684 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100685 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100686 |  | Bidinfo | Indiana Department of Transportation | 2025-09-10
|  |  | 2100687 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100688 |  |  | Indiana Department of Transportation | 2024-09-11
|  |  | 2100689 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100690 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100691 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100692 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100693 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100694 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100695 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100696 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100697 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100698 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100699 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100700 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100701 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100702 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100703 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100704 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100705 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100706 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100707 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100708 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100709 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100710 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100711 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100712 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100713 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100714 |  | AEROCON Photogrammetric Services, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2100715 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100716 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100717 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100718 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100719 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100720 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100721 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100722 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2100723 |  | CGS Real Estate Services, LLC | Indiana Department of Transportation | 2022-01-12
|  |  | 2100724 |  | CGS Real Estate Services, LLC | Indiana Department of Transportation | 2022-01-12
|  |  | 2100725 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100726 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100727 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100728 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2025-08-06
|  |  | 2100729 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100730 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100731 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100732 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100733 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100734 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100735 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100736 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100737 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100738 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100739 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100740 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100741 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100742 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100743 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100744 |  | Gregg A. Townsend | Indiana Department of Transportation | 2025-08-06
|  |  | 2100745 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100746 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100747 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100748 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100749 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100751 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100752 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100753 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100754 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100755 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100756 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100757 |  | CTLGroup | Indiana Department of Transportation | 2020-08-05
|  |  | 2100758 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100759 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100760 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100761 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100762 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100763 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100764 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100765 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100766 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100767 |  | Global Management Group, Inc. | Indiana Department of Transportation | 2026-03-11
|  |  | 2100768 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100769 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100770 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100771 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100772 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100773 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100774 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-11-13
|  |  | 2100775 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100776 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100777 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-09-10
|  |  | 2100778 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-10-08
|  |  | 2100779 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100780 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100781 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100782 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100783 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100784 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100785 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100786 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100787 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100788 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100789 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100790 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100791 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100792 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100793 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100794 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100795 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100796 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100797 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100798 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2025-11-13
|  |  | 2100799 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100800 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2100801 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100802 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100803 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100804 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100805 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100806 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100807 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100808 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100809 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100810 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100811 |  | Banning Engineering, P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 2100812 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100813 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100814 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2026-03-11
|  |  | 2100815 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100816 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100817 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100818 |  | Cambridge Systematics, Inc. | Indiana Department of Transportation | 2025-10-08
|  |  | 2100819 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100820 |  |  | Indiana Department of Transportation | 2026-03-11
|  |  | 2100821 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100822 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100823 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100824 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100825 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100826 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100827 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100828 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100829 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100830 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100831 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100832 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100833 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100834 |  | Gregg A. Townsend | Indiana Department of Transportation | 2025-08-06
|  |  | 2100835 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100836 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100837 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100838 |  |  | Indiana Department of Transportation | 2026-01-14
|  |  | 2100839 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100840 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100841 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100842 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100843 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2100844 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2100845 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2100846 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100847 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2100848 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100849 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2100850 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2100851 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100852 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100853 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2100854 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2100855 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2100856 |  | GS-IN P.C. | Indiana Department of Transportation | 2024-07-10
|  |  | 2100857 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100858 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100859 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100860 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100861 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100862 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2100863 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2100864 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2100865 |  | Bidinfo | Indiana Department of Transportation | 2024-11-14
|  |  | 2100866 |  | DCD Consulting LLC | Indiana Department of Transportation | 2025-02-05
|  |  | 2100867 |  |  | Indiana Department of Transportation | 2024-11-14
|  |  | 2100868 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2100869 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2100870 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2100871 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2100872 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2100873 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2100874 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2100875 |  | Dyer Environmental Services | Indiana Department of Transportation | 2023-07-12
|  |  | 2100876 |  | Dyer Environmental Services | Indiana Department of Transportation | 2023-07-12
|  |  | 2100877 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2100878 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100879 |  | ERES International, Inc. | Indiana Department of Transportation | 2022-12-07
|  |  | 2100880 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100881 |  | M-E Companies, Inc. | Indiana Department of Transportation | 2022-09-14
|  |  | 2100882 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100883 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100884 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100885 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100886 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100887 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100888 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2100889 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2100890 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2100891 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2100892 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100893 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100894 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100895 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100896 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100897 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100898 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100899 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100900 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100901 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100902 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100903 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100904 |  | Independent Appraisers-Consultants, Inc. | Indiana Department of Transportation | 2023-02-15
|  |  | 2100905 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100906 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2100907 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100908 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100909 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100910 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100911 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2100912 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100913 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100914 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100915 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100916 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100917 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100918 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100919 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2100920 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100921 |  | Consolidated Test Company | Indiana Department of Transportation | 2023-01-19
|  |  | 2100922 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100923 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100924 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 2022-12-07
|  |  | 2100925 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100926 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100927 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100928 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100929 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100930 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2100931 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100932 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100933 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100934 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 2022-09-14
|  |  | 2100935 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100936 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100937 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100938 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100939 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100940 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100941 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2100942 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100943 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100944 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100945 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2100946 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100947 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100948 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2100949 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2100950 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100951 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100952 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2100953 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2100954 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100955 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100956 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100957 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2100958 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100959 |  |  | Indiana Department of Transportation | 2022-10-13
|  |  | 2100960 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100961 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2100962 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 2100963 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 2100964 |  |  | Clay County | -339679.2083
|  |  | 2100965 |  |  | Madison County | -339679.2083
|  |  | 2100966 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100967 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100968 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100969 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2100970 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2100971 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100972 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100973 |  |  | Pulaski County | -339679.2083
|  |  | 2100974 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100975 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100976 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100977 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100978 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100979 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100980 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100981 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100982 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100983 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100984 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100985 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100986 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100987 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100988 |  | DCD Consulting LLC | Indiana Department of Transportation | 2026-02-11
|  |  | 2100989 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100990 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100991 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100992 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100993 |  |  | Starke County | -339679.2083
|  |  | 2100994 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100995 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2100996 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-12-10
|  |  | 2100997 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-12-10
|  |  | 2100998 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2100999 |  |  | Indiana Department of Transportation | 2026-02-11
|  |  | 2101000 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101001 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101002 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101003 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2101004 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101005 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101006 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101007 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2101008 |  |  | Indiana Department of Transportation | 2022-11-16
|  |  | 2101009 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2101010 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2101011 |  | III FFC | Indiana Department of Transportation | 2023-04-12
|  |  | 2101012 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083
|  |  | 2101013 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101014 |  |  | Indiana Department of Transportation | 2023-03-15
|  |  | 2101015 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2101016 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2101017 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101018 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101019 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101020 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101021 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101022 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2101023 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2101024 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101025 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2101026 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2101027 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101028 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101029 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2101030 |  |  | Indiana Department of Transportation | 2021-05-31
|  |  | 2101031 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101032 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101033 |  |  | Tippecanoe County | -339679.2083
|  |  | 2101034 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101035 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101036 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101037 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2101038 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2101039 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2101040 |  |  | Blackford County | -339679.2083
|  |  | 2101041 |  |  | Dekalb County | -339679.2083
|  |  | 2101042 |  |  | Lafayette CityBus | -339679.2083
|  |  | 2101043 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101044 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101045 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101046 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101047 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101048 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101049 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101050 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101051 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2101052 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 2101053 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101054 |  |  | Franklin County | -339679.2083
|  |  | 2101055 |  |  | Marshall County | -339679.2083
|  |  | 2101056 |  |  | Ripley County | -339679.2083
|  |  | 2101057 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2101058 |  | ARCADIS | Indiana Department of Transportation | 2025-10-08
|  |  | 2101059 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2101060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101061 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101062 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101063 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101064 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101065 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101066 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2101067 |  |  | South Bend Transit | -339679.2083
|  |  | 2101068 |  |  | South Bend Transit | -339679.2083
|  |  | 2101069 |  |  | South Bend Transit | -339679.2083
|  |  | 2101070 |  | DCD Consulting LLC | Indiana Department of Transportation | 2023-02-15
|  |  | 2101071 |  | Another Test Company | Indiana Department of Transportation | 2023-02-15
|  |  | 2101072 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2024-02-14
|  |  | 2101073 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101074 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101075 |  | E.J. Breneman, LP | Indiana Department of Transportation | 2025-02-12
|  |  | 2101076 |  |  | Indiana Department of Transportation | 2025-10-08
|  |  | 2101077 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101078 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101079 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101081 |  | Global Management Group, Inc. | New Haven | 2029-10-11
|  |  | 2101082 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2101083 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101084 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101085 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101086 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101087 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101088 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101089 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101090 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2101091 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101092 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101093 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-12-10
|  |  | 2101094 |  |  | Indiana Department of Transportation | 2025-12-10
|  |  | 2101095 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101096 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2101097 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101098 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101099 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2101100 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2101101 |  | AECOM Technical Services, Inc. | Indiana Department of Transportation | 2025-08-06
|  |  | 2101102 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2101103 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101104 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101105 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101106 |  |  | Indiana Department of Transportation | 2025-07-09
|  |  | 2101107 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101108 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2101109 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2101110 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2024-12-11
|  |  | 2101111 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101112 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101113 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101114 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101115 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101116 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101117 |  |  | Chesterton | 2024-12-11
|  |  | 2101118 |  | Browning Day Mullins Dierdorf Architects | East Chicago | 2025-12-10
|  |  | 2101119 |  |  | Griffith | 2026-12-09
|  |  | 2101120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101121 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101122 |  |  | Indiana Department of Transportation | 2025-02-12
|  |  | 2101123 |  | Archonsortium, LLC | Indiana Department of Transportation | 2021-08-11
|  |  | 2101124 |  | Collier Transport Inc. | Indiana Department of Transportation | 2025-12-10
|  |  | 2101125 |  |  | Tippecanoe County | 2023-11-15
|  |  | 2101126 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2101127 |  | Consolidated Test Company | Hammond | 2025-12-10
|  |  | 2101128 |  | Consolidated Test Company | Hammond | 2024-12-11
|  |  | 2101129 |  |  | Lake County | 2025-10-08
|  |  | 2101130 |  |  | Merrillville | 2026-03-11
|  |  | 2101131 |  |  | Merrillville | 2025-12-10
|  |  | 2101132 |  |  | Munster | 2024-12-09
|  |  | 2101133 |  | Leitner and Associates, Inc. | Valparaiso | 2027-03-10
|  |  | 2101134 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2101135 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2101136 | Marion |  | Indiana Department of Transportation | 2021-12-08 | CN
|  |  | 2101137 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2101138 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2101139 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2101140 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-08-05
|  |  | 2101141 |  | Leitner and Associates, Inc. | Valparaiso | 2025-12-10
|  |  | 2101142 |  | Douglass Environmental Services, Inc. | La Porte | -339679.2083
|  |  | 2101143 |  | Douglass Environmental Services, Inc. | La Porte | 2023-12-12
|  |  | 2101144 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 2101145 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 2101146 |  |  | Central Indiana Regional Transportation Authority | -339679.2083
|  |  | 2101147 |  | Farah and Sons, Inc. | Michigan City | 2025-12-09
|  |  | 2101148 |  | Farah and Sons, Inc. | Michigan City | 2026-12-01
|  |  | 2101149 |  |  | LaPorte County | 2026-12-09
|  |  | 2101150 |  | Karen | St. John | -339679.2083
|  |  | 2101151 |  | Associated Right-of-Way Services, Inc. | Columbus | 2023-10-12
|  |  | 2101152 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 2101153 |  |  | Indiana Department of Transportation | 2023-02-15
|  |  | 2101154 | Various |  | Indiana Department of Transportation | -339679.2083 | PL
|  |  | 2101155 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2101156 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2101157 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 2026-01-14
|  |  | 2101158 |  |  | Allen County | 2025-09-10
|  |  | 2101159 |  | Jacobs Engineering Group, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2101160 |  | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2019-03-06
|  |  | 2101161 |  |  | Indiana Department of Transportation | 2025-11-13
|  |  | 2101162 |  |  | Indiana Department of Transportation | 2025-08-06
|  |  | 2101163 |  |  | Vanderburgh County | -339679.2083
|  |  | 2101164 |  |  | White County | -339679.2083
|  |  | 2101165 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2021-01-13
|  |  | 2101166 |  | ABt SRBI | Indiana Department of Transportation | 2026-08-05
|  |  | 2101167 |  |  | Porter County | 2022-03-09
|  |  | 2101168 |  | McDonough Associates, Inc. | Winfield | 2025-11-13
|  |  | 2101169 |  | Archonsortium, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 2101170 |  |  | Indiana Department of Transportation | 2024-02-14
|  |  | 2101171 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2101172 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2021-06-11
|  |  | 2101173 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 2021-09-08
|  |  | 2101174 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2101175 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2101176 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2101177 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 2101178 |  | Bayswater Company, LLC | Indiana Department of Transportation | 2023-07-12
|  |  | 2101179 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101181 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101182 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101183 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101184 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101185 |  |  | Howard County | -339679.2083
|  |  | 2101186 |  |  | Jefferson County | -339679.2083
|  |  | 2101187 |  |  | Owen County | -339679.2083
|  |  | 2101188 |  |  | Tipton County | -339679.2083
|  |  | 2101189 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101190 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 2021-09-15
|  |  | 2101191 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 2101192 |  |  | Indiana Department of Transportation | 2024-04-10
|  |  | 2101193 |  |  | Indiana Department of Transportation | 2023-11-15
|  |  | 2101194 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2101195 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 2022-03-09
|  |  | 2101196 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101197 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101198 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101199 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2101200 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2101201 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101202 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101203 |  |  | Indiana Department of Transportation | 2022-05-31
|  |  | 2101204 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2101205 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101206 |  |  | Indiana Department of Transportation | 2025-09-10
|  |  | 2101207 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101208 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101209 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101211 |  | DCD Consulting LLC | Indiana Department of Transportation | 2021-07-14
|  |  | 2101212 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 2021-01-13
|  |  | 2101213 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101214 |  | Huff & Huff, Inc. | Portage | 2022-03-09
|  |  | 2101215 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2101216 |  |  | Indiana Department of Transportation | 2022-09-14
|  |  | 2101217 |  |  | Indiana Department of Transportation | 2022-07-13
|  |  | 2101218 |  | MainLine Management, Inc. | Indiana Department of Transportation | 2025-07-09
|  |  | 2101219 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 2022-09-14
|  |  | 2101220 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2101221 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2101222 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101223 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2101224 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2101225 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2101226 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 2020-08-05
|  |  | 2101227 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 2020-08-05
|  |  | 2101228 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101229 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 2101230 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101231 |  | Bowman, Barrett & Associates, Inc. | Indiana Department of Transportation | 2022-03-09
|  |  | 2101232 |  |  | Indiana Department of Transportation | 2022-08-10
|  |  | 2101233 |  |  | Indiana Department of Transportation | 2021-12-08
|  |  | 2101234 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101235 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2101236 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101237 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 2022-11-16
|  |  | 2101238 |  | Knies Constr/Calcar Paving J/V | Lapaz | 2024-08-14
|  |  | 2101239 |  |  | Indiana Department of Transportation | 2021-11-17
|  |  | 2101240 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101241 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2101242 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2101243 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2101244 |  | Casteel Real Estate | Indiana Department of Transportation | 2020-09-02
|  |  | 2101245 |  |  | Indiana Department of Transportation | 2017-06-22
|  |  | 2101246 |  |  | Indiana Department of Transportation | 2020-08-05
|  |  | 2101247 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 2020-08-05
|  |  | 2101248 |  | Bowman, Barrett & Associates, Inc. | Indiana Department of Transportation | 2020-08-05
|  |  | 2101249 |  |  | MPO - South Bend / Elkhart | -339679.2083
|  |  | 2101250 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101251 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101252 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101253 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101254 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101255 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2101256 |  |  | Indiana Department of Transportation | 2022-01-12
|  |  | 2101257 |  |  | Indiana Department of Transportation | 2026-05-31
|  |  | 2101258 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101259 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2022-10-13
|  |  | 2101260 |  | Garcia LE & Associates, L.L.C. | Brown County | 2022-04-06
|  |  | 2101261 |  | Louis Joyner, Architect | Indiana Department of Transportation | 2020-07-08
|  |  | 2101262 |  | All About Pavements, Inc. | Indiana Department of Transportation | 2023-07-12
|  |  | 2101263 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101264 |  | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2101265 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2101266 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2101267 |  |  | Indiana Department of Transportation | 2023-09-13
|  |  | 2101268 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101269 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101270 |  |  | Indiana Department of Transportation | 2022-03-09
|  |  | 2101271 |  |  | Louisville and Indiana Railroad Company | -339679.2083
|  |  | 2101272 |  | Burrell Appraisal Service, Inc. | Louisville and Indiana Railroad Company | -339679.2083
|  |  | 2101273 |  |  | Louisville and Indiana Railroad Company | -339679.2083
|  |  | 2101274 |  |  | Indiana Department of Transportation | 2020-09-02
|  |  | 2101275 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 2020-09-02
|  |  | 2101276 |  |  | Louisville and Indiana Railroad Company | -339679.2083
|  |  | 2101277 |  |  | Norfolk Southern Railway Co | -339679.2083
|  |  | 2101278 |  |  | Norfolk Southern Railway Co | -339679.2083
|  |  | 2101279 |  |  | Columbus | -339679.2083
|  |  | 2101280 |  | David B Patterson | Jonesville | -339679.2083
|  |  | 2101281 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101282 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 2022-07-13
|  |  | 2101283 |  |  | Indiana Department of Transportation | 2023-01-19
|  |  | 2101284 |  |  | Indiana Department of Transportation | 2023-10-12
|  |  | 2101285 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101286 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101287 |  |  | Indiana Department of Transportation | 2021-03-10
|  |  | 2101288 |  | ACMS Group, Inc. | Argos | 2025-01-15
|  |  | 2101289 |  |  | Indiana Department of Transportation | 2024-07-10
|  |  | 2101290 |  | DKA Associates, Inc. | Ingalls | 2026-07-08
|  |  | 2101291 |  | DKA Associates, Inc. | Ingalls | 2027-07-14
|  |  | 2101292 |  | DKA Associates, Inc. | Ingalls | 2027-07-14
|  |  | 2101293 |  | Casteel Real Estate | Indiana Department of Transportation | -339679.2083
|  |  | 2101294 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2101295 |  |  | Indiana Department of Transportation | 2022-12-07
|  |  | 2101296 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2101297 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101298 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101299 |  | Consolidated Test Company | Indiana Department of Transportation | 2021-02-10
|  |  | 2101300 |  | Active Environmental Services, Inc. | Bourbon | 2024-01-18
|  |  | 2101301 |  | CGI | Indiana Department of Transportation | 2021-10-14
|  |  | 2101302 |  |  | Indiana Department of Transportation | 2022-05-05
|  |  | 2101303 |  |  | Indiana Department of Transportation | 2021-08-11
|  |  | 2101304 |  | Dyer Environmental Services | Indiana Department of Transportation | 2021-02-10
|  |  | 2101305 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2101306 |  |  | Indiana Department of Transportation | 2021-02-10
|  |  | 2101307 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 2101308 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 2101309 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 2021-02-10
|  |  | 2101310 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101311 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101312 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101313 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101314 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101315 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101316 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101317 |  | Howard J. Barth & Associates, Inc. | Plymouth | 2025-03-12
|  |  | 2101318 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101319 |  |  | Indiana Department of Transportation | 2023-04-12
|  |  | 2101320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101321 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101322 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101323 |  | DCD Consulting LLC | Indiana Department of Transportation | -339679.2083
|  |  | 2101324 |  | Appraisal Office of Central Indiana | Indiana Department of Transportation | 2024-07-10
|  |  | 2101325 |  |  | Albion | 2022-05-31
|  |  | 2101326 |  |  | Allen County | 2022-05-31
|  |  | 2101327 |  | AAC Environmental Consulting, LLC | Anderson | 2022-05-31
|  |  | 2101328 |  | ABt SRBI | Angola | 2022-05-31
|  |  | 2101329 |  | ABt SRBI | Angola | 2022-05-31
|  |  | 2101330 |  | ACMS Group, Inc. | Argos | 2022-05-31
|  |  | 2101331 |  | AECOM Technical Services, Inc. | Ashley | 2022-05-31
|  |  | 2101332 |  | Quantum Spatial, Inc. | Auburn | 2022-05-31
|  |  | 2101333 |  | AES Services, Inc. | Avilla | 2022-05-31
|  |  | 2101334 |  | Wood Environment & Infrastructure Solutions, Inc. | Bargersville | 2022-05-31
|  |  | 2101335 |  |  | Bartholomew County | 2022-05-31
|  |  | 2101336 |  |  | Battle Ground | -339679.2083
|  |  | 2101337 |  | ASC Group, Inc. | Beech Grove | 2022-05-31
|  |  | 2101338 |  |  | Berne | 2022-05-31
|  |  | 2101339 |  | Absolute Title Services, LLC | Bloomington | 2022-05-31
|  |  | 2101340 |  |  | Boone County | -339679.2083
|  |  | 2101341 |  |  | Boswell | -339679.2083
|  |  | 2101342 |  |  | Boswell | -339679.2083
|  |  | 2101343 |  | Active Environmental Services, Inc. | Bourbon | 2022-05-31
|  |  | 2101344 |  | Active Environmental Services, Inc. | Bourbon | 2022-05-31
|  |  | 2101345 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2022-05-31
|  |  | 2101346 |  | Advanced Engineering Consultants, Ltd. | Bremen | 2022-05-31
|  |  | 2101347 |  | Advanced Engineering Services Inc. | Bristol | 2022-05-31
|  |  | 2101348 |  | Aerial Services, Inc. | Brooklyn | 2022-05-31
|  |  | 2101349 |  |  | Brookville | 2022-05-31
|  |  | 2101350 |  |  | Brown County | 2022-05-31
|  |  | 2101351 |  | American Commercial Title & Escrow | Burns Harbor | 2022-05-31
|  |  | 2101352 |  | American Engineers, Inc. | Butler | 2022-05-31
|  |  | 2101353 |  | American Resources Group, Ltd. | Cambridge City | 2022-05-31
|  |  | 2101354 |  | Another Test Company | Carmel | 2022-05-31
|  |  | 2101355 |  |  | Carthage | 2022-05-31
|  |  | 2101356 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2022-05-31
|  |  | 2101357 |  | Applied Pavement Technology, Inc. | Cedar Lake | 2022-05-31
|  |  | 2101358 |  | Appraisal Office of Central Indiana | Centerville | 2022-05-31
|  |  | 2101359 |  |  | Charlestown | 2022-05-31
|  |  | 2101360 |  |  | Chesterton | 2022-05-31
|  |  | 2101361 |  |  | Churubusco | 2022-05-31
|  |  | 2101362 |  |  | Clark County | 2022-05-31
|  |  | 2101363 |  |  | Clarks Hill | -339679.2083
|  |  | 2101364 |  |  | Clarksville | 2022-05-31
|  |  | 2101365 |  | Associated Appraisal Group, Inc. | Columbia City | 2022-05-31
|  |  | 2101366 |  | Associated Right-of-Way Services, Inc. | Columbus | 2022-05-31
|  |  | 2101367 |  | Wilcox Environmental Engineering, Inc. | Connersville | 2022-05-31
|  |  | 2101368 |  | B. L. A., Inc. | Corydon | 2022-05-31
|  |  | 2101369 |  |  | Crawford County | -339679.2083
|  |  | 2101370 |  |  | Crawford County | -339679.2083
|  |  | 2101371 |  |  | Crawfordsville | -339679.2083
|  |  | 2101372 |  | Baxter & Woodman, Inc. | Crown Point | 2022-05-31
|  |  | 2101373 |  | Baxter & Woodman, Inc. | Crown Point | 2022-05-31
|  |  | 2101374 |  |  | Daleville | 2022-05-31
|  |  | 2101375 |  |  | Danville | -339679.2083
|  |  | 2101376 |  |  | Daviess County | -339679.2083
|  |  | 2101377 |  |  | Dearborn County | 2022-05-31
|  |  | 2101378 |  | Bidinfo | Decatur | 2022-05-31
|  |  | 2101379 |  |  | Dekalb County | 2022-05-31
|  |  | 2101380 |  |  | Delaware County | 2022-05-31
|  |  | 2101381 |  |  | Delaware County | 2022-05-31
|  |  | 2101382 |  |  | Delaware County | 2022-05-31
|  |  | 2101383 |  |  | Dillsboro | 2022-05-31
|  |  | 2101384 |  |  | Dubois County | -339679.2083
|  |  | 2101385 |  | Booker Real Estate Services | Dune Acres | 2022-05-31
|  |  | 2101386 |  | Booker Real Estate Services | Dune Acres | 2022-05-31
|  |  | 2101387 |  | Boomerang Ventures, LLC | Dunkirk | 2022-05-31
|  |  | 2101388 |  | Brenner Design Incorporated | Dyer | 2021-05-31
|  |  | 2101389 |  |  | Economy | 2022-05-31
|  |  | 2101390 |  | Burrell Appraisal Service, Inc. | Edinburgh | 2022-05-31
|  |  | 2101391 |  |  | Elberfeld | -339679.2083
|  |  | 2101392 |  |  | Ellettsville | 2022-05-31
|  |  | 2101393 |  |  | Ellettsville | 2022-05-31
|  |  | 2101394 |  |  | Elnora | -339679.2083
|  |  | 2101395 |  | CKW Land Surveying, Inc. | Farmland | 2022-05-31
|  |  | 2101396 |  |  | Ferdinand | -339679.2083
|  |  | 2101397 |  | CPS Acquisitions, LLC | Fishers | 2022-05-31
|  |  | 2101398 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | 2022-05-31
|  |  | 2101399 |  |  | Fountain County | -339679.2083
|  |  | 2101400 |  |  | Frankfort | -339679.2083
|  |  | 2101401 |  | Casteel Real Estate | Franklin | 2022-05-31
|  |  | 2101402 |  |  | Franklin County | 2022-05-31
|  |  | 2101403 |  | Central Diving Contractors | Frankton | 2022-05-31
|  |  | 2101404 |  |  | Frankton | 2022-05-31
|  |  | 2101405 |  | Certified Engineering, Inc. | Fremont | -339679.2083
|  |  | 2101406 |  | Certified Engineering, Inc. | Fremont | 2022-05-31
|  |  | 2101407 |  |  | French Lick | -339679.2083
|  |  | 2101408 |  |  | Fulton County | 2022-05-31
|  |  | 2101409 |  | Cheri K. Lewis Engineers | Garrett | 2022-05-31
|  |  | 2101410 |  | Cheri K. Lewis Engineers | Garrett | 2022-05-31
|  |  | 2101411 |  | Christopher B. Burke Engineering, Ltd. | Gaston | 2022-05-31
|  |  | 2101412 |  |  | Grant County | 2022-05-31
|  |  | 2101413 |  |  | Greendale | 2022-05-31
|  |  | 2101414 |  |  | Greene County | -339679.2083
|  |  | 2101415 |  |  | Greene County | -339679.2083
|  |  | 2101416 |  |  | Greene County | -339679.2083
|  |  | 2101417 |  | Collier Transport Inc. | Greensburg | 2022-05-31
|  |  | 2101418 |  | Compliance Consulting Service, Inc. | Griffith | 2022-05-31
|  |  | 2101419 |  |  | Hamilton County | 2022-05-31
|  |  | 2101420 |  |  | Hamlet | 2022-05-31
|  |  | 2101421 |  | Consolidated Test Company | Hammond | 2022-05-31
|  |  | 2101422 |  |  | Hancock County | 2022-05-31
|  |  | 2101423 |  |  | Hardinsburg | -339679.2083
|  |  | 2101424 |  |  | Harmony | -339679.2083
|  |  | 2101425 |  | Continental Mapping Consultants, LLC | Hartford City | 2022-05-31
|  |  | 2101426 |  |  | Hillsboro | -339679.2083
|  |  | 2101427 |  | Courtland Title & Escrow, Inc. | Hobart | 2022-05-31
|  |  | 2101428 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2022-05-31
|  |  | 2101429 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2022-05-31
|  |  | 2101430 |  | Crawford, Murphy & Tilly, Inc. | Hope | 2022-05-31
|  |  | 2101431 |  |  | Huntingburg | -339679.2083
|  |  | 2101432 |  | D A Brown Engineering Consultants, Inc. | Huntington | 2022-05-31
|  |  | 2101433 |  |  | Hymera | -339679.2083
|  |  | 2101434 |  | DKA Associates, Inc. | Ingalls | 2022-05-31
|  |  | 2101435 |  |  | Jasper County | 2022-05-31
|  |  | 2101436 |  |  | Jefferson County | 2022-05-31
|  |  | 2101437 |  | Data Transfer Solutions, LLC | Jeffersonville | 2022-05-31
|  |  | 2101438 |  | Dave Helton & Associates, Inc. | Jonesboro | 2022-05-31
|  |  | 2101439 |  | Debbie L. Morris | Kendallville | 2022-05-31
|  |  | 2101440 |  |  | Kirklin | -339679.2083
|  |  | 2101441 |  | Dillabaugh, Inc. | Knightstown | 2022-05-31
|  |  | 2101442 |  | Dodd Title Corporation | Kokomo | 2022-05-31
|  |  | 2101443 |  |  | Kosciusko County | 2022-05-31
|  |  | 2101444 |  | Douglass Environmental Services, Inc. | La Porte | 2022-05-31
|  |  | 2101445 |  | Duesler Realty House | Lagrange | 2022-05-31
|  |  | 2101446 |  |  | Lake County | 2022-05-31
|  |  | 2101447 |  | Dummy Consulting Firm | Lake Station | 2022-05-31
|  |  | 2101448 |  | Dummy Consulting Firm Too | Lakeville | 2022-05-31
|  |  | 2101449 |  |  | LaPorte County | 2022-05-31
|  |  | 2101450 |  | Dyer Environmental Services | Lawrence | 2022-05-31
|  |  | 2101451 |  | Dyer Environmental Services | Lawrence | 2022-05-31
|  |  | 2101452 |  |  | Lawrence County | -339679.2083
|  |  | 2101453 |  | Dynasty Group, Inc. | Lawrenceburg | 2022-05-31
|  |  | 2101454 |  |  | Lebanon | -339679.2083
|  |  | 2101455 |  | EDP Consultants | Leo-Cedarville | 2022-05-31
|  |  | 2101456 |  | EFI Global, Inc. | Lewisville | 2022-05-31
|  |  | 2101457 |  | ERES International, Inc. | Ligonier | 2022-05-31
|  |  | 2101458 |  | Eco Logic, LLC | Logansport | 2022-05-31
|  |  | 2101459 |  | Eel River Abstract | Lynn | 2022-05-31
|  |  | 2101460 |  | Engineering Resources, Inc. | Madison | 2022-05-31
|  |  | 2101461 |  |  | Madison County | 2022-05-31
|  |  | 2101462 |  | ERES International, Inc. | Marion | 2022-05-31
|  |  | 2101463 |  | ERES International, Inc. | Marion | 2022-05-31
|  |  | 2101464 |  |  | Merrillville | 2022-05-31
|  |  | 2101465 |  |  | Miami County | -339679.2083
|  |  | 2101466 |  |  | Miami County | -339679.2083
|  |  | 2101467 |  | Farah and Sons, Inc. | Michigan City | 2022-05-31
|  |  | 2101468 |  | Farren Real Estate Services | Middlebury | 2022-05-31
|  |  | 2101469 |  | Feutz Contractors, Inc. | Middletown | 2022-05-31
|  |  | 2101470 |  |  | Milford (Kosciusko Co) | -339679.2083
|  |  | 2101471 |  | Flexible H.R. Solutions, LLC | Mishawaka | 2022-05-31
|  |  | 2101472 |  |  | Monroe County | 2022-05-31
|  |  | 2101473 |  |  | Monroe County | 2022-05-31
|  |  | 2101474 |  |  | Monroe County | 2022-05-31
|  |  | 2101475 |  |  | Monroe County | 2022-05-31
|  |  | 2101476 |  |  | Monroe County | 2022-05-31
|  |  | 2101477 |  |  | Monroe County | 2022-05-31
|  |  | 2101478 |  |  | Monroe County | 2022-05-31
|  |  | 2101479 |  |  | Montgomery County | -339679.2083
|  |  | 2101480 |  | Fugro Roadware, Inc. | Monticello | 2022-05-31
|  |  | 2101481 |  | G Herbert Pritchett Assoc., Inc. | Mooreland | 2022-05-31
|  |  | 2101482 |  |  | Moores Hill | 2022-05-31
|  |  | 2101483 |  | GAI Consultants, Inc. | Mooresville | 2022-05-31
|  |  | 2101484 |  |  | Mount Vernon | -339679.2083
|  |  | 2101485 |  |  | Mount Vernon | -339679.2083
|  |  | 2101486 |  |  | Mount Vernon | -339679.2083
|  |  | 2101487 |  |  | Mulberry | -339679.2083
|  |  | 2101488 |  | GS-IN P.C. | Muncie | 2022-05-31
|  |  | 2101489 |  |  | Munster | 2022-05-31
|  |  | 2101490 |  |  | Munster | 2022-05-31
|  |  | 2101491 |  | Gandhi and Associates, Inc. | Nappanee | 2022-05-31
|  |  | 2101492 |  | Garcia LE & Associates, L.L.C. | Nashville | 2022-05-31
|  |  | 2101493 |  | Garcia LE & Associates, L.L.C. | Nashville | 2022-05-31
|  |  | 2101494 |  | Gibson County Abstract & Title Co., Inc. | New Chicago | 2022-05-31
|  |  | 2101495 |  |  | New Haven | -339679.2083
|  |  | 2101496 |  | Greenman-Pedersen, Inc. | New Pekin | 2022-05-31
|  |  | 2101497 |  |  | Newburgh | -339679.2083
|  |  | 2101498 |  |  | Noble County | 2022-05-31
|  |  | 2101499 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2022-05-31
|  |  | 2101500 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2022-05-31
|  |  | 2101501 |  | H. Stewart Kline & Associates, Inc. | Noblesville | 2022-05-31
|  |  | 2101502 |  | H.R. Gray | North Judson | 2022-05-31
|  |  | 2101503 |  |  | North Vernon | 2022-05-31
|  |  | 2101504 |  | Haas & Associates, L.L.C. | Oldenburg | 2022-05-31
|  |  | 2101505 |  |  | Orleans | -339679.2083
|  |  | 2101506 |  | Hanson Professional Services, Inc. | Osceola | 2022-05-31
|  |  | 2101507 |  | Hardcore Concrete Sawing Inc. | Osgood | 2022-05-31
|  |  | 2101508 |  |  | Ossian | -339679.2083
|  |  | 2101509 |  |  | Paoli | -339679.2083
|  |  | 2101510 |  |  | Paoli | -339679.2083
|  |  | 2101511 |  |  | Parke County | -339679.2083
|  |  | 2101512 |  | Heritage Appraisal Service | Parker City | 2022-05-31
|  |  | 2101513 |  |  | Patoka | -339679.2083
|  |  | 2101514 |  | Hey and Associates, Inc. | Pendleton | 2022-05-31
|  |  | 2101515 |  | Hey and Associates, Inc. | Pendleton | 2022-05-31
|  |  | 2101516 |  | Hey and Associates, Inc. | Pendleton | 2022-05-31
|  |  | 2101517 |  |  | Peru | -339679.2083
|  |  | 2101518 |  |  | Petersburg | -339679.2083
|  |  | 2101519 |  | Home Guide Realty Services | Pierceton | 2022-05-31
|  |  | 2101520 |  |  | Pike County | -339679.2083
|  |  | 2101521 |  |  | Pike County | -339679.2083
|  |  | 2101522 |  |  | Pike County | -339679.2083
|  |  | 2101523 |  |  | Pike County | -339679.2083
|  |  | 2101524 |  |  | Pike County | -339679.2083
|  |  | 2101525 |  |  | Pittsboro | -339679.2083
|  |  | 2101526 |  |  | Plainfield | -339679.2083
|  |  | 2101527 |  | Hy-Tech Response, Inc. | Porter | 2022-05-31
|  |  | 2101528 |  | Hydrogeology, Inc. | Portland | 2022-05-31
|  |  | 2101529 |  | IHS Global Insight | Princes Lakes | 2022-05-31
|  |  | 2101530 |  | Indiana Appraisal Group, Inc. | Richmond | 2022-05-31
|  |  | 2101531 |  | Indiana Search Technologies | Rising Sun | 2022-05-31
|  |  | 2101532 |  |  | Roachdale | -339679.2083
|  |  | 2101533 |  |  | Rockport | -339679.2083
|  |  | 2101534 |  | InspectTech Systems, Inc. | Rome City | 2022-05-31
|  |  | 2101535 |  |  | Rush County | 2022-05-31
|  |  | 2101536 |  |  | Rush County | 2022-05-31
|  |  | 2101537 |  |  | Rush County | 2022-05-31
|  |  | 2101538 |  |  | Rush County | 2022-05-31
|  |  | 2101539 |  |  | Rush County | 2022-05-31
|  |  | 2101540 |  |  | Rush County | 2022-05-31
|  |  | 2101541 |  |  | Rush County | 2022-05-31
|  |  | 2101542 |  |  | Rush County | 2022-05-31
|  |  | 2101543 |  |  | Rush County | 2022-05-31
|  |  | 2101544 |  |  | Rush County | 2022-05-31
|  |  | 2101545 |  |  | Rush County | 2022-05-31
|  |  | 2101546 |  |  | Rush County | 2022-05-31
|  |  | 2101547 |  |  | Rush County | 2022-05-31
|  |  | 2101548 |  |  | Rush County | 2022-05-31
|  |  | 2101549 |  |  | Rush County | 2022-05-31
|  |  | 2101550 |  |  | Rush County | 2022-05-31
|  |  | 2101551 |  |  | Rush County | 2022-05-31
|  |  | 2101552 |  |  | Rush County | 2022-05-31
|  |  | 2101553 |  |  | Rush County | 2022-05-31
|  |  | 2101554 |  |  | Rush County | 2022-05-31
|  |  | 2101555 |  |  | Rush County | 2022-05-31
|  |  | 2101556 |  |  | Rush County | 2022-05-31
|  |  | 2101557 |  |  | Rush County | 2022-05-31
|  |  | 2101558 |  |  | Rush County | 2022-05-31
|  |  | 2101559 |  |  | Rush County | 2022-05-31
|  |  | 2101560 |  | J. Williams Appraisal Group, LLC | Rushville | 2022-05-31
|  |  | 2101561 |  | J. Williams Appraisal Group, LLC | Rushville | 2022-05-31
|  |  | 2101562 |  | JCI Bridge Group, Inc. | Salem | 2022-05-31
|  |  | 2101563 |  | Jackie S. Dodd, Attorney at Law | Schererville | 2022-05-31
|  |  | 2101564 |  |  | Scott County | 2022-05-31
|  |  | 2101565 |  |  | Scott County | 2022-05-31
|  |  | 2101566 |  | Jacobs Pannicke Architects, Inc. | Sellersburg | 2022-05-31
|  |  | 2101567 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2022-05-31
|  |  | 2101568 |  | Janssen & Spaans Engineering, Inc. | Seymour | 2022-05-31
|  |  | 2101569 |  | Jean Stewart, LLC | Sharpsville | 2022-05-31
|  |  | 2101570 |  |  | Shelby County | 2022-05-31
|  |  | 2101571 |  | Jeffrey S. Juday | Shelbyville | 2022-05-31
|  |  | 2101572 |  |  | Shipshewana | -339679.2083
|  |  | 2101573 |  | John G. Brinkworth, Inc. | Shirley | 2022-05-31
|  |  | 2101574 |  |  | Shoals | -339679.2083
|  |  | 2101575 |  | Jones & Henry Engineers, Ltd. | Sidney | 2022-05-31
|  |  | 2101576 |  |  | South Bend | 2022-05-31
|  |  | 2101577 |  |  | Spencer County | -339679.2083
|  |  | 2101578 |  |  | Spencer County | -339679.2083
|  |  | 2101579 |  |  | Spencer County | -339679.2083
|  |  | 2101580 |  |  | Spencer County | -339679.2083
|  |  | 2101581 |  | KPFF, Inc. | Springport | 2022-05-31
|  |  | 2101582 |  |  | St. Joe | -339679.2083
|  |  | 2101583 |  |  | Starke County | 2022-05-31
|  |  | 2101584 |  | Knight E/A, Inc. | Sulphur Springs | 2022-05-31
|  |  | 2101585 |  |  | Switzerland County | 2022-05-31
|  |  | 2101586 |  |  | Switzerland County | 2022-05-31
|  |  | 2101587 |  |  | Tell City | -339679.2083
|  |  | 2101588 |  |  | Terre Haute | -339679.2083
|  |  | 2101589 |  |  | Tippecanoe County | -339679.2083
|  |  | 2101590 |  | Land Construction Corp | Tipton | 2022-05-31
|  |  | 2101591 |  |  | Tipton County | 2022-05-31
|  |  | 2101592 |  |  | Topeka | -339679.2083
|  |  | 2101593 |  |  | Trafalgar | 2022-05-31
|  |  | 2101594 |  |  | Upland | 2022-05-31
|  |  | 2101595 |  | Lee & Ryan Environmental Consulting, Inc. | Utica | 2022-05-31
|  |  | 2101596 |  |  | Vanderburgh County | -339679.2083
|  |  | 2101597 |  | Loftus Engineering, Inc. | Vernon | 2022-05-31
|  |  | 2101598 |  |  | Vigo County | -339679.2083
|  |  | 2101599 |  |  | Wabash County | 2022-05-31
|  |  | 2101600 |  |  | Wakarusa | -339679.2083
|  |  | 2101601 |  | MCCARTIN - ASSOCIATES | Walton | 2022-05-31
|  |  | 2101602 |  |  | Warren County | -339679.2083
|  |  | 2101603 |  |  | Warrick County | -339679.2083
|  |  | 2101604 |  |  | Wayne County | 2022-05-31
|  |  | 2101605 |  |  | Wayne County | 2022-05-31
|  |  | 2101606 |  |  | Waynetown | -339679.2083
|  |  | 2101607 |  |  | Wells County | -339679.2083
|  |  | 2101608 |  |  | West Baden Springs | -339679.2083
|  |  | 2101609 |  |  | West Lebanon | -339679.2083
|  |  | 2101610 |  |  | Whitestown | -339679.2083
|  |  | 2101611 |  | Matt L. Nepote, MAI | Whiting | 2022-05-31
|  |  | 2101612 |  |  | Williamsport | -339679.2083
|  |  | 2101613 |  | Alt & Witzig Engineering, Inc. | Bunker Hill | 2022-05-31
|  |  | 2101614 |  |  | Indiana Department of Transportation | 2023-05-31
|  |  | 2101615 |  |  | Indiana Department of Transportation | 2024-05-31
|  |  | 2101616 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101617 |  |  | Indiana Department of Transportation | 2023-07-12
|  |  | 2101618 |  |  | Indiana Department of Transportation | 2025-05-31
|  |  | 2101619 |  |  | Indiana Department of Transportation | 2022-02-09
|  |  | 2101620 |  |  | Johnson County | 2022-05-31
|  |  | 2101621 |  | HLRD | Indiana Department of Transportation | 2023-12-13
|  |  | 2101622 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101623 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101624 |  |  | Indiana Department of Transportation | 2023-12-13
|  |  | 2101625 |  | DCD Consulting LLC | Indiana Department of Transportation | 2020-05-05
|  |  | 2101626 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2101627 |  |  | Indiana Department of Transportation | 2027-05-31
|  |  | 2101628 |  | Another Test Company | Indiana Department of Transportation | 2020-08-05
|  |  | 2101629 |  |  | Porter County | -339679.2083
|  |  | 2101630 |  |  | Allen County | -339679.2083
|  |  | 2101631 |  | Civil Inspection Services, LLC | Goshen | 2024-07-10
|  |  | 2101632 |  |  | Indiana Department of Transportation | 2020-07-08
|  |  | 2101633 |  | CPS Acquisitions, LLC | Fishers | 2023-10-12
|  |  | 2101634 |  | D & D Consulting Services, Inc. | Huntertown | 2026-10-07
|  |  | 2101635 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101636 |  |  | Indiana Department of Transportation | 2022-04-06
|  |  | 2101637 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 2101638 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 2101639 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101640 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101641 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101642 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 2101643 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101644 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101645 |  |  | Indiana Department of Transportation | 2020-05-07
|  |  | 2101646 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 6304431 |  | CGI |  | 1986-05-13
|  |  | 6304432 |  | CGI |  | 1986-06-10
|  |  | 6304433 |  | CGI |  | 1986-06-10
|  |  | 6304434 |  | CGI |  | 1987-06-02
|  |  | 6304435 |  | CGI |  | 1984-09-18
|  |  | 6304436 |  | CGI |  | 1985-03-19
|  |  | 6304437 |  | CGI |  | 1985-09-24
|  |  | 6304438 |  | CGI |  | 1984-03-20
|  |  | 6304439 |  | CGI |  | 1983-05-24
|  |  | 6304443 |  |  |  | 1983-08-23
|  |  | 6304444 |  |  |  | 1983-08-23
|  |  | 6304445 |  |  |  | 1983-08-23
|  |  | 6304446 |  |  |  | 1985-03-19
|  |  | 6304447 |  | CGI |  | 1985-03-19
|  |  | 6304448 |  |  |  | 1985-03-19
|  |  | 6304449 |  | CGI |  | 1987-06-02
|  |  | 6304451 |  | CGI | Indiana Department of Transportation | 1986-05-13
|  |  | 6304452 |  | CGI |  | 1986-05-13
|  |  | 6501460 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 6501461 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 6538110 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 6538120 |  |  |  | 1987-05-06
|  |  | 6538130 |  |  |  | 1987-05-06
|  |  | 6538140 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 6538150 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 6538151 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 6538152 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 6538160 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 6538170 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 6801880 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 6801881 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 7000120 |  |  |  | 1985-03-19
|  |  | 7000121 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 7000310 |  |  |  | 1983-11-15
|  |  | 7001080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7001230 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 7001370 |  |  |  | 1983-11-15
|  |  | 7001750 | Perry |  | Indiana Department of Transportation | 2001-10-16 | CE
CN
ROW
UT
|  |  | 700175A |  |  | Indiana Department of Transportation | 1999-10-13
|  |  | 700175C |  |  | Indiana Department of Transportation | 2000-02-22
|  |  | 7002690 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 7002700 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7020690 |  |  |  | 1983-11-15
|  |  | 7020790 |  |  |  | 1983-11-15
|  |  | 7021090 |  |  |  | 1983-10-25
|  |  | 7029250 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 7029260 |  | John Milner Associates, Architects, Archeologists, Planners, | Indiana Department of Transportation | -339679.2083
|  |  | 7029270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7029280 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7029290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7029300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7029310 |  | EcoTec, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 7101790 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7102178 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 710217B |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 710217C |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-02-09
|  |  | 7102231 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 7102232 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 7102233 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 7102234 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 7102235 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 7102330 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 7102331 |  |  | Indiana Department of Transportation | 1991-02-19
|  |  | 7103780 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7112680 |  |  |  | 1981-01-20
|  |  | 7115150 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7138190 |  |  | Indiana Department of Transportation | 1990-08-02
|  |  | 7138191 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 7138192 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 7138193 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 7138194 |  |  | Indiana Department of Transportation | 1990-08-02
|  |  | 7200070 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7200141 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 7200142 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 7200150 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7200320 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7200321 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7200322 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7200401 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7200402 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7200403 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7200430 |  |  | Indiana Department of Transportation | 1998-10-06
|  |  | 720043A |  |  | Indiana Department of Transportation | 1995-08-15
|  |  | 7200672 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1987-06-02
|  |  | 7200673 |  |  | Indiana Department of Transportation | 1988-01-12
|  |  | 7200674 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7200675 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7200676 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7200677 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7200678 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7200679 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 720067A |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 720067B |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 720067C |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 720067E |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 7200681 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 7200682 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 7200683 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 7200684 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 7200685 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 7200686 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 7201130 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 7201140 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7201150 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7201210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7201900 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7202174 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7202175 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7202176 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7202177 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 720217A |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7202600 |  | Consolidated Test Company |  | -339679.2083
|  |  | 720260A |  | Consolidated Test Company | Indiana Department of Transportation | 1995-08-15
|  |  | 7202760 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7202930 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7206530 |  | CGI | Indiana Department of Transportation | 1985-03-19
|  |  | 7206531 |  | CGI | Indiana Department of Transportation | 1985-03-19
|  |  | 7207470 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7207800 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1985-03-19
|  |  | 7208180 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1996-02-20 | CE
CN
|  |  | 7208190 | Porter | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1996-02-20 | CE
CN
|  |  | 7208450 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 7208830 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 7209070 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7211390 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 7211980 |  |  | Indiana Department of Transportation | 1984-09-18
|  |  | 7211981 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1983-07-26
|  |  | 7212000 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1984-09-18
|  |  | 7212010 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-07-26
|  |  | 7212020 |  |  | Indiana Department of Transportation | 1984-09-18
|  |  | 7212270 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7213580 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7213800 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7213810 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 7241440 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 7300110 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7300111 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1993-07-20
|  |  | 7300360 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7300361 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1993-07-20
|  |  | 7300380 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7300381 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 7300590 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 7301400 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1990-06-05
|  |  | 7301402 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 7301403 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 7301404 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 7302253 | Cass |  | Indiana Department of Transportation | 1997-12-16 | CN
PE
ROW
|  |  | 7302270 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7302311 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 7302471 | Miami |  | Indiana Department of Transportation | 1998-05-12 | CN
ROW
|  |  | 7302481 | Cass |  | Indiana Department of Transportation | 1998-05-12 | CE
CN
ROW
|  |  | 7303840 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 7304020 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 7304231 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7304232 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 7304233 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 7304234 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 7304260 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7304261 |  |  | Indiana Department of Transportation | 1990-11-20
|  |  | 7304270 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7304290 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | 1982-02-23
|  |  | 7304620 | Madison | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1996-01-23 | CE
CN
|  |  | 7304700 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1985-09-17
|  |  | 7304810 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7304840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7304842 |  |  | Indiana Department of Transportation | 1987-09-09
|  |  | 7304850 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7304860 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 7304940 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7304960 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7305030 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1988-11-15
|  |  | 7305080 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-12-14
|  |  | 7305180 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 7305580 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7305581 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7313340 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7331191 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7338200 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 7338201 |  |  | Indiana Department of Transportation | 1991-02-19
|  |  | 7338202 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 7338203 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 7338204 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 7338205 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 7338206 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 7338207 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 7338208 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 7338209 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 733820A |  |  | Indiana Department of Transportation | 1990-08-02
|  |  | 733820B |  |  | Indiana Department of Transportation | 1990-08-02
|  |  | 7400450 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 7400800 |  | ERES International, Inc. | Indiana Department of Transportation | 1983-05-24
|  |  | 7401121 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1990-06-14
|  |  | 7401122 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-07-28
|  |  | 7401123 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 7401125 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 7401126 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 7401127 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 7401128 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 7401129 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 740112B |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 740112C |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 740112D |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 740112E |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 740112F |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 740112G |  |  | Indiana Department of Transportation | 1993-10-19
|  |  | 740112H |  |  | Indiana Department of Transportation | 1993-10-19
|  |  | 740112J |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 740112K |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 740112L |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1994-05-17
|  |  | 740112S |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1989-09-19
|  |  | 7401500 | Lake |  | Indiana Department of Transportation | 1984-01-17 | PE
ROW
|  |  | 7401501 | Lake | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 2008-05-14 | PE
ROW
|  |  | 7401510 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 7401520 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1982-06-15
|  |  | 7401960 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 7402172 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7402173 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7404010 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 7404650 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1983-06-21
|  |  | 7404800 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1989-01-17
|  |  | 7404930 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1983-06-21
|  |  | 7404931 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1983-06-21
|  |  | 7405110 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 7405150 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 7405200 |  |  | Indiana Department of Transportation | 1982-12-14
|  |  | 7405310 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1990-02-06
|  |  | 7405340 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 7412240 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7415171 |  |  | Indiana Department of Transportation | 1982-07-20
|  |  | 742575L |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 7438500 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7444681 |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 7444682 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 7444683 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7444684 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 7444685 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 7444686 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 7444687 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 744468A |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 7444690 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 7444691 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7444692 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7444693 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7444694 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 7444695 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 7444700 |  |  | Indiana Department of Transportation | 1987-08-04
|  |  | 7444701 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 7444702 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 7444703 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 7444704 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 7444705 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 7444706 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 7444707 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 7444708 |  |  | Indiana Department of Transportation | 1987-08-04
|  |  | 7444709 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 7500730 |  |  | Indiana Department of Transportation | 1980-09-16
|  |  | 7500740 |  |  | Indiana Department of Transportation | 1980-09-16
|  |  | 7501440 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1981-10-27
|  |  | 7501450 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 7501770 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 7502630 |  |  | Indiana Department of Transportation | 1981-02-24
|  |  | 7503520 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 7503550 |  |  |  | -339679.2083
|  |  | 7505130 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 7505190 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 7507550 |  |  |  | 1979-11-20
|  |  | 7510950 |  |  |  | -339679.2083
|  |  | 7512420 |  | Collier Transport Inc. | Indiana Department of Transportation | 1981-12-15
|  |  | 7512670 |  |  |  | -339679.2083
|  |  | 7513140 |  |  |  | -339679.2083
|  |  | 7514720 |  |  |  | -339679.2083
|  |  | 7515590 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1986-01-14
|  |  | 7515620 |  | CE Solutions, Inc. | Indiana Department of Transportation | 1985-02-19
|  |  | 7515630 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7515670 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 7515750 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1983-06-21
|  |  | 7515820 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7515880 |  | ABt SRBI | Indiana Department of Transportation | 1992-11-10
|  |  | 7515940 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 1983-03-29
|  |  | 7516100 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7516160 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7516210 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 7516280 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7516300 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7516420 | Lake | Dummy Consulting Firm | Indiana Department of Transportation | 1997-08-12 | CE
CN
|  |  | 7516430 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 7516460 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1997-08-12
|  |  | 7516620 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7516630 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7516770 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7516920 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7517280 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 7517310 |  |  | Indiana Department of Transportation | 1982-07-20
|  |  | 7517430 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7518540 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7519290 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 7528410 |  |  |  | -339679.2083
|  |  | 7528440 |  |  |  | -339679.2083
|  |  | 7600160 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1983-05-24
|  |  | 7600190 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7600470 |  |  |  | 1980-10-21
|  |  | 7600820 |  |  |  | 1980-01-07
|  |  | 7601430 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 1993-03-16
|  |  | 7601660 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 7601760 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-09-16
|  |  | 7601780 |  |  | Indiana Department of Transportation | 1981-02-11
|  |  | 7602000 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 7602010 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7602240 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 1983-03-29
|  |  | 7602420 | Adams | Bidinfo | Indiana Department of Transportation | 1998-09-10 | CE
CN
PE
ROW
|  |  |  | Franklin | Bidinfo | Indiana Department of Transportation | 1998-09-10 | CN
|  |  | 760242A |  | Bidinfo | Indiana Department of Transportation | 1996-12-17
|  |  | 760242C |  | Bidinfo | Indiana Department of Transportation | 1997-08-12
|  |  | 760242E |  | Bidinfo | Indiana Department of Transportation | 1998-03-10
|  |  | 7602880 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7603070 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 7603080 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 7603120 |  |  | Indiana Department of Transportation | 1982-01-26
|  |  | 7603240 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7603260 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7603270 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7603290 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 7603291 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 7603400 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 7603470 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7603480 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7603820 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7603850 |  |  | Indiana Department of Transportation | 1981-05-19
|  |  | 7604310 |  |  | Indiana Department of Transportation | 1980-07-15
|  |  | 7604370 |  |  |  | 1978-03-06
|  |  | 7604490 |  | DCD Consulting LLC | Indiana Department of Transportation | 1980-03-18
|  |  | 7604680 |  |  | Indiana Department of Transportation | 1982-12-14
|  |  | 7605250 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7605500 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7605530 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 7606080 |  |  | Indiana Department of Transportation | 1982-01-26
|  |  | 7606110 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7606140 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 7606150 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 7606170 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7606340 |  |  |  | 1983-10-25
|  |  | 7606640 |  |  |  | -339679.2083
|  |  | 7606820 |  |  |  | 1981-06-23
|  |  | 7606900 | Knox |  | Vincennes | -339679.2083 | PE
|  |  | 7607420 |  |  |  | 1979-07-24
|  |  | 7607530 |  |  |  | 1982-01-26
|  |  | 7607730 |  |  |  | -339679.2083
|  |  | 7607920 |  |  |  | 1981-01-20
|  |  | 7608130 |  |  |  | -339679.2083
|  |  | 7608700 |  |  |  | 1984-07-17
|  |  | 7608730 |  |  |  | -339679.2083
|  |  | 7609290 |  |  |  | 1984-03-20
|  |  | 7609510 |  |  |  | 1983-04-26
|  |  | 7609570 |  |  |  | 1981-03-24
|  |  | 7609991 |  |  |  | -339679.2083
|  |  | 7609992 |  |  |  | 1987-09-09
|  |  | 7609993 |  |  |  | 1981-11-17
|  |  | 7610340 |  |  | Union County | -339679.2083
|  |  | 7610360 |  |  |  | 1980-04-15
|  |  | 7610470 |  |  | Warrick County | -339679.2083
|  |  | 7610520 |  |  |  | 1980-11-18
|  |  | 7610540 |  |  |  | -339679.2083
|  |  | 7610570 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7610960 |  |  |  | 1982-11-16
|  |  | 7611300 |  |  |  | -339679.2083
|  |  | 7611860 |  |  |  | -339679.2083
|  |  | 7612320 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 7613070 |  |  | Putnam County | -339679.2083
|  |  | 7613080 |  |  |  | 1987-02-03
|  |  | 7613100 |  |  | Madison County | -339679.2083
|  |  | 7613970 |  |  |  | -339679.2083
|  |  | 7613990 |  |  |  | -339679.2083
|  |  | 7614150 |  |  |  | 1982-06-15
|  |  | 7614330 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7615170 |  |  | Indiana Department of Transportation | 1980-05-13
|  |  | 7615180 |  |  |  | 1983-01-18
|  |  | 7615181 |  |  |  | 1983-05-24
|  |  | 7615182 |  |  |  | 1983-07-26
|  |  | 7615300 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7615490 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 7615540 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 7615660 |  |  | Indiana Department of Transportation | 1981-02-24
|  |  | 7615760 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7616030 |  |  |  | 1980-05-13
|  |  | 7616290 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7616310 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7616940 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 7617150 |  |  |  | -339679.2083
|  |  | 7617250 |  |  |  | 1982-04-20
|  |  | 7617700 |  | Alfred Benesch & Company | Indiana Department of Transportation | 1982-04-20
|  |  | 7617830 |  |  |  | 1981-09-22
|  |  | 7617950 |  | Collier Transport Inc. | Indiana Department of Transportation | 1980-09-16
|  |  | 7617960 |  | Collier Transport Inc. | Indiana Department of Transportation | 1980-09-16
|  |  | 7617980 |  |  | Indiana Department of Transportation | 1980-09-16
|  |  | 7618080 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 7621410 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 7628320 |  |  |  | 1983-10-25
|  |  | 7634180 |  |  |  | 1984-08-21
|  |  | 7634420 | Lake | Brenner Design Incorporated | Dyer | 2003-09-16 | CE
CN
PE
RR
|  |  | 7634421 | Lake | Brenner Design Incorporated | Dyer | 2000-10-17 | CE
CN
|  |  | 7634422 | Lake | Brenner Design Incorporated | Dyer | 2003-09-16 | CE
CN
RR
|  |  | 7634423 | Lake | Brenner Design Incorporated | Dyer | 2003-09-16 | CE
CN
RR
|  |  | 7634424 |  | Brenner Design Incorporated | Dyer | 1999-06-15
|  |  | 7634425 | Lake | Brenner Design Incorporated | Dyer | 2000-10-17 | CE
CN
PE
|  |  | 7634450 |  |  |  | 1987-06-02
|  |  | 7634740 |  |  |  | 1978-05-23
|  |  | 7634900 |  |  |  | -339679.2083
|  |  | 7634910 |  |  |  | -339679.2083
|  |  | 7639100 |  |  |  | -339679.2083
|  |  | 7685725 |  | DuSABLE, Inc. |  | 1994-07-19
|  |  | 7700030 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7700130 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7700180 |  |  |  | 1981-02-24
|  |  | 7700260 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7700340 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7700420 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 7700490 |  |  |  | -339679.2083
|  |  | 7700520 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 7700560 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7700580 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7700600 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7700750 |  | M-E Companies, Inc. | Indiana Department of Transportation | 1982-03-23
|  |  | 7700770 |  |  |  | -339679.2083
|  |  | 7700790 |  | Land Construction Corp | Indiana Department of Transportation | 1985-11-19
|  |  | 7700810 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 1982-03-23
|  |  | 7700830 |  |  |  | -339679.2083
|  |  | 7700920 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7700970 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7701940 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 7701980 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7702140 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7702150 |  | Applied Pavement Technology, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 7702220 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7702300 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1982-02-23
|  |  | 7702601 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1983-01-18
|  |  | 7702820 |  |  |  | 1981-04-21
|  |  | 7703030 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 1984-12-18
|  |  | 7703200 | Harrison |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
UT
|  |  |  | Washington |  | Indiana Department of Transportation | 2006-02-15 | CE
CN
PE
ROW
UT
|  |  | 7703380 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7703440 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7703630 |  |  |  | -339679.2083
|  |  | 7703660 |  |  |  | -339679.2083
|  |  | 7703680 |  |  |  | -339679.2083
|  |  | 7703700 |  |  | Indiana Department of Transportation | 1982-01-26
|  |  | 7703800 |  |  |  | -339679.2083
|  |  | 7703810 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7703880 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1990-04-17
|  |  | 7703881 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 7703890 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1990-04-17
|  |  | 7704180 |  | Bidinfo |  | -339679.2083
|  |  | 7704300 |  |  |  | -339679.2083
|  |  | 7704330 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 7704410 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1983-11-15
|  |  | 7704450 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1989-09-19
|  |  | 7704520 |  | CGI | Indiana Department of Transportation | 1985-05-21
|  |  | 7704530 |  | CGI | Indiana Department of Transportation | 1985-11-19
|  |  | 7704880 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 7705050 | Monroe |  | Indiana Department of Transportation | 1996-03-19 | RR
|  |  | 7705230 |  |  |  | -339679.2083
|  |  | 7705260 |  |  |  | -339679.2083
|  |  | 7705280 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7705320 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7705330 |  |  |  | -339679.2083
|  |  | 7705410 |  |  |  | -339679.2083
|  |  | 7705440 |  |  |  | -339679.2083
|  |  | 7705460 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7705470 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 7705480 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7705610 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1985-04-16
|  |  | 7705620 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7705700 |  |  |  | -339679.2083
|  |  | 7705730 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7705800 |  |  |  | -339679.2083
|  |  | 7705810 |  |  |  | -339679.2083
|  |  | 7705820 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 7705850 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7705940 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7705980 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7705990 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1986-06-10
|  |  | 7706000 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7706290 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 7706300 |  |  |  | -339679.2083
|  |  | 7706310 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 7706320 |  |  | Indiana Department of Transportation | 1997-02-11
|  |  | 7706330 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7706380 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 7706430 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7706480 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7706500 |  | CGI | Indiana Department of Transportation | 1987-06-02
|  |  | 7706520 |  |  | Muncie | -339679.2083
|  |  | 7706550 |  |  |  | -339679.2083
|  |  | 7707820 |  |  |  | 1982-06-15
|  |  | 7707840 |  |  |  | 1981-01-20
|  |  | 7707930 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7708070 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7708300 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7708360 |  |  |  | 1982-06-15
|  |  | 7708420 |  |  |  | 1982-06-15
|  |  | 7708470 |  |  |  | 1982-06-15
|  |  | 7708590 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7708600 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7708610 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7708640 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7708650 |  | Compliance Consulting Service, Inc. | Indiana Department of Transportation | 1983-01-18
|  |  | 7708690 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 7708710 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 7708810 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7708980 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7709010 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 7709020 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7709040 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7709050 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 7709061 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 7709110 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 7709111 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 7709120 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7709130 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7709160 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7709190 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 7709191 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 7709192 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 7709210 |  |  |  | -339679.2083
|  |  | 7709260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7709330 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1984-02-14
|  |  | 7709370 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7709380 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7709390 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7709430 |  |  |  | -339679.2083
|  |  | 7709480 |  |  |  | -339679.2083
|  |  | 7709520 |  |  |  | -339679.2083
|  |  | 7709540 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7709600 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7709790 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 7709800 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 7709810 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 7709830 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7709840 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 7709970 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7709980 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7710170 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7710190 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7710240 |  |  |  | 1983-06-21
|  |  | 7710241 |  |  |  | 1983-06-21
|  |  | 7710250 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 7710350 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 7710420 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7710450 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7710510 |  |  |  | 1980-11-18
|  |  | 7710591 |  |  |  | 1979-11-20
|  |  | 7710640 |  |  |  | 1980-01-15
|  |  | 7710650 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7710660 |  |  | Indiana Department of Transportation | 1995-04-04
|  |  | 7710700 | Porter | Leitner and Associates, Inc. | Valparaiso | -339679.2083 | RR
|  |  | 7710710 |  |  |  | -339679.2083
|  |  | 7710750 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7710760 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7710770 |  |  |  | -339679.2083
|  |  | 7710780 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7710790 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7710800 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7710820 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 7711000 |  |  |  | -339679.2083
|  |  | 7711170 |  |  |  | -339679.2083
|  |  | 7711190 |  |  |  | -339679.2083
|  |  | 7711210 |  |  |  | -339679.2083
|  |  | 7711220 |  |  |  | -339679.2083
|  |  | 7711280 |  |  |  | -339679.2083
|  |  | 7711360 |  |  |  | -339679.2083
|  |  | 7711370 |  |  |  | -339679.2083
|  |  | 7711400 |  |  |  | -339679.2083
|  |  | 7711410 |  |  |  | -339679.2083
|  |  | 7711420 |  |  |  | -339679.2083
|  |  | 7711620 |  |  |  | 1988-12-13
|  |  | 7711660 |  |  |  | -339679.2083
|  |  | 7711710 |  |  |  | 1985-06-25
|  |  | 7711730 |  |  |  | -339679.2083
|  |  | 7711750 |  |  |  | -339679.2083
|  |  | 7711820 |  |  |  | 1980-03-18
|  |  | 7711880 |  |  |  | 1981-09-22
|  |  | 7711920 |  |  |  | 1980-09-16
|  |  | 7711921 |  |  |  | 1981-06-23
|  |  | 7712530 |  |  |  | 1981-01-20
|  |  | 7712580 |  |  |  | 1981-02-24
|  |  | 7712590 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 7712730 | Lake |  | Lake County | -339679.2083 | PE
|  |  | 7712890 |  |  |  | 1983-08-23
|  |  | 7713010 |  |  | Putnam County | -339679.2083
|  |  | 7713030 |  |  |  | -339679.2083
|  |  | 7713040 |  |  |  | -339679.2083
|  |  | 7713220 |  |  |  | -339679.2083
|  |  | 7713250 |  |  |  | 1986-08-19
|  |  | 7713260 |  |  |  | 1988-06-14
|  |  | 7713270 |  |  |  | 1988-06-14
|  |  | 7713400 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7713420 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7713430 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7713450 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 7714030 |  |  |  | 1985-02-19
|  |  | 7714140 |  |  | Indianapolis | -339679.2083
|  |  | 7714260 |  |  |  | 1983-05-24
|  |  | 7714340 |  |  |  | 1979-11-20
|  |  | 7714800 |  |  |  | -339679.2083
|  |  | 7714820 |  |  | Sullivan County | -339679.2083
|  |  | 7714890 |  |  |  | -339679.2083
|  |  | 7715000 |  |  |  | -339679.2083
|  |  | 7715290 |  |  |  | -339679.2083
|  |  | 7715430 |  |  | Indiana Department of Transportation | 1981-01-20
|  |  | 7715700 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 7715720 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 7715770 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1983-05-24
|  |  | 7715810 |  |  |  | 1982-06-15
|  |  | 7715890 |  |  |  | 1991-03-13
|  |  | 7715970 |  |  | Hancock County | -339679.2083
|  |  | 7716020 |  |  |  | -339679.2083
|  |  | 7716040 |  |  | Hancock County | -339679.2083
|  |  | 7716150 |  |  | Hancock County | -339679.2083
|  |  | 7716170 |  |  |  | 1989-02-14
|  |  | 7716200 |  |  | Indiana Department of Transportation | 1983-05-20
|  |  | 7716320 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7716360 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7716710 |  |  |  | -339679.2083
|  |  | 7716910 |  |  |  | -339679.2083
|  |  | 7717020 |  |  |  | -339679.2083
|  |  | 7717090 |  | C Blair Enterprises, Inc. | Elkhart County | -339679.2083
|  |  | 7717110 |  |  |  | 1982-02-23
|  |  | 7717580 |  |  |  | -339679.2083
|  |  | 7717640 |  |  |  | -339679.2083
|  |  | 7717710 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 7717750 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1983-01-18
|  |  | 7717790 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7717810 |  |  |  | 1981-09-22
|  |  | 7717820 |  |  |  | 1981-09-22
|  |  | 7717840 |  |  |  | 1981-09-22
|  |  | 7717850 |  |  |  | 1981-09-22
|  |  | 7717851 |  |  |  | 1983-08-23
|  |  | 7717870 |  |  |  | -339679.2083
|  |  | 7717871 |  |  |  | 1985-09-24
|  |  | 7717872 |  |  |  | 1985-09-24
|  |  | 7717891 |  |  |  | 1989-08-15
|  |  | 7717892 |  |  |  | 1982-10-26
|  |  | 7718090 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 7718100 |  | Consolidated Test Company | Hammond | -339679.2083
|  |  | 7718880 |  |  |  | -339679.2083
|  |  | 7719330 |  |  | Indiana Department of Transportation | 1993-12-14
|  |  | 7723300 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723310 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723320 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723330 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723340 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723360 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723380 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723390 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723410 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7723420 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1980-12-16
|  |  | 7727970 |  |  |  | 1981-07-21
|  |  | 7728520 |  |  |  | 1980-06-10
|  |  | 7729410 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7730320 | Marion | DCD Consulting LLC | Indianapolis | -339679.2083 | PE
|  |  | 7733750 |  |  |  | 1983-06-21
|  |  | 7734190 |  |  |  | -339679.2083
|  |  | 7734280 |  |  |  | -339679.2083
|  |  | 7734380 |  |  |  | -339679.2083
|  |  | 7734810 |  |  | South Bend | -339679.2083
|  |  | 7800010 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7800050 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7800060 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 7800061 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 7800062 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 7800080 |  | Quantum Spatial, Inc. | Indiana Department of Transportation | 1983-11-15
|  |  | 7800165 |  |  | Vincennes | -339679.2083
|  |  | 7800210 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7800440 |  |  |  | 1985-07-23
|  |  | 7800480 |  |  |  | -339679.2083
|  |  | 7800500 |  |  |  | 1980-11-18
|  |  | 7800550 |  |  |  | -339679.2083
|  |  | 7800620 |  |  |  | 1982-08-24
|  |  | 7800650 |  |  |  | -339679.2083
|  |  | 7800680 |  |  |  | -339679.2083
|  |  | 7800950 |  |  |  | -339679.2083
|  |  | 7801000 |  |  |  | -339679.2083
|  |  | 7801070 |  |  |  | -339679.2083
|  |  | 7801250 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7801270 |  |  |  | -339679.2083
|  |  | 7801390 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7801420 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7801490 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 7801530 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7801550 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7801570 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 7801580 |  | M-E Companies, Inc. | Indiana Department of Transportation | 1982-11-16
|  |  | 7801590 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7801610 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7801630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7801640 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 7801680 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7801700 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7801730 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7801910 |  |  |  | -339679.2083
|  |  | 7801930 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 7802160 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7802190 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 7802200 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7802210 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7802230 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7802320 | Adams |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  | 7802370 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 7802400 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 7802530 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 7802620 |  |  | Indiana Department of Transportation | 1981-12-16
|  |  | 7802810 |  |  |  | -339679.2083
|  |  | 7802970 |  |  |  | 1980-09-16
|  |  | 7803000 |  |  |  | 1980-09-16
|  |  | 7803220 | Washington |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
UT
|  |  | 7803230 | Washington |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
UT
|  |  | 7803320 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7803330 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 7803340 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7803360 |  |  |  | -339679.2083
|  |  | 7803540 |  |  |  | -339679.2083
|  |  | 7803590 |  |  |  | -339679.2083
|  |  | 7803610 |  | Civil Inspection Services, LLC | Goshen | 1992-10-06
|  |  | 7803640 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7803710 |  |  |  | -339679.2083
|  |  | 7803760 |  |  | Indiana Department of Transportation | 1992-04-07
|  |  | 7803761 | Lawrence |  | Indiana Department of Transportation | 1998-10-06 | CE
CN
RR
UT
|  |  | 7803762 |  |  | Indiana Department of Transportation | 1998-10-06
|  |  | 7803770 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7803830 |  |  |  | -339679.2083
|  |  | 7803870 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7803920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7803940 |  |  |  | -339679.2083
|  |  | 7803990 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-02-14
|  |  | 7804000 |  |  |  | -339679.2083
|  |  | 7804040 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7804080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7804130 |  |  |  | -339679.2083
|  |  | 7804170 |  |  |  | -339679.2083
|  |  | 7804200 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 7804220 |  |  |  | -339679.2083
|  |  | 7804240 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 7804250 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7804320 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 7804380 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7804460 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7804480 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 7804540 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7804560 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 7804600 |  |  | Indiana Department of Transportation | 1980-05-13
|  |  | 7804660 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 7804670 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 7804710 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1984-01-17
|  |  | 7804730 |  |  |  | 1983-09-20
|  |  | 7804750 |  |  |  | 1985-06-25
|  |  | 7804790 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7804820 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7804910 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7805000 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7805120 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7805240 |  |  |  | -339679.2083
|  |  | 7805350 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7805370 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7805390 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7805430 |  |  |  | -339679.2083
|  |  | 7805510 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1983-12-13
|  |  | 7805520 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7805540 |  | CGI | Indiana Department of Transportation | 1991-09-24
|  |  | 7805650 |  |  |  | -339679.2083
|  |  | 7805651 |  |  |  | 1986-03-18
|  |  | 7805780 |  |  |  | -339679.2083
|  |  | 7805790 |  |  |  | -339679.2083
|  |  | 7805900 |  |  |  | -339679.2083
|  |  | 7805950 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 7806070 |  |  |  | -339679.2083
|  |  | 7806090 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7806100 |  |  |  | -339679.2083
|  |  | 7806120 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 7806130 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 7806210 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 7806230 |  |  |  | -339679.2083
|  |  | 7806240 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7806580 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 7806590 |  | DCD Consulting LLC | Indiana Department of Transportation | 1997-06-10
|  |  | 780659A |  | DCD Consulting LLC | Indiana Department of Transportation | 1997-04-29
|  |  | 7806630 |  |  | Indiana Department of Transportation | 1987-08-04
|  |  | 7806700 |  |  |  | -339679.2083
|  |  | 7806720 |  |  |  | -339679.2083
|  |  | 7806800 |  |  |  | -339679.2083
|  |  | 7807150 |  |  |  | 1981-10-27
|  |  | 7807170 |  |  |  | -339679.2083
|  |  | 7807180 |  |  |  | 1985-12-17
|  |  | 7807200 |  |  |  | -339679.2083
|  |  | 7807210 |  |  |  | -339679.2083
|  |  | 7807230 |  |  |  | -339679.2083
|  |  | 7807270 |  |  |  | 1982-02-23
|  |  | 7807310 |  |  |  | 1982-02-23
|  |  | 7807400 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 7807560 |  |  |  | 1981-01-20
|  |  | 7807660 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7807860 |  |  |  | 1980-12-16
|  |  | 7807870 |  |  |  | 1982-05-18
|  |  | 7807880 |  |  |  | 1983-10-25
|  |  | 7808000 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7808240 |  |  |  | 1980-04-15
|  |  | 7808250 |  |  |  | 1980-04-15
|  |  | 7808330 |  |  |  | 1981-01-20
|  |  | 7808340 |  |  |  | 1984-09-18
|  |  | 7808461 |  | Civil Inspection Services, LLC |  | 1992-10-06
|  |  | 7808560 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7808570 |  |  |  | 1983-09-20
|  |  | 7808820 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1989-11-14
|  |  | 7808840 |  |  |  | 1983-08-23
|  |  | 7808850 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 7808870 |  | GS-IN P.C. |  | -339679.2083
|  |  | 7809150 |  |  |  | 1986-03-18
|  |  | 7809240 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7809400 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7809580 |  |  |  | -339679.2083
|  |  | 7809610 |  |  |  | -339679.2083
|  |  | 7809620 |  |  |  | 1982-06-15
|  |  | 7809630 |  |  |  | 1987-08-04
|  |  | 7809930 |  |  |  | -339679.2083
|  |  | 7810090 |  |  |  | -339679.2083
|  |  | 7810120 |  |  |  | -339679.2083
|  |  | 7810160 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7810290 |  |  |  | -339679.2083
|  |  | 7810330 |  |  |  | 1981-06-23
|  |  | 7810430 |  |  |  | 1983-07-26
|  |  | 7810460 |  |  |  | -339679.2083
|  |  | 7810590 |  |  |  | 1979-11-20
|  |  | 7810680 |  |  |  | -339679.2083
|  |  | 7810720 |  |  |  | -339679.2083
|  |  | 7811020 |  | CoCal Consulting, LLC | Kokomo | -339679.2083
|  |  | 7811070 |  |  |  | -339679.2083
|  |  | 7811100 |  |  |  | -339679.2083
|  |  | 7811480 |  |  |  | 1981-02-24
|  |  | 7811580 |  |  |  | -339679.2083
|  |  | 7811600 |  |  |  | 1989-08-08
|  |  | 7811640 |  |  |  | -339679.2083
|  |  | 7811830 |  |  |  | 1981-09-22
|  |  | 7811900 |  |  |  | 1986-08-19
|  |  | 7812140 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1987-11-17
|  |  | 7812170 |  |  |  | -339679.2083
|  |  | 7812230 |  |  |  | -339679.2083
|  |  | 7812250 |  |  |  | -339679.2083
|  |  | 7812350 |  |  |  | -339679.2083
|  |  | 7812390 |  |  |  | -339679.2083
|  |  | 7812410 |  |  |  | 1984-03-20
|  |  | 7812480 |  |  |  | 1984-01-17
|  |  | 7812610 |  |  | Daviess County | -339679.2083
|  |  | 7812660 |  |  |  | -339679.2083
|  |  | 7812880 |  |  |  | -339679.2083
|  |  | 7813320 |  |  |  | 1981-01-20
|  |  | 7813360 |  |  |  | -339679.2083
|  |  | 7813560 |  |  |  | -339679.2083
|  |  | 7813730 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7813740 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 7813750 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 7813760 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 7814100 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7814110 |  |  |  | -339679.2083
|  |  | 7814220 |  |  |  | 1982-06-15
|  |  | 7814480 |  |  |  | -339679.2083
|  |  | 7814500 |  |  |  | -339679.2083
|  |  | 7814530 |  |  |  | -339679.2083
|  |  | 7814740 |  |  |  | -339679.2083
|  |  | 7814760 |  |  |  | -339679.2083
|  |  | 7814770 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7814840 |  |  |  | -339679.2083
|  |  | 7814860 |  |  |  | -339679.2083
|  |  | 7814870 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7815010 |  |  |  | -339679.2083
|  |  | 7815020 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7815030 |  |  |  | -339679.2083
|  |  | 7815070 |  |  |  | -339679.2083
|  |  | 7815120 |  |  |  | -339679.2083
|  |  | 7815140 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7815160 |  |  |  | -339679.2083
|  |  | 7815200 |  |  |  | -339679.2083
|  |  | 7815320 |  |  |  | -339679.2083
|  |  | 7815380 |  |  |  | -339679.2083
|  |  | 7815381 |  |  |  | -339679.2083
|  |  | 7815410 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 7815420 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7815440 |  | CE Solutions, Inc. | Indiana Department of Transportation | 1985-02-19
|  |  | 7815460 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7815470 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7815480 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7815520 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7815570 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7815580 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 7815640 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7815680 |  |  | Indiana Department of Transportation | 1991-10-24
|  |  | 7815790 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7815840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7815850 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 7815900 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7815910 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7815920 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7815930 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 7815980 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7815990 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 7816060 |  |  |  | 1984-08-21
|  |  | 7816070 |  |  | Indiana Department of Transportation | 1985-07-12
|  |  | 7816080 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 7816130 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7816190 |  |  |  | 1982-02-23
|  |  | 7816220 |  |  | Indiana Department of Transportation | 1983-10-25
|  |  | 7816260 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7816350 |  | ARCADIS | Indiana Department of Transportation | 1989-04-18
|  |  | 7816370 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7816400 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 7816450 |  |  | Indiana Department of Transportation | 1986-07-01
|  |  | 7816500 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7816571 |  |  |  | 1994-11-15
|  |  | 7816600 |  |  |  | 1982-02-23
|  |  | 7816610 |  |  |  | 1982-04-20
|  |  | 7816640 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7816660 |  |  |  | 1982-02-23
|  |  | 7816680 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7816730 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7816740 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7816750 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7816760 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7816810 |  |  |  | 1981-09-22
|  |  | 7816890 |  |  | Fountain County | -339679.2083
|  |  | 7817000 |  |  |  | 1980-09-16
|  |  | 7817160 |  |  |  | 1981-11-17
|  |  | 7817450 |  |  |  | 1981-06-23
|  |  | 7817490 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7817550 |  |  |  | 1989-04-18
|  |  | 7817560 |  |  |  | -339679.2083
|  |  | 7817610 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7817690 |  |  |  | -339679.2083
|  |  | 7817720 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 7818000 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7818010 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 7818040 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 7818070 |  |  |  | 1982-06-15
|  |  | 7818270 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 2000-01-19
|  |  | 7818290 |  |  |  | 1984-08-21
|  |  | 7818330 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 7818350 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7818490 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7818570 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818670 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818720 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 7818730 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818740 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818750 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818760 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818770 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7818860 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7818870 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7818890 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7818910 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 7818980 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7819000 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-03-23
|  |  | 7819010 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-03-23
|  |  | 7819020 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-03-23
|  |  | 7819090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7819100 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7819190 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7819360 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7819380 | Various |  | Indiana Department of Transportation | 1996-07-16 | CN
|  |  | 7819400 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7819430 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 7819440 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7819510 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1984-02-14
|  |  | 7819600 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7819620 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7819630 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7819640 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 7819650 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | 1983-02-22
|  |  | 7819651 |  | Construction Consultants & Inspection Services, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 7819660 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7819670 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7819730 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7819740 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7819750 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7819800 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7819870 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7819890 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 7819900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7819940 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7820570 | Dubois |  | Huntingburg | -339679.2083 | CE
CN
PE
|  |  | 7820700 |  |  |  | 1983-03-29
|  |  | 7820701 |  |  |  | 1984-06-12
|  |  | 7821390 |  |  | Monroe County | 1993-11-16
|  |  | 7821450 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7821480 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 7821481 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 7823061 |  | Accu-Air Surveys, Inc. | Indiana Department of Transportation | 1986-07-29
|  |  | 7823070 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7823130 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7823140 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7823150 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-02-23
|  |  | 7823160 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1981-12-15
|  |  | 7823210 |  |  |  | 1986-03-18
|  |  | 7823240 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 7823260 |  |  | Indiana Department of Transportation | 1988-01-12
|  |  | 7823580 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7823590 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 7823630 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7823660 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7823680 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7823700 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1992-12-15
|  |  | 7823760 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7823790 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7823810 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7824320 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 7824450 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7824560 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7824590 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7824620 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7824640 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7824710 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7824740 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7824750 |  | Archaeology and Geomorphology Services | Indiana Department of Transportation | 1983-01-18
|  |  | 7824760 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7824800 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 1983-06-21
|  |  | 7824810 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7824830 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7824840 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7824850 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7824860 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7824870 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7824910 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 7824920 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 7824940 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 7825120 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7825140 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 7825230 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 1983-05-24
|  |  | 7825470 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 7825550 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7825630 |  | CGI | Indiana Department of Transportation | 1983-06-21
|  |  | 7825640 |  | CGI | Indiana Department of Transportation | 1983-06-21
|  |  | 7825650 |  | CGI | Indiana Department of Transportation | 1982-07-20
|  |  | 7825660 |  | CGI | Indiana Department of Transportation | 1983-06-21
|  |  | 7825740 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-07-26
|  |  | 7825760 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-07-26
|  |  | 7825890 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 7828040 |  |  |  | 1983-03-29
|  |  | 7828060 |  |  |  | 1983-06-21
|  |  | 7828070 |  |  |  | 1986-12-16
|  |  | 7828100 |  |  |  | 1986-11-18
|  |  | 7828120 |  |  |  | -339679.2083
|  |  | 7828500 |  |  |  | -339679.2083
|  |  | 7828510 |  |  |  | -339679.2083
|  |  | 7828560 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 7829090 |  | Eco Logic, LLC | Indiana Department of Transportation | 1988-01-12
|  |  | 7829691 |  |  |  | 1979-07-24
|  |  | 7829970 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7830040 |  |  |  | 1979-07-24
|  |  | 7830210 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7831050 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7831140 |  |  |  | 1981-01-20
|  |  | 7831240 |  |  |  | 1982-09-21
|  |  | 7831310 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7831470 |  |  |  | 1983-05-24
|  |  | 7831570 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 7831590 |  |  |  | -339679.2083
|  |  | 7831820 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7832920 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7833070 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 7833110 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 7833220 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7833980 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7833981 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 7834100 |  |  |  | 1980-04-15
|  |  | 7834110 |  |  |  | 1980-04-15
|  |  | 7834290 |  |  |  | -339679.2083
|  |  | 7834310 |  |  |  | -339679.2083
|  |  | 7834460 |  |  |  | 1981-07-21
|  |  | 7834540 |  |  |  | 1980-10-21
|  |  | 7834620 |  |  |  | 1980-10-21
|  |  | 7834761 |  |  |  | 1983-06-21
|  |  | 7838992 |  |  |  | 1980-09-16
|  |  | 7838993 |  |  |  | 1982-03-23
|  |  | 7838994 |  |  |  | 1983-04-26
|  |  | 7839610 | Lake | Consolidated Test Company | Hammond | -339679.2083 | CE
CN
PE
|  |  | 7840722 |  |  |  | 1982-02-23
|  |  | 7891011 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7900460 |  |  |  | 1980-02-19
|  |  | 7900710 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 7900760 |  |  |  | 1982-11-16
|  |  | 7900780 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7900940 |  |  |  | -339679.2083
|  |  | 7900990 |  |  |  | -339679.2083
|  |  | 7901010 |  |  |  | -339679.2083
|  |  | 7901100 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7901170 |  |  |  | -339679.2083
|  |  | 7901260 |  |  |  | -339679.2083
|  |  | 7901600 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1985-06-25
|  |  | 7901890 |  |  |  | 1985-10-29
|  |  | 7901990 |  |  |  | 1981-04-21
|  |  | 7902100 |  |  |  | 1984-06-12
|  |  | 7902110 |  |  |  | 1984-01-17
|  |  | 7902130 |  |  |  | 1982-11-16
|  |  | 7902280 |  |  | Indiana Department of Transportation | 1980-02-19
|  |  | 7902290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7902340 |  |  |  | 1986-06-10
|  |  | 7902450 |  |  |  | 1981-01-20
|  |  | 7902560 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7902590 |  |  |  | 1981-01-20
|  |  | 7902750 |  |  |  | -339679.2083
|  |  | 7902850 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 7902900 |  |  |  | 1984-01-17
|  |  | 7902940 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1982-05-18
|  |  | 7903050 |  |  |  | 1986-09-16
|  |  | 7903130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7903140 |  |  |  | -339679.2083
|  |  | 7903160 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2000-05-23 | CE
CN
PE
ROW
|  |  | 7903180 |  |  |  | 1981-02-24
|  |  | 7903250 |  |  |  | 1981-02-24
|  |  | 7903370 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1990-12-18
|  |  | 7903720 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 7903900 |  | DCD Consulting LLC | Indiana Department of Transportation | 1980-01-15
|  |  | 7904090 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 7904120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7904470 |  |  |  | -339679.2083
|  |  | 7904690 |  |  |  | -339679.2083
|  |  | 7904720 |  |  |  | -339679.2083
|  |  | 7904760 |  |  |  | -339679.2083
|  |  | 7904830 |  |  |  | -339679.2083
|  |  | 7904870 |  |  |  | -339679.2083
|  |  | 7904900 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7904920 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7905400 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 7905760 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | 1983-06-21
|  |  | 7906200 |  |  |  | 1983-09-20
|  |  | 7906670 |  |  |  | 1981-02-24
|  |  | 7906680 |  |  |  | 1980-06-10
|  |  | 7906750 |  |  |  | -339679.2083
|  |  | 7906810 |  |  |  | 1980-02-19
|  |  | 7907000 |  |  |  | 1983-07-18
|  |  | 7907060 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7907070 |  |  |  | 1980-09-16
|  |  | 7907110 |  |  |  | -339679.2083
|  |  | 7907130 |  |  |  | 1980-05-13
|  |  | 7907160 |  |  |  | -339679.2083
|  |  | 7907250 |  |  |  | -339679.2083
|  |  | 7907300 |  |  |  | -339679.2083
|  |  | 7907330 |  |  |  | 1982-02-23
|  |  | 7907340 |  |  |  | 1980-04-15
|  |  | 7907480 |  |  |  | -339679.2083
|  |  | 7907490 |  |  |  | 1980-12-16
|  |  | 7907510 |  |  |  | -339679.2083
|  |  | 7907590 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 7907650 |  |  |  | 1982-06-15
|  |  | 7907790 |  |  |  | 1984-12-18
|  |  | 7907850 |  |  |  | 1980-09-16
|  |  | 7907900 |  |  |  | 1980-03-18
|  |  | 7907940 |  |  |  | 1980-04-15
|  |  | 7908010 |  |  |  | 1980-09-16
|  |  | 7908020 |  |  |  | 1980-07-15
|  |  | 7908021 |  |  |  | 1980-11-18
|  |  | 7908120 |  |  |  | 1980-04-15
|  |  | 7908150 |  |  |  | 1981-01-20
|  |  | 7908220 |  |  |  | 1980-10-21
|  |  | 7908230 |  |  |  | 1980-04-15
|  |  | 7908310 |  |  |  | 1981-03-24
|  |  | 7908365 |  |  | Vanderburgh County | 1993-07-20
|  |  | 7908400 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7908430 |  |  |  | -339679.2083
|  |  | 7908480 |  |  |  | 1981-01-20
|  |  | 7908500 |  |  |  | 1980-04-15
|  |  | 7908510 |  |  |  | 1980-01-15
|  |  | 7908530 |  |  |  | 1981-01-20
|  |  | 7908550 |  |  |  | 1981-03-24
|  |  | 7908670 |  |  |  | 1982-11-16
|  |  | 7908790 |  |  |  | -339679.2083
|  |  | 7908970 |  |  |  | 1981-09-22
|  |  | 7908990 |  |  | Terre Haute | 1988-09-20
|  |  | 7909270 |  |  |  | 1980-09-16
|  |  | 7909280 |  |  |  | 1983-05-24
|  |  | 7909310 |  |  |  | -339679.2083
|  |  | 7909320 |  |  |  | 1984-05-15
|  |  | 7909490 |  |  |  | 1980-04-15
|  |  | 7909700 |  |  |  | 1983-04-26
|  |  | 7909760 |  |  |  | 1980-10-21
|  |  | 7909910 |  |  |  | 1981-11-17
|  |  | 7910080 |  |  |  | 1982-03-23
|  |  | 7910150 |  |  |  | 1980-12-16
|  |  | 7910210 |  |  |  | 1980-01-15
|  |  | 7910670 |  |  |  | 1981-06-23
|  |  | 7910980 |  |  |  | 1980-01-15
|  |  | 7911260 |  |  |  | -339679.2083
|  |  | 7911330 |  |  |  | 1980-01-15
|  |  | 7911440 |  |  |  | 1982-08-24
|  |  | 7911560 |  |  |  | -339679.2083
|  |  | 7911650 |  |  |  | -339679.2083
|  |  | 7911850 |  |  |  | 1980-12-16
|  |  | 7912110 |  |  |  | 1980-10-21
|  |  | 7912380 |  |  |  | 1980-01-15
|  |  | 7912631 |  |  |  | 1980-06-10
|  |  | 7912690 |  |  |  | -339679.2083
|  |  | 7912770 |  |  |  | 1980-01-15
|  |  | 7912800 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7912850 |  |  |  | -339679.2083
|  |  | 7912870 |  |  |  | -339679.2083
|  |  | 7913280 |  |  |  | -339679.2083
|  |  | 7913440 |  |  |  | -339679.2083
|  |  | 7913540 |  |  | Indiana Department of Transportation | 1982-11-18
|  |  | 7913600 |  |  |  | 1984-12-18
|  |  | 7913710 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7913780 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 1997-10-22
|  |  | 7913870 |  |  |  | -339679.2083
|  |  | 7914010 |  |  |  | -339679.2083
|  |  | 7914190 |  |  |  | 1981-02-24
|  |  | 7914240 |  |  |  | -339679.2083
|  |  | 7914390 |  |  |  | -339679.2083
|  |  | 7914450 |  |  |  | 1982-11-16
|  |  | 7914490 |  |  |  | 1981-11-17
|  |  | 7914560 |  |  |  | -339679.2083
|  |  | 7914610 |  |  |  | -339679.2083
|  |  | 7914620 |  |  |  | 1981-11-17
|  |  | 7914900 |  |  |  | -339679.2083
|  |  | 7914920 |  |  |  | -339679.2083
|  |  | 7914970 |  |  |  | 1984-02-14
|  |  | 7914990 |  |  |  | 1984-02-14
|  |  | 7915210 |  |  |  | -339679.2083
|  |  | 7915250 |  |  |  | -339679.2083
|  |  | 7915360 |  |  |  | -339679.2083
|  |  | 7915501 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7915510 |  |  | Indiana Department of Transportation | 1981-01-20
|  |  | 7915560 |  |  | Indiana Department of Transportation | 1981-01-20
|  |  | 7915650 |  |  | Indiana Department of Transportation | 1981-02-24
|  |  | 7916180 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 7916270 |  |  | Indiana Department of Transportation | 1981-05-19
|  |  | 7916510 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 7916830 |  |  |  | 1980-01-15
|  |  | 7916870 |  |  |  | 1983-10-25
|  |  | 7916990 |  |  |  | 1981-03-24
|  |  | 7917120 |  |  |  | 1980-11-18
|  |  | 7917261 |  |  |  | 1981-06-23
|  |  | 7917340 | Porter |  | Porter County | 1999-02-23 | CE
CN
|  |  | 7917380 |  |  |  | 1980-01-15
|  |  | 7917620 |  |  |  | -339679.2083
|  |  | 7918310 |  |  | Indiana Department of Transportation | 1980-07-15
|  |  | 7918440 |  |  |  | 1980-01-15
|  |  | 7918830 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7919050 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7919120 |  |  | Indiana Department of Transportation | 1981-05-19
|  |  | 7919210 |  |  | Indiana Department of Transportation | 1995-06-13
|  |  | 7919690 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7919700 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7919710 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7919880 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7920560 |  |  | Vanderburgh County | 1993-07-20
|  |  | 7920780 |  |  |  | 1983-07-26
|  |  | 7921520 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7921660 |  |  |  | 1984-07-17
|  |  | 7923200 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7923290 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7923440 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 7923690 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-05-24
|  |  | 7924390 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7924480 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7925150 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 7925570 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7927190 |  |  |  | 1983-04-26
|  |  | 7927260 |  |  |  | 1983-03-29
|  |  | 7928250 |  |  |  | 1981-03-24
|  |  | 7928570 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 1988-06-14
|  |  | 7928580 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7928590 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7928600 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 7928610 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 7928620 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 7928640 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7928660 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7928670 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7928680 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7928690 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 7928700 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7928730 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 7928740 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7928750 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 7928770 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7928780 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7928790 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 7928800 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7928810 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7928820 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 7928830 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7928840 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7928850 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7928860 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 1985-09-24
|  |  | 7928870 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7928880 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7928890 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 7928910 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 7928920 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 7928930 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 7928940 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1988-04-19
|  |  | 7928950 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 7928960 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7928970 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7928980 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 7928990 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929000 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 7929010 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 7929020 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7929030 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 7929050 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7929060 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 7929070 |  |  | Indiana Department of Transportation | 1992-07-28
|  |  | 7929080 |  |  | Indiana Department of Transportation | 1992-07-28
|  |  | 7929100 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 7929110 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7929130 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 7929140 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 7929150 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1986-02-18
|  |  | 7929160 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 7929180 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 7929190 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 7929200 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7929210 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 7929220 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7929230 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929240 |  |  | Indiana Department of Transportation | 1984-11-23
|  |  | 7929350 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 7929360 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 1987-12-15
|  |  | 7929370 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 7929380 |  |  | Indiana Department of Transportation | 1987-08-04
|  |  | 7929390 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 7929430 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929440 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 7929450 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 7929460 | Clay | Bayswater Company, LLC | Indiana Department of Transportation | 2000-04-11 | CN
|  |  |  | Marion | Bayswater Company, LLC | Indiana Department of Transportation | 2000-04-11 | CE
CN
PE
UT
|  |  |  | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | 2000-04-11 | CE
CN
PE
ROW
|  |  | 7929470 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 7929480 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 7929490 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 7929500 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 7929510 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7929540 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929550 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7929570 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 7929580 |  | Bidinfo | Indiana Department of Transportation | 1986-02-18
|  |  | 7929600 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 7929610 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929620 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929630 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 7929660 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 7929670 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 7929680 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 7929760 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 7929780 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 7929790 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 7929800 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 7929890 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7929900 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7929980 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 7929990 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930020 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7930060 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930080 |  | Eco Logic, LLC | Indiana Department of Transportation | 1983-12-13
|  |  | 7930090 |  | Eco Logic, LLC | Indiana Department of Transportation | 1983-12-13
|  |  | 7930100 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7930110 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 7930140 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7930160 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7930170 |  | ERES International, Inc. | Indiana Department of Transportation | 1986-07-15
|  |  | 7930190 |  | ERES International, Inc. | Indiana Department of Transportation | 1983-05-24
|  |  | 7930220 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1983-12-13
|  |  | 7930240 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 7930270 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7930290 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930300 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930310 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7930360 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930370 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930380 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930420 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1994-04-19
|  |  | 7930430 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1994-04-19
|  |  | 7930440 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 7930480 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 7930500 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-06-10
|  |  | 7930501 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 7930502 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 7930510 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7930520 |  | Dodd Title Corporation | Indiana Department of Transportation | 1985-11-19
|  |  | 7930530 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7930590 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7930600 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 7930610 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 7930620 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 7930630 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 7930650 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 7930670 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7930690 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 7930710 | Perry |  | Indiana Department of Transportation | 1998-05-12 | CE
CN
|  |  | 7930740 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 7930760 |  | ASA Land Surveying | Indiana Department of Transportation | 1982-08-24
|  |  | 7930830 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 7930850 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 7930860 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7930870 |  | Dillabaugh, Inc. | Indiana Department of Transportation | 1993-03-16
|  |  | 7930890 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7930900 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 7930910 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1983-12-13
|  |  | 7930920 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1984-02-14
|  |  | 7930930 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7930940 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7930950 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7930960 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7930970 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7931000 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7931010 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7931060 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7931070 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7931100 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 1984-11-20
|  |  | 7931110 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 7931130 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7931150 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1984-02-14
|  |  | 7931170 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 7931180 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7931210 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 7931220 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1983-12-13
|  |  | 7931230 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1983-12-13
|  |  | 7931250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7931260 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 7931270 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 7931280 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7931290 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7931300 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 7931320 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-04-16
|  |  | 7931330 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 7931340 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 7931350 |  |  |  | -339679.2083
|  |  | 7931370 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 2000-05-23
|  |  | 7931390 |  |  |  | -339679.2083
|  |  | 7931400 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 7931430 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7931440 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7931450 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7931460 |  |  |  | -339679.2083
|  |  | 7931490 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 1995-03-21 | CE
CN
|  |  | 7931491 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 1995-03-21 | CE
CN
|  |  | 7931492 | Knox | Louis Joyner, Architect | Indiana Department of Transportation | 1995-03-21 | CE
CN
|  |  | 7931500 |  |  |  | 1985-07-23
|  |  | 7931510 |  | CGI | Indiana Department of Transportation | 1989-06-13
|  |  | 7931520 |  | CGI | Indiana Department of Transportation | 1982-10-26
|  |  | 7931530 |  |  |  | 1986-04-15
|  |  | 7931540 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7931630 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7931650 |  |  |  | -339679.2083
|  |  | 7931670 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 7931690 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 7931830 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7931840 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7931850 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7931880 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7931890 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 7932210 |  | CGI | Indiana Department of Transportation | 1983-06-21
|  |  | 7932220 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 7932480 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 7932650 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 7932750 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 7932760 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 7932770 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-05-18
|  |  | 7932780 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1988-11-15
|  |  | 7932790 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1987-03-10
|  |  | 7932800 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7932820 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 7932880 | Switzerland |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 7932890 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 7932970 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-03-20
|  |  | 7933080 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7933100 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 7933120 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7933130 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 7933150 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 7933170 |  |  |  | 1983-09-20
|  |  | 7933190 |  |  |  | 1984-01-17
|  |  | 7933210 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7933270 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 7933280 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-11-15
|  |  | 7933290 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-11-15
|  |  | 7933300 |  | Another Test Company | Indiana Department of Transportation | 1984-11-20
|  |  | 7933310 |  | Another Test Company | Indiana Department of Transportation | 1984-11-20
|  |  | 7933430 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7933450 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1983-08-23
|  |  | 7933540 |  |  |  | 1983-06-21
|  |  | 7933690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933700 |  |  |  | 1983-12-13
|  |  | 7933740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933790 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933800 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933880 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933950 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7933990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7934000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7934010 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7934040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 7934120 |  |  |  | -339679.2083
|  |  | 7934140 |  |  |  | -339679.2083
|  |  | 7934150 |  |  |  | -339679.2083
|  |  | 7934160 |  |  |  | -339679.2083
|  |  | 7934170 |  |  |  | -339679.2083
|  |  | 7934210 |  |  |  | -339679.2083
|  |  | 7934240 |  |  |  | 1983-09-20
|  |  | 7934250 |  |  |  | -339679.2083
|  |  | 7934320 |  |  |  | -339679.2083
|  |  | 7934330 |  |  |  | -339679.2083
|  |  | 7934340 |  |  |  | -339679.2083
|  |  | 7934360 |  |  |  | -339679.2083
|  |  | 7934370 |  |  |  | -339679.2083
|  |  | 7934430 |  |  |  | 1981-05-19
|  |  | 7934630 |  |  |  | 1983-10-25
|  |  | 7934820 |  |  |  | 1981-04-21
|  |  | 7934830 |  |  |  | 1980-05-13
|  |  | 7934860 |  |  |  | 1980-02-19
|  |  | 7934920 |  |  |  | -339679.2083
|  |  | 7934980 |  |  |  | 1980-07-15
|  |  | 7934990 |  |  |  | -339679.2083
|  |  | 7935120 |  |  |  | 1982-08-24
|  |  | 7935550 |  |  | Indiana Department of Transportation | 1980-06-10
|  |  | 7935760 |  |  | Indiana Department of Transportation | 1980-02-19
|  |  | 7936020 |  |  | Seymour | -339679.2083
|  |  | 7936140 |  |  |  | 1984-01-17
|  |  | 7937101 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 7937610 |  |  | Indiana Department of Transportation | 1980-01-15
|  |  | 7938430 |  |  |  | 1983-09-20
|  |  | 7939400 |  |  |  | -339679.2083
|  |  | 7941470 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 7944130 |  |  |  | -339679.2083
|  |  | 7945230 |  |  |  | 1982-06-15
|  |  | 7956870 | Various |  | Indiana Department of Transportation | 1996-07-16 | CN
ROW
|  |  | 7985835 |  |  | Vanderburgh County | 1993-07-20
|  |  | 8000910 |  | Continental Mapping Consultants, LLC |  | 1986-10-14
|  |  | 8001040 | Noble | Debbie L. Morris | Indiana Department of Transportation | 2006-06-01 | CE
CN
PE
ROW
UT
|  |  | 8001300 |  |  |  | -339679.2083
|  |  | 8001470 |  |  |  | 1986-11-25
|  |  | 8001720 |  | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 1990-10-16
|  |  | 8001830 |  |  |  | 1984-03-20
|  |  | 8001860 |  |  | Anderson | -339679.2083
|  |  | 8002350 |  |  |  | 1984-07-17
|  |  | 8002430 |  |  |  | 1982-06-15
|  |  | 8002640 |  |  |  | 1987-11-17
|  |  | 8002680 |  |  |  | 1983-07-26
|  |  | 8002740 |  |  |  | 1985-05-21
|  |  | 8002770 |  |  |  | 1985-11-19
|  |  | 8002840 |  |  |  | 1983-06-21
|  |  | 8002910 |  | Associated Right-of-Way Services, Inc. |  | 1983-11-15
|  |  | 8003040 |  |  |  | 1984-11-20
|  |  | 8003430 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8003450 |  |  |  | 1986-01-14
|  |  | 8003690 |  |  |  | 1983-06-21
|  |  | 8003740 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8004150 |  |  |  | -339679.2083
|  |  | 8004430 |  |  |  | 1984-11-20
|  |  | 8004500 |  |  |  | 1983-06-21
|  |  | 8004550 |  |  |  | 1983-05-24
|  |  | 8004610 |  |  |  | 1983-05-24
|  |  | 8004630 |  |  |  | 1983-05-24
|  |  | 8004640 |  |  |  | 1983-05-24
|  |  | 8004740 |  |  |  | 1984-12-18
|  |  | 8004770 |  |  |  | 1983-05-24
|  |  | 8004801 | Cass | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Fulton | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083 | CN
|  |  |  | Jefferson | Engineering Resources, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8005713 |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 8005714 |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 8005715 |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 8005716 |  | DCD Consulting LLC |  | 1986-03-18
|  |  | 8005717 |  | DCD Consulting LLC |  | 1986-03-18
|  |  | 8005718 |  | DCD Consulting LLC |  | 1986-03-18
|  |  | 8005719 |  | DCD Consulting LLC |  | 1986-03-18
|  |  | 800571A |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 800571B |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 800571C |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 800571D |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 800571E |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 800571F |  | DCD Consulting LLC |  | 1985-07-23
|  |  | 800571G |  | DCD Consulting LLC |  | 1986-10-14
|  |  | 800571H |  | DCD Consulting LLC |  | 1986-10-14
|  |  | 800571J |  | DCD Consulting LLC |  | 1986-10-14
|  |  | 800571K |  | DCD Consulting LLC |  | 1986-10-14
|  |  | 800571L |  | DCD Consulting LLC |  | 1987-10-20
|  |  | 800571M |  | DCD Consulting LLC |  | 1987-10-20
|  |  | 800571N |  | DCD Consulting LLC |  | 1987-10-20
|  |  | 800571P |  | DCD Consulting LLC |  | 1987-10-20
|  |  | 8006260 |  | DCD Consulting LLC |  | 1981-11-17
|  |  | 8006261 |  | DCD Consulting LLC |  | 1981-11-17
|  |  | 8006360 |  | DCD Consulting LLC |  | 1981-11-17
|  |  | 8006361 |  | DCD Consulting LLC |  | 1981-11-17
|  |  | 8006370 |  |  |  | 1981-11-17
|  |  | 8006390 |  |  |  | 1981-11-17
|  |  | 8006560 |  |  |  | 1981-11-17
|  |  | 8006561 |  |  |  | 1981-11-17
|  |  | 8006990 |  |  |  | 1981-11-17
|  |  | 8006991 |  |  |  | 1981-11-17
|  |  | 8006992 |  |  |  | 1981-11-17
|  |  | 8007030 |  |  |  | 1981-11-17
|  |  | 8007050 |  |  |  | 1981-11-17
|  |  | 8007140 |  |  |  | 1984-03-20
|  |  | 8007220 |  |  |  | 1983-06-21
|  |  | 8007370 |  | CGI |  | 1985-06-25
|  |  | 8007390 |  |  |  | 1983-11-15
|  |  | 8007500 |  |  |  | 1983-11-15
|  |  | 8007570 |  |  |  | 1983-06-21
|  |  | 8007620 |  |  |  | 1984-12-18
|  |  | 8007690 |  |  |  | 1984-12-18
|  |  | 8007760 |  |  |  | 1984-11-20
|  |  | 8007770 |  |  |  | 1984-11-20
|  |  | 8007810 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1997-03-11
|  |  | 8007830 |  |  |  | 1986-05-13
|  |  | 8007960 |  |  |  | 1980-04-15
|  |  | 8007990 |  |  |  | 1986-05-13
|  |  | 8008030 |  |  |  | 1984-11-20
|  |  | 8008050 |  |  |  | 1984-11-20
|  |  | 8008060 |  |  |  | 1984-11-20
|  |  | 8008260 |  |  |  | 1985-01-15
|  |  | 8008320 |  |  |  | 1980-04-15
|  |  | 8008410 |  |  |  | 1980-04-15
|  |  | 8008440 |  |  |  | 1985-05-21
|  |  | 8008520 |  |  |  | 1985-05-21
|  |  | 8008631 |  |  |  | 1984-06-12
|  |  | 8008780 |  |  |  | 1984-01-17
|  |  | 8008800 |  |  |  | 1986-03-18
|  |  | 8008880 |  |  |  | 1986-03-18
|  |  | 8008890 |  |  |  | 1988-05-17
|  |  | 8008910 |  |  |  | 1986-08-19
|  |  | 8009090 |  |  |  | 1986-11-18
|  |  | 8009170 |  |  |  | 1985-01-15
|  |  | 8009200 |  |  |  | 1986-11-18
|  |  | 8009220 |  |  |  | 1985-09-24
|  |  | 8009300 |  |  |  | 1985-09-24
|  |  | 8009420 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8009450 |  |  |  | 1984-03-20
|  |  | 8009460 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8009500 |  |  |  | 1986-03-18
|  |  | 8009590 |  |  |  | 1984-11-20
|  |  | 8009650 |  |  |  | 1985-05-21
|  |  | 8009670 |  |  |  | 1985-05-21
|  |  | 8009690 |  |  |  | 1986-02-18
|  |  | 8009730 |  |  |  | 1986-06-10
|  |  | 8009770 |  |  |  | 1985-05-21
|  |  | 8009780 |  |  |  | 1987-04-07
|  |  | 8009900 |  |  |  | 1987-05-06
|  |  | 8009901 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8010000 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8010070 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8010130 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8010220 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8010270 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8010300 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8010400 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8010440 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8010530 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8010550 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 8010620 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8010630 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8010690 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8010890 |  |  | Indiana Department of Transportation | 1988-09-06
|  |  | 8011130 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8011140 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8011150 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8011160 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8011161 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8011200 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8011230 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8011450 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8011470 |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 8011550 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8011570 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8011590 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8011610 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8011630 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 8011670 |  |  |  | -339679.2083
|  |  | 8011700 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8011720 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 8011810 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8011910 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8011940 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8011950 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8012090 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8012130 |  | Hazeltine & Associates, Inc. | Indiana Department of Transportation | 1993-05-27
|  |  | 8012160 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8012180 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 8012300 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8012370 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8012460 | Montgomery |  | Indiana Department of Transportation | 1995-12-19 | CE
CN
PE
|  |  | 8012510 | Montgomery |  | Indiana Department of Transportation | 1995-12-19 | CE
CN
PE
|  |  | 8012560 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 8012600 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8012700 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8012710 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8012760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8012790 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8012820 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8012860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8012920 |  |  |  | -339679.2083
|  |  | 8012970 |  | ASA Land Surveying | Indiana Department of Transportation | 1990-09-18
|  |  | 8013000 |  | CGI | Indiana Department of Transportation | 1985-03-19
|  |  | 8013050 | Parke |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
PE
ROW
UT
|  |  | 8013090 | Owen |  | Indiana Department of Transportation | 2001-08-14 | CE
CN
ROW
|  |  | 8013170 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8013171 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8013380 |  | Lorenz Williams Clinton | Indiana Department of Transportation | -339679.2083
|  |  | 8013610 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8013621 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1983-09-20
|  |  | 8013622 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-08-23
|  |  | 8013630 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8013631 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1983-03-29
|  |  | 8013700 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8013770 | Dekalb |  | Indiana Department of Transportation | 2011-03-09 | CE
CN
PE
ROW
UT
|  |  | 8013850 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1982-03-23
|  |  | 8013920 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8013960 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8014730 |  |  |  | 1983-08-23
|  |  | 8014980 |  |  |  | -339679.2083
|  |  | 8015350 |  |  |  | 1983-07-26
|  |  | 8016340 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8016970 |  | Consolidated Test Company | Indiana Department of Transportation | 1981-12-15
|  |  | 8017060 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1983-03-29
|  |  | 8017140 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8017170 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8017220 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 8017270 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 8017290 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8017350 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8017390 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 8017480 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8017510 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1985-03-19
|  |  | 8017520 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1984-08-21
|  |  | 8017540 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1981-04-21
|  |  | 8017570 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 8017730 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-03-29
|  |  | 8017800 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1984-11-20
|  |  | 8017920 |  |  |  | 1984-07-15
|  |  | 8017930 |  |  |  | 1984-07-15
|  |  | 8017970 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8017990 | Daviess |  | Indiana Department of Transportation | 2000-06-20 | CE
CN
PE
|  |  | 8018061 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1982-01-26
|  |  | 8018110 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8018250 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8018271 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8018620 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8018660 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 8018680 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 8018700 |  |  | Indiana Department of Transportation | 1981-08-25
|  |  | 8018780 |  |  | Indiana Department of Transportation | 1981-08-25
|  |  | 8018900 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 8018920 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 8018990 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8019130 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8019131 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8019230 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8019370 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-06-23
|  |  | 8019530 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8019540 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8019850 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8019860 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8020040 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8020150 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8020240 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1981-07-21
|  |  | 8020300 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1983-03-29
|  |  | 8020390 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1983-03-29
|  |  | 8020410 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 2003-05-20 | CE
CN
|  |  | 8020420 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8020430 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 8020470 |  |  | Indiana Department of Transportation | 1981-05-19
|  |  | 8020561 | Vanderburgh |  | Vanderburgh County | 2000-09-12 | CE
CN
PE
|  |  | 8020562 | Warrick |  | Vanderburgh County | 2005-03-16 | CE
CN
PE
UT
|  |  | 8020960 |  | ASA Land Surveying | Indiana Department of Transportation | 1981-04-21
|  |  | 8020980 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 8021030 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1983-03-29
|  |  | 8021080 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8021200 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8021320 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1983-03-29
|  |  | 8021330 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8021350 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8021400 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8021460 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8021470 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8021490 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8021500 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8021510 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8021530 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8021631 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8021860 |  |  |  | 1983-05-24
|  |  | 8022310 |  |  |  | 1984-03-20
|  |  | 8023230 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8023530 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8023540 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8023550 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8023560 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8023600 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8023610 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8023640 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8023720 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8023850 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8023870 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8023890 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1981-09-22
|  |  | 8024040 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8024050 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8024060 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8024170 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-03-24
|  |  | 8024290 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8024340 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8024350 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8024370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8024380 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8024500 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8024520 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8024530 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8024550 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8024580 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8024630 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 8024730 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8024820 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8024890 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8024980 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8025060 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8025160 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8025170 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8025250 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8025270 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-08-23
|  |  | 8025290 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8025310 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8025311 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8025360 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8025380 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8025450 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8025460 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8025510 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8025540 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8025580 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8025590 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8025600 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8025610 |  | Collier Transport Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 8025700 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8025730 |  |  |  | 1983-03-29
|  |  | 8025870 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8025880 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8025910 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 8025920 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8025930 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8026000 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 8026060 |  |  | Indiana Department of Transportation | 1993-03-16
|  |  | 8026810 |  | MCIS LLC | Indiana Department of Transportation | 1985-07-23
|  |  | 8027220 |  |  |  | 1983-03-29
|  |  | 8027920 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8027930 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8027940 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8027960 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8028090 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8028110 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8028140 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 8028150 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8028160 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8028190 |  |  | Indiana Department of Transportation | 1993-12-14
|  |  | 8028210 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8028260 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 8028270 |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8028300 | Madison |  | Indiana Department of Transportation | 1996-12-17 | CE
CN
|  |  | 8028310 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8028350 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8028360 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 1986-06-10
|  |  | 8028380 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8028450 |  |  | Indianapolis | -339679.2083
|  |  | 8028480 |  |  |  | 1980-10-21
|  |  | 8029340 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8029420 |  |  |  | -339679.2083
|  |  | 8029750 |  |  |  | -339679.2083
|  |  | 8029830 |  |  | Alexandria | -339679.2083
|  |  | 8029940 |  |  |  | 1986-09-16
|  |  | 8030050 |  | CE Solutions, Inc. | Indiana Department of Transportation | 1986-07-15
|  |  | 8030200 |  |  |  | -339679.2083
|  |  | 8030250 |  |  |  | -339679.2083
|  |  | 8030260 |  |  |  | -339679.2083
|  |  | 8030780 |  |  |  | -339679.2083
|  |  | 8030790 |  |  |  | 1982-11-16
|  |  | 8030810 |  |  |  | 1982-02-23
|  |  | 8032040 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8032050 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8032060 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8032070 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8032410 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8032490 |  |  |  | 1984-02-14
|  |  | 8032590 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8032700 |  |  |  | 1983-12-13
|  |  | 8032960 |  |  |  | 1984-05-15
|  |  | 8033140 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8033141 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8033142 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8033143 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8033144 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8033230 |  | DCD Consulting LLC | Indiana Department of Transportation | 1994-11-15
|  |  | 8033231 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8033233 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8033250 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033251 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033252 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033253 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033254 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033255 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033256 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-22
|  |  | 8033260 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-25
|  |  | 8033261 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-25
|  |  | 8033262 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-09-25
|  |  | 8033560 |  |  |  | 1981-01-20
|  |  | 8033590 |  |  |  | 1981-02-24
|  |  | 8033630 |  |  |  | 1983-12-13
|  |  | 8033660 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8033670 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8033680 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8033760 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8033850 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8033870 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8034060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8034080 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8034090 |  |  |  | 1982-02-23
|  |  | 8034270 |  |  |  | 1983-09-20
|  |  | 8034470 |  |  |  | 1983-08-23
|  |  | 8034610 |  |  |  | 1983-02-22
|  |  | 8034890 |  |  |  | 1988-09-20
|  |  | 8035110 |  |  |  | 1984-09-18
|  |  | 8035130 |  |  |  | 1981-02-24
|  |  | 8035150 |  |  |  | 1981-11-17
|  |  | 8035160 |  |  |  | 1981-05-19
|  |  | 8036450 |  |  |  | 1981-01-20
|  |  | 8036560 |  |  |  | 1986-05-13
|  |  | 8037010 |  |  |  | 1983-04-26
|  |  | 8037092 |  |  | Indiana Department of Transportation | 1984-08-21
|  |  | 8037140 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-05-19
|  |  | 8037150 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8037160 |  |  |  | 1983-11-15
|  |  | 8037180 |  |  |  | 1983-11-15
|  |  | 8037230 |  |  |  | 1983-11-15
|  |  | 8037260 |  |  |  | -339679.2083
|  |  | 8037280 |  |  | Clark County | -339679.2083
|  |  | 8037320 |  |  |  | -339679.2083
|  |  | 8037330 |  |  |  | -339679.2083
|  |  | 8037460 |  |  |  | -339679.2083
|  |  | 8037470 |  |  |  | -339679.2083
|  |  | 8037480 |  |  |  | -339679.2083
|  |  | 8037570 |  |  |  | 1983-06-21
|  |  | 8037640 |  |  |  | 1983-12-13
|  |  | 8037700 |  |  |  | 1982-06-15
|  |  | 8037720 |  |  |  | 1981-03-24
|  |  | 8037780 |  |  |  | 1981-01-20
|  |  | 8037940 |  |  |  | -339679.2083
|  |  | 8037960 |  |  |  | -339679.2083
|  |  | 8038030 |  |  |  | 1982-09-21
|  |  | 8038980 |  |  | Howard County | -339679.2083
|  |  | 8039030 |  |  | Plymouth | -339679.2083
|  |  | 8039050 |  |  |  | 1982-09-21
|  |  | 8039060 |  |  |  | -339679.2083
|  |  | 8039070 |  |  |  | -339679.2083
|  |  | 8039080 |  |  |  | 1982-09-21
|  |  | 8039140 |  |  |  | -339679.2083
|  |  | 8039190 |  |  |  | 1982-11-16
|  |  | 8039250 |  |  |  | -339679.2083
|  |  | 8039260 |  |  |  | -339679.2083
|  |  | 8039280 |  |  |  | -339679.2083
|  |  | 8039281 |  |  |  | -339679.2083
|  |  | 8039290 |  |  |  | -339679.2083
|  |  | 8039300 |  |  |  | -339679.2083
|  |  | 8039360 |  |  |  | 1980-09-16
|  |  | 8039540 |  |  |  | 1983-05-24
|  |  | 8039710 |  |  |  | -339679.2083
|  |  | 8039720 |  |  |  | -339679.2083
|  |  | 8039730 |  |  |  | -339679.2083
|  |  | 8039800 |  |  |  | -339679.2083
|  |  | 8039810 |  |  |  | -339679.2083
|  |  | 8039820 |  |  |  | -339679.2083
|  |  | 8039830 |  |  |  | -339679.2083
|  |  | 8039840 |  |  |  | -339679.2083
|  |  | 8039850 |  |  |  | -339679.2083
|  |  | 8039860 |  |  |  | -339679.2083
|  |  | 8039890 |  |  |  | 1983-06-21
|  |  | 8039930 |  |  |  | 1982-03-23
|  |  | 8039960 |  |  |  | -339679.2083
|  |  | 8039970 |  |  |  | 1983-09-20
|  |  | 8040060 |  |  |  | 1981-03-24
|  |  | 8040090 |  |  |  | -339679.2083
|  |  | 8040120 |  |  |  | 1986-06-10
|  |  | 8040140 |  |  |  | 1983-05-24
|  |  | 8040180 |  |  |  | -339679.2083
|  |  | 8040250 |  |  |  | -339679.2083
|  |  | 8040260 |  |  |  | -339679.2083
|  |  | 8040270 |  |  |  | 1981-09-22
|  |  | 8040300 |  |  |  | -339679.2083
|  |  | 8040310 |  |  |  | -339679.2083
|  |  | 8040320 |  |  |  | -339679.2083
|  |  | 8040330 |  |  |  | -339679.2083
|  |  | 8040340 |  |  |  | -339679.2083
|  |  | 8040350 |  |  |  | -339679.2083
|  |  | 8040360 |  |  |  | -339679.2083
|  |  | 8040370 |  |  |  | -339679.2083
|  |  | 8040380 |  |  |  | 1981-08-27
|  |  | 8040390 |  |  |  | -339679.2083
|  |  | 8040400 |  |  |  | -339679.2083
|  |  | 8040420 |  |  |  | -339679.2083
|  |  | 8040430 |  |  |  | -339679.2083
|  |  | 8040440 |  |  |  | -339679.2083
|  |  | 8040490 |  |  |  | -339679.2083
|  |  | 8040500 |  |  |  | -339679.2083
|  |  | 8040510 |  |  |  | -339679.2083
|  |  | 8040520 |  |  |  | -339679.2083
|  |  | 8040530 |  |  |  | -339679.2083
|  |  | 8040540 |  |  |  | -339679.2083
|  |  | 8040570 |  |  |  | -339679.2083
|  |  | 8040620 |  |  |  | 1985-12-17
|  |  | 8040630 |  |  |  | 1981-05-19
|  |  | 8040670 |  |  |  | 1982-03-23
|  |  | 8040721 |  |  |  | -339679.2083
|  |  | 8040740 |  |  |  | -339679.2083
|  |  | 8040810 |  |  |  | 1983-01-18
|  |  | 8040820 |  |  |  | -339679.2083
|  |  | 8040840 |  |  |  | 1984-04-17
|  |  | 8040860 |  |  |  | 1987-01-13
|  |  | 8040890 |  |  |  | 1984-08-21
|  |  | 8040920 |  |  |  | 1985-09-24
|  |  | 8040940 |  |  |  | -339679.2083
|  |  | 8040950 |  |  |  | 1982-11-16
|  |  | 8040960 |  |  |  | 1982-11-16
|  |  | 8040980 |  |  |  | -339679.2083
|  |  | 8040990 |  |  |  | -339679.2083
|  |  | 8041000 |  |  |  | 1987-07-07
|  |  | 8041020 |  |  |  | -339679.2083
|  |  | 8041060 |  |  |  | -339679.2083
|  |  | 8041080 |  |  |  | -339679.2083
|  |  | 8041110 |  |  |  | -339679.2083
|  |  | 8041130 |  |  |  | -339679.2083
|  |  | 8041140 |  |  |  | -339679.2083
|  |  | 8041150 |  |  |  | -339679.2083
|  |  | 8041170 |  |  |  | -339679.2083
|  |  | 8041270 |  |  |  | 1982-03-23
|  |  | 8041290 |  |  |  | 1983-02-22
|  |  | 8041360 |  |  | Indiana Department of Transportation | 1981-11-17
|  |  | 8041420 |  |  | Indiana Department of Transportation | 1980-07-15
|  |  | 8041450 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1983-03-29
|  |  | 8041520 |  |  |  | 1981-09-22
|  |  | 8043940 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-11-16
|  |  | 8043950 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8044140 |  |  |  | 1981-01-20
|  |  | 8044150 |  |  |  | -339679.2083
|  |  | 8044160 |  |  |  | -339679.2083
|  |  | 8044210 |  |  |  | 1981-06-23
|  |  | 8044250 |  |  |  | 1981-05-19
|  |  | 8044260 |  |  |  | -339679.2083
|  |  | 8044270 |  |  |  | -339679.2083
|  |  | 8044300 |  |  |  | -339679.2083
|  |  | 8044780 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8044960 |  |  | Indiana Department of Transportation | 1982-01-26
|  |  | 8045500 |  |  | Indiana Department of Transportation | 1993-12-14
|  |  | 8068100 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8068101 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8068102 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 806810A |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-05-19
|  |  | 806810B |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-05-19
|  |  | 806810D |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 806810E |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 806810F |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 806810G |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 806810H |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 8068110 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8068111 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-11-15
|  |  | 8068112 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-11-15
|  |  | 8068114 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8068115 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8068120 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8068121 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-02-14
|  |  | 8068122 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-02-14
|  |  | 8068124 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8068125 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8068127 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8100040 |  |  |  | 1984-07-17
|  |  | 8100100 |  |  | Indiana Department of Transportation | 1996-06-04
|  |  | 8100530 |  |  | Indiana Department of Transportation | 1996-02-20
|  |  | 8100700 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8100850 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8100851 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8100860 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1983-04-26
|  |  | 8100861 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8100870 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8100871 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8100880 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8100881 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8100890 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-04-26
|  |  | 8100900 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8101160 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8101180 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8101181 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8101182 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8101190 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8101220 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8101280 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8101310 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8101360 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8101380 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8101410 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 8101670 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8101850 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8102050 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-01-26
|  |  | 8102060 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1981-12-15
|  |  | 8102080 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8102090 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8102460 |  |  |  | 1983-09-20
|  |  | 8102500 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8102540 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1982-03-23
|  |  | 8102650 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 1982-04-20
|  |  | 8102710 |  |  | Indiana Department of Transportation | 1994-01-11
|  |  | 8102780 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 1982-01-26
|  |  | 8102790 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1982-05-18
|  |  | 8102980 |  | Global Land Surveying, LLC | Indiana Department of Transportation | 1982-04-20
|  |  | 8102990 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8103010 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-03-23
|  |  | 8103110 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8103570 | Starke |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8103801 |  |  |  | -339679.2083
|  |  | 8104070 |  |  |  | 1983-08-23
|  |  | 8104110 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8104160 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8104340 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8104390 |  |  | Indiana Department of Transportation | 1981-12-15
|  |  | 8104400 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8104890 | Harrison |  | Indiana Department of Transportation | 2000-11-21 | CE
CN
|  |  | 8104970 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8105010 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8105140 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 8105380 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1983-05-24
|  |  | 8105420 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 8105640 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8105660 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8105690 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8105720 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-06-21
|  |  | 8105740 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-06-21
|  |  | 8105830 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8105930 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8105960 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8105970 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8106010 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8106220 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8106270 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8106410 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8106470 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8106660 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8106710 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8106740 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8106760 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1984-02-14
|  |  | 8106780 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1984-02-14
|  |  | 8106870 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1984-02-14
|  |  | 8106930 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1984-02-14
|  |  | 8106940 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8107360 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1981-04-21
|  |  | 8107371 |  | CGI | Indiana Department of Transportation | 1985-06-25
|  |  | 8107610 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8107710 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8107890 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1987-06-02
|  |  | 8107950 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8108022 |  |  |  | 1983-08-23
|  |  | 8108080 |  | ASA Land Surveying | Indiana Department of Transportation | 1986-10-14
|  |  | 8108170 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 8108210 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8108380 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8108390 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8109250 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8109680 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8109860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8110060 |  |  |  | 1983-06-21
|  |  | 8110140 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1984-02-14
|  |  | 8110390 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8110500 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 8110580 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8110730 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8110810 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8110830 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1987-12-15
|  |  | 8110990 |  | Abonmarche Consultants of Indiana L.L.C. | Indiana Department of Transportation | -339679.2083
|  |  | 8111520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8111540 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1984-12-18
|  |  | 8112750 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8112910 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8113120 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8113130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8114280 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8114380 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-11-15
|  |  | 8114630 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-11-15
|  |  | 8114680 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8114810 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8114880 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8115050 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8115130 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8115310 |  |  |  | 1982-04-20
|  |  | 8115390 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8115689 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 8115690 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 8116000 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 8116331 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8116690 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8117061 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1983-03-29
|  |  | 8117062 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1983-03-29
|  |  | 8117063 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1983-03-29
|  |  | 8117064 |  | American Commercial Title & Escrow | Indiana Department of Transportation | 1983-03-29
|  |  | 8117065 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8117066 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8117070 |  |  | Indiana Department of Transportation | 1982-07-20
|  |  | 8117141 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8117142 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8117143 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8117190 |  |  | Indiana Department of Transportation | 1982-07-20
|  |  | 8117701 |  |  | Indiana Department of Transportation | 1982-04-06
|  |  | 8118400 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8118430 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-06-23
|  |  | 8118560 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8118580 |  | GS-IN P.C. | Indiana Department of Transportation | 1982-02-23
|  |  | 8118581 |  | GS-IN P.C. | Indiana Department of Transportation | 1982-02-23
|  |  | 8118640 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8118820 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8119141 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8119142 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8119250 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8119310 |  |  |  | 1982-11-16
|  |  | 8119470 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 8119490 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8119500 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8119610 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8119820 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8120010 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8120230 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1986-07-15
|  |  | 8120350 |  |  |  | 1982-03-23
|  |  | 8120401 |  | Eco Logic, LLC | Indiana Department of Transportation | 1980-11-18
|  |  | 8120481 |  |  | Indiana Department of Transportation | 1981-03-24
|  |  | 8120521 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1983-07-26
|  |  | 8120670 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1981-01-20
|  |  | 8120760 |  |  |  | 1982-04-20
|  |  | 8120810 |  |  |  | 1981-11-17
|  |  | 8120870 |  | EnviroScience, Inc. | Indiana Department of Transportation | 1981-06-23
|  |  | 8120871 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8120880 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1982-01-26
|  |  | 8120910 |  |  |  | 1981-12-15
|  |  | 8120920 |  |  |  | 1982-01-26
|  |  | 8121170 |  |  | Indiana Department of Transportation | 1980-12-16
|  |  | 8121260 |  | ASA Land Surveying | Indiana Department of Transportation | 1981-12-15
|  |  | 8121440 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8121600 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1981-02-24
|  |  | 8121650 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8121651 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8121652 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8121653 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8121654 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8121655 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8121656 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8121710 |  |  |  | 1984-08-21
|  |  | 8121800 |  |  |  | 1982-09-21
|  |  | 8121820 |  |  |  | 1982-01-26
|  |  | 8121850 |  |  |  | 1984-01-17
|  |  | 8121870 |  |  |  | 1982-10-26
|  |  | 8122010 |  |  |  | 1982-06-15
|  |  | 8122130 |  |  | LaPorte County | -339679.2083
|  |  | 8122220 |  | Dodd Title Corporation | Indiana Department of Transportation | 1982-01-26
|  |  | 8122230 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-02-23
|  |  | 8122240 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8122250 |  |  | Indiana Department of Transportation | 1982-01-26
|  |  | 8122290 |  |  |  | 1982-06-15
|  |  | 8122330 |  |  |  | 1983-11-15
|  |  | 8122350 |  |  |  | 1989-05-16
|  |  | 8122420 | Delaware |  | Muncie | -339679.2083 | RR
|  |  | 8122430 |  |  |  | -339679.2083
|  |  | 8122470 |  |  |  | -339679.2083
|  |  | 8122480 |  |  |  | -339679.2083
|  |  | 8122490 |  |  |  | -339679.2083
|  |  | 8122510 |  |  |  | -339679.2083
|  |  | 8122530 |  |  |  | -339679.2083
|  |  | 8122540 |  |  |  | -339679.2083
|  |  | 8122560 |  |  |  | -339679.2083
|  |  | 8122580 |  |  |  | -339679.2083
|  |  | 8122600 |  |  |  | -339679.2083
|  |  | 8122610 |  |  |  | -339679.2083
|  |  | 8122620 |  |  |  | -339679.2083
|  |  | 8122630 |  |  |  | -339679.2083
|  |  | 8122640 |  |  |  | -339679.2083
|  |  | 8122650 |  |  |  | -339679.2083
|  |  | 8122690 |  |  |  | -339679.2083
|  |  | 8122740 |  |  |  | -339679.2083
|  |  | 8122750 |  |  |  | -339679.2083
|  |  | 8122760 |  |  |  | -339679.2083
|  |  | 8122770 |  |  |  | -339679.2083
|  |  | 8122780 |  |  |  | -339679.2083
|  |  | 8123730 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8123800 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8123880 |  |  |  | -339679.2083
|  |  | 8124600 |  |  | Hancock County | -339679.2083
|  |  | 8124650 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8124670 | LaPorte |  | LaPorte County | -339679.2083 | CE
PE
RR
|  |  | 8124930 |  |  |  | -339679.2083
|  |  | 8125000 |  |  |  | -339679.2083
|  |  | 8125010 | Hendricks |  | La Porte | -339679.2083 | RR
|  |  |  | LaPorte |  | La Porte | -339679.2083 | CE
PE
|  |  | 8125020 |  |  |  | -339679.2083
|  |  | 8125030 |  |  |  | -339679.2083
|  |  | 8125040 |  |  |  | -339679.2083
|  |  | 8125050 |  |  |  | -339679.2083
|  |  | 8125080 |  |  |  | -339679.2083
|  |  | 8125100 |  |  |  | -339679.2083
|  |  | 8125130 |  |  |  | -339679.2083
|  |  | 8125190 |  |  |  | -339679.2083
|  |  | 8125200 |  |  |  | -339679.2083
|  |  | 8125210 |  |  |  | -339679.2083
|  |  | 8125220 |  |  |  | -339679.2083
|  |  | 8125240 |  |  |  | -339679.2083
|  |  | 8125260 |  |  |  | -339679.2083
|  |  | 8125340 |  |  |  | -339679.2083
|  |  | 8125350 |  |  |  | -339679.2083
|  |  | 8125400 |  |  |  | -339679.2083
|  |  | 8125430 |  |  |  | -339679.2083
|  |  | 8125710 |  |  |  | 1983-05-24
|  |  | 8125720 |  |  |  | 1983-04-26
|  |  | 8125754 |  | CGI | Indiana Department of Transportation | 1986-07-15
|  |  | 8125755 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8125756 |  | CGI | Indiana Department of Transportation | 1986-07-15
|  |  | 8125757 |  | CGI | Indiana Department of Transportation | 1986-07-15
|  |  | 8125759 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 812575A |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 812575B |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 812575C |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 812575D |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 812575E |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 812575F |  | CGI | Indiana Department of Transportation | 1985-11-19
|  |  | 812575G |  | CGI | Indiana Department of Transportation | 1985-10-29
|  |  | 812575N |  | CGI | Indiana Department of Transportation | 1988-05-17
|  |  | 812575P |  | CGI | Indiana Department of Transportation | 1988-05-17
|  |  | 812575R |  | CGI | Indiana Department of Transportation | 1987-10-20
|  |  | 812575S |  | CGI | Indiana Department of Transportation | 1988-04-19
|  |  | 8125811 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8127300 |  |  | LaPorte County | -339679.2083
|  |  | 8127310 |  |  | LaPorte County | -339679.2083
|  |  | 8130070 |  |  |  | 1986-10-14
|  |  | 8130901 |  | CGI | Indiana Department of Transportation | 1985-06-25
|  |  | 8131410 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8131860 |  |  |  | -339679.2083
|  |  | 8132120 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8133340 |  |  |  | 1985-07-23
|  |  | 8133530 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8133620 |  |  | Grant County | 1994-01-11
|  |  | 8134770 | Wayne | Indiana Appraisal Group, Inc. | Richmond | 1998-04-07 | CE
CN
PE
ROW
|  |  | 8134881 |  |  |  | 1983-04-26
|  |  | 8137110 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8137120 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8137130 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8138090 | Vanderburgh |  | Vanderburgh County | -339679.2083 | PE
ROW
|  |  | 8139740 |  |  |  | 1988-08-16
|  |  | 8140660 |  | CTL Engineering of Indiana, Inc. | Fort Wayne | -339679.2083
|  |  | 8140690 |  |  |  | 1983-06-21
|  |  | 8140770 |  |  |  | -339679.2083
|  |  | 8141490 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8141550 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 8141551 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1981-04-21
|  |  | 8142100 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8142101 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8142260 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8142600 |  |  | Indiana Department of Transportation | 1981-04-21
|  |  | 8143920 |  |  | Indiana Department of Transportation | 1981-09-22
|  |  | 8143930 |  |  | Indiana Department of Transportation | 1981-10-27
|  |  | 8144320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8144570 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8144580 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8144590 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8144600 | Porter |  | Indiana Department of Transportation | 2002-10-22 | CE
CN
ROW
|  |  | 8144610 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8144620 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8144640 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8144710 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8144720 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8144730 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8144740 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8144790 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8144800 |  | ERES International, Inc. | Indiana Department of Transportation | 1990-06-05
|  |  | 8144830 |  |  | Indiana Department of Transportation | 1983-10-25
|  |  | 8144850 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1994-02-08
|  |  | 8144880 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8144900 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8144910 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8144920 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8144930 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8144940 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8144950 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8144980 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8144990 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8145010 |  |  | Indiana Department of Transportation | 1994-10-18
|  |  | 8145040 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 8145050 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8145060 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8145070 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8145080 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8145090 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8145100 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8145110 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1987-05-19
|  |  | 8145120 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-06-25
|  |  | 8145140 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1993-02-16
|  |  | 8145150 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8145160 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-02-18
|  |  | 8145170 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-02-18
|  |  | 8145180 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-02-18
|  |  | 8145190 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8145210 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8145220 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-03-19
|  |  | 8145250 |  | Chicago Title Insurance Company | Indiana Department of Transportation | 1984-11-20
|  |  | 8145270 |  | Bella Villa Realtors, LLC | Indiana Department of Transportation | 1993-03-16
|  |  | 8145280 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8145290 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8145300 | Putnam |  | Indiana Department of Transportation | 2001-04-24 | CE
CN
PE
|  |  | 8145310 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8145330 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8145340 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8145350 | Allen |  | Indiana Department of Transportation | -339679.2083 | ROW
|  |  | 8145360 |  |  | Indiana Department of Transportation | 1994-07-19
|  |  | 8145380 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8145400 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-01-12
|  |  | 8145410 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8145420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8145430 |  | CGI | Indiana Department of Transportation | 1984-07-17
|  |  | 8145440 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1986-01-04
|  |  | 8145450 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1986-01-04
|  |  | 8145460 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8145470 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8145480 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8145490 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8145510 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8145530 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8145550 | Dearborn |  | Indiana Department of Transportation | 2008-04-23 | CE
CN
PE
UT
|  |  | 8145560 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8145570 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8145580 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8145590 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8145600 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8145610 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8145620 | Franklin |  | Indiana Department of Transportation | 2013-03-29 | PE
|  |  | 8200570 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8200571 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8200572 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8200573 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8200574 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8200575 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8200576 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8200577 |  |  | Indiana Department of Transportation | 1983-03-29
|  |  | 8200720 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-03-20
|  |  | 8201620 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-08-23
|  |  | 8201621 |  |  | Indiana Department of Transportation | 1983-08-23
|  |  | 8201710 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8201740 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1982-05-18
|  |  | 8201840 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8201950 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8202410 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8202411 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8202570 |  | Consolidated Test Company | Indiana Department of Transportation | 1985-05-21
|  |  | 8203150 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8203300 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8203310 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8203390 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8203500 |  |  |  | 1982-03-23
|  |  | 8203510 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8203730 |  |  |  | -339679.2083
|  |  | 8203860 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8204030 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8204280 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8204570 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8204580 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8205020 |  |  | Indiana Department of Transportation | 1994-01-11
|  |  | 8205100 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8205550 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8205600 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8205670 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8205840 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8205880 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8205920 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8206030 |  |  | Posey County | -339679.2083
|  |  | 8206050 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 8206051 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 8206171 |  |  | Indiana Department of Transportation | 1982-06-23
|  |  | 8206350 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8206400 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8206510 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8206610 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8206620 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8206690 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8206840 |  |  | Indiana Department of Transportation | 1994-08-16
|  |  | 8206880 |  |  |  | 1985-06-25
|  |  | 8207020 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8207080 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 8207090 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8207320 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8207350 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8207380 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8207410 |  |  |  | 1981-09-22
|  |  | 8207430 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8207450 |  | Eco Logic, LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8207600 |  |  | Indiana Department of Transportation | 1981-08-25
|  |  | 8207700 |  | Engineering Technologies, Inc. | Indiana Department of Transportation | 1992-05-21
|  |  | 8207701 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8207740 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8207780 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8207910 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8208561 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 8208580 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8208630 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8208720 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-08-27
|  |  | 8209140 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-02-19
|  |  | 8209340 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1984-04-17
|  |  | 8209550 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8209640 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8209660 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8209750 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1984-07-17
|  |  | 8210040 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8210200 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8210230 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8210370 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8210900 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8210910 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8210920 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8210940 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8210970 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8211050 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8211120 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8211250 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8211460 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 8211510 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-08-21
|  |  | 8211690 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 8211760 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8211770 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8211780 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8211960 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8211990 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8212070 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8212080 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8212120 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8212150 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8212151 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8212210 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8212310 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8212330 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8212340 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8212400 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8212430 |  | Another Test Company | Indiana Department of Transportation | 1984-11-20
|  |  | 8212540 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8212620 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8212650 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8212720 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8212780 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8212830 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8212960 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 1982-09-21
|  |  | 8212980 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8213021 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8213150 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8213190 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8213330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8213350 |  |  |  | 1983-10-25
|  |  | 8213370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8213390 | Dekalb |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8213410 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8213510 |  |  |  | 1983-10-25
|  |  | 8213550 |  | CGI | Indiana Department of Transportation | -339679.2083
|  |  | 8213590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8213640 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8213670 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8213680 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8213790 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1982-09-21
|  |  | 8213830 |  | Eco Logic, LLC | Indiana Department of Transportation | 1982-10-26
|  |  | 8213840 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1982-11-16
|  |  | 8213860 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8213880 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8213940 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1983-02-22
|  |  | 8214000 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 1983-06-21
|  |  | 8214020 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 8214040 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8214070 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8214080 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8214160 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8214170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8214270 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 1982-09-21
|  |  | 8214300 |  | All About Pavements, Inc. | Indiana Department of Transportation | 1982-10-26
|  |  | 8214370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8214400 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 8214430 |  | Casteel Real Estate | Indiana Department of Transportation | 1983-01-18
|  |  | 8214440 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1982-10-26
|  |  | 8214510 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1982-12-14
|  |  | 8214520 |  |  | Indiana Department of Transportation | 1982-12-14
|  |  | 8214660 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8214750 | Lake |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8214780 | Wells | Accidental Discoveries, LLC | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8214830 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8214910 | Lake | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8214960 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8215060 | Wells |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8215080 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1983-05-24
|  |  | 8215090 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-06-21
|  |  | 8215220 |  |  | Indiana Department of Transportation | 1991-10-24
|  |  | 8215230 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 1982-09-21
|  |  | 8215260 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1994-02-08
|  |  | 8215270 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1982-09-21
|  |  | 8215280 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 8215370 |  | Consolidated Test Company | Indiana Department of Transportation | 1983-01-18
|  |  | 8215530 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1983-06-21
|  |  | 8215610 | Morgan |  | Indiana Department of Transportation | 1998-04-07 | CE
CN
|  |  | 821561A |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8215870 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8215960 | Tippecanoe | DuSABLE, Inc. | Indiana Department of Transportation | 1995-01-25 | PE
ROW
|  |  | 8216090 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-09-21
|  |  | 8217281 |  |  | Indiana Department of Transportation | 1982-09-20
|  |  | 8217300 |  |  | Indiana Department of Transportation | 1982-07-20
|  |  | 8218420 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-09-21
|  |  | 8218500 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-12-14
|  |  | 8218600 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-09-21
|  |  | 8218630 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-12-14
|  |  | 8218960 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-09-21
|  |  | 8219350 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8219411 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8219412 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8219413 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8219414 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8219460 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1982-08-24
|  |  | 8219830 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1983-09-20
|  |  | 8219920 |  | CGI | Indiana Department of Transportation | 1982-10-26
|  |  | 8220090 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1983-01-18
|  |  | 8220250 |  | EnviroScience, Inc. | Indiana Department of Transportation | 1982-09-21
|  |  | 8220260 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 8220270 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8220280 |  | ARCADIS | Indiana Department of Transportation | 1982-11-16
|  |  | 8220330 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8220360 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8220361 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8220370 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8220440 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 8220450 |  |  | Indiana Department of Transportation | 1982-12-14
|  |  | 8220550 |  |  |  | 1984-05-15
|  |  | 8220600 |  |  |  | 1982-06-15
|  |  | 8220620 |  |  |  | 1982-06-15
|  |  | 8220640 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1982-10-26
|  |  | 8220650 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8220930 |  |  |  | 1983-06-21
|  |  | 8221171 |  |  | Indiana Department of Transportation | 1980-12-16
|  |  | 8221180 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1983-12-13
|  |  | 8221190 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1982-10-26
|  |  | 8221300 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1984-06-12
|  |  | 8221360 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1991-11-19
|  |  | 8221361 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1985-03-19
|  |  | 8221370 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-11-16
|  |  | 8221420 |  |  |  | 1984-03-20
|  |  | 8221441 |  |  | Indiana Department of Transportation | 1980-11-18
|  |  | 8221540 |  |  | Dubois County | -339679.2083
|  |  | 8221550 |  |  | Franklin County | -339679.2083
|  |  | 8221560 |  |  | Martin County | -339679.2083
|  |  | 8221570 |  |  |  | 1982-08-24
|  |  | 8221580 |  |  |  | 1982-08-24
|  |  | 8221590 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8221601 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1981-02-24
|  |  | 8221610 |  |  |  | 1982-09-21
|  |  | 8221690 |  |  |  | 1989-05-16
|  |  | 8221840 |  |  | Indiana Department of Transportation | 1982-09-21
|  |  | 8221890 |  |  |  | -339679.2083
|  |  | 8221910 |  |  |  | -339679.2083
|  |  | 8221920 |  |  |  | -339679.2083
|  |  | 8221930 |  |  |  | -339679.2083
|  |  | 8221940 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8221941 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8221950 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8221960 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8221970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8221971 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8221972 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8221973 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8221980 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8221990 |  |  | Indiana Department of Transportation | 1983-01-18
|  |  | 8222000 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8222040 |  |  |  | 1987-10-20
|  |  | 8222090 |  |  |  | 1988-10-18
|  |  | 8222160 |  |  |  | 1985-03-19
|  |  | 8222320 |  |  |  | 1983-07-26
|  |  | 8222360 |  |  |  | 1985-11-19
|  |  | 8222800 |  |  |  | 1983-07-01
|  |  | 8222870 |  |  |  | 1983-03-29
|  |  | 8223050 |  | Carters Appraisal Service | Indiana Department of Transportation | 1987-12-15
|  |  | 8223170 |  |  |  | 1984-02-14
|  |  | 8223180 |  |  |  | -339679.2083
|  |  | 8223570 |  |  |  | 1983-07-26
|  |  | 8223900 |  |  |  | 1983-04-26
|  |  | 8223990 |  |  |  | 1986-05-13
|  |  | 8224000 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8224220 |  |  |  | 1983-04-26
|  |  | 8224410 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8224540 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8224770 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8224771 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8224990 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8225180 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8225320 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8225330 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8225440 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8225480 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8225520 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8225530 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8225670 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8225680 |  |  |  | 1983-03-29
|  |  | 8225801 |  | Global Management Group, Inc. | Indiana Department of Transportation | 1982-02-23
|  |  | 8225810 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8225820 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1981-09-22
|  |  | 8225821 |  | Consolidated Test Company | Indiana Department of Transportation | 1982-01-26
|  |  | 8225830 |  | CGI | Indiana Department of Transportation | 1981-09-22
|  |  | 8225831 |  | CGI | Indiana Department of Transportation | 1981-09-22
|  |  | 8225840 |  | Consolidated Test Company | Indiana Department of Transportation | 1982-01-26
|  |  | 8225850 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 1981-11-17
|  |  | 8225860 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-11-17
|  |  | 8225900 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8225950 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8225980 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8225981 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8225990 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8226030 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8226040 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8226050 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8226090 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8226100 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8226110 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8226120 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8226130 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8226140 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8226150 |  | Dreibelbiss Title Company, Inc. | Indiana Department of Transportation | 1994-01-11
|  |  | 8226170 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8226180 |  |  | Indiana Department of Transportation | 1981-10-27
|  |  | 8226190 |  | Eco Logic, LLC | Indiana Department of Transportation | 1981-10-27
|  |  | 8226191 |  | Eco Logic, LLC | Indiana Department of Transportation | 1981-10-27
|  |  | 8226200 |  | DCD Consulting LLC | Indiana Department of Transportation | 1981-11-17
|  |  | 8226220 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1981-12-15
|  |  | 8226221 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1982-04-20
|  |  | 8226230 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1981-12-15
|  |  | 8226240 |  | Carters Appraisal Service | Indiana Department of Transportation | 1981-12-15
|  |  | 8226250 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1981-11-17
|  |  | 8226260 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1981-12-15
|  |  | 8226270 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1981-12-15
|  |  | 8226290 |  | ASA Land Surveying | Indiana Department of Transportation | 1981-12-15
|  |  | 8226300 |  | KHAFRA Engineering Consultants, Inc. | Indiana Department of Transportation | 1981-12-15
|  |  | 8226310 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1981-12-15
|  |  | 8226320 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1982-01-26
|  |  | 8226330 |  | ERES International, Inc. | Indiana Department of Transportation | 1981-12-15
|  |  | 8226340 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-02-23
|  |  | 8226350 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1982-02-23
|  |  | 8226360 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1982-02-23
|  |  | 8226370 |  | Global Management Group, Inc. | Indiana Department of Transportation | 1982-02-23
|  |  | 8226380 |  | GS-IN P.C. | Indiana Department of Transportation | 1982-01-26
|  |  | 8226390 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8226391 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8226400 |  | CE Solutions, Inc. | Indiana Department of Transportation | 1982-02-23
|  |  | 8226410 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8226411 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-04-26
|  |  | 8226530 |  |  | Adams County | -339679.2083
|  |  | 8226540 |  |  | Dearborn County | -339679.2083
|  |  | 8226550 |  |  |  | -339679.2083
|  |  | 8226570 |  |  | Jefferson County | -339679.2083
|  |  | 8226580 |  |  | Madison County | -339679.2083
|  |  | 8226590 |  |  | Montgomery County | -339679.2083
|  |  | 8226600 |  |  | Morgan County | -339679.2083
|  |  | 8226610 |  |  | Noble County | -339679.2083
|  |  | 8226620 |  |  | Owen County | -339679.2083
|  |  | 8226630 |  |  | Putnam County | -339679.2083
|  |  | 8226640 |  |  | Shelby County | -339679.2083
|  |  | 8226660 |  |  | Union County | -339679.2083
|  |  | 8226670 |  |  | Vermillion County | -339679.2083
|  |  | 8226680 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8226700 |  |  |  | -339679.2083
|  |  | 8226730 | LaPorte | Douglass Environmental Services, Inc. | La Porte | -339679.2083 | CE
CN
|  |  | 8226750 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8226800 |  |  |  | -339679.2083
|  |  | 8226950 |  |  | Benton County | -339679.2083
|  |  | 8226980 |  |  | Delaware County | -339679.2083
|  |  | 8227020 |  |  | Hendricks County | -339679.2083
|  |  | 8227040 |  |  | Jennings County | -339679.2083
|  |  | 8227060 |  |  | Lawrence County | -339679.2083
|  |  | 8227100 |  |  | Tippecanoe County | -339679.2083
|  |  | 8227110 |  |  | Tipton County | -339679.2083
|  |  | 8227140 |  |  | Wayne County | -339679.2083
|  |  | 8227150 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8227160 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8227161 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8227170 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8227180 |  |  | Fulton County | -339679.2083
|  |  | 8227200 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8227210 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8227211 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1989-07-18
|  |  | 8227230 |  |  |  | 1983-03-29
|  |  | 8227370 |  |  |  | -339679.2083
|  |  | 8227410 |  |  |  | 1983-03-29
|  |  | 8227430 |  |  |  | 1984-05-15
|  |  | 8227470 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 8227480 |  |  | Indiana Department of Transportation | 1991-12-05
|  |  | 8227490 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8227500 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8227510 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8227520 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8227530 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8227580 |  |  |  | -339679.2083
|  |  | 8227640 |  |  |  | -339679.2083
|  |  | 8227680 |  |  |  | -339679.2083
|  |  | 8227690 |  |  |  | -339679.2083
|  |  | 8227850 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8227851 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8227860 |  |  | Indiana Department of Transportation | 1982-06-15
|  |  | 8228050 |  |  |  | 1983-06-21
|  |  | 8228200 |  |  | Indiana Department of Transportation | 1982-10-26
|  |  | 8228650 |  |  |  | 1984-05-15
|  |  | 8229040 |  |  |  | 1986-03-18
|  |  | 8229560 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-10-25
|  |  | 8229720 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8229721 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8229730 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8229740 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8229860 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8229880 |  | Consolidated Test Company | Indiana Department of Transportation | 1982-07-20
|  |  | 8229910 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8229920 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1982-07-20
|  |  | 8229960 |  | Consolidated Test Company | Indiana Department of Transportation | 1982-07-20
|  |  | 8230120 |  |  |  | 1983-05-24
|  |  | 8230130 |  |  | Spencer County | -339679.2083
|  |  | 8230390 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8230410 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8230450 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8230460 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8230490 | St. Joseph |  | South Bend | -339679.2083 | PE
ROW
|  |  | 8230580 |  |  |  | -339679.2083
|  |  | 8230730 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-07-20
|  |  | 8230880 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-07-20
|  |  | 8230990 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1982-07-20
|  |  | 8231040 |  |  | Indiana Department of Transportation | 1982-07-20
|  |  | 8231870 |  |  |  | -339679.2083
|  |  | 8232250 |  |  |  | 1986-10-14
|  |  | 8232910 |  |  | Floyd County | -339679.2083
|  |  | 8232990 |  |  |  | 1989-06-13
|  |  | 8233050 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8233440 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8233490 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8233500 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8233810 |  |  |  | 1983-12-13
|  |  | 8233890 |  |  |  | 1983-07-01
|  |  | 8234510 |  |  | Indiana Department of Transportation | 1983-06-21
|  |  | 8234580 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8234590 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8234680 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8234720 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8234730 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8234791 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8234800 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8234850 |  |  |  | 1986-08-19
|  |  | 8234930 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8234970 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8235310 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8235340 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8235351 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8235391 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8235410 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8235420 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8235440 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8235460 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8235470 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8235471 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8235472 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8235480 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8235490 |  |  | Indiana Department of Transportation | 1982-03-23
|  |  | 8235491 |  |  | Indiana Department of Transportation | 1984-04-20
|  |  | 8235500 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8235510 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8235860 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8235870 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8235900 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8235970 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8235980 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8236000 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8236001 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8236040 |  | Collier Transport Inc. | Indiana Department of Transportation | 1984-12-18
|  |  | 8236050 |  | Collier Transport Inc. | Indiana Department of Transportation | 1984-12-18
|  |  | 8236090 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8236110 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8236120 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8236160 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8236440 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8236570 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8236580 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8236620 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8236660 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8236670 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8236730 |  |  | Indiana Department of Transportation | 1983-02-22
|  |  | 8236760 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8236770 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8236780 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8236790 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8236800 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8236810 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8236820 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8236830 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8236850 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8236860 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8237020 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8237210 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8237270 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8237350 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8237390 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8237410 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8237420 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8237430 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8237440 |  |  |  | 1983-11-15
|  |  | 8237450 |  | Metropolitan Title of Indiana, LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8237490 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8237500 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8237510 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8237520 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8237540 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8237630 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8237680 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8237740 | Perry |  | Indiana Department of Transportation | 2001-02-13 | CE
CN
|  |  | 8237750 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8237760 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8237820 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8237830 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8237850 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8237860 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8237870 |  |  |  | 1984-05-15
|  |  | 8237920 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8238020 |  |  |  | 1985-10-29
|  |  | 8238050 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8238060 |  |  | Indiana Department of Transportation | 1983-02-23
|  |  | 8238100 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8238240 |  | GS-IN P.C. | Indiana Department of Transportation | 1982-08-24
|  |  | 8238250 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1982-09-21
|  |  | 8238260 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1982-09-21
|  |  | 8238270 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1982-11-16
|  |  | 8238280 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-08-24
|  |  | 8238290 |  | DCD Consulting LLC | Indiana Department of Transportation | 1982-08-24
|  |  | 8238330 |  |  |  | 1984-09-18
|  |  | 8238340 |  |  |  | 1983-12-13
|  |  | 8238380 |  |  |  | 1985-04-16
|  |  | 8238390 |  |  |  | 1984-04-17
|  |  | 8238400 |  |  |  | 1988-06-14
|  |  | 8240780 |  |  |  | -339679.2083
|  |  | 8240900 |  |  |  | 1985-10-29
|  |  | 8241250 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8241351 |  |  | Indiana Department of Transportation | 1982-01-26
|  |  | 8241352 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8241371 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8241372 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8241391 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1981-09-14
|  |  | 8241411 |  |  | Indiana Department of Transportation | 1981-06-23
|  |  | 8241421 |  | Consolidated Test Company | Indiana Department of Transportation | 1980-07-15
|  |  | 8241560 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8241570 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8241580 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8241590 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8241600 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8241610 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8241730 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8241830 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 8242010 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8242040 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8242050 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242060 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8242070 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8242080 |  |  | Indiana Department of Transportation | 1983-08-23
|  |  | 8242090 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8242110 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242120 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8242130 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8242170 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242190 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8242200 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8242210 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8242220 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 8242280 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8242290 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8242300 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8242320 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242420 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8242430 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8242450 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8242610 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242620 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242650 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242660 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242670 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8242680 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8242700 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1984-06-12
|  |  | 8242710 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8242720 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8242740 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8242810 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8242830 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8242850 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8242920 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8242940 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8242970 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8242980 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8242990 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8243000 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8243010 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8243020 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8243040 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8243050 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8243060 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8243070 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8243120 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8243130 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8243210 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8243220 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8243240 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8243280 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8243300 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8243440 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8243490 |  |  | Indiana Department of Transportation | 1982-05-18
|  |  | 8243520 |  |  | Indiana Department of Transportation | 1982-02-23
|  |  | 8243530 |  |  | Indiana Department of Transportation | 1981-07-21
|  |  | 8243540 |  |  | Indiana Department of Transportation | 1982-04-20
|  |  | 8243570 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8243580 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8243590 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8243600 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8243620 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8243650 |  |  | Indiana Department of Transportation | 1996-03-19
|  |  | 8243660 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8243670 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8255980 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8257100 |  |  |  | 1985-09-24
|  |  | 8300631 |  | Mackie Consultants, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 8300632 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8301431 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 1993-03-16
|  |  | 8301511 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8301521 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1990-10-16
|  |  | 8303020 |  |  |  | 1983-08-17
|  |  | 8303460 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8304651 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8304691 |  |  |  | -339679.2083
|  |  | 8304841 |  |  | Indiana Department of Transportation | 1983-10-25
|  |  | 8306621 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8306910 |  |  |  | 1984-11-20
|  |  | 8309180 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8309940 |  |  |  | 1987-02-03
|  |  | 8309960 |  |  |  | 1985-11-19
|  |  | 8310010 |  |  |  | 1987-02-03
|  |  | 8310961 |  |  |  | 1983-09-20
|  |  | 8311761 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8312282 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8313690 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8313691 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1983-12-13
|  |  | 8313692 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8313841 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8314161 |  |  | Indiana Department of Transportation | 1982-11-16
|  |  | 8314690 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1983-11-15
|  |  | 8315701 |  |  | Indiana Department of Transportation | 1983-10-11
|  |  | 8320271 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8322060 |  |  |  | 1983-02-22
|  |  | 8322520 |  |  |  | -339679.2083
|  |  | 8322830 |  |  |  | 1987-11-17
|  |  | 8323460 |  |  |  | -339679.2083
|  |  | 8324010 |  |  |  | 1984-10-23
|  |  | 8324400 |  |  |  | 1985-10-29
|  |  | 8324430 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8324431 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8324432 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8324440 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8324441 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8324442 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8324470 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8324510 |  |  |  | -339679.2083
|  |  | 8324790 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8324791 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8326070 |  |  |  | -339679.2083
|  |  | 8326080 |  |  |  | -339679.2083
|  |  | 8326412 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8326480 |  |  |  | -339679.2083
|  |  | 8326500 |  |  |  | -339679.2083
|  |  | 8326650 |  |  | Sullivan County | -339679.2083
|  |  | 8326681 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8326720 |  |  |  | -339679.2083
|  |  | 8326890 |  |  |  | -339679.2083
|  |  | 8326960 |  |  | Cass County | -339679.2083
|  |  | 8326970 |  |  | Clay County | -339679.2083
|  |  | 8326990 |  |  | Fayette County | -339679.2083
|  |  | 8327000 |  |  | Fountain County | -339679.2083
|  |  | 8327010 |  |  | Harrison County | -339679.2083
|  |  | 8327070 |  |  | Orange County | -339679.2083
|  |  | 8327080 |  |  | Parke County | -339679.2083
|  |  | 8327130 |  |  | Washington County | -339679.2083
|  |  | 8327350 |  |  |  | -339679.2083
|  |  | 8327360 |  |  |  | -339679.2083
|  |  | 8327380 |  | C Blair Enterprises, Inc. | Elkhart | -339679.2083
|  |  | 8327420 |  |  |  | -339679.2083
|  |  | 8327540 |  |  |  | -339679.2083
|  |  | 8327610 |  |  |  | -339679.2083
|  |  | 8327620 |  |  |  | -339679.2083
|  |  | 8327660 |  |  |  | -339679.2083
|  |  | 8327670 |  |  |  | -339679.2083
|  |  | 8327700 |  |  |  | -339679.2083
|  |  | 8327720 |  |  |  | -339679.2083
|  |  | 8327750 |  |  |  | -339679.2083
|  |  | 8327770 |  |  |  | -339679.2083
|  |  | 8327790 |  |  |  | -339679.2083
|  |  | 8327810 |  |  |  | -339679.2083
|  |  | 8327840 |  |  |  | -339679.2083
|  |  | 8329731 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8329881 |  | Consolidated Test Company | Indiana Department of Transportation | 1982-07-20
|  |  | 8329911 |  |  | Indiana Department of Transportation | 1982-08-24
|  |  | 8329921 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1982-07-20
|  |  | 8329961 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1982-07-20
|  |  | 8330010 |  |  |  | -339679.2083
|  |  | 8330030 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 8330180 |  |  |  | 1987-05-19
|  |  | 8330540 |  |  |  | -339679.2083
|  |  | 8330550 |  |  |  | -339679.2083
|  |  | 8330660 |  |  | Indianapolis | -339679.2083
|  |  | 8330700 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8331030 |  |  |  | 1983-07-26
|  |  | 8333040 |  | Dodd Title Corporation | Indiana Department of Transportation | 1983-04-26
|  |  | 8333041 |  | Dodd Title Corporation | Indiana Department of Transportation | 1983-04-26
|  |  | 8333200 |  |  | Indiana Department of Transportation | 1983-04-26
|  |  | 8333441 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8333570 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8333580 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8333640 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 8333720 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8333730 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8333830 |  |  |  | 1989-08-08
|  |  | 8333840 |  |  | Marshall County | -339679.2083
|  |  | 8333930 |  |  | Huntington County | -339679.2083
|  |  | 8334020 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1984-01-17
|  |  | 8334030 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8334070 |  |  |  | 1983-07-26
|  |  | 8334480 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-07-17
|  |  | 8334490 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-07-17
|  |  | 8335170 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8335200 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8335950 |  |  |  | -339679.2083
|  |  | 8336430 |  |  | Hancock County | -339679.2083
|  |  | 8336550 |  |  | Ohio County | -339679.2083
|  |  | 8336582 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8336583 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8336710 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8337211 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8337213 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8339501 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-07-11
|  |  | 8340301 |  |  |  | -339679.2083
|  |  | 8340641 |  |  |  | 1983-01-18
|  |  | 8341991 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8342151 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8342191 |  | ERES International, Inc. | Indiana Department of Transportation | 1984-06-12
|  |  | 8342230 |  |  | Indiana Department of Transportation | 1983-05-24
|  |  | 8342421 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8342811 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8343081 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8343090 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8343091 |  |  | Indiana Department of Transportation | 1984-01-17
|  |  | 8343301 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8343610 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8343760 |  |  |  | 1985-06-25
|  |  | 8343970 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-02-19
|  |  | 8344280 |  |  | Indiana Department of Transportation | 1983-08-09
|  |  | 8344390 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8344400 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344430 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344440 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344450 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344460 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344470 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344490 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344500 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344510 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344520 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344540 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8344550 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8344560 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1983-12-13
|  |  | 8344650 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8344750 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8346000 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8346010 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346020 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8346030 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8346040 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8346050 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8346060 |  |  | Indiana Department of Transportation | 1992-09-01
|  |  | 8346070 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8346080 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8346090 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8346100 |  | InfoTech | Indiana Department of Transportation | 1989-03-14
|  |  | 8346120 |  | Fink Roberts & Petrie | Indiana Department of Transportation | 1993-03-16
|  |  | 8346130 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8346140 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8346150 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8346160 |  |  | Indiana Department of Transportation | 1989-10-17
|  |  | 8346170 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8346180 |  |  | Indiana Department of Transportation | 1993-05-11
|  |  | 8346190 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8346200 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8346210 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8346220 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8346230 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8346240 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346250 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 1991-09-24
|  |  | 8346260 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8346270 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8346280 |  |  | Indiana Department of Transportation | 1997-04-08
|  |  | 834628A |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8346290 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8346300 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8346310 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8346350 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1993-05-11
|  |  | 8346360 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8346370 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8346390 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8346400 | Monroe |  | Indiana Department of Transportation | 2002-02-19 | CE
CN
PE
|  |  | 8346410 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8346420 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8346430 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346440 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8346450 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8346460 | Franklin |  | Indiana Department of Transportation | 1999-02-23 | CE
CN
PE
|  |  | 8346480 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8346490 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 8346500 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346510 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8346520 | Sullivan |  | Indiana Department of Transportation | 2008-03-05 | CE
CN
UT
|  |  | 8346530 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8346540 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 8346550 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8346560 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8346570 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346580 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8346590 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1988-12-13
|  |  | 8346600 |  | CGI | Indiana Department of Transportation | 1997-03-11
|  |  | 8346610 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346620 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8346630 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8346640 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8346650 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8346660 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8346670 |  |  | Indiana Department of Transportation | 1997-11-20
|  |  | 8346680 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8346690 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8346700 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8346710 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8346720 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8346730 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8346740 |  |  | Indiana Department of Transportation | 2001-03-20
|  |  | 8346750 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8346760 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8346770 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8346780 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8346790 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8346800 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8346810 |  |  | Indiana Department of Transportation | 1995-12-19
|  |  | 8346820 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-07-17
|  |  | 8346830 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8346840 |  |  | Indiana Department of Transportation | 1995-01-10
|  |  | 8346850 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8346860 |  |  | Indiana Department of Transportation | 1995-01-10
|  |  | 8346870 | Perry |  | Indiana Department of Transportation | 2001-03-20 | CE
CN
PE
UT
|  |  | 8346900 |  |  | Indiana Department of Transportation | 1999-06-15
|  |  | 8346910 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8346920 | Posey |  | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
ROW
UT
|  |  | 8346940 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8346950 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8346960 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8346970 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8346980 |  |  | Indiana Department of Transportation | 1996-03-19
|  |  | 8346990 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8347000 |  |  | Indiana Department of Transportation | 1992-10-06
|  |  | 8347010 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8347020 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 8347030 |  |  | Indiana Department of Transportation | 1989-08-29
|  |  | 8347050 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8347060 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8347070 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8347080 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8347090 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8347100 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1994-09-20
|  |  | 8347110 |  | Collier Transport Inc. | Indiana Department of Transportation | 1996-12-17
|  |  | 8347120 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8347130 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | 2000-03-21 | CE
CN
|  |  | 8347140 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8347150 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8347160 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8347170 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8347180 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8347190 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8347200 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8347210 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8347220 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8347230 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8347240 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8347250 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8347260 |  |  | Indiana Department of Transportation | 1985-12-19
|  |  | 8347270 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8347280 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8347300 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8347310 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8347320 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8347330 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1992-11-10
|  |  | 8347340 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8347350 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8347360 |  | Eco Logic, LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8347370 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8347390 |  |  | Indiana Department of Transportation | 1994-01-11
|  |  | 8347400 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-06-25
|  |  | 8347410 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8347420 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1986-10-14
|  |  | 8347440 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8347460 | Johnson | Casteel Real Estate | Indiana Department of Transportation | 1996-12-17 | CE
CN
|  |  | 8347470 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8347480 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8347490 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8347500 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8347501 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8347502 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8347510 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 8347520 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8347530 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 1986-11-18
|  |  | 8347540 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8347550 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8347560 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8347570 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8347580 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8347590 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8347600 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8347610 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8347620 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8347640 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8347650 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1992-10-06
|  |  | 8347651 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1992-10-06
|  |  | 8347660 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8347680 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8347690 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8347700 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8347710 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8347720 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8347730 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8347740 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8347750 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8347760 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8347780 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8347790 |  |  | Indiana Department of Transportation | 1994-01-11
|  |  | 8347810 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8347830 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8347840 |  | Archaeology and Geomorphology Services | Indiana Department of Transportation | 1985-07-23
|  |  | 8347850 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8347860 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8347870 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8347880 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8347890 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8347900 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8347910 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8347940 | Harrison |  | Indiana Department of Transportation | 1997-02-11 | CE
CN
|  |  | 8347950 | Floyd | Civil & Environmental Consultants, Inc. | Indiana Department of Transportation | 2007-10-03 | CE
CN
PE
ROW
UT
|  |  | 8347960 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8347970 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8347980 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8347990 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8348000 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348010 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348020 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8348030 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8348040 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8348050 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8348060 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8348070 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348080 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8348090 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348100 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348110 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8348120 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348130 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348140 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348150 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348160 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348170 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8348190 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348200 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348210 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348220 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348221 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348230 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348240 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348250 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348260 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348270 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348280 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348290 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8348300 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8348310 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8348320 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8348330 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1985-01-15
|  |  | 8348340 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1986-07-15
|  |  | 8348350 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1986-07-15
|  |  | 8348360 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8348370 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348380 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348390 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8348400 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8348410 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8348420 |  | Bertsch-Frank & Associates, LLC | Indiana Department of Transportation | 1985-03-19
|  |  | 8348430 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348440 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348450 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8348460 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8348470 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8348480 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8348490 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8348500 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348510 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8348520 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8348530 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1985-11-19
|  |  | 8348540 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348550 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348560 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348570 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348580 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348590 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8348600 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8348610 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348620 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348630 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8348640 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8348650 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8348660 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8348670 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8348680 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8348690 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8348700 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8348710 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-06-14
|  |  | 8348720 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8348730 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8348740 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8348750 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 8348760 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 8348770 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 8348780 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348790 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348800 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348801 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348810 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348820 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348830 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348840 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348850 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348860 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348870 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348880 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8348881 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8348882 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8348890 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-02-16
|  |  | 8348900 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-02-16
|  |  | 8348910 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8348920 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8348930 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8348940 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8348950 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8348960 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8348970 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8348980 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8348990 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8349000 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8349010 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8349020 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8349030 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8349040 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8349050 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1986-10-14
|  |  | 8349060 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8349070 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8349080 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8349090 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349100 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349110 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349120 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349130 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349140 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349150 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349160 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349170 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349180 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349190 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349210 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1987-03-10
|  |  | 8349220 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8349230 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349240 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8349250 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-10-14
|  |  | 8349260 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349270 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8349280 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8349290 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8349300 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8349310 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8349320 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8349330 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8349340 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-11-18
|  |  | 8349350 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8349360 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8349370 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8349380 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8349390 |  |  | Indiana Department of Transportation | 1987-05-10
|  |  | 8349400 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1987-05-10
|  |  | 8349410 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1987-05-10
|  |  | 8349420 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1987-05-10
|  |  | 8349430 |  |  | Indiana Department of Transportation | 1987-05-10
|  |  | 8349440 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8349460 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8349470 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8349480 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8349490 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8349500 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8349510 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8349520 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8349540 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8349550 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8349560 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8349570 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8349580 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8349590 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8349600 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8349610 |  | HE-BFS, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8349630 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8349640 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8349650 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8349690 | Floyd |  | Indiana Department of Transportation | 1997-04-08 | CE
CN
|  |  | 8349700 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8349710 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8349720 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8349730 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8349750 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8349770 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8349780 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8349790 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8349800 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8349810 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8349820 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8349830 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8349840 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8349850 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-04-17
|  |  | 8349860 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8349870 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8349880 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8349890 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8349900 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8349910 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8349930 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349931 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349932 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8349950 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8349951 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8349960 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8349961 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8349980 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8350030 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8350031 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-12-18
|  |  | 8350040 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 8350041 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-11-20
|  |  | 8350050 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8350051 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8350052 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8350070 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8350080 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8350090 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8350100 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8350110 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8350111 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8350120 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8350130 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1984-06-12
|  |  | 8350131 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1984-06-12
|  |  | 8350132 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8350150 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8350180 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8350200 |  | Beals-Moore & Associates, Inc. | Indiana Department of Transportation | 1984-08-21
|  |  | 8350201 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8350210 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8350230 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8350240 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8350260 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8350263 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8350280 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8350281 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8350320 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8350360 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8350370 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-11-21
|  |  | 8350372 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-07-11
|  |  | 8350380 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-04-19
|  |  | 8350440 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8350450 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1987-06-02
|  |  | 8350460 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8350470 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8350480 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8350490 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8350500 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 8350510 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8350520 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8350570 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8350580 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8350610 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8350640 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8350641 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8350660 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8350690 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8350700 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8350720 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1992-04-21
|  |  | 8350721 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1992-04-21
|  |  | 8350730 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8350740 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8350750 |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8350760 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8350770 |  | DCD Consulting LLC | Indiana Department of Transportation | 1999-02-09
|  |  | 8350790 |  | DCD Consulting LLC | Indiana Department of Transportation | 1992-11-10
|  |  | 8350800 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8350810 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8350830 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-10-23
|  |  | 8350840 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-06-14
|  |  | 8350850 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-05-15
|  |  | 8350870 |  | DCD Consulting LLC | Indiana Department of Transportation | 1992-04-21
|  |  | 8350880 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8350890 |  | DCD Consulting LLC | Indiana Department of Transportation | 1998-11-17
|  |  | 8350900 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8350901 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8350902 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8350910 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8350911 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8350920 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8350940 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8350941 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8350950 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8350951 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8350952 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8350960 | Lake | DCD Consulting LLC | Indiana Department of Transportation | 1999-09-14 | CE
CN
RR
|  |  | 8350961 |  |  | Indiana Department of Transportation | 1999-09-14
|  |  | 8350962 |  |  | Indiana Department of Transportation | 1999-09-14
|  |  | 835096A |  |  | Indiana Department of Transportation | 1998-09-10
|  |  | 8350990 |  |  | Indiana Department of Transportation | 1983-12-13
|  |  | 8351010 | Lake | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1999-03-23 | CE
PE
ROW
|  |  | 835101A |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1996-02-20
|  |  | 8351020 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8351030 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8351040 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8351060 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8351070 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-05-15
|  |  | 8351090 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1985-06-25
|  |  | 8351110 | Franklin | Alfred Benesch & Company | Indiana Department of Transportation | 1998-06-11 | PE
|  |  | 8351120 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8351130 | LaPorte | Marine Solutions, Inc. | Indiana Department of Transportation | 2003-06-17 | CE
CN
ROW
|  |  | 8351140 | Noble | ERES International, Inc. | Indiana Department of Transportation | 1999-06-15 | CE
CN
|  |  | 8351150 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8351170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8351190 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8351200 | Wabash | M-E Companies, Inc. | Indiana Department of Transportation | 1999-12-14 | CE
CN
|  |  | 8351210 |  |  | Indiana Department of Transportation | 1996-02-20
|  |  | 8351211 |  |  | Indiana Department of Transportation | 1996-02-20
|  |  | 835121R | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083 | CN
RR
|  |  | 8351220 | Elkhart |  | Indiana Department of Transportation | 2015-04-01 | CE
CN
PE
ROW
|  |  | 8351230 | St. Joseph |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
PE
ROW
|  |  | 8351260 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8351330 | Allen | Global Management Group, Inc. | Indiana Department of Transportation | 1999-04-20 | CE
CN
|  |  | 8351420 | Tippecanoe |  |  | -339679.2083 | PE
|  |  | 8351430 | White |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8351440 | Daviess | AMEC E&I, Inc. | Indiana Department of Transportation | 2006-06-01 | CE
CN
ROW
|  |  | 8351470 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1988-06-14
|  |  | 8351500 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8351520 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-08-19
|  |  | 8351540 | Lake |  | Indiana Department of Transportation | 2016-04-06 | PE
RR
UT
|  |  |  | Porter |  | Indiana Department of Transportation | 2016-04-06 | CE
CN
PE
ROW
RR
|  |  | 8351550 | Washington | JCI Bridge Group, Inc. | Indiana Department of Transportation | 2000-05-23 | CE
CN
PE
|  |  | 8351570 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8351580 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8351590 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8351600 | Floyd |  | Indiana Department of Transportation | 2001-08-14 | CE
CN
ROW
UT
|  |  |  | Various |  | Indiana Department of Transportation | 2001-08-14 | CN
|  |  | 835160A |  |  | Indiana Department of Transportation | 1997-12-16
|  |  | 835160C |  |  | Indiana Department of Transportation | 1998-12-15
|  |  | 8351620 |  | Enginuity Management & Consulting Corporation | Indiana Department of Transportation | 1999-06-15
|  |  | 8351630 | Adams |  | Indiana Department of Transportation | 1997-11-20 | CE
CN
|  |  | 8351640 |  |  | Indiana Department of Transportation | 1996-03-19
|  |  | 8351650 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8351660 |  | DuSABLE, Inc. | Indiana Department of Transportation | 2000-06-20
|  |  | 8351670 |  | Clayton L. Roots | Indiana Department of Transportation | 1993-05-27
|  |  | 8351680 |  | DCD Consulting LLC | Indiana Department of Transportation | 1994-04-19
|  |  | 8351690 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8351700 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 1993-05-27
|  |  | 8351740 | Dekalb | American Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351750 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351760 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 8351770 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8351780 | Rush |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8351790 | Elkhart |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351800 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8351810 | Grant | ERES International, Inc. | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8351820 | Marshall |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351830 |  | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8351840 | Newton |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351850 | Jasper |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351870 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8351890 | Benton | CDM Smith, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351900 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8351910 | Rush |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8351930 | Howard | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8351940 | St. Joseph | HDR Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351950 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351960 | White | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8351980 | Montgomery | McKee Enterprises, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8351990 |  | J.F. New & Associates, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8352000 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352020 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352030 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352040 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352060 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
|  |  | 8352070 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 8352080 |  | Dodd Title Corporation | Indiana Department of Transportation | -339679.2083
|  |  | 8352090 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352110 | Vermillion |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352120 |  | GS-IN P.C. | Indiana Department of Transportation | -339679.2083
|  |  | 8352130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352140 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352150 | LaPorte | Farah and Sons, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352160 | Putnam | AI Engineers, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 8352180 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352190 | Morgan | EnviroScience, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352220 | Vigo | Bayswater Company, LLC | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8352240 | Putnam |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352260 | Monroe |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352280 | Bartholomew | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8352300 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352310 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352320 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352340 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352350 | Newton |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8352360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352370 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352380 | Greene | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352400 | Pike |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352410 | Warrick | Accu-Air Surveys, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352420 | Spencer |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352430 | Spencer |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352440 | Clark | Data Transfer Solutions, LLC | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8352470 | Gibson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352480 | Gibson |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352490 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352500 | Greene |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8352510 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352520 | Posey |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352530 | Ripley |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352540 |  | GeoSolutions, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8352550 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352560 | LaPorte |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352570 | Huntington | ABNA of Illinois | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352580 | Marion |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  |  | Marshall |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352590 | Jasper |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 8352600 | Ripley |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352610 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352620 | Dubois |  | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  |  | Hamilton |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352630 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352640 | Martin |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352650 | Washington |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352680 | Miami |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
RR
|  |  | 8352690 | Huntington |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352700 | Huntington |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352710 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352720 | Daviess |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352730 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352740 | Montgomery |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8352760 | Rush |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352770 | Spencer |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352780 | Wells |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352790 | Marshall |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352810 | Harrison |  | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8352820 | Harrison | BCA Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 8352840 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352850 | Clark |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8352870 | White |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8352880 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8352890 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1985-02-19
|  |  | 8352900 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1985-02-19
|  |  | 8352910 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8352920 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8352971 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8352980 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1983-09-20
|  |  | 8353040 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1985-09-24
|  |  | 8353050 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8353060 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1984-06-12
|  |  | 8353080 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | 1998-04-07 | CE
CN
|  |  | 8353110 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8353130 | Franklin |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8353170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8353200 |  |  | Indiana Department of Transportation | 1983-10-25
|  |  | 8353250 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8353260 |  |  | Indiana Department of Transportation | 1989-09-17
|  |  | 8353270 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8353280 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8353300 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8353310 |  |  | Indiana Department of Transportation | 1999-05-18
|  |  | 8353330 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8353340 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8353350 |  |  | Indiana Department of Transportation | 1990-11-20
|  |  | 8353360 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8353370 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8353380 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 8353390 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8353410 |  |  | Indiana Department of Transportation | 1995-05-16
|  |  | 8353420 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8353430 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8353450 | Warren |  | Indiana Department of Transportation | 1999-11-16 | CE
CN
PE
|  |  | 8353460 |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 8353480 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8353490 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8353510 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8353520 |  |  | Indiana Department of Transportation | 1993-09-14
|  |  | 8353530 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8353540 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8353550 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8353560 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8353570 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8353580 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8353600 |  |  | Indiana Department of Transportation | 1994-12-13
|  |  | 8353620 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8353630 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1997-09-16
|  |  | 8353650 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8353690 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8353710 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8353720 |  |  | Indiana Department of Transportation | 1992-07-28
|  |  | 8353730 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8353731 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8353732 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8353780 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8353810 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8353811 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8353820 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8353830 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8353863 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8353872 |  |  | Indiana Department of Transportation | 1990-11-20
|  |  | 8353900 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8353920 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8353940 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8353960 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8353961 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8353970 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8353971 |  |  | Indiana Department of Transportation | 1998-02-10
|  |  | 8353990 |  | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 2002-12-18
|  |  | 8353993 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8354040 |  |  | Indiana Department of Transportation | 1992-09-01
|  |  | 8354050 |  |  | Indiana Department of Transportation | 1994-03-15
|  |  | 8354060 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8354080 |  |  | Indiana Department of Transportation | 2000-01-02
|  |  | 8354090 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8354091 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8354100 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8354140 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8354150 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8354170 |  |  | Indiana Department of Transportation | 1992-09-01
|  |  | 8354190 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8354200 |  | Clayton L. Roots | Indiana Department of Transportation | 1989-05-16
|  |  | 8354230 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8354240 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1993-06-15
|  |  | 8354250 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8354270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8354280 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8354281 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8354282 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-02-06
|  |  | 8354283 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-02-06
|  |  | 8354284 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-08-15
|  |  | 8354285 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8354300 | LaPorte | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2003-01-22 | CE
CN
PE
ROW
UT
|  |  | 835430A |  | Douglass Environmental Services, Inc. | Indiana Department of Transportation | 2000-01-19
|  |  | 8354310 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8354320 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1992-01-14
|  |  | 8354321 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8354330 | Marion | DCD Consulting LLC | Indiana Department of Transportation | 2004-05-25 | CE
CN
ROW
UT
|  |  | 8354340 | Lake |  | Indiana Department of Transportation | 2000-02-22 | CE
CN
PE
ROW
UT
|  |  | 8354360 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 8354370 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8354371 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8354390 | Dearborn | Kaskaskia Engineering Group | Indiana Department of Transportation | 1995-04-18 | CE
CN
|  |  | 8354391 | Franklin |  | Indiana Department of Transportation | 1995-04-18 | CE
CN
|  |  | 8354410 |  | GeoSolutions, Inc. | Indiana Department of Transportation | 1993-03-16
|  |  | 8354420 | Elkhart |  | Indiana Department of Transportation | 2008-02-06 | CE
CN
ROW
UT
|  |  | 8354430 |  |  |  | 1984-07-17
|  |  | 8354470 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-09-01
|  |  | 8354480 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1992-05-21
|  |  | 8354490 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8354500 |  | ASA Land Surveying | Indiana Department of Transportation | -339679.2083
|  |  | 8354501 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8354511 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1994-04-19
|  |  | 8354512 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1994-04-19
|  |  | 8354513 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1994-04-19
|  |  | 8354530 |  | Archonsortium, LLC | Indiana Department of Transportation | 1997-02-11
|  |  | 8354560 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8354580 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8354600 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8354610 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8354630 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8354640 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8354650 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8354660 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8354700 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8354710 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8354730 |  |  | Indiana Department of Transportation | 1983-07-26
|  |  | 8354770 | Clay | Advanced Appraisals, LLC | Indiana Department of Transportation | 2001-06-19 | CE
CN
PE
|  |  | 8354790 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 1984-04-17
|  |  | 8354791 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 1984-07-17
|  |  | 8354800 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 1984-04-17
|  |  | 8354810 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8354820 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8354840 |  | GS-IN P.C. | Indiana Department of Transportation | 1984-02-14
|  |  | 8354850 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1983-09-20
|  |  | 8354860 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1983-09-20
|  |  | 8354870 |  | Burrell Appraisal Service, Inc. | Indiana Department of Transportation | 1983-09-20
|  |  | 8354890 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 1984-07-17
|  |  | 8354900 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8354910 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1984-06-12
|  |  | 8354920 |  | GS-IN P.C. | Indiana Department of Transportation | 1984-04-17
|  |  | 8354930 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8354940 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8354950 |  | Cornerstone Design | Indiana Department of Transportation | 1984-07-17
|  |  | 8354960 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8354970 |  | Jacobs Pannicke Architects, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8354990 |  | CGI | Indiana Department of Transportation | 1984-06-12
|  |  | 8355000 |  | CGI | Indiana Department of Transportation | 1984-03-20
|  |  | 8355010 |  | CGI | Indiana Department of Transportation | 1984-03-20
|  |  | 8355020 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8355030 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8355040 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8355050 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-10-23
|  |  | 8355060 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-10-23
|  |  | 8355070 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-10-23
|  |  | 8355080 |  | Farren Real Estate Services | Indiana Department of Transportation | 1985-01-15
|  |  | 8355090 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8355100 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8355110 |  | Consolidated Test Company | Indiana Department of Transportation | 1985-02-19
|  |  | 8355120 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8355130 |  | Brenner Design Incorporated | Indiana Department of Transportation | 1985-02-19
|  |  | 8355140 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8355150 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8355160 |  | Consolidated Test Company | Indiana Department of Transportation | 1985-02-19
|  |  | 8355170 |  | Casteel Real Estate | Indiana Department of Transportation | 1984-04-17
|  |  | 8355180 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-03-20
|  |  | 8355200 |  | HE-BFS, LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8355210 |  | Dodd Title Corporation | Indiana Department of Transportation | 1985-02-19
|  |  | 8355220 |  | Dodd Title Corporation | Indiana Department of Transportation | 1985-02-19
|  |  | 8355230 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8355240 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8355250 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8355260 |  | Casteel Real Estate | Indiana Department of Transportation | 1985-01-15
|  |  | 8355270 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1984-03-20
|  |  | 8355280 |  | Carters Appraisal Service | Indiana Department of Transportation | 1984-12-18
|  |  | 8355290 |  | Carters Appraisal Service | Indiana Department of Transportation | 1984-12-18
|  |  | 8355300 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-06-25
|  |  | 8355310 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1984-10-23
|  |  | 8355320 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-02-19
|  |  | 8355330 |  | All About Pavements, Inc. | Indiana Department of Transportation | 1985-08-27
|  |  | 8355340 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8355350 |  | Consolidated Test Company | Indiana Department of Transportation | 1984-05-15
|  |  | 8355360 |  | Cornerstone Design | Indiana Department of Transportation | 1984-10-23
|  |  | 8355370 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8355380 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8355390 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8355400 |  | B. L. A., Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8355410 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1985-06-25
|  |  | 8355420 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8355430 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8355450 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1983-08-23
|  |  | 8355460 |  | CGI | Indiana Department of Transportation | 1984-04-17
|  |  | 8355470 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1984-06-12
|  |  | 8355480 |  | Eco Logic, LLC | Indiana Department of Transportation | 1988-05-17
|  |  | 8355490 |  |  | Indiana Department of Transportation | 1983-11-15
|  |  | 8355510 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8355520 |  | H. Stewart Kline & Associates, Inc. | Indiana Department of Transportation | 1984-06-12
|  |  | 8355530 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-02-14
|  |  | 8355540 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-06-12
|  |  | 8355550 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1984-06-12
|  |  | 8355560 |  | Marbach & Brady Land Surveying, Inc. | Indiana Department of Transportation | 1984-02-14
|  |  | 8355580 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8355590 |  | ASA Land Surveying | Indiana Department of Transportation | 1986-07-15
|  |  | 8355600 |  | GAI Consultants, Inc. | Indiana Department of Transportation | 1983-12-13
|  |  | 8355610 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 1985-04-16
|  |  | 8355620 |  | Casteel Real Estate | Indiana Department of Transportation | 1983-12-13
|  |  | 8355630 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1985-11-19
|  |  | 8355640 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8355641 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8355650 |  | Collier Transport Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8355660 |  | Consolidated Test Company | Indiana Department of Transportation | 1984-09-18
|  |  | 8355670 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8355680 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8355700 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8355710 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8355720 |  | InfoTech | Indiana Department of Transportation | 1986-03-18
|  |  | 8355730 |  | Dave Helton & Associates, Inc. | Indiana Department of Transportation | 1984-03-20
|  |  | 8355740 |  | ERES International, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8355750 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8355760 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8355770 |  | Eco Logic, LLC | Indiana Department of Transportation | 1983-11-15
|  |  | 8355780 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | 1984-03-20
|  |  | 8355790 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8355800 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8355810 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8355820 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8355990 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8356000 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8356010 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8356030 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8356040 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8356050 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8356060 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8356070 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8356080 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8356090 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8356100 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8356120 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8356140 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356150 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8356160 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356171 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8356180 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8356190 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8356210 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-06-12
|  |  | 8356220 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8356230 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356240 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8356250 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356260 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356290 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8356300 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8356310 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8356311 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8356312 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8356320 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8356330 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8356340 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8356360 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8356370 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8356371 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8356372 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8356380 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8356420 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8356430 |  |  | Indiana Department of Transportation | 1992-09-29
|  |  | 8356440 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8356441 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8356442 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8356450 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8356460 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8356480 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8356490 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8356510 |  |  | Indiana Department of Transportation | 1986-06-30
|  |  | 8356530 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8356540 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8356550 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356570 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8356580 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8356590 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8356600 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8356930 |  | Wilcox Environmental Engineering, Inc. | Fayette County | 1992-07-28
|  |  | 8356960 |  |  |  | 1988-08-16
|  |  | 8357000 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1984-05-15
|  |  | 8357020 |  | Another Test Company | Indiana Department of Transportation | 1984-05-15
|  |  | 8357040 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8357190 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-08-19
|  |  | 8357191 |  | Another Test Company | Indiana Department of Transportation | 1986-08-19
|  |  | 8363800 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-07-23
|  |  | 8365000 |  | Carters Appraisal Service | Indiana Department of Transportation | 1986-05-13
|  |  | 8401240 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8401290 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8401320 |  |  | Indiana Department of Transportation | 1984-05-15
|  |  | 8401330 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8402751 |  |  |  | 1984-11-20
|  |  | 8402920 |  |  |  | -339679.2083
|  |  | 8403441 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8404605 |  |  | Benton County | 1991-08-20
|  |  | 8404615 |  |  | Benton County | 1991-06-18
|  |  | 8406540 |  |  |  | -339679.2083
|  |  | 8406980 | Vanderburgh |  | Vanderburgh County | 2004-03-23 | CE
CN
UT
|  |  | 8407580 |  |  |  | 1988-09-20
|  |  | 8409530 |  | Advanced Engineering Consultants, Ltd. | Indiana Department of Transportation | 1984-07-17
|  |  | 8409880 |  |  | Indiana Department of Transportation | 1984-04-23
|  |  | 8410020 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8410610 |  |  |  | 1983-12-13
|  |  | 8411840 |  |  |  | 1983-09-20
|  |  | 8412030 |  |  |  | 1985-12-17
|  |  | 8412632 |  |  |  | 1984-06-12
|  |  | 8413842 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1984-05-15
|  |  | 8415183 |  |  |  | 1984-03-20
|  |  | 8417511 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8421680 |  |  |  | 1984-06-12
|  |  | 8421681 |  |  |  | 1984-05-15
|  |  | 8421683 |  |  |  | 1984-10-23
|  |  | 8422101 |  |  |  | 1983-08-23
|  |  | 8422110 |  |  |  | 1983-08-23
|  |  | 8422140 |  |  |  | 1984-06-12
|  |  | 8422300 |  |  |  | 1984-07-17
|  |  | 8422340 |  |  |  | 1983-11-15
|  |  | 8422460 |  |  |  | -339679.2083
|  |  | 8424690 |  |  |  | -339679.2083
|  |  | 8424720 |  |  |  | -339679.2083
|  |  | 8425110 |  |  |  | -339679.2083
|  |  | 8426413 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-08-01
|  |  | 8426420 |  |  | Alexandria | -339679.2083
|  |  | 8426751 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8426760 |  |  |  | -339679.2083
|  |  | 8426871 |  |  |  | -339679.2083
|  |  | 8426920 |  |  |  | -339679.2083
|  |  | 8427030 |  |  | Howard County | -339679.2083
|  |  | 8427290 | Dekalb | Cheri K. Lewis Engineers | Indiana Department of Transportation | 1991-09-24 | CE
CN
PE
|  |  | 8427890 |  |  |  | -339679.2083
|  |  | 8428240 |  |  |  | 1985-02-19
|  |  | 8428460 |  |  |  | 1986-10-14
|  |  | 8428470 |  |  |  | 1985-01-15
|  |  | 8428561 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8429520 |  |  | Indiana Department of Transportation | 1984-08-07
|  |  | 8430560 |  |  |  | 1984-08-21
|  |  | 8430840 |  |  |  | 1984-05-15
|  |  | 8431420 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8431900 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8432240 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8432400 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8432850 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8432870 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8432940 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8433000 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8433180 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8433460 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8433610 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-04-16
|  |  | 8433710 |  | Carters Appraisal Service | Indiana Department of Transportation | 1985-01-15
|  |  | 8433770 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8433900 |  |  |  | 1984-04-17
|  |  | 8433910 |  | Digital Appraisals, LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8433920 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1985-03-19
|  |  | 8433970 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1985-03-19
|  |  | 8434130 |  |  |  | 1985-10-29
|  |  | 8434200 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1985-03-19
|  |  | 8434230 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1985-03-19
|  |  | 8434300 |  | Land Construction Corp | Indiana Department of Transportation | 1985-03-19
|  |  | 8434350 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1985-03-19
|  |  | 8434390 |  | Consolidated Test Company | Indiana Department of Transportation | 1985-03-19
|  |  | 8434400 |  |  |  | -339679.2083
|  |  | 8434500 |  |  |  | 1983-08-23
|  |  | 8434520 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8434530 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8434550 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8434640 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8434660 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8434870 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8434950 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8435700 |  | Bidinfo | Indiana Department of Transportation | 1985-06-25
|  |  | 8435710 |  |  |  | 1984-02-14
|  |  | 8436700 |  | Bidinfo | Indiana Department of Transportation | 1985-08-27
|  |  | 8436990 |  |  | Blackford County | -339679.2083
|  |  | 8437000 |  |  | Clark County | -339679.2083
|  |  | 8437080 |  |  | Gibson County | -339679.2083
|  |  | 8437250 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8437300 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8437310 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8437340 |  |  | Jay County | -339679.2083
|  |  | 8437370 |  |  | Johnson County | -339679.2083
|  |  | 8437530 |  |  | LaGrange County | -339679.2083
|  |  | 8437560 |  |  |  | -339679.2083
|  |  | 8437590 |  |  |  | 1983-10-25
|  |  | 8437710 |  |  | Pike County | -339679.2083
|  |  | 8437790 |  |  | Posey County | -339679.2083
|  |  | 8437910 |  |  | Ripley County | -339679.2083
|  |  | 8437950 |  |  | Rush County | -339679.2083
|  |  | 8437970 |  |  | Switzerland County | -339679.2083
|  |  | 8437980 |  |  |  | -339679.2083
|  |  | 8438000 |  |  | Jasper County | -339679.2083
|  |  | 8438010 |  |  | Newton County | -339679.2083
|  |  | 8438180 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8438450 |  |  | Porter County | -339679.2083
|  |  | 8438460 |  |  | Posey County | -339679.2083
|  |  | 8438470 |  |  | White County | -339679.2083
|  |  | 8438480 |  |  |  | -339679.2083
|  |  | 8438510 |  |  |  | 1984-06-12
|  |  | 8438520 |  |  |  | 1985-05-21
|  |  | 8438530 |  |  |  | 1983-10-25
|  |  | 8438540 |  |  |  | 1983-10-25
|  |  | 8438550 |  |  |  | 1983-08-23
|  |  | 8438580 |  |  |  | 1984-08-21
|  |  | 8438590 |  |  |  | 1984-04-17
|  |  | 8438650 |  |  |  | 1984-09-18
|  |  | 8438660 |  |  |  | 1985-05-21
|  |  | 8438680 |  |  |  | 1986-05-13
|  |  | 8438690 |  |  |  | 1988-08-16
|  |  | 8438700 |  |  |  | 1987-11-17
|  |  | 8438730 |  |  |  | 1987-02-03
|  |  | 8438740 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8438750 |  |  |  | 1987-07-07
|  |  | 8438760 |  |  |  | 1987-07-07
|  |  | 8438770 |  |  |  | 1986-03-18
|  |  | 8438780 |  |  |  | 1990-08-14
|  |  | 8438800 |  |  | Jay County | -339679.2083
|  |  | 8438850 |  |  | Jefferson County | 1993-04-13
|  |  | 8438860 |  |  | Indiana Department of Transportation | 1984-10-04
|  |  | 8438880 |  |  |  | 1986-07-15
|  |  | 8438900 |  |  | Johnson County | -339679.2083
|  |  | 8438920 |  |  |  | 1988-08-16
|  |  | 8438930 |  |  | Knox County | 1991-09-24
|  |  | 8438940 |  |  |  | 1988-12-13
|  |  | 8438950 |  |  |  | 1986-10-14
|  |  | 8439150 |  |  | Posey County | -339679.2083
|  |  | 8439200 |  |  | Spencer County | -339679.2083
|  |  | 8439210 |  |  |  | 1989-02-14
|  |  | 8439220 |  |  |  | 1987-03-10
|  |  | 8439270 |  |  |  | 1986-10-14
|  |  | 8439320 |  |  |  | 1987-02-03
|  |  | 8439330 |  |  |  | 1987-02-03
|  |  | 8439370 |  |  |  | 1987-02-03
|  |  | 8439380 |  |  |  | 1987-02-03
|  |  | 8439490 |  |  |  | 1984-05-15
|  |  | 8439520 |  |  |  | 1985-07-12
|  |  | 8439530 |  |  |  | 1988-02-09
|  |  | 8439600 |  |  |  | 1986-03-18
|  |  | 8439620 |  |  |  | 1986-03-18
|  |  | 8439640 |  |  |  | 1986-07-15
|  |  | 8439650 |  |  |  | 1986-04-15
|  |  | 8439670 |  |  | Cass County | 1993-03-16
|  |  | 8439700 |  |  | Clark County | 1994-05-17
|  |  | 8439750 |  |  |  | 1987-06-02
|  |  | 8439760 |  |  |  | 1986-03-18
|  |  | 8439770 |  |  |  | 1986-05-13
|  |  | 8439780 |  |  |  | 1986-10-14
|  |  | 8439790 |  |  |  | 1984-05-15
|  |  | 8439950 |  |  |  | 1988-04-19
|  |  | 8439990 |  |  |  | 1986-09-16
|  |  | 8440020 |  |  |  | 1986-07-15
|  |  | 8440130 |  |  |  | 1986-12-16
|  |  | 8440150 |  |  |  | 1985-09-24
|  |  | 8440210 |  |  |  | -339679.2083
|  |  | 8440240 |  |  |  | 1986-10-14
|  |  | 8440280 |  |  |  | 1986-09-16
|  |  | 8440410 |  |  |  | 1986-09-16
|  |  | 8440550 |  |  |  | 1987-06-02
|  |  | 8440640 |  |  |  | 1983-09-20
|  |  | 8440760 |  |  |  | 1986-04-15
|  |  | 8440790 |  |  |  | 1987-01-13
|  |  | 8440830 |  |  |  | 1981-08-27
|  |  | 8441090 |  |  |  | 1989-02-14
|  |  | 8441200 |  |  | Indiana Department of Transportation | 1984-08-07
|  |  | 8441210 |  |  |  | 1985-08-27
|  |  | 8441630 |  |  |  | 1988-09-20
|  |  | 8441640 |  |  |  | 1987-01-13
|  |  | 8441670 |  |  | Franklin County | 1991-02-19
|  |  | 8441720 |  |  |  | 1986-10-14
|  |  | 8441790 |  |  |  | -339679.2083
|  |  | 8441840 |  |  |  | 1989-05-16
|  |  | 8441860 | Floyd |  | Floyd County | 2013-02-06 | CE
CN
PE
UT
|  |  | 8441900 |  |  | Kosciusko County | -339679.2083
|  |  | 8441910 |  |  | Starke County | -339679.2083
|  |  | 8441920 |  |  |  | -339679.2083
|  |  | 8441930 |  |  |  | -339679.2083
|  |  | 8441940 |  |  |  | -339679.2083
|  |  | 8441950 |  |  |  | -339679.2083
|  |  | 8441970 |  |  |  | -339679.2083
|  |  | 8442020 |  |  |  | -339679.2083
|  |  | 8442160 |  |  |  | 1987-02-03
|  |  | 8442240 |  |  |  | 1991-02-19
|  |  | 8442330 |  |  |  | 1985-04-16
|  |  | 8442370 |  |  |  | 1986-08-19
|  |  | 8442380 | Gibson |  | Gibson County | -339679.2083 | CE
PE
RR
|  |  | 8442410 |  |  |  | 1987-02-03
|  |  | 8442470 |  |  |  | 1987-04-07
|  |  | 8442510 |  |  |  | 1989-07-18
|  |  | 8442690 |  |  |  | 1983-10-25
|  |  | 8442760 |  |  |  | 1989-03-14
|  |  | 8442770 |  |  |  | 1984-03-20
|  |  | 8442860 |  |  |  | 1989-05-16
|  |  | 8442870 |  |  | Steuben County | -339679.2083
|  |  | 8442900 |  |  |  | -339679.2083
|  |  | 8443160 |  |  |  | -339679.2083
|  |  | 8443170 |  |  |  | -339679.2083
|  |  | 8443180 |  |  | Vincennes | -339679.2083
|  |  | 8443250 |  |  |  | -339679.2083
|  |  | 8443260 |  |  |  | -339679.2083
|  |  | 8443270 |  |  |  | -339679.2083
|  |  | 8443290 |  |  |  | -339679.2083
|  |  | 8443310 |  |  |  | -339679.2083
|  |  | 8443320 |  |  |  | -339679.2083
|  |  | 8443330 |  |  |  | 1989-10-17
|  |  | 8443340 |  |  |  | -339679.2083
|  |  | 8443390 |  |  |  | -339679.2083
|  |  | 8443400 |  |  |  | -339679.2083
|  |  | 8443470 |  |  |  | -339679.2083
|  |  | 8443690 |  |  |  | -339679.2083
|  |  | 8443700 |  |  |  | 1988-08-16
|  |  | 8443720 |  |  |  | 1986-04-15
|  |  | 8443740 |  |  |  | 1983-10-25
|  |  | 8443770 |  |  |  | 1987-07-07
|  |  | 8443800 |  |  |  | 1984-05-15
|  |  | 8443830 |  |  |  | 1984-01-17
|  |  | 8443840 |  |  | Crawford County | -339679.2083
|  |  | 8443850 |  |  |  | -339679.2083
|  |  | 8443870 |  |  |  | 1984-05-15
|  |  | 8443980 |  |  | Brown County | -339679.2083
|  |  | 8443990 |  |  |  | -339679.2083
|  |  | 8444100 |  |  |  | 1984-11-20
|  |  | 8444370 |  |  |  | 1985-12-17
|  |  | 8444410 |  |  |  | -339679.2083
|  |  | 8444420 |  |  |  | -339679.2083
|  |  | 8444630 |  |  |  | 1985-05-23
|  |  | 8445200 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8445431 |  | CGI | Indiana Department of Transportation | 1984-07-17
|  |  | 8445520 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8449620 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8450000 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8450001 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8450042 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8455021 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8455771 |  | Eco Logic, LLC | Indiana Department of Transportation | 1983-11-15
|  |  | 8455781 |  | Fugro Roadware, Inc. | Indiana Department of Transportation | 1984-03-20
|  |  | 8455830 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455840 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455850 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1983-09-20
|  |  | 8455860 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455870 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455880 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-10-25
|  |  | 8455890 |  | DCD Consulting LLC | Indiana Department of Transportation | 1983-10-25
|  |  | 8455900 |  |  | Indiana Department of Transportation | 1983-10-25
|  |  | 8455910 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1983-10-25
|  |  | 8455920 |  |  | Indiana Department of Transportation | 1983-10-25
|  |  | 8455930 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455940 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455950 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455960 |  |  | Indiana Department of Transportation | 1983-09-20
|  |  | 8455970 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1984-06-12
|  |  | 8456200 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8456561 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8456562 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8456610 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8456620 |  | Collier Transport Inc. | Indiana Department of Transportation | 1984-04-17
|  |  | 8456630 |  | DCD Consulting LLC | Indiana Department of Transportation | 1991-05-23
|  |  | 8456650 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-11-18
|  |  | 8456660 |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-02-03
|  |  | 8456670 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8456690 |  | DCD Consulting LLC | Indiana Department of Transportation | 1991-11-19
|  |  | 8456700 | Lake |  | Indiana Department of Transportation | 1998-12-15 | CE
CN
PE
ROW
|  |  | 845670A |  |  | Indiana Department of Transportation | 1997-03-11
|  |  | 8456710 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8456730 |  | Consolidated Test Company | Indiana Department of Transportation | 1987-03-10
|  |  | 8456740 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-09-16
|  |  | 8456750 | Lake | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1997-07-15 | CE
CN
PE
ROW
RR
|  |  | 8456760 |  | Consolidated Test Company | Indiana Department of Transportation | 1991-07-16
|  |  | 8456770 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1988-10-11
|  |  | 8456780 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1995-05-16
|  |  | 8456790 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1993-07-20
|  |  | 8456800 |  | Consolidated Test Company | Indiana Department of Transportation | 1985-08-27
|  |  | 8456830 |  |  | Daviess County | -339679.2083
|  |  | 8456840 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8456850 |  |  |  | 1986-03-18
|  |  | 8456860 |  |  |  | 1984-06-12
|  |  | 8456900 |  |  |  | -339679.2083
|  |  | 8456980 |  |  |  | 1986-03-18
|  |  | 8457010 |  |  | Indiana Department of Transportation | 1984-03-20
|  |  | 8457030 |  |  | Indiana Department of Transportation | 1984-02-14
|  |  | 8457031 |  |  | Indiana Department of Transportation | 1984-01-24
|  |  | 8457110 |  |  |  | -339679.2083
|  |  | 8457130 |  |  | Indianapolis | -339679.2083
|  |  | 8457150 |  |  |  | 1987-06-02
|  |  | 8457160 |  |  |  | 1987-06-02
|  |  | 8457170 |  |  |  | 1985-04-16
|  |  | 8457180 |  |  |  | 1984-06-12
|  |  | 8457200 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8457210 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8457220 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8457230 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8457240 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8457250 |  |  | Indiana Department of Transportation | 1984-04-17
|  |  | 8457270 |  |  | Indiana Department of Transportation | 1988-01-12
|  |  | 8458000 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8458010 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8458020 |  |  | Indiana Department of Transportation | 1993-12-14
|  |  | 8458030 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1996-08-13
|  |  | 8458040 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8458050 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8458060 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1993-12-14
|  |  | 8458080 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8458090 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8458100 |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 8458110 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8458120 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8458130 |  |  | Indiana Department of Transportation | 1995-07-11
|  |  | 8458150 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | -339679.2083 | CE
CN
PE
|  |  | 8458160 | Rush | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 2003-02-18 | CE
CN
PE
|  |  | 8458170 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 8458180 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8458190 |  |  | Indiana Department of Transportation | 1994-10-18
|  |  | 8458200 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8458210 |  |  | Indiana Department of Transportation | 1993-08-17
|  |  | 8458220 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8458240 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8458250 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8458270 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8458280 | Gibson |  | Indiana Department of Transportation | 1998-01-13 | CE
CN
|  |  | 8458290 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8458300 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8458310 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 1994-10-18
|  |  | 8458320 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 8458330 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 8458340 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-05-13
|  |  | 8458350 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458360 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458370 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458380 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458390 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1993-06-15
|  |  | 8458410 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1987-06-02
|  |  | 8458420 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8458430 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8458450 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8458480 |  |  | Indiana Department of Transportation | 1995-01-10
|  |  | 8458500 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1986-06-10
|  |  | 8458510 |  |  | Indiana Department of Transportation | 1987-09-09
|  |  | 8458520 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 8458530 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8458540 |  |  | Indiana Department of Transportation | 1994-10-18
|  |  | 8458570 |  | Eco Logic, LLC | Indiana Department of Transportation | 1989-04-18
|  |  | 8458580 |  | Eco Logic, LLC | Indiana Department of Transportation | 1989-04-18
|  |  | 8458590 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1986-10-14
|  |  | 8458600 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1986-10-14
|  |  | 8458610 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1986-10-14
|  |  | 8458620 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-10-14
|  |  | 8458630 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8458640 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8458650 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8458660 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8458670 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8458680 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8458690 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1998-09-10
|  |  | 8458700 |  |  | Indiana Department of Transportation | 1986-09-16
|  |  | 8458710 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8458720 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8458730 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8458740 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1987-05-19
|  |  | 8458750 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8458770 |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-01-13
|  |  | 8458780 |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-01-13
|  |  | 8458790 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8458800 |  | Home Equity Appraisals | Indiana Department of Transportation | 1992-11-10
|  |  | 8458810 | Pike |  | Indiana Department of Transportation | 2000-09-12 | CE
CN
RR
|  |  | 8458820 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8458830 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8458840 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8458860 |  | GS-IN P.C. | Indiana Department of Transportation | 1987-12-15
|  |  | 8458870 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458880 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458890 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458900 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458910 |  | GS-IN P.C. | Indiana Department of Transportation | 1986-04-15
|  |  | 8458920 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8458930 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-02-09
|  |  | 8458940 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-02-09
|  |  | 8458950 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 8458970 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-04-21
|  |  | 8458980 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-04-21
|  |  | 8458990 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-04-21
|  |  | 8459000 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8459020 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8459030 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-02-16
|  |  | 8459040 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-02-16
|  |  | 8459050 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8459060 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8459070 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8459080 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8459090 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8459100 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8459110 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8459120 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8459130 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8459140 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8459150 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8459160 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8459170 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1987-11-17
|  |  | 8459180 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1987-11-17
|  |  | 8459190 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-04-19
|  |  | 8459200 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-04-19
|  |  | 8459210 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8459220 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-07-17
|  |  | 8459230 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1987-08-04
|  |  | 8459240 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1993-12-14
|  |  | 8459260 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8459300 |  |  | Indiana Department of Transportation | 1991-02-19
|  |  | 8459350 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8459370 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8459380 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8459400 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1990-06-14
|  |  | 8459430 |  |  | Indiana Department of Transportation | 1993-09-14
|  |  | 8459460 |  |  | Indiana Department of Transportation | 1992-09-01
|  |  | 8459480 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8459490 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8459550 |  |  | Indiana Department of Transportation | 1993-10-19
|  |  | 8459560 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8459570 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8459580 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8459590 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8459600 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8459610 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1990-09-25
|  |  | 8459630 |  |  | Indiana Department of Transportation | 1995-08-15
|  |  | 8459640 | Pike |  | Indiana Department of Transportation | 1997-11-20 | CE
CN
|  |  | 8459650 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8459660 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8459670 |  |  | Indiana Department of Transportation | 1989-10-17
|  |  | 8459680 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8459710 | Knox |  | Indiana Department of Transportation | 1997-02-11 | CN
|  |  | 8459720 | Knox |  | Indiana Department of Transportation | 1997-02-11 | CN
|  |  | 8459730 | Knox |  | Indiana Department of Transportation | 1997-03-11 | PE
|  |  | 8459740 |  |  | Indiana Department of Transportation | 1995-11-21
|  |  | 8459750 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8459760 |  |  | Indiana Department of Transportation | 1997-11-20
|  |  | 8459770 | Warrick |  | Indiana Department of Transportation | 1997-01-14 | CE
CN
PE
|  |  | 8459780 | Orange |  | Indiana Department of Transportation | 1999-07-20 | CE
CN
ROW
|  |  |  | Various |  | Indiana Department of Transportation | 1999-07-20 | PE
|  |  | 845978A |  |  | Indiana Department of Transportation | 1998-05-12
|  |  | 8459790 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8459800 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8459810 |  |  | Indiana Department of Transportation | 1996-05-14
|  |  | 8459830 |  |  | Indiana Department of Transportation | 1995-01-10
|  |  | 8459840 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8459900 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1991-07-16
|  |  | 8459920 | Steuben |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8459930 | Rush |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8459940 | Henry |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8459980 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8459990 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8460000 |  | CGS Real Estate Services, LLC | Indiana Department of Transportation | -339679.2083
|  |  | 8460050 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8460060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8460100 | Wayne | American Resources Group, Ltd. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8460110 | Lake | Consolidated Test Company | Indiana Department of Transportation | -339679.2083 | CE
CN
RR
|  |  | 8460130 | Union | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8460140 | Brown |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8460150 | Dearborn | Dynasty Group, Inc. | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8460160 | Tippecanoe |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8460170 | Greene |  | Indiana Department of Transportation | -339679.2083 | CE
CN
|  |  | 8460190 | Johnson | EHI Consultants, Inc. | Indiana Department of Transportation | -339679.2083 | CN
|  |  | 8460210 | Elkhart | Advanced Engineering Services Inc. | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8460230 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8460240 | Jay | Boomerang Ventures, LLC | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8460250 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8460260 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8460270 | Ripley | Hardcore Concrete Sawing Inc. | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8460460 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8460470 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8460490 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8460500 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1984-09-18
|  |  | 8460510 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8460520 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8460530 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8460540 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8460550 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8460560 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8460570 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8460580 |  | Duesler Realty House | Indiana Department of Transportation | 1984-09-18
|  |  | 8460590 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 1985-07-23
|  |  | 8460600 |  | ERES International, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8460610 |  | 2IM Group, LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8460630 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8460640 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1984-09-18
|  |  | 8460650 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8460670 |  | Collins Engineers Incorporated | Indiana Department of Transportation | 1985-03-19
|  |  | 8460680 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1986-04-15
|  |  | 8460690 |  | EHI Consultants, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8460700 |  | CityWise Real Estate Services, LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8460710 |  | Land Construction Corp | Indiana Department of Transportation | 1985-03-19
|  |  | 8460720 |  | Land Construction Corp | Indiana Department of Transportation | 1985-03-19
|  |  | 8460730 |  | Land Construction Corp | Indiana Department of Transportation | 1985-03-19
|  |  | 8460740 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1984-09-18
|  |  | 8460760 |  |  | Indiana Department of Transportation | 1984-09-18
|  |  | 8460770 |  | Home Guide Realty Services | Indiana Department of Transportation | 1985-05-21
|  |  | 8460780 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8460790 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8460800 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8460810 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8460820 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 8460830 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1984-09-18
|  |  | 8460840 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8460850 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1984-09-18
|  |  | 8460860 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8460870 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8460880 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8460890 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-01-15
|  |  | 8460900 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8460910 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-03-19
|  |  | 8460920 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8460930 |  | American Resources Group, Ltd. | Indiana Department of Transportation | 1986-02-18
|  |  | 8460940 |  | American Resources Group, Ltd. | Indiana Department of Transportation | 1986-02-18
|  |  | 8460950 |  | American Resources Group, Ltd. | Indiana Department of Transportation | 1986-02-18
|  |  | 8460970 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8460980 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-05-13
|  |  | 8460990 |  | Wilcox Environmental Engineering, Inc. | Indiana Department of Transportation | 1985-01-15
|  |  | 8461000 |  | AMEC E&I, Inc. | Indiana Department of Transportation | 1984-10-23
|  |  | 8461010 |  | Alliance Appraisal Group, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8461020 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1986-04-15
|  |  | 8461040 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8461050 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8461060 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8461070 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8461080 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8461090 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1984-10-23
|  |  | 8461100 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1985-09-24
|  |  | 8461110 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1985-09-24
|  |  | 8461120 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8461130 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8461150 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8461160 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1985-09-24
|  |  | 8461170 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1985-07-23
|  |  | 8461180 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8461200 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8461210 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8461220 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-05-13
|  |  | 8461240 |  | EcoTec, Inc. | Indiana Department of Transportation | 1984-10-23
|  |  | 8461250 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1986-02-18
|  |  | 8461270 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-05-13
|  |  | 8461280 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-05-13
|  |  | 8461290 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8461300 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1985-09-24
|  |  | 8461310 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-12-18
|  |  | 8461340 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8461360 | Spencer |  | Indiana Department of Transportation | 2004-01-21 | CE
CN
OT
PE
ROW
RR
UT
|  |  | 846136D | Spencer |  | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8461370 | Grant | ERES International, Inc. | Indiana Department of Transportation | 1998-10-06 | CE
ROW
RR
|  |  | 8461380 |  | ERES International, Inc. | Indiana Department of Transportation | 1995-09-12
|  |  | 8461390 | Marshall | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 2003-10-21 | CE
CN
PE
ROW
UT
|  |  | 8461420 |  |  | Indiana Department of Transportation | 1997-02-11
|  |  | 846142W |  |  | Indiana Department of Transportation | 1997-02-11
|  |  | 8461450 |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 8461470 |  | Brenner Design Incorporated | Indiana Department of Transportation | 1994-03-15
|  |  | 8461480 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1996-05-14
|  |  | 846148A |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1996-05-14
|  |  | 846148B |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1996-05-14
|  |  | 846148C |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1996-05-14
|  |  | 8461500 |  |  | Indiana Department of Transportation | 1992-10-06
|  |  | 8461540 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8461541 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8461610 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 2007-05-02 | CE
PE
ROW
UT
|  |  | 846161A |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1998-04-07
|  |  | 8461630 |  | ASA Land Surveying | Indiana Department of Transportation | 1992-06-16
|  |  | 8461640 | Warrick | CGI | Indiana Department of Transportation | 2000-04-18 | CE
CN
|  |  | 8461670 |  | All About Pavements, Inc. | Indiana Department of Transportation | 1988-07-12
|  |  | 8461700 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8461710 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8461730 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-09-24
|  |  | 8461740 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-09-24
|  |  | 8461760 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8461780 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1985-12-17
|  |  | 8461790 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1986-03-18
|  |  | 8461800 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8461810 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8461820 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8461830 |  | Archaeology and Geomorphology Services | Indiana Department of Transportation | 1985-11-19
|  |  | 8461860 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-05-17
|  |  | 8461861 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8461890 | Allen |  | Indiana Department of Transportation | 2000-04-11 | CE
CN
ROW
|  |  | 8461910 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-04-21
|  |  | 8461930 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8461940 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8461960 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8461970 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1985-09-24
|  |  | 8462000 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8462010 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8462020 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8462030 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8462040 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8462050 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1996-11-19
|  |  | 8462060 |  |  | Indiana Department of Transportation | 1996-11-19
|  |  | 8462090 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8462100 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8462150 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8462170 | Jennings |  | Indiana Department of Transportation | 2005-06-01 | UT
|  |  | 8462180 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8462190 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1996-02-20
|  |  | 8462210 | Tippecanoe |  | Indiana Department of Transportation | 1996-12-17 | CE
CN
|  |  | 8462240 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8462290 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8462300 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8462320 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462350 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8462360 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8462380 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 8462400 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8462430 |  |  | Indiana Department of Transportation | 1987-06-02
|  |  | 8462450 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8462460 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8462520 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8462530 |  | CGI | Indiana Department of Transportation | 1985-06-25
|  |  | 8462540 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8462550 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1986-08-19
|  |  | 8462580 |  |  | Indiana Department of Transportation | 1993-03-16
|  |  | 8462590 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8462600 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8462620 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462630 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462640 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462650 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462660 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462670 |  | DCD Consulting LLC | Indiana Department of Transportation | 1992-02-11
|  |  | 8462680 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462690 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462700 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462710 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462720 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462730 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462740 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462750 |  | DCD Consulting LLC | Indiana Department of Transportation | 1996-10-08
|  |  | 8462760 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1986-06-10
|  |  | 8462770 |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 8462780 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8462790 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8462800 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8462820 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1991-09-24
|  |  | 8462840 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8462850 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8462860 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8462870 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8462880 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8462890 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8462900 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8462910 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8462920 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8462930 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8462940 |  |  | Indiana Department of Transportation | 1994-01-11
|  |  | 8462960 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8462970 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8462980 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8462990 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8463010 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8463020 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8463050 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8463060 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8463080 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8463090 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8463150 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8463220 | Lawrence | ASA Land Surveying | Indiana Department of Transportation | 2000-02-22 | CE
CN
PE
ROW
|  |  | 8463221 | Lawrence |  | Indiana Department of Transportation | 2000-02-22 | CE
CN
|  |  | 8463222 | Lawrence |  | Indiana Department of Transportation | 2000-02-22 | CE
CN
|  |  | 8463340 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8463350 | Boone | Midwest Archaeological Research Services, Inc. | Indiana Department of Transportation | 2001-12-19 | CE
CN
PE
ROW
UT
|  |  | 8463360 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1997-01-14
|  |  | 8463390 | Grant | L'Acquis Consulting Enterprises Indianapolis, LLC | Indiana Department of Transportation | 1997-11-20 | CE
CN
|  |  | 8463450 | Grant | Chicago Title Insurance Company | Indiana Department of Transportation | 1997-04-08 | CE
CN
|  |  | 8463460 |  | DCD Consulting LLC | Indiana Department of Transportation | 1984-10-23
|  |  | 8463470 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8463530 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8463540 | Ripley | Lonco, Inc. | Indiana Department of Transportation | 2006-01-18 | CE
CN
PE
ROW
UT
|  |  | 8463550 |  | Lonco, Inc. | Indiana Department of Transportation | 1999-10-13
|  |  | 8463560 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8463620 | Vanderburgh |  | Indiana Department of Transportation | 2003-06-17 | CE
CN
ROW
|  |  | 8463650 |  | Central Diving Contractors | Indiana Department of Transportation | 1989-11-14
|  |  | 8463680 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8463700 |  | Consolidated Test Company | Indiana Department of Transportation | -339679.2083
|  |  | 8463750 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-02-18
|  |  | 8463760 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-06-10
|  |  | 8463770 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1987-04-07
|  |  | 8463780 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8463790 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8463810 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8463820 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8463821 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8463830 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8463850 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-03-19
|  |  | 8463860 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 8463870 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-04-16
|  |  | 8463880 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-07-23
|  |  | 8463890 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8463900 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-05-13
|  |  | 8463910 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8463920 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8463930 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8463990 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8464030 |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 8464040 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8464050 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8464060 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8464070 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8464100 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1989-07-18
|  |  | 8464110 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8464120 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8464130 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8464140 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8464150 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8464160 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8464170 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8464180 |  | Jackie S. Dodd, Attorney at Law | Indiana Department of Transportation | 1987-07-07
|  |  | 8464200 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8464210 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8464220 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8464230 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8464240 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 8464250 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8464260 |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 8464270 |  |  | Indiana Department of Transportation | 1985-03-19
|  |  | 8464300 |  |  | Indiana Department of Transportation | 1987-07-07
|  |  | 8464310 |  |  | Indiana Department of Transportation | 1994-12-13
|  |  | 8464320 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8464340 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8464350 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1984-07-17
|  |  | 8464360 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8464370 |  | Consolidated Test Company | Indiana Department of Transportation | 1984-07-17
|  |  | 8464380 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8464460 | Montgomery | Madison Milton Ferry LLC | Indiana Department of Transportation | 1997-02-11 | CN
|  |  | 8464470 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8464471 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8464472 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8464480 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8465470 |  |  |  | -339679.2083
|  |  | 8465590 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8485700 |  |  | Huntington County | 1992-07-28
|  |  | 8500170 |  |  |  | 1986-10-14
|  |  | 8501690 |  |  |  | 1984-09-18
|  |  | 8502040 |  |  | Allen County | -339679.2083
|  |  | 8502120 |  |  | Bartholomew County | -339679.2083
|  |  | 8502360 |  |  | Boone County | -339679.2083
|  |  | 8502380 |  |  | Carroll County | -339679.2083
|  |  | 8502660 |  |  | Clinton County | -339679.2083
|  |  | 8502890 |  |  | Decatur County | -339679.2083
|  |  | 8502950 |  |  |  | 1984-07-17
|  |  | 8503060 |  |  | Grant County | -339679.2083
|  |  | 8503090 |  |  | Greene County | -339679.2083
|  |  | 8503410 |  |  | Hamilton County | -339679.2083
|  |  | 8503530 |  |  |  | -339679.2083
|  |  | 8503950 |  |  | Henry County | -339679.2083
|  |  | 8504100 |  |  | Knox County | -339679.2083
|  |  | 8504140 |  |  | Lake County | -339679.2083
|  |  | 8504190 |  |  | Miami County | -339679.2083
|  |  | 8504360 |  |  | Monroe County | -339679.2083
|  |  | 8504590 |  |  | Perry County | -339679.2083
|  |  | 8505290 |  |  |  | -339679.2083
|  |  | 8505560 |  |  | Scott County | -339679.2083
|  |  | 850571Q |  |  | Indiana Department of Transportation | 1985-07-23
|  |  | 850571R |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 850571S |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 850571T |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 8506040 |  |  | Vigo County | -339679.2083
|  |  | 8506600 |  |  | Warrick County | -339679.2083
|  |  | 8506790 |  |  | Wells County | -339679.2083
|  |  | 8506830 |  |  |  | 1989-08-15
|  |  | 8507040 |  |  |  | 1987-02-03
|  |  | 8507290 |  |  |  | -339679.2083
|  |  | 8507630 | LaPorte |  | La Porte | -339679.2083 | CE
PE
RR
|  |  | 8508110 |  |  |  | -339679.2083
|  |  | 8508270 |  |  |  | 1985-09-24
|  |  | 8508370 |  |  |  | 1987-09-09
|  |  | 8508660 |  |  |  | 1985-08-27
|  |  | 8508750 |  |  |  | 1989-09-19
|  |  | 8508760 |  |  |  | 1986-08-19
|  |  | 8509080 |  |  |  | 1985-09-24
|  |  | 8509820 |  |  |  | -339679.2083
|  |  | 8509890 |  |  |  | 1987-06-02
|  |  | 8509920 |  |  |  | 1985-06-25
|  |  | 8510030 |  |  |  | 1989-08-15
|  |  | 8510260 |  | C Blair Enterprises, Inc. | Elkhart | 1990-09-18
|  |  | 8510280 |  |  |  | 1987-05-06
|  |  | 8510320 |  |  |  | -339679.2083
|  |  | 8510560 |  |  |  | -339679.2083
|  |  | 8511010 |  |  |  | 1990-02-06
|  |  | 8511110 |  |  |  | 1988-04-19
|  |  | 8511180 |  |  |  | 1985-12-17
|  |  | 8511240 |  |  |  | 1988-09-20
|  |  | 8511290 |  |  |  | 1988-04-19
|  |  | 8511320 |  |  |  | -339679.2083
|  |  | 8511680 |  |  | Ripley County | 1995-12-19
|  |  | 8511740 |  |  |  | 1985-05-21
|  |  | 8511800 |  |  |  | 1989-05-16
|  |  | 8511930 |  |  |  | 1987-12-15
|  |  | 8512220 |  |  | Greene County | -339679.2083
|  |  | 8512260 |  |  |  | 1988-07-12
|  |  | 8512360 |  |  | Martin County | -339679.2083
|  |  | 8512440 |  |  | Lawrence County | 1995-07-11
|  |  | 8512520 |  |  |  | 1987-11-17
|  |  | 8512550 |  |  |  | 1988-09-20
|  |  | 8512595 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8512740 |  |  |  | 1988-08-16
|  |  | 8512810 | Floyd |  | Floyd County | 1999-07-20 | CE
CN
|  |  | 8513252 |  |  | Fayette County | -339679.2083
|  |  | 8513460 |  |  | Terre Haute | 1993-09-14
|  |  | 8513461 |  |  |  | 1993-09-14
|  |  | 8513462 |  |  |  | 1993-09-14
|  |  | 8513470 |  |  |  | 1985-08-27
|  |  | 8513480 |  |  |  | -339679.2083
|  |  | 8513900 |  |  |  | 1986-07-15
|  |  | 8514050 |  |  |  | 1984-09-18
|  |  | 8514540 |  |  |  | 1988-09-06
|  |  | 8514570 |  |  |  | 1987-11-17
|  |  | 8515100 |  |  |  | 1988-10-18
|  |  | 8515800 |  |  |  | 1987-08-04
|  |  | 8516050 |  |  |  | 1988-03-15
|  |  | 8516120 |  |  |  | 1988-06-14
|  |  | 8516440 |  |  |  | 1985-10-29
|  |  | 8516580 |  |  |  | 1985-03-19
|  |  | 8517100 |  |  |  | 1987-08-04
|  |  | 8517101 |  |  |  | 1988-03-15
|  |  | 8517880 |  |  |  | 1988-09-20
|  |  | 8517940 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 8517951 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8518240 |  | DuSABLE, Inc. | Lafayette | -339679.2083
|  |  | 8518241 |  |  |  | 1986-03-18
|  |  | 8520750 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8521270 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8521380 |  |  | Indiana Department of Transportation | 1984-06-12
|  |  | 8521620 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8521640 |  |  |  | 1985-12-17
|  |  | 8521670 |  |  |  | 1986-09-16
|  |  | 8521750 |  |  |  | 1989-02-14
|  |  | 8521810 |  |  |  | 1989-10-17
|  |  | 8522030 |  |  |  | -339679.2083
|  |  | 8522070 |  |  |  | -339679.2083
|  |  | 8522100 |  |  |  | 1985-04-16
|  |  | 8522170 |  |  |  | -339679.2083
|  |  | 8522180 |  |  |  | 1986-07-15
|  |  | 8522200 |  |  |  | -339679.2083
|  |  | 8522270 | St. Joseph |  | South Bend | -339679.2083 | CE
PE
RR
|  |  | 8522321 |  |  |  | 1986-02-18
|  |  | 8522380 |  |  |  | -339679.2083
|  |  | 8522440 |  |  |  | -339679.2083
|  |  | 8522500 | Dekalb |  | Dekalb County | -339679.2083 | CE
PE
RR
|  |  | 8522550 |  |  | Dearborn County | -339679.2083
|  |  | 8522670 |  |  |  | -339679.2083
|  |  | 8522850 |  |  |  | -339679.2083
|  |  | 8522860 |  |  |  | -339679.2083
|  |  | 8522890 |  |  |  | -339679.2083
|  |  | 8522960 |  |  |  | 1989-07-18
|  |  | 8522970 |  |  |  | -339679.2083
|  |  | 8522990 |  |  |  | -339679.2083
|  |  | 8523000 |  |  |  | 1984-11-20
|  |  | 8523030 |  |  |  | -339679.2083
|  |  | 8523110 |  |  |  | 1986-05-13
|  |  | 8523750 | Knox | Louis Joyner, Architect | Knox County | -339679.2083 | PE
RR
|  |  | 8524110 |  |  |  | 1988-08-26
|  |  | 8524210 |  |  |  | 1984-08-21
|  |  | 8524490 |  |  | LaPorte County | -339679.2083
|  |  | 8524570 |  |  | LaPorte County | -339679.2083
|  |  | 8524610 |  |  |  | -339679.2083
|  |  | 8524950 |  |  |  | -339679.2083
|  |  | 8525280 |  |  |  | -339679.2083
|  |  | 8525370 |  |  |  | -339679.2083
|  |  | 8525420 | Marshall | ACMS Group, Inc. | Marshall County | -339679.2083 | PE
|  |  | 852575H |  | CGI | Indiana Department of Transportation | 1986-03-18
|  |  | 852575J |  | CGI | Indiana Department of Transportation | 1985-10-29
|  |  | 852575K |  | CGI | Indiana Department of Transportation | 1985-10-29
|  |  | 852575M |  | CGI | Indiana Department of Transportation | 1987-09-09
|  |  | 8525960 |  |  |  | -339679.2083
|  |  | 8526450 |  | CoCal Consulting, LLC | Alexandria | -339679.2083
|  |  | 8526560 |  |  |  | -339679.2083
|  |  | 8526710 |  |  | Shelby County | -339679.2083
|  |  | 8526790 |  |  |  | -339679.2083
|  |  | 8526840 |  |  |  | -339679.2083
|  |  | 8526860 |  |  |  | -339679.2083
|  |  | 8526940 |  |  |  | -339679.2083
|  |  | 8527050 |  |  |  | -339679.2083
|  |  | 8527090 |  |  |  | -339679.2083
|  |  | 8527120 |  |  |  | -339679.2083
|  |  | 8527320 | Vanderburgh | Louis Joyner, Architect | Evansville | -339679.2083 | CE
PE
RR
|  |  | 8527330 | Vanderburgh | CGI | Evansville | -339679.2083 | CE
PE
RR
|  |  | 8527390 |  |  |  | -339679.2083
|  |  | 8527400 |  |  |  | -339679.2083
|  |  | 8527440 |  |  |  | -339679.2083
|  |  | 8527590 |  |  |  | -339679.2083
|  |  | 8527780 |  |  |  | 1987-10-20
|  |  | 8528220 |  |  |  | 1987-12-15
|  |  | 8528230 |  |  |  | 1984-07-17
|  |  | 8528280 |  |  |  | 1989-05-16
|  |  | 8528370 |  |  |  | -339679.2083
|  |  | 8528390 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8528430 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8528550 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8529120 |  |  |  | 1984-10-23
|  |  | 8529330 |  |  |  | 1989-05-16
|  |  | 8529650 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8530340 |  |  |  | -339679.2083
|  |  | 8530770 |  |  |  | 1987-02-03
|  |  | 8531090 |  |  | Indiana Department of Transportation | 1984-09-18
|  |  | 8532660 |  |  |  | 1985-04-16
|  |  | 8532830 |  |  |  | 1987-10-20
|  |  | 8533510 |  |  |  | 1984-07-17
|  |  | 8533941 |  |  |  | 1987-02-03
|  |  | 8533942 |  |  |  | 1988-04-19
|  |  | 8533960 |  |  |  | 1984-09-18
|  |  | 8534801 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8534840 |  |  |  | 1985-08-27
|  |  | 8536010 |  |  |  | 1985-03-19
|  |  | 8536821 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8537650 |  |  |  | 1988-05-17
|  |  | 8537690 |  |  |  | -339679.2083
|  |  | 8537810 |  |  |  | 1986-10-14
|  |  | 8537880 |  |  |  | 1986-07-15
|  |  | 8538040 |  |  |  | 1986-05-13
|  |  | 8538440 |  |  |  | 1988-01-12
|  |  | 8538870 |  |  | Morgan County | 1990-03-13
|  |  | 8538970 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8539010 |  |  | Indiana Department of Transportation | 1984-10-23
|  |  | 8539510 |  |  |  | 1985-11-19
|  |  | 8539680 |  |  |  | 1987-03-10
|  |  | 8539870 |  |  |  | 1985-04-16
|  |  | 8539880 |  |  |  | 1985-04-16
|  |  | 8539910 |  |  |  | 1985-04-16
|  |  | 8539940 |  |  |  | 1985-04-16
|  |  | 8540040 |  |  |  | 1985-04-16
|  |  | 8540070 |  |  |  | 1986-02-18
|  |  | 8540080 |  |  |  | 1986-06-10
|  |  | 8540220 |  |  |  | 1988-02-09
|  |  | 8540290 |  |  |  | -339679.2083
|  |  | 8540291 |  |  |  | -339679.2083
|  |  | 8540450 |  |  |  | -339679.2083
|  |  | 8540470 |  |  |  | 1986-05-13
|  |  | 8540610 |  |  |  | 1988-02-09
|  |  | 8541180 |  |  |  | 1985-10-29
|  |  | 8541620 |  |  |  | 1985-08-27
|  |  | 8541680 |  |  |  | 1985-06-25
|  |  | 8541690 |  |  |  | -339679.2083
|  |  | 8541800 |  |  |  | 1987-04-07
|  |  | 8541890 |  |  |  | 1989-10-17
|  |  | 8542340 |  |  |  | -339679.2083
|  |  | 8542360 |  |  |  | 1985-09-24
|  |  | 8542440 |  |  |  | 1985-04-16
|  |  | 8542480 |  |  |  | 1985-04-16
|  |  | 8542540 |  |  |  | 1984-09-18
|  |  | 8542560 |  |  |  | 1984-08-21
|  |  | 8542570 |  |  |  | 1986-05-13
|  |  | 8542820 |  |  |  | -339679.2083
|  |  | 8543030 |  |  |  | -339679.2083
|  |  | 8543730 |  |  |  | 1985-06-25
|  |  | 8543750 |  |  |  | 1985-06-25
|  |  | 8543780 |  |  |  | -339679.2083
|  |  | 8543820 |  |  |  | 1987-07-07
|  |  | 8543860 |  |  |  | -339679.2083
|  |  | 8543880 |  |  |  | -339679.2083
|  |  | 8543960 |  |  |  | -339679.2083
|  |  | 8544330 |  |  |  | 1986-07-15
|  |  | 8544660 |  |  | Michigan City | -339679.2083
|  |  | 8545640 |  |  |  | -339679.2083
|  |  | 8545650 |  |  |  | -339679.2083
|  |  | 8545680 |  |  |  | -339679.2083
|  |  | 8545690 |  |  | Jay County | -339679.2083
|  |  | 8546110 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8549680 |  |  |  | -339679.2083
|  |  | 8549990 |  |  |  | -339679.2083
|  |  | 8550020 |  |  |  | -339679.2083
|  |  | 8550550 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8550642 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8550701 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1987-11-17
|  |  | 8553000 |  |  | Indiana Department of Transportation | 1985-04-16
|  |  | 8554361 |  |  | Indiana Department of Transportation | 1988-10-18
|  |  | 8554680 |  |  |  | -339679.2083
|  |  | 8554720 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8554740 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8554750 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8554760 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8554780 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8554830 |  |  |  | -339679.2083
|  |  | 8554880 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8555440 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8555500 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8555570 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8556970 |  |  |  | 1988-10-18
|  |  | 8557050 |  |  | Warren County | -339679.2083
|  |  | 8557070 |  |  |  | -339679.2083
|  |  | 8561990 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8562070 | Hendricks |  | Indiana Department of Transportation | 1998-11-17 | CE
CN
|  |  | 8562071 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8562072 | Hendricks | Horner and Shifrin, Inc. | Indiana Department of Transportation | 1998-11-17 | CE
CN
|  |  | 856207A |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8563260 |  |  | Indiana Department of Transportation | 1995-07-11
|  |  | 8563921 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-08-27
|  |  | 8563940 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8563950 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8563970 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8563971 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8563980 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8563981 |  | Advanced Appraisals, LLC | Indiana Department of Transportation | 1985-06-25
|  |  | 8564000 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8564410 | Posey |  | Indiana Department of Transportation | 1997-11-20 | CE
CN
ROW
|  |  | 856441A |  |  | Indiana Department of Transportation | 1997-01-23
|  |  | 8564520 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8564540 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8564550 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8564560 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8564570 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8564580 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564590 |  | Dummy Consulting Firm Too | Indiana Department of Transportation | 1986-04-15
|  |  | 8564600 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8564610 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8564620 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1985-05-21
|  |  | 8564630 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8564640 |  |  | Indiana Department of Transportation | 1984-11-20
|  |  | 8564650 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564660 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564690 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8564691 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8564710 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564720 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8564730 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8564740 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564741 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564750 |  |  | Indiana Department of Transportation | 1985-01-15
|  |  | 8564760 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8564770 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8564780 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8564950 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8565010 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8565240 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8565480 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8565490 |  |  | Indiana Department of Transportation | 1984-12-18
|  |  | 8565510 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8565520 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8565521 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8565522 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8565530 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8565531 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1986-03-18
|  |  | 8565532 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1986-03-18
|  |  | 8565540 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8565550 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8565560 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8565570 |  |  |  | 1986-02-18
|  |  | 8565571 |  |  |  | 1985-10-29
|  |  | 8565580 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1985-05-21
|  |  | 8565630 |  |  |  | 1988-03-15
|  |  | 8565650 |  |  |  | 1985-09-24
|  |  | 8565660 |  |  | Indiana Department of Transportation | 1985-02-19
|  |  | 8565680 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8565690 |  | Hy-Tech Response, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8565700 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8565710 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8565720 |  | Indiana Search Technologies | Indiana Department of Transportation | 1986-05-13
|  |  | 8565730 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8565740 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8565750 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8565770 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8565780 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8565790 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8565800 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8565810 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8565820 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8565830 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8565840 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8565860 |  |  | Indiana Department of Transportation | 2000-04-18
|  |  | 8565880 |  | MCIS LLC | Indiana Department of Transportation | 1986-03-18
|  |  | 8565890 |  |  | Indiana Department of Transportation | 1987-04-07
|  |  | 8568000 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8568040 |  |  | Indiana Department of Transportation | 1985-06-25
|  |  | 8568060 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8568070 |  |  | Indiana Department of Transportation | 1985-05-21
|  |  | 8568080 |  | Edwards and Kelcey | Indiana Department of Transportation | 1993-05-27
|  |  | 8568090 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8568200 |  |  | Indiana Department of Transportation | 1993-06-15
|  |  | 8568210 | Jennings |  | Indiana Department of Transportation | 1998-11-17 | CE
CN
PE
ROW
|  |  | 8568220 | Jennings |  | Indiana Department of Transportation | 1996-02-20 | CE
CN
|  |  | 8568230 |  |  | Indiana Department of Transportation | 1991-10-24
|  |  | 8568240 |  |  | Indiana Department of Transportation | 1991-10-24
|  |  | 8568250 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8568260 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8568270 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8568280 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8568290 |  |  | Indiana Department of Transportation | 1993-12-14
|  |  | 8568300 |  |  | Indiana Department of Transportation | 1995-04-18
|  |  | 8568310 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8568320 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1992-09-01
|  |  | 8568350 |  | Eco Logic, LLC | Indiana Department of Transportation | 1993-05-27
|  |  | 8568360 |  |  | Indiana Department of Transportation | 1995-07-11
|  |  | 8568370 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8568390 |  | Banning Engineering, P.C. | Indiana Department of Transportation | 1993-04-13
|  |  | 8568400 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8568410 |  |  | Indiana Department of Transportation | 1995-04-18
|  |  | 8568420 | Martin |  | Indiana Department of Transportation | 1999-03-23 | CE
CN
PE
|  |  | 8568430 | Dubois |  | Indiana Department of Transportation | 1997-10-22 | CE
|  |  |  | Jackson |  | Indiana Department of Transportation | 1997-10-22 | CE
CN
|  |  | 8568440 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8568450 |  |  | Indiana Department of Transportation | 1995-11-21
|  |  | 8568460 |  |  | Indiana Department of Transportation | 1994-10-18
|  |  | 8568470 | Knox |  | Indiana Department of Transportation | 1998-11-17 | CN
|  |  | 8568490 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8568500 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8568510 | Dubois |  | Indiana Department of Transportation | 1998-11-17 | CE
CN
|  |  | 8568520 | Dubois |  | Indiana Department of Transportation | 1998-11-17 | CE
CN
|  |  | 8568530 |  |  | Indiana Department of Transportation | 1996-01-23
|  |  | 8568540 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8568550 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8568560 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8568570 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8568580 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 1995-01-10
|  |  | 8568590 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8568600 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8568610 |  | Haas & Associates, L.L.C. | Indiana Department of Transportation | 1993-07-20
|  |  | 8568620 |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8568630 |  |  | Indiana Department of Transportation | 1990-11-20
|  |  | 8568640 |  |  | Indiana Department of Transportation | 1990-11-20
|  |  | 8568660 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8568680 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8568710 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8568720 |  |  | Indiana Department of Transportation | 1998-02-10
|  |  | 856872A |  |  | Indiana Department of Transportation | 1997-09-16
|  |  | 8568730 |  |  | Indiana Department of Transportation | 1993-04-13
|  |  | 8568740 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8568750 |  |  | Indiana Department of Transportation | 1994-01-11
|  |  | 8568760 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8568770 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8568780 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8568790 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8568800 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8568810 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8568820 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1995-11-21
|  |  | 8568830 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8568840 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8568850 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8568860 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 8568880 |  | Eco Logic, LLC | Indiana Department of Transportation | 1991-05-14
|  |  | 8568890 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8568900 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8568910 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8568920 |  | Brenner Design Incorporated | Indiana Department of Transportation | 1994-03-15
|  |  | 8568930 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8568940 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1989-03-14
|  |  | 8568950 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1989-03-14
|  |  | 8568960 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 1990-02-06
|  |  | 8568970 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8568980 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8568990 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8569000 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8569010 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8569020 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8569030 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8569040 |  | GS-IN P.C. | Indiana Department of Transportation | 1990-03-13
|  |  | 8569050 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8569060 |  |  | Indiana Department of Transportation | 1987-09-09
|  |  | 8569070 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8569080 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1988-06-14
|  |  | 8569090 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8569120 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8569130 |  | Louis Joyner, Architect | Indiana Department of Transportation | 1988-06-14
|  |  | 8569140 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8569150 |  | Brenner Design Incorporated | Indiana Department of Transportation | 1988-12-13
|  |  | 8569160 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8569170 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1988-01-12
|  |  | 8569180 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8569190 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1990-04-17
|  |  | 8569200 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8569210 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8569230 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8569240 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1988-03-15
|  |  | 8569260 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1989-03-14
|  |  | 8569270 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8569280 |  | Commonwealth Engineers, Inc. | Indiana Department of Transportation | 1989-11-14
|  |  | 8569290 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8569300 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8569310 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8569320 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8569330 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8569340 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8569350 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569351 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569352 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569353 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569354 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569360 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569366 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569370 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569371 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569372 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569380 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569381 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569382 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569383 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8569390 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8569400 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8569410 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8569420 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8569430 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8569440 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8569450 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8569460 |  |  | Indiana Department of Transportation | 1987-09-09
|  |  | 8569470 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8569480 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8569490 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8569500 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8569510 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8569540 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8569560 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-06-14
|  |  | 8569570 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-05-17
|  |  | 8569580 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-05-17
|  |  | 8569590 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8569600 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1989-02-14
|  |  | 8569610 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1989-02-14
|  |  | 8569620 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1990-02-06
|  |  | 8569630 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1990-02-06
|  |  | 8569640 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1997-04-08
|  |  | 8569650 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8569660 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8569670 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1993-10-19
|  |  | 8569680 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8569690 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8569700 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-02-06
|  |  | 8569710 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-02-06
|  |  | 8569720 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8569730 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8569740 |  |  | Indiana Department of Transportation | 1988-09-20
|  |  | 8569760 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1988-08-16
|  |  | 8569790 |  |  | Indiana Department of Transportation | 1989-01-17
|  |  | 8569800 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8569810 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1989-06-13
|  |  | 8569820 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1988-11-15
|  |  | 8569830 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-05-17
|  |  | 8569840 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1988-11-15
|  |  | 8569850 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8569860 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8569870 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8569880 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8569900 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8569910 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8569920 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8569930 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8569940 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8569950 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8569980 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8569990 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570010 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8570020 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8570030 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570040 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570050 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8570060 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8570070 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8570080 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8570090 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8570100 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8570110 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8570120 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8570130 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8570140 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570150 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8570160 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8570170 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8570172 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8570180 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570190 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8570220 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570230 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8570231 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8570240 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8570250 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8570260 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8570270 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570280 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570290 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8570300 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8570310 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8570320 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8570330 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8570350 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570360 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8570380 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570390 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570400 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8570430 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570440 |  |  | Indiana Department of Transportation | 1994-03-15
|  |  | 8570450 |  |  | Indiana Department of Transportation | 1988-04-05
|  |  | 8570460 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8570470 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570480 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8570490 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570500 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570510 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570520 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8570530 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570540 | Spencer |  | Indiana Department of Transportation | 1999-10-13 | CE
CN
|  |  | 8570550 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570560 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8570570 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8570580 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8570590 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8570600 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8570610 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8570620 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8570630 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570640 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8570650 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8570660 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8570670 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8570680 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8570690 |  |  | Indiana Department of Transportation | 1994-12-13
|  |  | 8570700 |  | CBRE, Inc. | Indiana Department of Transportation | 1992-12-15
|  |  | 8570710 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8570720 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8570730 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8570750 | Crawford |  | Indiana Department of Transportation | 2003-11-18 | CE
CN
|  |  | 8570760 |  |  | Indiana Department of Transportation | 1994-03-15
|  |  | 8570770 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8570780 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570790 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570800 |  | CGI | Indiana Department of Transportation | 2001-11-20
|  |  | 8570820 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8570840 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8570850 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570860 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8570870 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8570880 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8570890 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8570900 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8570910 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8570920 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8570930 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8570950 |  |  | Indiana Department of Transportation | 1991-07-30
|  |  | 8570960 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8570970 |  |  | Indiana Department of Transportation | 1991-07-30
|  |  | 8570980 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8570990 |  |  | Indiana Department of Transportation | 1992-01-14
|  |  | 8571000 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8571010 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8571020 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8571030 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8571040 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8571050 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8571060 |  |  | Indiana Department of Transportation | 1998-05-12
|  |  | 8571070 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8571080 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8571090 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8571110 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8571120 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8571130 |  |  | Indiana Department of Transportation | 1986-06-30
|  |  | 8571140 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8571150 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8571160 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8571170 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8571180 |  |  | Indiana Department of Transportation | 1988-02-09
|  |  | 8571190 |  | EcoTec, Inc. | Indiana Department of Transportation | 1994-03-15
|  |  | 8571200 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8571210 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8571220 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571230 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8571231 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8571232 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8571240 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8571270 |  | CGI | Indiana Department of Transportation | 1985-10-29
|  |  | 8571280 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-06-15
|  |  | 8571290 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8571300 |  | DCD Consulting LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8571320 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571330 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1992-07-28
|  |  | 8571340 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571350 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571360 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571370 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571380 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571390 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571400 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8571410 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 8571420 |  | EcoTec, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 8571430 |  | EcoTec, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 8571460 |  |  | Indiana Department of Transportation | 1989-08-15
|  |  | 8571470 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8571490 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8571510 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8571530 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-11-18
|  |  | 8571540 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8571550 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8571560 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8571570 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8571580 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8571590 |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 8571610 |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 8571620 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8571630 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8571650 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8571670 |  |  | Indiana Department of Transportation | 1990-01-13
|  |  | 8571680 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8571710 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8571720 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8571730 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8571740 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8571760 | Blackford | Continental Mapping Consultants, LLC | Indiana Department of Transportation | 1997-12-16 | CE
CN
|  |  | 8571770 | Lake | Huff & Huff, Inc. | Indiana Department of Transportation | 1996-03-19 | CE
CN
|  |  |  | Porter | Huff & Huff, Inc. | Indiana Department of Transportation | 1996-03-19 | CN
|  |  | 8571780 |  | Huff & Huff, Inc. | Indiana Department of Transportation | 1995-11-21
|  |  | 8571790 |  |  | Indiana Department of Transportation | 2001-04-24
|  |  | 8571820 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8571830 |  | InfoTech | Indiana Department of Transportation | -339679.2083
|  |  | 8571840 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 1992-10-06
|  |  | 8571890 | St. Joseph |  | Indiana Department of Transportation | 2006-10-18 | CE
CN
ROW
UT
|  |  | 8571900 | St. Joseph |  | Indiana Department of Transportation | 2006-10-18 | CE
CN
ROW
UT
|  |  | 8571910 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CE
CN
ROW
UT
|  |  | 8571920 | St. Joseph |  | Indiana Department of Transportation | 2008-04-09 | CE
CN
ROW
UT
|  |  | 8571930 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CE
CN
ROW
UT
|  |  | 8571950 | Pulaski | McCormick Engineering, LLC | Indiana Department of Transportation | -339679.2083 | PE
ROW
|  |  | 8571960 | Lake | Karen | Indiana Department of Transportation | 2009-06-03 | CE
CN
ROW
|  |  | 8571980 | Monroe | Absolute Title Services, LLC | Indiana Department of Transportation | 1997-01-14 | CE
CN
ROW
|  |  | 857198A |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1995-08-15
|  |  | 8572000 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8572010 |  | ASA Land Surveying | Indiana Department of Transportation | 1987-04-07
|  |  | 8572030 |  | CGI | Indiana Department of Transportation | 1986-04-15
|  |  | 8572050 | Gibson | III FFC | Indiana Department of Transportation | 2008-02-27 | CE
CN
ROW
UT
|  |  | 8572060 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1998-02-10
|  |  | 857206A |  |  | Indiana Department of Transportation | 1996-12-17
|  |  | 8572070 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8572080 | Porter | Leitner and Associates, Inc. | Indiana Department of Transportation | 1996-12-17 | ROW
|  |  | 857208A |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1996-02-20
|  |  | 8572090 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 1999-09-14 | CE
CN
PE
ROW
|  |  | 8572091 | Morgan | GAI Consultants, Inc. | Indiana Department of Transportation | 1999-09-14 | CE
CN
PE
ROW
|  |  | 8572100 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8572110 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1993-08-17
|  |  | 8572170 |  | Collier Transport Inc. | Indiana Department of Transportation | 1993-05-27
|  |  | 8572190 | Tippecanoe | ASA Engineering Consultants, Inc. | Indiana Department of Transportation | 2006-03-15 | CE
CN
ROW
UT
|  |  | 857220A |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1996-12-17
|  |  | 8572210 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8572230 | Hamilton |  | Indiana Department of Transportation | 1997-11-20 | CE
CN
ROW
|  |  | 8572270 | Bartholomew |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8572280 | Jackson | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 8572290 |  | LONCO, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8572300 | Grant | Dave Helton & Associates, Inc. | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8572310 | Kosciusko |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8572360 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8572380 | Sullivan |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8572400 |  | DuSABLE, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8572420 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8572430 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8572450 | Jackson | FAA National, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8572470 |  | Consoer Townsend Envirodyne Engineers of Indiana, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8572480 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8572490 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8572500 |  | March Environmental Services, LLC | Indiana Department of Transportation | 1986-06-10
|  |  | 8572520 |  | Collier Transport Inc. | Indiana Department of Transportation | 1987-02-03
|  |  | 8572530 |  | AES Services, Inc. | Indiana Department of Transportation | 1988-03-15
|  |  | 8572540 |  | American Engineers, Inc. | Indiana Department of Transportation | 1986-06-10
|  |  | 8572550 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8572560 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8572570 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1987-05-06
|  |  | 8572580 |  | ERES International, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 8572590 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8572600 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8572630 |  | InfoTech | Indiana Department of Transportation | 1985-11-19
|  |  | 8572640 |  | InfoTech | Indiana Department of Transportation | 1988-12-13
|  |  | 8572650 |  | InfoTech | Indiana Department of Transportation | 1985-11-19
|  |  | 8572660 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8572670 |  | Fusion by Design, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 8572680 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8572690 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8572700 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8572710 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8572720 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1987-12-15
|  |  | 8572730 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1987-12-15
|  |  | 8572740 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 8572750 |  | Dodd Title Corporation | Indiana Department of Transportation | 1987-05-06
|  |  | 8572760 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8572770 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8572790 |  | Indiana 15 Regional Planning Commission | Indiana Department of Transportation | 1987-05-19
|  |  | 8572800 |  | Eco Logic, LLC | Indiana Department of Transportation | 1986-08-19
|  |  | 8572810 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8572820 |  | Eco Logic, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8572830 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8572840 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8572850 |  | Basin Field Services, Inc. | Indiana Department of Transportation | 1986-06-10
|  |  | 8572870 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-01-12
|  |  | 8572890 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 8572900 |  |  | Indiana Department of Transportation | 1987-05-06
|  |  | 8572910 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1987-05-19
|  |  | 8572920 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1987-11-17
|  |  | 8573010 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1986-01-14
|  |  | 8573020 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8573030 |  | Horner and Shifrin, Inc. | Indiana Department of Transportation | 1986-08-19
|  |  | 8573040 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-03-14
|  |  | 8573060 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-08-19
|  |  | 8573090 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8573100 |  | Consolidated Test Company | Indiana Department of Transportation | 1987-05-06
|  |  | 8573110 |  | Cornerstone Design | Indiana Department of Transportation | 1987-05-06
|  |  | 8573120 |  | Consolidated Test Company | Indiana Department of Transportation | 1986-05-13
|  |  | 8573130 |  | Jeffrey S. Juday | Indiana Department of Transportation | 1986-08-19
|  |  | 8573140 |  | Absolute Title Services, LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8573150 |  | ASA Land Surveying | Indiana Department of Transportation | 1986-11-18
|  |  | 8573160 |  | Janssen & Spaans Engineering, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8573180 |  | Great Lakes Engineering, Inc. | Indiana Department of Transportation | 1985-11-19
|  |  | 8573200 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8573210 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 1986-11-18
|  |  | 8573220 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 1988-04-19
|  |  | 8573230 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8573240 |  | JCI Bridge Group, Inc. | Indiana Department of Transportation | 1986-06-10
|  |  | 8573250 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1986-10-14
|  |  | 8573270 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8573280 |  | GRL Engineers, Inc. | Indiana Department of Transportation | 1986-06-03
|  |  | 8573330 |  | Andrews Engineering, Inc. | Indiana Department of Transportation | 1986-11-18
|  |  | 8573380 |  | BA Martin Architects, PC | Indiana Department of Transportation | 1987-05-06
|  |  | 8573390 |  | Linda F. Russell | Indiana Department of Transportation | 1986-08-19
|  |  | 8573400 |  | MainLine Management, Inc. | Indiana Department of Transportation | 1987-05-06
|  |  | 8573410 |  | All About Pavements, Inc. | Indiana Department of Transportation | 1987-01-13
|  |  | 8573420 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8573430 |  | Heritage Land Services | Indiana Department of Transportation | 1986-06-10
|  |  | 8573440 |  | Danch Harner and Associates, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8573450 |  | Archonsortium, LLC | Indiana Department of Transportation | 1987-05-19
|  |  | 8573460 |  | Clayton L. Roots | Indiana Department of Transportation | 1986-10-14
|  |  | 8573470 |  | Clayton L. Roots | Indiana Department of Transportation | 1986-10-14
|  |  | 8573480 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8573490 |  | Consolidated Test Company | Indiana Department of Transportation | 1987-05-19
|  |  | 8573500 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | 1986-05-13
|  |  | 8573510 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | 1986-05-13
|  |  | 8573520 |  | Cheri K. Lewis Engineers | Indiana Department of Transportation | 1986-05-13
|  |  | 8573530 |  | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | 1986-02-18
|  |  | 8573540 |  | Blood Hound, Inc. (former) | Indiana Department of Transportation | 1988-01-12
|  |  | 8573560 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8573570 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1988-03-15
|  |  | 8573580 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 1986-07-15
|  |  | 8573610 |  | Civil Inspection Services, LLC | Indiana Department of Transportation | 1986-07-15
|  |  | 8573620 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1986-02-18
|  |  | 8573630 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1986-08-19
|  |  | 8573640 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1986-08-19
|  |  | 8573670 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1986-11-18
|  |  | 8573680 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8573690 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8573700 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1987-05-06
|  |  | 8573710 |  | Dodd Title Corporation | Indiana Department of Transportation | 1986-08-19
|  |  | 8573720 |  | Dodd Title Corporation | Indiana Department of Transportation | 1986-08-19
|  |  | 8573740 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8573750 |  |  | Indiana Department of Transportation | 1995-10-17
|  |  | 8573770 | Vanderburgh | CGI | Indiana Department of Transportation | -339679.2083 | PE
|  |  | 8573860 |  | Duke Energy Corporation | Indiana Department of Transportation | 1992-11-10
|  |  | 8573870 |  | Farah and Sons, Inc. | Indiana Department of Transportation | 1992-09-01
|  |  | 8573880 |  |  | Indiana Department of Transportation | 1992-02-11
|  |  | 8573910 |  | Bonar Group, LLC | Indiana Department of Transportation | 1994-06-14
|  |  | 8573920 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8573950 |  |  | Indiana Department of Transportation | 1995-04-18
|  |  | 8573970 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574000 |  |  | Indiana Department of Transportation | 1998-04-07
|  |  | 8574050 | Boone | E.J. Breneman, LP | Indiana Department of Transportation | 2004-03-23 | CE
CN
PE
ROW
RR
UT
|  |  | 8574060 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574090 |  |  | Indiana Department of Transportation | 1991-03-12
|  |  | 8574100 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8574120 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574130 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574141 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574160 | Lake |  | Indiana Department of Transportation | 2007-03-21 | CE
CN
PE
ROW
|  |  | 8574170 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574190 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574200 | Knox |  | Indiana Department of Transportation | 2000-10-17 | CE
CN
PE
ROW
UT
|  |  | 8574220 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8574240 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8574250 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1993-03-16
|  |  | 8574270 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574280 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8574290 | Dekalb | Mader Design, LLC | Indiana Department of Transportation | 2002-08-13 | CE
CN
ROW
|  |  | 8574300 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-03-24
|  |  | 8574310 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1992-03-24
|  |  | 8574330 |  |  | Indiana Department of Transportation | 1995-01-10
|  |  | 8574360 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8574390 |  |  | Indiana Department of Transportation | 1993-05-27
|  |  | 8574400 | Knox |  | Indiana Department of Transportation | 2008-10-01 | CE
CN
PE
UT
|  |  | 8574410 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8574440 |  |  | Indiana Department of Transportation | 1988-09-06
|  |  | 8574450 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8574470 |  |  | Indiana Department of Transportation | 1993-05-11
|  |  | 8574480 |  |  | Indiana Department of Transportation | 1987-09-09
|  |  | 8574490 | Daviess |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
PE
ROW
UT
|  |  |  | Knox |  | Indiana Department of Transportation | 2005-07-20 | CE
CN
PE
UT
|  |  | 8574530 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574590 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574620 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574630 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574640 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574650 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574660 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8574670 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574680 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574690 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8574700 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8574710 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8574720 |  |  | Indiana Department of Transportation | 1988-07-12
|  |  | 8574740 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8574750 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8574760 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8574770 |  |  | Indiana Department of Transportation | 1993-06-15
|  |  | 8574780 |  |  | Indiana Department of Transportation | 1993-06-15
|  |  | 8574820 |  |  | Indiana Department of Transportation | 2007-01-10
|  |  | 8574880 |  |  | Indiana Department of Transportation | 2001-02-13
|  |  | 8574910 |  |  | Indiana Department of Transportation | 2004-05-25
|  |  | 8574940 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8574980 |  |  | Wabash | 2005-08-17
|  |  | 8575010 |  |  | Indiana Department of Transportation | 1985-10-29
|  |  | 8575020 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-08-27
|  |  | 8575060 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8575300 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8575370 |  | Associated Appraisal Group, Inc. | Indiana Department of Transportation | 1986-03-18
|  |  | 8575390 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8575391 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8575400 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-08-27
|  |  | 8575750 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8575800 |  |  |  | 1986-09-16
|  |  | 8576000 |  |  | Indianapolis | 1988-09-20
|  |  | 8577090 |  |  | Indiana Department of Transportation | 1986-07-15
|  |  | 8577490 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8577500 |  |  | Indiana Department of Transportation | 1986-06-10
|  |  | 8577510 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8577520 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8577620 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8577630 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8577640 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8585840 |  |  | Clark County | 1995-10-17
|  |  | 8586920 |  | Bayswater Company, LLC | Terre Haute | 1992-10-06
|  |  | 8600015 |  |  | Terre Haute | 1991-06-18
|  |  | 8600025 |  | Bayswater Company, LLC | Terre Haute | 1998-04-07
|  |  | 8600055 |  |  |  | -339679.2083
|  |  | 8600350 |  |  |  | 1987-06-02
|  |  | 8600410 |  |  |  | 1987-06-02
|  |  | 8600495 |  |  |  | -339679.2083
|  |  | 8600980 |  |  |  | 1987-02-03
|  |  | 8601060 |  |  |  | 1986-03-18
|  |  | 8601401 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8601480 |  |  |  | 1990-07-17
|  |  | 8602610 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 8602720 |  |  | Kokomo | -339679.2083
|  |  | 8602860 |  |  |  | 1987-03-10
|  |  | 8603580 |  |  |  | 1986-03-18
|  |  | 8603750 |  |  |  | -339679.2083
|  |  | 8604050 |  |  |  | -339679.2083
|  |  | 8604060 |  |  |  | -339679.2083
|  |  | 8604105 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8604125 |  | CGI | Indiana Department of Transportation | 1987-07-07
|  |  | 8604135 |  | CGI | Indiana Department of Transportation | 1988-01-12
|  |  | 8604145 |  | CGI | Indiana Department of Transportation | 1988-06-14
|  |  | 8604185 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8604195 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1999-04-20
|  |  | 860443B |  | CGI | Indiana Department of Transportation | 1987-06-02
|  |  | 8604621 |  |  | Indiana Department of Transportation | 1994-11-15
|  |  | 8604675 |  | Carters Appraisal Service | Clinton County | 1994-04-19
|  |  | 8605090 |  |  |  | 1989-01-17
|  |  | 8605170 |  |  | Sullivan | -339679.2083
|  |  | 8605270 |  |  |  | 1985-06-25
|  |  | 8605750 |  |  |  | 1989-06-13
|  |  | 8605890 |  |  |  | -339679.2083
|  |  | 8606770 |  |  |  | -339679.2083
|  |  | 8606860 |  |  |  | -339679.2083
|  |  | 8606920 | Knox | Louis Joyner, Architect | Knox County | -339679.2083 | CE
PE
RR
|  |  | 8607010 |  |  |  | -339679.2083
|  |  | 8607120 |  |  |  | -339679.2083
|  |  | 8607125 |  |  |  | -339679.2083
|  |  | 8607280 |  | Consolidated Test Company |  | 1994-06-14
|  |  | 8607281 |  | Consolidated Test Company | Hammond | 1994-06-14
|  |  | 8607970 |  |  |  | 1986-07-15
|  |  | 8608100 |  |  |  | 1985-07-23
|  |  | 8608920 |  |  |  | 1986-09-16
|  |  | 8609100 |  |  | Orange County | -339679.2083
|  |  | 8609350 |  |  |  | -339679.2083
|  |  | 8609440 |  |  |  | 1987-02-03
|  |  | 8609560 | Knox | Louis Joyner, Architect | Vincennes | 1999-08-17 | CE
CN
PE
|  |  | 8610705 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8610715 |  | Associated Right-of-Way Services, Inc. | Indiana Department of Transportation | 1995-04-18
|  |  | 8610725 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8610735 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8610795 |  | Engineering Resources, Inc. |  | -339679.2083
|  |  | 8610825 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8610865 | Warren |  | Indiana Department of Transportation | 1999-11-16 | CE
CN
PE
|  |  | 8610875 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8610876 |  |  | Indiana Department of Transportation | 1992-05-21
|  |  | 8610885 | Parke |  | Indiana Department of Transportation | 2002-01-15 | CE
CN
ROW
UT
|  |  | 8610925 | Dearborn |  | Indiana Department of Transportation | 2000-04-18 | CE
CN
UT
|  |  | 8610945 |  | Approved Appraisals of Indiana, LLC | Indiana Department of Transportation | 1993-05-27
|  |  | 8610965 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8610975 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8610985 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8611015 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8611025 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8611035 |  |  | Indiana Department of Transportation | 1988-09-06
|  |  | 8611045 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8611055 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8611065 |  |  | Indiana Department of Transportation | 1990-07-17
|  |  | 8611095 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8611205 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8611340 |  |  |  | 1986-07-15
|  |  | 8612005 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8612025 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8612035 |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-01-13
|  |  | 8612045 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1986-09-16
|  |  | 8612055 |  | Howard J. Barth & Associates, Inc. | Indiana Department of Transportation | 1986-09-16
|  |  | 8612065 |  | Baxter & Woodman, Inc. | Indiana Department of Transportation | 1986-09-16
|  |  | 8612075 |  | Marine Solutions, Inc. | Indiana Department of Transportation | 1993-05-27
|  |  | 8612085 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-04-19
|  |  | 8612095 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8612100 |  |  |  | 1986-06-10
|  |  | 8612115 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8612135 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-11-16
|  |  | 8612195 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 1986-12-16
|  |  | 8612225 |  | HNTB Indiana, Inc. | Indiana Department of Transportation | 1996-02-20
|  |  | 8612295 |  | Manhard Consulting, Ltd. | Indiana Department of Transportation | 1987-02-03
|  |  | 8612325 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1986-12-16
|  |  | 8612335 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8612355 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1986-11-18
|  |  | 8612365 |  | ERES International, Inc. | Indiana Department of Transportation | 1987-03-10
|  |  | 8612395 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8612405 |  |  | Indiana Department of Transportation | 2000-01-02
|  |  | 8612415 | Wayne |  | Indiana Department of Transportation | 2000-01-02 | CE
CN
PE
|  |  | 8612425 |  | IXOYE, Limited | Indiana Department of Transportation | 1987-01-13
|  |  | 8612450 |  |  |  | 1986-07-15
|  |  | 8612455 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8612465 |  | Engineering Resources, Inc. | Indiana Department of Transportation | 1986-11-18
|  |  | 8612475 |  |  | Indiana Department of Transportation | 1987-03-10
|  |  | 8612485 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8612515 |  | All About Pavements, Inc. | Indiana Department of Transportation | 1986-11-18
|  |  | 8612525 |  | Apex Consulting & Surveying, Inc. | Indiana Department of Transportation | 1987-03-10
|  |  | 8612535 |  |  | Indiana Department of Transportation | 1986-12-16
|  |  | 8612555 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8612565 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8612575 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8612585 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8612605 |  |  | Indiana Department of Transportation | 1986-08-19
|  |  | 8612775 |  |  | Indiana Department of Transportation | 1986-09-25
|  |  | 8613105 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8613110 |  |  |  | -339679.2083
|  |  | 8613160 |  |  |  | -339679.2083
|  |  | 8613180 |  |  | Knox County | -339679.2083
|  |  | 8613210 |  |  |  | -339679.2083
|  |  | 8613490 |  |  |  | 1988-03-15
|  |  | 8614320 |  |  |  | 1986-07-01
|  |  | 8615190 |  |  |  | 1986-05-13
|  |  | 8615681 |  |  | Indiana Department of Transportation | 1986-04-08
|  |  | 8616720 |  |  |  | 1987-07-07
|  |  | 8618320 |  |  |  | 1988-02-09
|  |  | 8620060 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 8620340 |  | Data Transfer Solutions, LLC | Jeffersonville | -339679.2083
|  |  | 8620580 |  |  |  | 1987-07-07
|  |  | 8620630 |  |  |  | 1987-05-06
|  |  | 8621060 |  |  |  | 1985-09-24
|  |  | 8621235 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8621280 |  |  |  | 1985-11-19
|  |  | 8621730 |  |  | Greencastle | 1990-05-15
|  |  | 8621790 |  |  |  | 1986-10-14
|  |  | 8621830 |  |  |  | 1986-07-15
|  |  | 8621900 |  |  |  | 1987-06-02
|  |  | 8622810 | Whitley |  | Whitley County | -339679.2083 | PE
|  |  | 8622900 |  |  |  | 1987-05-06
|  |  | 8623020 |  |  |  | 1988-08-16
|  |  | 8623095 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8624360 |  |  |  | 1986-05-13
|  |  | 8627730 |  |  |  | -339679.2083
|  |  | 8627740 |  |  |  | -339679.2083
|  |  | 8627760 | Jasper | Douglass Environmental Services, Inc. | Jasper | -339679.2083 | PE
|  |  | 8627980 |  |  | Elwood | -339679.2083
|  |  | 8628000 |  |  |  | 1986-07-15
|  |  | 8628180 | Posey |  | Posey County | -339679.2083 | PE
|  |  | 8629770 |  |  |  | 1988-07-12
|  |  | 8629820 |  |  |  | 1987-05-06
|  |  | 8629870 |  |  |  | 1987-05-06
|  |  | 8630280 |  |  |  | 1986-05-13
|  |  | 8630570 |  |  |  | 1987-12-15
|  |  | 8631360 |  |  |  | 1989-03-14
|  |  | 8631480 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8631485 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8631660 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8631665 |  |  | Indiana Department of Transportation | 1992-09-29
|  |  | 8632440 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8632445 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 8632640 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8632645 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8632710 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8632715 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8633240 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8633245 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8633520 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8633525 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8633820 |  |  | Indiana Department of Transportation | 1988-08-16
|  |  | 8633825 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8634050 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8634055 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8634410 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8634415 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8634560 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8634565 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8634710 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8634715 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8634945 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8634960 |  | DLZ Indiana, LLC | Indiana Department of Transportation | 1992-11-10
|  |  | 8635145 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8635380 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8635385 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8636740 |  |  | Indiana Department of Transportation | 1990-03-13
|  |  | 8636745 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8636840 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8636845 |  |  | Indiana Department of Transportation | 1994-03-15
|  |  | 8636870 |  |  | Indiana Department of Transportation | 1995-11-21
|  |  | 8636875 |  |  | Indiana Department of Transportation | 1993-10-19
|  |  | 8637170 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8637175 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8637290 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8637295 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8637580 |  |  | Indiana Department of Transportation | 1987-02-03
|  |  | 8637585 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8638350 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8638355 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8638356 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8638360 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8638365 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8638370 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8638375 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8638410 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8638415 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8638425 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8638560 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8638565 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8638570 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8638575 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8638960 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8639180 |  |  | Indiana Department of Transportation | 1988-04-19
|  |  | 8639185 |  |  | Indiana Department of Transportation | 1992-07-28
|  |  | 8639230 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8639235 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8639240 |  |  | Indiana Department of Transportation | 1986-06-03
|  |  | 8639245 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8639550 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8639580 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8639590 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8639595 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 8639900 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8639905 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8639920 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8639925 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8640160 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8640165 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8640170 |  |  | Indiana Department of Transportation | 1988-03-15
|  |  | 8640175 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8640460 |  |  |  | 1987-03-10
|  |  | 8640590 |  |  |  | 1988-04-19
|  |  | 8640600 |  |  | Indiana Department of Transportation | 2000-02-22
|  |  | 8640605 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8640621 |  |  |  | 1985-12-17
|  |  | 8640650 |  |  |  | 1988-06-14
|  |  | 8640651 |  |  |  | 1988-06-14
|  |  | 8640680 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8640685 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8640800 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8640805 |  |  | Indiana Department of Transportation | 1987-12-15
|  |  | 8640850 |  |  | Linton | 1992-03-24
|  |  | 8641030 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8641035 |  |  | Indiana Department of Transportation | 1992-09-29
|  |  | 8641040 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8641045 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8641050 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8641055 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8641160 |  |  |  | 1985-09-24
|  |  | 8641201 |  |  | Indiana Department of Transportation | 1986-01-14
|  |  | 8641705 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8641710 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8641715 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8641750 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8641755 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8641760 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8641765 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8641770 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8641775 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8641785 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8642180 |  |  | Indiana Department of Transportation | 1987-05-19
|  |  | 8642185 |  |  | Indiana Department of Transportation | 1991-12-17
|  |  | 8642250 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8642255 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8642310 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8642315 |  |  | Indiana Department of Transportation | 1988-12-13
|  |  | 8642390 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8642395 |  |  | Indiana Department of Transportation | 1988-06-14
|  |  | 8642491 |  |  |  | 1986-04-15
|  |  | 8642500 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8642525 |  |  | Indiana Department of Transportation | 1995-01-10
|  |  | 8642580 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8642590 |  |  |  | 1986-02-18
|  |  | 8642730 |  |  | Indianapolis | -339679.2083
|  |  | 8642732 |  |  | Indianapolis | 1992-11-10
|  |  | 8642780 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8642790 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | CE
PE
RR
|  |  | 8642800 | Lake | Courtland Title & Escrow, Inc. | Hobart | -339679.2083 | CE
PE
RR
|  |  | 8643190 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8643230 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8643725 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8643790 |  |  | New Albany | -339679.2083
|  |  | 8644110 |  |  | Dearborn County | -339679.2083
|  |  | 8644120 |  |  | Huntington County | -339679.2083
|  |  | 8644170 |  |  | Jackson County | -339679.2083
|  |  | 8644180 |  |  | Jefferson County | -339679.2083
|  |  | 8644190 |  |  | Noble County | -339679.2083
|  |  | 8644220 |  |  | Owen County | -339679.2083
|  |  | 8644340 |  |  | Putnam County | -339679.2083
|  |  | 8644350 |  |  | Shelby County | -339679.2083
|  |  | 8644360 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8644480 |  |  | Sullivan County | -339679.2083
|  |  | 8644801 |  |  | Indiana Department of Transportation | 1990-06-05
|  |  | 8644820 |  |  | Union County | -339679.2083
|  |  | 8644840 |  |  | Vermillion County | -339679.2083
|  |  | 8644870 |  |  | Whitley County | -339679.2083
|  |  | 8644890 |  |  | Madison County | -339679.2083
|  |  | 8644970 |  |  | Dekalb County | -339679.2083
|  |  | 8645320 |  |  | Adams County | -339679.2083
|  |  | 8645370 |  |  | Montgomery County | -339679.2083
|  |  | 8645390 |  |  | Morgan County | -339679.2083
|  |  | 8645540 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8645630 |  |  | Elkhart County | -339679.2083
|  |  | 8645660 |  |  | Indianapolis | -339679.2083
|  |  | 8646330 |  |  |  | -339679.2083
|  |  | 8647450 | Floyd |  | New Albany | -339679.2083 | PE
RR
|  |  | 8647630 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8647920 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8647930 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8649760 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8649920 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8650010 |  |  | Monroe County | -339679.2083
|  |  | 8650140 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8650160 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8650170 |  |  |  | 1986-04-15
|  |  | 8650290 |  | C Blair Enterprises, Inc. | Elkhart | 1991-06-18
|  |  | 8650400 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8650530 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8650540 |  |  | Indiana Department of Transportation | 1991-05-14
|  |  | 8650600 |  |  | Hammond | 2000-02-22
|  |  | 8650620 |  |  |  | 1987-09-09
|  |  | 8650670 |  |  |  | 1986-08-19
|  |  | 8650831 |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-05-19
|  |  | 8651340 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1987-07-07
|  |  | 8651390 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1988-05-17
|  |  | 8651400 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 8652250 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8652460 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8652660 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8652860 |  | Brenner Design Incorporated | Indiana Department of Transportation | 1988-05-17
|  |  | 8652990 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8653010 |  | DCD Consulting LLC | Indianapolis | -339679.2083
|  |  | 8653030 |  | DCD Consulting LLC | Indianapolis | 1994-03-15
|  |  | 8653121 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8653122 |  | Dodd Title Corporation | Indiana Department of Transportation | 1990-10-16
|  |  | 8653290 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8653321 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1990-10-16
|  |  | 8653323 |  | GS-IN P.C. | Indiana Department of Transportation | 1990-10-16
|  |  | 8653324 |  | GS-IN P.C. | Indiana Department of Transportation | 1990-10-16
|  |  | 8653670 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8653770 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8653790 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8653791 |  | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1990-02-06
|  |  | 8653880 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8654000 |  | Cornerstone Design | Indiana Department of Transportation | 1988-05-17
|  |  | 8654010 |  | Consolidated Test Company | Indiana Department of Transportation | 1987-07-07
|  |  | 8654481 |  |  | Indiana Department of Transportation | 1988-04-05
|  |  | 8654482 |  |  | Indiana Department of Transportation | 1988-04-05
|  |  | 8654483 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1988-04-05
|  |  | 8654484 |  |  | Indiana Department of Transportation | 1988-04-05
|  |  | 8654561 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8654562 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8654563 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8654564 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8654565 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8654566 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8654567 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8654568 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8654620 |  |  | Indiana Department of Transportation | 1990-04-17
|  |  | 8654690 |  |  |  | 1985-10-29
|  |  | 8656020 |  |  |  | 1985-08-27
|  |  | 8656110 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 8656270 |  |  | Indiana Department of Transportation | 1988-05-17
|  |  | 8656390 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1989-07-18
|  |  | 8656391 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8656400 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8656410 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | 1990-12-18
|  |  | 8656411 |  |  | Indiana Department of Transportation | 1990-12-18
|  |  | 8656500 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8656820 |  |  |  | 1985-10-29
|  |  | 8656910 |  | Consolidated Test Company | Indiana Department of Transportation | 1988-05-17
|  |  | 8656950 |  |  |  | 1986-05-13
|  |  | 8656990 |  | Absolute Title Services, LLC | Monroe County | 1994-05-17
|  |  | 8657080 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8657280 |  |  |  | 1986-04-15
|  |  | 8657290 |  |  |  | 1990-09-18
|  |  | 8657320 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657330 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657340 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657350 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657360 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657370 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657380 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8657390 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1993-12-14
|  |  | 8657440 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8657480 |  |  | Indiana Department of Transportation | 1999-07-20
|  |  | 8657490 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8657500 |  |  | Indiana Department of Transportation | 1994-06-14
|  |  | 8657510 |  | Eco Logic, LLC | Indiana Department of Transportation | 1997-09-16
|  |  | 8657520 |  |  | Indiana Department of Transportation | 1999-02-23
|  |  | 8657530 |  |  | Indiana Department of Transportation | 2000-12-20
|  |  | 8657550 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8657640 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8657642 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8657650 |  |  | Indiana Department of Transportation | 1992-03-06
|  |  | 8657700 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8657710 |  |  | Indiana Department of Transportation | 1998-06-11
|  |  | 8657720 |  |  | Indiana Department of Transportation | 1991-03-19
|  |  | 8657750 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8657790 |  |  | Indiana Department of Transportation | 2000-05-23
|  |  | 8657810 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1986-09-16
|  |  | 8657820 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8657830 |  | DCD Consulting LLC | Indiana Department of Transportation | 1988-09-20
|  |  | 8657840 |  | DCD Consulting LLC | Indiana Department of Transportation | 1993-02-16
|  |  | 8657850 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-04-17
|  |  | 8657860 |  | DCD Consulting LLC | Indiana Department of Transportation | 1990-04-17
|  |  | 8657880 |  | DCD Consulting LLC | Indiana Department of Transportation | 1987-03-10
|  |  | 8657890 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8657900 |  |  | Indiana Department of Transportation | 1995-09-12
|  |  | 8657920 |  |  | Indiana Department of Transportation | 1993-11-16
|  |  | 8657930 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8657960 | Wayne | Indiana Appraisal Group, Inc. | Indiana Department of Transportation | 1998-03-10 | CE
CN
|  |  | 8658230 |  |  | Indiana Department of Transportation | 1986-11-18
|  |  | 8658760 |  | Consolidated Test Company | Indiana Department of Transportation | 1987-07-07
|  |  | 8659320 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8659340 |  |  | Indiana Department of Transportation | 1989-05-16
|  |  | 8659850 |  |  | Indiana Department of Transportation | 1989-04-18
|  |  | 8660220 |  |  | Indiana Department of Transportation | 1992-06-16
|  |  | 8660390 |  |  | Indiana Department of Transportation | 1994-10-18
|  |  | 8660400 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8660410 |  | Gandhi and Associates, Inc. | Indiana Department of Transportation | 1993-05-27
|  |  | 8660420 |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 8660421 |  |  | Indiana Department of Transportation | 1991-09-24
|  |  | 8660440 |  |  | Indiana Department of Transportation | 1997-11-20
|  |  | 8660450 |  |  | Indiana Department of Transportation | 1995-11-21
|  |  | 8660660 | Clark |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8661140 |  |  | Indiana Department of Transportation | 1989-01-17
|  |  | 8661190 |  |  | Indiana Department of Transportation | 1989-01-17
|  |  | 8661510 |  | Courtland Title & Escrow, Inc. | Indiana Department of Transportation | 1990-06-14
|  |  | 8661520 |  | CGI | Indiana Department of Transportation | 1991-03-19
|  |  | 8661550 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8661560 |  |  | Indiana Department of Transportation | 1989-10-17
|  |  | 8661590 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8661600 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8661620 |  | DCD Consulting LLC | Indiana Department of Transportation | 1991-01-15
|  |  | 8661631 |  | ASA Land Surveying | Indiana Department of Transportation | 1994-04-19
|  |  | 8661690 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8661770 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8662080 |  |  | Indiana Department of Transportation | 1989-09-19
|  |  | 8662570 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1999-03-23
|  |  | 8662810 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1988-05-17
|  |  | 8662922 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8663030 | Parke | Frontline Construction Inspection, Inc. | Indiana Department of Transportation | 2002-01-15 | CE
CN
ROW
UT
|  |  | 8663040 |  |  | Indiana Department of Transportation | 1993-07-20
|  |  | 8663100 | Lake | Cornerstone Design | Indiana Department of Transportation | 2003-04-22 | CE
CN
PE
ROW
UT
|  |  | 8663110 |  | Cornerstone Design | Indiana Department of Transportation | 1995-12-19
|  |  | 8663120 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8663130 |  |  | Indiana Department of Transportation | 1995-03-21
|  |  | 8663170 |  |  | Indiana Department of Transportation | 1996-02-20
|  |  | 8663190 |  |  | Indiana Department of Transportation | 1997-02-11
|  |  | 8663200 |  |  | Indiana Department of Transportation | 1998-05-12
|  |  | 8663230 |  |  | Indiana Department of Transportation | 1994-02-08
|  |  | 8663240 |  |  | Indiana Department of Transportation | 1993-01-12
|  |  | 8663250 |  |  | Indiana Department of Transportation | 1994-03-15
|  |  | 8663280 |  |  | Indiana Department of Transportation | 1995-07-11
|  |  | 8663290 |  |  | Indiana Department of Transportation | 1997-07-15
|  |  | 8663300 |  |  | Indiana Department of Transportation | 1993-10-19
|  |  | 8663320 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8663330 |  |  | Indiana Department of Transportation | 1995-02-14
|  |  | 8663420 |  | DCD Consulting LLC | Indiana Department of Transportation | 1989-11-14
|  |  | 8663430 |  |  | Indiana Department of Transportation | 1992-04-21
|  |  | 8663480 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8663570 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8663600 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8663730 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8663740 |  |  | Indiana Department of Transportation | 1992-11-10
|  |  | 8663960 |  |  | Indiana Department of Transportation | 1993-12-14
|  |  | 8664010 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8664020 |  |  | Indiana Department of Transportation | 1991-11-19
|  |  | 8664280 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8664330 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8664381 |  |  | Indiana Department of Transportation | 1984-07-17
|  |  | 8664420 |  |  | Indiana Department of Transportation | 1991-01-15
|  |  | 8664430 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8664440 |  | DCD Consulting LLC | Indiana Department of Transportation | 1991-08-20
|  |  | 8664490 |  | ASA Land Surveying | Indiana Department of Transportation | 1992-06-16
|  |  | 8664500 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | 2000-04-18 | CE
CN
PE
|  |  | 8664501 | Madison | CE Solutions, Inc. | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8664530 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1993-04-13
|  |  | 8664670 | Starke |  | Indiana Department of Transportation | 2000-10-16 | CE
CN
PE
ROW
|  |  | 8664790 |  |  | Indiana Department of Transportation | 1997-02-11
|  |  | 8664800 | Hendricks |  | Indiana Department of Transportation | 1997-02-11 | CE
CN
|  |  | 8664810 |  |  | Indiana Department of Transportation | 1998-03-10
|  |  | 8664830 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8664840 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8664850 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8664860 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8664870 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8664880 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8664890 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8664900 |  |  | Indiana Department of Transportation | 1991-06-18
|  |  | 8664910 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8664920 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8664930 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8664940 |  |  | Indiana Department of Transportation | 1993-02-16
|  |  | 8664960 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8664970 |  |  | Indiana Department of Transportation | 1994-04-19
|  |  | 8664980 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1990-02-06
|  |  | 8664990 |  |  | Indiana Department of Transportation | 1992-09-01
|  |  | 8665020 |  |  | Indiana Department of Transportation | 1992-12-15
|  |  | 8665030 |  | Mackie Consultants, LLC | Indiana Department of Transportation | 1992-12-15
|  |  | 8665040 |  |  | Indiana Department of Transportation | 1989-10-17
|  |  | 8665050 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8665060 |  | DuSABLE, Inc. | Indiana Department of Transportation | 1986-04-15
|  |  | 8665070 |  |  | Indiana Department of Transportation | 1996-02-20
|  |  | 8665080 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8665090 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8665100 |  |  | Indiana Department of Transportation | 1991-04-23
|  |  | 8665120 |  |  | Indiana Department of Transportation | 1992-03-24
|  |  | 8665130 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8665150 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8665160 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8665170 |  |  | Indiana Department of Transportation | 1990-05-15
|  |  | 8665180 |  | Another Test Company | Indiana Department of Transportation | 1991-07-16
|  |  | 8665190 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8665200 |  |  | Indiana Department of Transportation | 1990-02-06
|  |  | 8665210 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8665220 |  | Eco Logic, LLC | Indiana Department of Transportation | 1989-10-17
|  |  | 8665230 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8665250 |  |  | Indiana Department of Transportation | 1990-09-18
|  |  | 8665260 |  |  | Indiana Department of Transportation | 1989-11-14
|  |  | 8665270 |  |  | Indiana Department of Transportation | 1989-02-14
|  |  | 8665280 |  |  | Indiana Department of Transportation | 1989-07-18
|  |  | 8665290 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8665300 |  |  | Indiana Department of Transportation | 1990-06-14
|  |  | 8665330 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8665340 |  |  | Indiana Department of Transportation | 1991-08-20
|  |  | 8665350 |  | CGI | Indiana Department of Transportation | 1989-08-15
|  |  | 8665360 |  |  | Indiana Department of Transportation | 1990-08-14
|  |  | 8665370 |  |  | Indiana Department of Transportation | 1990-11-20
|  |  | 8665380 |  |  | Indiana Department of Transportation | 1993-03-16
|  |  | 8665390 |  |  | Indiana Department of Transportation | 1993-03-16
|  |  | 8665400 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8665420 |  |  | Indiana Department of Transportation | 1989-10-17
|  |  | 8665440 |  |  | Indiana Department of Transportation | 1989-03-14
|  |  | 8665450 |  |  | Indiana Department of Transportation | 1989-06-13
|  |  | 8665460 |  |  | Indiana Department of Transportation | 1989-12-12
|  |  | 8665870 | Lake | Consolidated Test Company | Indiana Department of Transportation | 2007-09-06 | CE
CN
PE
ROW
UT
|  |  | 8668050 | Bartholomew |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
PE
ROW
UT
|  |  |  | Decatur |  | Indiana Department of Transportation | 2003-05-20 | CE
CN
ROW
UT
|  |  | 8668140 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8668160 |  | AAC Environmental Consulting, LLC | Indiana Department of Transportation | 1995-12-19
|  |  | 8668180 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8668330 | Warren |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8668480 |  | C Blair Enterprises, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8670431 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8670432 |  |  | Indiana Department of Transportation | 1987-11-17
|  |  | 8670501 |  |  | Indiana Department of Transportation | 1987-01-13
|  |  | 8671131 |  |  | Indiana Department of Transportation | 1988-11-15
|  |  | 8671221 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8673260 | Floyd |  | Indiana Department of Transportation | -339679.2083 | RR
|  |  | 8673300 |  | Certified Engineering, Inc. | Indiana Department of Transportation | -339679.2083
|  |  | 8673320 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8673660 | Greene |  | Indiana Department of Transportation | -339679.2083 | CE
PE
RR
|  |  | 8674610 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8675030 |  | Infrastructure Engineers, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8675040 |  | Infrastructure Engineers, Inc. | Indiana Department of Transportation | 1985-12-17
|  |  | 8675050 |  | Bayswater Company, LLC | Indiana Department of Transportation | 1985-12-17
|  |  | 8675070 |  | E.J. Breneman, LP | Indiana Department of Transportation | 1986-01-14
|  |  | 8675080 |  | Holloway Engineering, LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8675090 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8675110 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-01-14
|  |  | 8675120 |  | DCD Consulting LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8675130 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8675140 |  |  | Indiana Department of Transportation | 1985-09-24
|  |  | 8675150 |  | Leitner and Associates, Inc. | Indiana Department of Transportation | 1985-09-24
|  |  | 8675160 |  |  | Indiana Department of Transportation | 1985-08-27
|  |  | 8675170 |  | Hardcore Concrete Sawing Inc. | Indiana Department of Transportation | 1985-08-27
|  |  | 8675180 |  | Dynasty Group, Inc. | Indiana Department of Transportation | 1985-08-27
|  |  | 8675190 |  | Consolidated Test Company |  | 1984-07-17
|  |  | 8675200 |  | Data Transfer Solutions, LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8675201 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8675210 |  | Browning Day Mullins Dierdorf Architects | Indiana Department of Transportation | 1985-11-19
|  |  | 8675211 |  | Atlas Appraisals, LLC | Indiana Department of Transportation | 1985-11-19
|  |  | 8675220 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8675221 |  |  | Indiana Department of Transportation | 1985-11-19
|  |  | 8675230 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8675231 |  | DCD Consulting LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8675240 | St. Joseph |  | Indiana Department of Transportation | -339679.2083 | CE
RR
|  |  | 8675250 | St. Joseph | Flexible H.R. Solutions, LLC | Indiana Department of Transportation | -339679.2083 | PE
RR
|  |  | 8675330 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1986-06-03
|  |  | 8675340 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1986-05-13
|  |  | 8675350 |  | Eagle Ridge Civil Engineering Services, LLC | Indiana Department of Transportation | 1986-05-13
|  |  | 8675360 |  |  | Indiana Department of Transportation | 1986-05-13
|  |  | 8675410 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8675411 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8675420 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8675421 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8675430 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8675431 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8675440 |  |  | Indiana Department of Transportation | 1986-03-18
|  |  | 8675450 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8675451 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8675470 |  |  | Indiana Department of Transportation | 1990-10-16
|  |  | 8675480 |  |  | Indiana Department of Transportation | 1991-07-16
|  |  | 8675490 |  | Chicago Testing Laboratory, Inc. | Indiana Department of Transportation | 1992-03-24
|  |  | 8675530 |  |  |  | 1988-03-15
|  |  | 8675560 |  |  |  | 1985-10-29
|  |  | 8675570 |  |  |  | 1988-04-19
|  |  | 8675580 |  |  |  | 1986-08-19
|  |  | 8675590 |  |  |  | 1986-08-19
|  |  | 8675600 |  |  |  | -339679.2083
|  |  | 8675610 |  |  |  | 1986-05-07
|  |  | 8675670 |  |  | Decatur County | 1993-02-16
|  |  | 8675700 |  |  |  | 1988-08-16
|  |  | 8675740 |  |  |  | 1987-09-09
|  |  | 8675790 |  |  |  | 1985-12-17
|  |  | 8675820 |  |  |  | -339679.2083
|  |  | 8675830 |  |  |  | -339679.2083
|  |  | 8675850 | Vanderburgh | Louis Joyner, Architect | Evansville | -339679.2083 | CE
PE
RR
|  |  | 8675860 |  |  |  | -339679.2083
|  |  | 8676060 |  |  |  | -339679.2083
|  |  | 8676110 |  |  |  | -339679.2083
|  |  | 8676120 |  |  |  | -339679.2083
|  |  | 8676130 |  |  |  | -339679.2083
|  |  | 8676140 |  |  | South Bend | -339679.2083
|  |  | 8676150 |  |  |  | -339679.2083
|  |  | 8676160 |  |  |  | -339679.2083
|  |  | 8676170 |  |  |  | -339679.2083
|  |  | 8676180 | Greene | Abonmarche Consultants of Indiana L.L.C. | Bloomfield | -339679.2083 | CE
PE
RR
|  |  | 8676190 |  |  |  | -339679.2083
|  |  | 8676200 |  |  | Elwood | -339679.2083
|  |  | 8676210 |  |  | Elwood | -339679.2083
|  |  | 8676240 |  |  |  | -339679.2083
|  |  | 8676250 |  |  |  | -339679.2083
|  |  | 8676280 |  |  |  | -339679.2083
|  |  | 8676290 |  |  |  | -339679.2083
|  |  | 8676300 |  |  |  | 1987-03-10
|  |  | 8676310 |  |  |  | -339679.2083
|  |  | 8676320 |  |  |  | -339679.2083
|  |  | 8676330 |  |  |  | -339679.2083
|  |  | 8676340 |  |  |  | -339679.2083
|  |  | 8676350 |  |  |  | -339679.2083
|  |  | 8676360 |  |  |  | -339679.2083
|  |  | 8676370 |  |  |  | -339679.2083
|  |  | 8676380 |  |  | Terre Haute | -339679.2083
|  |  | 8676390 |  |  |  | -339679.2083
|  |  | 8676410 |  |  |  | -339679.2083
|  |  | 8676420 |  |  |  | -339679.2083
|  |  | 8676430 | Daviess | AMEC E&I, Inc. | Washington | -339679.2083 | PE
RR
|  |  | 8676440 |  |  |  | -339679.2083
|  |  | 8676450 |  |  |  | -339679.2083
|  |  | 8676470 |  |  |  | -339679.2083
|  |  | 8676480 |  |  |  | -339679.2083
|  |  | 8676490 | Knox | Louis Joyner, Architect | Vincennes | -339679.2083 | CE
PE
RR
|  |  | 8676500 |  |  |  | 1990-07-17
|  |  | 8676510 |  |  | Bartholomew County | 1993-10-19
|  |  | 8676520 |  |  | Bartholomew County | -339679.2083
|  |  | 8676530 |  |  |  | 1989-10-17
|  |  | 8676540 |  |  |  | 1987-10-20
|  |  | 8676560 | Brown |  | Brown County | 1996-12-17 | CE
CN
|  |  | 8676570 |  |  | Carroll County | 1992-10-06
|  |  | 8676600 |  |  | Dearborn County | 1993-09-14
|  |  | 8676610 |  |  | Floyd County | 2002-01-15
|  |  | 8676620 | Floyd |  | Floyd County | 2013-03-06 | CE
CN
PE
|  |  | 8676630 |  |  | Floyd County | -339679.2083
|  |  | 8676640 |  |  | Gibson County | -339679.2083
|  |  | 8676670 |  |  | Hancock County | 1992-03-06
|  |  | 8676680 |  |  |  | 1988-07-12
|  |  | 8676710 |  | DCD Consulting LLC | Indianapolis | 1994-04-19
|  |  | 8676720 |  |  | Indianapolis | 1992-07-28
|  |  | 8676740 |  |  | Indianapolis | 1992-09-01
|  |  | 8676760 |  |  | Jefferson County | 1996-09-17
|  |  | 8676810 |  |  | Monroe County | 1995-05-16
|  |  | 8676830 |  |  |  | 1988-11-15
|  |  | 8676880 |  |  | Randolph County | 1993-08-17
|  |  | 8676890 |  |  |  | 1989-01-17
|  |  | 8676910 |  |  |  | 1989-06-06
|  |  | 8676930 | Sullivan |  | Indiana Department of Transportation | 1987-04-07 | CE
CN
|  |  | 8676960 |  |  |  | 1985-12-17
|  |  | 8676970 |  |  |  | 1986-12-16
|  |  | 8676990 |  |  | Warrick County | 1994-01-11
|  |  | 8677000 |  |  | White County | 1992-04-21
|  |  | 8677020 |  |  | White County | 1992-04-21
|  |  | 8677030 |  |  | White County | 1992-04-21
|  |  | 8677040 |  |  | White County | 1992-04-21
|  |  | 8677070 |  |  | White County | 1992-04-21
|  |  | 8677080 |  |  |  | -339679.2083
|  |  | 8677100 |  |  |  | 1987-12-15
|  |  | 8677110 |  |  |  | -339679.2083
|  |  | 8677120 |  |  |  | 1986-02-18
|  |  | 8677140 |  | GS-IN P.C. | Muncie | 1995-03-21
|  |  | 8677160 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8677161 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8677170 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8677171 |  |  | Indiana Department of Transportation | 1986-02-18
|  |  | 8677200 |  |  |  | 1988-05-17
|  |  | 8677230 |  |  |  | 1986-11-18
|  |  | 8677250 |  |  |  | 1986-09-16
|  |  | 8677260 |  |  |  | -339679.2083
|  |  | 8677270 |  |  |  | -339679.2083
|  |  | 8677290 |  |  | Indiana Department of Transportation | 1996-04-23
|  |  | 8677300 |  |  | Indiana Department of Transportation | 1987-08-04
|  |  | 8677320 |  | CTL Engineering of Indiana, Inc. | Indiana Department of Transportation | 1986-04-15
|  |  | 8677330 |  | CoCal Consulting, LLC | Indiana Department of Transportation | 1986-04-15
|  |  | 8677340 |  | EcoTec, Inc. | Indiana Department of Transportation | 1986-04-15
|  |  | 8677350 |  | III FFC | Indiana Department of Transportation | 1986-04-15
|  |  | 8677360 |  |  | Indiana Department of Transportation | 1986-04-15
|  |  | 8677390 |  |  | Indiana Department of Transportation | 1994-05-17
|  |  | 8677400 |  |  | Indiana Department of Transportation | -339679.2083
|  |  | 8677410 |  |  | Indiana Department of Transportation | 1991-05-23
|  |  | 8677420 | Howard |  | Kokomo | 2004-06-15 | CE
CN
PE
ROW
RR
UT
|  |  | 8677430 |  | Douglass Environmental Services, Inc. | Cedar Lake | -339679.2083
|  |  | 8677521 |  |  | Indiana Department of Transportation | 1985-12-17
|  |  | 8677530 |  |  | Posey County | -339679.2083
|  |  | 8677540 |  |  | Gibson County | -339679.2083
|  |  | 8677550 |  |  | Pike County | -339679.2083
|  |  | 8677560 |  |  | Clark County | -339679.2083
|  |  | 8677580 |  |  | Jasper County | -339679.2083
|  |  | 8677590 |  |  | Jay County | -339679.2083
|  |  | 8677600 |  |  | Porter County | -339679.2083
|  |  | 8677610 |  |  | Ripley County | -339679.2083
|  |  | 8677650 |  |  | Brown County | -339679.2083
|  |  | 8677660 |  |  | Johnson County | -339679.2083
|  |  | 8677670 |  |  | Newton County | -339679.2083
|  |  | 8677680 |  |  | Posey County | -339679.2083
|  |  | 8677690 |  |  |  | 1987-10-20
|  |  | 8677720 |  |  | Indiana Department of Transportation | 1986-10-14
|  |  | 8677730 |  |  | Indiana Department of Transportation | 1987-10-20
|  |  | 8677735 |  | Accidental Discoveries, LLC | Indiana Department of Transportation | 1988-07-12
|  |  | 8677740 |  | Edwards and Kelcey | Indiana Department of Transportation | 1988-01-12
|  |  | 8677750 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 8677760 |  | J. Williams Appraisal Group, LLC | Indiana Department of Transportation | 1987-11-17
|  |  | 8677780 |  | D A Brown Engineering Consultants, Inc. | Indiana Department of Transportation | 1987-01-13