## Sheet1
LPA Bridge Inspection Contract Timeline
2027-04-01
ACTIVITY | START | END | NOTES
ERC Given DES number | 2025-11-01 | 2025-11-02 | ERC to request and receive DES number for new contract from INDOT (1 DAYS) | LPA COUNTY
Request DBE goal (if required) | 2025-11-02 | 2025-11-16 | ERC to request and receive DBE goal email for contract from INDOTDBEGoalRequest@indot.in.gov (DES number required) (14 DAYS) | DES NUMBER
Submit RFP for posting | 2025-11-16 | 2025-11-30 | ERC to submit RFP for approval and subsequent posting to INDOT, while requesting a BIAS check run confirmation (14 DAYS) | CYCLE YEARS (CALENDAR)
RFP requested to be advertised | 2025-11-30 | 2025-12-07 | INDOT internal activity (7 DAYS)
RFP advertised | 2025-12-07 | 2026-01-06 | INDOT internal activity (30 DAYS)
ERC team to score LOI's | 2026-01-06 | 2026-02-05 | ERC internal activity (30 DAYS) | **IF COUNTY IS IN A MPO: IT IS THE COUNTY ERC RESPONSIBILITY TO SUBMIT MPO TIP REQUEST; ONCE REQUEST HAS BEEN SUBMITTED THEN FORWARD A COPY OF SUBMITTAL TO LPA BRIDGE INSPECTION PROGRAM MANAGER, BIPM WILL PROVIDE SUBMITTAL TO CONTRACT PROGRAM DIRECTOR
Submit LOI scoring results | 2026-02-05 | 2026-02-08 | ERC to submit scoring results and contract selection to INDOT for approval (3 DAYS)
Approval to negotiate LPA/Consultant Contract | 2026-02-08 | 2026-02-15 | INDOT notice to ERC of approval to negotiate LPA/Consultant Contract (7 DAYS)
ERC to negotiate LPA/Consultant Contract | 2026-02-15 | 2026-05-16 | ERC internal activity (90 DAYS) | NOTES: 1. FOR JUNE CONTRACTS SUBTRACT ONE MONTH FROM DATES SHOWN TO ACCOUNT FOR POTENTIAL FISCAL YEAR END DELAYS 2.FOR DATES FALLING ON WEEKENDS OR HOLIDAYS, MOVE TARGET DATE BACK TO THE NEXT FULL WORKING DAY
Submit LPA/Consultant Contract for review and approval | 2026-05-16 | 2026-05-18 | ERC to submit LPA/Consultant Contract to INDOT for approval (2 DAYS)
**Approval to execute LPA/Consultant Contract & TIP/STIP submittal/approval | 2026-05-18 | 2026-09-15 | INDOT review of LPA/Consultant Contract and approval to execute notification to ERC via email & INDOT to prepare and request STIP, **ERC to request TIP (If MPO)-INDOT internal activity (120 DAYS)
LPA/Consultant Contract executed and TIP APPROVAL | 2026-09-15 | 2026-10-01 | LPA/Consultant Contract executed and TIP APPROVAL (if MPO) returned to INDOT (15 DAYS)
INDOT/LPA contract prepared | 2026-10-01 | 2026-10-05 | INDOT/LPA contract prepared by INDOT (Per our goals 4 DAYS, should have the fully correct and executed consultant contract 6 months prior to compliance month) | AMENDMENT CONTRACTS: THE TIMELINE ACTIVITIES FOR A SUPPLEMENT TO THE CONTRACT REQUIRING ADDITIONAL FUNDS WOULD INCLUDE LINES 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, AND 22. ITEM 14 CAN BE GREATLY REDUCED BY CLEAR COMMUNICATION BETWEEN THE ERC AND INDOT LPA BRIDGE INSPECTION MANAGER.
INDOT/LPA contract routed via docusign | 2026-10-05 | 2026-12-04 | INDOT/LPA contract routed via docusign and signed by County designee (60 DAYS)
INDOT/LPA Contract executed | 2026-12-04 | 2027-02-01 | INDOT/LPA Contract executed by INDOT-INDOT internal activity and additional Agencies (60 DAYS)
Submit FMIS request (1 month prior to NTP date, in otherwords, 2 months prior to Compliance Month ) | 2027-02-01 | 2027-02-01 | ERC to prepare and submit FMIS request to INDOT
Work Order Submitted | 2027-02-01 | 2027-02-03 | INDOT CPD has a 2 day goal for PO WO submittal
Purchase Order approval | 2027-02-03 | 2027-02-27 | Purchase Order approval-INDOT internal activity (24 DAYS)
Purchase Order and draft NTP sent from the Contracts Program Director to the Bridge Inspection Project Manager | 2027-02-27 | 2027-03-01 | The CPD has 2 days to send the PO/Draft NTP to the BI PM
NTP issued by INDOT | 2027-03-01 | 2027-03-01 | NTP issued by INDOT to ERC. THIS SHOULD BE THE FIRST DAY of the Month prior to the COMPLIANCE MONTH
Formulas:
START = [END, row above]
END = [START]+1