## Full TIP
2018-2021 Transportation Improvement Program for Lake, LaPorte, and Porter Counties, Indiana
|  |  |  | Northwestern Indiana Regional Planning Commission | [10 empty] | List 04 | NE | Non Exempt
|  |  |  | All Project List |  | 2018-07-01 |  | Current thru Amendment #012, (adopted April, 2018) | [7 empty] | RS | Regionally Significant
[8 empty] | Because of the conversion to RTIP, which is in process now, July amendments and admisistrative modifications are not shown here. | [7 empty] | A# | Amendment #
[16 empty] | AM-XX/XX | Administrative Modification-Month/Year
Row ID | Des # | Sponsor | Route | Work Category | Work Type | Location | County | Des Length | Letting Date | Federal Fund Type | Year | Phase | Total Funds | Federal Funds | Non-Federal Funds | NE/ RS/ A#/ AM | Comments | FY 18 | [5 empty] | FY 19 |  |  |  | FY 20 |  |  |  | FY 21 |  |  |  | FY 22 |  |  |  | FY 23+
[18 empty] | STBG State | State | NHPP Non Interstate | NHPP Interstate | Section 130 | RTP
INDIANA DEPARTMENT of TRANSPORTATION (INDOT) Sponsored Projects
1 | 0500028 | INDOT | SR 2 | District Bridge Project (Replacement) | Br Repl, Cont. Rc Slab | Bridge over M J Brown Ditch, 2.70 miles E of I-65 | Lake | 0 | 03/07/2018 | STBG State | 2018 | CN | 1342000 | 1073600 | 268400
2 | 0500480 | INDOT | US 20 | Added Travel Lanes Project | Added Travel Lanes, Construct Turn Lanes | US 421 to US 35/SR 212 in Michigan City | LaPorte | 3.873 | 10/12/2017 | STBG State | 2018 | CN | 720000 | 576000 | 144000 | RS
3 | 0500480 | INDOT | US 20 | Added Travel Lanes Project | Added Travel Lanes, Construct Turn Lanes | US 421 to US 35/SR 212 in Michigan City | LaPorte | 3.873 | 10/12/2017 | STBG State | 2018 | PE | 820000 | 656000 | 164000 | RS
4 | 0500480 | INDOT | US 20 | Added Travel Lanes Project | Added Travel Lanes, Construct Turn Lanes | US 421 to US 35/SR 212 in Michigan City | LaPorte | 3.873 | 10/12/2017 | STBG State | 2018 | PE | 1182000 | 945600 | 236400 | RS
5 | 0500480 | INDOT | US 20 | Added Travel Lanes Project | Added Travel Lanes, Construct Turn Lanes | US 421 to US 35/SR 212 in Michigan City | LaPorte | 3.873 | 10/12/2017 | STBG State | 2018 | CN | 8480000 | 6784000 | 1696000 | RS
6 | 0500480 | INDOT | US 20 | Added Travel Lanes Project | Added Travel Lanes, Construct Turn Lanes | US 421 to US 35/SR 212 in Michigan City | LaPorte | 3.873 | 10/12/2017 | STBG State | Total |  | 11202000 | 8961600 | 2240400
7 | 0902261 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | over Trail Creek, 0.21 miles East of US 35 | LaPorte | 0 | 03/07/2018 | STBG State | 2018 | PE | 240000 | 192000 | 48000
8 | 0902261 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | over Trail Creek, 0.21 miles East of US 35 | LaPorte | 0 | 03/07/2018 | STBG State | 2018 | CN | 2654647 | 2123717.6 | 530929.4
9 | 0902261 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | over Trail Creek, 0.21 miles East of US 35 | LaPorte | 0 | 03/07/2018 | STBG State | Total |  | 2894647 | 2315717.6 | 578929.4
10 | 1006456 | INDOT | PR 1078 | New Road Construction Project | New Road Construction | Illiana Expressway | Lake | 0 | 05/31/2016 | State | 2018 | PE | 0 | 0 | 0 | RS/NE
11 | 1006456 | INDOT | PR 1078 | New Road Construction Project | New Road Construction | Illiana Expressway | Lake | 0 | 05/31/2016 | State | 2018 | CN | 0 | 0 | 0 | RS/NE
12 | 1006456 | INDOT | PR 1078 | New Road Construction Project | New Road Construction | Illiana Expressway | Lake | 0 | 05/31/2016 | State | Total |  | 0 | 0 | 0
13 | 1006608 | INDOT | SR 130 | District Intersection Improvement Project | Other Intersection Improvement | SR 130 & CR 600N, 0.65 miles E of Lake/Porter Co Line | Porter | 0 | 07/01/2019 | STBG State | 2018 | PE | 50000 | 40000 | 10000
14 | 1006608 | INDOT | SR 130 | District Intersection Improvement Project | Other Intersection Improvement | SR 130 & CR 600N, 0.65 miles E of Lake/Porter Co Line | Porter | 0 | 07/01/2019 | STBG State | 2018 | UT1 | 50000 | 40000 | 10000
15 | 1006608 | INDOT | SR 130 | District Intersection Improvement Project | Other Intersection Improvement | SR 130 & CR 600N, 0.65 miles E of Lake/Porter Co Line | Porter | 0 | 07/01/2019 | STBG State | 2020 | CN | 836186 | 668948.8 | 167237.2
16 | 1006608 | INDOT | SR 130 | District Intersection Improvement Project | Other Intersection Improvement | SR 130 & CR 600N, 0.65 miles E of Lake/Porter Co Line | Porter | 0 | 07/01/2019 | STBG State | 2020 | RR2 | 350000 | 280000 | 70000
17 | 1006608 | INDOT | SR 130 | District Intersection Improvement Project | Other Intersection Improvement | SR 130 & CR 600N, 0.65 miles E of Lake/Porter Co Line | Porter | 0 | 07/01/2019 | STBG State | Total |  | 1286186 | 1028948.8 | 257237.2
18 | 1006612 | INDOT | US 30 | District Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | & Randolph St | Lake | 0 | 03/07/2018 | NHPP Non Interstate | 2018 | CN | 537000 | 429600 | 107400
19 | 1006619 | INDOT | SR 149 | District Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | & CR 1050N | Porter | 0 | 03/07/2018 | STBG State | 2018 | CN | 643000 | 514400 | 128600
20 | 1006622 | 73435952 | US 20 | District Intersection Improvement Project | Other Intersection Improvement | & Waverly Rd | Porter | 0 | 03/07/2018 | STBG State | 2018 | CN | 799000 | 639200 | 159800
21 | 1006624 | INDOT | US 6 | District Intersection Improvement Project | Other Intersection Improvement | & Meridian St | Porter | 0 | 03/07/2018 | STBG State | 2018 | PE | 45000 | 36000 | 9000
22 | 1006624 | INDOT | US 6 | District Intersection Improvement Project | Other Intersection Improvement | & Meridian St | Porter | 0 | 03/07/2018 | STBG State | 2018 | CN | 582564 | 466051.2 | 116512.8
23 | 1006624 | INDOT | US 6 | District Intersection Improvement Project | Other Intersection Improvement | & Meridian St | Porter | 0 | 03/07/2018 | STBG State | Total |  | 627564 | 502051.2 | 125512.8
24 | 1006634 | INDOT | SR 51 | District Pavement Project (Non-I) | HMA Overlay, Functional | from US 30 to US 20 | Lake | 9.554 | 07/12/2017 | STBG State | 2018 | PE | 15000 | 12000 | 3000
25 | 1006634 | INDOT | SR 51 | District Pavement Project (Non-I) | HMA Overlay, Functional | from US 30 to US 20 | Lake | 9.554 | 07/12/2017 | STBG State | 2018 | CN | 4994973 | 3995978.4 | 998994.6
26 | 1006634 | INDOT | SR 51 | District Pavement Project (Non-I) | HMA Overlay, Functional | from US 30 to US 20 | Lake | 9.554 | 07/12/2017 | STBG State | Total |  | 5009973 | 4007978.4 | 1001994.6
27 | 1006635 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | from SR 2 N jct to 2.57mi S of US 231 (135th Ave) | Lake | 7.372 | 03/07/2018 | NHPP Non Interstate | 2018 | CN | 3100000 | 2480000 | 620000
28 | 1006716 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | NB Bridge over Conrail RR, Central Ave and Ditch, 0.67 miles N of I80/94 | Lake | 0 | 01/18/2018 | NHPP Interstate | 2018 | CN | 4749000 | 4274100 | 474900
29 | 1006746 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.86 mi E of US 421 | LaPorte | 0 | 04/04/2018 | NHPP Interstate | 2018 | CN | 489000 | 440100 | 48900
30 | 1006747 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 1.31 mi E of US 421 | LaPorte | 0 | 04/04/2018 | NHPP Interstate | 2018 | CN | 273000 | 245700 | 27300
31 | 1006756 | INDOT | SR 51 | District Bridge Project (Replacement) | Bridge Replacement, Concrete | SR 51, SBL at Burns Ditch (Deep River), 2.95 miles N of US 6 | Lake | 0 | 07/12/2017 | STBG State | 2018 | CN | 2314937 | 1851949.6 | 462987.4
32 | 1006756 | INDOT | SR 51 | District Bridge Project (Replacement) | Bridge Replacement, Concrete | SR 51, SBL at Burns Ditch (Deep River), 2.95 miles N of US 6 | Lake | 0 | 07/12/2017 | STBG State | 2018 | PE | 335000 | 268000 | 67000
33 | 1006756 | INDOT | SR 51 | District Bridge Project (Replacement) | Bridge Replacement, Concrete | SR 51, SBL at Burns Ditch (Deep River), 2.95 miles N of US 6 | Lake | 0 | 07/12/2017 | STBG State | Total |  | 2649937 | 2119949.6 | 529987.4
34 | 1006772 | INDOT | US 231 | District Pavement Project (Non-I) | HMA Overlay, Functional | from W Jct of SR 55 to US 41 | Lake | 5.556 | 03/07/2018 | NHPP Non Interstate | 2018 | CN | 1700000 | 1360000 | 340000
35 | 1172245 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Conrail, IHB RR, and 4 other streets, 1.95 miles S of I-90 | Lake | 0 | 12/13/2017 | STBG State | 2018 | CN | 1259000 | 1007200 | 251800
36 | 1172430 | INDOT | I 65 | Added Travel Lanes Project | Added Travel Lanes | I-65 ATL from US 231 to US 30 | Lake | 5.583 | 05/26/2016 | NHPP Interstate | 2019 | PE | 3750000 | 3375000 | 375000 | RS/NE
37 | 1173422 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | SBBridge over Conrail RR, Central Ave and Ditch, 0.67 miles N of I80/94 | Lake | 0 | 01/18/2018 | NHPP Interstate | 2018 | CN | 4749000 | 4274100 | 474900
38 | 1296339 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak and Chandler Rd, 0.88 miles E of SR 520 | Porter | 0 | 10/07/2020 | STBG State | 2021 | PE | 50000 | 40000 | 10000
39 | 1296339 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak and Chandler Rd, 0.88 miles E of SR 520 | Porter | 0 | 10/07/2020 | STBG State | 2021 | CN | 572488 | 457990.4 | 114497.6
40 | 1296339 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak and Chandler Rd, 0.88 miles E of SR 520 | Porter | 0 | 10/07/2020 | STBG State | Total |  | 622488 | 497990.4 | 124497.6
41 | 1296364 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak, 0.33 miles N of I-94 | Porter | 0 | 02/07/2018 | NHPP Non Interstate | 2018 | PE | 27740 | 22192 | 5548
42 | 1296364 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak, 0.33 miles N of I-94 | Porter | 0 | 02/07/2018 | NHPP Non Interstate | 2018 | RR1 | 100000 | 80000 | 20000
43 | 1296364 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak, 0.33 miles N of I-94 | Porter | 0 | 02/07/2018 | NHPP Non Interstate | 2020 | CN | 349312 | 279449.6 | 69862.4
44 | 1296364 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak, 0.33 miles N of I-94 | Porter | 0 | 02/07/2018 | NHPP Non Interstate | 2020 | CE | 130000 | 104000 | 26000
45 | 1296364 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Amtrak, 0.33 miles N of I-94 | Porter | 0 | 02/07/2018 | NHPP Non Interstate | Total |  | 607052 | 485641.6 | 121410.4
46 | 1296943 | INDOT | US 20 | District Intersection Improvement Project | Interchange Modification | US 20 at US 35/SR 212 | LaPorte | 0 | 02/07/2018 | STBG State | 2018 | CN | 647000 | 517600 | 129400
47 | 1296981 | INDOT | SR 51 | District Bridge Project (Replacement) | Bridge Replacement, Concrete | NB Bridge over Burns Ditch, 0.55 miles S of US 20 | Lake | 0 | 07/12/2017 | STBG State | 2018 | CN | 2681955 | 2145564 | 536391
48 | 1296986 | INDOT | I 65 | District Bridge Project (Replacement) | Bridge Replacement, Steel | 101st Avenue over I-65, 2.50 miles S of US 30 | Lake | 0 | 01/18/2018 | NHPP Interstate | 2018 | CN | 1472000 | 1324800 | 147200
49 | 1296990 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Amtrak and Chandler Rd, 0.88 miles E. of SR 520 | Porter | 0 | 10/07/2020 | STBG State | 2021 | CN | 3756771 | 3005416.8 | 751354.2
50 | 1296990 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Amtrak and Chandler Rd, 0.88 miles E. of SR 520 | Porter | 0 | 10/07/2020 | STBG State | 2021 | PE | 165000 | 132000 | 33000
51 | 1296990 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Amtrak and Chandler Rd, 0.88 miles E. of SR 520 | Porter | 0 | 10/07/2020 | STBG State | 2021 | PE | 250000 | 200000 | 50000
52 | 1296990 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Amtrak and Chandler Rd, 0.88 miles E. of SR 520 | Porter | 0 | 10/07/2020 | STBG State | Total |  | 4171771 | 3337416.8 | 834354.2
53 | 1298068 | INDOT | SR 2 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 1.4 mi E of SR 4 (Burson) to US 20 | LaPorte | 6.8 | 02/07/2018 | STBG State | 2018 | CN | 8741000 | 6992800 | 1748200
54 | 1298125 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 212 to SR 39 | LaPorte | 4.801 | 08/09/2017 | STBG State | 2018 | CN | 5333000 | 4266400 | 1066600
55 | 1298128 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 39 to SR 2 | LaPorte | 7.743 | 02/07/2018 | STBG State | 2018 | CN | 7642000 | 6113600 | 1528400
56 | 1298302 | INDOT | SR 2 | District Intersection Improvement Project | Intersection Improvement, Roundabout | SR 2 at CR100S, 4.32 mi. W of US 30 | Porter | 0 | 03/07/2018 | STBG State | 2018 | CN | 1325000 | 1060000 | 265000
57 | 1298309 | INDOT | US 41 | Added Travel Lanes Project | Added Travel Lanes, Construct Turn Lanes | From 1.48 mi. S of US 30 (82nd Lane) to 0.83 mi. S of US 30 (77th Ave.) | Lake | 0.658 | 03/07/2018 | NHPP Non Interstate | 2018 | CN | 2700000 | 2160000 | 540000
58 | 1298312 | INDOT | SR 2 | District Intersection Improvement Project | Other Intersection Improvement | SR 2 at CR 500W, 6.79 mi. W of US 30 | Porter | 0 | 03/07/2018 | STBG State | 2018 | CN | 530000 | 424000 | 106000
59 | 1298313 | INDOT | US 20 | District Pavement Project (Non-I) | Intersect. Improv. W/ Added Turn Lanes | US 20 at CR 400W, 1.44 mi. E of US 35 | LaPorte | 0 | 08/09/2017 | STBG State | 2018 | CN | 1235770 | 988616 | 247154
60 | 1298316 | INDOT | US 6 | District Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | US 6 at Calumet Rd., 0.48 mi. E of SR 49 | Porter | 0 | 03/07/2018 | STBG State | 2018 | CN | 646859 | 517487.2 | 129371.8
61 | 1298397 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | Bridge over EJ&E RR, Conrail RR, and Carey St., 1.33 mi W of SR 912 | Lake | 0 | 12/13/2017 | STBG State | 2018 | CN | 3086000 | 2468800 | 617200
62 | 1298398 | INDOT | US 12 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Pedestrian walkway over US-12, 0.83 mi W of SR 912 | Lake | 0 | 07/10/2019 | STBG State | 2018 | RW | 50000 | 40000 | 10000
63 | 1298398 | INDOT | US 12 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Pedestrian walkway over US-12, 0.83 mi W of SR 912 | Lake | 0 | 07/10/2019 | STBG State | 2018 | UT1 | 102600 | 82080 | 20520
64 | 1298398 | INDOT | US 12 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Pedestrian walkway over US-12, 0.83 mi W of SR 912 | Lake | 0 | 07/10/2019 | STBG State | 2020 | CN | 1139868 | 911894.4 | 227973.6
65 | 1298398 | INDOT | US 12 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Pedestrian walkway over US-12, 0.83 mi W of SR 912 | Lake | 0 | 07/10/2019 | STBG State | Total |  | 1292468 | 1033974.4 | 258493.6
66 | 1298402 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over CSX RR, 1.3 mi. W of SR 249 | Porter | 0 | 01/18/2018 | STBG State | 2018 | CN | 3257000 | 2605600 | 651400
67 | 1298444 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Conrail RR and 236th Avenue, NBL, 4.54 mi. S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | PE | 250000 | 200000 | 50000
68 | 1298444 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Conrail RR and 236th Avenue, NBL, 4.54 mi. S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | CN | 1755000 | 1404000 | 351000
69 | 1298444 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Conrail RR and 236th Avenue, NBL, 4.54 mi. S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | Total |  | 2005000 | 1604000 | 401000
70 | 1298448 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Conrail RR and 236th Avenue, SBL, 4.54 mi. S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | CN | 1350000 | 1080000 | 270000
71 | 1298541 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | Bridge over Guthrie St., 0.32 mi. W of US 12 | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | CN | 1887000 | 1509600 | 377400
72 | 1298543 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Replace Superstructure | Bridge over US 12/Industrial Highway | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | CN | 1728000 | 1382400 | 345600
73 | 1298544 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Replace Superstructure | SR-912 ramp SSE over SR-912 and US-12 WB ramp | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | CN | 2884000 | 2307200 | 576800
74 | 1298548 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Georgia St bridge over I-80 | Lake | 0 | 04/04/2018 | NHPP Interstate | 2018 | CN | 1264000 | 1137600 | 126400
75 | 1298548 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Georgia St bridge over I-80 | Lake | 0 | 04/04/2018 | NHPP Interstate | 2018 | PE | 158000 | 142200 | 15800
76 | 1298548 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Georgia St bridge over I-80 | Lake | 0 | 04/04/2018 | NHPP Interstate | Total |  | 1422000 | 1279800 | 142200
77 | 1298562 | INDOT | US 35 | District Small Structure Project | Small Structure Maint and Repair | 0.61 mi. S of US-20 (35-46-204.30) | LaPorte | 0 | 02/07/2018 | STBG State | 2018 | CN | 266335 | 213068 | 53267
78 | 1298566 | INDOT | SR 55 | District Small Structure Project | Small Structure Maint and Repair | 1.03 mi. S of US-231 | Lake | 0 | 02/07/2018 | STBG State | 2018 | CN | 510000 | 408000 | 102000
79 | 1298567 | INDOT | I 65 | District Small Structure Project | Small Structure Pipe Lining | Small structure over Little Calumet River, 0.17 mi N of I-80/94 | Lake | 0 | 01/18/2018 | NHPP Interstate | 2018 | CN | 570000 | 513000 | 57000
80 | 1298621 | INDOT | US 30 | District Small Structure Project | Small Structure Maint and Repair | 0.02 mi. E of SR-53 | Lake | 0 | 02/07/2018 | NHPP Non Interstate | 2018 | CN | 660000 | 528000 | 132000
81 | 1383250 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Functional | 1.56 mi E. of US 41 (Schrage Ave) to US 12 & US 20 Jct (Columbus Dr) | Lake | 3.246 | 04/04/2018 | NHPP Non Interstate | 2018 | PE | 10000 | 8000 | 2000
82 | 1383250 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Functional | 1.56 mi E. of US 41 (Schrage Ave) to US 12 & US 20 Jct (Columbus Dr) | Lake | 3.246 | 04/04/2018 | NHPP Non Interstate | 2018 | CN | 2120000 | 1696000 | 424000
83 | 1383250 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Functional | 1.56 mi E. of US 41 (Schrage Ave) to US 12 & US 20 Jct (Columbus Dr) | Lake | 3.246 | 04/04/2018 | NHPP Non Interstate | 2018 | PE | 180000 | 144000 | 36000
84 | 1383250 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Functional | 1.56 mi E. of US 41 (Schrage Ave) to US 12 & US 20 Jct (Columbus Dr) | Lake | 3.246 | 04/04/2018 | NHPP Non Interstate | Total |  | 2310000 | 1848000 | 462000
85 | 1383583 | INDOT | SR 49 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 8 to US 30 | Porter | 8.751 | 12/12/2018 | STBG State | 2019 | PE | 450000 | 360000 | 90000
86 | 1383583 | INDOT | SR 49 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 8 to US 30 | Porter | 8.751 | 12/12/2018 | STBG State | 2019 | CN | 5537477 | 4429981.6 | 1107495.4
87 | 1383583 | INDOT | SR 49 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 8 to US 30 | Porter | 8.751 | 12/12/2018 | STBG State | Total |  | 5987477 | 4789981.6 | 1197495.4
88 | 1383614 | INDOT | US 20 | New Interchange Project | New Interchange Construction | at SR 2 | LaPorte | 0 | 12/12/2018 | STBG State | 2019 | CN | 11748000 | 9398400 | 2349600
89 | 1383615 | INDOT | SR 55 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 55 and 73rd Ave., 1.0 mi N of US 30 | Lake | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | RW | 500000 | 400000 | 100000
90 | 1383615 | INDOT | SR 55 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 55 and 73rd Ave., 1.0 mi N of US 30 | Lake | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | UT2 | 120000 | 96000 | 24000
91 | 1383615 | INDOT | SR 55 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 55 and 73rd Ave., 1.0 mi N of US 30 | Lake | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CN | 1996000 | 1596800 | 399200
92 | 1383615 | INDOT | SR 55 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 55 and 73rd Ave., 1.0 mi N of US 30 | Lake | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CE | 170000 | 136000 | 34000
93 | 1383615 | INDOT | SR 55 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 55 and 73rd Ave., 1.0 mi N of US 30 | Lake | 0 | 01/15/2020 | NHPP Non Interstate | Total |  | 2786000 | 2228800 | 557200
94 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | 2018 | PE | 5000 | 4000 | 1000
95 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | 2018 | UT1 | 5000 | 4000 | 1000
96 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | CN | 1269000 | 1015200 | 253800
97 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | RW | 80000 | 64000 | 16000
98 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | UT2 | 35000 | 28000 | 7000
99 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CE | 54000 | 43200 | 10800
100 | 1383631 | INDOT | US 6 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of US 6 and SR 2 | LaPorte | 0 | 01/15/2020 | NHPP Non Interstate | Total |  | 1448000 | 1158400 | 289600
101 | 1383633 | INDOT | SR 2 | Intersection Improvement Project | Other Intersection Improvement | at Hayes-Leonard | Porter | 0 | 01/16/2019 | NHPP Non Interstate | 2019 | CN | 1234000 | 987200 | 246800
102 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2018 | PE | 10000 | 8000 | 2000
103 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2018 | UT1 | 10000 | 8000 | 2000
104 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | RW | 240000 | 192000 | 48000
105 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2019 | UT2 | 90000 | 72000 | 18000
106 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | PE | 42000 | 33600 | 8400
107 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CN | 1057000 | 845600 | 211400
108 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | Total |  | 1449000 | 1159200 | 289800
109 | 1383635 | INDOT | SR 2 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 2 at Horse Prairie Ave, 0.25 mi W of US 30 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CE | 42000 | 33600 | 8400
110 | 1383695 | INDOT | US 41 | Added Travel Lanes Project | Auxiliary Lanes, Two-way Left Turn Lanes | From US 231 to 1.99 mi. N of US 231 (93rd Avenue) | Lake | 1.998 | 02/06/2019 | NHPP Non Interstate | 2019 | CN | 4989000 | 3991200 | 997800
111 | 1383706 | INDOT | SR 8 | District Bridge Project (Replacement) | Bridge Replacement, Steel | Bridge Over Hanna Arm, 2.01 mi W of SR 39 | LaPorte | 0 | 03/07/2018 | STBG State | 2018 | PE | 77000 | 61600 | 15400
112 | 1383706 | INDOT | SR 8 | District Bridge Project (Replacement) | Bridge Replacement, Steel | Bridge Over Hanna Arm, 2.01 mi W of SR 39 | LaPorte | 0 | 03/07/2018 | STBG State | 2018 | RW | 30000 | 24000 | 6000
113 | 1383706 | INDOT | SR 8 | District Bridge Project (Replacement) | Bridge Replacement, Steel | Bridge Over Hanna Arm, 2.01 mi W of SR 39 | LaPorte | 0 | 03/07/2018 | STBG State | 2018 | CN | 684207 | 547365.6 | 136841.4
114 | 1383706 | INDOT | SR 8 | District Bridge Project (Replacement) | Bridge Replacement, Steel | Bridge Over Hanna Arm, 2.01 mi W of SR 39 | LaPorte | 0 | 03/07/2018 | STBG State | Total |  | 791207 | 632965.6 | 158241.4
115 | 1383711 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | 01.20 N US-30 | Lake | 0 | 02/06/2019 | NHPP Non Interstate | 2019 | CN | 2875000 | 2300000 | 575000
116 | 1383718 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 3.21 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | 2019 | CN | 345000 | 310500 | 34500
117 | 1383719 | INDOT | US 30 | District Small Structure Project | Small Structure Maint and Repair | Box Culvert near CR 325 E - WB | Porter | 0 | 10/11/2018 | NHPP Non Interstate | 2019 | CN | 117000 | 93600 | 23400
118 | 1383725 | INDOT | US 6 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 51 to 0.51 mi E of SR 51 (Union St) | Lake | 0.515 | 01/15/2020 | NHPP Non Interstate | 2018 | PE | 50000 | 40000 | 10000
119 | 1383725 | INDOT | US 6 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 51 to 0.51 mi E of SR 51 (Union St) | Lake | 0.515 | 01/15/2020 | NHPP Non Interstate | 2020 | CN | 587898 | 470318.4 | 117579.6
120 | 1383725 | INDOT | US 6 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 51 to 0.51 mi E of SR 51 (Union St) | Lake | 0.515 | 01/15/2020 | NHPP Non Interstate | Total |  | 637898 | 510318.4 | 127579.6
121 | 1400116 | INDOT | US 35 | District Pavement Project (Non-I) | HMA Overlay, Functional | Boyd to SR 2 | LaPorte | 2.52 | 01/15/2020 | STBG State | 2020 | CN | 2706347 | 2165077.6 | 541269.4
122 | 1400204 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | 0.51 mi. W of US 20 (Lift Bridge) | Lake | 0 | 09/12/2018 | NHPP Non Interstate | 2019 | PE | 69600 | 55680 | 13920
123 | 1400204 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | 0.51 mi. W of US 20 (Lift Bridge) | Lake | 0 | 09/12/2018 | NHPP Non Interstate | 2019 | CN | 464000 | 371200 | 92800
124 | 1400204 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Replacement | 0.51 mi. W of US 20 (Lift Bridge) | Lake | 0 | 09/12/2018 | NHPP Non Interstate | Total |  | 533600 | 426880 | 106720
125 | 1400287 | INDOT | SR 149 | District Small Structure Project | Small Structure Pipe Lining | 1.64 mi S of jct US 20 | Porter | 0 | 07/12/2017 | NHPP Non Interstate | 2018 | CN | 112901 | 90320.8 | 22580.2
126 | 1401586 | INDOT | US 35 | District Bridge Project (Rehabilitation) | Bridge Deck Sealing | 2.45 mi S of US 6 over the Kankakee River | LaPorte | 0 | 07/12/2017 | STBG State | 2018 | CN | 16203 | 12962.4 | 3240.6
127 | 1500081 | INDOT | US 41 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Over GTW RR, 2.80 mi N of US-30 | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | RW | 100000 | 80000 | 20000
128 | 1500081 | INDOT | US 41 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Over GTW RR, 2.80 mi N of US-30 | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | CN | 5275842 | 4220673.6 | 1055168.4
129 | 1500081 | INDOT | US 41 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Over GTW RR, 2.80 mi N of US-30 | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | PE | 575000 | 460000 | 115000
130 | 1500081 | INDOT | US 41 | District Bridge Project (Replacement) | Bridge Replacement, Other Construction | Over GTW RR, 2.80 mi N of US-30 | Lake | 0 | 12/13/2017 | NHPP Non Interstate | Total |  | 5950842 | 4760673.6 | 1190168.4
131 | 1500090 | INDOT | US 12 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | US 12(Columbus Dr) with Railroad Ave & McShane Ave 0.25mi E of US 20 (Indy Blvd) | Lake | 0.056 | 04/04/2018 | NHPP Non Interstate | 2018 | PE | 123000 | 98400 | 24600
132 | 1500090 | INDOT | US 12 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | US 12(Columbus Dr) with Railroad Ave & McShane Ave 0.25mi E of US 20 (Indy Blvd) | Lake | 0.056 | 04/04/2018 | NHPP Non Interstate | 2018 | RW | 200000 | 160000 | 40000
133 | 1500090 | INDOT | US 12 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | US 12(Columbus Dr) with Railroad Ave & McShane Ave 0.25mi E of US 20 (Indy Blvd) | Lake | 0.056 | 04/04/2018 | NHPP Non Interstate | 2018 | CN | 1543000 | 1234400 | 308600
134 | 1500090 | INDOT | US 12 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | US 12(Columbus Dr) with Railroad Ave & McShane Ave 0.25mi E of US 20 (Indy Blvd) | Lake | 0.056 | 04/04/2018 | NHPP Non Interstate | Total |  | 1866000 | 1492800 | 373200
135 | 1500091 | INDOT | SR 55 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 55 at 57th Ave, 3.0 mi N of US 30 | Lake | 0.109 | 01/15/2020 | NHPP Non Interstate | 2019 | RW | 100000 | 80000 | 20000
136 | 1500091 | INDOT | SR 55 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 55 at 57th Ave, 3.0 mi N of US 30 | Lake | 0.109 | 01/15/2020 | NHPP Non Interstate | 2019 | UT2 | 100000 | 80000 | 20000
137 | 1500091 | INDOT | SR 55 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 55 at 57th Ave, 3.0 mi N of US 30 | Lake | 0.109 | 01/15/2020 | NHPP Non Interstate | 2020 | CE | 64000 | 51200 | 12800
138 | 1500091 | INDOT | SR 55 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 55 at 57th Ave, 3.0 mi N of US 30 | Lake | 0.109 | 01/15/2020 | NHPP Non Interstate | 2020 | CN | 593000 | 474400 | 118600
139 | 1500091 | INDOT | SR 55 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | Intersection of SR 55 at 57th Ave, 3.0 mi N of US 30 | Lake | 0.109 | 01/15/2020 | NHPP Non Interstate | Total |  | 857000 | 685600 | 171400
140 | 1500170 | INDOT | IR 1001 | Railroad Grade Crossing Project | Railroad Protection | CR 200S at CN RR DOT# 283306K near Mill Creek | LaPorte | 0 | 05/31/2018 | Sec 130 | 2018 | CN | 320000 | 320000 | 0
141 | 1500171 | INDOT | IR 1001 | Railroad Grade Crossing Project | Railroad Protection | Froberg Rd/150W at CN RR DOT# 283242B W of Valparaiso | Porter | 0 | 05/31/2018 | Sec 130 | 2018 | CN | 320000 | 320000 | 0
142 | 1500590 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Conrail RR & 236th Ave, NBL, 4.54 mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | PE | 13000 | 10400 | 2600
143 | 1500590 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Conrail RR & 236th Ave, NBL, 4.54 mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | CN | 110028 | 88022.4 | 22005.6
144 | 1500590 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Conrail RR & 236th Ave, NBL, 4.54 mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | Total |  | 123028 | 98422.4 | 24605.6
145 | 1500602 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Conrail RR & 236th Ave, SBL, 4.54mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | CN | 110028 | 88022.4 | 22005.6
146 | 1500602 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Conrail RR & 236th Ave, SBL, 4.54mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | 2018 | PE | 13000 | 10400 | 2600
147 | 1500602 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over Conrail RR & 236th Ave, SBL, 4.54mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Non Interstate | Total |  | 123028 | 98422.4 | 24605.6
148 | 1500674 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB Ramp NS RR and EJ&E RR, 0.50mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2021 | PE | 157000 | 141300 | 15700
149 | 1500674 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB Ramp NS RR and EJ&E RR, 0.50mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2021 | CN | 1993376 | 1794038.4 | 199337.6
150 | 1500674 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB Ramp NS RR and EJ&E RR, 0.50mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 20201 | PE | 75000 | 67500 | 7500
151 | 1500674 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB Ramp NS RR and EJ&E RR, 0.50mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | Total |  | 2225376 | 2002838.4 | 222537.6
152 | 1500689 | INDOT | SR 249 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From US 20 to US 12 | Porter | 1.904 | 11/15/2017 | NHPP Non Interstate | 2018 | CN | 1065000 | 852000 | 213000
153 | 1592854 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From I-80/94 to 0.77mi S of I-90 (Huehn St) | Lake | 0.001 | 08/09/2017 | NHPP Non Interstate | 2018 | PE | 70000 | 56000 | 14000
154 | 1592854 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From I-80/94 to 0.77mi S of I-90 (Huehn St) | Lake | 0.001 | 08/09/2017 | NHPP Non Interstate | 2018 | PE | 275000 | 220000 | 55000
155 | 1592854 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From I-80/94 to 0.77mi S of I-90 (Huehn St) | Lake | 0.001 | 08/09/2017 | NHPP Non Interstate | 2018 | CN | 2782000 | 2225600 | 556400
156 | 1592854 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From I-80/94 to 0.77mi S of I-90 (Huehn St) | Lake | 0.001 | 08/09/2017 | NHPP Non Interstate | Total |  | 3127000 | 2501600 | 625400
157 | 1592857 | INDOT | SR 49 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 1.14mi S of SR 8 to SR 8 | Porter | 1.168 | 08/09/2017 | STBG State | 2018 | CN | 412419 | 329935.2 | 82483.8
158 | 1592857 | INDOT | SR 49 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 1.14mi S of SR 8 to SR 8 | Porter | 1.168 | 08/09/2017 | STBG State | 2018 | PE | 58000 | 46400 | 11600
159 | 1592857 | INDOT | SR 49 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 1.14mi S of SR 8 to SR 8 | Porter | 1.168 | 08/09/2017 | STBG State | Total |  | 470419 | 376335.2 | 94083.8
160 | 1592873 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Scour Protection (Erosion) | .22mi E of I-80. Little Calumet River | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | CN | 159414 | 127531.2 | 31882.8
161 | 1592873 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Scour Protection (Erosion) | .22mi E of I-80. Little Calumet River | Lake | 0 | 12/13/2017 | NHPP Non Interstate | 2018 | PE | 22500 | 18000 | 4500
162 | 1592873 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Scour Protection (Erosion) | .22mi E of I-80. Little Calumet River | Lake | 0 | 12/13/2017 | NHPP Non Interstate | Total |  | 181914 | 145531.2 | 36382.8
163 | 1593079 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Sealing | 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 28523 | 25670.7 | 2852.3
164 | 1593079 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Sealing | 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 388942 | 350047.8 | 38894.2
165 | 1593079 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Sealing | 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | 2020 | CE | 29712 | 26740.8 | 2971.2
166 | 1593079 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Sealing | 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | Total |  | 447177 | 402459.3 | 44717.7
167 | 1593213 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | 73rd over I-65, 0.94mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 157000 | 141300 | 15700
168 | 1593213 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | 73rd over I-65, 0.94mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 886906 | 798215.4 | 88690.6
169 | 1593213 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | 73rd over I-65, 0.94mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CE | 117750 | 103620 | 14130
170 | 1593213 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | 73rd over I-65, 0.94mi N of US 30 | Lake | 0 |  | NHPP Interstate | Total |  | 1161656 | 1043135.4 | 118520.6
171 | 1593219 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 912 EB Ramp to I-80 at N&S RR | Lake | 0 |  | NHPP Interstate | 2018 | PE | 82380 | 74142 | 8238
172 | 1593219 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 912 EB Ramp to I-80 at N&S RR | Lake | 0 |  | NHPP Interstate | 2020 | CN | 949232 | 854308.8 | 94923.2
173 | 1593219 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 912 EB Ramp to I-80 at N&S RR | Lake | 0 |  | NHPP Interstate | 2020 | CE | 126000 | 113400 | 12600
174 | 1593219 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 912 EB Ramp to I-80 at N&S RR | Lake | 0 |  | NHPP Interstate | Total |  | 1157612 | 1041850.8 | 115761.2
175 | 1593246 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.94mi E of SR 51 | Lake | 0 | 07/11/2018 | NHPP Interstate | 2019 | CN | 200000 | 180000 | 20000
176 | 1593246 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.94mi E of SR 51 | Lake | 0 | 07/11/2018 | NHPP Interstate | 2019 | PE | 30000 | 27000 | 3000
177 | 1593246 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.94mi E of SR 51 | Lake | 0 | 07/11/2018 | NHPP Interstate | Total |  | 230000 | 207000 | 23000
178 | 1593247 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 2.66 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | 2019 | PE | 30000 | 27000 | 3000
179 | 1593247 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 2.66 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | 2019 | CN | 200000 | 180000 | 20000
180 | 1593247 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 2.66 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | Total |  | 230000 | 207000 | 23000
181 | 1593248 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 4.56 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | 2019 | PE | 30000 | 27000 | 3000
182 | 1593248 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 4.56 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | 2019 | CN | 200000 | 180000 | 20000
183 | 1593248 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 4.56 mi E of US 421 | LaPorte | 0 | 07/11/2018 | NHPP Interstate | Total |  | 230000 | 207000 | 23000
184 | 1593265 | INDOT | US 421 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 2 (N Jct) to 0.3mi S of I 94 (CR 300 N) | LaPorte | 6.373 | 07/11/2018 | NHPP Non Interstate | 2019 | CN | 1567500 | 1254000 | 313500
185 | 1593265 | INDOT | US 421 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 2 (N Jct) to 0.3mi S of I 94 (CR 300 N) | LaPorte | 6.373 | 07/11/2018 | NHPP Non Interstate | 2019 | PE | 156750 | 125400 | 31350
186 | 1593265 | INDOT | US 421 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 2 (N Jct) to 0.3mi S of I 94 (CR 300 N) | LaPorte | 6.373 | 07/11/2018 | NHPP Non Interstate | Total |  | 1724250 | 1379400 | 344850
187 | 1593278 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Cook Ditch, 4.01mi S of SR 8 | Porter | 0 | 02/06/2019 | STBG State | 2019 | CN | 200000 | 160000 | 40000
188 | 1593278 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Cook Ditch, 4.01mi S of SR 8 | Porter | 0 | 02/06/2019 | STBG State | 2019 | PE | 30000 | 24000 | 6000
189 | 1593278 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Cook Ditch, 4.01mi S of SR 8 | Porter | 0 | 02/06/2019 | STBG State | Total |  | 230000 | 184000 | 46000
190 | 1600012 | INDOT | I 65 | District Small Structure Project | Small Structure Pipe Lining | 2.96 mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Interstate | 2018 | CN | 165000 | 148500 | 16500
191 | 1600012 | INDOT | I 65 | District Small Structure Project | Small Structure Pipe Lining | 2.96 mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Interstate | 2018 | PE | 20625 | 18562.5 | 2062.5
192 | 1600012 | INDOT | I 65 | District Small Structure Project | Small Structure Pipe Lining | 2.96 mi S of SR 2 | Lake | 0 | 01/18/2018 | NHPP Interstate | Total |  | 185625 | 167062.5 | 18562.5
193 | 1600015 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | 2.03 mi W of SR 53 at I-80/94 EB/WB | Lake | 0 | 04/04/2018 | NHPP Interstate | 2018 | CN | 322193 | 289973.7 | 32219.3
194 | 1600015 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | 2.03 mi W of SR 53 at I-80/94 EB/WB | Lake | 0 | 04/04/2018 | NHPP Interstate | 2018 | PE | 40275 | 36247.5 | 4027.5
195 | 1600015 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | 2.03 mi W of SR 53 at I-80/94 EB/WB | Lake | 0 | 04/04/2018 | NHPP Interstate | Total |  | 362468 | 326221.2 | 36246.8
196 | 1600026 | INDOT | SR 51 | Signal Project (New/Modernized) | Traffic Signals Modernization | SR 51 & Petro Truck Plaza Dr., 2.95mi N of US 6 | Lake | 0 | 07/12/2017 | NHPP Non Interstate | 2018 | CN | 95219 | 76175.2 | 19043.8
197 | 1600028 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From US 20 (Columbus Dr.) to SR 912 | Lake |  |  | NHPP Non Interstate | 2018 | PE | 122000 | 97600 | 24400
198 | 1600028 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From US 20 (Columbus Dr.) to SR 912 | Lake |  |  | NHPP Non Interstate | 2020 | CN | 1524583 | 1219666.4 | 304916.6
199 | 1600028 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From US 20 (Columbus Dr.) to SR 912 | Lake |  |  | NHPP Non Interstate | 2020 | CE | 134900 | 107920 | 26980
200 | 1600028 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From US 20 (Columbus Dr.) to SR 912 | Lake |  |  | NHPP Non Interstate | Total |  | 1876702 | 1501361.6 | 375340.4
201 | 1600029 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 1.07mi W of SR 249 (Burns Harbor Ditch) To 1.32mi E of SR 149 (Oak Hill Rd) | Porter | 3.93 | 07/11/2018 | NHPP Non Interstate | 2019 | CN | 1960000 | 1568000 | 392000
202 | 1600029 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 1.07mi W of SR 249 (Burns Harbor Ditch) To 1.32mi E of SR 149 (Oak Hill Rd) | Porter | 3.93 | 07/11/2018 | NHPP Non Interstate | 2019 | PE | 196000 | 156800 | 39200
203 | 1600029 | INDOT | US 12 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 1.07mi W of SR 249 (Burns Harbor Ditch) To 1.32mi E of SR 149 (Oak Hill Rd) | Porter | 3.93 | 07/11/2018 | NHPP Non Interstate | Total |  | 2156000 | 1724800 | 431200
204 | 1600340 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.24 mi W of SR 149 to 0.11mi E of I-94 (Babcock Rd) | Porter | 1.407 | 07/11/2018 | NHPP Non Interstate | 2019 | CN | 755000 | 604000 | 151000
205 | 1600340 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.24 mi W of SR 149 to 0.11mi E of I-94 (Babcock Rd) | Porter | 1.407 | 07/11/2018 | NHPP Non Interstate | 2019 | PE | 113000 | 90400 | 22600
206 | 1600340 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.24 mi W of SR 149 to 0.11mi E of I-94 (Babcock Rd) | Porter | 1.407 | 07/11/2018 | NHPP Non Interstate | Total |  | 868000 | 694400 | 173600
207 | 1600344 | INDOT | US 35 | District Pavement Project (Non-I) | Concrete Pavement Restoration (CPR) | From SR 2 (in LaPorte) to 0.5mi N of SR 2 | LaPorte | 0.494 | 07/11/2018 | STBG State | 2019 | CN | 604000 | 483200 | 120800
208 | 1600344 | INDOT | US 35 | District Pavement Project (Non-I) | Concrete Pavement Restoration (CPR) | From SR 2 (in LaPorte) to 0.5mi N of SR 2 | LaPorte | 0.494 | 07/11/2018 | STBG State | 2019 | PE | 90000 | 72000 | 18000
209 | 1600344 | INDOT | US 35 | District Pavement Project (Non-I) | Concrete Pavement Restoration (CPR) | From SR 2 (in LaPorte) to 0.5mi N of SR 2 | LaPorte | 0.494 | 07/11/2018 | STBG State | Total |  | 694000 | 555200 | 138800
210 | 1600346 | INDOT | US 421 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.52 mi N of I-94 (Gruenke Rd) to US 20 | LaPorte | 0.993 | 07/11/2018 | NHPP Non Interstate | 2019 | CN | 485000 | 388000 | 97000
211 | 1600346 | INDOT | US 421 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.52 mi N of I-94 (Gruenke Rd) to US 20 | LaPorte | 0.993 | 07/11/2018 | NHPP Non Interstate | 2019 | PE | 97000 | 77600 | 19400
212 | 1600346 | INDOT | US 421 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.52 mi N of I-94 (Gruenke Rd) to US 20 | LaPorte | 0.993 | 07/11/2018 | NHPP Non Interstate | Total |  | 582000 | 465600 | 116400
213 | 1600351 | INDOT | US 30 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Deep River, 1.96mi E of SR 51 | Lake | 0 | 02/06/2019 | NHPP Non Interstate | 2019 | CN | 850000 | 680000 | 170000
214 | 1600351 | INDOT | US 30 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Deep River, 1.96mi E of SR 51 | Lake | 0 | 02/06/2019 | NHPP Non Interstate | 2019 | PE | 170000 | 136000 | 34000
215 | 1600351 | INDOT | US 30 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Deep River, 1.96mi E of SR 51 | Lake | 0 | 02/06/2019 | NHPP Non Interstate | Total |  | 1020000 | 816000 | 204000
216 | 1600352 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Painting | Over I-90, 3.60 mi E of SR 39 | LaPorte | 0 | 01/16/2019 | STBG State | 2019 | PE | 135000 | 108000 | 27000
217 | 1600352 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Painting | Over I-90, 3.60 mi E of SR 39 | LaPorte | 0 | 01/16/2019 | STBG State | 2019 | CN | 1350000 | 1080000 | 270000
218 | 1600352 | INDOT | US 20 | District Bridge Project (Rehabilitation) | Bridge Painting | Over I-90, 3.60 mi E of SR 39 | LaPorte | 0 | 01/16/2019 | STBG State | Total |  | 1485000 | 1188000 | 297000
219 | 1600358 | INDOT | US 20 | Environmental Mitigation Project | Environmental Mitigation | US 421 to US 35/SR 212 in Michigan City | LaPorte | 3.883 | 10/12/2017 | NHPP Non Interstate | 2018 | CN | 300000 | 240000 | 60000
220 | 1600406 | INDOT | SR 912 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.1mi N of Highway Ave to Ridge Road | Lake | 0.363 | 08/09/2017 | NHPP Non Interstate | 2018 | CN | 218175 | 174540 | 43635
221 | 1600406 | INDOT | SR 912 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.1mi N of Highway Ave to Ridge Road | Lake | 0.363 | 08/09/2017 | NHPP Non Interstate | 2018 | PE | 30000 | 24000 | 6000
222 | 1600406 | INDOT | SR 912 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.1mi N of Highway Ave to Ridge Road | Lake | 0.363 | 08/09/2017 | NHPP Non Interstate | 2018 | PE | 10000 | 8000 | 2000
223 | 1600406 | INDOT | SR 912 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From 0.1mi N of Highway Ave to Ridge Road | Lake | 0.363 | 08/09/2017 | NHPP Non Interstate | Total |  | 258175 | 206540 | 51635
224 | 1600448 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Tryon Road at CSX DOT #232070F in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
225 | 1600448 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Tryon Road at CSX DOT #232070F in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 320000 | 320000 | 0
226 | 1600448 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Tryon Road at CSX DOT #232070F in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | Total |  | 340000 | 340000 | 0
227 | 1600449 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Tilden Street at CSX RR DOT #232080L in Michigan City | LaPorte | 0 | 06/26/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
228 | 1600449 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Tilden Street at CSX RR DOT #232080L in Michigan City | LaPorte | 0 | 06/26/2019 | Sec 130 | 2019 | CN | 320000 | 320000 | 0
229 | 1600449 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Tilden Street at CSX RR DOT #232080L in Michigan City | LaPorte | 0 | 06/26/2019 | Sec 130 | Total |  | 340000 | 340000 | 0
230 | 1600450 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Sohl Street at IHB DOT #326991C in Hammond | Lake | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
231 | 1600450 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Sohl Street at IHB DOT #326991C in Hammond | Lake | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 400000 | 400000 | 0
232 | 1600450 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Sohl Street at IHB DOT #326991C in Hammond | Lake | 0 | 05/31/2019 | Sec 130 | Total |  | 420000 | 420000 | 0
233 | 1600451 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Roeske Ave at CSX DOT #232074H in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
234 | 1600451 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Roeske Ave at CSX DOT #232074H in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 320000 | 320000 | 0
235 | 1600451 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Roeske Ave at CSX DOT #232074H in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | Total |  | 340000 | 340000 | 0
236 | 1600452 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Greenwood Ave at CSX DOT #232075P in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
237 | 1600452 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Greenwood Ave at CSX DOT #232075P in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 320000 | 320000 | 0
238 | 1600452 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Greenwood Ave at CSX DOT #232075P in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | Total |  | 340000 | 340000 | 0
239 | 1600454 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Carroll Ave at CSX DOT #232077D in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
240 | 1600454 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Carroll Ave at CSX DOT #232077D in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 320000 | 320000 | 0
241 | 1600454 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Carroll Ave at CSX DOT #232077D in Michigan City | LaPorte | 0 | 05/31/2019 | Sec 130 | Total |  | 340000 | 340000 | 0
242 | 1600455 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Calumet St at NS RR DOT #522625P in Chesterton | Porter | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
243 | 1600455 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Calumet St at NS RR DOT #522625P in Chesterton | Porter | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 320000 | 320000 | 0
244 | 1600455 | INDOT | VA VARI | Railroad Grade Crossing Project | Railroad Protection | Calumet St at NS RR DOT #522625P in Chesterton | Porter | 0 | 05/31/2019 | Sec 130 | Total |  | 340000 | 340000 | 0
245 | 1600481 | INDOT | US 231 | Signal Project (New/Modernized) | New Signal Installation | Intersection of US 231 at Fathke Rd, 2.8 mi E of US 41 | Lake | 0 | 10/12/2017 | NHPP Non Interstate | 2018 | CN | 120000 | 96000 | 24000
246 | 1600481 | INDOT | US 231 | Signal Project (New/Modernized) | New Signal Installation | Intersection of US 231 at Fathke Rd, 2.8 mi E of US 41 | Lake | 0 | 10/12/2017 | NHPP Non Interstate | 2018 | PE | 20000 | 16000 | 4000
247 | 1600481 | INDOT | US 231 | Signal Project (New/Modernized) | New Signal Installation | Intersection of US 231 at Fathke Rd, 2.8 mi E of US 41 | Lake | 0 | 10/12/2017 | NHPP Non Interstate | Total |  | 140000 | 112000 | 28000
248 | 1600499 | INDOT | US 30 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 2.65mi W of W Jct of SR 2 (CR 250W) to 0.6mi E of SR 49 (Industrial Dr) | Porter | 5.42 | 01/15/2020 | NHPP Non Interstate | 2020 | PE | 315000 | 252000 | 63000
249 | 1600499 | INDOT | US 30 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 2.65mi W of W Jct of SR 2 (CR 250W) to 0.6mi E of SR 49 (Industrial Dr) | Porter | 5.42 | 01/15/2020 | NHPP Non Interstate | 2020 | CN | 5160618 | 4128494.4 | 1032123.6
250 | 1600499 | INDOT | US 30 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 2.65mi W of W Jct of SR 2 (CR 250W) to 0.6mi E of SR 49 (Industrial Dr) | Porter | 5.42 | 01/15/2020 | NHPP Non Interstate | 2020 | CE | 315000 | 252000 | 63000
251 | 1600499 | INDOT | US 30 | District Pavement Project (Non-I) | HMA Overlay, Functional | From 2.65mi W of W Jct of SR 2 (CR 250W) to 0.6mi E of SR 49 (Industrial Dr) | Porter | 5.42 | 01/15/2020 | NHPP Non Interstate | Total |  | 5790618 | 4632494.4 | 1158123.6
252 | 1600500 | INDOT | SR 249 | District Bridge Project (Replacement) | Replace Superstructure | US 12, 2 RR, 2 Roads, 2.0mi N of I-94 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2018 | PE | 1600000 | 1280000 | 320000
253 | 1600500 | INDOT | SR 249 | District Bridge Project (Replacement) | Replace Superstructure | US 12, 2 RR, 2 Roads, 2.0mi N of I-94 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CN | 18938015 | 15150412 | 3787603
254 | 1600500 | INDOT | SR 249 | District Bridge Project (Replacement) | Replace Superstructure | US 12, 2 RR, 2 Roads, 2.0mi N of I-94 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | 2020 | CE | 1000000 | 800000 | 200000
255 | 1600500 | INDOT | SR 249 | District Bridge Project (Replacement) | Replace Superstructure | US 12, 2 RR, 2 Roads, 2.0mi N of I-94 | Porter | 0 | 01/15/2020 | NHPP Non Interstate | Total |  | 21538015 | 17230412 | 4307603
256 | 1600504 | INDOT | SR 51 | Intersection Improvement Project | Added Travel Lanes, Construct Turn Lanes | Intersection with 10th St and Lincoln St | Lake | 0.07 | 10/07/2020 | STBG State | 2018 | PE | 45000 | 36000 | 9000
257 | 1600504 | INDOT | SR 51 | Intersection Improvement Project | Added Travel Lanes, Construct Turn Lanes | Intersection with 10th St and Lincoln St | Lake | 0.07 | 10/07/2020 | STBG State | 2021 | CN | 299571 | 239656.8 | 59914.2
258 | 1600504 | INDOT | SR 51 | Intersection Improvement Project | Added Travel Lanes, Construct Turn Lanes | Intersection with 10th St and Lincoln St | Lake | 0.07 | 10/07/2020 | STBG State | Total |  | 344571 | 275656.8 | 68914.2
259 | 1600694 | INDOT | SR 130 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | SR 130 @ CR 450 W | Porter | 0 | 10/07/2020 | NHPP Non Interstate | 2018 | PE | 56000 | 44800 | 11200
260 | 1600694 | INDOT | SR 130 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | SR 130 @ CR 450 W | Porter | 0 | 10/07/2020 | NHPP Non Interstate | 2021 | CN | 378629 | 302903.2 | 75725.8
261 | 1600694 | INDOT | SR 130 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | SR 130 @ CR 450 W | Porter | 0 | 10/07/2020 | NHPP Non Interstate | Total |  | 434629 | 347703.2 | 86925.8
262 | 1600700 | INDOT | SR 130 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | SR 149 @ SR 130 | Porter | 0 | 10/07/2020 | NHPP Non Interstate | 2018 | PE | 69000 | 55200 | 13800
263 | 1600700 | INDOT | SR 130 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | SR 149 @ SR 130 | Porter | 0 | 10/07/2020 | NHPP Non Interstate | 2021 | CN | 462428 | 369942.4 | 92485.6
264 | 1600700 | INDOT | SR 130 | Intersection Improvement Project | Intersect. Improv. W/ Added Turn Lanes | SR 149 @ SR 130 | Porter | 0 | 10/07/2020 | NHPP Non Interstate | Total |  | 531428 | 425142.4 | 106285.6
265 | 1600906 | INDOT | SR 4 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 4 @ GTW RR, 2.79 mi E of SR 104 | LaPorte | 0 | 07/08/2020 | STBG State | 2018 | PE | 63449 | 50759.2 | 12689.8
266 | 1600906 | INDOT | SR 4 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 4 @ GTW RR, 2.79 mi E of SR 104 | LaPorte | 0 | 07/08/2020 | STBG State | 2020 | PE | 60000 | 48000 | 12000
267 | 1600906 | INDOT | SR 4 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 4 @ GTW RR, 2.79 mi E of SR 104 | LaPorte | 0 | 07/08/2020 | STBG State | 2021 | CN | 606428 | 485142.4 | 121285.6
268 | 1600906 | INDOT | SR 4 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 4 @ GTW RR, 2.79 mi E of SR 104 | LaPorte | 0 | 07/08/2020 | STBG State | Total |  | 729877 | 583901.6 | 145975.4
269 | 1600907 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 EB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | 2018 | PE | 107000 | 85600 | 21400
270 | 1600907 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 EB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | 2020 | PE | 65000 | 52000 | 13000
271 | 1600907 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 EB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | 2021 | CN | 1023518 | 818814.4 | 204703.6
272 | 1600907 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 EB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | Total |  | 1195518 | 956414.4 | 239103.6
273 | 1600913 | INDOT | SR 2 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 2 at Heavilin Rd (CR 50W) | Porter | 0 | 10/11/2018 | NHPP Non Interstate | 2018 | PE | 30000 | 24000 | 6000
274 | 1600913 | INDOT | SR 2 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 2 at Heavilin Rd (CR 50W) | Porter | 0 | 10/11/2018 | NHPP Non Interstate | 2018 | RW | 30000 | 24000 | 6000
275 | 1600913 | INDOT | SR 2 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 2 at Heavilin Rd (CR 50W) | Porter | 0 | 10/11/2018 | NHPP Non Interstate | 2019 | CN | 1493324 | 1194659.2 | 298664.8
276 | 1600913 | INDOT | SR 2 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 2 at Heavilin Rd (CR 50W) | Porter | 0 | 10/11/2018 | NHPP Non Interstate | 2019 | PE | 203000 | 162400 | 40600
277 | 1600913 | INDOT | SR 2 | Intersection Improvement Project | Intersection Improvement, Roundabout | Intersection of SR 2 at Heavilin Rd (CR 50W) | Porter | 0 | 10/11/2018 | NHPP Non Interstate | Total |  | 1756324 | 1405059.2 | 351264.8
278 | 1600914 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 WB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | 2018 | PE | 107000 | 85600 | 21400
279 | 1600914 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 WB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | 2020 | PE | 65000 | 52000 | 13000
280 | 1600914 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 WB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | 2021 | CN | 1023518 | 818814.4 | 204703.6
281 | 1600914 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | US 12 WB @ NS RR, Beth Steel Ramp, 0.24 mi E of SR 149 | Porter | 0 | 07/08/2020 | NHPP Non Interstate | Total |  | 1195518 | 956414.4 | 239103.6
282 | 1600923 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 NB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | 2018 | PE | 132000 | 105600 | 26400
283 | 1600923 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 NB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | 2020 | PE | 65000 | 52000 | 13000
284 | 1600923 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 NB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | 2021 | CN | 1261850 | 1009480 | 252370
285 | 1600923 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 NB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | Total |  | 1458850 | 1167080 | 291770
286 | 1600924 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 SB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | 2018 | PE | 120300 | 96240 | 24060
287 | 1600924 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 SB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | 2020 | PE | 65000 | 52000 | 13000
288 | 1600924 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 SB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | 2021 | CN | 1149451 | 919560.8 | 229890.2
289 | 1600924 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SR 49 SB @ CSX RR, Little Calumet R, 0.37 mi S of I-94 | Porter | 0 | 07/08/2020 | STBG State | Total |  | 1334751 | 1067800.8 | 266950.2
290 | 1601031 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB Ramp SE & NE @ NS RR and EJ&E RR, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2018 | PE | 254000 | 228600 | 25400
291 | 1601031 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB Ramp SE & NE @ NS RR and EJ&E RR, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2020 | PE | 60000 | 54000 | 6000
292 | 1601031 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB Ramp SE & NE @ NS RR and EJ&E RR, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2021 | CN | 2427790 | 2185011 | 242779
293 | 1601031 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB Ramp SE & NE @ NS RR and EJ&E RR, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | Total |  | 2741790 | 2467611 | 274179
294 | 1601047 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB @ NS RR, EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2018 | PE | 300000 | 270000 | 30000
295 | 1601047 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB @ NS RR, EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2020 | PE | 60000 | 54000 | 6000
296 | 1601047 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB @ NS RR, EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2021 | CN | 3025327 | 2722794.3 | 302532.7
297 | 1601047 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 EB @ NS RR, EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | Total |  | 3385327 | 3046794.3 | 338532.7
298 | 1601049 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB @ NS RR & EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2018 | PE | 300000 | 270000 | 30000
299 | 1601049 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB @ NS RR & EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2019 | PE | 60000 | 54000 | 6000
300 | 1601049 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB @ NS RR & EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | 2021 | CN | 3156716 | 2841044.4 | 315671.6
301 | 1601049 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | I-80 WB @ NS RR & EJ&E RR Spur, 0.50 mi E of SR 912 | Lake | 0 | 07/08/2020 | NHPP Interstate | Total |  | 3516716 | 3165044.4 | 351671.6
302 | 1601069 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 2 to 3.95 mi E of SR 2 (LaPorte/St Joseph County Line) | LaPorte | 4.04 | 10/07/2020 | STBG State | 2019 | PE | 30000 | 24000 | 6000
303 | 1601069 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 2 to 3.95 mi E of SR 2 (LaPorte/St Joseph County Line) | LaPorte | 4.04 | 10/07/2020 | STBG State | 2020 | PE | 10000 | 8000 | 2000
304 | 1601069 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 2 to 3.95 mi E of SR 2 (LaPorte/St Joseph County Line) | LaPorte | 4.04 | 10/07/2020 | STBG State | 2021 | CN | 2678103 | 2142482.4 | 535620.6
305 | 1601069 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Functional | From SR 2 to 3.95 mi E of SR 2 (LaPorte/St Joseph County Line) | LaPorte | 4.04 | 10/07/2020 | STBG State | Total |  | 2718103 | 2174482.4 | 543620.6
306 | 1601122 | INDOT | ST 1001 | Railroad Grade Crossing Project | Railroad Protection | 15th Street at CSX Railroad DOT # 232115K in Chesterton | Porter | 0 | 05/31/2019 | Sec 130 | 2018 | PE | 20000 | 20000 | 0
307 | 1601122 | INDOT | ST 1001 | Railroad Grade Crossing Project | Railroad Protection | 15th Street at CSX Railroad DOT # 232115K in Chesterton | Porter | 0 | 05/31/2019 | Sec 130 | 2019 | CN | 400000 | 400000 | 0
308 | 1601122 | INDOT | ST 1001 | Railroad Grade Crossing Project | Railroad Protection | 15th Street at CSX Railroad DOT # 232115K in Chesterton | Porter | 0 | 05/31/2019 | Sec 130 | Total |  | 420000 | 420000 | 0
309 | 1601381 | INDOT | SR 55 | Signal Project (New/Modernized) | New Signal Installation | Intersection of SR 55 and 129th Ave, 2.14mi S of US 231 | Lake | 0 | 10/12/2017 | STBG State | 2018 | PE | 20000 | 16000 | 4000
310 | 1601381 | INDOT | SR 55 | Signal Project (New/Modernized) | New Signal Installation | Intersection of SR 55 and 129th Ave, 2.14mi S of US 231 | Lake | 0 | 10/12/2017 | STBG State | 2018 | CN | 120000 | 96000 | 24000
311 | 1601381 | INDOT | SR 55 | Signal Project (New/Modernized) | New Signal Installation | Intersection of SR 55 and 129th Ave, 2.14mi S of US 231 | Lake | 0 | 10/12/2017 | STBG State | Total |  | 140000 | 112000 | 28000
312 | 1601711 | INDOT | US 20 | New Interchange Project | New Bridge, Other | At SR 2 | LaPorte | 0 | 12/12/2018 | STBG State | 2019 | CN | 2000000 | 1600000 | 400000
313 | 1601716 | INDOT | US 12 | District Pavement Project (Non-I) | Pavement, Other | 0.25 mi E of Lake St in Gary | Lake | 1.087 | 11/15/2018 | NHPP Non Interstate | 2018 | RW | 200000 | 160000 | 40000
314 | 1601716 | INDOT | US 12 | District Pavement Project (Non-I) | Pavement, Other | 0.25 mi E of Lake St in Gary | Lake | 1.087 | 11/15/2018 | NHPP Non Interstate | 2019 | CN | 2300000 | 1840000 | 460000
315 | 1601716 | INDOT | US 12 | District Pavement Project (Non-I) | Pavement, Other | 0.25 mi E of Lake St in Gary | Lake | 1.087 | 11/15/2018 | NHPP Non Interstate | Total |  | 2500000 | 2000000 | 500000
316 | 1602106 | INDOT | SR 2 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 39 to Burson Ave. | LaPorte | 1.54 |  | STBG State | 2018 | PE | 163760 | 131008 | 32752
317 | 1602106 | INDOT | SR 2 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 39 to Burson Ave. | LaPorte | 1.54 |  | STBG State | 2020 | CN | 2227563 | 1782050.4 | 445512.6
318 | 1602106 | INDOT | SR 2 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 39 to Burson Ave. | LaPorte | 1.54 |  | STBG State | Total |  | 2391323 | 1913058.4 | 478264.6
319 | 1602107 | INDOT | US 6 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From E Jct of US 421 to SR 39 | LaPorte | 7.99 |  | STBG State | 2018 | PE | 160000 | 128000 | 32000
320 | 1602107 | INDOT | US 6 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From E Jct of US 421 to SR 39 | LaPorte | 7.99 |  | STBG State | 2020 | CN | 2176417 | 1741133.6 | 435283.4
321 | 1602107 | INDOT | US 6 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From E Jct of US 421 to SR 39 | LaPorte | 7.99 |  | STBG State | Total |  | 2336417 | 1869133.6 | 467283.4
322 | 1602110 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 152 to SR 912 | Lake | 2.49 |  | STBG State | 2018 | PE | 67920 | 54336 | 13584
323 | 1602110 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 152 to SR 912 | Lake | 2.49 |  | STBG State | 2020 | CN | 754677 | 603741.6 | 150935.4
324 | 1602110 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | From SR 152 to SR 912 | Lake | 2.49 |  | STBG State | Total |  | 822597 | 658077.6 | 164519.4
325 | 1602120 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Painting | over Guthrie St., 0.32mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 46000 | 36800 | 9200
326 | 1602120 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Painting | over Guthrie St., 0.32mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 327883 | 262306.4 | 65576.6
327 | 1602120 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Painting | over Guthrie St., 0.32mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | Total |  | 373883 | 299106.4 | 74776.6
328 | 1700293 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over US 20 (exit #22) 0.88mi E of SR 149 | Porter | 0 |  | NHPP Interstate | 2018 | PE | 75400 | 67860 | 7540
329 | 1700293 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over US 20 (exit #22) 0.88mi E of SR 149 | Porter | 0 |  | NHPP Interstate | 2020 | CN | 1034652 | 931186.8 | 103465.2
330 | 1700293 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over US 20 (exit #22) 0.88mi E of SR 149 | Porter | 0 |  | NHPP Interstate | Total |  | 1110052 | 999046.8 | 111005.2
331 | 1700294 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over US 20 (exit #22) 0.88mi E of SR 149 | Porter | 0 |  | NHPP Interstate | 2018 | PE | 75400 | 67860 | 7540
332 | 1700294 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over US 20 (exit #22) 0.88mi E of SR 149 | Porter | 0 |  | NHPP Interstate | 2020 | CN | 1034652 | 931186.8 | 103465.2
333 | 1700294 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over US 20 (exit #22) 0.88mi E of SR 149 | Porter | 0 |  | NHPP Interstate | Total |  | 1110052 | 999046.8 | 111005.2
334 | 1700295 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over EJ&E RR and Gary Ave | Lake | 0 |  | STBG State | 2018 | PE | 101200 | 80960 | 20240
335 | 1700295 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over EJ&E RR and Gary Ave | Lake | 0 |  | STBG State | 2020 | CN | 1385640 | 1108512 | 277128
336 | 1700295 | INDOT | US 12 | District Bridge Project (Rehabilitation) | Bridge Painting | Bridge over EJ&E RR and Gary Ave | Lake | 0 |  | STBG State | Total |  | 1486840 | 1189472 | 297368
337 | 1700296 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over US 20, Willow Creek & CSX RR | Porter | 0 |  | NHPP Interstate | 2018 | PE | 108480 | 97632 | 10848
338 | 1700296 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over US 20, Willow Creek & CSX RR | Porter | 0 |  | NHPP Interstate | 2020 | CN | 1488581 | 1339722.9 | 148858.1
339 | 1700296 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over US 20, Willow Creek & CSX RR | Porter | 0 |  | NHPP Interstate | Total |  | 1597061 | 1437354.9 | 159706.1
340 | 1700297 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over US 20, Willow Creek & CSX RR | Porter | 0 |  | NHPP Interstate | 2018 | PE | 108480 | 97632 | 10848
341 | 1700297 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over US 20, Willow Creek & CSX RR | Porter | 0 |  | NHPP Interstate | 2020 | CN | 1488581 | 1339722.9 | 148858.1
342 | 1700297 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over US 20, Willow Creek & CSX RR | Porter | 0 |  | NHPP Interstate | Total |  | 1597061 | 1437354.9 | 159706.1
343 | 1700298 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over Amtrak, 0.54mi W of SR 49 | Porter | 0 |  | NHPP-Interstate | 2018 | PE | 64800 | 58320 | 6480
344 | 1700298 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over Amtrak, 0.54mi W of SR 49 | Porter | 0 |  | NHPP-Interstate | 2020 | CN | 880982 | 792883.8 | 88098.2
345 | 1700298 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over Amtrak, 0.54mi W of SR 49 | Porter | 0 |  | NHPP-Interstate | Total |  | 945782 | 851203.8 | 94578.2
346 | 1700299 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over Amtrak, 0.54mi W of SR 49 | Porter | 0 |  | NHPP-Interstate | 2018 | PE | 64800 | 58320 | 6480
347 | 1700299 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over Amtrak, 0.54mi W of SR 49 | Porter | 0 |  | NHPP-Interstate | 2020 | CN | 880982 | 792883.8 | 88098.2
348 | 1700299 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over Amtrak, 0.54mi W of SR 49 | Porter | 0 |  | NHPP-Interstate | Total |  | 945782 | 851203.8 | 94578.2
349 | 1700300 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over NICTD, 1.74mi E of US 20 | LaPorte | 0 |  | NHPP Interstate | 2018 | PE | 33000 | 29700 | 3300
350 | 1700300 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over NICTD, 1.74mi E of US 20 | LaPorte | 0 |  | NHPP Interstate | 2020 | CN | 401785 | 361606.5 | 40178.5
351 | 1700300 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | EBL over NICTD, 1.74mi E of US 20 | LaPorte | 0 |  | NHPP Interstate | Total |  | 434785 | 391306.5 | 43478.5
352 | 1700301 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over NICTD, 1.74mi E of US 20 | LaPorte | 0 |  | NHPP Interstate | 2018 | PE | 33000 | 29700 | 3300
353 | 1700301 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over NICTD, 1.74mi E of US 20 | LaPorte | 0 |  | NHPP Interstate | 2020 | CN | 401785 | 361606.5 | 40178.5
354 | 1700301 | INDOT | I 94 | District Bridge Project (Rehabilitation) | Bridge Painting | WBL over NICTD, 1.74mi E of US 20 | LaPorte | 0 |  | NHPP Interstate | Total |  | 434785 | 391306.5 | 43478.5
355 | 1700311 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | NB@.-US 30 EB/WB, CD, RAMPS | Lake | 0 |  | NHPP Interstate | 2018 | PE | 42700 | 38430 | 4270
356 | 1700311 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | NB@.-US 30 EB/WB, CD, RAMPS | Lake | 0 |  | NHPP Interstate | 2020 | CN | 508185 | 457366.5 | 50818.5
357 | 1700311 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | NB@.-US 30 EB/WB, CD, RAMPS | Lake | 0 |  | NHPP Interstate | Total |  | 550885 | 495796.5 | 55088.5
358 | 1700312 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | SB@.-US 30 EB/WB, CD, RAMPS | Lake | 0 |  | NHPP Interstate | 2018 | PE | 40000 | 36000 | 4000
359 | 1700312 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | SB@.-US 30 EB/WB, CD, RAMPS | Lake | 0 |  | NHPP Interstate | 2020 | CN | 475022 | 427519.8 | 47502.2
360 | 1700312 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | SB@.-US 30 EB/WB, CD, RAMPS | Lake | 0 |  | NHPP Interstate | Total |  | 515022 | 463519.8 | 51502.2
361 | 1700322 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | SB Ramp over I-80 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 30000 | 27000 | 3000
362 | 1700322 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | SB Ramp over I-80 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 355190 | 319671 | 35519
363 | 1700322 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | SB Ramp over I-80 | Lake | 0 |  | NHPP Interstate | Total |  | 385190 | 346671 | 38519
364 | 1700323 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | I-80 WB to I-65 SB Ramp | Lake | 0 |  | NHPP Interstate | 2018 | PE | 38300 | 34470 | 3830
365 | 1700323 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | I-80 WB to I-65 SB Ramp | Lake | 0 |  | NHPP Interstate | 2020 | CN | 454575 | 409117.5 | 45457.5
366 | 1700323 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | I-80 WB to I-65 SB Ramp | Lake | 0 |  | NHPP Interstate | Total |  | 492875 | 443587.5 | 49287.5
367 | 1700324 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EB & EB Ramp over Burns Ditch, 0.45mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 40540 | 36486 | 4054
368 | 1700324 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EB & EB Ramp over Burns Ditch, 0.45mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 481398 | 433258.2 | 48139.8
369 | 1700324 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EB & EB Ramp over Burns Ditch, 0.45mi E of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 521938 | 469744.2 | 52193.8
370 | 1700325 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WB & WB Ramp over Burns Ditch, 0.45mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 44200 | 39780 | 4420
371 | 1700325 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WB & WB Ramp over Burns Ditch, 0.45mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 524187 | 471768.3 | 52418.7
372 | 1700325 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WB & WB Ramp over Burns Ditch, 0.45mi E of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 568387 | 511548.3 | 56838.7
373 | 1700326 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EBL over Central Ave, CSX RR, 0.92mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 46700 | 42030 | 4670
374 | 1700326 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EBL over Central Ave, CSX RR, 0.92mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 554501 | 499050.9 | 55450.1
375 | 1700326 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EBL over Central Ave, CSX RR, 0.92mi E of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 601201 | 541080.9 | 60120.1
376 | 1700327 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WBL over Central Ave, Conrail RR, 0.92mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 50550 | 45495 | 5055
377 | 1700327 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WBL over Central Ave, Conrail RR, 0.92mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 600052 | 540046.8 | 60005.2
378 | 1700327 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WBL over Central Ave, Conrail RR, 0.92mi E of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 650602 | 585541.8 | 65060.2
379 | 1700329 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Painting | Colfax Ave over I-80, 1.0mi E of SR 912 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 27500 | 24750 | 2750
380 | 1700329 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Painting | Colfax Ave over I-80, 1.0mi E of SR 912 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 335296 | 301766.4 | 33529.6
381 | 1700329 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Painting | Colfax Ave over I-80, 1.0mi E of SR 912 | Lake | 0 |  | NHPP Interstate | Total |  | 362796 | 326516.4 | 36279.6
382 | 1700332 | INDOT | SR 149 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Bridge over Little Calumet River, 0.14mi S of US 12 | Porter | 0 |  | STBG State | 2018 | PE | 194050 | 155240 | 38810
383 | 1700332 | INDOT | SR 149 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Bridge over Little Calumet River, 0.14mi S of US 12 | Porter | 0 |  | STBG State | 2020 | CN | 2634600 | 2107680 | 526920
384 | 1700332 | INDOT | SR 149 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Bridge over Little Calumet River, 0.14mi S of US 12 | Porter | 0 |  | STBG State | Total |  | 2828650 | 2262920 | 565730
385 | 1700334 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Painting | Ramp over RR Yard, 1.40mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 70560 | 56448 | 14112
386 | 1700334 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Painting | Ramp over RR Yard, 1.40mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 859554 | 687643.2 | 171910.8
387 | 1700334 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Painting | Ramp over RR Yard, 1.40mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | Total |  | 930114 | 744091.2 | 186022.8
388 | 1700335 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EBL over CFE RR, 0.57mi W of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 24000 | 21600 | 2400
389 | 1700335 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EBL over CFE RR, 0.57mi W of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 284249 | 255824.1 | 28424.9
390 | 1700335 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EBL over CFE RR, 0.57mi W of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 308249 | 277424.1 | 30824.9
391 | 1700336 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WBL over CFE RR, 0.57mi W of I-64 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 24600 | 22140 | 2460
392 | 1700336 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WBL over CFE RR, 0.57mi W of I-64 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 291975 | 262777.5 | 29197.5
393 | 1700336 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WBL over CFE RR, 0.57mi W of I-64 | Lake | 0 |  | NHPP Interstate | Total |  | 316575 | 284917.5 | 31657.5
394 | 1700341 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EB over Clay Street, 1.18mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 21100 | 18990 | 2110
395 | 1700341 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EB over Clay Street, 1.18mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 250148 | 225133.2 | 25014.8
396 | 1700341 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | EB over Clay Street, 1.18mi E of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 271248 | 244123.2 | 27124.8
397 | 1700343 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WB over Clay Street, 1.18mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 22825 | 20542.5 | 2282.5
398 | 1700343 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WB over Clay Street, 1.18mi E of I-65 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 270974 | 243876.6 | 27097.4
399 | 1700343 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | WB over Clay Street, 1.18mi E of I-65 | Lake | 0 |  | NHPP Interstate | Total |  | 293799 | 264419.1 | 29379.9
400 | 1700354 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NB over N&S RR, 1.04mi S of I-94 | Porter | 0 |  | NHPP Non Interstate | 2018 | PE | 38000 | 30400 | 7600
401 | 1700354 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NB over N&S RR, 1.04mi S of I-94 | Porter | 0 |  | NHPP Non Interstate | 2020 | CN | 451527 | 361221.6 | 90305.4
402 | 1700354 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NB over N&S RR, 1.04mi S of I-94 | Porter | 0 |  | NHPP Non Interstate | Total |  | 489527 | 391621.6 | 97905.4
403 | 1700355 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB over N&S RR, 1.04mi S of I-94 | Porter | 0 |  | NHPP Non Interstate | 2018 | PE | 38000 | 30400 | 7600
404 | 1700355 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB over N&S RR, 1.04mi S of I-94 | Porter | 0 |  | NHPP Non Interstate | 2020 | CN | 451527 | 361221.6 | 90305.4
405 | 1700355 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB over N&S RR, 1.04mi S of I-94 | Porter | 0 |  | NHPP Non Interstate | Total |  | 489527 | 391621.6 | 97905.4
406 | 1700357 | INDOT | SR 53 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over I-80/94 | Lake | 0 |  | STBG State | 2018 | PE | 118273 | 94618.4 | 23654.6
407 | 1700357 | INDOT | SR 53 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over I-80/94 | Lake | 0 |  | STBG State | 2020 | CN | 1606638 | 1285310.4 | 321327.6
408 | 1700357 | INDOT | SR 53 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over I-80/94 | Lake | 0 |  | STBG State | Total |  | 1724911 | 1379928.8 | 344982.2
409 | 1700358 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Grand Calumet River, 0.58mi S of SR 312 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 114560 | 91648 | 22912
410 | 1700358 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Grand Calumet River, 0.58mi S of SR 312 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 1382803 | 1106242.4 | 276560.6
411 | 1700358 | INDOT | US 41 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over Grand Calumet River, 0.58mi S of SR 312 | Lake | 0 |  | NHPP Non Interstate | Total |  | 1497363 | 1197890.4 | 299472.6
412 | 1700359 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Elevation Change-up Ramp, 1.17mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 121633 | 97306.4 | 24326.6
413 | 1700359 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Elevation Change-up Ramp, 1.17mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 1468193 | 1174554.4 | 293638.6
414 | 1700359 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Elevation Change-up Ramp, 1.17mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | Total |  | 1589826 | 1271860.8 | 317965.2
415 | 1700360 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over GTW RR< 1.85mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 69840 | 62856 | 6984
416 | 1700360 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over GTW RR< 1.85mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 843137 | 758823.3 | 84313.7
417 | 1700360 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over GTW RR< 1.85mi N of US 30 | Lake | 0 |  | NHPP Interstate | Total |  | 912977 | 821679.3 | 91297.7
418 | 1700361 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over GTW RR< 1.85mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 69840 | 62856 | 6984
419 | 1700361 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over GTW RR< 1.85mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 843137 | 758823.3 | 84313.7
420 | 1700361 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Over GTW RR< 1.85mi N of US 30 | Lake | 0 |  | NHPP Interstate | Total |  | 912977 | 821679.3 | 91297.7
421 | 1700362 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NB over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 71590 | 64431 | 7159
422 | 1700362 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NB over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 864268 | 777841.2 | 86426.8
423 | 1700362 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NB over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | Total |  | 935858 | 842272.2 | 93585.8
424 | 1700363 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 51935 | 46741.5 | 5193.5
425 | 1700363 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 626971 | 564273.9 | 62697.1
426 | 1700363 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | Total |  | 678906 | 611015.4 | 67890.6
427 | 1700366 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB Ramp over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 30600 | 27540 | 3060
428 | 1700366 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB Ramp over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 369428 | 332485.2 | 36942.8
429 | 1700366 | INDOT | I 65 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SB Ramp over Turkey Creek, 2.70mi N of US 30 | Lake | 0 |  | NHPP Interstate | Total |  | 400028 | 360025.2 | 40002.8
430 | 1700368 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | EBL over Industrial Highway, 0.52mi W of SR 312 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 69250 | 55400 | 13850
431 | 1700368 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | EBL over Industrial Highway, 0.52mi W of SR 312 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 836065 | 668852 | 167213
432 | 1700368 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | EBL over Industrial Highway, 0.52mi W of SR 312 | Lake | 0 |  | NHPP Non Interstate | Total |  | 905315 | 724252 | 181063
433 | 1700369 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | WBL over Industrial Highway, 0.52mi W of SR 312 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 77570 | 62056 | 15514
434 | 1700369 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | WBL over Industrial Highway, 0.52mi W of SR 312 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 936564 | 749251.2 | 187312.8
435 | 1700369 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | WBL over Industrial Highway, 0.52mi W of SR 312 | Lake | 0 |  | NHPP Non Interstate | Total |  | 1014134 | 811307.2 | 202826.8
436 | 1700370 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Ramp over RR Yard, 1.40mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 60920 | 48736 | 12184
437 | 1700370 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Ramp over RR Yard, 1.40mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 735498 | 588398.4 | 147099.6
438 | 1700370 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Ramp over RR Yard, 1.40mi W of US 12 | Lake | 0 |  | NHPP Non Interstate | Total |  | 796418 | 637134.4 | 159283.6
439 | 1700379 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | Over US 12/20, Private Rd., 1.46mi E of US 41 | Lake | 0 |  | NHPP Non Interstate | 2018 | PE | 56700 | 45360 | 11340
440 | 1700379 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | Over US 12/20, Private Rd., 1.46mi E of US 41 | Lake | 0 |  | NHPP Non Interstate | 2020 | CN | 675820 | 540656 | 135164
441 | 1700379 | INDOT | SR 912 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | Over US 12/20, Private Rd., 1.46mi E of US 41 | Lake | 0 |  | NHPP Non Interstate | Total |  | 732520 | 586016 | 146504
442 | 1700371 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Ramp L-WB to SR 51 over Ramp M (I-90 to WB I-80) | Lake | 0 |  | NHPP Interstate | 2018 | PE | 58270 | 52443 | 5827
443 | 1700371 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Ramp L-WB to SR 51 over Ramp M (I-90 to WB I-80) | Lake | 0 |  | NHPP Interstate | 2020 | CN | 703756 | 633380.4 | 70375.6
444 | 1700371 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | Ramp L-WB to SR 51 over Ramp M (I-90 to WB I-80) | Lake | 0 |  | NHPP Interstate | Total |  | 762026 | 685823.4 | 76202.6
445 | 1700374 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SBL over CR 300N/Evans Rd., 0.56mi N of SR 2 | Porter | 0 |  | NHPP Non Interstate | 2018 | PE | 87400 | 69920 | 17480
446 | 1700374 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SBL over CR 300N/Evans Rd., 0.56mi N of SR 2 | Porter | 0 |  | NHPP Non Interstate | 2020 | CN | 1182370 | 945896 | 236474
447 | 1700374 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | SBL over CR 300N/Evans Rd., 0.56mi N of SR 2 | Porter | 0 |  | NHPP Non Interstate | Total |  | 1269770 | 1015816 | 253954
448 | 1700375 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NBL over CR 300N/Evans Rd., 0.56mi N of SR 2 | Porter | 0 |  | NHPP Non Interstate | 2018 | PE | 87400 | 69920 | 17480
449 | 1700375 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NBL over CR 300N/Evans Rd., 0.56mi N of SR 2 | Porter | 0 |  | NHPP Non Interstate | 2020 | CN | 1182370 | 945896 | 236474
450 | 1700375 | INDOT | SR 49 | District Bridge Project (Rehabilitation) | Bridge Deck Overlay | NBL over CR 300N/Evans Rd., 0.56mi N of SR 2 | Porter | 0 |  | NHPP Non Interstate | Total |  | 1269770 | 1015816 | 253954
451 | 1700376 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.21mi E of US 20 | Porter | 0 |  | NHPP Interstate | 2018 | PE | 8000 | 7200 | 800
452 | 1700376 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.21mi E of US 20 | Porter | 0 |  | NHPP Interstate | 2020 | CN | 93105 | 83794.5 | 9310.5
453 | 1700376 | INDOT | I 94 | District Small Structure Project | Small Structure Pipe Lining | 0.21mi E of US 20 | Porter | 0 |  | NHPP Interstate | Total |  | 101105 | 90994.5 | 10110.5
454 | 1700377 | INDOT | I 80 | District Small Structure Project | Small Structure Pipe Lining | 0.03mi E of SR 152 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 8300 | 7470 | 830
455 | 1700377 | INDOT | I 80 | District Small Structure Project | Small Structure Pipe Lining | 0.03mi E of SR 152 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 100371 | 90333.9 | 10037.1
456 | 1700377 | INDOT | I 80 | District Small Structure Project | Small Structure Pipe Lining | 0.03mi E of SR 152 | Lake | 0 |  | NHPP Interstate | Total |  | 108671 | 97803.9 | 10867.1
457 | 1700383 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 12 to SR 152 | Lake | 2.49 |  | STBG State | 2018 | PE | 70480 | 56384 | 14096
458 | 1700383 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 12 to SR 152 | Lake | 2.49 |  | STBG State | 2020 | CN | 738101 | 590480.8 | 147620.2
459 | 1700383 | INDOT | US 20 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 12 to SR 152 | Lake | 2.49 |  | STBG State | Total |  | 808581 | 646864.8 | 161716.2
460 | 1700385 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | I-80/94 WB over I-65 Ramp, 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | 2018 | PE | 30270 | 27243 | 3027
461 | 1700385 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | I-80/94 WB over I-65 Ramp, 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | 2020 | CN | 359245 | 323320.5 | 35924.5
462 | 1700385 | INDOT | I 80 | District Bridge Project (Rehabilitation) | Bridge Thin Deck Overlay | I-80/94 WB over I-65 Ramp, 1.18mi E of SR 53 | Lake | 0 |  | NHPP Interstate | Total |  | 389515 | 350563.5 | 38951.5
463 | 1700406 | INDOT | I 80 | Interchange Modifications (Lane Reconfig.) | Pavement Markings, Signage | I-80/94 at I-65 | Lake | 2.93 |  | NHPP-Interstate | 2018 | CN | 770000 | 616000 | 154000
464 | 1702393 | INDOT | Various | Statewide funding | ISP Patrols | Statewide | Statewide | 0 |  | STP | Various | N/A | 2000000 | 2000000 | 0 |  | A6
465 | 1702708 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 41 from 0.27 mi No of US 30 (Sauzer Pl.) to 0.90 mi N of US 30 (Willowbrook Pl.) | Lake | 0.63 |  | NHPP | 2018 | PE | 41000 | 32800 | 8200 |  | A6
466 | 1702708 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 41 from 0.27 mi No of US 30 (Sauzer Pl.) to 0.90 mi N of US 30 (Willowbrook Pl.) | Lake | 0.63 |  | NHPP | 2019 | UT | 18000 | 14400 | 3600
467 | 1702708 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 41 from 0.27 mi No of US 30 (Sauzer Pl.) to 0.90 mi N of US 30 (Willowbrook Pl.) | Lake | 0.63 |  | NHPP | 2019 | CN | 901000 | 720800 | 180200
468 | 1702708 | INDOT | US 41 | District Pavement Project (Non-I) | HMA Overlay, Preventive Maintenance | US 41 from 0.27 mi No of US 30 (Sauzer Pl.) to 0.90 mi N of US 30 (Willowbrook Pl.) | Lake | 0.63 |  | NHPP | 2019 | CE | 31000 | 24800 | 6200
469 | 1702743 | INDOT | I-65 | District Pavement Project (Interstate) | Concrete Pavement Restoration (CPR) | US 231 to US 30 | Lake | 5.73 |  | NHPP Interstate | 2018 | PE | 300000 | 270000 | 30000 |  | A6
470 | 1702743 | INDOT | I-65 | District Pavement Project (Interstate) | Concrete Pavement Restoration (CPR) | US 231 to US 30 | Lake | 5.73 |  | NHPP Interstate | 2018 | CN | 8025117 | 7222605 | 802512
471 | 1702276 | DNR |  | Rec. Trails Program | Rec. Trails Program | Inner- City East Chicago #17-005 | Lake |  |  | RTP | 2018 | PE | 20000 | 16000 | 4000 |  | A5
472 | 1702276 | DNR |  | Rec. Trails Program | Rec. Trails Program | Inner- City East Chicago #17-005 | Lake |  |  | RTP | 2019 | PE | 20000 | 16000 | 4000
473 | 1702276 | DNR |  | Rec. Trails Program | Rec. Trails Program | Inner- City East Chicago #17-005 | Lake |  |  | RTP | 2019 | RW | 25000 | 20000 | 5000
474 | 1702276 | DNR |  | Rec. Trails Program | Rec. Trails Program | Inner- City East Chicago #17-005 | Lake |  |  | RTP | 2019 | CN | 185000 | 148000 | 37000
475 | 1800173 | INDOT | Various | Bicycle-Pedestrian Facilities | ADA Curb Ramps | ADA Curb Ramps Along US 6 in Lake Station & US 30 in Dyer | Lake |  |  | NHPP Non Interstate | 2020 | ROW | 15000 | 12000 | 3000
476 | 1800173 | INDOT | Various | Bicycle-Pedestrian Facilities | ADA Curb Ramps | ADA Curb Ramps Along US 6 in Lake Station & US 30 in Dyer | Lake |  |  | NHPP Non Interstate | 2020 | RR | 20000 | 16000 | 4000
477 | 1800173 | INDOT | Various | Bicycle-Pedestrian Facilities | ADA Curb Ramps | ADA Curb Ramps Along US 6 in Lake Station & US 30 in Dyer | Lake |  |  | NHPP Non Interstate | 2021 | CN | 373681 | 298945 | 74736
478 | 1800173 | INDOT | Various | Bicycle-Pedestrian Facilities | ADA Curb Ramps | ADA Curb Ramps Along US 6 in Lake Station & US 30 in Dyer | Lake |  |  | NHPP Non Interstate | Total |  | 408681 | 326945 | 81736
479 | 1801093 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 8, Over Pitner Ditch, 2.24mi E of US 421 | LaPorte |  |  | STP | 2020 | CN | 52000 | 41600 | 10400
480 | 1801093 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 8, Over Pitner Ditch, 2.24mi E of US 421 | LaPorte |  |  | STP | 2019 | PE | 6240 | 4992 | 1248
481 | 1801093 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 8, Over Pitner Ditch, 2.24mi E of US 421 | LaPorte |  |  | STP | 2020 | UT | 20000 | 16000 | 4000
482 | 1801093 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 8, Over Pitner Ditch, 2.24mi E of US 421 | LaPorte |  |  | STP | Total |  | 78240 | 62592 | 15648
483 | 1801094 | INDOT | SR 53 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 53, Over Beaver Dam Ditch, 1.93mi N of US 231 | Lake |  |  | STP | 2020 | CN | 52000 | 41600 | 10400
484 | 1801094 | INDOT | SR 53 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 53, Over Beaver Dam Ditch, 1.93mi N of US 231 | Lake |  |  | STP | 2019 | PE | 6240 | 4992 | 1248
485 | 1801094 | INDOT | SR 53 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 53, Over Beaver Dam Ditch, 1.93mi N of US 231 | Lake |  |  | STP | 2020 | UT | 20000 | 16000 | 4000
486 | 1801094 | INDOT | SR 53 | Bridge Rehabilitation or Repair | Bridge Deck Sealing | SR 53, Over Beaver Dam Ditch, 1.93mi N of US 231 | Lake |  |  | STP | Total |  | 78240 | 62592 | 15648
487 | 1801096 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Thin Overlay | SR 8, Over Sandy Hook Ditch, 2.73mi W of SR 49 | Porter |  |  | STP | 2020 | CN | 110000 | 88000 | 22000
488 | 1801096 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Thin Overlay | SR 8, Over Sandy Hook Ditch, 2.73mi W of SR 49 | Porter |  |  | STP | 2019 | PE | 13200 | 10560 | 2640
489 | 1801096 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Thin Overlay | SR 8, Over Sandy Hook Ditch, 2.73mi W of SR 49 | Porter |  |  | STP | 2020 | UT | 20000 | 16000 | 4000
490 | 1801096 | INDOT | SR 8 | Bridge Rehabilitation or Repair | Bridge Deck Thin Overlay | SR 8, Over Sandy Hook Ditch, 2.73mi W of SR 49 | Porter |  |  | STP | Total |  | 143200 | 114560 | 28640
491 | 1801186 | INDOT | I 80 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 80, COLUMBIA AVENUE @. I-80/I-94, 177th St, 0.48mi E of US 41, Lake Co | Lake |  |  | STP | 2020 | CN | 110000 | 88000 | 22000
492 | 1801186 | INDOT | I 80 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 80, COLUMBIA AVENUE @. I-80/I-94, 177th St, 0.48mi E of US 41, Lake Co | Lake |  |  | STP | 2019 | PE | 13200 | 10560 | 2640
493 | 1801186 | INDOT | I 80 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 80, COLUMBIA AVENUE @. I-80/I-94, 177th St, 0.48mi E of US 41, Lake Co | Lake |  |  | STP | 2020 | UT | 20000 | 16000 | 4000
494 | 1801186 | INDOT | I 80 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 80, COLUMBIA AVENUE @. I-80/I-94, 177th St, 0.48mi E of US 41, Lake Co | Lake |  |  | STP | Total |  | 143200 | 114560 | 28640
495 | 1801188 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BROWN RD/CR 500E @. I-94 EB/WB, 4.59mi E of SR 49 | Porter |  |  | NHPP Interstate | 2020 | CN | 65000 | 58500 | 6500
496 | 1801188 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BROWN RD/CR 500E @. I-94 EB/WB, 4.59mi E of SR 49 | Porter |  |  | NHPP Interstate | 2019 | PE | 7800 | 7020 | 780
497 | 1801188 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BROWN RD/CR 500E @. I-94 EB/WB, 4.59mi E of SR 49 | Porter |  |  | NHPP Interstate | 2020 | UT | 20000 | 18000 | 2000
498 | 1801188 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BROWN RD/CR 500E @. I-94 EB/WB, 4.59mi E of SR 49 | Porter |  |  | NHPP Interstate | Total |  | 92800 | 83520 | 9280
499 | 1801189 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BLECK ROAD @. I-94 EB/WB, 3.77mi E of US 421 | LaPorte |  |  | NHPP Interstate | 2020 | CN | 72000 | 64800 | 7200
500 | 1801189 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BLECK ROAD @. I-94 EB/WB, 3.77mi E of US 421 | LaPorte |  |  | NHPP Interstate | 2019 | PE | 8640 | 7776 | 864
501 | 1801189 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BLECK ROAD @. I-94 EB/WB, 3.77mi E of US 421 | LaPorte |  |  | NHPP Interstate | 2020 | UT | 20000 | 18000 | 2000
502 | 1801189 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | Repair Or Replace Joints, I 94, BLECK ROAD @. I-94 EB/WB, 3.77mi E of US 421 | LaPorte |  |  | NHPP Interstate | Total |  | 100640 | 90576 | 10064
503 | 1801191 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 94, CR 800N @ I-94 EB/WB, 2.05mi E of US 20 | LaPorte |  |  | NHPP Interstate | 2020 | CN | 72000 | 64800 | 7200
504 | 1801191 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 94, CR 800N @ I-94 EB/WB, 2.05mi E of US 20 | LaPorte |  |  | NHPP Interstate | 2019 | PE | 8640 | 7776 | 864
505 | 1801191 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 94, CR 800N @ I-94 EB/WB, 2.05mi E of US 20 | LaPorte |  |  | NHPP Interstate | 2020 | UT | 20000 | 18000 | 2000
506 | 1801191 | INDOT | I 94 | Bridge Rehabilitation or Repair | Repair Or Replace Joints | I 94, CR 800N @ I-94 EB/WB, 2.05mi E of US 20 | LaPorte |  |  | NHPP Interstate | Total |  | 100640 | 90576 | 10064
507 | 1801212 | INDOT | I 80 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | I 80, Over I-80/I-94, 177th St, 0.48mi E of US 41 | Lake |  |  | NHPP Interstate | 2020 | CN | 285000 | 256500 | 28500
508 | 1801212 | INDOT | I 80 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | I 80, Over I-80/I-94, 177th St, 0.48mi E of US 41 | Lake |  |  | NHPP Interstate | 2019 | PE | 34200 | 30780 | 3420
509 | 1801212 | INDOT | I 80 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | I 80, Over I-80/I-94, 177th St, 0.48mi E of US 41 | Lake |  |  | NHPP Interstate | 2020 | UT | 20000 | 18000 | 2000
510 | 1801212 | INDOT | I 80 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | I 80, Over I-80/I-94, 177th St, 0.48mi E of US 41 | Lake |  |  | NHPP Interstate | Total |  | 339200 | 305280 | 33920
511 | 1801215 | INDOT | SR 912 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | SR 912, US 12 EB/SR 912@.-US 12 EB/US 20, 0.47mi E of I-90 | Lake |  |  | STP | 2020 | CN | 300000 | 240000 | 60000
512 | 1801215 | INDOT | SR 912 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | SR 912, US 12 EB/SR 912@.-US 12 EB/US 20, 0.47mi E of I-90 | Lake |  |  | STP | 2019 | PE | 36000 | 28800 | 7200
513 | 1801215 | INDOT | SR 912 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | SR 912, US 12 EB/SR 912@.-US 12 EB/US 20, 0.47mi E of I-90 | Lake |  |  | STP | 2020 | UT | 20000 | 16000 | 4000
514 | 1801215 | INDOT | SR 912 | Bridge Rehabilitation or Repair | Substructure Repair And Rehabilitation | SR 912, US 12 EB/SR 912@.-US 12 EB/US 20, 0.47mi E of I-90 | Lake |  |  | STP | Total |  | 356000 | 284800 | 71200
515 | 1801219 | INDOT | Various | Signal Project (New/Modernized) | Traffic Signals Modernization | Signals on SR2, SR4 and US35 in the City of LaPorte | LaPorte |  |  | NHPP | 2020 | CN | 1260000 | 1008000 | 252000
516 | 1801219 | INDOT | Various | Signal Project (New/Modernized) | Traffic Signals Modernization | Signals on SR2, SR4 and US35 in the City of LaPorte | LaPorte |  |  | NHPP | 2019 | PE | 40000 | 32000 | 8000
517 | 1801219 | INDOT | Various | Signal Project (New/Modernized) | Traffic Signals Modernization | Signals on SR2, SR4 and US35 in the City of LaPorte | LaPorte |  |  | NHPP | 2020 | UT | 15000 | 12000 | 3000
518 | 1801219 | INDOT | Various | Signal Project (New/Modernized) | Traffic Signals Modernization | Signals on SR2, SR4 and US35 in the City of LaPorte | LaPorte |  |  | NHPP | 2019 | RW | 30000 | 24000 | 6000
519 | 1801219 | INDOT | Various | Signal Project (New/Modernized) | Traffic Signals Modernization | Signals on SR2, SR4 and US35 in the City of LaPorte | LaPorte |  |  | NHPP | Total |  | 85000 | 68000 | 17000
|  | Subtotal INDOT-Sponsored Projects: | [10 empty] | 466795989 | 374401275 | 80828597
[7 empty] | Local Public Agency (LPA) Sponsored Projects: Lake & Porter Counties | [10 empty] | STBG | CMAQ | HSIP | TA |  |  | STBG | CMAQ | HSIP | TA | STBG | CMAQ | HSIP | TA | STBG | CMAQ | HSIP | TA | STBG | CMAQ | HSIP | TA | STBG | CMAQ | HSIP | TA
520 | 1601147 | Burns Harbor | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Marquette Greenway Trail, SR149 to Babcock Rd | Porter | 1.4 |  | CMAQ Chicago UZA | 2019 | RW | 0 | 0 | 0 | A10 | No ROW is needed
521 | 1601147 | Burns Harbor | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Marquette Greenway Trail, SR149 to Babcock Rd | Porter | 1.4 |  | CMAQ Chicago UZA | 2021 | CN | 1247418 | 997934.4 | 249483.6
522 | 1382594 | Cedar Lake | Lake Shore Drive | Local Safety Project | Intersect. Improvements (Roundabout) | at Cline Ave | Lake |  |  | STBG I Chicago UZA | 2018 | RW | 99225 | 79380 | 19845 | A2
523 | 1382594 | Cedar Lake | Lake Shore Drive | Local Safety Project | Intersect. Improvements (Roundabout) | at Cline Ave | Lake |  |  | STBG I Chicago UZA | 2019 | CN | 1875000 | 1500000 | 375000 | A4
524 | 1382594 | Cedar Lake | Lake Shore Drive | Local Safety Project | Intersect. Improvements (Roundabout) | at Cline Ave | Lake |  |  | STBG I Chicago UZA | 2019 | CE | 0 | 0 | 0
525 | 1382594 | Cedar Lake | Lake Shore Drive | Local Safety Project | Intersect. Improvements (Roundabout) | at Cline Ave | Lake |  |  | STBG I Chicago UZA | Total |  | 1974225 | 1579380 | 394845
526 | 1173427 | Crown Point | 101st Ave | Other Type Project (Miscellaneous) | Roadside Improvements (Drainage) | 101st Ave @ SR 53 | Lake | 0 |  | STBG I Chicago UZA | 2021 | RW | 250000 | 200000 | 50000
527 | 1401030 | Crown Point | 125th Ave | Local Road Project | Intersect. Improv. W/ Added Turn Lanes | From SR 55 to Court St | Lake | 0.75 |  | HSIP Chicago UZA | 2018 | PE | 25000 | 22500 | 2500 | A2
528 | 1401030 | Crown Point | 125th Ave | Local Road Project | Intersect. Improv. W/ Added Turn Lanes | From SR 55 to Court St | Lake | 0.75 |  | HSIP Chicago UZA | 2019 | CN | 1558940 | 1403046 | 155894
529 | 1401030 | Crown Point | 125th Ave | Local Road Project | Intersect. Improv. W/ Added Turn Lanes | From SR 55 to Court St | Lake | 0.75 |  | HSIP Chicago UZA | 2019 | CE | 0 | 0 | 0
530 | 1401030 | Crown Point | 125th Ave | Local Road Project | Intersect. Improv. W/ Added Turn Lanes | From SR 55 to Court St | Lake | 0.75 |  | HSIP Chicago UZA | Total |  | 1583940 | 1425546 | 158394
531 | 1500323 | Crown Point | US 231 | Local Safety Project | Other Intersection Improvement | Courthouse Square, construct pedestrian bump-outs | Lake |  |  | HSIP Chicago UZA | 2018 | RW | 0 | 0 | 0 | A10 | No ROW is needed
532 | 1500323 | Crown Point | US 231 | Local Safety Project | Other Intersection Improvement | Courthouse Square, construct pedestrian bump-outs | Lake |  |  | HSIP Chicago UZA | 2019 | CN | 484867 | 436380.3 | 48486.7
533 | 1500323 | Crown Point | US 231 | Local Safety Project | Other Intersection Improvement | Courthouse Square, construct pedestrian bump-outs | Lake |  |  | HSIP Chicago UZA | 2019 | CE | 0 | 0 | 0
534 | 1500323 | Crown Point | US 231 | Local Safety Project | Other Intersection Improvement | Courthouse Square, construct pedestrian bump-outs | Lake |  |  | HSIP Chicago UZA | Total |  | 484867 | 436380.3 | 48486.7
535 | 1601157 | Crown Point | 109th Ave | Road Reconstruction (3R/4R Standards) | Access Control | 109th Ave Access Control, Delaware Pkwy to SR 53, includes median construction | Lake | 0.29 |  | HSIP Chicago UZA | 2018 | PE | 40505 | 36454.5 | 4050.5 | AM 05/18
536 | 1601157 | Crown Point | 109th Ave | Road Reconstruction (3R/4R Standards) | Access Control | 109th Ave Access Control, Delaware Pkwy to SR 53, includes median construction | Lake | 0.29 |  | HSIP Chicago UZA | 2019 | RW | 112500 | 101250 | 11250 | AM 05/18
537 | 1601157 | Crown Point | 109th Ave | Road Reconstruction (3R/4R Standards) | Access Control | 109th Ave Access Control, Delaware Pkwy to SR 53, includes median construction | Lake | 0.29 |  | HSIP Chicago UZA | 2020 | CN | 1220000 | 1098000 | 122000 | AM 03/18 | AM 03/18; Move from FY 21 to FY 20
538 | 1601157 | Crown Point | 109th Ave | Road Reconstruction (3R/4R Standards) | Access Control | 109th Ave Access Control, Delaware Pkwy to SR 53, includes median construction | Lake | 0.29 |  | HSIP Chicago UZA | 2020 | CE | 0 | 0 | 0
539 | 1601157 | Crown Point | 109th Ave | Road Reconstruction (3R/4R Standards) | Access Control | 109th Ave Access Control, Delaware Pkwy to SR 53, includes median construction | Lake | 0.29 |  | HSIP Chicago UZA | Total |  | 1373005 | 1235704.5 | 137300.5
540 | 1601158 | Crown Point | 109th Ave | Local Safety Project | Intersect. Improvements (Roundabout) | at Iowa St | Lake | 0 |  | HSIP Chicago UZA | 2018 | PE | 295266.6667 | 265740 | 29526.6667
541 | 1601158 | Crown Point | 109th Ave | Local Safety Project | Intersect. Improvements (Roundabout) | at Iowa St | Lake | 0 |  | HSIP Chicago UZA | 2019 | RW | 125000 | 112500 | 12500
542 | 1601158 | Crown Point | 109th Ave | Local Safety Project | Intersect. Improvements (Roundabout) | at Iowa St | Lake | 0 |  | HSIP Chicago UZA | Total |  | 420266.6667 | 378240 | 42026.6667
543 | 0900064 | East Chicago | ST1001 | Local Road Project | Road Rehab (3R/4R Standards) | Indy Bld from McShane Dr to Michigan St | Lake | 2.3 |  | SMFR | 2019 | CN | 963509.13 | 770807.304 | 192701.826 | AM 03/18 | AM 03/18; Move from FY 19 to FY 20
544 | 0901321 | East Chicago | ST1001 | Local Road Project | Intersection Improvement | 129th & Dickey Rd., 129th & Broad St. | Lake | 0 |  | IEDC/BP | 2020 | CN | 2250000 | 1000000 | 1250000 | A10 | A10; not previously in FY 18-21 TIP
545 | 1601146 | East Chicago | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | from Indinapolis Blvd. (US 20) to Kennedy Ave | Lake | 0.7 |  | CMAQ Chicago UZA | 2018 | PE | 309800 | 247840 | 61960 | AM 03/18 | AM 03/18; change location, need CMAQ approval
546 | 1601146 | East Chicago | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | from Indinapolis Blvd. (US 20) to Kennedy Ave | Lake | 0.7 |  | CMAQ Chicago UZA | 2021 | RW | 0 | 0 | 0 | A10 | RW is not needed
547 | 1601146 | East Chicago | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | from Indinapolis Blvd. (US 20) to Kennedy Ave | Lake | 0.7 |  | CMAQ Chicago UZA | 2020 | CN | 1035000 | 828000 | 207000 | A10 | A10; not previously in FY 18-21 TIP; change location, need CMAQ approval
548 | 1601146 | East Chicago | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | from Indinapolis Blvd. (US 20) to Kennedy Ave | Lake | 0.7 |  | CMAQ Chicago UZA | 2020 | CE |  | 0 | 0
549 | 1601146 | East Chicago | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | from Indinapolis Blvd. (US 20) to Kennedy Ave | Lake | 0.7 |  | CMAQ Chicago UZA | Total |  | 1344800 | 1075840 | 268960
550 | 0710064 | Gary | 15th Ave | Local Signal Project | Signals, New or Upgraded | Multiple locations at/near intersection of 15th Ave and MLK Dr, | Lake | 0 |  | STBG I Chicago UZA | 2020 | RW | 200000 | 160000 | 40000
551 | 0710064 | Gary | 15th Ave | Local Signal Project | Signals, New or Upgraded | Multiple locations at/near intersection of 15th Ave and MLK Dr, | Lake | 0 |  | STBG I Chicago UZA | 2022 | CN | 896000 | 716800 | 179200
552 | 0710064 | Gary | 15th Ave | Local Signal Project | Signals, New or Upgraded | Multiple locations at/near intersection of 15th Ave and MLK Dr, | Lake | 0 |  | STBG I Chicago UZA | 2022 | CE | 0 | 0 | 0
553 | 0710064 | Gary | 15th Ave | Local Signal Project | Signals, New or Upgraded | Multiple locations at/near intersection of 15th Ave and MLK Dr, | Lake | 0 |  | STBG I Chicago UZA | Total |  | 1096000 | 876800 | 219200
554 | 1172078 | Gary | Ridge Rd | Local Road Project | Road Reconstruction (3R/4R Standards) | Ridge Road Reconstruction, Connecticut St to Mississippi St. Phase 2 | Lake | 0.89 |  | STBG I Chicago UZA | 2020 | CN | 6325000 | 5060000 | 1265000
555 | 1601165 | Gary |  | Local Safety Project | Regulatory & Warning Sign Replacement | City-wide | Lake | 0 |  | HSIP Chicago UZA | 2018 | PE | 68826 | 61943.4 | 6882.6
556 | 1601165 | Gary |  | Local Safety Project | Regulatory & Warning Sign Replacement | City-wide | Lake | 0 |  | HSIP Chicago UZA | 2020 | CN | 500000 | 450000 | 50000
557 | 1601165 | Gary |  | Local Safety Project | Regulatory & Warning Sign Replacement | City-wide | Lake | 0 |  | HSIP Chicago UZA | Total |  | 568826 | 511943.4 | 56882.6
558 | 1401032 | Gary / INDOT | SR 53 | Local Safety Project | Lighting & Signal Improvements | SR 53 Crosswalk & Lighting Improvements | Lake |  |  | HSIP Chicago UZA | 2018 | PE | 33400 | 33400 | 0
559 | 1702158 | Gary | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Gary Green Links/Marquette Trail. Roosevelt St to Polk St. | Lake | 0.8 |  | STBG I Chicago UZA | 2019 | RW | 25000 | 20000 | 5000 | A2
560 | 1702158 | Gary | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Gary Green Links/Marquette Trail. Roosevelt St to Polk St. | Lake | 0.8 |  | STBG I Chicago UZA | 2021 | CN | 1250000 | 1000000 | 250000 | A2
561 | 1702158 | Gary | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Gary Green Links/Marquette Trail. Roosevelt St to Polk St. | Lake | 0.8 |  | STBG I Chicago UZA | 2021 | CE | 0 | 0 | 0
562 | 1702158 | Gary | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Gary Green Links/Marquette Trail. Roosevelt St to Polk St. | Lake | 0.8 |  | STBG I Chicago UZA | Total |  | 1275000 | 1020000 | 255000
563 | 1600418 | Gary | Airport Rd | Local Road Project | Road Rehab (3R/4R Standards) | Airport Road 3R/4R Reconstruction: Cline Ave to EJ&E RR Bridge | Lake | 1.32 |  | STBG I Chicago UZA | 2019 | CN | 4375000 | 3500000 | 875000 | A2
564 | 1600632 | Gary PTC | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | Broadway Express Year #2 | Lake | 0 |  | CMAQ Chicago UZA | 2018 | Flex | 1230381.25 | 984305 | 246076.25
565 | 1600632 | Gary PTC | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | Broadway Express Year #3 | Lake | 0 |  | CMAQ Chicago UZA | 2019 | Flex | 1118527.5 | 894822 | 223705.5
566 | 1600632 | Gary PTC | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | Broadway Express | Lake | 0 |  | CMAQ Chicago UZA | Total |  | 2348908.75 | 1879127 | 469781.75
567 | 1500320 | Griffith |  | Local Safety Project | Sign Replacement - Multiple Types | City-wide | Lake | 0 |  | HSIP Chicago UZA | 2018 | CN | 302875 | 272587.5 | 30287.5 | A1
568 | 1500320 | Griffith |  | Local Safety Project | Sign Replacement - Multiple Types | City-wide | Lake | 0 |  | STBG I Chicago UZA | 2018 | CN | 52126 | 41700.8 | 10425.2 | A1
569 | 1500321 | Griffith | Main St | Local Safety Project | Flashing Beacon Installation | at E-L Trail Crossing | Lake | 0 |  | HSIP Chicago UZA | 2018 | CN | 103500 | 93150 | 10350 |  | LET 07/17
570 | 1382659 | Hammond | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Interstate Connector (Lake Michigan to IN/IL State Line | Lake | 0.5 |  | TAP Chicago UZA | 2018 | PE | 25000 | 20000 | 5000
571 | 1382659 | Hammond | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Interstate Connector (Lake Michigan to IN/IL State Line | Lake | 0.5 |  | TAP Chicago UZA | 2018 | CN | 260000 | 208000 | 52000
572 | 1382659 | Hammond | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | Interstate Connector (Lake Michigan to IN/IL State Line | Lake | 0.5 |  | TAP Chicago UZA | Total |  | 285000 | 228000 | 57000
573 | 1500221 | Hammond | Chicago Ave | Local Road Project | Added Travel Lanes | from IN/IL State Line to Marble St | Lake | 0.95 |  | STBG I Chicago UZA | 2020 | CN | 11750000 | 9400000 | 2350000 | RS/NE A4
574 | 1500416 | Hammond |  | Local Bridge Project | Bike/Pedestrian Bridge | over US 41 near Conkey St | Lake | 0 |  | TAP Chicago UZA | 2019 | CN | 5268000 | 2000000 | 3268000 |  | 632160
575 | 1500416 | Hammond |  | Local Bridge Project | Bike/Pedestrian Bridge | over US 41 near Conkey St | Lake | 0 |  | TAP Chicago UZA | 2019 | CE | 620000 | 494000 | 126000 | AM 9/17
576 | 1500416 | Hammond |  | Local Bridge Project | Bike/Pedestrian Bridge | over US 41 near Conkey St | Lake | 0 |  | TAP Chicago UZA | Total |  | 5888000 | 2494000 | 3394000
577 | 1601145 | Hammond | Marquette Trail | Local Other Type Project | Bike/Pedestrian Facilities | from State St at Rabin Plaza to Toll Road overpass at Kosciusko St | Lake | 2.11 |  | CMAQ Chicago UZA | 2021 | CN | 1500000 | 1200000 | 300000
578 | 1601163 | Hammond | 173rd Ave | Local Safety Project | Pedestrian Island Construction | at Main Entrance to Purdue NW Campus | Lake | 0 |  | STBG I Chicago UZA | 2019 | RW | 50000 | 40000 | 10000
| 1601163 | Hammond | 173rd Ave | Local Safety Project | Pedestrian Island Construction | at Main Entrance to Purdue NW Campus | Lake | 0 |  | STBG I Chicago UZA | 2020 | CN | 850000 | 680000 | 170000 | AM-6/18
1 | 1601163 | Hammond | 173rd Ave | Local Safety Project | Pedestrian Island Construction | at Main Entrance to Purdue NW Campus | Lake | 0 |  | STBG I Chicago UZA | 2020 | CE | 0 | 0 | 0 | AM-6/18
2 | 1601163 | Hammond | 173rd Ave | Local Safety Project | Pedestrian Island Construction | at Main Entrance to Purdue NW Campus | Lake | 0 |  | STBG I Chicago UZA | Total |  | 900000 | 720000 | 180000
3 | 1601164 | Hammond |  | Local Safety Project | Pedestrian Flashing Beacons, Installed | at 3 trail crossings | Lake | 0 |  | HSIP Chicago UZA | 2018 | CN | 241239 | 174951 | 66288 |  | Awarded amount - $194,390.29 NIRPC obligated $174,951.00 for CN & $18,039.00 for CE
4 | 1601164 | Hammond |  | Local Safety Project | Pedestrian Flashing Beacons, Installed | at 3 trail crossings | Lake | 0 |  | HSIP Chicago UZA | 2018 | CE | 20043 | 18038.7 | 2004.3
5 | 1601164 | Hammond |  | Local Safety Project | Pedestrian Flashing Beacons, Installed | at 3 trail crossings | Lake | 0 |  | HSIP Chicago UZA | Total |  | 261282 | 192989.7 | 68292.3
6 | 0710068 | Highland | 45th Ave | Local Road Project | Intersection Improvements | at 5th Ave | Lake | 0 |  | STBG I Chicago UZA | 2018 | CN | 1092000 | 502425 | 319200 |  | Awarded amount - $628,031.20 NIRPC obligated $502,425.00 for CN & $64,213.00 for CE
7 | 0710068 | Highland | 45th Ave | Local Road Project | Intersection Improvements | at 5th Ave | Lake | 0 |  | STBG I Chicago UZA | 2018 | CE | 80266 | 64212.8 | 16053.2
8 | 0710068 | Highland | 45th Ave | Local Road Project | Intersection Improvements | at 5th Ave | Lake | 0 |  | STBG I Chicago UZA | Total |  | 1172266 | 566637.8 | 335253.2
9 | 1500322 | Highland | 45th Ave | Local Safety Project | Pedestrian HAWK System, Installed | at E-L Trail Crossing | Lake | 0 |  | HSIP Chicago UZA | 2018 | CN | 123437 | 111093.3 | 12343.7
10 | 1592274 | Highland |  | Local Other Type Project | Signage on multiple trails, installed | Multiple Trails; Multiple LPA's | Lake | 0 | 2018-11-15 | TAP Chicago UZA | 2019 | CN | 1000000 | 800000 | 200000 | A4
11 | 1382598 | Hobart | County Line Rd | Local Road Project | Road Reconstruction (3R/4R Standards) | from US 6 to Cleveland Ave | Lake | 1 |  | STBG I Chicago UZA | 2020 | RW | 250000 | 200000 | 50000 | A2
12 | 1382598 | Hobart | County Line Rd | Local Road Project | Road Reconstruction (3R/4R Standards) | from US 6 to Cleveland Ave | Lake | 1 |  | STBG I Chicago UZA | 2021 | CN | 8596250 | 6877000 | 1719250 | A2
13 | 1382598 | Hobart | County Line Rd | Local Road Project | Road Reconstruction (3R/4R Standards) | from US 6 to Cleveland Ave | Lake | 1 |  | STBG I Chicago UZA | 2021 | CE |  | 0 | 0
14 | 1382598 | Hobart | County Line Rd | Local Road Project | Road Reconstruction (3R/4R Standards) | from US 6 to Cleveland Ave | Lake | 1 |  | STBG I Chicago UZA | Total |  | 8846250 | 7077000 | 1769250
15 | 1401034 | Hobart | Colorado St | Local Safety Project | Line of Sight Corrections; Access Management | North of US 30 | Lake | 0.25 |  | HSIP Chicago UZA | 2019 | RW | 62500 | 56250 | 6250 | A10 | A10; not previously in FY 18-21 TIP
16 | 1401034 | Hobart | Colorado St | Local Safety Project | Line of Sight Corrections; Access Management | North of US 30 | Lake | 0.25 |  | HSIP Chicago UZA | 2020 | CN | 816500 | 734850 | 81650 | AM 03/18 | AM 03/18; Move from FY 21 to FY 20
17 | 1401034 | Hobart | Colorado St | Local Safety Project | Line of Sight Corrections; Access Management | North of US 30 | Lake | 0.25 |  | HSIP Chicago UZA | 2020 | CE |  | 0 | 0
18 | 1401034 | Hobart | Colorado St | Local Safety Project | Line of Sight Corrections; Access Management | North of US 30 | Lake | 0.25 |  | HSIP Chicago UZA | Total |  | 879000 | 791100 | 87900
19 | 1500417 | Hobart |  | Local Other Type Project | Bicycle & Pedestrian Facilities | in vicinity of Hobart Middle School | Lake | 0.62 |  | TAP Chicago UZA | 2020 | CN | 309000 | 247200 | 61800 | AM 03/18 | AM 03/18; Move from FY 19 to FY 20
20 | 1592275 | Hobart |  | Local Other Type Project | Environmental Mitigation | Deep River Stormwater Outfall and BMP. | Lake |  |  | TAP Chicago UZA | 2018 | PE | 45000 | 36000 | 9000
21 | 1592275 | Hobart |  | Local Other Type Project | Environmental Mitigation | Deep River Stormwater Outfall and BMP. | Lake |  |  | TAP Chicago UZA | 2020 | CN | 308100 | 246480 | 61620
22 | 1592275 | Hobart |  | Local Other Type Project | Environmental Mitigation | Deep River Stormwater Outfall and BMP. | Lake |  |  | TAP Chicago UZA | 2020 | CE | 0 | 0 | 0
23 | 1592275 | Hobart |  | Local Other Type Project | Environmental Mitigation | Deep River Stormwater Outfall and BMP. | Lake |  |  | TAP Chicago UZA | Total |  | 353100 | 282480 | 70620
24 | 1601897 | Hobart |  | Local Safety Project | Road Safety Audits | Road Safety Audits | Lake |  |  | HSIP Chicago UZA | 2018 | PE | 60000 | 60000 | 0
25 | 1601161 | Kouts |  | Local Safety Project | Regulatory & Warning Sign Replacement | Town-wide | Porter |  |  | HSIP Chicago UZA | 2018 | PE | 20000 | 18000 | 2000
26 | 1601161 | Kouts |  | Local Safety Project | Regulatory & Warning Sign Replacement | Town-wide | Porter |  |  | HSIP Chicago UZA | 2019 | CN | 45000 | 40500 | 4500
27 | 1601161 | Kouts |  | Local Safety Project | Regulatory & Warning Sign Replacement | Town-wide | Porter |  |  | HSIP Chicago UZA | 2020 | CE | 0 | 0 | 0
28 | 1601161 | Kouts |  | Local Safety Project | Regulatory & Warning Sign Replacement | Town-wide | Porter |  |  | HSIP Chicago UZA | Total |  | 65000 | 58500 | 6500
29 | 1601162 | Kouts |  | Local Safety Project | Pavement Markings | Town-wide | Porter |  |  | HSIP Chicago UZA | 2018 | PE | 20000 | 18000 | 2000 | A1
30 | 1601162 | Kouts |  | Local Safety Project | Pavement Markings | Town-wide | Porter |  |  | HSIP Chicago UZA | 2019 | CN | 13000 | 11700 | 1300
31 | 1601162 | Kouts |  | Local Safety Project | Pavement Markings | Town-wide | Porter |  |  | HSIP Chicago UZA | 2020 | CE | 0 | 0 | 0
32 | 1601162 | Kouts |  | Local Safety Project | Pavement Markings | Town-wide | Porter |  |  | HSIP Chicago UZA | Total |  | 33000 | 29700 | 3300
33 | 0088990 | Lake County |  | Local Bridge Project | Bridge Rehabilitation Or Repair | Lake County Bridge #36 (State Line Road over Kankakee River) | Lake |  |  | INDOT BRIDGE | 2018 | CN | 875200 | 700160 | 175040
34 | 0088990 | Lake County |  | Local Bridge Project | Bridge Rehabilitation Or Repair | Lake County Bridge #36 (State Line Road over Kankakee River) | Lake |  |  | STBG I Chicago UZA | 2018 | CN | 1023750 | 819000 | 204750
35 | 0088990 | Lake County |  | Local Bridge Project | Bridge Rehabilitation Or Repair | Lake County Bridge #36 (State Line Road over Kankakee River) | Lake |  |  | STBG I Chicago UZA | 2020 | CE | 0 | 0 | 0
36 | 0088990 | Lake County |  | Local Bridge Project | Bridge Rehabilitation Or Repair | Lake County Bridge #36 (State Line Road over Kankakee River) | Lake |  |  | STBG I Chicago UZA | Total |  | 1898950 | 1519160 | 379790
37 | 1172007 | Lake County | 45th Ave | Local Road Project | Added Travel Lanes | 45th Ave. from Whitcomb to Chase (Ph 2B) | Lake | 1.5 |  | STBG I Chicago UZA | 2019 | CN | 1950000 | 1560000 | 390000 | RS/NE
38 | 1172007 | Lake County | 45th Ave | Local Road Project | Added Travel Lanes | 45th Ave. from Whitcomb to Chase (Ph 2B) | Lake | 1.5 |  | STBG I Chicago UZA | 2018 | RW LID | 625000 | 500000 | 125000 | RS/NE
39 | 1172007 | Lake County | 45th Ave | Local Road Project | Added Travel Lanes | 45th Ave. from Whitcomb to Chase (Ph 2B) | Lake | 1.5 |  | STBG I Chicago UZA | 2020 | CE | 243750 | 195000 | 48750
40 | 1172007 | Lake County | 45th Ave | Local Road Project | Added Travel Lanes | 45th Ave. from Whitcomb to Chase (Ph 2B) | Lake | 1.5 |  | STBG I Chicago UZA | Total |  | 2818750 | 2255000 | 563750
41 | 9707970 | Lake County | 45th Ave | Local Road Project | Intersect. Improv. W/ Added Turn Lanes | at Colfax St. | Lake |  |  | STBG I Chicago UZA | 2018 | CN | 527880 | 422304 | 105576 |  | 389052.47
42 | 1592160 | Lake County |  | Local bridge inspection | Bridge Inspections | countywide inventory program for 2018-2021 | Lake |  |  | Local Bridge | 2019 | PE | 215760 | 172608 | 43152
43 | 1592160 | Lake County |  | Local bridge inspection | Bridge Inspections | countywide inventory program for 2018-2021 | Lake |  |  | Local Bridge | 2020 | PE | 129240 | 103392 | 25848
44 | 1592160 | Lake County |  | Local bridge inspection | Bridge Inspections | countywide inventory program for 2018-2021 | Lake |  |  | Local Bridge | 2020 | PE | 224880 | 179904 | 44976
45 | 1592160 | Lake County |  | Local bridge inspection | Bridge Inspections | countywide inventory program for 2018-2021 | Lake |  |  | Local Bridge | Total |  | 569880 | 455904 | 113976
46 | 9980080 | Lake County | 45th Ave | Local Road Project | Added Travel Lanes | Colfax to Whitcomb St | Lake | 1.5 | 2020-07-08 | STBG I Chicago UZA | 2021 | CN | 9582000 | 7665600 | 1916400 | RS/NE A2
47 | 1400843 | Lake County | IR 1043 | Local Bridge Project | Bridge replacement | #61 135th Ave over West Creek | Lake | 0.5 |  | Local Bridge | 2018 | CN | 1177840 | 942272 | 235568
48 | 1601211 | Lake County |  | Local Other Type Project | Truck Stop Electrification. CMAQ Equipment. 3P Agreement | Flying J at I-65/SR 2. 3P Agreement | Lake |  |  | CMAQ Chicago UZA | 2018 | PE | 433732 | 329386 | 104346 |  | to be eliminated on A12
49 | 1601902 | Lake County |  | Local Safety Project | Safety Planning | Road Safety Audit (101st/Sheffield/109th Ave) | Lake |  |  | HSIP Chicago UZA | 2018 | PE | 0 | 0 | 0 | DELETED A2
50 | 1600930 | Lake County | 125th Ave | Local Bridge Project | Bridge Replacement | Bridge #65, 125th Ave over West Creek | Lake |  |  | State Bridge | 2018 | PE | 280933 | 224746.4 | 56186.6 | A2
51 | 1600930 | Lake County | 125th Ave | Local Bridge Project | Bridge Replacement | Bridge #65, 125th Ave over West Creek | Lake |  |  | State Bridge | 2019 | RW | 80000 | 64000 | 16000 | A2
52 | 1600930 | Lake County | 125th Ave | Local Bridge Project | Bridge Replacement | Bridge #65, 125th Ave over West Creek | Lake |  |  | State Bridge | Total |  | 360933 | 288746.4 | 72186.6
53 | 1702159 | Lake County | 101st Ave | Local Road Project | Signals, New or Improved | 101st Ave New Signals at Sheffield Ave. | Lake |  |  | STBG I Chicago UZA | 2018 | PE | 145000 | 116000 | 29000 | A2
54 | 1702159 | Lake County | 101st Ave | Local Road Project | Signals, New or Improved | 101st Ave New Signals at Sheffield Ave. | Lake |  |  | STBG I Chicago UZA | 2019 | RW | 25000 | 20000 | 5000 | A2
55 | 1702159 | Lake County | 101st Ave | Local Road Project | Signals, New or Improved | 101st Ave New Signals at Sheffield Ave. | Lake |  |  | STBG I Chicago UZA | 2020 | CN | 488750 | 391000 | 97750 | A2
56 | 1702159 | Lake County | 101st Ave | Local Road Project | Signals, New or Improved | 101st Ave New Signals at Sheffield Ave. | Lake |  |  | STBG I Chicago UZA | 202 | CE | 0 | 0 | 0
57 | 1702159 | Lake County | 101st Ave | Local Road Project | Signals, New or Improved | 101st Ave New Signals at Sheffield Ave. | Lake |  |  | STBG I Chicago UZA | Total |  | 658750 | 527000 | 131750
58 | 1601846 | Lake Station |  | Local Other Type Project | Alternative Fuel Infrastructure | Public Access E-85 & CNG Station. 3P Agreement. | Lake |  |  | CMAQ Chicago UZA | 2021 | PE | 1000641 | 600385 | 400256
59 | 1592273 | Lowell |  | Local Other Type Project | Bicycle & Pedestrian Equipment | Up to 20 Bicycle Racks | Lake |  |  | CMAQ Chicago UZA | 2019 | PE | 2000 | 1600 | 400 | A1 / AM-06/18
60 | 1006787 | Merrillville | Mississippi St | ATL | Added Travel Lanes | Mississippi St from 93rd to 101st Ave | Lake |  |  | STBG I Chicago UZA | 2020 | CN | 4515250 | 3612000 | 903250 | A10 | A10; not previously in FY 18-21 TIP
61 | 1592420 | Merrillville |  | Local Safety Project | Install Signal Pre-Emption Devices 1 & 2 | All signals in Hobart, Crown Point, Schererville, Merrillville, Highland | Lake |  |  | HSIP Chicago UZA | 2019 | CN | 3503813 | 3153432 | 350381
62 | 1592420 | Merrillville |  | Local Safety Project | Install Signal Pre-Emption Devices 2 | All Signals in Other Lake County LPA's) | Lake |  |  | HSIP Chicago UZA | 2021 | CN | 1130625 | 1017563 | 113062 | Deleted- AF combined with row 71 in FY 2019
63 | 0710056 | Munster | 45th St | New Road Construction | Railroad Grade Separation & Added Travel Lanes | Reconstruction of 45th St from 0.2 mi E of Calumet Ave to Calumet Ave | Lake |  |  | GROUP III | 2019 | CN | 9000000 | 7200000 | 1800000 | RS/NE AM-01/18 | Admin Mod; Jan 18
64 | 0710056 | Munster | 45th St | New Road Construction | Railroad Grade Separation & Added Travel Lanes | Reconstruction of 45th St from 0.2 mi E of Calumet Ave to Calumet Ave | Lake |  |  | PYB Chicago UZA | 2019 | CN | 8725805 | 6980644 | 1745161 | RS/NE AM-01/18 | Admin Mod; Jan 18
65 | 0710056 | Munster | 45th St | New Road Construction | Railroad Grade Separation & Added Travel Lanes | Reconstruction of 45th St from 0.2 mi E of Calumet Ave to Calumet Ave | Lake |  |  | STBG I Chicago UZA | 2019 | CN | 3917488 | 2619356 | 1298132 | RS/NE AM-03/18 | AM-3/18; moved from FY 18 to FY 19
66 | 0710056 | Munster | 45th St | New Road Construction | Railroad Grade Separation & Added Travel Lanes | Reconstruction of 45th St from 0.2 mi E of Calumet Ave to Calumet Ave | Lake |  |  | STBG I Chicago UZA | 202 | CE | 0 | 0 | 0
67 | 0710056 | Munster | 45th St | New Road Construction | Railroad Grade Separation & Added Travel Lanes | Reconstruction of 45th St from 0.2 mi E of Calumet Ave to Calumet Ave | Lake |  |  | STBG I Chicago UZA | Total |  | 21643293 | 16800000 | 4843293
68 | 1173597 | Munster | E-L/Pennsy Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | Bike/Ped Trail Connector: Erie-Lackawanna & Pennsy Greenway Trails at Cady Ditch and Marsh Ditch | Lake | 0.15 |  | TAP Chicago UZA | 2022 | CN | 0 | 0 | 0 | A10 | A10; moved from FY 19 to FY 22 (Total Costs $980,100)
69 | 1173707 | Munster | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Construct Pennsy Greenway Trail from Fisher St at Timrick Dr to Calumet Ave north of 45th St | Lake | 0.96 |  | CMAQ Chicago UZA | 2020 | CN | 693800 | 555040 | 138760
70 | 1600543 | NIRPC |  | Local Other Type Project | Purchase Alt Fuel | for Dunes Learning Center | Porter | 0 |  | CMAQ Chicago UZA | 2018 | UPWP | 50000 | 40000 | 10000
71 | 1600543 | NIRPC |  | Local Other Type Project | CMAQ Planning | Public Education SFY 2018 | Porter | 0 |  | CMAQ Chicago UZA | 2018 | UPWP | 450000 | 360000 | 90000
72 | 1600543 | NIRPC |  | Local Other Type Project | Regional Planning | Origin-Destination Study | Porter | 0 |  | STBG I Chicago UZA | 2018 | UPWP | 156250 | 125000 | 31250
73 | 1600543 | NIRPC |  | Local Other Type Project | Regional Planning | TIP Software License Fee | Porter | 0 |  | STBG I Chicago UZA | 2018 | UPWP | 45000 | 36000 | 9000
74 | 1600543 | NIRPC |  | Local Other Type Project | Regional Planning | TIP Software License Fee | Porter | 0 |  | STBG I Chicago UZA | Total |  | 701250 | 561000 | 140250
75 |  | NIRPC |  | Local Other Type Project | CMAQ Planning | Public Education SFY 2019 | Porter | 0 |  | CMAQ Chicago UZA | 2019 | UPWP | 450000 | 360000 | 90000 | A10 | Amend #10; Need Des #
76 |  | NIRPC |  | Local Other Type Project | CMAQ Planning | Public Education SFY 2020 | Porter | 0 |  | CMAQ Chicago UZA | 2020 | UPWP | 450000 | 360000 | 90000 | A10 | Amend #10; Need Des #
77 |  | NIRPC |  | Local Other Type Project | CMAQ Planning | Public Education SFY 2020 | Porter | 0 |  | CMAQ Chicago UZA | Total |  | 900000 | 720000 | 180000
78 | 0300602 | Portage | Iron Horse Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | Construct Trail from Hamstrom Rd to Portage Ave | Porter |  |  | CMAQ Chicago UZA | 2018 | CN | 205850 | 164680 | 41170
79 | 0600754 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) Env Mit. | Central Ave Reconstruction: Hamstrom Rd to I-80/90 (Toll Road) | Porter | 0.42 |  | STBG I Chicago UZA | 2018 | RW | 20000 | 16000 | 4000 | A2
80 | 0600754 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) | Central Ave Reconstruction: Hamstrom Rd to I-80/90 (Toll Road) | Porter | 0.42 |  | STBG I Chicago UZA | 2018 | CN | 5552361 | 4371154 | 1181207 | A2
81 | 0600754 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) | Central Ave Reconstruction: Hamstrom Rd to I-80/90 (Toll Road) | Porter | 0.42 |  | STBG I Chicago UZA | Total |  | 5572361 | 4387154 | 1185207
82 | 0900080 | Portage | Central Ave | Local Road Project | Access Control | Willowcreek Rd Intersection Improvements at Central Ave. | Porter | 0 | 2019-01-16 | CMAQ Chicago UZA | 2019 | CN | 1260410 | 1037000 | 223410 | AM-03/18 | AM-03/18; Move from FY 18 to Fy 19
83 | 0900080 | Portage | Central Ave | Local Road Project | Access Control | Willowcreek Rd Intersection Improvements at Central Ave. | Porter | 0 | 2019-01-16 | CMAQ Chicago UZA | 2019 | CE | 156294 | 115000 | 41294
84 | 0900080 | Portage | Central Ave | Local Road Project | Access Control | Willowcreek Rd Intersection Improvements at Central Ave. | Porter | 0 | 2019-01-16 | CMAQ Chicago UZA | Total |  | 1416704 | 1152000 | 264704
85 | 1173430 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) | Central Ave. reconstruction from Lake/Porter Co. Line to Willowcreek Road | Porter | 2.08 | 2020-07-08 | STBG I Chicago UZA | 2020 | RW | 750000 | 200000 | 550000 | AM-03/18 | AM-03/18; Moved from 2018 to 2020
86 | 1173430 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) | Central Ave. reconstruction from Lake/Porter Co. Line to Willowcreek Road | Porter | 2.08 | 2020-07-08 | STBG I Chicago UZA | 2021 | CN | 10223500 | 2080000 | 520000
87 | 1173430 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) | Central Ave. reconstruction from Lake/Porter Co. Line to Willowcreek Road | Porter | 2.08 | 2020-07-08 | STBG I Chicago UZA | 2021 | CE | 0 | 0 | 0
88 | 1173430 | Portage | Central Ave | Local Road Project | Road Reconstruction (3R/4R Standards) | Central Ave. reconstruction from Lake/Porter Co. Line to Willowcreek Road | Porter | 2.08 | 2020-07-08 | STBG I Chicago UZA | Total |  | 10973500 | 2280000 | 1070000
89 | 1382010 | Portage | Samuelson Road | Local Road Project | Road Reconstruction (3R/4R Standards) | Centeral Ave to Portage Ave | Porter | 0.41 |  | DEMO | 2022 | CN | 0 | 0 | 0 | A10 | A10; moved from 2019 to 2022 (Total costs $2,209,393)
90 | 1500418 | Portage | Marquette Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | Construct Marquette Greenway along Ameriplex Drive from SR 249 east to Salt Creek. | Porter | 2.05 | 2020-08-05 | TAP Chicago UZA | 2021 | CN | 1869450 | 1495560 | 373890
91 | 1601923 | Portage | Willowcreek Road | Local Bridge Project | Bridge Rehabilitation Or Repair | Rehabilitate Willowcreek Rd Bridge over I-80/90. | Porter | 0 |  | STBG I Chicago UZA | 2019 | CN | 800000 | 640000 | 160000
92 | 1383364 | Porter County | IR 1026 | Local Bridge Project | Bridge replacement | 1.6 miles south of CR 1000 S over Kankakee #62 | Porter | 0.19 | 2019-10-09 | Local Bridge | 2018 | ROW | 200000 | 160000 | 40000 |  | Admend #08
93 | 1383364 | Porter County | IR 1026 | Local Bridge Project | Bridge replacement | 1.6 miles south of CR 1000 S over Kankakee #62 | Porter | 0.19 | 2019-10-09 | Local Bridge | 2020 | CN | 1806400 | 1445120 | 361280 | AM-03/18 | AM-03/18; FY moved from FY 19 to FY 20
94 | 1383364 | Porter County | IR 1026 | Local Bridge Project | Bridge replacement | 1.6 miles south of CR 1000 S over Kankakee #62 | Porter | 0.19 |  | Local Bridge | Total |  | 2006400 | 1605120 | 401280
95 | 1401029 | Porter County | CR 100S | Local Road Project | Intersec. Improvement | CR 100S-2000 W of CR725 Wto 1000 E of CR 500W | Porter | 5 |  | GroupIV | 2019 | PE | 815000 | 652000 | 163000 | A10
96 | 1401029 | Porter County | CR 100S | Local Road Project | Intersec. Improvement | CR 100S-2000 W of CR725 Wto 1000 E of CR 500W | Porter | 5 |  | GroupIV | 2019 | RW | 668575 | 534860 | 133715 | AM-03/18 | AM-03/18; Moving from FY 18 to FY 19; 4/12/18 moved back to FY 18 and added
97 | 1401029 | Porter County | CR 100S | Local Road Project | Intersec. Improvement | CR 100S-2000 W of CR725 Wto 1000 E of CR 500W | Porter | 5 |  | GroupIV | 2020 | CN | 6100987.5 | 4880790 | 1220197.5 | AM-03/18 | AM-03/18; Moving from FY 19 to FY 20
98 | 1401029 | Porter County | CR 100S | Local Road Project | Intersec. Improvement | CR 100S-2000 W of CR725 Wto 1000 E of CR 500W | Porter | 5 |  |  | Total |  | 7584562.5 | 6067650 | 1516912.5
99 | 1592163 | Porter County | County wide Bridge inspection and Inventory | Local Road Project | Bridge inspection and inventory | County wide | Porter |  |  | State Bridge | 2018 | PE | 126960 | 101568 | 25392
100 | 1700500 | Porter County | Willowcreek Road | New Road Construction | Willowcreek Road Extension Corridor Study (with NEPA) | CR 700N to SR 130 | Porter | 4.7 |  | STBG I Chicago UZA | 2018 | PE | 310000 | 248000 | 62000 | NE/RS
101 | 1382092 | Porter County | County wide Bridge inspection and Inventory | Local Road Project | Bridge inspection and inventory | County wide | Porter |  |  | State Bridge | 2018 | PE | 15800 | 12640 | 3160
102 | 1592163 | Porter County | County wide Bridge inspection and Inventory | Local Road Project | Bridge inspection and inventory | County wide | Porter |  |  | State Bridge | 2019 | PE | 17040 | 13632 | 3408
103 | 1592163 | Porter County | County wide Bridge inspection and Inventory | Local Road Project | Bridge inspection and inventory | County wide | Porter |  |  | State Bridge | 2018 | PE | 126960 | 101568 | 25392
104 | 1592163 | Porter County | County wide Bridge inspection and Inventory | Local Road Project | Bridge inspection and inventory | County wide | Porter |  |  | State Bridge | Total |  | 144000 | 115200 | 28800
105 | 0401062 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway - Multiple Phases (Non-CN DES) | Lake |  |  | STBG I Chicago UZA | 2018 | PE | 80970 | 64776 | 16194 | A2; AM 4/18 | Admin Mod; Apr-18 adding $4,776 fed
106 | 0401062 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway - Multiple Phases (Non-CN DES) | Lake |  |  | STBG I Chicago UZA | 2019 | RR | 385000 | 308000 | 77000 | A2; AM 05/18
107 | 0401062 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway - Multiple Phases (Non-CN DES) | Lake |  |  | STBG I Chicago UZA | Total |  | 465970 | 372776 | 93194
108 | 1173595 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway P2. Main St to 137th Ave. | Lake | 1.5 |  | TAP Chicago UZA | 2019 | CN | 483752.5 | 387002 | 96750.5
109 | 1173595 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway P2. Main St to 137th Ave. | Lake | 1.5 |  | STBG I Chicago UZA | 2019 | CN | 1000000 | 800000 | 200000 | A2
110 | 1173595 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway P2. Main St to 137th Ave. | Lake | 1.5 |  | STBG I Chicago UZA | 2019 | CE | 0 | 0 | 0
111 | 1173595 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway P2. Main St to 137th Ave. | Lake | 1.5 |  | STBG I Chicago UZA | Total |  | 1483752.5 | 1187002 | 296750.5
112 | 1382661 | Schererville | Pennsy Greenway | Local Other Type Project | Bicycle & Pedestrian Facilities | Pennsy Greenway, P3 from Wilhelm Street at Schererville Town Hall to 213th Street | Lake | 1.79 |  | STBG I Chicago UZA | 2019 | CN | 1597500 | 1278000 | 319500 | A2
113 | 1173760 | Schererville | Kennedy Ave | Local Road Project | Added Travel Lanes | Kennedy Ave at Junction St. South to 67th St. and then South to US 30 | Lake | 0.83 |  | STBG I Chicago UZA | 2019 | RW | 250000 | 200000 | 50000 | RS/NE
114 | 1173760 | Schererville | Kennedy Ave | Local Road Project | Added Travel Lanes | Kennedy Ave at Junction St. South to 67th St. and then South to US 30 | Lake | 0.83 |  | STBG I Chicago UZA | 2020 | CN | 5258090 | 4206472 | 1051618 | RS/NE
115 | 1173760 | Schererville | Kennedy Ave | Local Road Project | Added Travel Lanes | Kennedy Ave at Junction St. South to 67th St. and then South to US 30 | Lake | 0.83 |  | STBG I Chicago UZA | 2019 | CE | 0 | 0 | 0
116 | 1173760 | Schererville | Kennedy Ave | Local Road Project | Added Travel Lanes | Kennedy Ave at Junction St. South to 67th St. and then South to US 30 | Lake | 0.83 |  | STBG I Chicago UZA | Total |  | 5508090 | 4406472 | 1101618
117 | 0900075 | Valparaiso | Silhavy Rd | Local Road Project | Road Reconstruction (3R/4R Standards) | Silhavy Rd (Evans Ave South to LaPorte Ave) | Porter | 0.63 | 2019-02-06 | STBG I Chicago UZA | 2018 | RW | 250000 | 200000 | 50000 | A2
118 | 0900075 | Valparaiso | Silhavy Rd | Local Road Project | Rebuild 3R/4R | Evans Ave to LaPorte Ave | Porter | 0.63 | 2019-02-06 | STBG I Chicago UZA | 2019 | CN | 3868220 | 3094576 | 773644 | A4
119 | 0900075 | Valparaiso | Silhavy Rd | Local Road Project | Rebuild 3R/4R | Evans Ave to LaPorte Ave | Porter | 0.63 | 2019-02-06 | STBG I Chicago UZA | 2019 | CE | 580230 | 464184 | 116046
120 | 0900075 | Valparaiso | Silhavy Rd | Local Road Project | Rebuild 3R/4R | Evans Ave to LaPorte Ave | Porter | 0.63 |  | STBG I Chicago UZA | Total |  | 4698450 | 3758760 | 939690
121 | 1298670 | Valparaiso | US 30 | Other Type Project (Miscellaneous) | Corridor Improvements | US 30 | Porter | 0 | 2019-01-16 | SMFR | 2019 | PE | 3470880 | 2776704 | 694176 | A10 | A10; not previously in FY 18-21 TIP
122 | 1298670 | Valparaiso | US 30 | Other Type Project (Miscellaneous) | Corridor Improvements | US 30 | Porter | 0 | 2019-01-16 | SMFR | 2020 | RW | 3643900 | 2915120 | 728780 | A10 | A10; not previously in FY 18-21 TIP
123 | 1298670 | Valparaiso | US 30 | Other Type Project (Miscellaneous) | Corridor Improvements | US 30 | Porter | 0 | 2019-01-16 | SMFR | 2021 | CN | 20400000 | 16320000 | 4080000 | A10 | A10; not previously in FY 18-21 TIP
124 | 1298670 | Valparaiso | US 30 | Other Type Project (Miscellaneous) | Corridor Improvements | US 30 | Porter | 0 |  | SMFR | Total |  | 27514780 | 22011824 | 5502956
125 | 1382601 | Valparaiso | Silhavy Rd | Local Intersection Improvement Project | Intersection Improvement, Roundabout | Silhavy Rd Roundabout at LaPorte Ave | Porter | 0 | 2018-04-11 | STBG I Chicago UZA | 2018 | CN | 4698118.7 | 3534186 | 1163932.7 | AM-03/18 | Added funds for construction (Total $175,000; $140,000 Federal) approved at 2/27/18 TROC
126 | 1382601 | Valparaiso | Silhavy Rd | Local Intersection Improvement Project | Intersection Improvement, Roundabout | Silhavy Rd Roundabout at LaPorte Ave | Porter | 0 | 2018-04-11 | STBG I Chicago UZA | 2018 | CE | 487800 | 390240 | 97560
127 | 1382601 | Valparaiso | Silhavy Rd | Local Intersection Improvement Project | Intersection Improvement, Roundabout | Silhavy Rd Roundabout at LaPorte Ave | Porter | 0 | 2018-04-11 | STBG I Chicago UZA | Total |  | 5185918.7 | 3924426 | 1261492.7
128 | 1401814 | Valparaiso | SP Bike | Local other Project | Bike/Pedestrian Facilities | US 30 shared use path, Hayes Leonard to Washington | Porter | 0 |  | SMFR | 2018 | CN | 3747951 | 2998360.8 | 749590.2 | A2
129 | 1401813 | Valparaiso | ST1001 | Local Road Project | Intersection improv. With new signals | US 30 intersection improvement, signals, lighting at Washington | Porter | 0 |  | SMFR | 2019 | CN | 3527050 | 2821640 | 705410 | AM-03/18 | AM-03/18; Moving from FY 18 to FY 19
130 | 1500421 | Valparaiso |  | Local Other Type Project | Bicycle & Pedestrian Facilities | Construct Sidewalks in vicinity of Northview Elementary School (TAP SRTS) | Porter | 0 | 2018-04-11 | TAP Chicago UZA | 2018 | CN | 449031.24 | 359224.992 | 89806.248 | A4; AM-03/18 | AM-03/18; Added funds ($80,000) for additional sidewalks in front of the school and for CE
131 | 1500421 | Valparaiso |  | Local Other Type Project | Bicycle & Pedestrian Facilities | Construct Sidewalks in vicinity of Northview Elementary School (TAP SRTS) | Porter | 0 | 2018-04-11 | TAP Chicago UZA | 2018 | CE | 53740 | 42992 | 10748
132 | 1500421 | Valparaiso |  | Local Other Type Project | Bicycle & Pedestrian Facilities | Construct Sidewalks in vicinity of Northview Elementary School (TAP SRTS) | Porter | 0 | 2018-04-11 | TAP Chicago UZA | Total |  | 502771.24 | 402216.992 | 100554.248
133 | 1601159 | Valparaiso | Ransom Rd | Local Safety Project | Other Type Project (Miscellaneous) | Ransom Road Safety Improvements, CR50W to CR 150W | Porter | 1 |  | HSIP Chicago UZA | 2019 | RW | 0 | 0 | 0 | A10 | No ROW is needed
134 | 1601159 | Valparaiso | Ransom Rd | Local Safety Project | Other Type Project (Miscellaneous) | Ransom Road Safety Improvements, CR50W to CR 150W | Porter | 1 |  | HSIP Chicago UZA | 2019 | CN | 529290 | 476361 | 52929 | AM-03/18 | Added funds for construction ($23,400 from ROW & $33,741) approved at 1/30/18 TROC
135 | 1601184 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | V-Line Porter Hospital (Year #1) | Porter | 0 |  | CMAQ Chicago UZA | 2018 | Flex | 425000 | 340000 | 85000
136 | 1601184 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | V-Line Porter Hospital (Year #2) | Porter | 0 |  | CMAQ Chicago UZA | 2019 | Flex | 416000 | 332800 | 83200 | A4
137 | 1601184 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | V-Line Porter Hospital (Year #3) | Porter | 0 |  | CMAQ Chicago UZA | 2020 | Flex | 408000 | 326400 | 81600 | A4
139 | 1601184 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | V-Line Porter Hospital | Porter | 0 |  | CMAQ Chicago UZA | Total |  | 1249000 | 999200 | 249800
138 | 1601185 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | CMAQ Demo Chicago DASH Bus #5 (Year #1) | Porter | 0 |  | CMAQ Chicago UZA | 2019 | Flex | 344000 | 275200 | 68800 | A4
140 | 1601185 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | CMAQ Demo Chicago DASH Bus #5 (Year #2) | Porter | 0 |  | CMAQ Chicago UZA | 2020 | Flex | 337000 | 269600 | 67400
141 | 1601185 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | CMAQ Demo Chicago DASH Bus #5 (Year #3) | Porter | 0 |  | CMAQ Chicago UZA | 2021 | Flex | 330000 | 264000 | 66000
142 | 1601185 | Valparaiso | FTA Transfers | Local Transit Projects | CMAQ Demo Operating Assistance | CMAQ Demo Chicago DASH Bus #5 | Porter | 0 |  | CMAQ Chicago UZA | Total |  | 1011000 | 808800 | 202200
143 | 1702150 | Valparaiso | US 30 | Other Type Project (Miscellaneous) | Landscaping | Sturdy Rd to Silhavy Rd | Porter | 0 | 2019-11-14 | SMFR | 2020 | CN | 2750000 | 2200000 | 550000 | A10
144 | 1702151 | Valparaiso | US 30 | Other Type Project (Miscellaneous) | Landscaping | Hayes Leonard Rd to Industrial Dr | Porter | 0 | 2019-01-16 | SMFR | 2019 | CN | 2859607.9 | 2287686.32 | 571921.58 | A10
145 | 1601726 | Winfield | Randolph St | Local Safety Project | Other Type Project (Miscellaneous) | Randolph St HAWK Signal | Lake | 0 |  | HSIP Chicago UZA | 2020 | CN | 78000 | 70200 | 7800
146 | 1601727 | Winfield | Randolph St | Local Safety Project | Other Type Project (Miscellaneous) | Randolph St School Zone Flashers | Lake | 0 |  | HSIP Chicago UZA | 2020 | CN | 10000 | 9000 | 1000
147 | 1601728 | Winfield | 109th Ave | Local Safety Project | Signage, New or Replacement | 109th Ave Signage Improvements | Lake | 0 |  | HSIP Chicago UZA | 2020 | CN | 6000 | 5400 | 600
Local Public Agency (LPA) Sponsored Projects: LaPorte County
148 | 1401028 | La Porte | Chessie Trail I | Local Other Type Project | Bicycle & Pedestrian Facilities | From Truesdell Ave NW to East Shore Pkwy at Pine Lake Ave | LaPorte |  | 2018-05-10 | CMAQ Mich City UZA | 2018 | PE | 18526 | 14820.8 | 3705.2 | AM 05/18
149 | 1401028 | La Porte | Chessie Trail I | Local Other Type Project | Bicycle & Pedestrian Facilities | From Truesdell Ave NW to East Shore Pkwy at Pine Lake Ave | LaPorte |  | 2018-05-10 | CMAQ Mich City UZA | 2018 | CN | 818515 | 654812 | 163703
150 | 1401028 | La Porte | Chessie Trail I | Local Other Type Project | Bicycle & Pedestrian Facilities | From Truesdell Ave NW to East Shore Pkwy at Pine Lake Ave | LaPorte |  | 2018-05-10 | DEMO | 2018 | CN | 341585 | 273268 | 68317
151 | 1401028 | La Porte | Chessie Trail I | Local Other Type Project | Bicycle & Pedestrian Facilities | From Truesdell Ave NW to East Shore Pkwy at Pine Lake Ave | LaPorte |  | 2018-05-10 | CMAQ Mich City UZA | 2018 | CE | 120000 | 96000 | 24000 | AM 05/18
152 | 1401028 | La Porte | Chessie Trail I | Local Other Type Project | Bicycle & Pedestrian Facilities | From Truesdell Ave NW to East Shore Pkwy at Pine Lake Ave | LaPorte |  |  |  | Total |  | 1160100 | 928080 | 232020
153 | 1500422 | La Porte | Sidewalks | Local Other Type Project | Bicycle & Pedestrian Facilities | SRTS near Handley Elementary School. | LaPorte |  | 2018-12-12 | FHWA TAP (LaPorte) | 2019 | CN | 242525 | 194020 | 48505 |  | A5 Change Letting Year
154 | 1700641 | La Porte |  | Local Transit Projects | Transit Capital Projects | Replace Two Revenue Vehicles | LaPorte |  |  | STBG II Mich City UZA | 2019 | Flex | 176000 | 140800 | 35200
155 | 1700642 | La Porte |  | Local Transit Projects | Transit Capital Projects | Replace Two Revenue Vehicles | LaPorte |  |  | STBG II Mich City UZA | 2020 | Flex | 176000 | 140800 | 35200
156 | 1700756 | La Porte |  | Bicycle-Pedestrian Project | Bike/Pedestrian Facilities | Construct Sidewalks at various locations in City of LaPorte. | LaPorte |  | 2019-09-25 | STBG II Mich City UZA | 2020 | CN | 150000 | 120000 | 30000 | AM 03/18 | AM 03/18; Move from FY 19 to FY 20
157 | 1700757 | La Porte |  | Bicycle-Pedestrian Project | Bike/Pedestrian Facilities | Construct Sidewalks at various locations in City of LaPorte. | LaPorte |  | 2020-03-19 | STBG II Mich City UZA | 2020 | CN | 150000 | 120000 | 30000
158 | 1700758 | La Porte |  | Local Road Project | Road Preventive Maintenance | At various locations in City of LaPorte. | LaPorte |  | 2019-09-25 | STBG II Mich City UZA | 2019 | CN | 125000 | 100000 | 25000
159 | 1700759 | La Porte |  | Local Road Project | Road Preventive Maintenance | At various locations in City of LaPorte. | LaPorte |  | 2020-02-18 | STBG II Mich City UZA | 2020 | CN | 125000 | 100000 | 25000
160 | 1700760 | La Porte |  | Local Road Project | Road Preventive Maintenance | At various locations in City of LaPorte. | LaPorte |  | 2021-01-13 | STBG II Mich City UZA | 2021 | CN | 250000 | 200000 | 50000
161 | 1601867 | La Porte | Chessie Trail II | Local Other Type Project | Bicycle & Pedestrian Facilities | from Pine Lake Ave Entrance to Newporte Landing SW to J Street at 1st St. | LaPorte |  |  | STBG II Mich City UZA | 2018 | PE | 300000 | 240000 | 60000 | AM 05/18
162 | 1601867 | La Porte | Chessie Trail II | Local Other Type Project | Bicycle & Pedestrian Facilities | from Pine Lake Ave Entrance to Newporte Landing SW to J Street at 1st St. | LaPorte |  |  | STBG II Mich City UZA | 2020 | RW | 200000 | 160000 | 40000
163 | 1601867 | La Porte | Chessie Trail II | Local Other Type Project | Bicycle & Pedestrian Facilities | from Pine Lake Ave Entrance to Newporte Landing SW to J Street at 1st St. | LaPorte |  |  | STBG II Mich City UZA | 2021 | CN | 1200000 | 960000 | 240000
164 | 1601867 | La Porte | Chessie Trail II | Local Other Type Project | Bicycle & Pedestrian Facilities | from Pine Lake Ave Entrance to Newporte Landing SW to J Street at 1st St. | LaPorte |  |  | STBG II Mich City UZA | 2021 | CE | 0 | 0 | 0
165 | 1601867 | La Porte | Chessie Trail II | Local Other Type Project | Bicycle & Pedestrian Facilities | from Pine Lake Ave Entrance to Newporte Landing SW to J Street at 1st St. | LaPorte |  |  | STBG II Mich City UZA | Total |  | 1700000 | 1360000 | 340000
166 | 1702262 | La Porte |  | Local Other Type Project | Signage | Sign Inventory | LaPorte |  |  | STBG II Mich City UZA | 2018 | PE | 92000 | 73600 | 18400 | A2
167 | 1702281 | La Porte | Michigan Ave | Local Road Project | Preventive Maintenance | Harrison to Kingsbury | LaPorte |  |  | STBG II Mich City UZA | 2018 | CN | 264797.9 | 211838.32 | 52959.58 | A2 | A5 Fix Corrected Award, AM 5/18 letting: CN $ 235,797.90 ($188, 638.32 fed) CE $29,000 ($23,200 fed)
168 | 1702282 | La Porte | Madison St | Local Road Project | Preventive Maintenance | SR 2 to Perry | LaPorte |  |  | STBG II Mich City UZA | 2018 | CN | 141127 | 112902 | 28225 | A5 / A10 | A5 Fix Corrected Award / A10 eliminated project
169 | 1500346 | LaPorte County |  | Bridge Inventory and Inspection | County wide Bridge Inspections and Inventory | Various bridges in the county | LaPorte |  |  | State Bridge | 2019 | PE | 147678 | 118142.4 | 29535.6
170 | 1382219 | LaPorte County | Johnson Rd | Local Road Project | Intersection improv. With new signals | Johnson Rd Int Imp @ CR 400 North (Keiffer Rd) | LaPorte |  |  | STBG II Mich City UZA | 2018 | RW | 370500 | 296400 | 74100
171 | 1382219 | LaPorte County | Johnson Rd | Local Road Project | Intersection improv. With new signals | Johnson Rd Int Imp @ CR 400 North (Keiffer Rd) | LaPorte |  |  | STBG II Mich City UZA | 2019 | CN | 1250000 | 1000000 | 250000 | AM 03/18 | AM 03/18; Move from FY 19 to FY 20
172 | 1382219 | LaPorte County | Johnson Rd | Local Road Project | Intersection improv. With new signals | Johnson Rd Int Imp @ CR 400 North (Keiffer Rd) | LaPorte |  |  | STBG II Mich City UZA | 2019 | CE | 0 | 0 | 0
173 | 1382219 | LaPorte County | Johnson Rd | Local Road Project | Intersection improv. With new signals | Johnson Rd Int Imp @ CR 400 North (Keiffer Rd) | LaPorte |  |  | STBG II Mich City UZA | Total |  | 1620500 | 1296400 | 324100
174 | 1382604 | LaPorte County | Lincoln Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | From US 421 W to Existing Lincoln Trail AND Sidewalks within Town of Westville | LaPorte |  |  | Demo IN047 | 2018 | RW | 92100 | 73680 | 18420 | A1
175 | 1382604 | LaPorte County | Lincoln Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | From US 421 W to Existing Lincoln Trail AND Sidewalks within Town of Westville | LaPorte |  |  | CMAQ Mich City UZA | 2018 | CN | 399996.25 | 319997 | 79999.25
176 | 1382604 | LaPorte County | Lincoln Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | From US 421 W to Existing Lincoln Trail AND Sidewalks within Town of Westville | LaPorte |  |  | CMAQ Mich City UZA | 2018 | CE | 0 | 0 | 0
177 | 1382604 | LaPorte County | Lincoln Trail | Local Other Type Project | Bicycle & Pedestrian Facilities | From US 421 W to Existing Lincoln Trail AND Sidewalks within Town of Westville | LaPorte |  |  | CMAQ Mich City UZA | Total |  | 492096.25 | 393677 | 98419.25
178 | 1383479 | LaPorte County | CR 875 W | Local Bridge Project | Bridge Replacement, Other Construction | LaPorte County Bridge #018 Located between CR 400 N and I-94. (Carries CR 875 W over tributary to Trail Creek) | LaPorte |  |  | Demo IN047 | 2018 | RW | 40000 | 32000 | 8000 | A1
179 | 1383479 | LaPorte County | CR 875 W | Local Bridge Project | Bridge Replacement, Other Construction | LaPorte County Bridge #018 Located between CR 400 N and I-94. (Carries CR 875 W over tributary to Trail Creek) | LaPorte |  |  | INDOT BRIDGE | 2018 | CN | 1180903.75 | 944723 | 236180.75
180 | 1383479 | LaPorte County | CR 875 W | Local Bridge Project | Bridge Replacement, Other Construction | LaPorte County Bridge #018 Located between CR 400 N and I-94. (Carries CR 875 W over tributary to Trail Creek) | LaPorte |  |  | Demo IN047 | 2018 | CN | 150000 | 120000 | 30000 | A1
181 | 1383479 | LaPorte County | CR 875 W | Local Bridge Project | Bridge Replacement, Other Construction | LaPorte County Bridge #018 Located between CR 400 N and I-94. (Carries CR 875 W over tributary to Trail Creek) | LaPorte |  |  |  | Total |  | 1370903.75 | 1096723 | 274180.75
182 | 1400774 | LaPorte County | Sidewalks | Local Other Type Project | Bicycle & Pedestrian Facilities | ADA Sidewalks in Union Mills, Hanna, & Rolling Prairie | LaPorte |  |  | TAP INDOT | 2018 | CN | 395000 | 316000 | 79000 |  | A5; increase funding $19,999 Total-$557,396; Fed-$465,916; Non Fed-$79,000 Awarded amount $336,595.51 (CN) & $50,000 (CE); ($269,276.40 CN & $40,000 Federal funds)($215,315.40 TA (section 133(h)) & $93,961.00 TAP Group II)
183 | 1400774 | LaPorte County | Sidewalks | Local Other Type Project | Bicycle & Pedestrian Facilities | ADA Sidewalks in Union Mills, Hanna, & Rolling Prairie | LaPorte |  |  | TAP Mich City UZA | 2018 | CN | 187395 | 149916 | 37479 | A2
184 | 1400774 | LaPorte County | Sidewalks | Local Other Type Project | Bicycle & Pedestrian Facilities | ADA Sidewalks in Union Mills, Hanna, & Rolling Prairie | LaPorte |  |  |  | Total |  | 582395 | 465916 | 116479
185 | 1401027 | LaPorte County | Ottis Rd | Local Bridge Project | Bridge Replacement | Ottis Bridge over the Little Calumet River | LaPorte |  |  | DEMO | 2020 | CN | 1125700.53 | 892600.42 | 233100.11 | A10
186 | 1592335 | LaPorte County | Marquette /Singing Sands Trail (LPCO) | Local Other Type Project | Bicycle & Pedestrian Facilities | Along US 12 from IN/MI State Line to Meer Rd | LaPorte |  |  | STBG II Mich City UZA | 2020 | CN | 956747.5 | 765398 | 191349.5
187 | 1592338 | LaPorte County | Other | Other Project Type | Planning Project | LaPorte Economic Development Corridor Project Phase I | LaPorte |  |  | STBG II Mich City UZA | PE | 2018 | 20000 | 16000 | 4000 | AM 05/18
188 | 1601868 | LaPorte County |  | Local Other Type Project | Signage, New or Replacement | Wayfinding Signage Purchase/Installation at Kingsbury Industrial Park | LaPorte |  |  | STBG II Mich City UZA | 2018 | PE | 40395 | 32316 | 8079 | AM 05/18
189 | 1601868 | LaPorte County |  | Local Other Type Project | Signage, New or Replacement | Wayfinding Signage Purchase/Installation at Kingsbury Industrial Park | LaPorte |  |  | STBG II Mich City UZA | 2019 | RW | 36575 | 29260 | 7315 | A2; AM 05/18
190 | 1601868 | LaPorte County |  | Local Other Type Project | Signage, New or Replacement | Wayfinding Signage Purchase/Installation at Kingsbury Industrial Park | LaPorte |  |  | STBG II Mich City UZA | 2018 | CN | 100000 | 80000 | 20000 | A2
191 | 1601868 | LaPorte County |  | Local Other Type Project | Signage, New or Replacement | Wayfinding Signage Purchase/Installation at Kingsbury Industrial Park | LaPorte |  |  | STBG II Mich City UZA | 2018 | CE | 0 | 0 | 0
192 | 1601868 | LaPorte County |  | Local Other Type Project | Signage, New or Replacement | Wayfinding Signage Purchase/Installation at Kingsbury Industrial Park | LaPorte |  |  | STBG II Mich City UZA | Total |  | 136575 | 109260 | 27315
193 | 0301165 | Michigan City | Singing Sands Trail I (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 1, Porter Co to MC | LaPorte |  |  | State STBG or TE | 2019 | CN | 2572500 | 2058000 | 514500 | AM 03/18 | AM 03/18; Move from FY 18 to FY 19
194 | 0301165 | Michigan City | Singing Sands Trail I (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 1, Rail Safety Component | LaPorte |  |  | Sec 130 | 2019 | CN | 558000 | 446400 | 111600 | AM 03/18 | AM 03/18; Move from FY 18 to FY 19
195 | 0301165 | Michigan City | Singing Sands Trail I (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 1, Rail Safety Component | LaPorte |  |  |  | Total |  | 3130500 | 2504400 | 626100
196 | 1500324 | Michigan City | Singing Sands Trail 2 (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 2, US 12 to Liberty Trail | LaPorte |  |  | STBG II Mich City UZA | 2019 | CN | 1605577.5 | 1284462 | 321115.5 | AM 03/18 | AM 03/18; Move from FY 18 to FY 19
197 | 1601869 | Michigan City | Singing Sands Trail 3 (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 3, Liberty Trail to Meer Rd | LaPorte |  |  | STBG II Mich City UZA | 2020 | PE | 93191 | 74553 | 18638 |  | A5; Add PE Phase
198 | 1601869 | Michigan City | Singing Sands Trail 3 (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 3, Liberty Trail to Meer Rd | LaPorte |  |  | STBG II Mich City UZA | 2021 | CN | 1014761.25 | 811809 | 202952.25
199 | 1601869 | Michigan City | Singing Sands Trail 3 (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 3, Liberty Trail to Meer Rd | LaPorte |  |  | STBG II Mich City UZA | 2021 | CE | 0 | 0 | 0
200 | 1601869 | Michigan City | Singing Sands Trail 3 (MC) | Local Other Type Project | Bike/Pedestrian Facilities | Michigan City - Singing Sands Lighthouse Trail Phase 3, Liberty Trail to Meer Rd | LaPorte |  |  | STBG II Mich City UZA | Total |  | 1107952.25 | 886362 | 221590.25
201 | 1601922 | LaCrosse | Sidewalks | Bicycle-Pedestrian Project | Bike/Pedestrian Facilities | Construct Sidewalks at various locations in City of LaPorte. | LaPorte |  |  | STBG II Mich City UZA | 2019 | CN | 125000 | 100000 | 25000 |  | A5; Increase Award $20,000
[5 empty] | Subtotal LPA-Sponsored Projects -- All Counties: | [7 empty] | 372344028.6733 | 278741447.548 | 77814831.1253
NATIONAL PARK SERVICE (NPS) Sponsored Projects (for Indiana Dunes National Lakeshore)
202 | NP-INDU-0014 | NPS-INDU | County Line Rd | NPS Safety Project | Intersection Improvements | Multiple Intersections | Lake | 0 | Safety Improvements | FLTP | 2019 | CN | 1200000 | 1200000 | 0 | from FHWA EFLD TIP (Oct 2016)
203 | NP-INDU-0945 | NPS-INDU | Lake St (Gary) | NPS Bicycle/Pedestrian Project | Pedestrian Bridge Replacement | Bridge to Paul Douglas Center | Lake | 0 | Pedestrian Bridge Replacement | FLTP | 2019 | CN | 1000000 | 1000000 | 0 | from FHWA EFLD TIP (Oct 2016)
| Subtotal National Park Service Projects: | [11 empty] | 2200000 | 2200000 | 0
Public Transit Projects
Chicago UZA
204 | 1382061 | East Chicago | FTA | Preventive Maint. |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 271330 | 217064 | 54266
205 | 1382062 | East Chicago | FTA | Comp. Paratransit |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 287500 | 229999.4534 | 57500.5466
206 | 1382963 | East Chicago | FTA | Replace 2-57 Passenger Vehicles | Replace 2-57 Passenger Vehicles | East Chicago | Lake |  |  | FTA Section 5339 | 2018 | Capital Equipment | 760000 | 646000 | 114000
207 | 1592020 | East Chicago | FTA | Operating Assistance |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 372874 | 186437 | 186437 | A12 | Increased Funds from $236,368
208 | 1592021 | East Chicago | FTA | Comp. Paratransit |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 343327 | 274661.6 | 68665.4 | A12 | Increased Funds from $210,408
209 | 1592022 | East Chicago | FTA | Replace Two Revenue Vehicles | Replace 2-57 passenger buses | East Chicago | Lake |  |  | FTA Section 5339 | 2018 | Capital Equipment | 760000 | 646000 | 114000
210 | 1592023 | East Chicago | FTA | Preventive Maint. |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 288933 | 231146.4 | 57786.6 | A12 | Increased funds from $271,330
211 | 1592079 | East Chicago | FTA | Preventive Maint. |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 288933 | 231146.4 | 57786.6 | A12 | Increased funds from $271,330
212 | 1592080 | East Chicago | FTA | Comp. Paratransit |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 343327 | 274661.6 | 68665.4 | A12 | Increased Funds from $210,408
213 | 1592081 | East Chicago | FTA | Operating Assistance |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 372874 | 186437 | 186437 | A12 | Increased Funds from $236,368
214 | 1592082 | East Chicago | FTA | Replace One Non-revenue Vehicle | Purchase Service Truck | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 60000 | 51000 | 9000
215 | 1592133 | East Chicago | FTA | Operating Assistance |  | East Chicago | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 168272 | 84136 | 84136
216 | 1382970 | GPTC | FTA | Automatic Passenger Counters | Moved from FY 2014 | Gary | Lake |  |  | FTA 5339 Chicago UA | 2018 | Capital Equipment | 200000 | 160000 | 40000
217 | 1382986 | GPTC | FTA | Preventive Maint. |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 4507185 | 3605748 | 901437
218 | 1382987 | GPTC | FTA | Comp. Paratransit |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 866553 | 693242 | 173311
219 | 1382988 | GPTC | FTA | FY 2017 Operating Assistance |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 1277294 | 638647 | 638647
220 | 1382989 | GPTC | FTA | Service Planning |  | Gary | Lake |  |  | FTA 5339 Chicago UA | 2018 | PL | 100000 | 80000 | 20000
221 | 1529029 | GPTC | FTA | Driver Training Infrastr. | Training Course and Simulator | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 245000 | 196000 | 49000
222 | 1592019 | GPTC | FTA | Comp. Paratransit |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 801250 | 641000 | 160250
223 | 1592024 | GPTC | FTA | Preventive Maint. |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 4507185 | 3605748 | 901437
224 | 1592025 | GPTC | FTA | FY 2018 Operating Assistance |  | Gary | Lake |  |  | FTA 5307 Chicago UZA | 2018 | Operating Subsidy | 1277294 | 638647 | 638647
225 | 1592026 | GPTC | FTA | Service Planning |  | Gary | Lake |  |  | FTA 5307 Chicago UZA | 2018 | PL | 100000 | 80000 | 20000
226 | 1592027 | GPTC | FTA | JARC Service |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 1451246 | 725623 | 725623
227 | 1592028 | GPTC | FTA | Fare Payment Kiosks |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 135000 | 108000 | 27000
228 | 1592030 | GPTC | FTA | Training Hardware and Software | Admin. and Human Capital Improvs. | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 2000 | 1600 | 400
229 | 1592031 | GPTC | FTA | Associated Transit | System-Wide Station Improvs. | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 62500 | 50000 | 12500
230 | 1592032 | GPTC | FTA | Fleet Managt. Software |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 75000 | 60000 | 15000
231 | 1592039 | GPTC | FTA | Replace Three Revenue Vehicles | Replace #7001-7003 | Gary | Lake |  |  | FTA Chicago UA | 2018 | Capital Equipment | 1200000 | 1020000 | 180000
232 | 1592075 | GPTC | FTA | Replace One revenue Vehicle | Replace 1 35' Vehicle No. 9706 | Gary | Lake |  |  | FTA 5339 Chicago UA | 2018 | Capital Equipment | 1200000 | 1020000 | 180000
233 | 1592076 | GPTC | FTA | Replace Six Revenue Vehicles | Replace 6 Accessible Vans for Comp. Paratransit Service | Gary | Lake |  |  | FTA 5339 Chicago UA | 2018 | Capital Equipment | 540000 | 459000 | 81000
234 | 1592083 | GPTC | FTA | Preventive Maint. |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 4507185 | 3605748 | 901437
235 | 1592084 | GPTC | FTA | FY 2019 Operating Assistance |  | Gary | Lake |  |  | FTA 5307 Chicago UZA | 2019 | Operating Subsidy | 1277294 | 638647 | 638647
236 | 1592085 | GPTC | FTA | FY 2019 ADA Comp. Paratransit |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 801250 | 641000 | 160250
237 | 1592086 | GPTC | FTA | Service Planning |  | Gary | Lake |  |  | FTA 5307 Chicago UZA | 2019 | PL | 100000 | 80000 | 20000
238 | 1592087 | GPTC | FTA | JARC Service |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 1451246 | 725623 | 725623
239 | 1592088 | GPTC | FTA | Associated Transit | System-Wide Station Improvs. | Gary | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 62500 | 50000 | 12500
240 | 1592089 | GPTC | FTA | ADA Call Tracking Software |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 35000 | 28000 | 7000
241 | 1592090 | GPTC | FTA | Replace Revenue Vehicles | Replace #7004-7006 | Gary | Lake |  |  | FTA Chicago UA | 2019 | Capital Equipment | 1200000 | 1020000 | 180000
242 | 1592134 | GPTC | FTA | Replace Maint. Equip. Part 1 | Replace Maint. Equip. Part 2 | Gary | Lake |  |  | FTA 5339 Chicago UA | 2018 | Capital Equipment | 573750 | 459000 | 114750
243 | 1592135 | GPTC | FTA | Replace Maint. Facility Lighting | Replace Maint. Facility Lighting | Gary | Lake |  |  | FTA 5339 Chicago UA | 2018 | Capital Equipment | 75000 | 60000 | 15000
244 | 1600629 | GPTC | FTA | Operating Assistance |  | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 150000 | 120000 | 30000 | A12 | In 2016 TIP, not in current TIP
245 | 1593038 | GPTC | FTA | Replace Maint. Equip. Part 1 | Heating and Exhaust System Repairs, Replace Hoists and Floor Drains | Gary | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 126250 | 101000 | 25250
246 | 1600629 | GPTC | FTA | Expansion Vehicles |  | Gary | Lake |  |  | FHWA STBG | 2018 | Capital Equipment | 150000 | 120000 | 30000 |  | A12
247 | 1600632 | GPTC | FTA | Transit Operating Grants | Broadway BRT (Year 1 Part 3 of 3) | Gary | Lake |  | FTA | FHWA CMAQ (Lake Porter) | 2018 | Operating Subsidy | 1291900 | 1033520 | 258380 |  | A12
248 | 1700715 | GPTC | FTA | Transit Operating Grants | Lake Ridge Pilot Service (Year #4) Extension of FFY 2012 Funded Project | Gary | Lake |  | FTA | FHWA CMAQ (Lake Porter) | 2018 | Operating Subsidy | 625000 | 500000 | 125000
249 | 1592040 | NICTD | FTA | Local Transit Projects | Maintenance Overhaul |  | Multiple |  |  | FTA 5307 Chicago UZA | 2018 | PL | 5281263 | 4225010 | 1056253 |  | A7; Add Project
250 | 1383005 | NIRPC | FTA | Subgrantee Grant Admin. |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UZA | 2018 | PL | 327025 | 261620 | 65405
251 | 1383006 | NIRPC | FTA | MPO Planning |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UZA | 2018 | PL | 100000 | 80000 | 20000
252 | 1592041 | NIRPC | FTA | MPO Planning |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UZA | 2018 | PL | 176000 | 140800 | 35200
253 | 1592042 | NIRPC | FTA | Subgrantee Grant Admin. |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UZA | 2018 | PL | 327025 | 261620 | 65405
254 | 1592092 | NIRPC | FTA | MPO Planning |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UZA | 2019 | PL | 176000 | 140800 | 35200
255 | 1592093 | NIRPC | FTA | Subgrantee Grant Admin. |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UZA | 2019 | PL | 327025 | 261620 | 65405
256 | 1592094 | NIRPC | FTA | Replace computers and Related Equipment |  | Region-wide | Multiple |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 100000 | 80000 | 20000
257 | 1700528 | NICTD | FTA | Local Transit Projects | West Lake Project Development |  | Lake |  |  | N/A | 2018 | PE | 20000000 | 0 | 20000000 | RS
258 | 1700529 | NICTD | FTA | Local Transit Projects | Double Track Gary to Michigan City Project Development |  | Multiple |  |  | N/A | 2018 | PE | 4000000 | 0 | 4000000 | RS
259 | 1700530 | NICTD | FTA | Local Transit Projects | PTC Implementation |  | Multiple |  |  | N/A | 2018 | CN | 25000000 | 0 | 25000000
260 | 1700531 | NICTD | FTA | Local Transit Projects | Maintenance Overhaul |  | Multiple |  |  | FTA 5307 Chicago UA | 2018 |  | 4953825 | 3963060 | 990765
261 | 1700532 | NICTD | FTA | Local Transit Projects | South Bend Station Relocation Study |  | St Joseph |  |  | SOGR | 2018 | PL | 1000000 | 800000 | 200000
262 | 1700533 | NICTD | FTA | Local Transit Projects | Add Track 7 - Millennium Station | Chicago, IL | Cook |  |  | SOGR | 2018 | PE | 2630122.5 | 2104098 | 526024.5
263 | 1700534 | NICTD | FTA | Local Transit Projects | Positive Train Control |  | Multiple |  |  | SOGR | 2018 | PE | 1500000 | 1200000 | 300000
264 | 1700535 | NICTD | FTA | Local Transit Projects | Mid-Life - 2000 Cars |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 500000 | 400000 | 100000
265 | 1700536 | NICTD | FTA | Local Transit Projects | End of Life - 1982 Cars |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 1017500 | 814000 | 203500
266 | 1700537 | NICTD | FTA | Local Transit Projects | Catenary Replacement |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 2000000 | 1600000 | 400000
267 | 1700538 | NICTD | FTA | Local Transit Projects | Substation Improvements |  | Multiple |  |  | SOGR | 2018 | CN | 1500000 | 1200000 | 300000
268 | 1700539 | NICTD | FTA | Local Transit Projects | Bridge Rehabilitation |  | Multiple |  |  | SOGR | 2018 | CN | 1500000 | 1200000 | 300000
269 | 1700540 | NICTD | FTA | Local Transit Projects | Replacement Rail |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 700000 | 560000 | 140000
270 | 1700541 | NICTD | FTA | Local Transit Projects | Mtce./Supv./Police Vehicles |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 500000 | 400000 | 100000
271 | 1700542 | NICTD | FTA | Local Transit Projects | Track Equipment |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 600000 | 480000 | 120000
272 | 1700543 | NICTD | FTA | Local Transit Projects | Hammond MOW and Parking |  | Multiple |  |  | SOGR | 2018 | CN | 1625000 | 1300000 | 325000
273 | 1700544 | NICTD | FTA | Local Transit Projects | Station Improvements |  | Multiple |  |  | SOGR | 2018 | CN | 1325000 | 1060000 | 265000
274 | 1700545 | NICTD | FTA | Local Transit Projects | Shop Equipment |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 250000 | 200000 | 50000
275 | 1700546 | NICTD | FTA | Local Transit Projects | Track Improvements |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 2300000 | 1840000 | 460000
276 | 1700547 | NICTD | FTA | Local Transit Projects | Control Center Contingency Plan |  | Multiple |  |  | SOGR | 2018 | PL | 250000 | 200000 | 50000
277 | 1700548 | NICTD | FTA | Local Transit Projects | Pines Yard PE |  | Multiple |  |  | SOGR | 2018 | PE | 375000 | 300000 | 75000
278 | 1700549 | NICTD | FTA | Local Transit Projects | New Roof - Mechanical Shop |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 1000000 | 800000 | 200000
279 | 1700550 | NICTD | FTA | Local Transit Projects | Computer Facilities |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 325000 | 260000 | 65000
280 | 1700551 | NICTD | FTA | Local Transit Projects | Replace Public Address Systems |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 250000 | 200000 | 50000
281 | 1700552 | NICTD | FTA | Local Transit Projects | Replace Dispatcher Communication System |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 500000 | 400000 | 100000
282 | 1700553 | NICTD | FTA | Local Transit Projects | PE - Voice Radio System Upgrade |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 175000 | 140000 | 35000
283 | 1700556 | NICTD | FTA | Local Transit Projects | West Lake PE/Real Estate Acquisition |  | Multiple |  |  | New Start | 2018 | RW | 4620000 | 2310000 | 2310000 | RS / A12 | Change funding type
284 | 1700557 | NICTD | FTA | Local Transit Projects | 2nd Track Gary to Michigan City Eng./Real Estate Acq. |  | Multiple |  |  | Core Capacity | 2018 | RW | 30800000 | 15400000 | 15400000 | RS / A12 | Change funding type
285 | 1700558 | NICTD | FTA | Local Transit Projects | South Bend Realignment NEPA/Final Engineering |  | Multiple |  |  | TIGER | 2018 | PE | 5000000 | 2500000 | 2500000 | A12 | Change funding type
286 | 1700559 | NICTD | FTA | Local Transit Projects | PTC Implementation |  | Multiple |  |  | N/A | 2018 | CN | 25000000 | 0 | 25000000
287 | 1700560 | NICTD | FTA | Local Transit Projects | Add Track 7 - Millenium Station |  | Multiple |  |  | SOGR | 2018 | CN | 4696575 | 3757260 | 939315
288 | 1700561 | NICTD | FTA | Local Transit Projects | Positive Train Control |  | Multiple |  |  | SOGR | 2018 | CN | 1500000 | 1200000 | 300000
289 | 1700562 | NICTD | FTA | Local Transit Projects | Mid-Life - 2000 Cars |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 500000 | 400000 | 100000
290 | 1700563 | NICTD | FTA | Local Transit Projects | End of Life - 1982 Cars |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 1500000 | 1200000 | 300000
291 | 1700564 | NICTD | FTA | Local Transit Projects | Catenary/Signal Improvements |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 2100000 | 1680000 | 420000
292 | 1700565 | NICTD | FTA | Local Transit Projects | Substation Improvements |  | Multiple |  |  | SOGR | 2018 | CN | 2000000 | 1600000 | 400000
293 | 1700566 | NICTD | FTA | Local Transit Projects | Bridge Rehabilitation |  | Multiple |  |  | SOGR | 2018 | CN | 1850000 | 1480000 | 370000 | A12 | Increased funds from $1,500,000
294 | 1700567 | NICTD | FTA | Local Transit Projects | Replacement Rail |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 750000 | 600000 | 150000
295 | 1700568 | NICTD | FTA | Local Transit Projects | Mtce./Supv./Police Vehicles |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 550000 | 440000 | 110000
296 | 1700569 | NICTD | FTA | Local Transit Projects | Track Equipment |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 650000 | 520000 | 130000
297 | 1700570 | NICTD | FTA | Local Transit Projects | Station Improvements |  | Multiple |  |  | SOGR | 2018 | CN | 1750000 | 1400000 | 350000 | A12 | Decreased funds from $2,100,000
298 | 1700571 | NICTD | FTA | Local Transit Projects | Train Control Improvements |  | Multiple |  |  | SOGR | 2018 | Capital Equipment | 412500 | 330000 | 82500
299 | 1700572 | NICTD | FTA | Local Transit Projects | New Line and Signal Building |  | Multiple |  |  | SOGR | 2018 | CN | 2500000 | 2000000 | 500000
300 | 1700573 | NICTD | FTA | Local Transit Projects | Replacement Lighting - Shops Yards |  | Multiple |  |  | SOGR | 2018 | CN | 1500000 | 1200000 | 300000
301 | 1700574 | NICTD | FTA | Local Transit Projects | West Lake Project Engineering/Real Estate Acquisition |  | Multiple |  |  | New Start | 2019 | RW | 252300000 | 126150000 | 126150000 | RS / A12 | Increased funds from $91,190,000
302 | 1700575 | NICTD | FTA | Local Transit Projects | 2nd Track Gary - Michigan City Real Estate Acq./Const. |  | Multiple |  |  | Core Capacity | 2019 | RW | 143500000 | 71750000 | 71750000 | RS / A12 | Increased funds from $110,000
303 | 1700576 | NICTD | FTA | Local Transit Projects | S. Bend Realignment Real Estate Acq./Construction |  | Multiple |  |  | TIGER | 2019 | RW | 5000000 | 2500000 | 2500000
304 | 1700579 | NICTD | FTA | Local Transit Projects | PTC Implementation |  | Multiple |  |  | N/A | 2019 | CN | 25000000 | 0 | 25000000
305 | 1700580 | NICTD | FTA | Local Transit Projects | Positive Train Control |  | Multiple |  |  | SOGR | 2019 | CN | 1250000 | 1000000 | 250000
306 | 1700581 | NICTD | FTA | Local Transit Projects | Mid-Life - 2000 Cars |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 625000 | 500000 | 125000
307 | 1700582 | NICTD | FTA | Local Transit Projects | End of Life - 1982 Cars |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 2375000 | 1900000 | 475000
308 | 1700583 | NICTD | FTA | Local Transit Projects | Catenary/Signal Improvements |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 2100000 | 1680000 | 420000
309 | 1700584 | NICTD | FTA | Local Transit Projects | Substation Improvements |  | Multiple |  |  | SOGR | 2019 | CN | 2000000 | 1600000 | 400000
310 | 1700585 | NICTD | FTA | Local Transit Projects | Bridge Rehabilitation |  | Multiple |  |  | SOGR | 2019 | CN | 1625000 | 1300000 | 325000
311 | 1700586 | NICTD | FTA | Local Transit Projects | Replacement Rail |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 750000 | 600000 | 150000
312 | 1700588 | NICTD | FTA | Local Transit Projects | Mtce./Supv./Police Vehicles |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 550000 | 440000 | 110000
313 | 1700589 | NICTD | FTA | Local Transit Projects | Track Equipment |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 650000 | 520000 | 130000
314 | 1700590 | NICTD | FTA | Local Transit Projects | Station Improvements |  | Multiple |  |  | SOGR | 2019 | CN | 6079256.25 | 4863405 | 1215851.25 | A12 | Delete project
315 | 1700591 | NICTD | FTA | Local Transit Projects | Add Track 7 - Millenium Station |  | Multiple |  |  | SOGR | 2019 | CN | 8779256 | 7023404.8 | 1755851.2 | A12 | Increased funds from $2,700,000
316 | 1700592 | NICTD | FTA | Local Transit Projects | Inward Facing Cameras |  | Multiple |  |  | SOGR | 2019 | Capital Equipment | 2000000 | 1600000 | 400000
317 | 1700593 | NICTD | FTA | Local Transit Projects | West Lake Project Construction |  | Lake |  |  | New Start | 2020 | CN | 230700000 | 115350000 | 115350000 | RS / A12 | Decreased funds from $231,920,000
318 | 1700594 | NICTD | FTA | Local Transit Projects | Double Track Gary to Michigan City Construction |  | Multiple |  |  | Core Capacity | 2020 | CN | 134400000 | 67200000 | 67200000 | RS / A12 | Increased funds from $120,000,000
319 | 1700595 | NICTD | FTA | Local Transit Projects | South Bend Realignment Construction |  | Multiple |  |  | TIGER | 2020 | CN | 15000000 | 7500000 | 7500000 | A12 | Increased funds from $10,000,000
320 | 1700596 | NICTD | FTA | Local Transit Projects | Rolling Stock Acquisition |  | Multiple |  |  | N/A | 2020 | Capital Equipment | 5000000 | 0 | 5000000 | A12 | Delete project
321 | 1700597 | NICTD | FTA | Local Transit Projects | Mid-Life - 2000 Cars |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 1172000 | 937600 | 234400 | A12 | Increased funds from $625,000
322 | 1700598 | NICTD | FTA | Local Transit Projects | End of Life - 1982 Cars |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 5028000 | 4022400 | 1005600 | A12 | Increased funds from $2,375,000
323 | 1700599 | NICTD | FTA | Local Transit Projects | Catenary/Signal Improvements |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 2100000 | 1680000 | 420000
324 | 1700600 | NICTD | FTA | Local Transit Projects | Substation Improvements |  | Multiple |  |  | SOGR | 2020 | CN | 2000000 | 1600000 | 400000
325 | 1700601 | NICTD | FTA | Local Transit Projects | Bridge Rehabilitation |  | Multiple |  |  | SOGR | 2020 | CN | 1625000 | 1300000 | 325000
326 | 1700602 | NICTD | FTA | Local Transit Projects | Replacement Rail |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 1033342 | 826673.6 | 206668.4 | A12 | Increased funds from $750,000
327 | 1700603 | NICTD | FTA | Local Transit Projects | Mtce./Supv./Police Vehicles |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 550000 | 440000 | 110000
328 | 1700604 | NICTD | FTA | Local Transit Projects | Track Equipment |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 650000 | 520000 | 130000
329 | 1700605 | NICTD | FTA | Local Transit Projects | Station Improvements |  | Multiple |  |  | SOGR | 2020 | CN | 1000000 | 800000 | 200000 | A12 | Decreased funds from $1,283,341
330 | 1700606 | NICTD | FTA | Local Transit Projects | Rolling Stock Acquisition |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 8000000 | 6400000 | 1600000 | A12 | Decreased funds from $10,000,000
331 | 1700607 | NICTD | FTA | Local Transit Projects | Inward Facing Cameras |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 0 | 0 | 0 | A12 | Delete project
332 | 1700619 | NICTD | FTA | Local Transit Projects | Mechanical Components |  | Multiple |  |  | SOGR | 2020 | Capital Equipment | 1200000 | 960000 | 240000 | A12 | Delete project
333 | 1700620 | NICTD | FTA | Local Transit Projects | Double Tracking - Gary to Michigan City |  | Multiple |  |  | Core Capacity | 2021 | CN | 500000 | 250000 | 250000 | RS / A12 | Decreased funds from $36,000,000
334 | 1700621 | NICTD | FTA | Local Transit Projects | West Lake Service |  | Multiple |  |  | New Start | 2021 | CN | 112600000 | 56300000 | 56300000 | RS / A12 | Decreased funds from $210,920,000
335 | 1700622 | NICTD | FTA | Local Transit Projects | Rolling Stock Acquisition |  | Multiple |  |  | N/A | 2021 | Capital Equipment | 5000000 | 0 | 5000000 | A12 | Delete project
336 | 1700623 | NICTD | FTA | Local Transit Projects | Mid-Life - 2000 Cars |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 1179500 | 943600 | 235900 | A12 | Increased funds from $625,000
337 | 1700624 | NICTD | FTA | Local Transit Projects | End of Life - 1982 Cars |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 5195500 | 4156400 | 1039100 | A12 | Increased funds from $2,500,000
338 | 1700626 | NICTD | FTA | Local Transit Projects | Catenary/Signal Improvements |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 2100000 | 1680000 | 420000
339 | 1700627 | NICTD | FTA | Local Transit Projects | Substation Improvements |  | Multiple |  |  | SOGR | 2021 | CN | 2000000 | 1600000 | 400000
340 | 1700630 | NICTD | FTA | Local Transit Projects | Bridge Rehabilitation |  | Multiple |  |  | SOGR | 2021 | CN | 1625000 | 1300000 | 325000
341 | 1700631 | NICTD | FTA | Local Transit Projects | Replacement Rail |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 1000000 | 800000 | 200000
342 | 1700632 | NICTD | FTA | Local Transit Projects | Mtce./Supv./Police Vehicles |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 562500 | 450000 | 112500
343 | 1700633 | NICTD | FTA | Local Transit Projects | Track Equipment |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 675000 | 540000 | 135000
344 | 1700634 | NICTD | FTA | Local Transit Projects | Station Improvements |  | Multiple |  |  | SOGR | 2021 | CN | 1284008 | 1027206 | 256802
345 | 1700635 | NICTD | FTA | Local Transit Projects | Rolling Stock Acquisition |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 8000000 | 6400000 | 1600000 | AM04/18 | Decreased funds from $10,000,000
346 | 1700636 | NICTD | FTA | Local Transit Projects | Mechanical Components |  | Multiple |  |  | SOGR | 2021 | Capital Equipment | 1250000 | 1000000 | 250000 | A12 | Delete project
347 | 1801484 | NICTD | FTA | Local Transit Projects |  |  | Multiple |  |  | FTA 5307 Chicago UA | 2019 |  | 5153750 | 4123000 | 1030750 | A12 | New Project
348 | 1383013 | North Township | FTA | Preventive Maint. |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 37500 | 30000 | 7500
349 | 1383014 | North Township | FTA | Route Match | Participant in Regional Dispatch. | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 12500 | 10000 | 2500
350 | 1383015 | North Township | FTA | Replace one vehicle | Replace One Revenue Vehicle (DAR 16) | Lake County | Lake |  |  | STP Transfer | 2018 | Capital Equipment | 72480.0064 | 57984.0051 | 14496.0013
351 | 1592018 | North Township | FTA | Expanded Demand Response | Year 5 | Lake County | Lake |  |  | CMAQ | 2019 | Operating Subsidy | 600000 | 480000 | 120000
352 | 1592043 | North Township | FTA | Preventive Maint. |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 35000 | 28000 | 7000 | AM04/18 | Decreased funds from $57,288
353 | 1592044 | North Township | FTA | Route Match | Participant in Regional Dispatch. | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 13500 | 10800 | 2700 | AM06/18 | Increased amount from $13,500
354 | 1592045 | North Township | FTA | Replace One Revenue Vehicle (DAR 17) |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 70500 | 56400 | 14100 | A12 | Decreased funds from $135,000
355 | 1592095 | North Township | FTA | Preventive Maint. |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 35000 | 28000 | 7000 | A12 | Decreased funds from $59,000
356 | 1592096 | North Township | FTA | Route Match | Participant in Regional Dispatch | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 14500 | 11600 | 2900
357 | 1592097 | North Township | FTA | Replace One Revenue Vehicle (DAR 18) |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 74025 | 59220 | 14805 | A12 | Decreased funds from $141,000
358 | 1592098 | North Township | FTA | Replace 9 Tablets | Includes Vehicle Securement Devices | Lake County | Lake |  |  | FTA Chicago UZA | 2021 | Capital Equipment | 4500 | 3600 | 900 | A12 | Moved years from 2019
359 | 1592099 | North Township | FTA | Replace Office Computer Equipment |  | Lake County | Lake |  |  | FTA Chicago UA | 2019 | Capital Equipment | 3500 | 2800 | 700
360 | 1592136 | North Township | FTA | Facility Improvs. |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Associated Transit Improvements | 10000 | 8000 | 2000
361 | 1701045 | North Township | FTA | Operating Assistance |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 350000 | 175000 | 175000 | A12 | Increased funds from $230,000
362 | 1801485 | North Township | FTA | Operating Assistance |  | Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 380000 | 190000 | 190000 | A12; AM 06/18 | New Project; Change Year
363 | 1383019 | OE | FTA | Preventive Maint. |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 155000 | 124000.2411 | 30999.7589
364 | 1383020 | OE | FTA | Replace 3 Revenue Vehicles | Replace 3 Revenue Vehicles | Porter County | Porter |  |  | STP Transfer | 2018 | Capital Equipment | 238241.7811 | 190593.4249 | 47648.3562
365 | 1592046 | OE | FTA | Preventive Maint. |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 132459 | 105972 | 26487
366 | 1592047 | OE | FTA | Replace 2 Revenue Vehicles |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 148568 | 126283 | 22285 | AM 06/18 | Changed fund type from FTA to 5307
367 | 1592100 | OE | FTA | Preventive Maint. |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 139431 | 111545 | 27886
368 | 1592101 | OE | FTA | Replace 2 Revenue Vehicles |  | Porter County | Porter |  |  | FTA Chicago UA | 2019 | Capital Equipment | 198000 | 158400 | 39600 | AM04/18 | Increased funds from $153,025
369 | 1801486 | OE | FTA | Computer Equipment |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2019 | Computer Equipment | 6500 | 5200 | 1300 | A12 | New Project
370 | 0183030 | PCACS | FTA | Operating Assistance |  | Porter County | Porter |  |  | FTA Chicago UA | 2018 | Operating Subsidy | 165872 | 82936 | 82936
371 | 1383027 | PCACS | FTA | Preventive Maint. |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 95000 | 76000 | 19000
372 | 1383029 | PCACS | FTA | Route Match | Participant in Regional Dispatch | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 12281 | 9825 | 2456
373 | 1592017 | PCACS | FTA | FTA 5310 Operating Assistance | Extended Hours & Days of Service for persons with disabilities (Porter County). Year #7 | Porter County | Porter |  |  | FTA 5310 Chicago UA | 2018 | Operating Subsidy | 165872 | 82936 | 82936
374 | 1592048 | PCACS | FTA | Replace Two Revenue Vehicles | Replace #70 and #719 | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 155000 | 131750 | 23250
375 | 1592049 | PCACS | FTA | Preventive Maint. |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 174000 | 139200 | 34800
376 | 1592050 | PCACS | FTA | Route Match | Participant in Regional Dispatch | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 16151 | 12920.8 | 3230.2 | AM 06/18 | Change fund type from 5307 & add $476.00
377 | 1592102 | PCACS | FTA | Replace Three Revenue Vehicles | Replace #65,66 and 67 | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 210000 | 178500 | 31500
378 | 1592104 | PCACS | FTA | Preventive Maint. |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 180000 | 144000 | 36000
379 | 1592105 | PCACS | FTA | Route Match | Participant in Regional Dispatch | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 14000 | 11200 | 2800
380 | 1592131 | PCACS | FTA | FTA 5310 Operating Assistance | Extended Hours & Days of Service for persons with disabilities (Porter County). Year #8 | Porter County | Porter |  |  | FTA 5310 Chicago UA | 2019 | Operating Subsidy | 165872 | 82936 | 82936
381 | 1701046 | PCACS | FTA | Operating Assistance |  | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 280000 | 140000 | 140000
382 | 1801487 | PCACS | FTA | Replace Two Revenue Vehicles | Replace Two Revenue Vehicles | Porter County | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 127000 | 107950 | 19050 | A12 | New Project
383 | 1383036 | SLCCS | FTA | Replace Two Revenue Vehicles | Replace Two Revenue Vehicles | Porter County | Porter |  |  | STP Transfer | 2018 | Capital Equipment | 139328.8739 | 111463.0991 | 27865.7748
384 | 1383037 | SLCCS | FTA | Route Match |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 24781 | 19824.8 | 4956.2
385 | 1383039 | SLCCS | FTA | Preventive Maint. |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 115000 | 91999.8944 | 23000.1056
386 | 1383039 | SLCCS | FTA | Preventive Maint. |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 435633 | 348506 | 87127
387 | 1383040 | SLCCS | FTA | Replace 2 Revenue Vehicles | Replace #934 and 935 | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 154350 | 131198 | 23152
388 | 1383042 | SLCCS | FTA | Route Match Maint. | Annual Licensing for Route Match | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 36340 | 29072 | 7268 | AM06/18 | Increased funds from $27,259
389 | 1383043 | SLCCS | FTA | Operating Assistance |  | South Lake County | Lake |  |  | FTA 5310 Chicago UA | 2018 | Operating Subsidy | 250000 | 125000 | 125000
390 | 1592051 | SLCCS | FTA | Route Match | Replace Tablets for 17 Vehicles | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 30000 | 24000 | 6000 | A12 | Delete project
391 | 1592077 | SLCCS | FTA Transfer | FTA 5310 Operating Assistance | For expanded services with ARC of NW In. | South Lake County | Lake |  |  | FTA 5310 Chicago UA | 2018 | Operating Subsidy | 250000 | 125000 | 125000
392 | 1592106 | SLCCS | FTA | Preventive Maint. |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 214200 | 118999.9881 | 95200.0119 | A12 | Decrease funds from $435,633; split project with 1801488
393 | 1592107 | SLCCS | FTA | Route Match | Annual Licensing for Route Match | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 29482 | 23585.6 | 5896.4 | A12 | Increase funds from $27,259
394 | 1592108 | SLCCS | FTA | Replace Ten Revenue Vehicles | Replace 436-439, and 540-545 | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 700000 | 595000 | 105000 | A12 | Decreased funds /scope (from 10 buses to 4)
395 | 1592130 | SLCCS | FTA | FTA 5310 Operating Assistance | For expanded services with ARC NW In. | South Lake County | Lake |  |  | FTA 5310 Chicago UA | 2019 | Operating Subsidy | 250000 | 125000 | 125000
396 | 1701047 | SLCCS | FTA | Operating Assistance |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 286000 | 143000 | 143000 | A12 | Increase funds from $275,000
397 | 1801488 | SLCCS | FTA | Operating Assistance |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 243700 | 194960 | 48740 | A12; AM 06/18 | Add project; split from 1592106; Change Year
398 | 1801489 | SLCCS | FTA | Replace five computers |  | South Lake County | Lake |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 6000 | 4800 | 1200 | A12 | Add project
399 | 1383048 | Valparaiso | FTA | Capital Cost of Contract | V-Line | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 280670 | 224536 | 56134
400 | 1383049 | Valparaiso | FTA | Capital Cost of Contract | ChicaGo Dash | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 469585 | 375668 | 93917
401 | 1383050 | Valparaiso | FTA | Assoc. Transit Improvs. |  | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 125000 | 100000 | 25000 | A12 | Change Year
402 | 1592053 | Valparaiso | FTA | Capital Cost of Contract | V-Line | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 453175 | 377646 | 75529 | A12 | Cost increase from $314,705 (TC)
403 | 1592055 | Valparaiso | FTA | Capital Cost of Contract | ChicaGo Dash | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2018 | Operating Subsidy | 483673 | 386938 | 96735
404 | 1592056 | Valparaiso | FTA | Assoc. Transit ImprovS. | Improve Grounds at TOD | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | CN | 275000 | 120000 | 155000 | A12 | Change Year; Added funds
405 | 1592057 | Valparaiso |  | Replace 2 Revenue Vehicles | Replace 2 Revenue Vehicles | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 165031.3992 | 132025.1194 | 33006.2798
406 | 1592057 | Valparaiso | FTA | Replace 2 Revenue Vehicles | Replace VL 11 and VL 12 | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2018 | Capital Equipment | 220000 | 176000 | 44000
407 | 1592109 | Valparaiso | FTA | Capital Cost of Contract | V-Line | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 486220 | 388976 | 97244
408 | 1592110 | Valparaiso | FTA | Capital Cost of Contract | ChicaGo Dash | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | Operating Subsidy | 748275 | 598620 | 149655
409 | 1592111 | Valparaiso | FTA | Replace 3 Revenue Vehicles | Replace VL 13, VL 14 and VL 15 | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 345000 | 276000 | 69000
410 | 1592112 | Valparaiso | FTA | Assoc. Transit Improvs. | Replace Bus Stop Signs for V-Line Service | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 150000 | 120000 | 30000
411 | 1592114 | Valparaiso | FTA | Replace 1 ChicaGo Dash Bus | Replace 1 53-passenger commuter bus DA 1002 | Valparaiso | Porter |  |  | FTA 5307 Chicago UA | 2019 | Capital Equipment | 750000 | 637500 | 112500
Michigan City/LaPorte UZA
412 | 1382997 | LaPorte (City) | FTA | Operating Assistance |  | LaPorte (City) | LaPorte |  |  | FTA 5307 Mich City UA | 2018 | OA | 631537 | 276207 | 355330
413 | 1700716 | LaPorte (City) | FTA | Transit Grants | Transit Capital Grants | PU Truck | LaPorte |  | STP II | FTA | 2018 |  | 55000 | 44000 | 11000
414 | 1700797 | LaPorte (City) | FTA | Transit Grants | Transit Capital Grants | TransPorte Building Improvements | LaPorte |  | STP II | FTA | 2018 |  | 24000 | 19200 | 4800
415 | 1700798 | LaPorte (City) | FTA | Transit Grants | Transit Capital Grants | TransPorte Computers | LaPorte |  | STP II | FTA | 2018 |  | 11000 | 8800 | 2200
416 | 1700799 | LaPorte (City) | FTA | Transit Grants | Transit Capital Grants | TransPorte Building Office Furnishings | LaPorte |  | STP II | FTA | 2018 |  | 400 | 320 | 80
417 | 1383001 | MC Transit | FTA | Operating Assistance |  | Michigan City | LaPorte |  |  | FTA | 2018 |  | 1450896 | 667412 | 783484
418 | 1592117 | MC Transit | FTA | Local Transit Projects | Operating Assistance | Michigan City | LaPorte |  |  | FTA 5307 Mich City UA | 2018 | OA | 1686748 | 843374 | 843374 | A12 | Increased funds from $1,486,747
419 | 1700638 | MC Transit | FTA Transfer | Local Transit Projects | Bike Racks for Buses | Michigan City | LaPorte |  |  | STP transfer | 2018 | Capital Equipment | 43750 | 35000 | 8750
420 | 1700639 | TransPorte, City of La Porte | FTA | Local Transit Projects | Operating Assistance | LaPorte (City) | LaPorte |  |  | FTA 5307 Mich City UA | 2018 | OA | 541374 | 270687 | 270687
421 | 1700640 | TransPorte, City of La Porte | FTA | Local Transit Projects | Operating Assistance | LaPorte (City) | LaPorte |  |  | FTA 5307 Mich City UA | 2019 | OA | 552200 | 276100 | 276100
422 | 1700641 | TransPorte, City of La Porte | FTA Transfer | Local Transit Projects | Revenue Vehicle Replacement (2) | LaPorte (City) | LaPorte |  |  | FHWA STBG | 2018 | Capital Equipment | 176000 | 140800 | 35200
214 | 1700642 | TransPorte, City of La Porte | FTA Transfer | Local Transit Projects | Revenue Vehicle Replacement (2) | LaPorte (City) | LaPorte |  |  | FHWA STBG | 2019 | Capital Equipment | 176000 | 140800 | 35200
| Subtotal Public Transit Projects: | [11 empty] | 1230065591.8106 | 613729865.8255 | 616335725.9851
[12 empty] | Listings | All Funds | Federal | Non-Federal
[11 empty] | INDOT | 340 | 466795989 | 374401275 | 92394714
[11 empty] | LPA Hwys | 130 | 372344028.6733 | 278741447.548 | 93602581.1253
[11 empty] | NPS | 2 | 2200000 | 2200000 | 0
[11 empty] | Transit | 211 | 1230065591.8106 | 613729865.8255 | 616335725.9851
[11 empty] | Total | 683 | 2071405609.484 | 1269072588.3735 | 802333021.1105