## Slide 1: ESSA Update

## Slide 2: Requirements
Community Meetings
Technical Working Groups
Timeline

## Slide 3: Community Meetings
9 Community Meetings in March and April
Over 350 teachers, administrators, parents and community leaders participated in our community meetings
Feedback is being analyzed, and will be compiled into a report that will feed into the writing of our state ESSA plan

## Slide 4: Technical Working Groups
Made up of parents, teachers, administrators, state board members, field experts, state board staff and advocates
Four total meetings to advise ESSA plan writing
DOE Working Group Leads:
  Accountability – Maggie Paino
  Supporting Excellent Educators – Scott Syverson
  Supporting All Students – Nathan Williamson
  Assessment – Charity Flores

## Slide 5: Timeline
Phases | Notes | Dates
Internal Planning |  | January-March 1
Stakeholder Engagement | Community Meetings Technical Working Groups | March 1 – April 30
Writing the Plan | Technical Working Groups Internal and External support | May 1 – June 30
First Draft | Present First Draft for Public Comment Formally Present ESSA Plan to State Board on July 12 | July 1 – August 1
Submit Plan to Governor | Must be 30 days before plan is due | August 15
Submit final ESSA plan to USDOE |  | September 18